File No.: VIS (2021-22)-PL1046-886-1162	       	               Dated: 15.03.2021

4TH PROJECT LIE REPORT

(FOR THE PERIOD 1ST OCT. 2021 – 31TH DEC. 2021)

OF

IT CAMPUS PROJECT

“DIGITAL PARK”

SITUATED AT

PLOT NO. B-9, SECTOR-132, NOIDA, GAUTAM BUDDHA NAGAR,

UTTAR PRADESH

PROMOTER/S

M/S. MACONNS INFRA PRIVATE LIMITED (MIPL)

REPORT PREPARED FOR

STATE BANK OF INDIA, COMMERCIAL BRANCH, PUSA ROAD,

KAROL BAGH, NEW DELHI

**Important - In case of any query/ issue or escalation you may please contact Incident Manager

at le@rkassociates.org. We will appreciate your feedback in order to improve our services.

NOTE: As per IBA Guidelines please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct

| TABLE OF CONTENTS |  |  |
| --- | --- | --- |
| S.NO. | DESCRIPTION | PAGE NO. |
| PART A | Report Summary | 03 |
| PART B | Introduction | 05 |
|  | - The Project | 05 |
|  | - About the Company | 05 |
|  | - Location of the Project | 06 |
|  | - Project Overview | 10 |
|  | - Scope of the Report | 14 |
|  | - Purpose of the Report | 14 |
|  | - Methodology Adopted | 14 |
| PART C | Plant Infrastructure Sections & Facility Details | 15 |
|  | - Land Details | 15 |
|  | - Project Infrastructure Details | 16 |
| PART D | Project Consultants, Contractors & Suppliers | 20 |
|  | - Confirmed Contractors | 20 |
| PART E | Project Cost and Means of Finance | 22 |
|  | - Total Project Cost | 22 |
|  | - Current Status and Total Expenditure Incurred Till Date | 23 |
|  | - Sources of Finance & Utilization of Funds | 25 |
| PART F | Statutory & Regulatory Approvals, Clearances & NOC | 26 |
| PART G | Project Schedule & Current Status | 28 |
|  | - Project Schedule Chart | 28 |
| PART H | Observations and Comments | 33 |
| PART I | Disclaimer | 35 |

# IMPORTANT NOTICE

COPYRIGHT FORMAT: This report is prepared on the copyright format of R.K Associates, to serve our clients with the best available information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format by any organization or individual other than R.K Associates will be seen as unlawful act and necessary legal action can be taken against the defaulters.

This report is intended for the sole use of the intended recipient/s and contain material that is STRICTLY CONFIDENTIAL AND PRIVATE.

DEFECT LIABILITY PERIOD: - In case of any query/ issue or escalation you may please contact Incident Manager: @ le@rkassociates.org. We try our level best to ensure correctness in the calculations done, rates adopted and various other data points & information mentioned in the report but still can’t rule out typing, human errors or any other mistakes. In case you find any such mistake or inaccuracy in any data point of the report please help us by bringing all such points into our notice immediately or within 15 days of the report delivery in writing, to rectify these timely failing after which R.K Associates won’t be held responsible for any such inaccuracy in any manner. We would highly appreciate your feedback in order to improve our services.

| PART A | REPORT SUMMARY |
| --- | --- |

- Name of the Project		:	IT Campus Project

- Project Location		:        	Plot No. B-9, Sector-132, Noida, Gautam Buddha Nagar, Uttar Pradesh

- Name of the Promoters		: 	M/s. Maconns Infra Pvt. Ltd. (MIPL)

- Address and Phone Number	:     	M/s. Maconns Infra Pvt. Ltd. (MIPL)

Corporate Office: C-129, Block-C,

Sector-2, Noida, Uttar Pradesh

- Prepared for Bank			:	State Bank of India, Commercial

Branch, Pusa Road, Karol Bagh, New

Delhi, India

- Date of Survey			:   	8th Day of March, 2022

- Date of Report			:   	15th Day of March, 2021

- Report type			:   	Project LIE Report

- Purpose of the Report		:   	Review & evaluate Project Progress,

capital expenditure & other execution

details of the Project to facilitate

creditors for taking business decision

- Scope of the Report		:         To assess, evaluate & comment on

reasonableness & sufficiency of:

- Project expenditures

- Project physical progress

- Project schedules

- Statutory Approvals, Licenses &

Registrations

- Documents produced for perusal	:	1. CA Certificate

2. PO/ PI/ Invoices

3. Account Ledger

- Annexure with the Report		:	1. Site Photographs

2. PO/ PI/ Invoices

3. Account Ledger

4. CA Certificate

| PART B | INTRODUCTION |
| --- | --- |

- THE PROJECT: Maconns Infra Private Limited (MIPL) has proposed to develop an IT Campus Project named ‘Digital Park’ accommodating Office space saleable area approx. 8,37,455 sq. ft. and retail saleable area approx. 1,00,000 sq.ft. spread over a land area measuring 20,000 sq. mtr. at Plot No. B-09, Sector-132, Noida, Gautam Buddha Nagar, Uttar Pradesh.

MIPL has signed the Memorandum of Agreement (MOA) with M/s. Steria India Ltd. for the lease of office spaces in 3 phases as per their required specifications.

- ABOUT THE COMPANY: Maconns Infra Pvt. Ltd., a company incorporated under Companies Act, 1956 in October, 2007 and is categorised as Company limited by Shares and a Non-govt company.

Their main promoter Mr. Rajesh Manocha, 57 years old is an engineer having 35 years of experience in the real estate industry. He has executed more than 90 projects, ranging from 18,000 sq.ft. to 2.5 lakh sq.ft. across sphere of Residential, Commercial, Office, IT/ITES, and Industrial. The first project was under taken 28 years back. Some are occupied by and sold to renowned personalities like ITC, DS Group, Altron Technologies, Contata Solutions, Kapil Dev Group, Prismart, CRC, Inficare technologies, Samco, IDC Technologies, BBF Industries Ltd., Seismic Solutions, Sensorise, etc.

The group works on Built-to-suit development on SPV model. There is no registered group as such.

Currently company is only executing Built-to-suit Project for Sopra Steria at B-9 Sector 132, NOIDA. There is no other project, company is handling currently.

- LOCATION: The Project is strategically located in Sector-132 Noida which has become an important Institutional/Office hub of Noida. Noida is attracting considerable office employment. Since the office space has become increasingly scarce in Delhi, many businessmen, even though residents of Delhi, are setting-up offices in Noida because, here, the rents are still in the affordable range. The employees in these offices are thus finding it more convenient to live in Noida. In the next stage it is expected that the businessmen themselves will also plan shift to Noida. Policies of the Noida Authority during last few years have been conducive for the development of office spaces at various places in Noida. NOIDA has developed sector 62, 125, 126, 127, 132, 135, 136, 142,143, 144, 153, 154, etc., where Institutional and other office facilities will house large number of offices and employment opportunities. In addition to this, Noida is also a convenient place to live for people who, though employed in Delhi, have bought or rented accommodation here because of relatively affordable rates. Due to the above factors, and also considering the fact that the level of facilities in Noida and transport linkages with Delhi are bound to increase in the short run, the rate of growth of population is also likely to accelerate in the future. Details of the availability of public transport from this Project is mentioned as under:

ROAD:

Gautam Buddha Nagar District (entailing Noida and Greater Noida) is well connected to New Delhi and other cities of NCR. Expressways like the eight-lane DND flyover with Toll Bridge and the Noida-Greater Noida Expressway provide excellent linkages of Noida to New Delhi and Greater Noida respectively.

The Dadri-Surajpur-Chalera (DSC) road connects Noida with Sikanderabad and Dadri. The Mathura Road or NH-19 connects the city with Faridabad and other cities located towards the south and south-west. The NH-24 by-pass facilitates access to Ghaziabad, New Delhi and other parts of North India. Further, the Kondli Road running through Sector VIII and Sector IX serves to link Noida with eastern Delhi and Ghaziabad. The Eastern/ FNG Expressway (Faridabad-Noida-Ghaziabad) which was a proposed six lane expressway is under different phases of construction. State Road Transport bus services play throughout the township and provide regular and frequent connectivity to city residents and others, to and fro from Noida, Delhi, Ghaziabad and other major cities of Uttar Pradesh.

RAIL:

Both Noida and Greater Noida lie closest to Hazrat Nizamuddin Railway Station in Delhi, at a distance of approx. 10 km and 40 km respectively. However, the nearest railway station at present is Dadri to both, located just outside the notified area on the main railway line but it is not a prominent boarding line. The rail link from Tughlakabad to Dadri and Boraki via Noida is planned, which will link the area to the western railway main line to Mumbai.

AIR:

The nearest International Airport is the Indira Gandhi International Airport, located at a distance of 35 Km from Noida and 65 kms from Greater Noida. On 24th June 2017, Ministry of Civil Aviation has granted in principle approval for development of Greenfield International Airport near Jewar. The proposed Airport is likely to cater to 30-50 million passengers per year over the next 10-15 years. The area notified for Greenfield Airport is 3,000 hectares. The first phase will be developed in 1,000 hectares. YEIDA (Yamuna Expressway Industrial Development Authority) is also planning to set up a civil aircraft maintenance, repair and overhaul (MRO) near proposed airport.

METRO:

The nearest Metro Station to this Project will be Sector-137, Noida. Noida is well connected to Delhi by blue line & magenta line of Delhi Metro. Currently both the lines are operational, blue line connectivity is up to Noida Electronic City and have metro stations at Noida Sector 15, Noida Sector 16, Noida Sector 18, Botanical Garden, Golf Course, Noida City Centre, Sector 34, Sector 52, Sector 61, Sector 59, Sector 62 and Noida Electronic City in Noida. While Magenta line connectivity is upto Botanical Garden having 2 Metro Stations at Okhla Bird Sanctuary and Botanical Garden Metro Station in Noida.

The Aqua Line is a line of Noida Metro, a rapid transit system in Noida, India. It consists of 21 metro stations from Sector 52 in Noida to Depot metro station in Greater Noida. The line has been operational between Sector 51 in Noida to Depot metro stations in Greater Noida since 25 January 2019. The 29.7 kilometre (18.5 mi) Aqua Line has 21 stations. The line starts from Noida Sector 51 metro station and will run through sectors 51, 50, 76, 101, 81, NSEZ, 83, 137, 142, 143, 144, 145, 146, 147 and 148 in Noida; after this it will enter Greater Noida and will go through Knowledge Park-II, Pari Chowk, Alpha-1, Delta-1 and GNIDA Office before terminating in Depot Station.

| AMENITIES |  |
| --- | --- |
| 🚍 | Jaypee Bus Stop [01 km] |
| 🚉 | Hazrat Nizamuddin Junction [10 Kms] |
| 🛪 | IGI Airport (New Delhi) [35 Kms] |
| 🚇 | Noida Sector 137 Metro [04 Kms] |
| 🚑 ¦ 🛒 | Basis amenities located within 500 mtr range |

Source:https://www.google.com/maps/place/28%C2%B030'44.8%22N+77%C2%B022'20.4%22E/@28.5123734,77.3713726,18.24z/data=!4m5!3m4!1s0x0:0x0!8m2!3d28.5124444!4d77.3723333

- PROJECT OVERVIEW: Maconns Infra Private Limited (MIPL) is a non-govt. company incorporated on 19th Oct., 2007. MIPL has proposed to develop an IT Campus Project named ‘Digital Park’ accommodating Office space having approx. saleable area measuring 8,37,455 sq.ft. and retail saleable area approx. 1,00,000 sq.ft. spread over a land area measuring 20,000 sq. mtr. at Plot No. B-09, Sector-132, Noida, Gautam Buddha Nagar, Uttar Pradesh.

In November, 2018, MIPL has signed the Memorandum of Agreement (MOA) with M/s. Steria (India) Ltd. for the lease of office spaces in 3 phases as per their required specifications.

Main extracts & highlights of the Agreement signed between M/s. Maconns Infra Pvt. Ltd. (MIPL) & M/s. Steria (India) Ltd. are herewith mentioned below:

Total proposed project cost has been estimated at Rs.357.29 cr., which is proposed to be funded with a debt-equity ratio of 56:44, i.e. debt of Rs.200.00 cr. and equity of Rs.157.29 cr. Debt requirement of the Project is proposed to be financed through Term Loan (TL) from State Bank of India which has shown interest to process the debt amount of Rs.200.00 cr.

As per the records provided by the company the total amount incurred till date is Approx. Rs.110 Crore.

Company has obtained all the required preliminary, statutory approvals & clearances (Pollution NOC, Letter of Comfort, Environment clearance, Provisional Firefighting NOC, Consent to Establishment, Height Clearances, Mining Permission, and Structural Stability Certificate etc.).

For the Land, MIPL has already acquired the land measuring 20,000 sq.mtr. From Noida Authority on long term lease for the period of 90 years in Sector-132, Noida, Gautam Buddha Nagar.

For the construction purpose, MIPL has signed a Construction Agreement with M/s. Hi-Tech competent Builders Pvt. Ltd. on 28.02.2020 to construct proposed IT Campus Project having total Built-up area 11,92,945 sq. ft. comprising of 2 High rise Towers.

As per the current status on the site, site development and Excavation work has been already completed. M/s. S.B. Construction was engaged for Excavation work at site.

The company has assigned some new contractors/consultant as follows:

- IPDM Services (India) Pvt. Ltd. – Consultant for Landscape Planners and architect

- Ingenious Work Solutions– for the HVAC Work

- Dova Infracon Private Limited- For Fire and Plumbing Work

- Zephyrs Cooling Solutions- For Mechanical Ventilation

- Tomar Electricals Service- For Raceway Installation Work

- Sant Electricals- High Side electric work

The contractors/consultant assigned in the previous quarter is as follows:

- KSP Hydro Engineers Pvt. Ltd. – For STP Work

- Uri Design Studio – Lightning Consultants

- TK Elevator India Pvt. Ltd. – Elevator Contractor

- Mitsubishi Elevator India Pvt. Ltd. – Elevators Contractor

Currently the superstructure of Tower B is completely which is constructed with 2 Basement + G + 10 Floors. Currently the Interior work for the office floor’s i.e., 3rd to 10th floors is on Progress and Construction of Tower A was also in execution as observed during the site visit. The material for glazing work is lying at site and is erected for the office floors.

- SCOPE OF THE REPORT: To review & scrutinize following below points:

- Review current status of the Project on site

- Review capital expenditure incurred on site including preliminary and preparative expenses.

- Review position of various statutory, non-statutory clearances and regulatory clearances obtained by the company.

- To check the status of physical progress of the Project.

- Review the construction schedule of the project and advice on the scheduled COD of the project, whether same is achievable by the company or not.

- Advise Lender’s on any other issue/ constraints in the project which may affect its progress.

- PURPOSE OF THE REPORT: To provide fair detailed analysis report to the Bank based on the “in-scope points” mentioned above subject to the details/ data/ information provided by the client for facilitating Bank to take appropriate decision on providing credit facility to the Project.

- METHODOLOGY ADOPTED:

- Site Survey.

- Review & analysis of the Project initiation, planning, contract agreements, statutory regulatory approval documents and other data, information provided by the MIPL.

- Preparation of the Report based on “in scope points”.

- Approval of the Report.

- Report submission.

| PART C | PLANT INFRASTRUCTURE SECTIONS & FACILITY DETAILS |
| --- | --- |

- LAND DETAILS: MIPL has already acquired the land measuring 20,000 sq.mtr. from M/s. Living Media (India) Pvt. Ltd. through Transfer Deed cum Sale Deed on long term lease for the period of 90 years in Sector-132, Noida, Gautam Buddha Nagar in the year 2013.

{Table: 1}

| PARTICULARS | DETAILS |
| --- | --- |
| Total Land Area | 20,000 m2 |
| Location | - Plot No. B-9, Sector - 132, Noida, Gautam Buddha Nagar, Uttar Pradesh |
| Boundaries | - North : Plot No. B-8 & B-25 - South : 24 mtr. wide Road - East : 24 mtr. wide Road - West : 45 mtr. wide Road |

- PROJECT INFRASTRUCTURE DETAILS: Maconns Infra Pvt. Ltd. (MIPL) has proposed to set-up an IT Campus Project named ‘Digital Park’ accommodating Office space having approx. saleable area measuring 8,37,455 sq.ft. and retail saleable area approx. 1,00,000 sq. ft. spread over a land area measuring 20,000 sq. mtr. at Plot No. B-09, Sector-132, Noida, Gautam Buddha Nagar, Uttar Pradesh.

This is a Built to Suit IT/ITES Project comprising of 2 high rise towers (3B+G+19) & (3B+G+10) having total Built-up area Approx. 13,11,000 sq.ft. This Project would be based on Modern Advanced IBMS System (Intelligence Building Management System) which is known as a building automation system (BAS), is a computer-based control system installed in buildings that controls and monitors the building's mechanical and electrical equipment such as ventilation, lighting, power systems, fire systems, and security systems. Apart from this there are total 6 Entries & Exits and 4 Ramps proposed.

For the purpose of the development of the Project, MIPL has engaged 2 main Architect M/s. Design Forum of Architects (DFA) for external Design Services & M/s. Adrianse Group for Interior Design Services and M/s. NNC Design International Consulting Structural Engineers as a Structural Design Services & Supervision. Some other consultants are also engaged for different Consultancy Services.	MIPL has engaged M/s. High-Tech Competent Builders Pvt. Ltd. for Building / Structural construction work as per below mentioned Terms & Conditions.

As per the proposed plan following blocks & sections are proposed to be built:

{Table: 2}

| PART D | PROJECT CONSULTANTS, CONTRACTORS & SUPPLIERS |
| --- | --- |

- Confirmed Contractors: Following below consultants, contractors & suppliers have been engaged/ confirmed for different activities of the Project initiation and implementation activities:

{Table: 3}

Apart from these above-mentioned contractors the company has signed some other contract in this Quarter:

Apart from these the company has issued some LOI in this Quarter as mentioned below:

- Contract value is considered as per the contract agreement between the company and the contractor provided to us.

- The amount incurred till date for the installation of lifts are considered as per the ledger and disbursement and fund utilisation sheet provided to us by the client.

| PART E | PROJECT COST & MEANS OF FINANCE |
| --- | --- |

- TOTAL PROJECT COST: As per the Bank Loan Sanctioned Letter, MIPL has estimated the total Project Cost is Rs.357.29 cr. in which Rs.56.14 cr. is for Land & Land Development Cost and Rs.266.54.00 cr. for the Construction Cost.

{Table: 5}

| Sr. No. | Particulars | Amount (In Cr.) |
| --- | --- | --- |
| 1. | Land & Land Development Cost | 56.14 |
| 2. | Cost of Construction | 266.54 |
|  | Hard Cost | 322.68 |
| 3. | Contingency (3%) | 8.00 |
| 4. | Interest During Construction | 26.61 |
|  | Soft Cost | 34.61 |
|  | Total Project Cost | 357.29 |
| Source: Bank Loan Sanctioned Letter |  |  |
| Observations & Comments: - The basis of the above estimated cost is as per the estimates provided by the MIPL. - Detailed estimate for quantity of material required is not obtained by MIPL. - This is a Built to Suit IT/ITES Project and hard cost includes complete interiors, finishing, furnishing, furniture and fittings & fixtures of Phase-I are admeasuring 6,29,000 sq.ft. |  |  |

- CURRENT STATUS & TOTAL EXPENDITURE INCURRED TILL DATE: Details of the expenditure in the Table below is recorded for the expenditure incurred up to 31th December, 2021 only.

{Table: 6}

| SR. NO. | PARTICULARS | TOTAL ESTIMATED COST | INCURRED TILL 31th DECEMBER 2021 | CURRENT STATUS OF WORK AND REMARKS |
| --- | --- | --- | --- | --- |
|  |  | (All figures in cr.) |  |  |
| - 1. | Land & Land Development | Allocated Amount | 56.14 | Total Project Expenditure against Plot Cost shown by the MIPL is Rs.50.33 cr. Up to 31st December 2021 as per the below breakup: - Lease Extension charges of amount Rs.3.94 cr. - Interest against Plot Loan of amount Rs.2.63 cr. are included. - Rs.0.09 cr. has been paid for the Land Development Cost - No other cost has been incurred from the period of Dec., 2019 to December, 2021. |
|  |  | Expenses incurred up to last LIE report | 50.33 |  |
|  |  | Incurred up to period ending 31st December, 2021 | 50.33 |  |
| - 2. | Building & Civil Construction | Allocated Amount | 266.54 | Based on physical progress observed during site visit and information provided by the company, they have constructed approximately 3,13,240 Sq. ft. area. Thus assuming construction rate of approx. Rs.1,850/- per sq. ft. the total expenditure on construction comes out to approximately Rs.58 Crore which seems reasonable in our view For construction of such high end commercial places. |
|  |  | Expenses incurred up to last LIE report | 51.57 |  |
|  |  | Incurred up to period ending 31st December, 2021 | 58.00 |  |
| - 3. | Contingency | Allocated Amount | 8.00 | No cost incurred under this head up to 31th Dec., 2021. |
|  |  | Expenses incurred up to last LIE report | 0.00 |  |
|  |  | Incurred up to period ending 31st December, 2021 | 0.00 |  |
| - 4. | Interest During Construction | Allocated Amount | 26.61 | We have relied on CA certificate and other information provided by the company For interest cost paid during construction. |
|  |  | Expenses incurred up to last LIE report | 1.20 |  |
|  |  | Incurred up to period ending 31st December, 2021 | 2.11 |  |
| 5. | Total | Allocated Amount | 357.29 | Based on physical progress observed during site visit, copies of invoices provided by the company and other information received we are of the view that the company has made an expenditure amounting to approx. Rs.110 Crore as against 109.73 Crore certified by M. B. Gupta and Co. chartered accountant vide CA certificate dated 22nd January 2022 with UDIN. 22525377AAAA52847. |
|  |  | Expenses incurred up to last LIE report | 103.10 |  |
|  |  | Incurred up to period ending 31st December, 2021 | 110.38 |  |
| Notes: - Expenses which were redundant and has been incurred multiple time on the same item and has remain unutilised because of project execution delay has not been approved. - All amount considered is based on the break-up of expenditure, copy of bills, accounts ledgres provided to us. - Amount has been checked based on cost analysis and not based on accounting principles. - Amount checked is based on macro analysis as a whole and not based on item wise bills of wuantity or micro basis and is non investigative in nature. |  |  |  |  |

Comments:

The Company has provided the cost sheet of the total envisaged construction expenses in the project. As per the said sheet the company has proposed to spend approximately 276 Crore, out of which contracts worth Rs.71.60 Crore has already been given. The cost sheet is as attached below:

SOURCES OF FINANCE & UTILIZATION OF FUNDS: The Project cost mentioned above has been planned to be covered from following resources:

{Table: 7}

| PARTICULARS | PLANNED AMOUNT | CURRENT STATE OF INVESTMENT | BALANCE |
| --- | --- | --- | --- |
|  | (Amount in Cr.) |  |  |
| Promoter’s Equity | 157.29 | 77.05 | 80.24 |
| Term Loan from Bank | 200.00 | 37.45 | 162.55 |
| TOTAL | 357.29 | 114.5 | 242.79 |

Source: As per Bank Loan Sanctioned Letter.

{Figure: 3}

Comments:

As per the CA certificate dated 22nd January 2022 with UDIN. 22525377AAAA52847, the company has made an expenditure amounting to approx. Rs.110 Crore on the project up to 31st December 2021. However as per means of finance dated 22nd January 2022 with UDIN. 22525377AAAAAT2339 the company has infused approx. Rs.114 Crore till 31st December 2021. Details of balance infusion is not provided to us.

| PART F | STATUTORY & REGULATORY APPROVALS, CLEARANCES & NOC |
| --- | --- |

{Table: 8}

| Sr. No. | NAME OF LICENSE/ REGISTRATION | PURPOSE | DATE OF ISSUE | Current Status |
| --- | --- | --- | --- | --- |
|  | ISSUING AUTHORITY |  | LICENCE NO. |  |
| 1. | NOC for Pollution for Non-Abnoxius and Non-Hazardous Industry | Pollution | 17.09.2018 | Obtained |
|  | Office of the Deputy Commissioner Industries, Gautam Buddha Nagar, Uttar Pradesh |  | 1660 D.I.C./ G.B.N.(U.P.) POLL. NOC/ 2018-19 |  |
| 2. | Letter of Comfort | For Industry Set-up | 17.09.2018 | Obtained |
|  | Office of the Deputy Commissioner Industries, Gautam Buddha Nagar, Uttar Pradesh |  | 1660/DIEPC/GBN/2017-18 |  |
| 3. | Provisional Fire NOC | Firefighting | 08.12.2018 | Obtained |
|  | Office of the Deputy Director, Fire Services, Meerut/ Saharanpur, Uttar Pradesh |  | 842/DD/FS/Meerut-18(2)/1460 |  |
| 4. | Building Plan Approval | Building Plan Sanctioned | 18.01.2019 | Obtained |
|  | Noida Authority, Noida, Gautam Buddha Nagar, Uttar Pradesh |  | Noida/MVN/2019/V-819/400 |  |
| 5. | Environment Clearance | Environment | 10.05.2019 | Obtained |
|  | State Level Environment Impact Assessment Authority, Uttar Pradesh |  | 32/Praya/SEAC/4504/2019 |  |
| 6. | Consent to Establish | Waste Water Discharge | 01.07.2019 | Obtained |
|  | Uttar Pradesh Pollution Control Board |  | 50001/UPPCB/Noida(UPPCBRO)/ CTE/NOIDA/2019 |  |
| 7. | NOC for Height Clearances | Height Clearances | 01.07.2019 | Obtained |
|  | Airports Authority of India |  | AAI/RHQ/NR/ATM/NOC/ REVALIDATION/2014/251/ 1101-1105 |  |
| 8. | Structural Stability Certificate | Structural Stability | 13.11.2018 | Obtained |
|  | Jamia Millia Islamia, New Delhi |  | 2018/2580 |  |
| 8. | Structural Stability Certificate | Structural Stability | 22.10.2019 | Obtained |
|  | Indian Institute of Technology, Delhi |  | IITD/IRD/CWG/AKJAIN-27 |  |
| 9. | Permission for Mining | Mining Permission | 31.05.2019 | Obtained |
|  | Office of the District Magistrate, Gautam Buddha Nagar, Uttar Pradesh |  | 89/Kh. Anu./2019-20 |  |
| 10. | No dues Certificate | No Dues Certificate | 09.08.2018 | Obtained |
|  | Noida Authority, Noida, Gautam Buddha Nagar, Uttar Pradesh |  | Noida/2018/1653 |  |
| Observations & Comments: - MIPL has obtained all the required Preliminary & Statutory Approvals from different Government Agencies. |  |  |  |  |

| PART G | PROJECT SCHEDULE & CURRENT STATUS |
| --- | --- |

- PROJECT SCHEDULE CHART: Project schedule is summarized in the below chart mentioning the important activities and milestones. This has been consolidated based on the current actual status of the various activities and rational projections for their completion time, considering the practical site conditions and what has been enumerated as time line in various contracts.

{Table: 9}

| S. No. | ACTIVITIES |  | PLANNED COMMENCEMENT | PLANNED COMPLETION | CURRENT STATUS |
| --- | --- | --- | --- | --- | --- |
|  | Land Acquisition & Development |  | Completed | Completed | Completed |
|  | Site excavation |  | 1st Feb., 2020 | 15th Nov., 2021 | Completed |
|  | Building Construction |  |  |  |  |
|  | Structure Work | Tower B & Retail Area | 1st Sep., 2020 | 7th Sep., 2021 | Superstructure of the Tower is completed having Basement 1 + Basement 2 + G + 10 floors. Retail/commercial floors are also complete |
|  |  | Tower A | 1st April, 2021 | 9th Oct., 2022 | Foundation work is completed, roof of basement 1 & 2 is partially laid and construction work is in progress. |
|  | Façade works | Tower B & Retail Area | 4th July, 2021 | 1st Dec., 2021 | Aluminum material and DGU for frame work of glazing is available at site. Glazing work for the office space i.e., 3rd to 10th floor of Tower-B is complete from three sides and is partially done for three floors for the fourth side. |
|  |  | Tower A | 23rd March, 2022 | 17th Jan., 2023 | Not yet started |
|  | Electrical, Fire Alarm & Low Voltage Works | Tower B & Retail Area | 15th May, 2021 | 9th June, 2022 | Not yet started |
|  |  | Tower A | 26th Oct., 2021 | 19th Jan., 2023 | Not yet started |
|  | HVAC Works | Tower B & Retail Area | 15th May, 2021 | 9th June, 2022 | Not yet started |
|  |  | Tower A | 26th Oct., 2021 | 19th Jan., 2023 | Not yet started |
|  | DG, Lift, UPS, STP, HSD & Other Equipment Works | Tower B & Retail Area | 15th May, 2021 | 9th July, 2022 | Work in Progress for 4 lifts in the Tower-B |
|  | PHE Works | Tower B & Retail Area | 25th April, 2021 | 20th May, 2022 | Not yet started |
|  |  | Tower A | 26th Oct., 2021 | 19th Jan., 2023 | Not yet started |
|  | BMS, CCTV & PA, Security system Works | Tower B & Retail Area | 4th July, 2021 | 30th Jan., 2022 | Not yet started |
|  |  | Tower A | 24th Jan., 2022 | 19th Jan., 2023 | Not yet started |
|  | Interior & Finishing works | Tower B & Retail Area | 15th May, 2021 | 9th June, 2022 | Plaster work, and Raceway’s installation for the Tower-B office units i.e. 3rd to 10th floor is complete and screeding is completed for 3rd to 9th floor, trimix at the basement level of tower-B is in progress. Water poofing in the toilet and AHU rooms is complete for office Floors |
|  |  | Tower A | 26th Oct., 2021 | 19th Jan., 2023 | Not yet started |
|  | External development, Landscaping & other beautification works | Tower B & Retail Area | 7th Sep., 2021 | 5th Jan., 2022 | Not yet started |
|  |  | Tower A | 21st July, 2022 | 17th Jan., 2023 | Not yet started |
|  | Handing Over & Rectification of Snags for Tower B & Retail |  | 9th July, 2022 | 23rd Aug., 2022 | Not yet started |
|  | Handing Over & Rectification of Snags for Tower A |  | 3rd Jan., 2023 | 14th Feb., 2023 | Not yet started |
| OBSERVATIONS: - Based on physical progress observed during site visit, the project seems to be delayed by about 4 months for Tower B and about 1 year for Tower A since construction works of Tower A are yet to be started. The company is advised to seek timeline extension from the lender. |  |  |  |  |  |

{Table: 10}

| PART H | OBSERVATIONS & COMMENTS |
| --- | --- |

- Based on physical progress observed during site visit, copies of invoices provided by the company and other information received we are of the view that the company has made an expenditure amounting to approx. Rs.110 Crore as against 109.73 Crore  certified by M. B. Gupta and Co. chartered accountant vide CA certificate dated 22nd January 2022 with UDIN. 22525377AAAA52847.

- The Company has provided the cost sheet of the total envisaged construction expenses in the project. As per the said sheet the company has proposed to spend approximately 276 Crore, out of which contracts worth Rs.71.60 Crore has already been given.

- As per the CA certificate dated 22nd January 2022 with UDIN. 22525377AAAA52847, the company has made an expenditure amounting to approx. Rs.110 Crore on the project up to 31st December 2021. However as per means of finance dated 22nd January 2022 with UDIN. 22525377AAAAAT2339 the company has infused approx. Rs.114 Crore till 31st December 2021. Details of balance infusion is not provided to us.

- The company has assigned some new contractors/Consultants during the quarter as follows:

-Dova Infracon Private Limited- Fire and Plumbing Contractor

-Mindstudio Private Limited- Consultant for interior work

-Ingenious work solution- HVAC contractor

-Zephyrs Cooling Solutions- Mechanical Ventilation Contractor

- As per the current status of the site, the superstructure of Tower B is completed and foundation works for Tower A are under progress. Glazing works have started in Tower B.  During visit no construction works were being carried out because of NGT ban imposed by the government to tackle rising pollution.

- Based on physical progress observed during site visit, the project seems to be delayed by about 4 months for Tower B and about 1 year for Tower A since construction works of Tower A are yet to be started. The company is advised to seek timeline extension from the lender.

| PART I | DISCLAIMER |
| --- | --- |

      - No employee or member of R.K Associates has any direct/ indirect interest in the Project.

      - This report is prepared based on the copies of the documents/ information which the Bank/ Company has provided to us out of the standard checklist of documents sought from them and further based on our assumptions and limiting conditions. The client/owner and its management/representatives warranted to us that the information they supplied was complete, accurate and true and correct to the best of their knowledge. All such information provided to us has been relied upon in good faith and we have assumed that it is true and correct in all respect. I/We shall not be liable for any loss, damages, cost or expenses arising from fraudulent acts, misrepresentations, or wilful default on part of the owner, company, its directors, employee, representative or agents. Verification or cross checking of the documents provided to us from the originals or from any Govt. departments/ Record of Registrar has not been done at our end since this is beyond the scope of our work. If at any time in future, it is found or came to our knowledge that misrepresentation of facts or incomplete or distorted information has been provided to us then this report shall automatically become null & void.

      - Legal aspects for eg. investigation of title, ownership rights, lien, charge, mortgage, lease, sanctioned maps, verification of documents, etc. have not been done at our end and same has to be taken care by legal expert/ Advocate. It is assumed that the concerned Lender/ Financial Institution has satisfied them with the authenticity of the documents, information given to us and for which the legal verification has been already taken and cleared by the competent Advocate before requesting for this report. I/ We assume no responsibility for the legal matters including, but not limited to, legal or title concerns.

      - This report is a general analysis of the project based on the scope mentioned in the report. This is not an Audit report, Design document, DPR or Techno feasibility study. All the information gathered is based on the facts seen on the site during survey, verbal discussion & documentary evidence provided by the client and is believed that information given by the company is true best of their knowledge.

      - All observations mentioned in the report is only based on the visual observation and the documents/ data/ information provided by the client. No mechanical/ technical tests, measurements or any design review have been performed or carried out from our side during Project assessment.

      - Bank/FII should ONLY take this report as an Advisory document from the Financial/ Chartered Engineering firm and its specifically advised to the creditor to cross verify the original documents for the facts mentioned in the report which can be availed from the borrowing company directly.

      - In case of any default in loans or the credit facility extended to the borrowing company, R.K Associates shall not be held responsible for whatsoever reason may be and any request for seeking any explanation from the employee/s of R.K Associates will not be entertained at any instance or situation.

      - The documents, information, data provided to us during the course of this assessment by the client is reviewed only upto the extent required in relation to the scope of the work. No document has been reviewed beyond the scope of the work.

      - This report only contains general assessment & opinion as per the scope of work evaluated as per the information given in the copy of documents, information, data provided to us and/ and confirmed by the owner/ owner representative to us at site which has been relied upon in good faith. It doesn’t contain any other recommendations of any sort including but not limited to express of any opinion on the suitability or otherwise of entering into any transaction with the borrower.

      - We have relied on data from third party, external sources & information available on public domain also to conclude this report. These sources are believed to be reliable and therefore, we assume no liability for the truth or accuracy of any data, opinions or estimates furnished by others that have been used in this analysis. Where we have relied on data, opinions or estimates from external sources, reasonable care has been taken to ensure that such data has been correctly extracted from those sources and /or reproduced in its proper form and context, however still we can’t vouch its authenticity, correctness or accuracy.

      - This Report is prepared by our competent technical team which includes Engineers and financial experts & analysts.

      - This is just an opinion report and doesn’t hold any binding on anyone. It is requested from the concerned Financial Institution which is using this report for taking financial decision on the project that they should consider all the different associated relevant & related factors also before taking any business decision based on the content of this report.

      - All Pages of the report including annexures are signed and stamped from our office. In case any paper in the report is without stamp & signature then this should not be considered a valid paper issued from this office.

      - Though adequate care has been taken while preparing this report as per its scope, but still we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it shall be considered that the report is complete in all respect and has been accepted by the client upto their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

      - Defect Liability Period is 15 DAYS. We request the concerned authorized reader of this report to check the contents, data and calculations in the report within this period and intimate us in writing if any corrections are required or in case of any other concern with the contents or opinion mentioned in the report. Corrections only related to typographical, calculation, spelling mistakes, incorrect data/ figures/ statement will be entertained within the defect liability period. Any new changes for any additional information in already approved report will be regarded as additional work for which additional fees may be charged. No request for any illegitimate change in regard to any facts & figures will be entertained.

      - R.K Associates encourages its customers to give feedback or inform concerns over its services through proper channel at valuers@rkassociates.org in writing within 15 days of report delivery. After this period no concern/ complaint/ proceedings in connection with the Financial Feasibility Study Services will be entertained due to possible change in situation and condition of the subject Project.

      - Our Data retention policy is of ONE YEAR. After this period, we remove all the concerned records related to the assignment from our repository. No clarification or query can be answered after this period due to unavailability of the data.

      - This Financial Feasibility Study report is governed by our (1) Internal Policies, Processes & Standard Operating Procedures, (2) Information/ Data/ Inputs given to us by the client and (3) Information/ Data/ Facts given to us by our field/ office technical team. Management of R.K Associates never gives acceptance to any unethical or unprofessional practice which may affect fair, correct & impartial assessment and which is against any prevailing law. In case of any indication of any negligence, default, incorrect, misleading, misrepresentation or distortion of facts in the report then it is the responsibility of the user of this report to immediately or at least within the defect liability period bring all such act into notice of R.K Associates management so that corrective measures can be taken instantly.

      - R.K Associates never releases any report doing alterations or modifications from pen. In case any information/ figure of this report is found altered with pen then this report will automatically become null & void.

Place	:	Noida    					FOR INTERNAL USE

Date	:	15.03.2022					SURVEYED BY:  Er. Abhishek Sharma

Note	:	This report contains 40 pages		PREPARED BY: PE Team

REVIEWED BY: MA

For R.K Associates Valuers & Techno

Engineering Consultants Pvt. Ltd.

- DEFECT LIABILITY PERIOD - In case of any query/ issue or escalation you may please contact Incident Manager by writing at valuers@rkassociates.org. We ensure 100% accuracy in the Calculations done, Rates adopted and various other data points & information mentioned in the report but still can’t rule out typing, human errors or any other mistakes. In case you find any mistake, variation, discrepancy or inaccuracy in any data point of the report, please help us by bringing all such points into our notice in writing at valuers@rkassociates.orgwithin 30 days of the report delivery, to get these rectified timely, failing which R.K Associates Valuers Techno Engineering Consultants (P) Ltd. won’t be held responsible for any inaccuracy in any manner. Also if we will not hear back anything from you within 30 days, we will assume that report is correct in all respect and no further claim of any sort will be entertained thereafter. We would welcome and appreciate your feedback & suggestions in order to improve our services.

COPYRIGHT FORMAT - This report is prepared on the copyright format of R.K Associates Valuers Techno Engineering Consultants (P) Ltd. to serve our clients in the best possible way. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the organization as mentioned on the cover page of this report. Distribution or use of this format other than R.K Associates will be seen as unlawful act and necessary legal action can be taken against the defaulter