## Area Details
Building Details as per Approved Plan |  |  | Building Details as per Agreement
Description | Area (m2) | Area (ft2) | Description | Area (m2) | Area (ft2)
Total Plot Area: | 1158.74 | 12472.5615 | Total Plot Area: | NA | NA
Road widening Area: | 198.38 | 2135.3425 | Road widening Area: | NA | NA
Net Plot Area: | 960.36 | 10337.219 | Net Plot Area: | NA | NA
Covered area of Basement: | 218.25 | 2349.2212 | Covered area of Basement: | 218.1365 | 2348
Covered area of Ground floor: | 283.85 | 3055.333 | Covered area of Ground floor: | 283.7262 | 3054
Covered area of first floor | 283.85 | 3055.333 | Covered area of first floor | 283.7262 | 3054
Covered area of second floor: | 283.85 | 3055.333 | Covered area of second floor: | 283.7262 | 3054
Covered area of Third floor: | 283.85 | 3055.333 | Covered area of Third floor: | 283.7262 | 3054
Total Covered area | 1353.65 | 14570.5532 | Total Covered area | 1353.0412 | 14564
Total Floor Area | 953.73 | 10265.8543 | Total Floor Area | NA | NA
Open Area | 676.51 | 7281.886 | Open Area | NA | NA
Parking Details |  |  | Parking Details
Covered Parking area | 6.31 ECS |  | Covered Parking area | 6.31 ECS
Open Parking area | 1085 ECS |  | Open Parking area | 1085 ECS
Building Details as per Actual Site Drawings
Description | Area (m2) | Area (ft2)
Covered area of Basement: | 773.8831 | 8330
Covered area of Ground floor: | 773.8831 | 8330
Covered area of first floor | 773.8831 | 8330
Covered area of second floor: | 773.8831 | 8330
Covered area of Third floor: | 773.8831 | 8330
Total Covered area | 3869.4154 | 41650

## Agreement Cost est.
CONSTRUCTION COST ASSESSMENT AS PER AGREEMENT
CONSTRUCTION COST ASSESSMENT¦ M/S PRATAP TOWERS PRIVATE LIMITED¦ HALDWANI, DISTRICT NAINITAL, UTTARAKHAND ¦ SITE VISIT DATED MARCH 14, 2022
Sr. No. | Particulars | Estimate | Estimate | Estimate | Progress Observed | Expenses | Remarks
1 | 4 Water Tank | 1459700 | 14.597 | 0.14597 | 0% | 0 | No water tank were found to be constructed during site visit.
2 | 2 Septic tank | 457650 | 4.5765 | 0.045765 | 90% | 0.041189 | 2 septic tanks were under construction stage during site visit.
3 | Foundation + Column Work | 2418829 | 24.1883 | 0.24188 | 80% | 0.19351 | Foundation and column works have been considered only for basement area for half of the columns only reinforcement binding is done and cement concrete works were pending. Foundation works were found to be completed. Percentage progress has been taken accordingly.
4 | Basement walls + ramp | 3571494 | 35.7149 | 0.35715 | 45% | 0.16072 | Ramp work has not yet started. Therefore the progress percentage pertains to only Basement walls. Approximately 45% of the basement walls were completed. For remaining walls reinforcement works were completed but Cement concrete works were pending.
5 | Slab + Beam | 927168 | 9.2717 | 0.092717 | 30% | 0.027815 | Slab + Beam works have been considered for Ground floor only since only one side Ground floor works have completed.
6 | Cement Plaster | 1350960 | 13.5096 | 0.1351 | 0% | 0 | No plaster works is started in the project
7 | Oil bound distempering | 1104150 | 11.0415 | 0.11041 | 0% | 0 | No Oil bound distempering works started in the project.
8 | Electricity and sanitary | 994676 | 9.9468 | 0.099468 | 0% | 0 | No electricity and sanitary works started in the project.
9 | Ground floor | 7428844 | 74.2884 | 0.74288 | 0% | 0 | No description is mentioned in relation to the works that has to be carried out in this item. Therefore no cost has been taken under this head.
10 | Architect fee | 1500000 | 15 | 0.15 | 0% | 0 | No invoice has been given against this item. Therefore no cost has been taken under this head.
11 | Advance to Raw material supplier for next floor | 1800000 | 18 | 0.18 | 0% | 0 | Against the provided bill we do not have any breakup against the adavnce to raw material suppliers for next floor. Therefore no cost has been taken under this head.
12 | First Floor work | 7428844 | 74.2884 | 0.74288 | 0% | 0 | First floor construction works have not been started yet.
13 | Second floor work | 7428844 | 74.2884 | 0.74288 | 0% | 0 | Second floor construction works have not been started yet.
14 | Third Floor work + balance architecture fee | 7128844 | 71.2884 | 0.71288 | 0% | 0 | Third floor construction works have not been started yet.
| Grand Total | 45000003 | 450 | 4.5 | 17.5% | 0.42323 | -
Note: 1. Percentage progress has been done based on Actual physical progress obsereved during site visit considering Stages of construction mentioned in agreement rather than specific measurements, since Detailed BOQ was not provided to us. 2. As per site visit conducted on March 14, 2022, the company has constructed area more than the approved area. Therfore as per our assessment based on actual physical progress observed during site visit and site specific drawings shared by the company, they have incurred approximately Rs.1.30 Crore on the project till the date of site visit.

## Cons. Cost Working
RCC Rates of construction
Total Project Cost (Rs.) | 40005000
METHOD 1 |  |  |  |  | METHOD 1A (Market Rate Analysis)
Particulars | Area | Rate/m2 | Amount |  | Particulars | Area | Rate/m2 | Amount
Basement Construction Area | 773.8831 | 10700 | 8280548.8717 |  | Basement Construction Area | 773.8831 | 13993.07 | 10829000
Ground floor construction area | 173.7289 | 9687.51 | 1683000 |  | Ground floor construction area | 173.7289 | 12916.68 | 2244000
Total |  |  | 9963548.8717 |  | Total |  |  | 13073000
METHOD 2 |  |  |  |  | METHOD 2A (Modifying Method 2)
Particulars | Percetage Allocation | Amount | Site Progress | Cost | Particulars | Percentage Allocation | Amount | Site Progress | Cost
Site work | 6.8% | 2720340 | 95% | 2584323 | Site work | 6.8% | 2720340 | 95% | 2584323
Foundation | 9.5% | 3800475 | 100% | 3800475 | Foundation | 19.5% | 7800975 | 100% | 7800975
Framing | 19.1% | 7640955 |  |  | Framing | 28.1% | 11241405
Ground Floor | - | 1910238.75 | 30.45% | 581648.2071 | Ground Floor | - | 2810351.25 | 30.45% | 855723.2786
First Floor | - | 1910238.75 | 0% | 0 | First Floor | - | 2810351.25 | 0% | 0
Second Floor | - | 1910238.75 | 0% | 0 | Second Floor | - | 2810351.25 | 0% | 0
Third Floor | - | 1910238.75 | 0% | 0 | Third Floor | - | 2810351.25 | 0% | 0
Exterior finishes | 14.4% | 5760720 |  |  | Exterior finishes | 14.4% | 5760720
Ground Floor | - | 1440180 | 0% | 0 | Ground Floor | - | 1440180 | 0% | 0
First Floor | - | 1440180 | 0% | 0 | First Floor | - | 1440180 | 0% | 0
Second Floor | - | 1440180 | 0% | 0 | Second Floor | - | 1440180 | 0% | 0
Third Floor | - | 1440180 | 0% | 0 | Third Floor | - | 1440180 | 0% | 0
Major systems | 13.4% | 5360670 |  |  | Major systems | 13.4% | 5360670
Ground Floor | - | 1340167.5 | 0% | 0 | Ground Floor | - | 1340167.5 | 0% | 0
First Floor | - | 1340167.5 | 0% | 0 | First Floor | - | 1340167.5 | 0% | 0
Second Floor | - | 1340167.5 | 0% | 0 | Second Floor | - | 1340167.5 | 0% | 0
Third Floor | - | 1340167.5 | 0% | 0 | Third Floor | - | 1340167.5 | 0% | 0
Interior finishes | 29.3% | 11721465 |  |  | Interior finishes | 9.3% | 3720465
Ground Floor | - | 2930366.25 | 0% | 0 | Ground Floor | - | 930116.25 | 0% | 0
First Floor | - | 2930366.25 | 0% | 0 | First Floor | - | 930116.25 | 0% | 0
Second Floor | - | 2930366.25 | 0% | 0 | Second Floor | - | 930116.25 | 0% | 0
Third Floor | - | 2930366.25 | 0% | 0 | Third Floor | - | 930116.25 | 0% | 0
Final steps | 6.6% | 2640330 |  |  | Final steps | 2.6% | 1040130 | 0% | 0
Others | 0.9% | 360045 | 12% | 43205.4 | Others | 5.9% | 2360295 | 12% | 283235.4
Total | 100% | 40005000 | 12.5% | 7009651.6071 | Total | 100% | 40005000 | 11.87% | 11524256.6786
METHOD 3 (TATA Tiscon estimates) |  |  |  |  | METHOD 4 (BMTPC estimates)
Particulars | PerceNtage Allocation | Amount | Site Progress | Cost | Particulars | PerceNtage Allocation | Amount | Site Progress | Cost
Excavation, Concrete for foundation and Plinth | 15% | 6000750 | 100% | 6000750 | Excavation, Concrete for foundation and Plinth | 15% | 6000750 | 100% | 6000750
Superstructure, Concrete and brickwork | 30% | 12001500 | 22% | 2640330 | Superstructure, Concrete and brickwork | 25% | 10001250 | 22.45% | 2245178.5714
Roof slab | 15% | 6000750 | 0% | 0 | Roof slab | 15% | 6000750 | 0% | 0
Flooring | 5% | 2000250 | 0% | 0 | Flooring | 5% | 2000250 | 0% | 0
Plastering and painting | 10% | 4000500 | 0% | 0 | Plastering and painting | 10% | 4000500 | 0% | 0
Doors, windows & woodwork | 10% | 4000500 | 0% | 0 | Doors, windows & woodwork | 13% | 5200650 | 0% | 0
Water Supply, Santiary fittings, electrification and others | 15% | 6000750 | 0% | 0 | Water Supply, Santiary fittings, electrification and others | 17% | 6800850 | 0% | 0
Total | 100% | 40005000 | 17.43% | 8641080 | Total | 100% | 40005000 | 17.49% | 8245928.5714
10001250