File No. : VIS (2021-22)-PL672-Q162-906-1184                          Dated: 01/04/2022

PROJECT PROGRESS REPORT

OF

SHOPPING COMPLEX “PRATAP TOWERS”

SITUATED AT

HALDWANI, NAINITAL, UTTARAKHAND

PROMOTER/S

M/S PRATAP TOWERS PRIVATE LIMITED

REPORT PREPARED FOR

IFCI VENTURE CAPITAL FUNDS LIMITED, NEHRU PLACE, DELHI

**Important - In case of any query/ issue or escalation you may please contact Incident Manager at le@rkassociates.org. We will appreciate your feedback in order to improve our services.

NOTE: As per IBA Guidelines please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct.

| TABLE OF CONTENTS |  |  |
| --- | --- | --- |
| SR. NO. | DESCRIPTION | PAGE NO. |
| PART A | REPORT SUMMARY | 03 |
| PART B | INTRODUCTION | 04 |
|  | - The Project | 04 |
|  | - Project Overview | 04 |
|  | - Project Location | 05 |
|  | - Scope of the Report | 05 |
|  | - Purpose of the Report | 05 |
|  | - Methodology Adopted | 06 |
| PART C | SHOPPING COMLEX DETAILS AND ACTUAL PROGRESS | 07 |
|  | - Building and Structural Details | 07 |
|  | - Site Plans and Drawings | 09 |
|  | - Physical and Expenditure Progress | 15 |
| PART D | DISCLAIMER | 16 |
| PART E | REFERENCE DOCUMENTS | 19 |
| PART F | SITE PHOTOGRAPHS | 24 |

# IMPORTANT NOTICE

COPYRIGHT FORMAT: This report is prepared on the copyright format of R.K Associates, to serve our clients with the best available information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format by any organization or individual other than R.K Associates will be seen as unlawful act and necessary legal action can be taken against the defaulters.

This report is intended for the sole use of the intended recipient/s and contain material that is STRICTLY CONFIDENTIAL AND PRIVATE.

DEFECT LIABILITY PERIOD: In case of any query/ issue or escalation you may please contact Incident Manager: @ le@rkassociates.org. We try our level best to ensure correctness in the calculations done, rates adopted and various other data points & information mentioned in the report but still can’t rule out typing, human errors or any other mistakes. In case you find any such mistake or inaccuracy in any data point of the report please help us by bringing all such points into our notice immediately or within 15 days of the report delivery in writing, to rectify these timely failing after which R.K Associates won’t be held responsible for any such inaccuracy in any manner. We would highly appreciate your feedback in order to improve our services.

| PART A | REPORT SUMMARY |
| --- | --- |

| 1. |  | Name of Project: |  | Construction of a shopping complex under the name of “Pratap Tower” |  |
| --- | --- | --- | --- | --- | --- |
| 2. |  | Project Location: |  | Haldwani, Uttarakhand |  |
| 3. |  | Name of the Borrower Company/Promoter: |  | M/s Pratap Towers Private Limited |  |
| 4. |  | Director’s as per MCA |  | Devendra Kumar (DIN No. 07906770) Ashish Kumar (DIN No.08968012) |  |
| 5. |  | Prepared for: |  | IFCI Venture Capital Funds Limited, Nehru Place, Delhi |  |
| 6. |  | LIE Consultant Firm: |  | M/s. R.K. Associates Valuers & Techno Engineering Consultants (P) Ltd. |  |
| 7. |  | Date of Survey: |  | 14th March 2022 |  |
| 8. |  | Date of Report: |  | 1st April 2022 |  |
| 9. |  | Purpose of the Report: |  | To ascertain the current status and expenditure incurred on the project in regard to construction progress. |  |
| 10. |  | Scope of the Report: |  | To provide progress Report for shopping complex under the name of “Pratap Towers”: |  |
| 11. |  | Documents perused for Proposal: |  | - Approved Building Plan - MOU For construction of shopping complex signed between Golden Bricks engineering and Pratap towers private limited. - Copies of Invoices |  |
| 12. |  | Annexure with the report: |  | - Excerpts of MOU For construction of shopping complex signed between Golden Bricks engineering and Pratap towers private limited. - Copies of Invoices/bills |  |
| PART B |  | INTRODUCTION |  |

- THE PROJECT:

M/s Pratap Towers Private Limited is constructing a shopping complex under the name of “Pratap Towers”. As per approved building plan provided to us the project is being constructed on total land area admeasuring 12,472 ft2 at Haldwani, Uttarakhand and the project is proposed to have elevation with Basement + Ground +3 Floors +Terrace.

- PROJECT OVERVIEW:

The Project is funded by IFCI venture Capital Funds Limited and therefore IFCI venture wants to know the current physical progress with expenditure status of the Project.

M/s Pratap Towers Private Limited is constructing a shopping complex under the name of “Pratap Towers”. As per approved building plan provided to us the project is being constructed on total land area admeasuring 12,472 ft2 at Haldwani, Uttarakhand. The project is proposed to have elevation with Basement + Ground +3 Floors +Terrace.

For the purpose of construction, M/s Pratap Towers Private Limited has signed a construction agreement with golden bricks engineering for the construction of this shopping complex with a total agreement cost of Rs.4.50 Crore.

To verify the construction progress in the project the site visit of the project was conducted on 14th March 2022. During site visit of the project it was observed that the construction of the project is currently at its nascent stage with foundation works majorly under progress and Basement slab at ground level have just started. Approximately 10 labours were found to be working at site.

The project was also tracked as per the copy of approved plan provided by the company. As per our observations there are certain changes on site with respect to the construction plan envisaged in the approved plan. Therefore the company has to renew the approved building plan.

- PROJECT LOCATION:

Details of Location of the project is as below:

| Particulars | Description |
| --- | --- |
| Latitude | # 29°11'49.8"N |
| Longitude | # 79°28'37.1"E |
| Connectivity Systems |  |
| Road | The project site of the under construction commercial tower is well connected by road network and is abutted by RTO Road which can be easily accessed by NH41 (Kaladhungi Road) which passes through Haldwani. The project is approximately 5 km from the NH 41. |
| Rail | Railway network is available in the near vicinity of the under construction commercial tower. The nearest railway station is Haldwani Railway station at a distance of approx. 9 Km. |
| Air | The nearest domestic airport is Pantnagar airport situated at about 30 km distance from the Subject Unit. The nearest international airport is at Lucknow at a distance of about 350 km from the project site. |

Figure 1: Location of Under Construction Commercial Tower

- SCOPE OF THE REPORT: To provide progress Report of under construction shopping complex under the name of “Pratap Tower”.

- PURPOSE OF THE REPORT: To provide progress Report of under construction shopping complex under the name of “Pratap Tower”

- METHODOLOGY ADOPTED:

- Study of Project Planning documents/ reports to know about the Project.

- Additional information, data, documents collection the company.

- Study and analysis of the documents and information obtained from the company.

- Site inspection.

- Information compilation, analysis and reporting.

| PART C | SHOPPING COMPLEX DETAILS & ACTUAL PROGRESS |
| --- | --- |

- BUILDING & STRUCTURAL DETAILS:

The company has proposed to construct a shopping complex having Basement+Ground+3 Floors. Details of the structure as per documents shared by the company are as below

| Building Details as per Approved Plan Dated 31/12/2015 |  |  |
| --- | --- | --- |
| Description | Area (m2) | Area (ft2) |
| Total Plot Area: | 1,158.74 | 12,472.56 |
| Road widening Area: | 198.38 | 2,135.34 |
| Net Plot Area: | 960.36 | 10,337.22 |
| Covered area of Basement: | 218.25 | 2,349.22 |
| Covered area of Ground floor: | 283.85 | 3,055.33 |
| Covered area of first floor | 283.85 | 3,055.33 |
| Covered area of second floor: | 283.85 | 3,055.33 |
| Covered area of Third floor: | 283.85 | 3,055.33 |
| Total Covered area | 1,353.65 | 14,570.55 |
| Total Floor Area | 953.73 | 10,265.85 |
| Open Area | 676.51 | 7,281.89 |
| Parking Details |  |  |
| Covered Parking area | 6.31 ECS | - |
| Open Parking area | 1085 ECS | - |

| Building Details as per Actual Site Drawings |  |  |
| --- | --- | --- |
| Description | Area (m2) | Area (ft2) |
| Covered area of Basement: | 773.88 | 8,330.00 |
| Covered area of Ground floor: | 773.88 | 8,330.00 |
| Covered area of first floor | 773.88 | 8,330.00 |
| Covered area of second floor: | 773.88 | 8,330.00 |
| Covered area of Third floor: | 773.88 | 8,330.00 |
| Total Covered area | 3,869.42 | 41,650.00 |

As per our analysis based on area statements available, it has been observed that there is a mismatch in actual construction covered area calculated during site survey and construction covered area approved in the site plan. Also, the cost estimate amounting to Rs.4.50 Crore is as per the approved drawings only as per the agreement.

| Building Details as per Contract Agreement with Golden Bricks Engineering |  |  |
| --- | --- | --- |
| Description | Area (m2) | Area (ft2) |
| Total Plot Area: | NA | NA |
| Road widening Area: | NA | NA |
| Net Plot Area: | NA | NA |
| Covered area of Basement: | 218.14 | 2,348.00 |
| Covered area of Ground floor: | 283.73 | 3,054.00 |
| Covered area of first floor | 283.73 | 3,054.00 |
| Covered area of second floor: | 283.73 | 3,054.00 |
| Covered area of Third floor: | 283.73 | 3,054.00 |
| Total Covered area | 1,353.04 | 14,564.00 |
| Total Floor Area | NA | NA |
| Open Area | NA | NA |
| Parking Details |  |  |
| Covered Parking area | 6.31 ECS | NA |
| Open Parking area | 1085 ECS | NA |

CIVIL ESTIMATE SIGNED WITH GOLDEN BRICKS ENGINEERING VIDE AGREEMENT DATED 26th MARCH 2021

| (Amount in Rs. Crore) |  |  |
| --- | --- | --- |
| Sr. No. | Particulars | Estimated Amount |
| 1. | 4 Water Tank | 0.15 |
| 2. | 2 Septic tank | 0.05 |
| 3. | Foundation + Colum Work | 0.24 |
| 4. | Basement walls + ramp | 0.36 |
| 5. | Slab + Beam | 0.09 |
| 6. | Cement Plaster | 0.14 |
| 7. | Oil bound distempering | 0.11 |
| 8. | Electricity and sanitary | 0.10 |
| 9. | Ground floor | 0.74 |
| 10. | Architect fee | 0.15 |
| 11. | Advance to Raw material supplier for next floor | 0.18 |
| 12. | First Floor work | 0.74 |
| 13. | Second floor work | 0.74 |
| 14. | Third Floor work + balance architecture fee | 0.71 |
|  | Grand Total | 4.50 |

- SITE PLANS AND DRAWINGS:

  - APPROVED SITE PLAN OF THE PROJECT:

  - ACTUAL CONSTRUCTION PLANS OF THE PROJECT PROVIDED BY THE COMPANY

- PHYSICAL & EXPENDITURE PROGRESS:

As per physical progress observed during site visit based on Actual site drawings provided by the company and current applicable market rates the company has incurred approximately Rs.1.30 Crore on the project till the date of site visit.  The above cost is estimated based on increased area measurement which the company is constructing in deviation to approved building plan and construction agreement. As per site visit based on actual site drawings the Basement area including foundation area admeasuring 8330 Sq. Ft. is complete and Ground floor area admeasuring approx. 1870 Sq. Ft. is complete.

During the site visit it was observed that the actual constructed area on site is more than the approved area and the same was also confirmed by the company. The Site survey was conducted based on Actual construction drawings only. The copies of drawings are also attached above. Thus, if same percentage progress is applied on the civil estimate singed in the agreement which was prepared based on the area mentioned in the approved plan, the actual incurred cost on the project comes to approximately Rs.42 Lakhs.

Breakup of physical progress observed during site visit and expenditure incurred on the project is as below:

| CONSTRUCTION COST ASSESSMENT¦ M/S PRATAP TOWERS PRIVATE LIMITED¦ HALDWANI, DISTRICT NAINITAL, UTTARAKHAND ¦ SITE VISIT DATED MARCH 14, 2022 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sr. No. | Particulars | Estimate | Progress Observed | Expenses | Remarks |
| 1. | 4 Water Tank | 0.15 | 0% | 0.00 | No water tank was found to be constructed during site visit. |
| 2. | 2 Septic tank | 0.05 | 90% | 0.04 | 2 septic tanks were under construction stage during site visit. |
| 3. | Foundation + Column Work | 0.24 | 80% | 0.19 | Foundation and column works have been considered only for basement area for half of the columns only reinforcement binding is done and cement concrete works were pending. Foundation works were found to be completed. Percentage progress has been taken accordingly. |
| 4. | Basement walls + ramp | 0.36 | 45% | 0.16 | Ramp work has not yet started. Therefore, the progress percentage pertains to only Basement walls. Approximately 45% of the basement walls were completed. For remaining walls reinforcement works were completed but Cement concrete works were pending. |
| 5. | Slab + Beam | 0.09 | 30% | 0.03 | Slab + Beam works have been considered for Ground floor only since only one side Ground floor works have completed. |
| 6. | Cement Plaster | 0.14 | 0% | 0.00 | No plaster works is started in the project |
| 7. | Oil bound distempering | 0.11 | 0% | 0.00 | No Oil bound distempering works started in the project. |
| 8. | Electricity and sanitary | 0.10 | 0% | 0.00 | No electricity and sanitary works started in the project. |
| 9. | Ground floor | 0.74 | 0% | 0.00 | No description is mentioned in relation to the works that has to be carried out in this item. Therefore, no cost has been taken under this head. |
| 10. | Architect fee | 0.15 | 0% | 0.00 | No invoice has been given against this item. Therefore, no cost has been taken under this head. |
| 11. | Advance to Raw material supplier for next floor | 0.18 | 0% | 0.00 | Against the provided bill we do not have any breakup against the advance to raw material suppliers for next floor. Therefore, no cost has been taken under this head. |
| 12. | First Floor work | 0.74 | 0% | 0.00 | First floor construction works have not been started yet. |
| 13. | Second floor work | 0.74 | 0% | 0.00 | Second floor construction works have not been started yet. |
| 14. | Third Floor work + balance architecture fee | 0.71 | 0% | 0.00 | Third floor construction works have not been started yet. |
|  | Grand Total | 4.50 | 18% | 0.42 | - |
| Note: 1. Percentage progress has been done based on Actual physical progress observed during site visit considering Stages of construction mentioned in agreement rather than specific measurements, since Detailed BOQ was not provided to us. 2. As per site visit conducted on March 14, 2022, the company has constructed area more than the approved area. Therefore, as per our assessment based on actual physical progress observed during site visit and site-specific drawings shared by the company, they have incurred approximately Rs.1.30 Crore on the project till the date of site visit. |  |  |  |  |  |

| PART D | DISCLAIMER |
| --- | --- |

      - No employee or member of R.K Associates has any direct/ indirect interest in the Project.

      - This report is prepared based on the copies of the documents/ information which the Bank/ Company has provided to us out of the standard checklist of documents sought from them and further based on our assumptions and limiting conditions. The client/owner and its management/representatives warranted to us that the information they supplied was complete, accurate and true and correct to the best of their knowledge. All such information provided to us has been relied upon in good faith and we have assumed that it is true and correct in all respect. I/We shall not be liable for any loss, damages, cost or expenses arising from fraudulent acts, misrepresentations, or wilful default on part of the owner, company, its directors, employee, representative or agents. Verification or cross checking of the documents provided to us from the originals or from any Govt. departments/ Record of Registrar has not been done at our end since this is beyond the scope of our work. If at any time in future, it is found or came to our knowledge that misrepresentation of facts or incomplete or distorted information has been provided to us then this report shall automatically become null & void.

      - Legal aspects for eg. investigation of title, ownership rights, lien, charge, mortgage, lease, sanctioned maps, verification of documents, etc. have not been done at our end and same has to be taken care by legal expert/ Advocate. It is assumed that the concerned Lender/ Financial Institution has satisfied them with the authenticity of the documents, information given to us and for which the legal verification has been already taken and cleared by the competent Advocate before requesting for this report. I/ We assume no responsibility for the legal matters including, but not limited to, legal or title concerns.

      - This report is a general analysis of the project based on the scope mentioned in the report. This is not an Audit report, Design document, DPR or Techno feasibility study. All the information gathered is based on the facts seen on the site during survey, verbal discussion & documentary evidence provided by the client and is believed that information given by the company is true best of their knowledge.

      - All observations mentioned in the report is only based on the visual observation and the documents/ data/ information provided by the client. No mechanical/ technical tests, measurements or any design review have been performed or carried out from our side during Project assessment.

      - Bank/FII should ONLY take this report as an Advisory document from the Financial/ Chartered Engineering firm and its specifically advised to the creditor to cross verify the original documents for the facts mentioned in the report which can be availed from the borrowing company directly.

      - In case of any default in loans or the credit facility extended to the borrowing company, R.K Associates shall not be held responsible for whatsoever reason may be and any request for seeking any explanation from the employee/s of R.K Associates will not be entertained at any instance or situation.

      - The documents, information, data provided to us during the course of this assessment by the client is reviewed only upto the extent required in relation to the scope of the work. No document has been reviewed beyond the scope of the work.

      - This report only contains general assessment & opinion as per the scope of work evaluated as per the information given in the copy of documents, information, data provided to us and/ and confirmed by the owner/ owner representative to us at site which has been relied upon in good faith. It doesn’t contain any other recommendations of any sort including but not limited to express of any opinion on the suitability or otherwise of entering into any transaction with the borrower.

      - We have relied on data from third party, external sources & information available on public domain also to conclude this report. These sources are believed to be reliable and therefore, we assume no liability for the truth or accuracy of any data, opinions or estimates furnished by others that have been used in this analysis. Where we have relied on data, opinions or estimates from external sources, reasonable care has been taken to ensure that such data has been correctly extracted from those sources and /or reproduced in its proper form and context, however still we can’t vouch its authenticity, correctness or accuracy.

      - This Report is prepared by our competent technical team which includes Engineers and financial experts & analysts.

      - This is just an opinion report and doesn’t hold any binding on anyone. It is requested from the concerned Financial Institution which is using this report for taking financial decision on the project that they should consider all the different associated relevant & related factors also before taking any business decision based on the content of this report.

      - All Pages of the report including annexures are signed and stamped from our office. In case any paper in the report is without stamp & signature then this should not be considered a valid paper issued from this office.

      - Though adequate care has been taken while preparing this report as per its scope, but still we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it shall be considered that the report is complete in all respect and has been accepted by the client upto their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

      - Defect Liability Period is 15 DAYS. We request the concerned authorized reader of this report to check the contents, data and calculations in the report within this period and intimate us in writing if any corrections are required or in case of any other concern with the contents or opinion mentioned in the report. Corrections only related to typographical, calculation, spelling mistakes, incorrect data/ figures/ statement will be entertained within the defect liability period. Any new changes for any additional information in already approved report will be regarded as additional work for which additional fees may be charged. No request for any illegitimate change in regard to any facts & figures will be entertained.

      - R.K Associates encourages its customers to give feedback or inform concerns over its services through proper channel at valuers@rkassociates.org in writing within 15 days of report delivery. After this period no concern/ complaint/ proceedings in connection with the Financial Feasibility Study Services will be entertained due to possible change in situation and condition of the subject Project.

      - Our Data retention policy is of ONE YEAR. After this period, we remove all the concerned records related to the assignment from our repository. No clarification or query can be answered after this period due to unavailability of the data.

      - R.K Associates never releases any report doing alterations or modifications from pen. In case any information/ figure of this report is found altered with pen then this report will automatically become null & void.

| Place: Delhi | FOR INTERNAL USE |
| --- | --- |
| Date: 01/04/2022 | SURVEYED BY: Er. Sachin Pandey |
| Note: Report contains 30 Pages | PREPARED BY: Er. Tejas Bharadwaj |
| For R.K. Associates Valuers and Techno Engineering Consultants Pvt. Ltd. |  |

| PART E | REFERENCE DOCUMENTS |
| --- | --- |

COPY OF AGREEMENT WITH GOLDEN BRICKS ENGINEERING

BUIILDING PLAN APPROVAL LETTER DATED 31.12.2015

| PART F | SITE PHOTOGRAPHS |
| --- | --- |