PROGRESS REPORT

- Greenfield Integrated Cement Plant at Panna, MP:

Construction

- Civil Work

- Site Enabling Work:

- Project Office: Completed and Occupied by team

- Workshop and Stores Status: In progress and expected to hand over by coming quarter i.e. January-March-22

- Weighbridge Work Status: Commissioned

- Main Plant Work

- Pile Work:  100% completed

- Stacker / Reclaimer to Clinker Silo

- RCC status :23768 cum completed

# Coal stacker re-claimer:

Wall final lift in progress. Shed footing work in progress.

# Raw Mill Hopper -1:

Column lifts above +23.6Mtr tie beam in progress for +27.1mtr tie beam.

# Raw Mill Hopper -2:

Pile chipping completed. Plinth beam work in progress.

# Raw Mill House -1:

Slab at +20.6mtr casting completed. Column lift for +34.70mtr level completed.

# Raw Mill House -2:

Roller press foundation completed. 1st wall lift casting done, 2nd lift preparation in progress.

# Blending Silo:

Backfilling work completed. Ring beam staging work in progress.

# Raw Mill Baghouse:

Column casting for Bal Slab at +3.5 meter completed. Column lifts for +8.5Mtr    completed for 1’-8 grid.

# Ducting Complex:

All Plinth Beam completed, Footings 16/17 nos completed.

# Preheater Tower:

# Column lifts for 5th Slab at +90.10Mtr completed.

# Kiln Pier 1, 2 & 3:

Kiln pier RCC work completed. Base frame placed.

# Coal Mill:

# Mill foundation RCC completed & Mill stand positioned.

# Clinker Cooler

Excavation, Footing & it’s column in progress. DPC raft plum PCC in progress.

# Clinker Silo:

Tunnel Wall(3nos.) casting Completed.

Centre shaft up to +34.0mtr completed.

Conventional method shuttering work for silo in progress.

# Raw Mill Hopper-2:

Plinth Beam work in progress.

# Raw Mill House-2:

Roller press foundation completed. 1st wall lift casting done, 2nd lift preparation in progress

- WHRS, Cement Mill, Cement Silo, Flyash Silo to Packing Plant Status:

    - RCC status :15028cum completed

# Cement Mill Hopper:

Column lifts in progress for +27Mtr tie beam in progress. Staging for tie beam casting in progress.

# Cement Mill Building:

Column lift for +31mtr slab completed. Staging for slab casting in progress.

# Cement Mill Bag House:

Slab at +18.6Mtr level casting done. Column above +18.6mtr reinforcement work in progress.

# Fly Ash Silo:

Ring Beam casting completed. 1st lift shuttering in progress

# Cement Silo #1

Staging for ring beam and cone lifts in progress.

# Cement Silo # 2:

Cone Profile PCC work completed. Grid slab completed.

# Cement Silo # 3:

Cone lifts completed for cone. Preparing for PCC profiling

# Packing Plant:

+26.1mtr slab casting completed. Column lift above +26.1mtr in progress. Loader area slab @+16.00mtr level casting is in progress.

# Clinker bulk Loading:

Column lifts in progress.

# Water Tank:

Slab casting Completed.

# HAG Building:

# Column lifts for Slab at +19.25Mtr completed. Staging for slab casting in progress. Casting is in progress.

# TG Building:

# Colum up to TG deck at +9.0mtr in progress.

# WHRS ACC building:

Column lifts & Plinth Beam in progress.

# Stacker & Reclaimer, WHRS AQC ,LC102 & ESP

    - RCC status 6153 cum completed

# LS Stacker Re-claimer & Rain Protection Cover:

# Stacker & reclaimer wall final lift casing in progress. Shed footing in progress.

- LC102(Raw Material Handling):

Slab at +3.8Mtr completed. Columns above in progress.

- WHRS AQC Boiler:

Plinth Beam casting completed. Column above +0mtr level in progress.

- ESP Building:

RCC Footing in progress. Footing column in progress for plinth beam.

  - CCR, Admin building, MCC room

    - RCC status 5105 cum completed

# CCR:

Brick work & Flooring work in progress. Transformer foundation wall work in progress.

# Gate Complex:

Plumbing work completed. Handover & Puja ceremony done.

# Oxygen Plant:

Civil Work completed and handed over.

# Admin Building:

# Brick Work in progress.

- Load Center LC 106:

Slab at +8.8 Meter casting completed.

- Load Center LC105:

Slab at +3.8 Meter casting completed. Further column lifts for +8.80mtr level completed. Slab expected shortly.

- Load Center LC107:

Slab preparation in progress. Transformer foundation casting completed.

  - Bachelor hotel & Guest House:

    - RCC status: 1079 Cum completed

      - Guest House:

Brick work in progress.

      - Bachelor Hostel:

GF 12 Rooms handed-over, and balance 12 Rooms handover expected in coming quarter.

  - Intake & Jack well:

    - RCC status:126Cum completed

    - Pipe laying: Pipe laying completed

  - Belt Conveyor Foundations / TT:

    - RCC status :574 Cum completed.

# Mech Work:

# Fabrication Status:

      - Pre-Clinkerisation(HAPBCO):

        - Plate work 2,345 MT completed

        - Structure work 1693 completed

          - Raw Mill Hopper, PH Tower Structure, Raw Mill Hopper, Raw Mill House, Kiln Pier progress.

      - Post –Clinkerisation(MONOMARK) :

        - Plate work 808 MT completed

        - Structure work 1,109 MT completed

        - Cement Silos, packing plant, cement mill & hopper building work in progress.

      - Structure & TT (KEC):

        - Structure work 119 MT completed

      - LS crusher, conveyor & Misc.(SUMMIT):

        - Structure work 616 MT completed

        - Conveyors work in progress.

# Erection Status:

- Pre - Clinkerisation: (HAPBCo)

  - Erection 321MT Completed

- Oxygen Plant Commissioned

  - Coal Mill Building Stack erection in progress & Mill Base Frame alignment in progress. 2nos Mill Pedestal erection completed.

  - Preheater Tower: Staircase completed up to +30.2Mtr slab.

  - Preheater Tower: Mixing Bin cylindrical piece, B.E boot casing placed. Kiln Inlet Chamber placed, center alignment in progress.

  - Raw Mill Hopper 1: Staircase erection in progress up to Slab at +17.85Mtr. Structural platform at +12.2mtr erection done.

  - KP2: Kiln Base frame placed. Connecting platform between Kiln piers in progress.

  - KP1 base frame erection done.

- Post- Clinkerisation (MONOMARK):

  - Erection 247 MT Completed

  - Cement Mill: Bridges, Pedestal placed. Alignment in progress.

  - Cement Mill hopper: Hopper erection in done.

  - Packing Plant: Loader Area steel platform, column & truss erection in progress

  - Cement Mill Building: Staircase erection in progress.

- Transmission Line

  - Status:

- 110nos of tower Footing & Pedestal work completed

- 31nos of tower erected at site

- Grinding Unit at Hamirpur,UP:

- Construction

- Civil Work

- Cement Mill, Cement Silo, Flyash Silo to Packing Plant Status:

    - RCC status :3917cum completed

# Additive stockpile:

(16/43 Nos.) foundation completed. (12/43 Nos.) columns up to +0.0mtr completed.

# Clinker silo:

(208/245 Nos.) Pile chipping completed. Balance expected to complete shortly.

# Cement Mill Hopper:

(17/17 Nos.) ground beams completed. Column lifts above +0.0 Mtr in progress.

# Cement Mill Building:

(5/5 Nos.) Foundation completed. Column lift up to +0.0mtr in progress.

# Cement Mill Bag House:

(23/26 Nos.) foundation completed. Ground beam in progress.

# Cement Mill VRM:

Casting of foundation in progress. Expected to complete shortly.

# Fly Ash Silo:

Piling completed. Excavation in progress. Expected to complete shortly.

# Cement Silo #1

Wall slipping up to +38.0 Mtr in progress. Expected to be completed by coming quarter.

# Cement Silo # 2:

Piling completed. Excavation work in progress. Expected to completed shortly.

# Packing Plant (Packer & Loader):

(17/19 Nos..) foundation completed. (2/3 Nos.) bucket elevator    foundation completed.

# CCR & MCC room:

+4.5mtr slab preparation in progress. Expected to complete by coming quarter.

- Mechanical Work

- Fabrication Status:

    - Structure 232 MT completed.

    - Plate   196 MT completed

PROJECT PHOTOGRAPHS- Panna Integrated Cement Plant

Latest

- Workshop & Store: Brick work in progress.

Latest

- Pre-heater Tower: Column lifts for +90.100 Meter Slab completed.(40/40 lifts)

Latest

- Cement Silo#2:  Cone Lifts completed. Ground floor work in progress
   Latest

- Cement Silo#3: Silo Cone lifts completed. (9/9 lifts)

Latest

- Fly ash Silo: Silo Ring Beam preparation in progress.

Latest

- L/S Stacker & Re-claimer: Wall Final lifts & Shed footings in progress.

Latest

- Coal Stacker & Re-claimer: Wall Final Lift Casting & Rail Fixing in progress.

Latest

- Cement Mill Hopper: Column lifts in progress for Slab at +27.00 Meter.

Latest

- Cement Mill Building: Slab at +24.40 Meter casting done.

Latest

- Cement Mill Baghouse:  Staging, reinforcement & shuttering works in progress for Slab at +18.60 Meter.

Latest

- Clinker Bulk Loading Hopper: Column lifts are in progress.

Latest

- Packing Plant: Packer Area Tie Beam at +22.79 Meter casting completed.

Loader area slab at +16.0 Meter slab preparation in progress.

L atest

- Guest House & Bachelor Hostel: Bachelor hostel, 12 Rooms ready. Bal. rooms finishing work in progress.                                                                                                                Guest House Slab casting completed. Brick work in progress

Latest

- CR Cum Pyro Load Centre 104: Brick work & RCC Flooring in progress.

Latest

- LC105 CM: Slab +3.5m Casting Completed. Slab preparation for +8.8m in progress

Latest

- LC 106 Packing Plant: Slab at +8.80 Meter casting completed.

Latest

- LC 102 Material Handling:  Slab at +3.800 Meter casted. Column lift u/p

Latest

- HAG Building: Slab at +12.0 Meter casted. Column lifts for Slab at +19.25 Meter in progress.

Latest

- WHR S-TG Building: Column lifts in progress.

Latest

- Raw Mill Hopper 1:  Column lifts up to tie beam at +23.600 meter completed.

Latest

- Raw Mill House1: Columns up to +34.70 Meter in progress

Latest

- Raw Mill Baghouse: Slab at +3.50 Meter Casting Completed.

Slab at +8.50 Meter 50% column lifts completed up to +8.50 Meter.

Latest

- Kiln Pier 1: KP1 Slab casting completed.

Latest

- Kiln Pier 2- Kiln base frame placed.

Latest

- Kiln Pier 3 – Kiln base frame placed. 
Latest

- Coal Mill Building: +11.00 Meter Slab preparation in progress. Slab exp. to cast shortly

Latest

- Fine Coal Building: Plinth Beam in progress. : Tie Beam at +5.2m in progress.

Latest

- Ducting Complex: RCC footing & C olumn lifts work in progress.

Latest

- Cooler Bu ilding: Excavation & Footings in progress.

Latest

- WHRS AQC Building: Plinth Beam preparation in progress.

Latest

- ESP Building: Shuttering work in progress for ESP Fan.

Latest

- WHRS ACC Building: Plinth Beam work in progress.

Latest

- LC 107: Slab at +3.800meter preparation in progress.

Latest

- Belt Conveyor & TT: Excavation & Foo tings in progress.

Latest

  - Clinker Silo: Silo Outer Wall Reinforcement & shuttering work in progress.

Central Shaft Wall Slipping completed up to +45.00 Meter. Side slipping wall in progress.

Latest

- Admin Building: Brick work in progress. 
Mechanical Fabrication Activities

- M/s HAPBCo Pre-Assembly Area: Coal Mill Ring duct fitup & root welding completed.

- M/s KEC:  Bolt Fixing in Coal Stacker & Reclaimer, Rail laying & Reclaimer boogie assembly under progress.

- Kiln: Shell ground assembly in progress.                                                                               Gas Duct: Stack piece assembly.

Mixing Bin – Stool piece erection in progress				                          Coal Mill: 2 no’s pedestal erection done.

Preheater: 13mtr level erection activities:                                                                                                        Smoke chamber placing done.

Cement Mill Hopper building: bin erection done.                                                                                 Packing plant: Bag filter erection done.

# PROJECT PHOTOGRAPHS- Hamirpur: Grinding Unit

Latest

- Weigh Bridge- Foundation: Control Room work completed

Latest

                - Cement Silo#1: Slipping work in progress

Latest

- Cement Mill VRM: Casting in progress

Latest

- Cement Mill Building: RCC

Latest

- Additive Shed: 16 Nos footing completed out of 43 Nos

Latest

- Clinker Silo: Pile Breaking in progress

Latest

- Cement Mill Hopper: RCC footing work completed & Plinth beam work in progress

Latest

- Cement Mill Baghouse: RCC footing work in progress

Latest

- Packing Plant: 17 out of 19 Nos. footings completed. Plinth beam & Column work in progress

Latest

- CCR Building: RCC footing completed, slab preparation activities is in progress

Latest