## R 202
S.No. | REQUIRED APPROVALS | REFERENCE NO./ DATE | STATUS
(Approved/ Applied For/ Pending)
1. | Land conversion to Industrial/ non agriculture |  | As per Land deed, land is Industrial Land.
2. | Factory Registration |  | To be taken after start of production
Chief Inspector of Labour Commissioner Organisation, As per the provisions under the Factory Act, 1948
3. | Factory Layout Plan Approval | 15.02.2022 | In Progress
Factory Plan Layout Approval from concerned local authority
4. | Provisional Fire NOC (pre sanction) | Part NOC received
Fire Services Department, UP
5. | Fire NOC (on completion) |  | To be taken after start of production
Fire Services Department, UP
6. | Permission for drawing ground water for Industrial purposes |  | Not Applicable
Xxx Ground Water (Management and Regulation) Act, 2019
7. | Information Entrepreneurs Memorandum (IEM) |  | Not mandatory
Infrastructure & Industrial Development Department, Government of xxxx
8. | Power Load Sanction |  | To be applied in due course
xxx Electricity Regulatory Commission
9. | Consent to establish (under Water Act & Air Act) |  | To be taken after start of production
xxxxxxx Pollution Control Board, Government Of xxxxxx
xxxxxxx Pollution Control Board, Government Of xxxxxxxx
10. | Import-Export License |  | Not Applicable

## Bengaluru
S.No. | REQUIRED APPROVALS | REFERENCE NO./ DATE | STATUS
(Approved/ Applied For/ Pending)
1. | Land conversion to Industrial/ non agriculture |  | As per Land deed, land is Industrial Land.
2. | Factory Registration |  | To be taken after start of production
Chief Inspector of Labour Commissioner Organisation, As per the provisions under the Factory Act, 1948
3. | Factory Layout Plan Approval | 2022-03-01 | Brownfield. Layout will be approved by Structural Consultant
Factory Plan Layout Approval from concerned local authority
4. | Provisional Fire NOC (pre sanction) |  | Available
Fire Services Department, Karnataka
5. | Fire NOC (on completion) |  | To be taken after start of production
Fire Services Department, Karnataka
6. | Permission for drawing ground water for Industrial purposes |  | Not Applicable
Xxx Ground Water (Management and Regulation) Act, 2019
7. | Information Entrepreneurs Memorandum (IEM) |  | Not mandatory
Infrastructure & Industrial Development Department, Government of xxxx
8. | Power Load Sanction | 01.07.2022 | To be applied in due course
xxx Electricity Regulatory Commission
9. | Consent to establish (under Water Act & Air Act) |  | To be taken after start of production
xxxxxxx Pollution Control Board, Government Of xxxxxx
xxxxxxx Pollution Control Board, Government Of xxxxxxxx
10. | Import-Export License |  | Not required

## Noida
S.No. | REQUIRED APPROVALS | REFERENCE NO./ DATE | STATUS
(Approved/ Applied For/ Pending)
1. | Land conversion to Industrial/ non agriculture |  | As per Land deed, land is Industrial Land.
2. | Factory Registration |  | To be taken after start of production
Chief Inspector of Labour Commissioner Organisation, As per the provisions under the Factory Act, 1948
3. | Factory Layout Plan Approval | 2022-03-01
Factory Plan Layout Approval from concerned local authority
4. | Provisional Fire NOC (pre sanction) | After building plan approval
Fire Services Department, UP
5. | Fire NOC (on completion) | 2022-07-01 | To be taken after start of production
Fire Services Department, UP
6. | Permission for drawing ground water for Industrial purposes |  | Not Applicable
Xxx Ground Water (Management and Regulation) Act, 2019
7. | Information Entrepreneurs Memorandum (IEM) |  | Not mandatory
Infrastructure & Industrial Development Department, Government of xxxx
8. | Power Load Sanction | 2022-09-01 | To be applied in due course
xxx Electricity Regulatory Commission
9. | Consent to establish (under Water Act & Air Act) |  | To be taken after start of production
xxxxxxx Pollution Control Board, Government Of xxxxxx
xxxxxxx Pollution Control Board, Government Of xxxxxxxx
10. | Import-Export License |  | Not Applicable