## Plots (1)
Frozen / Unfreeze plots & Stage of Construction
S. No. | Category of Plots | Plot's No. | Approved Plot No. | Floors | Cat. | Plot no. | Units | Sales Unit No. | Plot Size (sq.mtr.) | Stage of Construction
1 | A5 | 2 | A5-2 | B+S+4 | G | 1 | A,B,C,D | G-1/A,B,C,D | 148.2 | Foundation work complete
2 | B5 | 15 | B5-15 | B+S+4 | G | 2 | A,B,C,D | G-2/A,B,C,D | 148.2 | Foundation work complete
3 | C1 | 1 | C1-1 | B+S+4 | G | 3 | A,B,C,D | G-3/A,B,C,D | 148.2 | Foundation work complete
4 | C2 | 6 | C2-6 | B+S+4 | G | 3 | A,B,C,D | G-3/A,B,C,D | 148.2 | Foundation work complete
5 | C2 | 9 | C2-9 | B+S+4 | G | 4 | A,B,C,D | G-4/A,B,C,D | 148.2 | Foundation work complete
6 | C3 | 8 | C3-8 | B+S+4 | G | 5 | A,B,C,D | G-5/A,B,C,D | 148.2 | Foundation work complete
7 | C8 | 15 | C8-15 | B+S+4 | G | 6 | A,B,C,D | G-6/A,B,C,D | 148.2 | Foundation work complete
8 | C8A | 20 | C8A-20 | B+S+4 | G | 7 | A,B,C,D | G-7/A,B,C,D | 148.2 | Stilt slab casting work is in progress
9 | C8A | 33 | C8A-33 | B+S+4 | G | 8 | A,B,C,D | G-8/A,B,C,D | 148.2 | Stilt slab casting work is in progress
10 | D1 | 18 | D1-18 | B+S+4 | G | 9 | A,B,C,D | G-9/A,B,C,D | 148.2 | Stilt slab casting work is in progress
11 | D1 | 19 | D1-19 | B+S+4 | G | 10 | A,B,C,D | G-10/A,B,C,D | 148.2 | Stilt slab casting work is in progress
12 | D1 | 20 | D1-20 | B+S+4 | G | 11 | A,B,C,D | G-11/A,B,C,D | 148.2 | Stilt slab casting work is in progress
13 | D1 | 21 | D1-21 | B+S+4 | G | 12 | A,B,C,D | G-12/A,B,C,D | 148.2 | Stilt slab casting work is in progress
14 | D6 | 1 | D6-1 | B+S+4 | G | 13 | A,B,C,D | G-13/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
15 | D6 | 2 | D6-2 | B+S+4 | G | 14 | A,B,C,D | G-14/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
16 | D6 | 3 | D6-3 | B+S+4 | G | 15 | A,B,C,D | G-15/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
17 | D6 | 4 | D6-4 | B+S+4 | G | 16 | A,B,C,D | G-16/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
18 | D7 | 1 | D7-1 | B+S+4 | G | 17 | A,B,C,D | G-17/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
19 | D7 | 2 | D7-2 | B+S+4 | G | 18 | A,B,C,D | G-18/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
20 | D7 | 3 | D7-3 | B+S+4 | H | 19 | A,B,C,D | H-19/A,B,C,D | 148.2 | Stilt roof complete
21 | D8 | 20 | D8-20 | B+S+4 | H | 18 | A,B,C,D | H-18/A,B,C,D | 148.2 | Stilt roof complete
22 | D8 | 23 | D8-23 | B+S+4 | H | 17 | A,B,C,D | H-17/A,B,C,D | 148.2 | Stilt roof complete
23 | D8 | 24 | D8-24 | B+S+4 | H | 16 | A,B,C,D | H-16/A,B,C,D | 148.2 | Stilt roof complete
24 | E1 | 22 | E1-22 | B+S+4 | H | 15 | A,B,C,D | H-15/A,B,C,D | 148.2 | Stilt roof complete
25 | NA | 1 | NA-1 | B+S+4 | H | 14 | A,B,C,D | H-14/A,B,C,D | 148.2 | Stilt roof complete
26 | NA | 2 | NA-2 | B+S+4 | H | 13 | A,B,C,D | H-13/A,B,C,D | 148.2 | Basement slab complete
27 | WA | 21 | WA-21 | B+S+4 | H | 12 | A,B,C,D | H-12/A,B,C,D | 148.2 | Basement slab complete
28 | WA | 41 | WA-41 | B+S+4 | H | 11 | A,B,C,D | H-11/A,B,C,D | 148.2 | Basement slab complete
29 | WA | 42 | WA-42 | B+S+4 | H | 10 | A,B,C,D | H-10/A,B,C,D | 148.2 | Basement slab complete
4297.8

## Plots
|  | Sq.ft. | 10.7639
PLOT DETAILS-GARDEN CITY, SECTOR-91-92, GURUGRAM
S. No. | Category of Plots | Plot's No. | Plot No. | Plot Size |  | Status | Pemissible FAR area |  | Provided FAR area |  | BUILT UP AREA |  | NON FAR AREA |  | Permissible Ground coverage |  | Ground coverage
|  |  |  | Sq. mtr. | Sq.ft. |  | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft.
1 | A5 | 15 | A5-15 | 387.75 | 4173.7022 |  | 930.6 | 10016.8853 | 930.31 | 10013.7638 | 1333.67 | 14355.4905 | 403.36 | 4341.7267 | 232.65 | 2504.2213 | 228.82 | 2462.9956
2 | A5 | 15A | A5-15A | 420 | 4520.838 |  | 1008 | 10850.0112 | 1007.27 | 10842.1536 | 1735.84 | 18684.4082 | 728.57 | 7842.2546 | 252 | 2712.5028 | 249.18 | 2682.1486
3 | A8 | 18 | A8-18 | 420 | 4520.838 |  | 1008 | 10850.0112 | 1007.27 | 10842.1536 | 1735.84 | 18684.4082 | 728.57 | 7842.2546 | 252 | 2712.5028 | 249.18 | 2682.1486
4 | A9 | 1B | A9-1B | 426.93 | 4595.4318 |  | 1024.64 | 11029.1225 | 1016.07 | 10936.8759 | 1531.81 | 16488.2497 | 515.74 | 5551.3738 | 256.16 | 2757.2806 | 255.51 | 2750.2841
5 | A9 | 1C | A9-1C | 430.85 | 4637.6263 |  | 1034.04 | 11130.3032 | 1016.07 | 10936.8759 | 1531.81 | 16488.2497 | 515.74 | 5551.3738 | 258.51 | 2782.5758 | 255.51 | 2750.2841
6 | A9 | 1E | A9-1E | 437.5 | 4709.2063 |  | 1050 | 11302.095 | 989.48 | 10650.6638 | 1501.74 | 16164.5792 | 512.26 | 5513.9154 | 262.5 | 2825.5237 | 255.51 | 2750.2841
7 | A9 | 1F | A9-1F | 440.3 | 4739.3452 |  | 1056.72 | 11374.4284 | 989.48 | 10650.6638 | 1501.74 | 16164.5792 | 512.26 | 5513.9154 | 264.18 | 2843.6071 | 255.51 | 2750.2841
8 | A9 | 8 | A9-8 | 360.5 | 3880.3859 |  | 865.2 | 9312.9263 | 859.13 | 9247.5894 | 1283.78 | 13818.4795 | 424.65 | 4570.8901 | 216.3 | 2328.2316 | 215.5 | 2319.6204
9 | A10 | 1 | A10-1 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
10 | A10 | 02 | A10-02 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
11 | A10 | 03 | A10-03 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
12 | A10 | 04 | A10-04 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
13 | A10 | 09 | A10-09 | 224.87 | 2420.4782 |  | 593.66 | 6390.0969 | 586.21 | 6309.9058 | 859.63 | 9252.9714 | 273.42 | 2943.0655 | 148.41 | 1597.4704 | 147.71 | 1589.9357
14 | A10 | 10 | A10-10 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
15 | A10 | 11 | A10-11 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
16 | A10 | 12 | A10-12 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
17 | A10 | 14 | A10-14 | 241.8 | 2602.711 |  | 638.35 | 6871.1356 | 634.49 | 6829.5869 | 939.4 | 10111.6077 | 304.91 | 3282.0207 | 159.59 | 1717.8108 | 158.1 | 1701.7726
18 | A15 | 19 | A15-19 | 314.9 | 3389.5521 |  | 755.77 | 8135.0327 | 744.79 | 8016.8451 | 1089.38 | 11725.9774 | 344.59 | 3709.1323 | 188.94 | 2033.7313 | 185.96 | 2001.6548
19 | A15 | 20 | A15-20 | 358.08 | 3854.3373 |  | 859.4 | 9250.4957 | 848.15 | 9129.4018 | 1259.01 | 13551.8577 | 410.86 | 4422.456 | 214.85 | 2312.6239 | 211.71 | 2278.8253
20 | A16 | 14 | A16-14 | 281.06 | 3025.3017 |  | 674.55 | 7260.7887 | 673.59 | 7250.4554 | 994.96 | 10709.6499 | 321.37 | 3459.1945 | 168.64 | 1815.2241 | 165.64 | 1782.9324
21 | E3 | 30 | E3-30 | 371.79 | 4001.9104 |  | 892.3 | 9604.628 | 892.1 | 9602.4752 | 1304.7 | 14043.6603 | 412.6 | 4441.1851 | 223.07 | 2401.1032 | 222.98 | 2400.1344
22 | G-7C | 04 | G-7C-04 | 219.66 | 2364.3983 |  | 579.91 | 6242.0932 | 576.52 | 6205.6036 | 860.5 | 9262.336 | 283.98 | 3056.7323 | 144.98 | 1560.5502 | 144.86 | 1559.2586
23 | G-7C | 7 | G-7C-7 | 239.88 | 2582.0443 |  | 633.29 | 6816.6702 | 633.13 | 6814.948 | 929.85 | 10008.8124 | 296.72 | 3193.8644 | 158.32 | 1704.1406 | 157.74 | 1697.8976
24 | G-7C | 8 | G-7C-8 | 239.88 | 2582.0443 |  | 633.29 | 6816.6702 | 633.13 | 6814.948 | 929.85 | 10008.8124 | 296.72 | 3193.8644 | 158.32 | 1704.1406 | 157.74 | 1697.8976
25 | G-7C | 9 | G-7C-9 | 252.85 | 2721.6521 |  | 633.29 | 6816.6702 | 633.13 | 6814.948 | 929.85 | 10008.8124 | 296.72 | 3193.8644 | 158.32 | 1704.1406 | 157.74 | 1697.8976
26 | G-7C | 10 | G-7C-10 | 239.88 | 2582.0443 |  | 633.29 | 6816.6702 | 633.13 | 6814.948 | 929.85 | 10008.8124 | 296.72 | 3193.8644 | 158.32 | 1704.1406 | 157.74 | 1697.8976
27 | G-7C | 1 | G-7C-1 | 219.83 | 2366.2281 |  | 580.35 | 6246.8294 | 576.52 | 6205.6036 | 860.5 | 9262.336 | 283.98 | 3056.7323 | 145.09 | 1561.7343 | 144.86 | 1559.2586
28 | G-7C | 1A | G-7C-1A | 219.83 | 2366.2281 |  | 580.35 | 6246.8294 | 576.52 | 6205.6036 | 860.5 | 9262.336 | 283.98 | 3056.7323 | 145.09 | 1561.7343 | 144.86 | 1559.2586 | 1b
29 | G-7C | 3 | G-7C-3 | 219.83 | 2366.2281 |  | 580.35 | 6246.8294 | 576.52 | 6205.6036 | 860.5 | 9262.336 | 283.98 | 3056.7323 | 145.09 | 1561.7343 | 144.86 | 1559.2586
30 | G-7C | 2 | G-7C-2 | 219.83 | 2366.2281 |  | 580.35 | 6246.8294 | 576.52 | 6205.6036 | 860.5 | 9262.336 | 283.98 | 3056.7323 | 145.09 | 1561.7343 | 144.86 | 1559.2586
31 | G-7C | 1B | G-7C-1B | 219.83 | 2366.2281 |  | 318.75 | 3430.9931 | 576.52 | 6205.6036 | 860.5 | 9262.336 | 283.98 | 3056.7323 | 145.09 | 1561.7343 | 144.86 | 1559.2586
TOTAL |  |  |  | 9100.23 | 97953.9657 | 0 | 22612.9 | 243402.9943 | 22627.48 | 243559.932 | 34061.51 | 366634.6875 | 11434.03 | 123074.7555 | 5718.64 | 61554.8691 | 5663.64 | 60962.8546
|  |  |  | 1 | [6 empty] | 9100.23 |  | Sq. mtr.
|  |  |  | 2 | Ground Coverage |  | Permissible |  |  |  | 5718.64 |  | Sq. mtr.
[7 empty] | Proposed |  |  |  | 5663.64 |  | Sq. mtr.
|  |  |  | 3 | FAR |  | Permissible |  |  |  | 22612.9 |  | Sq. mtr.
[7 empty] | Proposed |  |  |  | 22627.48 |  | Sq. mtr. | 243559.932
|  |  |  | 4 | Non FAR Area |  | Proposed |  |  |  | 11434.03 |  | Sq. mtr. | 123074.7555

## Total Plots
Break-up of Plots of the whole project
S. No. | Category | Plot's No. | Total No. of Plots | Plot Size |  | Total Area of Plots
|  |  |  | Sq. mtr. | Sq. yds. | Sq. mtr. | Sq. yds.
1 | A | A-1 to A-118 | 118 | 148.2 | 177.2472 | 17487.6 | 20915.1696
2 | B | B-1 to B-114 | 114 | 140.4 | 167.9184 | 16005.6 | 19142.6976
3 | C | C-1 to C-16 | 16 | 105.225 | 125.8491 | 1683.6 | 2013.5856
4 | D | D-1 to D-97 | 97 | 107.813 | 128.9443 | 10457.861 | 12507.6018
5 | E | E-1 to E-6 | 6 | 100 | 119.6 | 600 | 717.6 | 100.506
6 | P1 | P-1 | 1 | 140.445 | 167.9722 | 140.445 | 167.9722 | 2.425
7 | P2 | P-2 | 1 | 114.13 | 136.4995 | 114.13 | 136.4995 | 7.006
8 | P3 | P-3 | 1 | 85.649 | 102.4362 | 85.649 | 102.4362 | 3.9
9 | P4 | P-4 | 1 | 147.987 | 176.9925 | 147.987 | 176.9925 | 113.837
10 | P5 | P-5 | 1 | 119.465 | 142.8801 | 119.465 | 142.8801
11 | P6 | P-6 | 1 | 124.71 | 149.1532 | 124.71 | 149.1532
12 | P7 | P-7 | 1 | 94.71 | 113.2732 | 94.71 | 113.2732
13 | P8 | P-8 | 1 | 124.3 | 148.6628 | 124.3 | 148.6628
14 | P9 | P-9 | 1 | 142.469 | 170.3929 | 142.469 | 170.3929
15 | P10 | P-10 | 1 | 81.463 | 97.4297 | 81.463 | 97.4297
16 | P11 | P-11 | 1 | 90.54 | 108.2858 | 90.54 | 108.2858
|  |  | 362 |  |  | 47500.529 | 56810.6327

## Sheet3
Break up of Fair Market Value of Independent Floor
Sr. No. | Category | No. of Plots | No. of Units | Block | No. of Plots | No. of Units | Unit Type | Carpet Area | Saleable Area | Adopted Market Rate per sq ft on Super Area |  | Fair Market Value (FMV) of Independent Floor |  | Average Market Value of Independent Floor for Calculation Purpose | Prospective Fair Market Value of Project for Calculation Purpose
| As per Approved Layout Plan |  |  | As per Sales
[8 empty] | Sq. ft. | Sq. ft. | Min (In INR) | Max (In INR) | Min (In INR) | Max (In INR) | (In INR) | (In INR)
1 | A | 118 | 472 | G | 18 | 72 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1290960000 | 117360
|  |  |  | H | 19 | 76 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1362680000 | 123880
|  |  |  | D | 11 | 44 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 788920000 | 71720
|  |  |  | C | 15 | 60 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1075800000 | 97800
|  |  |  | B | 15 | 60 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1075800000 | 97800
|  |  |  | I | 40 | 160 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 2868800000 | 260800
2 | B | 114 | 456 | H | 10 | 40 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 682000000 | 62000
|  |  |  | G | 11 | 44 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 750200000 | 68200
|  |  |  | F | 29 | 116 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 1977800000 | 179800
|  |  |  | E | 29 | 116 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 1977800000 | 179800
|  |  |  | A | 35 | 140 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 2387000000 | 217000
3 | C | 12 | 48 | M | 4 | 16 | 2.5 BHK | 603.54 | 1120 | 10500 | 11500 | 11760000 | 12880000 | 12320000 | 197120000 | 17920
|  |  |  | L | 4 | 16 | 2.5 BHK | 603.54 | 1120 | 10500 | 11500 | 11760000 | 12880000 | 12320000 | 197120000 | 17920
|  |  |  | K | 4 | 16 | 2.5 BHK | 603.54 | 1120 | 10500 | 11500 | 11760000 | 12880000 | 12320000 | 197120000 | 17920
4 | D | 83 | 332 | M | 14 | 56 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 708400000 | 64400
|  |  |  | L | 28 | 112 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 1416800000 | 128800
|  |  |  | K | 28 | 112 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 1416800000 | 128800
|  |  |  | J | 13 | 52 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 657800000 | 59800
|  | 327 | 1308 | [11 empty] | 21028920000 | 1911720

## Sanctioned
Area Details as per Sanctioned building plans under self certification scheme
Smartworld Orchard
[5 empty] | GROUND COVERAGE |  |  |  | FAR / FSI |  |  |  | NON FAR
Sr. No. | Plot Type |  | No. of Plots | Plot Size | Permissible |  | Provided |  | Permissible |  | Provided |  | Stilt | Basement | Stair | Total
|  |  |  | (sq.mtr) | (sq.mtr) | %age | (sq.mtr) | %age | (sq.mtr) | %age | (sq.mtr) | %age | (sq.mtr) | (sq.mtr) | (sq.mtr) | (sq.mtr)
1 | A | Left Side | 60 | 148.2 | 97.812 | 66% | 97.802 | 65.99% | 391.248 | 264% | 356.3 | 240.4% | 97.802 | 128.7 | 31.788 | 258.29
2 | A | Right Side | 58 | 148.2 | 97.812 | 66% | 97.802 | 65.99% | 391.248 | 264% | 356.3 | 240.4% | 97.802 | 128.7 | 31.788 | 258.29
3 | B | Left Side | 56 | 140.4 | 92.664 | 66% | 92.649 | 65.99% | 370.656 | 264% | 335.728 | 239.1% | 92.649 | 120.9 | 31.788 | 245.337
4 | B | Right Side | 58 | 140.4 | 92.664 | 66% | 92.649 | 65.99% | 370.656 | 264% | 335.728 | 239.1% | 92.649 | 120.9 | 31.788 | 245.337
5 | C | Left Side | 6 | 105.225 | 69.449 | 66% | 69.42 | 65.97% | 277.794 | 264% | 247.296 | 235% | 69.42 | 86.925 | 30.38 | 186.725
6 | C | Right Side | 6 | 105.225 | 69.449 | 66% | 69.42 | 65.97% | 277.794 | 264% | 247.296 | 235% | 69.42 | 86.925 | 30.38 | 186.725
7 | D | Left Side | 41 | 107.8125 | 71.156 | 66% | 71.146 | 65.99% | 284.625 | 264% | 254.204 | 235.8% | 71.146 | 89.063 | 30.38 | 190.589
8 | D | Right Side | 42 | 107.8125 | 71.156 | 66% | 71.146 | 65.99% | 284.625 | 264% | 254.204 | 235.8% | 71.146 | 89.063 | 30.38 | 190.589
327
1 | Total Plots Area | [7 empty] | 43704.338 |  | Sq. mtr.
2 | Total Ground Coverage |  |  |  | Permissible |  |  |  | 28844.848 |  | Sq. mtr.
[5 empty] | Proposed |  |  |  | 28840.78 |  | Sq. mtr.
3 | Total FAR |  |  |  | Permissible |  |  |  | 115379.451 |  | Sq. mtr.
[5 empty] | Proposed |  |  |  | 104382.876 |  | Sq. mtr.
4 | Total NON FAR |  |  |  | Proposed |  |  |  | 76506.225 |  | Sq. mtr.