## Plots (1)
Frozen / Unfreeze plots & Stage of Construction
S. No. | Category of Plots | Plot's No. | Approved Plot No. | Floors | Cat. | Plot no. | Units | Sales Unit No. | Plot Size (sq.mtr.) | Stage of Construction
1 | A5 | 2 | A5-2 | B+S+4 | G | 1 | A,B,C,D | G-1/A,B,C,D | 148.2 | Foundation work complete
2 | B5 | 15 | B5-15 | B+S+4 | G | 2 | A,B,C,D | G-2/A,B,C,D | 148.2 | Foundation work complete
3 | C1 | 1 | C1-1 | B+S+4 | G | 3 | A,B,C,D | G-3/A,B,C,D | 148.2 | Foundation work complete
4 | C2 | 6 | C2-6 | B+S+4 | G | 3 | A,B,C,D | G-3/A,B,C,D | 148.2 | Foundation work complete
5 | C2 | 9 | C2-9 | B+S+4 | G | 4 | A,B,C,D | G-4/A,B,C,D | 148.2 | Foundation work complete
6 | C3 | 8 | C3-8 | B+S+4 | G | 5 | A,B,C,D | G-5/A,B,C,D | 148.2 | Foundation work complete
7 | C8 | 15 | C8-15 | B+S+4 | G | 6 | A,B,C,D | G-6/A,B,C,D | 148.2 | Foundation work complete
8 | C8A | 20 | C8A-20 | B+S+4 | G | 7 | A,B,C,D | G-7/A,B,C,D | 148.2 | Stilt slab casting work is in progress
9 | C8A | 33 | C8A-33 | B+S+4 | G | 8 | A,B,C,D | G-8/A,B,C,D | 148.2 | Stilt slab casting work is in progress
10 | D1 | 18 | D1-18 | B+S+4 | G | 9 | A,B,C,D | G-9/A,B,C,D | 148.2 | Stilt slab casting work is in progress
11 | D1 | 19 | D1-19 | B+S+4 | G | 10 | A,B,C,D | G-10/A,B,C,D | 148.2 | Stilt slab casting work is in progress
12 | D1 | 20 | D1-20 | B+S+4 | G | 11 | A,B,C,D | G-11/A,B,C,D | 148.2 | Stilt slab casting work is in progress
13 | D1 | 21 | D1-21 | B+S+4 | G | 12 | A,B,C,D | G-12/A,B,C,D | 148.2 | Stilt slab casting work is in progress
14 | D6 | 1 | D6-1 | B+S+4 | G | 13 | A,B,C,D | G-13/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
15 | D6 | 2 | D6-2 | B+S+4 | G | 14 | A,B,C,D | G-14/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
16 | D6 | 3 | D6-3 | B+S+4 | G | 15 | A,B,C,D | G-15/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
17 | D6 | 4 | D6-4 | B+S+4 | G | 16 | A,B,C,D | G-16/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
18 | D7 | 1 | D7-1 | B+S+4 | G | 17 | A,B,C,D | G-17/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
19 | D7 | 2 | D7-2 | B+S+4 | G | 18 | A,B,C,D | G-18/A,B,C,D | 148.2 | 2nd floor slab casting work is in progress
20 | D7 | 3 | D7-3 | B+S+4 | H | 19 | A,B,C,D | H-19/A,B,C,D | 148.2 | Stilt roof complete
21 | D8 | 20 | D8-20 | B+S+4 | H | 18 | A,B,C,D | H-18/A,B,C,D | 148.2 | Stilt roof complete
22 | D8 | 23 | D8-23 | B+S+4 | H | 17 | A,B,C,D | H-17/A,B,C,D | 148.2 | Stilt roof complete
23 | D8 | 24 | D8-24 | B+S+4 | H | 16 | A,B,C,D | H-16/A,B,C,D | 148.2 | Stilt roof complete
24 | E1 | 22 | E1-22 | B+S+4 | H | 15 | A,B,C,D | H-15/A,B,C,D | 148.2 | Stilt roof complete
25 | NA | 1 | NA-1 | B+S+4 | H | 14 | A,B,C,D | H-14/A,B,C,D | 148.2 | Stilt roof complete
26 | NA | 2 | NA-2 | B+S+4 | H | 13 | A,B,C,D | H-13/A,B,C,D | 148.2 | Basement slab complete
27 | WA | 21 | WA-21 | B+S+4 | H | 12 | A,B,C,D | H-12/A,B,C,D | 148.2 | Basement slab complete
28 | WA | 41 | WA-41 | B+S+4 | H | 11 | A,B,C,D | H-11/A,B,C,D | 148.2 | Basement slab complete
29 | WA | 42 | WA-42 | B+S+4 | H | 10 | A,B,C,D | H-10/A,B,C,D | 148.2 | Basement slab complete
4297.8

## Plots
DETAILS OF PLOTS BASED ON SCRUTINY REPORT
PLOT DETAILS-ALAMEDA, SECTOR-73, GURUGRAM
Sr. No. | Category of Plots | Plot's No. | Plot No. | Plot Size |  | Permissible Ground coverage |  | Ground coverage |  | Pemissible FAR area |  | Provided FAR area |  | BUILT UP AREA |  | NON FAR AREA |  | Stage of Construction
|  |  |  | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. | Sq. mtr. | Sq.ft. |  | 10.7639
1 | A5 | 2 | A5-2 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Excavation completed and further in progress
2 | B5 | 15 | B5-15 | 579.74 | 6240.2634 | 347.84 | 3744.115 | 347.68 | 3742.3928 | 1391.38 | 14976.6752 | 1388.39 | 14944.4911 | 2412.66 | 25969.631 | 1024.27 | 11025.1399 | Excavation completed and further in progress
3 | C1 | 1 | C1-1 | 510.88 | 5499.0612 | 306.53 | 3299.4583 | 302.65 | 3257.6943 | 1226.11 | 13197.7254 | 1211.8 | 13043.694 | 2069.11 | 22271.6931 | 857.31 | 9227.9991 | Raft Foundation in Progress
4 | C2 | 6 | C2-6 | 512 | 5511.1168 | 307.2 | 3306.6701 | 304.86 | 3281.4826 | 1228.8 | 13226.6803 | 1220.68 | 13139.2775 | 2133.98 | 22969.9473 | 913.3 | 9830.6699 | Excavation completed and further in progress
5 | C2 | 9 | C2-9 | 512 | 5511.1168 | 307.2 | 3306.6701 | 305.26 | 3285.7881 | 1228.8 | 13226.6803 | 1222.24 | 13156.0691 | 2143.48 | 23072.2044 | 921.24 | 9916.1352 | Excavation completed and further in progress
6 | C3 | 8 | C3-8 | 512 | 5511.1168 | 307.2 | 3306.6701 | 304.86 | 3281.4826 | 1228.8 | 13226.6803 | 1220.64 | 13138.8469 | 2133.98 | 22969.9473 | 913.34 | 9831.1004 | Excavation completed and further in progress
7 | C8 | 15 | C8-15 | 210.88 | 2269.8912 | 139.18 | 1498.1196 | 132.63 | 1427.6161 | 556.73 | 5992.586 | 554.53 | 5968.9055 | 815.38 | 8776.6688 | 260.85 | 2807.7633 | Excavation completed and further in progress
8 | C8A | 20 | C8A-20 | 187.89 | 2022.4292 | 124.01 | 1334.8312 | 118.34 | 1273.7999 | 496.03 | 5339.2173 | 495.74 | 5336.0958 | 728.97 | 7846.5602 | 233.23 | 2510.4644 | Excavation completed and further in progress
9 | C8A | 33 | C8A-33 | 196.88 | 2119.1966 | 129.94 | 1398.6612 | 124.9 | 1344.4111 | 519.77 | 5594.7523 | 519.07 | 5587.2176 | 770.18 | 8290.1405 | 251.11 | 2702.9229 | Excavation completed and further in progress
10 | D1 | 18 | D1-18 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Raft Foundation complete
11 | D1 | 19 | D1-19 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Raft Foundation in Progress
12 | D1 | 20 | D1-20 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Raft Foundation in Progress
13 | D1 | 21 | D1-21 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Raft Foundation complete
14 | D6 | 1 | D6-1 | 391.5 | 4214.0669 | 234.9 | 2528.4401 | 234.62 | 2525.4262 | 939.6 | 10113.7604 | 936.7 | 10082.5451 | 1696.24 | 18258.1577 | 759.54 | 8175.6126 | Raft Foundation complete
15 | D6 | 2 | D6-2 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Raft Foundation complete
16 | D6 | 3 | D6-3 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Raft Foundation complete
17 | D6 | 4 | D6-4 | 386.25 | 4157.5564 | 231.75 | 2494.5338 | 228.98 | 2464.7178 | 927 | 9978.1353 | 923.94 | 9945.1978 | 1419.17 | 15275.804 | 495.23 | 5330.6062 | Raft Foundation complete
18 | D7 | 1 | D7-1 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Basement Slab work in Progress
19 | D7 | 2 | D7-2 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Basement Slab Completed
20 | D7 | 3 | D7-3 | 450 | 4843.755 | 270 | 2906.253 | 266.46 | 2868.1488 | 1080 | 11625.012 | 1079.04 | 11614.6787 | 1802.3 | 19399.777 | 723.26 | 7785.0983 | Basement Slab Completed
21 | D8 | 20 | D8-20 | 245.75 | 2645.2284 | 162.2 | 1745.9046 | 155.27 | 1671.3108 | 648.78 | 6983.403 | 635.75 | 6843.1494 | 1093.41 | 11769.3559 | 457.66 | 4926.2065 | Not6 yet started
22 | D8 | 23 | D8-23 | 256.08 | 2756.4195 | 153.65 | 1653.8732 | 150.21 | 1616.8454 | 614.59 | 6615.3853 | 614.22 | 6611.4027 | 1060.45 | 11414.5778 | 446.23 | 4803.1751 | Raft Completed
23 | D8 | 24 | D8-24 | 256.04 | 2755.989 | 153.65 | 1653.8732 | 150.21 | 1616.8454 | 614.5 | 6614.4165 | 614.22 | 6611.4027 | 1060.45 | 11414.5778 | 446.23 | 4803.1751 | Raft Completed
24 | E1 | 22 | E1-22 | 157.55 | 1695.8524 | 103.98 | 1119.2303 | 99.07 | 1066.3796 | 415.93 | 4477.0289 | 414.7 | 4463.7893 | 614.26 | 6611.8332 | 199.56 | 2148.0439 | Raft Completed and retaining wall work in Progress
25 | NA | 1 | NA-1 | 252.85 | 2721.6521 | 151.71 | 1632.9913 | 146.33 | 1575.0815 | 606.84 | 6531.9651 | 601.36 | 6472.9789 | 1074.56 | 11566.4564 | 473.2 | 5093.4775 | PCC base for Raft completed Steel binding in Progress
26 | NA | 2 | NA-2 | 191.64 | 2062.7938 | 126.48 | 1361.4181 | 117.92 | 1269.2791 | 505.93 | 5445.7799 | 501.02 | 5392.9292 | 738.6 | 7950.2165 | 237.58 | 2557.2874 | PCC base for Raft completed Steel binding in Progress
27 | WA | 21 | WA-21 | 466.87 | 5025.342 | 280.12 | 3015.1837 | 271.74 | 2924.9822 | 1120.48 | 12060.7347 | 1105.53 | 11899.8144 | 1836.37 | 19766.503 | 730.84 | 7866.6887 | Excavation completed and further in progress
28 | WA | 41 | WA-41 | 457.35 | 4922.8697 | 274.41 | 2953.7218 | 270.21 | 2908.5134 | 1097.64 | 11814.8872 | 1097.11 | 11809.1823 | 1827.19 | 19667.6904 | 730.08 | 7858.5081 | Raft Completed
29 | WA | 42 | WA-42 | 458.85 | 4939.0155 | 275.31 | 2963.4093 | 270.21 | 2908.5134 | 1101.24 | 11853.6372 | 1099.41 | 11833.9393 | 1827.19 | 19667.6904 | 727.78 | 7833.7511 | Raft Completed
TOTAL |  |  |  | 11243 | 121018.5277 | 6817.26 | 73380.3049 | 6700.55 | 72124.0501 | 27268.95 | 293520.2509 | 27167.45 | 292427.7151 | 45478.63 | 489527.4255 | 18311.18 | 197099.7104
[5 empty] | 1 | Total Plots Area | [7 empty] | 11243 |  | Sq. mtr.
[5 empty] | 2 | Total Ground Coverage |  |  |  | Permissible |  |  |  | 6817.26 |  | Sq. mtr.
[10 empty] | Proposed |  |  |  | 6700.55 |  | Sq. mtr.
[5 empty] | 3 | Total FAR |  |  |  | Permissible |  |  |  | 27268.95 |  | Sq. mtr.
[10 empty] | Proposed |  |  |  | 27167.45 |  | Sq. mtr.
[5 empty] | 4 | Total NON FAR |  |  |  | Proposed |  |  |  | 18311.18 |  | Sq. mtr.

## Total Plots
Break-up of Plots of the whole project
S. No. | Category | Plot's No. | Total No. of Plots | Plot Size |  | Total Area of Plots
|  |  |  | Sq. mtr. | Sq. yds. | Sq. mtr. | Sq. yds.
1 | A | A-1 to A-118 | 118 | 148.2 | 177.2472 | 17487.6 | 20915.1696
2 | B | B-1 to B-114 | 114 | 140.4 | 167.9184 | 16005.6 | 19142.6976
3 | C | C-1 to C-16 | 16 | 105.225 | 125.8491 | 1683.6 | 2013.5856
4 | D | D-1 to D-97 | 97 | 107.813 | 128.9443 | 10457.861 | 12507.6018
5 | E | E-1 to E-6 | 6 | 100 | 119.6 | 600 | 717.6 | 100.506
6 | P1 | P-1 | 1 | 140.445 | 167.9722 | 140.445 | 167.9722 | 2.425
7 | P2 | P-2 | 1 | 114.13 | 136.4995 | 114.13 | 136.4995 | 7.006
8 | P3 | P-3 | 1 | 85.649 | 102.4362 | 85.649 | 102.4362 | 3.9
9 | P4 | P-4 | 1 | 147.987 | 176.9925 | 147.987 | 176.9925 | 113.837
10 | P5 | P-5 | 1 | 119.465 | 142.8801 | 119.465 | 142.8801
11 | P6 | P-6 | 1 | 124.71 | 149.1532 | 124.71 | 149.1532
12 | P7 | P-7 | 1 | 94.71 | 113.2732 | 94.71 | 113.2732
13 | P8 | P-8 | 1 | 124.3 | 148.6628 | 124.3 | 148.6628
14 | P9 | P-9 | 1 | 142.469 | 170.3929 | 142.469 | 170.3929
15 | P10 | P-10 | 1 | 81.463 | 97.4297 | 81.463 | 97.4297
16 | P11 | P-11 | 1 | 90.54 | 108.2858 | 90.54 | 108.2858
|  |  | 362 |  |  | 47500.529 | 56810.6327

## Sheet3
Break up of Fair Market Value of Independent Floor
Sr. No. | Category | No. of Plots | No. of Units | Block | No. of Plots | No. of Units | Unit Type | Carpet Area | Saleable Area | Adopted Market Rate per sq ft on Super Area |  | Fair Market Value (FMV) of Independent Floor |  | Average Market Value of Independent Floor for Calculation Purpose | Prospective Fair Market Value of Project for Calculation Purpose
| As per Approved Layout Plan |  |  | As per Sales
[8 empty] | Sq. ft. | Sq. ft. | Min (In INR) | Max (In INR) | Min (In INR) | Max (In INR) | (In INR) | (In INR)
1 | A | 118 | 472 | G | 18 | 72 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1290960000 | 117360
|  |  |  | H | 19 | 76 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1362680000 | 123880
|  |  |  | D | 11 | 44 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 788920000 | 71720
|  |  |  | C | 15 | 60 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1075800000 | 97800
|  |  |  | B | 15 | 60 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 1075800000 | 97800
|  |  |  | I | 40 | 160 | 3 BHK | 855.85 | 1630 | 10500 | 11500 | 17115000 | 18745000 | 17930000 | 2868800000 | 260800
2 | B | 114 | 456 | H | 10 | 40 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 682000000 | 62000
|  |  |  | G | 11 | 44 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 750200000 | 68200
|  |  |  | F | 29 | 116 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 1977800000 | 179800
|  |  |  | E | 29 | 116 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 1977800000 | 179800
|  |  |  | A | 35 | 140 | 3 BHK | 801.49 | 1550 | 10500 | 11500 | 16275000 | 17825000 | 17050000 | 2387000000 | 217000
3 | C | 12 | 48 | M | 4 | 16 | 2.5 BHK | 603.54 | 1120 | 10500 | 11500 | 11760000 | 12880000 | 12320000 | 197120000 | 17920
|  |  |  | L | 4 | 16 | 2.5 BHK | 603.54 | 1120 | 10500 | 11500 | 11760000 | 12880000 | 12320000 | 197120000 | 17920
|  |  |  | K | 4 | 16 | 2.5 BHK | 603.54 | 1120 | 10500 | 11500 | 11760000 | 12880000 | 12320000 | 197120000 | 17920
4 | D | 83 | 332 | M | 14 | 56 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 708400000 | 64400
|  |  |  | L | 28 | 112 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 1416800000 | 128800
|  |  |  | K | 28 | 112 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 1416800000 | 128800
|  |  |  | J | 13 | 52 | 2.5 BHK | 621.73 | 1150 | 10500 | 11500 | 12075000 | 13225000 | 12650000 | 657800000 | 59800
|  | 327 | 1308 | [11 empty] | 21028920000 | 1911720

## Sanctioned
Area Details as per Sanctioned building plans under self certification scheme
Smartworld Orchard
[5 empty] | GROUND COVERAGE |  |  |  | FAR / FSI |  |  |  | NON FAR
Sr. No. | Plot Type |  | No. of Plots | Plot Size | Permissible |  | Provided |  | Permissible |  | Provided |  | Stilt | Basement | Stair | Total
|  |  |  | (sq.mtr) | (sq.mtr) | %age | (sq.mtr) | %age | (sq.mtr) | %age | (sq.mtr) | %age | (sq.mtr) | (sq.mtr) | (sq.mtr) | (sq.mtr)
1 | A | Left Side | 60 | 148.2 | 97.812 | 66% | 97.802 | 65.99% | 391.248 | 264% | 356.3 | 240.4% | 97.802 | 128.7 | 31.788 | 258.29
2 | A | Right Side | 58 | 148.2 | 97.812 | 66% | 97.802 | 65.99% | 391.248 | 264% | 356.3 | 240.4% | 97.802 | 128.7 | 31.788 | 258.29
3 | B | Left Side | 56 | 140.4 | 92.664 | 66% | 92.649 | 65.99% | 370.656 | 264% | 335.728 | 239.1% | 92.649 | 120.9 | 31.788 | 245.337
4 | B | Right Side | 58 | 140.4 | 92.664 | 66% | 92.649 | 65.99% | 370.656 | 264% | 335.728 | 239.1% | 92.649 | 120.9 | 31.788 | 245.337
5 | C | Left Side | 6 | 105.225 | 69.449 | 66% | 69.42 | 65.97% | 277.794 | 264% | 247.296 | 235% | 69.42 | 86.925 | 30.38 | 186.725
6 | C | Right Side | 6 | 105.225 | 69.449 | 66% | 69.42 | 65.97% | 277.794 | 264% | 247.296 | 235% | 69.42 | 86.925 | 30.38 | 186.725
7 | D | Left Side | 41 | 107.8125 | 71.156 | 66% | 71.146 | 65.99% | 284.625 | 264% | 254.204 | 235.8% | 71.146 | 89.063 | 30.38 | 190.589
8 | D | Right Side | 42 | 107.8125 | 71.156 | 66% | 71.146 | 65.99% | 284.625 | 264% | 254.204 | 235.8% | 71.146 | 89.063 | 30.38 | 190.589
327
1 | Total Plots Area | [7 empty] | 43704.338 |  | Sq. mtr.
2 | Total Ground Coverage |  |  |  | Permissible |  |  |  | 28844.848 |  | Sq. mtr.
[5 empty] | Proposed |  |  |  | 28840.78 |  | Sq. mtr.
3 | Total FAR |  |  |  | Permissible |  |  |  | 115379.451 |  | Sq. mtr.
[5 empty] | Proposed |  |  |  | 104382.876 |  | Sq. mtr.
4 | Total NON FAR |  |  |  | Proposed |  |  |  | 76506.225 |  | Sq. mtr.