## Physical Progress as per SP
COST OF BUILDINGS AND OTHER CIVIL STRUCTURES
Sr. No. | DESCRIPTION | Area (in sq.ft.) | Building Cost | March Building Progress (in Percentage) | March Foundation Progress (in Percentage) | Foundation expenditure
1 | Main Factory Building
1.1 | (Basement Floor) | 5088 | 1090 | 100% | 100% | #REF!
1.2 | (Ground Floor) |  | 100 | 100% | 100% | #REF!
1.3 | (First Floor) |  |  | 100% | 100%
1.4 | (Second Floor) |  | 720 | 100% | 100% | #REF!
1.5 | (Basement Floor) | 10605 | 2415 | 100% | 100% | #REF!
1.6 | (Ground Floor) |  | 185 | 100% | 100% | #REF!
1.7 | (First Floor) |  | 770 | 100% | 100% | #REF!
1.8 | (Second Floor) |  | 60 | 100% | 100% | #REF!
1.9 | (Basement Floor) |  |  | 100% | 100%
2 | (Ground Floor) |  |  | 100% | 100%
2.1 | (First Floor) |  |  | 100% | 100%
2.2 | (Second Floor) |  |  | 100% | 100%
2.3 | (Basement Floor) |  |  | 100% | 100%
2.4 | (Ground Floor) |  |  | 100% | 100%
2.5 | (First Floor) |  |  | 100% | 100%
2.6 | (Second Floor) |  |  | 100% | 100%
2.7 | Passage (Basement floor) | 320 |  | 100% | 100%
2.8 | Passage (First floor) | 320 |  | 100% | 100%
2.9 | Passage (Second floor) | 320 |  | 100% | 100%
| SUB TOTAL (1.0) |  | 8565 | 100% | 100% | #REF!
2 | Other Structures
2.1 | Section-6 |  | 350 | 100% | 100% | 95
2.2 | Section-7 |  | 155 | 100% | 100% | #REF!
2.3 | Section-8 |  | 185 | 100% | 100% | #REF!
2.4 | Section-9 |  | 340 | 100% | 100% | #REF!
2.5 | Section-10 |  | 630 | 100% | 100% | #REF!
2.6 | Section-11 |  | 2175 | 100% | 100% | #REF!
2.7 | Section-12 |  | 0 | 100% | 100% | #REF! | cement silo are 4 in No. but aqs per the Holtec Clinker Silo are 4 in No. and previous report is also reported as clinker silo to be 4
2.8 | Section-13 |  | 295 | 100% | 100% | #REF!
2.9 | Section-14 |  | 290 | 100% | 100% | #REF!
2.1 | Section-15 |  | 340 | 100% | 100% | #REF!
2.11 | Section-16 |  | 400 | 100% | 100% | #REF!
2.12 | Section-17 |  | 1385 | 100% | 100% | #REF!
2.13 | Section-17 |  |  | 100% | 100%
| SUB TOTAL (2.0) |  | 6945 |  |  | #REF!
3 | Auxiliary Services
| SUB TOTAL (4.0) |  | 455 | #REF! | 100% | #REF!
100%
| SUB TOTAL (5.0) |  | 292 | 0% | 100% | #REF!
100%
| SUB TOTAL (7.0) |  | 6405 | #REF! | 100% | #REF!
100%
8 | Total (1.0+2.0+3.0+4.0+5.0+7.0) |  | #REF! | - | 100% | #REF!
9 | Deep foundations cost-provisioning (Indicative 10% lumpsum provisioning considered as Geotechnical investigations at proposed plant site are at preliminary level only) |  | 3040 | - | 100% | #REF!
10 | Indicative GST component on Civil works (average approx.18% of total civil cost considered for TEFR formulation purpose) |  | 5470 | - | 100% | #REF!
11 | Total Civil Works Cost (7.0+8.0+9.0) |  | #REF! | - | 100% | #REF!
| Grand Total |  | #REF! |  | 100%
100%
|  |  | #REF! | #REF! | 100%
|  |  | #REF! |  | 100%
|  |  | #REF! |  | 100%
#REF!

## 1
S.NO. | Machine Name | DESCRIPTION | SUPPLIER NAME | DATE | INVOICE NO. | QUANTITY | PRICE | FINAL PRICE (Including freight) | Term Loan Payment | Current Account payment
1 | Main Machine | Automatic Rotary Table Polyurethane Injection Moulding Machine | Desma Schuhmaschinen Gmbh | 2020-11-10 | 9014016 | 1 | 65232000 | 65232000 | 76973760 | 11741760
2 | compressor Room | Screw Air Comp. | AS Equipment Pvt. Ltd. | 2021-04-22 | AU/RCD/001/21-22 | 1 | 853647.4 | 1214348.62 |  | #REF!
3 |  | Air Dryers | AS Equipment Pvt. Ltd. | 2021-04-22 | AU/RCD/001/21-22 | 1 | 232578
4 |  | VA00040 1000 12.5 | AS Equipment Pvt. Ltd. | 2021-04-22 | AU/RCD/001/21-22 | 1 | 89154.9
5 |  | Pre-Filter Assy. | AS Equipment Pvt. Ltd. | 2021-04-22 | AU/RCD/001/21-22 | 1 | 24808.32
6 | Transformer | Transformer 500 KVA, 11/0.433 KV, 3 phase | Marson's Electrical Industries | 2021-05-04 | MEI/2021-22/025 | 1 | 1132800 | 1132800
7 | D.G. SET | Diesel Generating Set 250 KVA / 200 KW | Jakson Limited | 2021-03-31 | 1P0520101251 | 1 | 1599999.76 | 1599999.76
8 | In use | Beem Cutter Travelling Head Machine | Ningbo Mama papa Export & Import Co. Ltd. | 2021-06-03 | MP2021DL15 | 2 | 2762401.95 | 2762401.95
9 | Not in use | Clicking Machine (For Cutting) | Ningbo Mama papa Export & Import Co. Ltd. | 2021-06-03 | MP2021DL15 | 6
10 | UPS | Uninterrupted Power Supply System Rating 50 KVA | Autometers Alliance Ltd. | 2021-03-04 | 20201836 | 1 | 507400 | 507400
11 | Fire Equipment | Accessories & Fixing sprinkler | Vijay Enterprises | 2021-03-16 | 214 | 1066 | 665343 | 665343
12 | D.G. SET Panel | DG Distribution Board Panel | Zeniya Electech Pvt. Ltd. | 2021-04-09 | ZG3192 | 1 | 668824 | 889664
13 | Panel | Distribution Board Panel Ground & First Floor | Zeniya Electech Pvt. Ltd. | 2021-04-09 | ZG3192 | 2 | 211692
14 | Panel | Distribution Board Panel Basement Floor | Zeniya Electech Pvt. Ltd. | 2021-04-09 | ZG3193 | 1 | 118590 | 232574
15 | Panel | Distribution Board Panel Second Floor | Zeniya Electech Pvt. Ltd. | 2021-04-09 | ZG3193 | 1 | 109032
TOTAL | [7 empty] | 74236531.33
[7 empty] | Local | 7504042.38
[7 empty] | Imported | 67994401.95
| lift | Total Composite Works contract value | Omega Elevators | 2021-09-01 | UP/2122/00096 | 1 | 1261913 | 1261913

## Machineries
S.NO. | Machine Name | DESCRIPTION | SUPPLIER NAME | DATE | QUANTITY | PRICE | FINAL PRICE (Including freight) | Term Loan Payment | Current Account payment
1 | Main Machine | Automatic Rotary Table Polyurethane Injection Moulding Machine | Desma Schuhmaschinen Gmbh | 2020-11-10 | 1 | 65232000 | 65232000 | 76973760 | 11741760
2 | compressor Room | Screw Air Comp. | AS Equipment Pvt. Ltd. | 2021-04-22 | 1 | 853647.4 | 1214348.62 |  | #REF!
3 |  | Air Dryers | AS Equipment Pvt. Ltd. | 2021-04-22 | 1 | 232578
4 |  | VA00040 1000 12.5 | AS Equipment Pvt. Ltd. | 2021-04-22 | 1 | 89154.9
5 |  | Pre-Filter Assy. | AS Equipment Pvt. Ltd. | 2021-04-22 | 1 | 24808.32
6 | Transformer | Transformer 500 KVA, 11/0.433 KV, 3 phase | Marson's Electrical Industries | 2021-05-04 | 1 | 1132800 | 1132800
7 | D.G. SET | Diesel Generating Set 250 KVA / 200 KW | Jakson Limited | 2021-03-31 | 1 | 1599999.76 | 1599999.76
8 | In use | Beem Cutter Travelling Head Machine | Ningbo Mama papa Export & Import Co. Ltd. | 2021-06-03 | 2 | 2762401.95 | 2762401.95
9 | Not in use | Clicking Machine (For Cutting) | Ningbo Mama papa Export & Import Co. Ltd. | 2021-06-03 | 6
10 | UPS | Uninterrupted Power Supply System Rating 50 KVA | Autometers Alliance Ltd. | 2021-03-04 | 1 | 507400 | 507400
11 | Fire Equipment | Accessories & Fixing sprinkler | Vijay Enterprises | 2021-03-16 | 1066 | 665343 | 665343
12 | D.G. SET Panel | DG Distribution Board Panel | Zeniya Electech Pvt. Ltd. | 2021-04-09 | 1 | 668824 | 889664
13 | Panel | Distribution Board Panel Ground & First Floor | Zeniya Electech Pvt. Ltd. | 2021-04-09 | 2 | 211692
14 | Panel | Distribution Board Panel Basement Floor | Zeniya Electech Pvt. Ltd. | 2021-04-09 | 1 | 118590 | 232574
15 | Panel | Distribution Board Panel Second Floor | Zeniya Electech Pvt. Ltd. | 2021-04-09 | 1 | 109032
TOTAL | [6 empty] | 74236531.33
[6 empty] | Local | 7504042.38
[6 empty] | Imported | 67994401.95
| lift | Total Composite Works contract value | Omega Elevators | 2021-09-01 | 1 | 1261913 | 1261913

## Physical Progress
S.No. | Particular | March Building Progress (in Percentage) | March Foundation Progress (in Percentage) | ~Area (in sq.ft.) | Rate | Amount | Usage
Main Factory Building-1
1 | Basement | 100 | 100 | 13056 | 1200 | 15667200 | Consist of Working Hall, Warehouse & Room
2 | Ground floor | 100 | 100 | 13056 | 1200 | 15667200 | Consist of Cutting Department, lasting Room, Die Store, Toe Cap Store, Preparation department, Bottom Store, Office area, Toilets
3 | First Floor | 100 | 100 | 13056 | 1200 | 15667200 | Consist of Fitter Store, Fitter Department, Consumable Store, Cabin, toilet
4 | Second floor | 100 | 100 | 13056 | 1200 | 15667200 | Consist of Hall and store
| Sub-Total | 100 | 100 | 52224 |  | 62668800
Main Factory Building-2
5 | Basement | 100 | 100 | 5088 | 1200 | 6105600 | Consist of Working Hall
6 | Ground floor | 100 | 100 | 5088 | 1200 | 6105600 | Consist of Lather Store, D.G. Room, Compressor Room
7 | First Floor | 100 | 100 | 5088 | 1200 | 6105600 | Consist of Working Hall, Cateen, Kitchen
8 | Second floor | 100 | 100 | 5088 | 1200 | 6105600 | used as Store
| Sub-Total | 100 | 100 | 20352 |  | 24422400
Passage
9 | Basement | 100 | 100 | 320 | 800 | 256000 | Connecting Passage between the two Main Factory Building
10 | First Floor | 100 | 100 | 320 | 800 | 256000 | Connecting Passage between the two Main Factory Building
11 | Second floor | 100 | 100 | 320 | 800 | 256000 | Connecting Passage between the two Main Factory Building
| Sub-Total | 100 | 100 | 960 |  | 768000
Other Structures
12 | Section-6/Adhesive store | 100 | 100 | 150 | 900 | 135000 | Adhesive store
13 | Section-7/Store | 100 | 100 | 300 | 900 | 270000 | Store
14 | Section-8/Toilet | 100 | 100 | 70 | 900 | 63000 | Toilet
15 | Section-9/Toilet | 100 | 100 | 40 | 900 | 36000 | Toilet
16 | Section-10/First Aid | 100 | 100 | 80 | 900 | 72000 | First Aid
17 | Section-11/H.R. Cabin | 100 | 100 | 150 | 900 | 135000 | H.R. Cabin
18 | Section-12/Waiting room | 100 | 100 | 120 | 900 | 108000 | Waiting room
19 | Section-13/Security Room | 100 | 100 | 120 | 900 | 108000 | Security Room
20 | Section-14/Store | 100 | 100 | 110 | 900 | 99000 | Store
21 | Section-15/Store | 100 | 100 | 110 | 900 | 99000 | Store
22 | Section-16/Store | 100 | 100 | 110 | 900 | 99000 | Store
23 | Section-17/Store | 100 | 100 | 180 | 900 | 162000 | Store
| Sub-Total | 100 | 100 | 1540 |  | 1386000
| Total | 100 | 100 | 75076 |  | 89245200 |  | 80 | 6006080 |  | 0.068096
[9 empty] | 8.82 | 10000000 | 88200000

## Schedule
Event | Target Timeline
Company Incorporation | Existing Company
Purchase of Land | Already Acquired
Construction Start Date | 2020-02-01
Construction end Date | 2020-12-01
Placing orders for machineries | 2020-12-01
Arrival of Machineries | 2021-01-01
Installation of Machineries | 2021-02-01
Trial Runs | 2021-03-01
Commercial Production | 2021-04-01

## means of finance
As per Techno Economic Viability Report
Buildings | 8.79
Plant and Machinery | 10.11
Furniture and fixtures including industrial Electrification and lift | 0.8
Contingency and spares etc. | 0.99
Total Project Cost | 20.69
Promoter’s Contribution (Equity) | 7.19
Term Loan (Debt) | 13.5

## Proposed machineries
Sr. No. | Machine Name | Supplier Name
Cutting Department
1 | Cutting machine | Ares
2 | Material Cutting Machine | Ares
3 | Heavy Duty Beam Press | Ningbo Mama Papa
Preparation Department
4 | Skivining machine | Topson
5 | Cloth Pasting | SIECK
6 | Stamping Machine | Western
7 | Splitting Machine | SIECK
8 | CE Label Pasting machine | Ningbo Mama Papa
9 | Embossing Machine | Sangeetha Ent.
Socks department
10 | 31k Machine | Topson Ent.
11 | 2 KG 2AG Machine | Hind Ent.
12 | Post Bed Single Needle | Iyun Shuaima
13 | Post Bed Double Needle | Iyun Shuaima
14 | Zig Zag Machine | Hind Ent.
15 | Thread Burning | Alra Machine Tools
16 | Glue Spray | Gaitonde
Eyelet
17 | Automatic O-ring | TMC
18 | Eyeletting | TMC
19 | Hook machine | RS Machine Tools
20 | Plastic HooK sps | TMC
Strobel Department
21 | Cursher Moulding Machine | Yili
22 | Strobel Machine | Global
23 | Strobel Machine Heavy Duty | SIECK
Cement Lasting Line
24 | Lasting Conveyor | Kalra Machine Tools
25 | Toe lasting M/c | TMC
26 | Mulling machine | Kalra Machine Tools
27 | Heater Sealer | Kalra Machine Tools
28 | Buffing machine | Kalra Machine Tools
29 | Plane Press | Kalra Machine Tools
30 | Heat Activator | Kalra Machine Tools
31 | Lasting machine | joro Tech
32 | Toe Filling machine | Pioneer Tech
33 | Double Pad sole Press machine | Kalra Machine Tools
34 | Spray Booth | Kalra Machine Tools
35 | Reactivating Plane for soles | TMC
Injection Department
36 | Desma Machine
37 | Chiller | Kalra Machine Tools
38 | Trimming machine | TMC
39 | Sole Buffing Machine | Kalra Machine Tools
Finishing Department
40 | Finishing Conveyor | Kalra Machine Tools
41 | Spray Booth | Kalra Machine Tools
42 | Brushing Machine Double side | Pioneer
Utilities
43 | Generator | Jakson
44 | Compressor | As equipment Private Limited
45 | Air Dryer | As equipment Private Limited
Moulds
46 | PU Mould Double Density | Ningbo Mama Papa
47 | Turning Head | Ningbo Mama Papa
48 | TPU Mould | Ningbo Mama Papa
49 | TPU Outsole Bottom | Ningbo Mama Papa
50 | Transformer | Mekon
51 | Lift
52 | Furniture+Fixtures & Fitting