## Cost to Complete
SUPREME SUYOG FUNICULAR ROPEWAYS PVT. LTD.
HAJI MALANG FUNICULAR RAIL PROJECT
Balance Cost for Completion of Work
Sr. No. | Item | Unit | Qty | Rate | Amount | Balance work in % | Balance work Cost in Rs | Minimum Fund to make the Project Functional (without compliting many Items 100%)
2 | Lower Station
a | Structure | Sqft | 52000 | 850 | 44200000 | 5% | 2210000 | 2210000
b | Finishing Item | Sqft | 52000 | 853.7829 | 44396709 | 40% | 17758683.6 | 4439670.9
3 | Upper Station
a | Structure | Sqft | 25000 | 1500 | 37500000 | 15% | 5625000 | 5625000
b | Finishing Item | Sqft | 25000 | 1000 | 25000000 | 100% | 25000000 | 6250000
| Total | [5 empty] | 50593683.6

## Feb 15 (hidden)
SUPREME INFRASTRUCTURE INDIA LTD.
HAJI MALANG FUNICULAR RAIL RAIL PROJECT
CASH FLOW FOR COMPLETION OF HAJI MALANG PROJECT BY Feb 2015
Sr. No. | Item | Unit | Qty | Rate | Amount | Balance work in % | Balance work Cost in RS | Month wise cash flow |  |  |  | Total
[8 empty] | oct | nov | dec | jan
1 | Yashita Works | No | 1 | 295000000 | 295000000 | 50% | 147500000 | 36875000 | 36875000 | 36875000 | 36875000 | 147500000
2 | Lower Station | [6 empty] | 0 | 0 | 0 | 0 | 0
a | Structure | Sqft | 52000 | 850 | 44200000 | 55% | 24310000 | 6077500 | 6077500 | 6077500 | 6077500 | 24310000
b | Finishing Item | Sqft | 52000 | 850 | 44200000 | 95% | 41990000 | 10497500 | 10497500 | 10497500 | 10497500 | 41990000
3 | Upper Station | [6 empty] | 0 | 0 | 0 | 0 | 0
a | Structure | Sqft | 32500 | 1000 | 32500000 | 60% | 19500000 | 4875000 | 4875000 | 4875000 | 4875000 | 19500000
b | Finishing Item | Sqft | 32500 | 1000 | 32500000 | 100% | 32500000 | 8125000 | 8125000 | 8125000 | 8125000 | 32500000
c | Logistic | MT | 3500 | 10000 | 35000000 | 50% | 17500000 | 4375000 | 4375000 | 4375000 | 4375000 | 17500000
4 | Water Tank | Ltrs | 300000 | 25 | 7500000 | 10% | 750000 | 750000 | 0 | 0 | 0 | 750000
5 | Staff Quarters | Sqft | 4000 | 1000 | 4000000 | 80% | 3200000 | 800000 | 800000 | 800000 | 800000 | 3200000
6 | Parking lots | Sqm | 6500 | 1200 | 7800000 | 50% | 3900000 | 1950000 | 1950000 | 0 | 0 | 3900000
7 | Roads | Sqm | 3000 | 2500 | 7500000 | 50% | 3750000 | 1875000 | 1875000 | 0 | 0 | 3750000
8 | Infra Work (R/W. Inner & Outer) | Cum | 2500 | 5000 | 12500000 | 5% | 625000 | 625000 | 0 | 0 | 0 | 625000
9 | STP | No | 1 | 2500000 | 2500000 | 100% | 2500000 | 0 | 0 | 1250000 | 1250000 | 2500000
10 | Laying of Seawage Line from U/S to STP at L/S along the Track | RMT | 1400 | 1500 | 2100000 | 100% | 2100000 | 525000 | 525000 | 525000 | 525000 | 2100000
11 | Public Toilet | No | 2 | 500000 | 1000000 | 100% | 1000000 | 0 | 0 | 500000 | 500000 | 1000000
12 | Toll Booth | No | 2 | 1000000 | 2000000 | 100% | 2000000 | 0 | 666666.6667 | 666666.6667 | 666666.6667 | 2000000
13 | Electrification Outer | No | 1 | 5000000 | 5000000 | 100% | 5000000 | 1250000 | 1250000 | 1250000 | 1250000 | 5000000
14 | Drain | RMT | 700 | 3000 | 2100000 | 50% | 1050000 | 262500 | 262500 | 262500 | 262500 | 1050000
15 | Land Acquisition Pvt. | EKAR | 3.1 | 5500000 | 17050000 | 50% | 8525000 | 8525000 | 0 | 0 | 0 | 8525000
16 | Land Acquisition Forest | HECT | 4.97 | 3600000 | 17892000 | 0% | 0 | 0 | 0 | 0 | 0 | 0
17 | Consultants, BP,Design, Salary etc. Misc.all other expenses | Month | 30 | 1400000 | 42000000 | 15% | 6300000 | 1575000 | 1575000 | 1575000 | 1575000 | 6300000
|  |  |  | Total Cost | 614342000 | BALANCE Cost in RS. | 324000000 | 88962500 | 79729166.6667 | 77654166.6667 | 77654166.6667 | 324000000
[6 empty] | BALANCE Cost in Lacs. | 3240 | 889.625 | 797.2917 | 776.5417 | 776.5417 | 3240
[6 empty] | BALANCE Cost in CR per month. | 32.4 | 8.8963 | 7.9729 | 7.7654 | 7.7654 | 32.4

## March 15 (hidden)
SUPREME INFRASTRUCTURE INDIA LTD.
HAJI MALANG FUNICULAR RAIL RAIL PROJECT
CASH FLOW FOR COMPLETION OF HAJI MALANG PROJECT BY March 2015
Sr. No. | Item | Unit | Qty | Rate | Amount | Balance work in % | Balance work Cost in RS | Month wise cash flow |  |  |  |  | Total
[8 empty] | oct | nov | dec | jan | Feb
1 | Yashita Works | No | 1 | 295000000 | 295000000 | 50% | 147500000 | 29500000 | 29500000 | 29500000 | 29500000 | 29500000 | 147500000
2 | Lower Station | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
a | Structure | Sqft | 52000 | 850 | 44200000 | 55% | 24310000 | 4862000 | 4862000 | 4862000 | 4862000 | 4862000 | 24310000
b | Finishing Item | Sqft | 52000 | 850 | 44200000 | 95% | 41990000 | 8398000 | 8398000 | 8398000 | 8398000 | 8398000 | 41990000
3 | Upper Station | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
a | Structure | Sqft | 32500 | 1000 | 32500000 | 60% | 19500000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 19500000
b | Finishing Item | Sqft | 32500 | 1000 | 32500000 | 100% | 32500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 32500000
c | Logistic | MT | 3500 | 10000 | 35000000 | 50% | 17500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 17500000
4 | Water Tank | Ltrs | 300000 | 25 | 7500000 | 10% | 750000 | 750000 | 0 | 0 | 0 | 0 | 750000
5 | Staff Quarters | Sqft | 4000 | 1000 | 4000000 | 80% | 3200000 | 640000 | 640000 | 640000 | 640000 | 640000 | 3200000
6 | Parking lots | Sqm | 6500 | 1200 | 7800000 | 50% | 3900000 | 1300000 | 1300000 | 1300000 | 0 | 0 | 3900000
7 | Roads | Sqm | 3000 | 2500 | 7500000 | 50% | 3750000 | 1250000 | 1250000 | 1250000 | 0 | 0 | 3750000
8 | Infra Work (R/W. Inner & Outer) | Cum | 2500 | 5000 | 12500000 | 5% | 625000 | 312500 | 312500 | 0 | 0 | 0 | 625000
9 | STP | No | 1 | 2500000 | 2500000 | 100% | 2500000 | 0 | 0 | 833333.3333 | 833333.3333 | 833333.3333 | 2500000
10 | Laying of Seawage Line from U/S to STP at L/S along the Track | RMT | 1400 | 1500 | 2100000 | 100% | 2100000 | 420000 | 420000 | 420000 | 420000 | 420000 | 2100000
11 | Public Toilet | No | 2 | 500000 | 1000000 | 100% | 1000000 | 0 | 0 | 333333.3333 | 333333.3333 | 333333.3333 | 1000000
12 | Toll Booth | No | 2 | 1000000 | 2000000 | 100% | 2000000 | 0 | 500000 | 500000 | 500000 | 500000 | 2000000
13 | Electrification Outer | No | 1 | 5000000 | 5000000 | 100% | 5000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
14 | Drain | RMT | 700 | 3000 | 2100000 | 50% | 1050000 | 210000 | 210000 | 210000 | 210000 | 210000 | 1050000
15 | Land Acquisition Pvt. | EKAR | 3.1 | 5500000 | 17050000 | 50% | 8525000 | 8525000 | 0 | 0 | 0 | 0 | 8525000
16 | Land Acquisition Forest | HECT | 4.97 | 3600000 | 17892000 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Consultants, BP,Design, Salary etc. Misc.all other expenses | Month | 30 | 1400000 | 42000000 | 15% | 6300000 | 1260000 | 1260000 | 1260000 | 1260000 | 1260000 | 6300000
|  |  |  | Total Cost | 614342000 | BALANCE Cost in RS. | 324000000 | 72327500 | 63552500 | 64406666.6667 | 61856666.6667 | 61856666.6667 | 324000000
[6 empty] | BALANCE Cost in Lacs. | 3240 | 723.275 | 635.525 | 644.0667 | 618.5667 | 618.5667 | 3240
[6 empty] | BALANCE Cost in CR per month. | 32.4 | 7.2327 | 6.3552 | 6.4407 | 6.1857 | 6.1857 | 32.4

## Apr 15 (hidden)
SUPREME INFRASTRUCTURE INDIA LTD.
HAJI MALANG FUNICULAR RAIL RAIL PROJECT
CASH FLOW FOR COMPLETION OF HAJI MALANG PROJECT BY April 2015
Sr. No. | Item | Unit | Qty | Rate | Amount | Balance work in % | Balance work Cost in RS | Month wise cash flow | [5 empty] | Total
[8 empty] | oct | nov | dec | jan | Feb | Mar
1 | Yashita Works | No | 1 | 295000000 | 295000000 | 50% | 147500000 | 24583333.3333 | 24583333.3333 | 24583333.3333 | 24583333.3333 | 24583333.3333 | 24583333.3333 | 147500000 | 0
2 | Lower Station | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | Structure | Sqft | 52000 | 850 | 44200000 | 55% | 24310000 | 4862000 | 4862000 | 4862000 | 4862000 | 4862000 | 0 | 24310000 | 0
b | Finishing Item | Sqft | 52000 | 850 | 44200000 | 95% | 41990000 | 6998333.3333 | 6998333.3333 | 6998333.3333 | 6998333.3333 | 6998333.3333 | 6998333.3333 | 41990000 | 0
3 | Upper Station | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | Structure | Sqft | 32500 | 1000 | 32500000 | 60% | 19500000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 0 | 19500000 | 0
b | Finishing Item | Sqft | 32500 | 1000 | 32500000 | 100% | 32500000 | 5416666.6667 | 5416666.6667 | 5416666.6667 | 5416666.6667 | 5416666.6667 | 5416666.6667 | 32500000 | 0
c | Logistic | MT | 3500 | 10000 | 35000000 | 50% | 17500000 | 2916666.6667 | 2916666.6667 | 2916666.6667 | 2916666.6667 | 2916666.6667 | 2916666.6667 | 17500000 | 0
4 | Water Tank | Ltrs | 300000 | 25 | 7500000 | 10% | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 750000 | 0
5 | Staff Quarters | Sqft | 4000 | 1000 | 4000000 | 80% | 3200000 | 640000 | 640000 | 640000 | 640000 | 640000 | 0 | 3200000 | 0
6 | Parking lots | Sqm | 6500 | 1200 | 7800000 | 50% | 3900000 | 1300000 | 1300000 | 1300000 | 0 | 0 | 0 | 3900000 | 0
7 | Roads | Sqm | 3000 | 2500 | 7500000 | 50% | 3750000 | 1250000 | 1250000 | 1250000 | 0 | 0 | 0 | 3750000 | 0
8 | Infra Work (R/W. Inner & Outer) | Cum | 2500 | 5000 | 12500000 | 5% | 625000 | 312500 | 312500 | 0 | 0 | 0 | 0 | 625000 | 0
9 | STP | No | 1 | 2500000 | 2500000 | 100% | 2500000 | 0 | 0 | 625000 | 625000 | 625000 | 625000 | 2500000 | 0
10 | Laying of Seawage Line from U/S to STP at L/S along the Track | RMT | 1400 | 1500 | 2100000 | 100% | 2100000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 2100000 | 0
11 | Public Toilet | No | 2 | 500000 | 1000000 | 100% | 1000000 | 0 | 0 | 333333.3333 | 333333.3333 | 333333.3333 | 0 | 1000000 | 0
12 | Toll Booth | No | 2 | 1000000 | 2000000 | 100% | 2000000 | 0 | 500000 | 500000 | 500000 | 500000 | 0 | 2000000 | 0
13 | Electrification Outer | No | 1 | 5000000 | 5000000 | 100% | 5000000 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 5000000 | 0
14 | Drain | RMT | 700 | 3000 | 2100000 | 50% | 1050000 | 210000 | 210000 | 210000 | 210000 | 210000 | 0 | 1050000 | 0
15 | Land Acquisition Pvt. | EKAR | 3.1 | 5500000 | 17050000 | 50% | 8525000 | 8525000 | 0 | 0 | 0 | 0 | 0 | 8525000 | 0
16 | Land Acquisition Forest | HECT | 4.97 | 3600000 | 17892000 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Consultants, BP,Design, Salary etc. Misc.all other expenses | Month | 30 | 1400000 | 42000000 | 15% | 6300000 | 1050000 | 1050000 | 1050000 | 1050000 | 1050000 | 1050000 | 6300000 | 0
|  |  |  | Total Cost | 614342000 | BALANCE Cost in RS. | 324000000 | 63897833.3333 | 55122833.3333 | 55768666.6667 | 53218666.6667 | 53218666.6667 | 42773333.3333 | 324000000 | 0
[6 empty] | BALANCE Cost in Lacs. | 3240 | 638.9783 | 551.2283 | 557.6867 | 532.1867 | 532.1867 | 427.7333 | 3240 | 0
[6 empty] | BALANCE Cost in CR per month. | 32.4 | 6.3898 | 5.5123 | 5.5769 | 5.3219 | 5.3219 | 4.2773 | 32.4 | 0

## Cost to Complete Revised (hidden)
SUPREME SUYOG FUNICULAR ROPEWAYS PVT. LTD.
HAJI MALANG FUNICULAR RAIL PROJECT
COST TO COMPLETION OF HAJI MALANG PROJECT
Sr. No. | Item | Unit | Qty | Rate | Amount | Balance work in % | Balance work Cost in RS | Minimum Fund to make the Project Functional (without compliting many Items 100%) | Remark
201022
1 | Yashita Works( track support,track and electro mech ) | No | 1 | 264690000 | 264690000 | 28% | 74113200 | 74113200 |  | last bill of yashita ref
2 | Lower Station | No | 1 | 11391413 | 11391413 | 100% | 11391413 |  |  |  | 0.71807
3 | Upper Station | No | 1 | 18359727.4 | 18359727.4 | 100% | 18359727.4 |  |  |  | #REF!
4 | Infra Works
a | Staff Quarters / Water Tank | No | 1 | 30569236 | 30569236 | 66% |  | 0
b | Public Toilet | No | 2 | 3120674.5 | 6241349 | 100% | 6241349 | 3120674.5 |  |  |  |  | 0.43478
c | Outer Retaining Wall | No | 1 | 18432866 | 18432866 | 0% | 0 | 0 |  |  |  |  | 43.4783
d | Inner Retaining Wall | No | 1 | 6667040 | 6667040 | 10% | 666704 | 666704 |  |  |  |  | 56.5217
5 | S.T.P. | [8 empty] | Contact to Maruf
a | civil work | No | 1 | 110000 | 110000 | 100% | 110000
b | Mechanical work | No | 1 | 1600000 | 1600000 | 100% | 1600000
6 | Paver BLOCKS(Parking and internal roads ) | Sqm | 9200 | 775 | 7130000 | 30% | 2139000 | 534750 |  | exact bal qty as on today. Put remarks for payment.
7 | Fire Fighting, Plumbing & Sanitory | No | 1 | 37132625 | 37132625 | 100% | 37132625 | 9283156.25 |  | bhave
8 | Mechanical | No | 1 | 2015440 | 2015440 | 100% | 2015440 | 0 |  | 98jj
9 | Electrical Work | No | 1 | 6401683 | 6401683 | 95% | 6081598.85 | 6081598.85 |  | power trackmworkmorder
10 | Furnitur's & Security | No | 1 | Cost to be Decide
Total |  |  |  |  | 410741379.4 |  | 159851057.25 | 93800083.6
Excluding SPV related Payment and taxes