## Phy, Prog. and exp. sheet (hidden)
SUMMARY OF EXPENDITURE ASSESSED BASED ON PHYSICAL PROGRESS
| INTEGRATED UNIT (Amount in Lakh) |  |  | GRINDING UNIT (Amount in Lakh)
Particulars | Construction progress achieved | Expenditure allocated | Expenditure done | Construction progress achieved | Expenditure allocated | Expenditure done
Building and Civil works | 51.24% | 37858 | 19399.7 | 20.37% | 8205 | 1671.57 | 21071.27
Plant and machinery works | 13.62% | 89511 | 12187 | 1.507% | 14930 | 225 | 12412
Total expenditure | 32.43% | 127369 | 31586.7 | 10.94% | 23135 | 1896.57
Total progress Achieved | 21.68%
Total expenditure incurred till date | 334.8327 | Crore

## Detailed Physical Progress IU
PHYSICAL PROGRESS OF STRUCTURES IN THE PROJECT- INTEGRATED UNIT
Sr. No. | DESCRIPTION | Remarks
1 | Main Factory Building | civil | Mechanical
1.1 | Limestone crusher complex (including retaining wall, ramp, stone pitching, etc.) | The limestone crusher unit was in operation at the time of survey and all the civil structure was developed | 1. Grizzle Feeder to be installed was installed 2. Connecting Conveyors were Present at the site at the time of Survey in the previous quarter and is complete now. 3. Surge bin, Primary Screener and Secondary screener were installed 4. 33 Kv transformer was in Place and charged at the site 5. Overall the Limestone Crusher Mechanical progress is about 90% | 95%
1.2 | Correctives & Additive crusher house (including short ramp, pitching, etc.) | work was in Progress |  | 50%
1.3 | Raw mills complex | 1. Raw Mil-1 Civil Structure Complete 2. Raw mill-2 Civil Structure Complete | a. Raw mill-1: - All the mechanical work right from the hoppers and the fan motors rollers and compressors were in Place and are ready for the trial run b. Raw mill-2: - All the major equipment like the roller unit and the motors were in place and are installed along with the conveying system whereas the compressor at the ground floor was yet to be placed and as per information both the raw mills are to be trial by upcoming week which seems reasonable The overall mechanical work is around 90% for the raw mills | 95%
1.4 | Raw mill bag house & stack support structure | civil work of the raw mill bag house is completed | Insulation work remaining | 95%
1.5 | Preheater tower (Six stage, Double string) | 1. Out of total of 8 slabs all 8 Slabs are completed (Total height of Preheater is 159.6m) 2. Supporting Strucutre for the boiler is in progress | 1. Preheater Fan (from BHEL) was installed this time 3. Boiler Erection Remaining 4. boiler for the preheater was being fabricated at the time of the survey | 95%
1.6 | Rotary Kiln Piers, Walkways, TA duct support | Complete | All the machinery and the fabrication is complete for the TA duct and the Rotary Kiln only refactory bricks for the kilns were in last stage and the burner was ready to be inserted in the kiln | 90%
1.7 | Clinker cooler house (including Dedusting structures & Stack supporting structure) | all the three floors were constructed at the time of survey | Mechanical work for the cooler house was complete and was around 80% (Major equipments like fan,shaft, motors, Plate were installed ) | 85%
1.8 | Coal Crusher House (incl. short retaining wall, ramp, stone pitching, etc.) | Coal crusher house structure is Completed | Coal mill and the supporting Mechanical conveyor system were complete | 90%
1.9 | Coal mill house | 1. Structure work is complete 2. Total height of 57.6m is achieved | a 1. All the received tanks are installed in coal mill house. (Total 3 Tanks) 2. 3 out of 3 bins are erected 3. 5 blowers out of 5 are also erected. However final connection to Fans which was under progress earlier is complete. b 4. Ducting work is complete 5. Bag House Installation complete 6. Conveying System complete | 90%
1.1 | HAG supporting structure | HAG support structure is complete | Mechanical work for the HAG is complete | 90%
1.11 | Cement mill house (Including Dedusting structures & Stack supporting structure) | Complete | Was in Operation | 95%
1.12 | Packing plant, truck & bulk loading, bags godown | Complete | Was in Operation | 95%
SUB TOTAL (1.0)
2 | Silos, Hoppers, Storages, Covered Gantry, etc.
2.1 | Limestone preblending stockpile (linear, covered, with S/R foundations) | Fabricated Steel Column Erected At Site | Reclaimer and stacker are in operation and the conveyor is also complete | 95%
2.2 | AFR Storage | Fabricated Steel Column Erected At Site And Other Mechanical Work Of Conveyor Are In Progress | Trial Done, only Conveying System is in Progress i.e. conveyor to Coal Hopper and futher to Coal Mill remainig
2.3 | Solid fuel storage (linear, covered, with S/R foundations) | Fabricated Steel Column Erected At Site And Other Mechanical Work Of Conveyor Are In Progress | Reclaimer and stacker are in operation and the conveyor is also complete
2.4 | Raw mill hoppers & building | Structure of Raw mill hoppers is complete and all the hoppers are in place. Civil works of the same is complete. Only block work in few section of the building is remaining | Hooper and the way feeder are already installed
2.5 | Blending (Raw Meal) silo | 1. Foundation of Blending silo is almost completed with minor misclelaneous and small works pending for the silo. 2. Blending silo is completely erected only the roof of the silo is remaining | Mechanical work of air sliders is in Progress and bag filter and the bucket elevators are already installed
2.6 | Clinker silo & transport supporting structure | 1. tunnel work completed 2. RCC strcuture of the silo is completed 3. Centre shaft completed | Penthouse and DPC erection work is complete and the load out hopper along with the conveyors were found to be operational as on the date of visit
2.7 | Unburnt clinker silo | Not yet started
2.8 | Clinker load-out silos (4 nos.) | Out of 4 silos, 4 silos are completely erected only the floors are remaining. | 80% of the Mechanical Work is complete and the conveyor from the silo is yet to be connected to these silos
2.9 | Gypsum, pond ash and sweetener storage (linear, covered) | Struture is already erect as per the observation during the site survey | Currently
2.1 | Cement mill hoppers & building | Out of 3 no. of RCC Slabs, 3no. of RCC Slabs have been casted and structure is completed. | 90% mechanical work is complete for the cement mill hopper building
2.11 | Flyash silo | Erection of fly ash Silo completed with some minor internal works pending which are anticipated to completed in due course. | Open air slider for the silo are yet to be erected
2.12 | Cement silos | Civil work of Cement silos are completed. There are a total of 3 silo's and curently mechanical part of the silo's are in progress as per discussion during site visit with the engineer. | One of the three silos are already in use The mechanical work for the second Silo is already at the finishing stage whereas the mechanical work for the third Silo is in progress which will be completed with in next 15 days as per information during the site visit
SUB TOTAL (2.0)
3 | Auxiliary Services
3.1 | Switch yard | Civil work for substation is complete and erection of electric towers are complete | Mechanical work for the Switchyard is complete and the line is charged
3.2 | Main indoor substation | As per information provided by the engineer during visit, the main indoor substaion is at CCR building. During site visit the same was found to be completed. | Mechanical work for the substation is complete
3.3 | CCR, including Lab, Technical Offices, etc. | Structure of CCR building is completed and is currently finsishing works are under progress. | Robo lab and the CCR room was complete | 90%
3.4 | Load centres & MCC rooms |  | Panels installed in the LC and the MCC rooms and cabling work in Cable celler was in Progress | 90%
3.5 | Electrical/ Mechanical Workshop & Yard | Structure of the workshop is completed
3.6 | Compressor house & rooms | No progress was observed during site visit | No progress was observed during site visit
3.8 | Belt conveyors, TTs, etc. (plant internal; partly with gallery & partly locally covered) | Work for Belt conveyor is in Progress in the Plant
3.9 | Water Storage (UG+OH) | Water storage tank is completed only connecting Pipeline Remaining
3.1 | Weigh Bridges & Weigh Rooms | 4 Weigh bridge was found to be installed at site. | all the weigh bridges were installed 1) at the Main Security Gate 2) At packaging Plant
3.11 | Overhead cable galleries | Overhed cable gallery is complete | Cabling work in the Galleries is in final stage
3.12 | Dump hoppers & Truck tippler foundations | Work was in Progress | Work was in Progress
3.13 | Cable Tunnels, Trenches, etc. | Work was in Progress
SUB TOTAL (3.0)
4 | Office/ Non factory buildings, etc
4.1 | Administrative & Services building | Complete
4.2 | Gate house, Time & Security office | Complete
4.3 | Sales, Dispatch & Logistics offices | Complete
4.4 | General store & yard | Complete
4.5 | Canteens (Executive, Workers, Truckers, etc.) | Complete
4.6 | Shift units/ washrooms (in general/common areas) | Complete
SUB TOTAL (4.0)
5 | Mines offices, buildings, services, etc.
5.1 | Mines offices & basic workshop (Basic provisioning only) | No progress was observed during site visit
5.2 | Mines load centre | Civil work was Complete | Panels and the transformer were found installed at the time of Survey
5.3 | Magazine building | No progress was observed during site visit | No progress was observed during site visit
5.4 | Mines garage (Future) | No progress was observed during site visit | No progress was observed during site visit
SUB TOTAL (5.0)
7 | Residential Colony & Social Amenities
7.1 | Unit Head's Villa - 1 no. of ~250 sqm | No progress was observed during site visit | No progress was observed during site visit
7.2 | TH/CH House - 02 nos of ~225 sqm | No progress was observed during site visit | No progress was observed during site visit
7.3 | Type A Quarters - 8 nos. of ~200 sqm each | No progress was observed during site visit | No progress was observed during site visit
7.4 | Type B Quarters - 16 nos. of ~150 sqm each (Multi Storey) | No progress was observed during site visit | No progress was observed during site visit
7.5 | Type C Quarters - 32 nos. of ~125 sqm each (Multi Storey) | No progress was observed during site visit | No progress was observed during site visit
7.6 | Type D Quarters - 40 nos. of ~100 sqm each (Multi Storey) | No progress was observed during site visit | No progress was observed during site visit
7.7 | Type E Quarters - 120 nos. of ~80 sqm each (Multi Storey) | No progress was observed during site visit | No progress was observed during site visit
7.8 | Bachelor Executives' Hostel - 1 no. | the status is similar to previous quarter, Bachelor's Executive hostel is complete and operational. However minor works of the asthetic works are still left which will be completed in due course.
7.9 | Workers' Dormitories - 2 nos. | Workers Dorms is complete and operational.
7.1 | Occupational Health Centre | No progress was observed during site visit
7.11 | Temple complex | No progress was observed during site visit
7.12 | Community hall, playground, shops, etc. | No progress was observed during site visit
7.13 | Guest house | Guest house is complete and operational.
7.14 | Club, gymnasium, recreation, etc | Structure of Club, gymnasium, recreation, etc. is complete.
7.15 | School building and allied Facilities | No progress was observed during site visit
7.16 | Other services (STP, WTP, roads, drains, water supply, green areas, etc.) | 1. Road works started in the project. The road connecting the gate to the main approach road is complete. 2. Single lane of the road connecting the office to the gate was complete in the previous quarter whereas the other lane is completed in the Sep quarter 3. Road Construction in the Plant area is still hasn't started 4. Drains work was in Progress 5. Green area Not yet established 6.Water tank and WTP work is 85 to 90% complete as per observation
SUB TOTAL (7.0)
8 | Total (1.0+2.0+3.0+4.0+5.0+7.0)
9 | Deep foundations cost-provisioning (Indicative 10% lumpsum provisioning considered as Geotechnical investigations at proposed plant site are at preliminary level only)
10 | Indicative GST component on Civil works (average approx.18% of total civil cost considered for TEFR formulation purpose)
11 | Total Civil Works Cost (7.0+8.0+9.0)
Grand Total

## Detailed Phy. progress GU (hidden)
COST OF CIVIL STRUCTURES AND FOUNDATIONS - GRINDING UNIT
Sr. No. | Description | Remarks
1 | Main Factory Building
1.1 | HAG supporting structure | the strcuture is not found at the site at the time of survey
1.2 | Cement mill house & dedusting building | Civil work completed and Mechanical and machinery work is in progress.
1.3 | Packing plant, truck loading, bags godown | 3 out of 5 Slabs are completed, 4th floor column erected during site visit
SUB TOTAL (1.0)
2 | Silos, Hoppers, Storages, Covered Gantry, etc.
2.1 | Foundation network for linear & covered storage sheds for Gypsum, Pond ash & Coal | Foundation work Completed
2.2 | Clinker silo & transport supporting infrastructure | foundation work of the silo is complete upto 11.5m silo wall height out of 50m of total height and tunnel work in progress
2.3 | Support structure for cement mill hoppers (hoppers excluded) | foundation work completed
2.4 | Dry Flyash silo | Flysash silo foundation works are under progress
2.5 | Cement silos (2nos. RCC silos) | One Silo complete another in Progress (foundation work completed)
2.6 | Cement silo (1no. Steel silo) | -
3 | Auxiliary Services
3.1 | Switchyard & Main receiving substation | No Progress observed during site visit
3.2 | CCR, Technical office, Laboratory, etc. | Foundation work completed superstructure under finishing
3.3 | MCC rooms & Load centres | Superstructure completed the strcuture along the bag house is load centre
3.5 | Compressor house | Structure Completed
3.6 | Foundations & pedestals for belt conveyor galleries & transfer towers | foundation work completed and column erection work in Progress
3.7 | Water storage (UG+OH) & Water treatment plant | No progress Observed during site visit
3.8 | Weigh bridges & weigh rooms | 2 no. of weigh bridges installed on site and 1 need to be installed foundation work completed
3.9 | BRU & truck tippler foundations with common ramp for receiving clinker & gypsum | partial erection of belt convyor is completed
3.1 | Foundations & pedestals for Overhead cable galleries | excavation of the trenches is in progress
3.11 | Cable tunnels & trenches, etc. | excavation of the trenches is in progress
4 | Office/ Non factory Buildings, etc
4.1 | Administation & services office block | No Progress observed during site visit
4.2 | Time, security & dispatch offices block | No Progress observed during site visit
4.3 | Executives' & workers' canteens | No Progress observed during site visit
4.4 | General store & yard | No Progress observed during site visit
4.5 | Shift units/ washrooms (in general/common areas) | No Progress observed during site visit
SUB TOTAL (4.0)
7 | Total (1.0+2.0+3.0+4.0+5.0+6.0)
8 | Deep foundations cost-provisioning (Indicative 5% lumpsum provisioning considered; Geotechnical investigations at proposed plant site not carried out yet)
9 | Indicative GST component on Civil works (average approx.18% of total civil cost considered for TEFR formulation purpose)
10 | Total Civil Works Cost (7.0+8.0+9.0)

## IU COP (hidden)
INVESTMENT COST ESTIMATES - IU
(In Lakh INR Unless Specified Otherwise)
SN | DESCRIPTION | TOTAL COST
1.0 | Land and site development
1.1 | Land cost for plant (Govt land) | 42420
1.2 | Land cost for plant (Private land)
1.3 | Land cost for mining area (Govt land)
1.4 | Land cost for mining area (Private land)
1.5 | Mines development expenses | 124
1.6 | Site preparation, leveling and grading | 150
1.7 | Geo-technical, hydrological investigation & Topographic survey | 60
1.8 | Boundary wall | 733
1.9 | Gates, security pickets, etc. | 30
1.10 | Approach road | 627
1.11 | Plant internal roads | 1341
1.12 | Truck parking, logistics offices & other semi-paved areas | 1109
1.13 | Plant drainage | 861
1.14 | Landscaping and provision of green belt | 40
| Sub-total | 47495
2.0 | Buildings and other civil structures
2.1 | Main factory buildings | 8565
2.2 | Silos, hoppers, storages, covered gantry, etc. | 6945
2.3 | Auxiliary services | 2864
2.4 | Office/ Non-factory buildings & Mines Buildingd | 752
2.5 | Residential colony | 6405
2.6 | Equipment foundations cost | 2985
2.7 | Deep foundations cost provisioning on account of possibility of weaker soil bearing capacity (based on preliminary findings of soil investigations) | 3340
2.8 | Indicative GST componment on civil works | 6007
| Sub-total | 37863
3.0 | Plant and Machinery
3.1 | Total cost of Mechanical and Electrical equipment | 89510.8779
3.2 | Equipment for Distribution of Power | 14862.828
3.3 | Waste Heat Recovery System (WHRS) based Power Plant | 20000
3.4 | Mining machinery | 4150
| Sub-total | 128523.7059
4.0 | Engineering & Know How (Various Consultants) | 1100
4.1 | Expenses on foreign technicians and training abroad of local technicians | 750
| Sub-total | 1850
5.0 | Miscellaneous Fixed Assets (MFA)
5.1 | Furniture | 200
5.2 | Office Machinery and Equipment including RFID & IT | 150
5.3 | Miscellaneous Tools and Tackles | 200
5.4 | Vehicles and vehicle expenses | 150
5.6 | Captive Power Plant | -
5.8 | Railway Siding | -
5.9 | Equipment for Water Supply & Water intake | 300
5.10 | Sewage collection, transport to Sewage treatment Plant | 60
5.11 | Laboratory Equipment | 210
5.12 | Workshop Equipment | 150
5.13 | Fire Fighting Equipment & Fire Hydrant System | 400
5.14 | Road Weigh Bridges | 173
5.15 | Office Computers, RFID & IT | 955
5.16 | Front End Loaders (2 Nos) | 70
| Sub-total | 3018
| Total | 218749.7059

## IU Civil cost
COST OF BUILDINGS AND OTHER CIVIL STRUCTURES - IU
SR. NO. | DESCRIPTION | Building Cost | June 2022 Building Progress (%) | September 2022 Building Progress (%) | March 2022 Building Progress (%) | December 2021 Building Progress (%) | September 2021 Building Progress (%) | June 2022 Foundation Progress (%) | September 2022 Foundation Progress (%) | March 2022 Foundation progress (%) | December 2021 Foundation progress (%) | September 2021 Foundation Progress (%) |  | Foundation expenditure
1 | Main Factory Building
1.1 | Limestone crusher complex (including retaining wall, ramp, stone pitching, etc.) | 1090 | 35% | 85% | 10% | 60% | 60% | 60% | 95% | 40% | 0% | 0% | 100% | 0 | 1090 | 135 | 926.5 | 128.25
1.2 | Correctives & Additive crusher house (including short ramp, pitching, etc.) | 100 | 25% | 30% | 25% | 0% | 60% | 45% | 50% | 45% | 0% | 0% | 100% | 0 | 100 | 25 | 30 | 12.5
1.3 | Raw mills complex | 1040 | 90% | 95% | 90% | 90% | 70% | 90% | 95% | 90% | 90% | 90% | 100% | 0.63 | 1040 | 210 | 988 | 199.5
| Raw Mill Hopper 1 |  |  |  |  | 80% | 80% |  |  |  | 80% | 80% | 100% | 0.64 |  |  | 0 | 0
| Raw Mill House 1 |  |  |  |  | 80% | 70% |  |  |  | 80% | 80% | 100% | 0.56 |  |  | 0 | 0
| Raw mill Hopper 2 |  |  |  |  | 80% | 30% |  |  |  | 80% | 80% | 100% | 0.24 |  |  | 0 | 0
| Raw mill House 2 |  |  |  |  | 80% | 30% |  |  |  | 80% | 80% | 100% | 0.24 |  |  | 0 | 0
1.4 | Raw mill bag house & stack support structure | 720 | 90% | 95% | 90% | 80% | 40% | 90% | 95% | 90% | 80% | 80% | 100% | 0.32 | 720 | 90 | 684 | 85.5
1.5 | Preheater tower (Six stage, Double string) | 2415 | 90% | 95% | 90% | 85% | 55% | 90% | 95% | 90% | 90% | 90% | 100% | 0.495 | 2415 | 35 | 2294.25 | 33.25
1.6 | Rotary Kiln Piers, Walkways, TA duct support | 185 | 90% | 95% | 85% | 80% | 30% | 90% | 95% | 85% | 80% | 45% | 100% | 0.24 | 185 | 410 | 175.75 | 389.5
1.7 | Clinker cooler house (including Dedusting structures & Stack supporting structure) | 770 | 75% | 90% | 60% | 25% | 0% | 90% | 95% | 90% | 50% | 45% | 100% | 0 | 770 | 180 | 693 | 171
1.8 | Coal Crusher House (incl. short retaining wall, ramp, stone pitching, etc.) | 60 | 85% | 90% | 80% | 90% | 90% | 90% | 95% | 90% | 90% | 0% | 100% | 0.81 | 60 | 35 | 54 | 33.25
1.9 | Coal mill house | 745 | 90% | 95% | 85% | 85% | 40% | 90% | 95% | 90% | 85% | 85% | 100% | 0.34 | 745 | 205 | 707.75 | 194.75
1.1 | HAG supporting structure | 225 | 95% | 95% | 95% | 90% | 50% | 95% | 95% | 95% | 90% | 65% | 100% | 0.45 | 225 | 25 | 213.75 | 23.75
1.11 | Cement mill house (Including Dedusting structures & Stack supporting structure) | 675 | 90% | 95% | 90% | 85% | 70% | 95% | 95% | 95% | 85% | 85% | 100% | 0.595 | 675 | 225 | 641.25 | 213.75
1.12 | Packing plant, truck & bulk loading, bags godown | 540 | 95% | 95% | 95% | 95% | 80% | 95% | 95% | 95% | 95% | 90% | 100% | 0.76 | 540 | 5 | 513 | 4.75
| SUB TOTAL (1.0) | 8565 |  |  |  | 74.06% | 158000% |  |  |  | 72.19% | 995% | 100% | 6.32 |  |  | 0 | 0
2 | Silos, Hoppers, Storages, Covered Gantry, etc. | [15 empty] | 0 | 0
2.1 | Limestone preblending stockpile (linear, covered, with S/R foundations) | 350 | 50% | 50% | 40% | 0% | 0% | 70% | 70% | 60% | 0% | 0% | 100% | 0 | 350 | 450 | 175 | 315
2.2 | Correctives storage (linear, covered, with S/R foundations) | 155 | 0% | 50% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 100% | 0 | 155 | 195 | 77.5 | 117
2.3 | Solid fuel storage (linear, covered, with S/R foundations) | 185 | 50% | 50% | 40% | 0% | 0% | 60% | 60% | 60% | 0% | 0% | 100% | 0 | 185 | 465 | 92.5 | 279
2.4 | Raw mill hoppers & building | 340 | 90% | 95% | 90% | 90% | 90% | 90% | 95% | 90% | 85% | 85% | 100% | 0.765 | 340 | 10 | 323 | 9.5
2.5 | Blending (Raw Meal) silo | 630 | 95% | 95% | 95% | 95% | 85% | 95% | 95% | 95% | 95% | 90% | 100% | 0.8075 | 630 | 20 | 598.5 | 19
2.6 | Clinker silo & transport supporting structure | 2175 | 90% | 95% | 90% | 90% | 90% | 90% | 95% | 90% | 85% | 85% | 100% | 0.765 | 2175 | 20 | 2066.25 | 19
2.7 | Unburnt clinker silo | 0 |  |  | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 100% | 0 |  |  | 0 | 0
2.8 | Clinker load-out silos (4 nos.) | 295 | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 85% | 100% | 0.9025 | 295 | 15 | 280.25 | 14.25
2.9 | Gypsum, pond ash storage (linear, covered) | 290 | 80% | 95% | 75% | 75% | 75% | 80% | 95% | 75% | 75% | 75% | 100% | 0.5625 | 290 | 0 | 275.5 | 0
2.1 | Cement mill hoppers & building | 340 | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 90% | 100% | 0.9025 | 340 | 10 | 323 | 9.5
2.11 | Flyash silo | 400 | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 90% | 90% | 100% | 0.855 | 400 | 10 | 380 | 9.5
2.12 | Cement silos | 1385 | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 90% | 90% | 100% | 0.855 | 1385 | 15 | 1315.75 | 14.25
2.13 | AFR Storage | 400 | 40% | 40% | 40% | 60% | 60% | 60% | 60% | 60% | 0% | 0% | 100% | 0 | 400 | 15 | 160 | 9
| SUB TOTAL (2.0) | 6945 |  |  |  | 60.77% | 122500% |  |  |  | 54.62% | 690% | 100% | 669.0385 |  |  | 0 | 0
3 | Auxiliary Services | [15 empty] | 0 | 0
3.1 | Switch yard | 45 | 95% | 95% | 95% | 90% | 60% | 95% | 95% | 95% | 90% | 70% | 100% | 0.54 | 45 | 60 | 42.75 | 57
3.2 | Main indoor substation | 145 | 70% | 70% | 60% | 80% | 80% | 80% | 80% | 80% | 0% | 0% | 100% | 0 | 145 | 20 | 101.5 | 16
3.3 | CCR, including Lab, Technical Offices, etc. | 542 | 95% | 95% | 95% | 95% | 70% | 95% | 95% | 95% | 95% | 95% | 100% | 0.665 | 542 | 5 | 514.9 | 4.75
3.4 | Load centres & MCC rooms | 530 | 80% | 90% | 75% | 55% | 40% | 80% | 90% | 80% | 55% | 55% | 100% | 0.22 | 530 | 20 | 477 | 18
3.5 | Electrical/ Mechanical Workshop & Yard | 72 | 90% | 90% | 90% | 90% | 50% | 90% | 90% | 90% | 90% | 90% | 100% | 0.45 | 72 | 10 | 64.8 | 9
3.6 | Compressor house & rooms | 75 |  |  | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 100% | 0 | 75 | 10 | 0 | 0
3.8 | Belt conveyors, TTs, etc. (plant internal; partly with gallery & partly locally covered) | 715 | 90% | 90% | 90% | 90% | 15% | 90% | 90% | 90% | 90% | 15% | 100% | 0.135 | 715 | 0 | 643.5 | 0
3.9 | Water Storage (UG+OH) | 265 | 90% | 90% | 90% | 80% | 80% | 90% | 90% | 90% | 80% | 80% | 100% | 0.64 | 265 | 5 | 238.5 | 4.5
3.1 | Weigh Bridges & Weigh Rooms | 35 | 80% | 90% | 80% | 80% | 0% | 40% | 90% | 40% | 0% | 0% | 100% | 0 | 35 | 25 | 31.5 | 22.5
3.11 | Overhead cable galleries | 250 | 60% | 85% | 35% | 0% | 0% | 40% | 80% | 40% | 0% | 0% | 100% | 0 | 250 | 0 | 212.5 | 0
3.12 | Dump hoppers & Truck tippler foundations | 130 | 0% | 20% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 100% | 0 | 130 | 20 | 26 | 4
3.13 | Cable Tunnels, Trenches, etc. | 60 | 40% | 50% | 30% | 20% | 20% | 40% | 50% | 30% | 20% | 20% | 100% | 4% | 60 |  | 30 | 0
| SUB TOTAL (3.0) | 2864 |  |  |  | 56.67% | 17500% |  |  |  | 43.33% | 425% | 100% | 2.69 |  |  | 0 | 0
4 | Office/ Non factory buildings, etc | [15 empty] | 0 | 0
4.1 | Administrative & Services building | 210 | 90% | 95% | 90% | 90% | 70% | 90% | 95% | 90% | 90% | 90% | 100% | 0.63 | 210 |  | 199.5 | 0
4.2 | Gate house, Time & Security office | 30 | 95% | 95% | 95% | 90% | 75% | 95% | 95% | 90% | 90% | 90% | 100% | 0.675 | 30 |  | 28.5 | 0
4.3 | Sales, Dispatch & Logistics offices | 45 | 0% | 80% | 0% | 0% | 0% | 0% | 90% | 0% | 0% | 0% | 100% | 0 | 45 |  | 36 | 0
4.4 | General store & yard | 95 | 90% | 95% | 90% | 90% | 0% | 90% | 95% | 90% | 90% | 0% | 100% | 0 | 95 |  | 90.25 | 0
4.5 | Canteens (Executive, Workers, Truckers, etc.) | 35 | 95% | 95% | 90% | 0% | 0% | 95% | 95% | 90% | 0% | 0% | 100% | 0 | 35 |  | 33.25 | 0
4.6 | Shift units/ washrooms (in general/common areas) | 40 | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 0% | 0% | 100% | 0 | 40 |  | 0 | 0
| SUB TOTAL (4.0) | 455 |  |  |  | 45% | 0% |  |  |  | 0% | 180% | 100% | 1.305 |  |  | 0 | 0
[12 empty] | 180% | 100% |  |  |  | 0 | 0
5 | Mines offices, buildings, services, etc. | [15 empty] | 0 | 0
5.1 | Mines offices & basic workshop (Basic provisioning only) | 217 | 20% | 20% | 0% | 50% | 50% | 40% | 40% | 0% | 0% | 0% | 100% | 0 | 217 |  | 43.4 | 0
5.2 | Mines load centre | 35 | 50% | 90% | 10% | 70% | 70% | 70% | 95% | 0% | 0% | 0% | 100% | 0 | 35 |  | 31.5 | 0
5.3 | Magazine building | 40 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 40 |  | 0 | 0
5.4 | Mines garage (Future) | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 |  |  | 0 | 0
| SUB TOTAL (5.0) | 292 |  |  |  | 0% | 500% |  |  |  | 0% | 0% | 100% | 0 |  |  | 0 | 0
[12 empty] | 0% | 100% |  |  |  | 0 | 0
7 | Residential Colony & Social Amenities | [15 empty] | 0 | 0
7.1 | Unit Head's Villa - 1 no. of ~250 sqm | 65 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 65 |  | 0 | 0 | 255
7.2 | TH/CH House - 02 nos of ~225 sqm | 110 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 110 |  | 0 | 0 | 0
7.3 | Type A Quarters - 8 nos. of ~200 sqm each | 325 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 325 |  | 0 | 0
7.4 | Type B Quarters - 16 nos. of ~150 sqm each (Multi Storey) | 475 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 475 |  | 0 | 0
7.5 | Type C Quarters - 32 nos. of ~125 sqm each (Multi Storey) | 900 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 900 |  | 0 | 0
7.6 | Type D Quarters - 40 nos. of ~100 sqm each (Multi Storey) | 800 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 800 |  | 0 | 0
7.7 | Type E Quarters - 120 nos. of ~80 sqm each (Multi Storey) | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 0 |  | 0 | 0
7.8 | Bachelor Executives' Hostel - 1 no. | 175 | 95% | 95% | 90% | 90% | 90% | 95% | 95% | 90% | 0% | 0% | 100% | 0 | 175 |  | 166.25 | 0
7.9 | Workers' Dormitories - 2 nos. | 70 | 95% | 95% | 90% | 90% | 90% | 95% | 95% | 90% | 0% | 0% | 100% | 0 | 70 |  | 66.5 | 0
7.1 | Occupational Health Centre | 80 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 80 |  | 0 | 0
7.11 | Temple complex | 250 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 250 |  | 0 | 0
7.12 | Community hall, playground, shops, etc. | 150 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 150 |  | 0 | 0
7.13 | Guest house | 400 | 95% | 95% | 90% | 90% | 90% | 95% | 95% | 90% | 0% | 0% | 100% | 0 | 400 |  | 380 | 0
7.14 | Club, gymnasium, recreation, etc | 125 | 95% | 95% | 90% | 90% | 90% | 95% | 95% | 90% | 0% | 0% | 100% | 0 | 125 |  | 118.75 | 0
7.15 | School building & allied facilities | 1000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 1000 |  | 0 | 0
7.16 | Other services (STP, WTP, roads, drains, water supply, green areas, etc.) | 1480 | 35% | 35% | 0% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 100% | 0 | 1480 |  | 518 | 0
| SUB TOTAL (7.0) | 6405 |  | 5 |  | 25% | 0 |  |  |  | 0% | 0 | 100% | 0 |  |  | 0 | 0
[12 empty] | 0 | 100% |  |  |  | 0 | 0
8 | Total (1.0+2.0+3.0+4.0+5.0+7.0) | 25526 |  |  |  | - | 2985 |  |  |  | - | 22.9 | 100% | 679.3535 | 25526 | 2980 | 18083.35 | 2440.5
9 | Deep foundations cost-provisioning (Indicative 10% lumpsum provisioning considered as Geotechnical investigations at proposed plant site are at preliminary level only) | 3040 |  |  |  | - | 300 |  |  |  | - | 2.29 | 100% | 67.9353 | 28506 |  | 20523.85 | 205.2385
10 | Indicative GST component on Civil works (average approx.18% of total civil cost considered for TEFR formulation purpose) | 5470 |  |  |  | - | 537 |  |  |  | - | 4.5342 | 100% | 134.512 |  |  | 28506 | 285.06
11 | Total Civil Works Cost (7.0+8.0+9.0) | 34036 |  |  |  | - | 3822 |  |  |  | - | 29.7242 | 100% | 881.8008 |  |  |  | 72%
| Grand Total | 37858 | [8 empty] | - | 911.525 | 100%
[12 empty] | 2.408% | 100%
|  | 30387 |  |  |  | 3038.7 | [6 empty] | 100%
|  | 3038.7 | [10 empty] | 100%
|  | 33425.7 | [10 empty] | 100%
5469.66

## IU M&E (hidden)
COST OF MECHANICAL AND ELECTRICAL EQUIPMENT - IU
Sr. No. | DESCRIPTION | F.O.B. (Imported) | F.O.R. (Indigeneous) | FOB Progress | FOR progress | FOB Expenditure | FOR Expenditure
1.0 | Mechanical Equipment
1.1 | Crushers
1.1.1 | Limestone crushing and wobbler | 0 | 20 | 0% | 0% | 0 | 0
1.1.2 | Coal Crushing | 0 | 1 | 0% | 0% | 0 | 0
1.1.3 | Additve/ Corrective Crusher | 0 | 1.5 | 0% | 0% | 0 | 0
1.2 | Stockpiles stackers & Reclaimers including the following:
1.2.1 | Limestone Storage, Stacker & Reclaimer including shed | 0 | 26.66 | 0% | 10% | 0 | 2.666
1.2.2 | Corrective Storage Stacker & Reclaimer including shed | 0 | 17.01 | 0% | 10% | 0 | 1.701
1.2.3 | Coal storage stacker and reclaimer including shed | 0 | 15.725 | 0% | 10% | 0 | 1.5725
1.3 | Material Grinding and Pyroprocessing including the following:
1.3.1 | Raw Material and Coal Drying and Grinding including Baghouse | 23.15 | 92.6 | 0% | 15% | 0 | 13.89
1.3.2 | Blending Silo feed B/Ele, Silo, kiln feed, Clinkerisation (upto clinker silo extraction), Fine coal firing from silo extraction including ESP | 25 | 100 | 0% | 15% | 0 | 15
1.3.3 | Clinker transport to mill through DPC, Clinker drying & grinding (Upto cement silo feed B/E) including Baghouse | 28 | 42 | 0% | 15% | 0 | 6.3
1.4 | Cement Silo's and packing plant
1.4.1 | Clinker extraction system | 0 | 1.5 | 0% | 10% | 0 | 0.15
1.4.2 | Cement extraction from cement silo upto rotary packers including steel cement silo | 0 | 7.64 | 0% | 10% | 0 | 0.764
1.4.3 | Packing, truck loaders and bulk loading. | 0 | 8.6 | 0% | 0% | 0 | 0
1.4.4 | Clinker loading to trucks | 0 | 2.5 | 0% | 0% | 0 | 0
1.4.5 | AFR system with Shed | 0 | 20.77 | 0% | 0% | 0 | 0
1.4.6 | Flyash Silo | 0 | 1.5 | 0% | 10% | 0 | 0.15
| Sub-total of Main Machinery (1.0) | 76.15 | 359.005 |  |  | 0 | 42.1935
2.0 | MECHANICAL AUXILIARY EQUIPMENT(S)
2.1 | Steel for Duct/ Chute/hoppers/chimneys 8,000 t @ Rs 46200/ t | 0 | 36.96 | 0% | 44.21% | 0 | 16.3409
2.2 | Plant belt conveyors including belting 3,500 m @ Rs 45,000/ m | 0 | 15.75 | 0% | 0% | 0 | 0
2.5 | Refractory & Castable 8,000 t @ Rs 35,000/ t | 0 | 28 | 0% | 44.21% | 0 | 12.3795
2.6 | Insulation 70,000 m2 @ Rs 1130/ sq. m | 0 | 7.91 | 0% | 44% | 0 | 3.4804
2.7 | Lubricants | 0 | 1.6 | 0% | 40% | 0 | 0.64
2.8 | Passenger Lifts (4 nos) | 0 | 1.5 | 0% | 0% | 0 | 0
2.10 | Compressors & Driers inclusind piping | 0 | 3.5 | 0% | 0% | 0 | 0
2.11 | Misc. items like Water Tank, Water Pump, Water Piping, Compressed Air Piping, etc. | 0 | 4.62 | 0% | 0% | 0 | 0
2.12 | BRU & Truck Tippler (4 nos.) | 0 | 2.8 | 0% | 10% | 0 | 0.28
2.13 | Cranes/Hoists and other miscl items including HAG, N2 system etc. | 0 | 6.5 | 0% | 60% | 0 | 3.9
| Sub-total of Mechanical Auxiliary Equipment (2.0) | 0 | 109.14 | 0% | 0% | 0 | 0
| Total of Mechanical Equipment (1.0 + 2.0) | 76.15 | 468.145 |  |  | 0 | 37.0208
3.0 | Electrical and Instrumentation
3.1 | HT Motors | 0 | 9.6 | 0% | 0% | 0 | 0
3.2 | LV & MV AC variable Speed Drives | 0 | 15.05 | 0% | 0% | 0 | 0
3.3 | LT Motors | 0 | 6.27 | 0% | 0% | 0 | 0
3.4 | Cross Belt Analyser, XRF, XRD, etc | 2.5 | 4.81 | 0% | 0% | 0 | 0
3.5 | Control & Automation and Field Instruments & Robo Lab | 0 | 24.57 | 0% | 0% | 0 | 0
| Total Electrical and Instrumentation (3.0) | 2.5 | 60.3 |  |  | 0 | 0
| Total Mechanical and Electrical equipment (1.0+2.0+3.0) | 78.65 | 528.445 |  |  | 0 | 79.2143
4.0 | Landed cost of equipment
4.1 | Imported equipment
4.1.1 | F.O.B Cost (Imported) | 78.65 |  | 0
4.1.2 | Ocean Freight, Insurance, etc. @ 6 % of (4.1.1) | 4.719 |  | 0
4.1.3 | Basic import duty @ 7.5 % of (4.1.1 + 4.1.2) | 6.2527 |  | 0
4.1.4 | IGST @ 18 % of (4.1.1 to 4.1.3) | 16.1319 |  | 0
4.1.5 | Clearing/ Loading/ Inland freight, etc. @ 5 % of (4.1.1 + 4.1.2) | 4.1684 |  | 0
| Sub-total of imported equipment (4.1) | 109.922 |  | 0
4.2 | Indigenous Equipment
4.2.1 | F.O.R cost (Indigenous Equipment) | 528.445 |  | 79.2143
4.2.2 | GST @ 18 % on F.O.R. | 95.1201 |  | 14.2586
4.2.3 | Freight, handling, insurance, etc. @ 5 % of 4.2.1 | 26.4222 |  | 3.9607
| Sub-total of indigenous equipment (4.2) | 649.9873 |  | 97.4336
| Total landed cost of equipment (4.1 + 4.2) | 759.9094 |  | 97.4336
5.0 | Spare parts @ 5 % of F.O.B. + F.O.R. | 30.3547 |  | 4.8717
6.0 | Fabrication of Duct/ Chute/hoppers/chimneys 8,000 t @ Rs 20,000/ t | 16 |  | 7.074
7.0 | Erection, commissioning & supervision charges @ 12 % of (F.O.R. + F.O.B) | 72.8514 |  | 9.5057
8.0 | GST @18% on (6.0+7.0) | 15.9933 |  | 2.9843
| Total cost of Mechanical and Electrical equipment | 895.1088 |  | 121.8694
A | TOTAL COST OF EQUIPMENT (4.1+ 4.2+5.0+6.0+7.0+8.0) | 895.1088 |  | 121.8694
B | IGST+GST | 127.2453 |  | 21.9365
C | TOTAL LANDED COST OF EQUIPMENT (NET of IGST+GST) | 767.8635 |  | 99.9329
|  | 895.1088 |  | 121.8694 |  | also consider WHRS expenditure
13.62%
1168
85%
| s |  | 992.8
300
|  |  | 30 | 18%
|  |  | 1322.8 | 10%
1560.904
424
1984.904
2183.3944

## IU Power Distribution (hidden)
Annexure 8.5
COST OF POWER DISTRIBUTION EQUIPMENT - IU
(In Lakh INR Unless Specified Otherwise)
SN | DESCRIPTION | F.O.B. | F.O.R.
1 | Power distribution equipment | -
1.1 | 132 kV Transmission line ~45 Km | - | 22.5
1.2 | 132 kV yard at sub-station | - | 1
1.3 | Development charges/Security deposit | - | 4.9
1.4 | Supervison charges SEB (10% of line cost) | - | 2.25
1.5 | Incomer switchyard and power transformer | - | 5.87
1.6 | 11 KV Switch board with Capacitor Bank | - | 6.61
1.7 | 11/0.433 kV , Distribution transformer with bus duct | - | 5.44
1.8 | LT switchboards and bus trunkings | - | 4.45
1.9 | MCC & Push button Station | - | 7.09
1.10 | LV Capacitor | - | 1.8
1.11 | Capacitor and Reactor for 11 KV HT motors |  | 1.8
1.12 | LRS/GRR/GRS |  | 1.8
1.13 | Earthing, cable trays & erection hardware | - | 6
1.14 | Cables - Power, Control & Instrumentation | - | 18.18
1.15 | Plant Illumination with LDB | - | 3.72
1.16 | Battery and Battery Charger with LRS | - | 0.83
1.17 | Ventilation System for Electrical Building | - | 1.43
1.18 | Air Conditioning | - | 1.85
1.19 | Fire Detection System | - | 0.74
1.2 | PA system for intercom and Telephone exchange | - | 0.45
1.21 | Mine Power Distribution | - | 0
1.22 | DG Sets for Construction (2 MW) | - | 1.13
1.23 | Construction Power | - | 2.61
1.24 | EMS/Synchronisation/load shedding | - | 0.75
1.25 | Non-plant buildings electrification | - | 0.85
1.26 | Misc. Electricals | - | 0.5
| Sub total | 0 | 104.55
2.0 | Landed cost of equipment
2.1 | F.O.R cost | 0 | 104.55
2.2 | GST @ 18 % on F.O.R. | - | 18.819
2.5 | Freight, handling, insurance, etc. @ 5 % of 4.2.1 | - | 5.2275
| Total landed cost of equipment | 0 | 128.5965
3.0 | Spare parts @ 5 % of FOR cost | - | 5.2275
4.0 | Erection, commissioning & supervision charges @ 12% of F.O.R. | - | 12.546
5.0 | GST @ 18% of 4.0 | - | 2.2583
A | Total cost of power distribution equipment | 0 | 148.6283
B | GST | 21.0773
C | TOTAL COST OF POWER DISTRIBUTION EQUIPMENT NET OF GST | 127.551

## GU COP (hidden)
Annexure 8.7
INVESTMENT COST ESTIMATES - GU
( In Lakhs INR Unless Specified Otherwise )
Sn | Description | Total Cost | Remarks
1.0 | Land and Site Development
1.1 | Capital Cost of procured land for setting up the plant | 900 | Total cost estimated
1.2 | Site preparation & development | 50 | Refer Annexure 8.8
1.3 | Site enabling investigations (Topographical, Geotechnical & Hydrological) | 50 | Lumpsum
1.4 | Boundary Wall | 125 | Refer Annexure 8.8
1.5 | Gates, Security Pickets, etc. | 30 | Lumpsum
1.6 | Approach Road to Plant | 190 | Refer Annexure 8.8
1.7 | Plant Internal Roads | 400 | Refer Annexure 8.8
1.8 | Truck Parking & Logistics Office | 370 | Refer Annexure 8.8
1.9 | Plant Drainage | 135 | Refer Annexure 8.8
1.10 | Landscaping and Provision of Green Belt | 20 | Refer Annexure 8.8
| Sub-total (1.0) | 2270
2.0 | Buildings and other civil structures
2.1 | Main Factory Buildings | 1785 | Refer Annexure 8.8
2.2 | Silos, Hoppers, Storages, Covered Gantry, etc. | 3100 | Refer Annexure 8.8
2.3 | Auxiliary Services | 1220 | Refer Annexure 8.8
2.4 | Office/ Non-factory buildings | 250 | Refer Annexure 8.8
2.5 | Residential colony & social amenities | 0 | Refer Annexure 8.8
2.6 | Deep foundations cost provisioning on account of possibility of weaker soil bearing capacity (Soil investigations yet to take place) | 400 | Refer Annexure 8.8
2.7 | Indicative GST componment on civil works | 1450 | Refer Annexure 8.8
| Sub-total (2.0) | 8205
3.0 | Plant & Machinery related
3.1 | Total Cost of Mechanical and Electrical Equipment (Net of GST) | 14930 | Refer Annexure 8.9
3.2 | GST component on Plant & Machinery (approx. provisioning) | 2450 | Refer Annexure 8.9
3.3 | Equipment for Distribution of Power (Net of GST) | 2560 | Refer Annexure 8.10
3.4 | GST component on Power distribution (approx. provisioning) | 420 | Refer Annexure 8.10
3.5 | Equip. Foundations' (Machine Fnds.) civil cost component | 423 | Refer Annexure 8.8
3.6 | Secondary Equipment:
3.4.1 | Laboratory equipment & setup | 85
3.4.2 | Fire-fighting equipment & hydrant system | 40
3.4.3 | Water treatment system | 50
3.4.4 | Multi-utility equipment (front-end loader, fork lifts, truck-mounted lifting crane) | 130
3.4.5 | Weighbridges | 75
| Sub-total (3.0) | 21163
4 | Expenses on technical know-how & training
4.1 | Engineering & know-how (various consultants & agencies) | 400
4.2 | Training & skill upgradation related expenses (technicians & others) | 50
| Sub-total (4.0) | 450
5 | Miscellaneous Fixed Assets (MFA)
5.1 | Office furniture, machinery & equipment | 70
5.2 | Office gadgetary (computers, printers, LAN peripherals, etc.) | 30
5.3 | Generic tools & tackles | 50
5.4 | Light motor vehicles for office use | 60
5.5 | Railway track/ siding | -
| Sub-total (5.0) | 210
9.0 | Loan on Working Capital
| Estimated Total Project Cost (1.0+2.0+3.0+4.0+5.0) | 32298

## Detailed Phy. Prog. of GU
Sr. No. | Description | Remarks
1 | Main Factory Building | Civil | Mechanical
1.1 | HAG supporting structure | Foundation is complete and the frame structure is also complete only the Block work for the Structure is in Progress | Machinery for the HAG is already installed | 85%
1.2 | Cement mill house & dedusting building | 1. RCC Structure complete 2. 50% of the steel frame remaining | All the Fabrication and the Bag House Equipments like the Bag Filters Cages are installed in the Dedusting Building along with Bucket Elevators and the Fan
1.3 | Packing plant, truck loading, bags godown | 1. Packing plant structure complete brick work in Progress 2. truck loading Section Complete 3. Bags Godown structure complete | Machinery for the Bulk loading is the only major machinery Left in the Packaging Plant all of the Packing section related to Bag Packaging is complete | 85%
2 | Silos, Hoppers, Storages, Covered Gantry, etc.
2.1 | linear & covered storage sheds for Gypsum, Pond ash & Coal | Fabricated steel column are erected, shed installion and flooring Complete
2.2 | Clinker silo & transport supporting infrastructure | As per physical progress observed and subsequent discussion with the site engnieer, structure of Clinker silo is complete only roof in progress | Mechanical work supporting the transfer of Clinker is complete along with the extract line
2.3 | Support structure for cement mill hoppers (hoppers excluded) | Out of 4 slabs, all the 4 slabs completed | Hopper for the same is completely erected and the connecting Conveyors are also erected
2.4 | Dry Flyash silo | Silo is completely erected | Flyash Silo pneumatic system and the Bag Filters were erected at the time of survey | 95%
2.5 | Cement silos (2nos. RCC silos) | 1. cement silo-1 RCC structure complete 2. cement silo-2 RCC structure Complete | Mechanical work for both the silo are complete
2.6 | Cement silo (1no. Steel silo) | Not yet started
3 | Auxiliary Services
3.1 | Switchyard & Main receiving substation | Electric pole foundation works complete. Erection of Towers under progress. | Complete and Charged
3.2 | CCR, Technical office, Laboratory, etc. | Structure for CCR, Technical office, Laboratory, etc. is complete. During site visit finsihing works were under progress. | Majority of the Equipments are in the Lab The technical office is in the finishing Stage The CCR is already established
3.3 | MCC rooms & Load centres | Structure of MCC room is complete and Structures of various small load centres in the project are under progress. All the panel in the MCC rooms are installed whereas cable work is going on in the Main Load centre | Mechanical work of the MCC room is complete and the Cable in the Cable Celler is also in the final Stage of the work
3.5 | Compressor house | No work started in Compressor house | No work started in Compressor house
3.6 | Foundations & pedestals for belt conveyor galleries & transfer towers | Foundations & pedestals for belt conveyor galleries are Complete 1.belt conveyor from clinker silo to clinker hopper is completed. 2. Connecting Conveyor from Cement mill recirculation building to cement mill hopper building is also complete 3.BRU to Clinker silo is also at the end stage | Already complete and is ready for trial run
3.7 | Water storage (UG+OH) & Water treatment plant | Water storage Tank side walls completed and top slab works under progress. Water treatment works yet to start in the project. | Mechanical work for the Treatment Plant is complete and is in final Stage of the installatin
3.8 | Weigh bridges & weigh rooms | Weigh bridges is completely installed | Mechanical work complete
3.9 | BRU (Bulk Reception Unit) & truck tippler foundations with common ramp for receiving clinker & gypsum | 1. Foundation,retaining walls and steel frame for the shed is complete for the BRU 2. both the box feeders are installed 3. 1 Ramp is complete and other is in progress as found at site. 4. Foundation for the Fan is Complete | Mechanical for the BRU unit is complete and is already undergone Pseudo Trial
3.1 | Foundations & pedestals for Overhead cable galleries | Cable galleries foundation and pedastal erection works is completed. | Cables are completely ran in these galleries
3.11 | Cable tunnels & trenches, etc. | RCC drains work was in progress.
4 | Office/ Non factory Buildings, etc
4.1 | Administation & services office block | Not yet started
4.2 | Time, security & dispatch offices block | Not yet started
4.3 | Executives' & workers' canteens | Not yet started
4.4 | General store & yard | Not yet started
4.5 | Shift units/ washrooms (in general/common areas) | Not yet started
| VRM | 60 to 65% Complete

## GU Civil Cost
COST OF CIVIL STRUCTURES AND FOUNDATIONS - GU
Sr. No. | Description | Building Cost | Equip. Fnd. Cost (Machine Fnds.) |  | June'22 Building Progress % | September'22 Building progress % | March Building Progress % | December Building Progress % | September Building Progress % |  | June'22 Foundation Progress % | September'22 Foundation progress % | March Foundation Progress % | December Foundation Progress % | September Foundation progress % | Building Cost | Foundation work Cost
1 | Main Factory Building
1.1 | HAG supporting structure | 220 | 30 | 100% | 0% | 60% | 0% | 0% | 85% | 100% | 90% | 90% | 90% | 0% | 0% | 0 | 0 |  | 220 | 30 | 132 | 27
1.2 | Cement mill house & dedusting building | 1025 | 225 | 100% | 80% | 90% | 75% | 60% | 15% | 100% | 90% | 90% | 90% | 90% | 80% | 615 | 202.5 |  | 1025 | 225 | 922.5 | 202.5
1.3 | Packing plant, truck loading, bags godown | 540 | 5 | 100% | 90% | 90% | 85% | 60% | 15% | 100% | 90% | 90% | 90% | 90% | 80% | 324 | 4.5 |  | 540 | 5 | 486 | 4.5
| SUB TOTAL (1.0) | 1785 | 260 |  |  |  |  | 40% | [5 empty] | 60% | 100% | 939 | 207 |  |  |  | 0 | 0
2 | Silos, Hoppers, Storages, Covered Gantry, etc. | [19 empty] | 0 | 0
2.1 | linear & covered storage sheds for Gypsum, Pond ash & Coal | 110 | 0 | 100% | 60% | 90% | 40% | 20% | 20% | 100% | 90% | 90% | 90% | 85% | 40% | 22 | 0 |  | 110 |  | 99 | 0
2.2 | Clinker silo & transport supporting infrastructure | 1365 | 20 | 100% | 85% | 90% | 70% | 5% | 0% | 100% | 100% | 100% | 100% | 100% | 90% | 68.25 | 20 |  | 1365 | 20 | 1228.5 | 20
2.3 | Support structure for cement mill hoppers (hoppers excluded) | 210 | 10 | 100% | 90% | 95% | 90% | 40% | 0% | 100% | 95% | 95% | 95% | 95% | 0% | 84 | 9.5 |  | 210 | 10 | 199.5 | 9.5
2.4 | Dry Flyash silo | 460 | 10 | 100% | 90% | 95% | 90% | 60% | 15% | 100% | 100% | 100% | 100% | 100% | 55% | 276 | 10 |  | 460 | 10 | 437 | 10
2.5 | Cement silos (2nos. RCC silos) | 850 | 10 | 100% | 85% | 95% | 70% | 50% | 15% | 100% | 90% | 90% | 90% | 90% | 70% | 425 | 9 |  | 850 | 10 | 807.5 | 9
2.6 | Cement silo (1no. Steel silo) | 105 | 5 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  | 105 | 5 | 0 | 0
| SUB TOTAL (2.0) | 3100 | 55 |  |  |  |  | 29.17% | [5 empty] | 78.33% |  | 875.25 | 48.5 |  |  |  | 0 | 0
3 | Auxiliary Services | [19 empty] | 0 | 0
3.1 | Switchyard & Main receiving substation | 90 | 30 | 100% | 60% | 85% | 50% | 50% | 50% | 100% | 70% | 85% | 50% | 0% | 0% | 45 | 0 |  | 90 | 30 | 76.5 | 25.5
3.2 | CCR, Technical office, Laboratory, etc. | 380 | 0 | 100% | 85% | 90% | 85% | 85% | 45% | 100% | 95% | 95% | 95% | 95% | 70% | 323 | 0 |  | 380 | 0 | 342 | 0
3.3 | MCC rooms & Load centres | 210 | 10 | 100% | 70% | 85% | 70% | 45% | 45% | 100% | 90% | 90% | 90% | 50% | 50% | 94.5 | 5 |  | 210 | 10 | 178.5 | 9
3.5 | Compressor house | 45 | 8 | 100% | 90% | 90% | 90% | 90% | 0% | 100% | 90% | 90% | 90% | 90% | 0% | 40.5 | 7.2 |  | 45 | 8 | 40.5 | 7.2
3.6 | Foundations & pedestals for belt conveyor galleries & transfer towers | 150 | 0 | 100% | 80% | 90% | 60% | 10% | 10% | 100% | 85% | 90% | 75% | 70% | 10% | 15 | 0 |  | 150 |  | 135 | 0
3.7 | Water storage (UG+OH) & Water treatment plant | 110 | 10 | 100% | 75% | 90% | 75% | 25% | 25% | 100% | 90% | 90% | 90% | 30% | 30% | 27.5 | 3 |  | 110 | 10 | 99 | 9
3.8 | Weigh bridges & weigh rooms | 5 | 15 | 100% | 90% | 90% | 90% | 70% | 70% | 100% | 90% | 90% | 90% | 90% | 85% | 3.5 | 13.5 |  | 5 | 15 | 4.5 | 13.5
3.9 | BRU & truck tippler foundations with common ramp for receiving clinker & gypsum | 165 | 35 | 100% | 70% | 95% | 70% | 0% | 0% | 100% | 90% | 95% | 90% | 50% | 0% | 0 | 17.5 |  | 165 | 35 | 156.75 | 33.25
3.1 | Foundations & pedestals for Overhead cable galleries | 45 | 0 | 100% | 75% | 85% | 60% | 60% | 60% | 100% | 90% | 90% | 90% | 50% | 0% | 27 | 0 |  | 45 | 0 | 38.25 | 0
3.11 | Cable tunnels & trenches, etc. | 20 | 0 | 100% | 60% | 75% | 50% | 20% | 20% | 100% | 60% | 75% | 60% | 25% | 25% | 4 | 0 |  | 20 | 0 | 15 | 0
| SUB TOTAL (3.0) | 1220 | 108 |  |  |  |  | 45.5% | [5 empty] | 55% |  | 580 | 46.2 |  |  |  | 0 | 0
4 | Office/ Non factory Buildings, etc | [19 empty] | 0 | 0
4.1 | Administation & services office block | 65 | 0 |  | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  | 65 |  | 0 | 0
4.2 | Time, security & dispatch offices block | 20 | 0 |  | 0% | 50% | 0% | 0% | 0% |  | 0% | 50% | 0% | 0% | 0% | 0 | 0 | 100% | 20 |  | 10 | 0
4.3 | Executives' & workers' canteens | 65 | 0 |  | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  | 65 |  | 0 | 0
4.4 | General store & yard | 80 | 0 |  | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  | 80 |  | 0 | 0
4.5 | Shift units/ washrooms (in general/common areas) | 20 | 0 |  | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  | 20 |  | 0 | 0
| SUB TOTAL (4.0) | 250 | 0 |  | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  |  |  | 0 | 0
7 | Total (1.0+2.0+3.0+4.0+5.0+6.0) | 6355 | 423 |  | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 2394.25 | 301.7 |  |  |  | 0 | 0
8 | Deep foundations cost-provisioning (Indicative 5% lumpsum provisioning considered; Geotechnical investigations at proposed plant site not carried out yet) | 380 | 20 |  |  |  |  | 0% | [5 empty] | 0% | 0% | 119.7125 | 15.085 |  |  |  | 0 | 0
9 | Indicative GST component on Civil works (average approx.18% of total civil cost considered for TEFR formulation purpose) | 1375 | 75 |  |  |  |  | 0% | [5 empty] | 0% | 0% | 430.965 | 54.306 |  |  |  | 0 | 0
10 | Total Civil Works Cost (7.0+8.0+9.0) | 8110 | 518 |  |  |  |  | 0% | [5 empty] | 0% | 0% | 2944.9275 | 371.091 |  |  |  | 0 | 0
|  | 8205 | [13 empty] | 3316.0185 |  |  |  |  | 0 | 0
[16 empty] | 40.41% |  |  | 6355 | 423 | 5408 | 379.95
[19 empty] | 6778 |  | 5787.95 | 57.8795
0.85393
85.39%

## June CA CERTIFICATE
[5 empty] | Total Capacity | 4 Mn. TPA
[5 empty] | Date | 2022-06-30
[5 empty] | Common Loan Agreement | 2021-11-18
[5 empty] | UDIN No. | 22424004AOQULC5196
[5 empty] | CA Certificate date | 2022-08-09
Source of Funds
|  |  | S.No. | Particulars | Rs. In Crores |  | Item | Expenses incurred (in cr.) | Estimated Project Cost as per Holtec | % expenses
|  |  | 1 | Promoters Contribution | 1167.09 |  | Land and site Development | 316.26 | 497.65 | 63.55%
1 | Debt | 840.5 | 2 | Loan Disbursement | 840.5 |  | Plant and Machinery/ Building & Civil Structures/ Miscellaneous Fixed assests | 1663.14 | 1989.93 | 83.58%
2 | Equity Contribution | 1167.09 | 3 | Total (1) + (2) | 2007.59 |  | Pre-operative Expenses/ Engineering and Knowhow/ Training & Foreign Technician Expenses | 74.95 | 140.46 | 53.36%
|  | 0.72017 | 4 | Balance in Bank Account/FDRs | 24.36 |  | Interest during construction Period | 18.05 | 130.31 | 13.85%
|  |  | 5 | Total (3) - (4) | 1983.23 |  | Contingency | - | 197.1 | 0%
|  |  | 6 | Others (Project Creditors) | 89.17 |  | Margin Money Capital for working Capital | - | 14.94 | 0%
|  |  |  | Total (5) + (6) | 2072.4 |  | Total | 2072.4 | 2970.39 | 69.77%

## March CA certificate (hidden)
Item | Expense Incured in September (in crores) | Expense incured in crore (Dec.) | Estimated Project Cost as per the Holtec Report | September | December | January
Land and site Development | 208.49 | 259.13 | 497.65 | 41.89% | 52.07% | 24.29%
Plant and Machinery/ Building & Civil Structures/ Miscellaneous Fixed assests | 432.34 | 664.63 | 1989.93 | 21.73% | 33.4% | 53.73%
Pre-operative Expenses/ Engineering and Knowhow/ Training & Foreign Technician Expenses | 27.1 | 36.17 | 140.46 | 19.29% | 25.75% | 33.47%
Interest during construction Period | 0 | 1.06 | 130.31 | 0% | 0.8134% | #DIV/0!
Contingency | 0 | 0 | 197.1 | 0% | 0% | #DIV/0!
Margin Money Capital for working Capital | 0 | 0 | 14.94 | 0% | 0% | #DIV/0!
Total | 667.93 | 960.99 | 2970.39 | 22.49% | 32.35% | 43.88%
Particulars | Rs. (in crore) | Rs. in crore
Promoter’s Contribution (Equity) | 658.21 | 815.65
Term Loan (Debt) | 0 | 131.93
Project Creditors | 9.72 | 13.41
Total | 667.93 | 960.99

## GU M&E (hidden)
COST OF MECHANICAL AND ELECTRICAL EQUIPMENT - GU
( In Lakhs INR Unless Specified Otherwise )
Sr. No | Description | F.O.B. | F.O.R. | FOB Progress | FOR Progress | FOB Expenditur | FOR Expenditure
1.0 | Mechanical Equipment
1.1 | Gypsum & Pond ash handling, storage and transport to mill feed hoppers | 0 | 0.75 | 0% | 0% | 0 | 0
1.2 | Dry Flyash handling, transport, storage & feeding to mill | 0 | 1.5 | 0% | 0% | 0 | 0
1.3 | Coal handling, storage, feeding and transport (including HAG system) | 0 | 2.05 | 0% | 0% | 0 | 0
1.4 | Clinker transport, handling, storage, extraction & feeding system | 0 | 2.25 | 0% | 0% | 0 | 0
1.5 | Clinker grinding circuit & feeding to cement silos | 24 | 36 | 0% | 0% | 0 | 0
1.6 | Cement mill dedusting | 0 | 6 | 0% | 0% | 0 | 0
1.7 | Cement extraction from silos upto packers | 0 | 3.1 | 0% | 0% | 0 | 0
1.8 | Packing, loading & dispatch (2 packers, 6 truck loaders and 1 bulk loader) | 0 | 8.1 | 0% | 0% | 0 | 0
| Sub-total of Main Machinery (1.0) | 24 | 59.75 |  |  | 0 | 0
2.0 | MECHANICAL AUXILIARY EQUIPMENT(S)
2.1 | Structural Steel for sheds, hoppers, conveyors, ducts, chutes, etc. (approx. 2,250 t @Rs.50,000/ t) | 0 | 11.25 | 0% | 10.31% | 0 | 1.16
2.2 | Material conveying system (approx.1200m @Rs.40,000/ m) | 0 | 4.8 | 0% | 0% | 0 | 0
2.3 | Insulation (approx.8,500sqm @Rs.1000/ sqm) | 0 | 0.85 | 0% | 0% | 0 | 0
2.4 | Auxillary bag filters (approx. 12nos.) | 0 | 0.6 | 0% | 0% | 0 | 0
2.5 | Lubricants | 0 | 0.15 | 0% | 0% | 0 | 0
2.6 | Material receiving system (Bulk receiving units with truck tippler facility, 2 nos.) | 0 | 2.1 | 0% | 0% | 0 | 0
2.7 | Passenger lift (for CCR) | 0 | 0.25 | 0% | 0% | 0 | 0
2.8 | Roots blowers | 0 | 0.35 | 0% | 0% | 0 | 0
2.9 | Compressors & dryers | 0 | 0.6 | 0% | 0% | 0 | 0
2.10 | Misc. items like water pump & pipeline, compressed air piping, etc. | 0 | 0.6 | 0% | 0% | 0 | 0
2.11 | Cranes/Hoists and other miscellaneous items, etc. | 0 | 1 | 0% | 0% | 0 | 0
| Sub-total of Mechanical Auxiliary Equipment (2.0) | 0 | 22.55 |  |  | 0 | 1.16
| Total of Mechanical Equipment (1.0 + 2.0) | 24 | 82.3 |  |  | 0 | 1.16
3.0 | Electrical and Instrumentation
3.1 | HT motors | 0 | 2.35 | 0% | 0% | 0 | 0
3.2 | LV & MV AC variable Speed Drives | 0 | 1.65 | 0% | 0% | 0 | 0
3.3 | LT motors | 0 | 1.05 | 0% | 0% | 0 | 0
3.4 | Table-top XRF | 0 | 0.7 | 0% | 0% | 0 | 0
3.5 | Control & Automation | 0 | 2.6 | 0% | 0% | 0 | 0
| Total Electrical and Instrumentation (3.0) | 0 | 8.35 |  |  | 0 | 0
| Total Mechanical and Electrical equipment (1.0+2.0+3.0) | 24 | 90.65 |  |  | 0 | 1.16
4.0 | Landed cost of equipment
4.1 | Imported Equipment
4.1.1 | F.O.B. Cost | 24 |  | 0
4.1.2 | Provisioning for Ocean Freight, Insurance, etc. (approx.@6% of 4.1.1) | 1.45 |  | 0
4.1.3 | Basic Import Duty provision (approx. @7.5% of 4.1.1 & 4.1.2) | 1.9 |  | 0
4.1.4 | GST (all taxes assumed to be clubbed under GST, approx.@18% of 4.1.1 to 4.1.3) | 4.9 |  | 0
4.1.5 | Clearing/ Loading/ Inland Freight, etc. (approx.@5% of 4.1.1 + 4.1.2) | 1.25 |  | 0
| Sub-total of Imported Equipment (4.1) | 33.5 |  | 0
4.2 | Indigenous Equipment
4.2.1 | F.O.R. cost | 90.65 |  | 1.16
4.2.2 | GST provisioning on F.O.R. cost (@18% of 4.2.1) | 16.3 |  | 0.2088
4.2.3 | Provisioning for freight, handling, insurance, etc. (approx.@5% of 4.2.1) | 4.55 |  | 0.058
| Sub-total of Indigenous Equipment (4.2) | 111.5 |  | 1.4268
| Total Landed Cost of Equipment (4.1 + 4.2) | 145 |  | 1.4268
5.0 | Provisioning for Spares (approx. @5% of F.O.B. & F.O.R. landed cost) | 7.25 |  | 0.07134
6.0 | Fabrication of Str. Steel as in 2.1 above (2,250 t @Rs.20,000/ t) | 4.5 |  | 0.464
7.0 | Erection, Comissioning & Supervision Charges (approx.@12 % of F.O.R. + F.O.B.) | 13.75 |  | 0.17122
8.0 | GST on Fabrication, erection & supervision charges (approx.@18% on (6.0+7.0)) | 3.3 |  | 0.11434
| Total cost of Mechanical and Electrical equipment | 173.8 |  | 2.2477
A | Total landed cost of equipment | 173.8 |  | 2.2477
C | GST component on Plant & Machinery (approx. provisioning) | 24.5
B | Total landed cost of equipment (Net of GST) | 149.3 |  | 2.2477
1.505%
151.5477
151.5477
300
451.5477

## GU Power Distrbution (hidden)
Annexure 8.10
COST OF POWER DISTRIBUTION EQUIPMENT - GU
( In Lakhs INR Unless Specified Otherwise )
Sn. | Description | F.O.B. | F.O.R.
1 | Power distribution equipment
1.1 | Transmission line from Grid substation (33kV, approx.6 km) | - | 3.6
1.2 | Incomer switchyard & power trasnformer | - | 2
1.3 | 6.6 kV switchboard | - | 1.8
1.4 | 6.6 /0.433 kV distribution transformer | - | 1
1.5 | LT switchboard & trunking | - | 1.2
1.6 | MCC & push button Station | - | 2.1
1.7 | LV capacitors & control panel | - | 0.35
1.8 | Lighting transformer & main lighting distribution board | - | 0.6
1.9 | Cables (Power, Control & Instrumentation) | - | 3.75
1.10 | Construction power cables | - | 0.35
1.11 | Earthing, lighting protection & erection hardware |  | 1.5
1.12 | Plant Illumination | - | 0.15
1.13 | UPS, battery & battery charger | - | 0.25
1.14 | Ventilation system for electrical buildings | - | 0.2
1.15 | Air conditioning | - | 0.2
1.16 | PA system for intercom | - | 0.05
1.17 | Fire detection system | - | 0.15
1.18 | DG set for construction & emergency power supply | - | 1.25
1.19 | Miscellaneous electricals | - | 0.25
| Sub total (1.0) | 0 | 20.75
2.0 | Landed cost of equipment
2.1 | Imported Equipment
2.1.1 | F.O.B. Cost | 0
2.1.2 | Ocean Freight, Insurance, etc. (approx.@6% of 2.1.1) | 0
2.1.3 | Basic Import Duty (@7.5% of 2.1.1 & 2.1.2) | 0
2.1.4 | GST (all taxes assumed to be clubbed under GST, approx.@18% of 2.1.1 to 2.1.3) | 0
2.1.5 | Clearing/ Loading/ Inland Freight, etc. (approx.@5% of 2.1.1 + 2.1.2) | 0
| Sub-total of Imported Equipment (2.1) | 0
2.2 | Indigenous Equipment
2.2.1 | F.O.R. cost | 20.75
2.2.2 | GST provisioning on F.O.R. cost (@18% of 2.2.1) | 3.75
2.2.3 | Provisioning for freight, handling, insurance, etc. (approx.@5% of 2.2.1) | 1.05
| Sub total (2.0) | 25.55 | 0
| Total Landed Cost of Equipment (2.1 + 2.2) | 25.55
3.0 | Provisioning for Spares (approx. @5% of total landed cost) | 1.3
4.0 | Erection, Comissioning & Supervision Charges (approx.@12 % of 2.1.1 + 2.2.1) | 2.5
5.0 | GST on erection & supervision charges (approx.@18% of 4.0) | 0.45
A | Total landed cost of Power Distribution Equipment (2.0+3.0+4.0+5.0) | 29.8
C | GST component on Power distribution (approx. provisioning) | 4.2
B | Total landed cost of Power Distribution Equipment (Net of GST) | 25.6

## Constractors and suppliers (hidden)
HAMIRPUR PROJECT
Description | Vendor | Agreement Amount | Value (Rs. In Lakh)
LOI For environemnt Clearance for GU at Hamirpur | Environement and technical Research centre, Lucknow | 0.085 | 8.5 | 100
Preparation of TEFR for Proposed GU At Hamirpur, UP | Holtec consulting Pvt. Ltd. | 0.0785 | 7.85 | 100
Engg. Consultancy | Holtec consulting Pvt. Ltd. | 1.55 | 155 | 100
Raw mill and Cement mill for Hamirpur | loesche (India Part) | 39.38 | 3938 | 100
Raw mill and Cement mill for Hamirpur | loesche (Foreign Part) | 28.91 | 2891 | 100
Boundary wall construction | M/s Vishal Enterprises | 1.45 | 145 | 100
Packing plant for hamirpur | Beumer | 14.91 | 1491 | 100
Engg. Services | Loesche, India | 2.9418 | 294.18 | 100
Grand total as During 1st LIE Report |  | 89.3053 | 8930.53
PANNA PROJECT
Description | Vendor | Agreement Amount | Value (Rs. In Lakh)
Boundary wall construction | Apex Precast | 0.7436 | 74.36 | 100
Topographical Wall Construction | RK Consultants and Contractors | 0.2352 | 23.52 | 100
Consultancy for Water lifting from ken river | Vexl Environ Project private limited | 0.425 | 42.5 | 100
Master plan , architectural , landscape design and interior design services for panna colony | R+D Studio | 0.61 | 61 | 100
3.15 MVA 33.0.433 KVA Trasformer | Voltamp | 0.3215 | 32.15 | 100
Supply of TMT Bar | TATA Steel | 1.689 | 168.9 | 100
500 KVA DG Set | Sudhir Power limited | 0.2875 | 28.75 | 100
Brick masonary Boundary wall work at panna site | Jay shree mahakal contractor | 0.5999 | 59.99 | 100
Crushing system | L&T | 23.635 | 2363.5 | 100
WHRS | Thermax | 99.5 | 9950 | 100
ESP and Bag hOuse | Himenviro | 21.25 | 2125 | 100
Crushing system 2 years spare | L&T | 0.9575 | 95.75 | 100
Weigh Bridge 100 MT-4Nos. | Rice lake weighing systems india Limited | 0.557 | 55.7 | 100
Engg services | Loesche | 4.0698 | 406.98 | 100
Civl stacker, reclaimer, Pyro, blending and clinker silo, mech. Staker reclaimer | KEC International limited | 97.71 | 9771 | 100
TMT supply-4000MT/PMC Services | KEC International limited | 20.64 | 2064 | 100
Mechanical fabrication erection for Pyro | Hajee AP Bava | 53.5 | 5350 | 100
PMC services | Hajee AP Bava | 1.5 | 150 | 100
Civil and structural work, WHRS, Cement Mill, packing plant, Cement mill silo and Fly ash silo | Buildwell roject india pvt. Limited | 29.99 | 2999 | 100
Site grading and levelling work at panna | Karni Construction | 2.2685 | 226.85 | 100
Civil consultancy order | SecMec | 2.75 | 275 | 100
Road and Drainage work | Karni construction | 12.8294 | 1282.94 | 100
Mech. & E&I Consultancy | Holtec | 6.15 | 615 | 100
Civil work for workshop, Project office and Weighbridge | Shree ram associates | 2.5316 | 253.16 | 100
Piling works | Parul foundation | 2.66 | 266 | 100
Pre-Cast Boundary wall work at panna site | Tirupati Cemnt articles | 0.89 | 89 | 100
Cooler for Pyro | IKN engineering India pvt. Ltd. | 28.9528 | 2895.28 | 100
Raw mill and pyro | Thyssen | 143.81 | 14381 | 100
Raw mill and cement mill for Panna | loesche (India Part) | 73.13 | 7313 | 100
Raw mill and cement mill for Panna | loesche (Foreign Part) | 25.97 | 2597 | 100
Packing plant for Panna | Beumer | 21.99 | 2199 | 100
Pre cast boundary wall work at panna site | RKB Enterprise | 0.814 | 81.4 | 100
Precast boundary wall | Maharishi parashar Buildtech LLP | 0.435 | 43.5 | 100
Precast boundary wall | Mohira precast Narsingpur | 0.45 | 45 | 100
stacker and reclaimer | Takraf | 34.55 | 3455 | 100
Precast boundary wall | Tiranag precast | 0.3416 | 34.16 | 100
Construction cable | Havells india Limited | 0.5652 | 56.52 | 100
Construction of guest house and hostel block | M/s Asiatic | 4.594 | 459.4 | 100
Civil piling work | M/s KEC | 97.71 | 9771 | 100
Mineral exploration in Kakra block | M/s GDS India | 1.9709 | 197.09 | 100
Procurement of steel | SAIL Jabalpur | 15.2199 | 1521.99 | 100
Boundary wall construction | Amit singh Construction Company | 0.501 | 50.1 | 100
BLS type ambulance | CK Motor | 0.1798 | 17.98 | 100
Water lifting arrangement from ken river | M/s aanjana pump services | 3.15 | 315 | 100
hiring of hydraulic drilling rig | M/s National infra projects | 0.27 | 27 | 100
Hiring of 2nd Hydraulic drilling rig | M/s National infra projects | 0.27 | 27 | 100
Supply of 28mm TMT | JSPL | 2.64 | 264 | 100
Supply of MS Plate | Shakti steel | 0.7862 | 78.62 | 100
Oxygen/Nitrogen plant capacity 80 Cu. M | Sanghi organisation, Mumbai | 1.022 | 102.2 | 100
Rain protection cover | M/s ARDEE engineering | 40 | 4000 | 100
Service contract for steel procurement | Shree ganpatlal omkarlal agarwal and company | 1.95 | 195 | 100
Supply of Dry Fly Ash | Ramesh chand grover | 0.425 | 42.5 | 100
Civil structural work-Plant buildings | M.s kamal Builders | 15.25 | 1525 | 100
Civil structural work-Crusher section | M/s Karni | 9.23 | 923 | 100
Bought out items | Beumer | 8.3103 | 831.03 | 100
Bought out items | Mahindra tsubaki | 5.6485 | 564.85 | 100
Bought out items | Tsubaki | 2.3169 | 231.69 | 100
Bought out items | Beumer Germany | 4.8344 | 483.44 | 100
132 KV Transmission line | Suresh techno (India) LLP | 21 | 2100 | 100
Turbine for WHRS | Siemens | 12.9 | 1290 | 100
Steel supply | SAIL Indore | 3.3749 | 337.49 | 100
Site grading and levelling works | M/s Amit singh construction | 0.6988 | 69.88 | 100
Construction of Service road | M/s Amit singh construction | 0.43 | 43 | 100
Supply and instllation fo pre-fabricated security barrack | M/s tinny Craft | 0.63 | 63 | 100
Security services | SIS | 1.9764 | 197.64 | 100
Grand total as During 1st LIE Report |  | 976.5981 | 97659.81

## Cost of Project (hidden)
Land and Site Development | 497.65
Buildings and Civil Structures | 460.68
Plant and Machinery | 1496.87
Engineering & Know how | 15
Expense on training and foreign technicians | 8
Miscellaneous Fixed assets | 32.28
Pre-operative expenses including during IDC | 247.78
Contingency@7.5% | 197.1
Margin money for working capital | 14.94
Total Project Cost | 2970.3
Promoter’s Contribution (Equity) | 1291.44
Term Loan (Debt) | 1678.86