## EPC Claims
Barasat-Krishnagar Expressways Limited
EPC Contractor claims on BKEL
S. No. | Description | Amount
1 | Losses Due to Expenditure on Maintenance | 14620750
2 | Compensation due to Idling and Under Utilization of Plant & Machinery to full extent | 1308431314
3 | Losses due to idling/underutilisation of Manpower | 86172024
4 | Compensation due to delay in handing over of site | 597442507
5 | Losses due to Price Escalation on the works already executed | 1369946472
6 | Loss of overheads and profit | 1133600000
7 | Losses of Expenses incurred due ti Miscellaneous works | 50656748
8 | Losses incurred for Bank Guarantee
| a) BG submitted as per agreement | 433500000
| b) BG Commission Charges | 31200000
9 | Termination Payments at the rate of 10% of works which were not commenced/started | 466200000
10 | Loss of Business Opportunity and Profit due to delay in Release of Bank Guarantee | 232350000
11 | Loss of Goodwill @ 25% of Balance works | 1167500000
12 | Presuit pendente lite & future interest on 18% PA on all claims | 0
13 | Cost of Arbitration | 1500000
Total Claim Amount |  | 6893119815

## BKEL Claims
Barasat-Krishnagar Expressways Limited
BKEL claims against NHAI
S. No. | Description | Amount
1 | Losses Due to Expenses incurred on Cutting and Removal of trees | 3642476
2 | Loss due to Interest on Debt | 1976274739
3 | Loss due to Interest on Equity infused into the project | 1744700000
4 | Loss due to extra expenditure on maintenance | 14620750
5 | Losses due to idling/underutilization of Machinery and Equipment | 169068515
6 | Losses due to idling/underutilization of Manpower | 131540639
7 | Losses due to extension of Bank Guarantee | 221143403
8 | Losses due to miscellaneous expenditure incurred at site | 33984428
9 | Compensation due to delay in handing over of site | 574607968
10 | Losses due to expenses incurred on payment of fee of Independent Engineer | 47960883
11 | Losses due to Price Escalation on the works already executed | 1074872658
12 | Losses due to expenses incurred on the works executed | 3481600000
13 | Loss of overheads and profit | 569361758
14 | Termination Payment | 8267100000
15 | Presuit pendente lite & future interest on 18% PA on all claims | 1838945568
16 | Cost of Arbitration & Litigation | 0
Total Claim Amount |  | 20149423785

## NHAI Claims
Barasat-Krishnagar Expressways Limited
NHAI counter claims against BKEL
S. No. | Description | Amount
1 | Claim for recovery of repair and maintenance cost incurred by the authority on risk and cost of Concessionaire | 537051925
2 | Non-Reimbursement of 50% of fee amd expenses of Independent Engineer as per Clause 23.3 of Concession Agreement | 11753520
3 | Claim of Authority for Loss of Toll due to Concessionaire's Defaults | 3054006802
4 | Claim of Authority due to additional cost being the difference between the likely completion cost of the project and the cost of balance work as per terminated Concession Agreement - EPC cost of the Concessionaire | 6313700437
5 | Claim of Authority for recovering additional cost of new 4 Lane Multi-Cell box RUB at KM 112+215 entrusted to M/s ITD Cementation Ltd as Sub Contractor | 251395769
6 | Claim of Authority for reconstruction of newly constructed defective stretch from KM 51.092 to KM 52.310 and a structure (Jalangi Structure) | 87212774
7 | Delay damages for failure to achieve Milestone-II | 302149500
8 | Watch and ward of Concessionaire's camps | 89396
9 | Interest on delayed payment as per clause 47.5 | 0
10 | Pendent elite and future interest | 0
11 | Litigation costs | 0
12 | Cost of Arbitration | 0
Total Claim Amount |  | 10557360123

## Arbitration Method RK
Barasat-Krishnagar Expressways Limited
| Particulars | Amount (In Crs) | Remarks |  | No. of Years | 5 |  |  |  | 5
| Total Claim filed by the Company (A) | 2014.9424 | [7 empty] | 7
| Less: Award received so far out of (A) above (B) | 0 |  |  | Discount Rate
| Total Award Claimed (C) =(A-B) | 2014.9424 |  |  | Nifty 50 5-year return |  | 14% | https://kunaldesai.blog/nifty-returns/
| Less: Claims filed by EPC against the company (D) | 689.312 |  |  | Company Risk Premium |  | 2.5%
| Less: Counter claims by NHAI against the company ('E) | 1055.736 |  |  | Appropriate Discount Rate |  | 16.5%
| Total Award Claimed (F) =(C-D-E) | 269.8944
45% | Expected Realization out of F (G) | 121.4525 |  |  |  | 103.2346 | 0.46598
15% | Less: Expected Expenses to be incurred to realize the claim amount (H) | 18.2179 |  |  | NPV | 48.1056
| Claim Realization available for lenders (G-H) | 103.2346
| NPV as on date @ 13% | 48.1056 | Rolling Nifty CAGR for 10 years
| Total Available balance. | #REF! | As a proxy of Enterprise Value
| Enterprise Value | #REF!
| NPV(As a proxy of Enterprise Value) | 48.1056 | It is assumed that this will take around 5 years to get realized.
|  |  |  | Year | 1 | 2 | 3 | 4 | 5
|  |  |  | Net Recovery | 103.2346
|  |  |  | Yearly Recovery | 0 | 0 | 0 | 0 | 103.2346
|  |  |  | Discount period | 1 | 2 | 3 | 4 | 5
|  |  |  | Discount Factor | 0.85837 | 0.7368 | 0.63244 | 0.54287 | 0.46598
|  |  |  | Discount Rate | 16.5%
|  |  |  | Present Value | 0 | 0 | 0 | 0 | 48.1056
|  |  |  | Net Present Value (NPV) | 48.1056