File No.: VIS(2022-23)-PL460-367-645       	                            Dated: 22/11/2022

PROGRESS REPORT

OF

MACHINERIES & EQUIPMENTS

SITUATED AT

KHASRA NO. 361/2, 361/3, 396/1, VILLAGE BHOGPUR, PARGANA JWALAPUR, DISTRICT HARIDWAR, UTTARAKHAND

OWNER/S

M/S. POLYPALS GLOBAL PRIVATE LIMITED

REPORT PREPARED FOR

STATE BANK OF INDIA, SME BRANCH, RANIPUR, HARIDWAR

**Important - In case of any query/ issue or escalation you may please contact Incident Manager

at le@rkassociates.org. We will appreciate your feedback in order to improve our services.

NOTE: As per IBA Guidelines please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct.

| TABLE OF CONTENTS |  |  |
| --- | --- | --- |
| SR. NO. | DESCRIPTION | PAGE NO. |
| PART A | Report Summary | 4 |
| PART B | Introduction | 5 |
|  | - About the Project | 5 |
|  | - Location of the Project | 5 |
|  | - Project Overview | 6 |
|  | - Scope of the Report | 7 |
|  | - Purpose of the Report | 7 |
|  | - Methodology Adopted | 7 |
| PART C | Society Infrastructure Sections & Facility Details | 8 |
|  | - Land Details | 8 |
|  | - Project Infrastructure Details | 8 |
| PART D | Project Consultants, Contractors & Suppliers | 12 |
| PART E | Project Cost and Means of Finance | 13 |
|  | - Total Project Cost | 13 |
|  | - Current Status and Total Expenditure Incurred till Date | 13 |
| PART F | Project Schedule & Current Status | 15 |
|  | - Project Schedule Chart | 15 |
|  | - Current Status | 15 |
| PART G | Statutory & Regulatory Approvals, Clearances & NOC | 17 |
| PART H | Documents of the Project | 18 |
| PART I | Site Photographs | 26 |
| PART J | Disclaimers | 29 |
|  | Annexure (Details of Invoices provided) | 32 |

# IMPORTANT NOTICE

COPYRIGHT FORMAT: This report is prepared on the copyright format of R.K Associates, to serve our clients with the best available information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format by any organization or individual other than R.K Associates will be seen as unlawful act and necessary legal action can be taken against the defaulters.

This report is intended for the sole use of the intended recipient/s and contain material that is STRICTLY CONFIDENTIAL AND PRIVATE.

DEFECT LIABILITY PERIOD: - In case of any query/ issue or escalation you may please contact Incident Manager: @ le@rkassociates.org. We try our level best to ensure correctness in the calculations done, rates adopted and various other data points & information mentioned in the report but still can’t rule out typing, human errors or any other mistakes. In case you find any such mistake or inaccuracy in any data point of the report please help us by bringing all such points into our notice immediately or within 15 days of the report delivery in writing, to rectify these timely failing after which R.K Associates won’t be held responsible for any such inaccuracy in any manner. We would highly appreciate your feedback in order to improve our services.

| PART A | REPORT SUMMARY |
| --- | --- |

- Name of the Company			          M/S. Polypals Global Private Limited

- Location	Khasra No. 361/2, 361/3, 396/1, Village                        Bhogpur, Pargana Jwalapur, District Haridwar, Uttarakhand

- Prepared for Bank		          State Bank of India, SME Branch, Ranipur, Haridwar

- Date of Survey			          21st November 2022

- Date of Report			          22nd November 2022

- Report type			          Progress Report

- Purpose of the Report	          Review & evaluate progress of the machineries to be installed, capital expenditure

- Scope of the Report		          To assess, evaluate & comment on

Reasonableness & sufficiency of:

- Capital expenditures

- Physical progress of the machines installed

- Documents produced for perusal	          CAPITAL EXPENDITURE

DETAILS:

- Invoices

- CA Certificate

- Annexure with the Report		          1. Site Photographs

2. PO/ PI/ Invoices

3. Trial Balance Sheet

4. CA Certificate

| PART B | INTRODUCTION |
| --- | --- |

- ABOUT THE COMPANY: M/s Polypals Global Private Limited is a rigid PVC sheet manufacturing plant located at Khasra No. 361/2, 361/3, 396/1, Village Bhogpur, Pargana Jwalapur, District Haridwar, Uttarakhand.

- REPORT OVERVIEW: M/s Polypals Global Private Limited is a rigid PVC sheet manufacturing plant that is currently being installed at Khasra No. 361/2, 361/3, 396/1, Village                        Bhogpur, Pargana Jwalapur, District Haridwar, Uttarakhand.

The progress of the machineries and equipments that are being installed in the subject plant is incorporated in this report and the capital expenditure incurred related to the machines.

As per site visit on 21/11/2022, few machines are purchased and installed out of the total machines as per the list of machines presented to us by the client, the details of which is stated in the report below.

- SCOPE OF THE REPORT:

- Review current status of the machines to be installed in the plant.

- Review capital expenditure incurred for the respective machines installing.

- Review position of various statutory, non-statutory clearances and regulatory clearances obtained by the company.

- This report doesn’t cover any technical check of the machines, verification of vendors/ suppliers, verification of any document from Govt. department, any legal matter or any other point other than the above-mentioned points.

- PURPOSE OF THE REPORT: To provide fair detailed analysis report to the bank based on the “in-scope points” mentioned above subject to the details/ data/ information provided by the client for facilitating bank to take appropriate decision in regard to credit facility extended for the machines in the plant.

- METHADOLOGY ADOPTED:

- Site Survey

- Review & analysis of the progress of the machines to be installed in the plant and the capital expenditure incurred related to the machines.

- Compilation & Preparation of the report based on “in scope points”.

- Report submission.

| PART C | DETAILS OF MACHINES AND EQUIPMENTS TO BE INSTALLED |
| --- | --- |

- MACHINERY DETAILS: The list of machines and equipments along with the supplier’s name provided by the client is shown below:

| LIST OF MACHINES |  |
| --- | --- |
| S. NO. | NAME OF MACHINERY |
| 1 | AIR COMPRESSOR (PMGC) |
| 2 | THERMIC FLUID HEATER (NEOTECH) |
| 3 | COOLING TOWER (NORTH STREET) |
| 4 | CALENDER LINE (SHANGHAI) |
| 5 | CORE CUTTING |
| 6 | ONLINE SHEET CUTTING (EN PLAST) |
| 7 | SLITTING MACHINE (GUPTA ENTERPRISES) |
| 8 | DG SET 400KVA (JAKSON) |
| 9 | DG SET 200KVA (JAKSON) |
| 10 | EOT CRANE (VENUS ENGINEERS) |
| 11 | QA TESTING (DEEPAK POLYPLAST) |
| 12 | CORONA TREATMENT SYSTEM (IEEC) |
| 13 | AIR HANDLING UNIT (INFANITE) |
| 14 | FIRE FIGHTING SYSTEM |
| 15 | TRANSFORMER 800KVA (JAYBEE INDUSTRIES) |
| 16 | SERVO STABLIZER (RED PHASE) |
| 17 | ELECTRIC PANEL (ZAD) |
| 18 | MACHINE INSTALLATION (SK ENGINEER) |
| 19 | MISC TOOLS (SKARC) |
| 20 | X RAY SCANNER (JASCH) |
| 21 | INDUSTRIAL PROCESS CHILLER (REYNOLD) |
| 22 | GRINDER MACHINE (VIJAY ENGINEER) |
| 23 | MISC TOOLS (INDUSTRIAL EQUIPMENT SYNDICATE) |

As per the observation by the surveyor during the site survey, the following machines are present in the plant:

| LIST OF MACHINES |  |  |
| --- | --- | --- |
| S. NO. | NAME OF MACHINERY | STATUS |
| 1 | AIR COMPRESSOR (PMGC) | Purchased |
| 2 | THERMIC FLUID HEATER (NEOTECH) | Not yet purchased |
| 3 | COOLING TOWER (NORTH STREET) | Not yet purchased |
| 4 | CALENDER LINE (SHANGHAI) | Not yet purchased |
| 5 | CORE CUTTING | Not yet purchased |
| 6 | ONLINE SHEET CUTTING (EN PLAST) | Not yet purchased |
| 7 | SLITTING MACHINE (GUPTA ENTERPRISES) | Not yet purchased |
| 8 | DG SET 400KVA (JAKSON) | Purchased & installed |
| 9 | DG SET 200KVA (JAKSON) | Purchased & installed |
| 10 | EOT CRANE (VENUS ENGINEERS) | Purchased & installed |
| 11 | QA TESTING (DEEPAK POLYPLAST) | Not yet purchased |
| 12 | CORONA TREATMENT SYSTEM (IEEC) | Not yet purchased |
| 13 | AIR HANDLING UNIT (INFANITE) | Not yet purchased |
| 14 | FIRE FIGHTING SYSTEM | Purchased |
| 15 | TRANSFORMER 800KVA (JAYBEE INDUSTRIES) | Purchased |
| 16 | SERVO STABLIZER (RED PHASE) | Purchased |
| 17 | ELECTRIC PANEL (ZAD) | Not yet purchased |
| 18 | MACHINE INSTALLATION (SK ENGINEER) | Not yet purchased |
| 19 | MISC TOOLS (SKARC) | Purchased |
| 20 | X RAY SCANNER (JASCH) | Not yet purchased |
| 21 | INDUSTRIAL PROCESS CHILLER (REYNOLD) | Not yet purchased |
| 22 | GRINDER MACHINE (VIJAY ENGINEER) | Not yet purchased |
| 23 | MISC TOOLS (INDUSTRIAL EQUIPMENT SYNDICATE) | Not yet purchased |

| PART E | PROJECT COST & MEANS OF FINANCE |
| --- | --- |

- TOTAL PROJECT COST: Complete project cost and its breakup has not been provided to us. However, proposed cost for building construction is mentioned in Engineer’s Certificate dated 11/06/2022 uploaded on RERA and also as forwarded by the Bank, as per which the total proposed project cost for the subject three blocks was estimated to be Rs.13.29 Cr. which includes Rs.12.29 Cr. for the buildings/blocks and Rs.1.00 Cr. for the internal and external development of the project as shown below:

| Estimated cost to be incurred in | Amount (in Rs. Cr.) |
| --- | --- |
| a. Building | 12.29 |
| b. Internal and external development | 1.00 |
| Total | 13.29 |

`

- TOTAL EXPENDITURE INCURRED TILL DATE OF THIS REPORT:

- Expenditure as per Developer: As per the CA Certificate dated: 15/10/2022, the total project expenditure incurred has been tabulated below:

| Sr. No. | Particulars | Cost Incurred (In Rs. Cr.) |
| --- | --- | --- |
| 1 | Land | 6.62 |
| 2 | Construction and Site Development | 7.05 |
| Total Project Cost incurred |  | 13.67 |

- Expenditure as per LIE:

  - Land:

  - Building & Civil Works

- In respect to the expenditure of the construction only Rs.2.5 Cr. amount of bills have been provided to us. However, work has been done more than this.

- Therefore, in the absence of any proper breakup of expenses and invoices we have estimated the expenditure incurred based on the percentage of work completed and the market rate for such kind of construction.

- As per the market trend and our engineering experience of the similar projects we are of the opinion to adopt the construction cost for similar type of structures to be averagely Rs.1,900/- per sq. ft. with all finishing and ready to use structure. This cost does not include the soft cost such as IDC charges, Labour Cost, Architectural fees, Approval fees, advance to suppliers etc. The same has not been vetted by us.

- Considering the same as the base rate of construction, the estimated cost incurred as on date of this report has been tabulated below:

| S.No. | Particulars | Estimated Cost Incurred (in Rs.) |  |  | Total: A+B+C (in Rs.) |
| --- | --- | --- | --- | --- | --- |
|  |  | Block A | Block B | Block C |  |
| 1 | Excavation, Concrete for Foundation & Plinth | 44,17,500 | 47,02,500 | 47,02,500 | 1,38,22,500 |
| 2 | Superstructure Concrete & Brickwork | 73,62,500 | 78,37,500 | 3,91,875 | 1,55,91,875 |
| 3 | Roof Slab | 44,17,500 | 47,02,500 | - | 91,20,000 |
| 4 | Flooring | 2,94,500 | - | - | 2,94,500 |
| 5 | Plastering & Painting | 11,78,000 | 6,27,000 | - | 18,05,000 |
| 6 | Door, Windows & Woodwork | 22,97,100 | 16,30,200 | - | 39,27,300 |
| 7 | Water supply, Sanitary Fittings, Electrification, Lifts & Others | 17,67,000 | 13,32,375 | - | 30,99,375 |
| Total |  | 2,17,34,100 | 2,08,32,075 | 50,94,375 | 4,76,60,550 |
| Boundary Wall and Site Development |  |  |  |  | 30,00,000 |
| Grand Total |  |  |  |  | 5,06,60,550 |

- As per our estimation, building construction cost incurred in the three blocks is Rs.5.07 Cr. upto 15/10/2022.

- Amount paid in advance to suppliers has not been considered in this assessment.

  - Internal and external development:

- Presently as a part of Internal and external development, boundary wall is erected with some other developments. However, the plaster on the boundary on the boundary wall has not been done.

- Around Rs.30,00,000/- has been estimated to have incurred in the boundary wall and other developments based on its current status and type.

  - Total Expenditure estimated as per LIE:

| Sr. No. | Particulars | Cost Incurred (in Rs. Cr.) |  |
| --- | --- | --- | --- |
|  |  | as per CA Certificate | as per RKA |
| 1 | Land | 6.62 | 6.62 |
| 2 | Building | 7.05 | 5.07 |
| 3 | Internal and external development |  | 0.30 |
| Total Project Cost incurred |  | 13.67 | 11.99 |

NOTE: The above cost approved by us does not include the soft cost such as IDC charges, Labour Cost, Architectural fees, Approval fees, advance to suppliers, etc. which may have been considered in CA Certificate as per books of accounts/ records of the developer company The same has not been vetted by us.

| PART F | PROJECT SCHEDULE & CURRENT STATUS |
| --- | --- |

- PROJECT SCHEDULE CHART:

| Sr. No. | As per Developer |  |  |
| --- | --- | --- | --- |
|  | Nature of work | Commencement Status | Completion Status |
| 1 | Land Acquisition | Already acquired | Already acquired |
| 2 | Plan Approvals | Already acquired | Already acquired |
| 3 | Land Development | Already Done | Already Done |
| 4 | Foundation & Plinth | Already Done | Already Done |
| 5 | RCC Columns & Slabs | May-2021 | December-2022 |
| 6 | Brick Work | May-2021 | December-2022 |
| 7 | Electrical Plumbing & Drainage | December-2021 | December-2022 |
| 8 | Internal & External Plaster | December-2021 | December-2022 |
| 9 | Bath Tiles & Flooring | December-2021 | December-2022 |
| 10 | Sanitary & Bath Fitting | December-2021 | December-2022 |
| 11 | Aluminium Section & Door Fitting | December-2021 | December-2022 |
| 12 | Colour Work | December-2021 | December-2022 |
| 13 | Common Development | December-2021 | December-2022 |
| 14 | Elevation work & others | December-2021 | December-2022 |

Source: Developer company

Remarks:

- Above completion status is as provided by the company.

- However, based on the current progress of the work when Block C is only at the plinth level, major finishing work in Block A & B is remaining and internal and external development work is also pending, in our estimate the Project completion may stretch beyond the above timeline.

- CURRENT STATUS:

The current status of the project is summarized in the table below mentioning the important activities and the construction works:

| S. No. | Particulars | Block A | Block B | Block C |
| --- | --- | --- | --- | --- |
| 1 | Civil Structure | Completed | Completed | Only foundation work completed |
| 2 | Brick/Block Work | Completed | Completed | Not started yet |
| 3 | Electrical | In progress | In progress | Not started yet |
| 4 | Plumbing | In progress | In progress | Not started yet |
| 5 | Plastering | In progress | In progress | Not started yet |
| 6 | Lifts | Not started yet | Not started yet | Not started yet |
| 7 | Flooring - Apartment area | In progress | Not started yet | Not started yet |
| 8 | Flooring - Corridor | In progress | Not started yet | Not started yet |
| 9 | Doors / Window frames | Completed | Completed | Not started yet |
| 10 | Doors / Windows | In progress | Not started yet | Not started yet |
| 11 | Paint Work | In progress | Not started yet | Not started yet |

As per the observation during the site survey and as per our eye-estimation/ visual observation, the current status of the project is as described in the table below:

| Sr. No. | Particulars | Estimated | Completed |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Block A | Block B | Block C |
| 1 | Excavation, Concrete for Foundation & Plinth | 15% | 100% | 100% | 100% |
| 2 | Superstructure Concrete & Brickwork | 25% | 100% | 100% | 5% |
| 3 | Roof Slab | 15% | 100% | 100% | 0% |
| 4 | Flooring | 5% | 20% | 0% | 0% |
| 5 | Plastering & Painting | 10% | 40% | 20% | 0% |
| 6 | Door, Windows & Woodwork | 13% | 60% | 40% | 0% |
| 7 | Water supply, Sanitary Fittings, Electrification, Lifts & Others | 17% | 35% | 25% | 0% |
| Total |  | 100% | 74% | 66% | 16% |
| Grand Total |  |  | 52% |  |  |

As per the observation made during the site visit, construction of the subject project is approx. 50% is complete.

| PART G | STATUTORY & REGULATORY APPROVALS, CLEARANCES & NOC |
| --- | --- |

| Sr. No. | NAME OF LICENSE/ REGISTRATION | PURPOSE | DATE OF ISSUE | Current Status |
| --- | --- | --- | --- | --- |
|  | ISSUING AUTHORITY |  | LICENCE NO. |  |
| 1. | Building Plan Approval | Building Plan | 29/12/2021 | Obtained |
|  | Meerut Development Authority |  | MDA/BP/20-21/0870 |  |
| 2. | Sanction of Power Load | Electricity | --- | Not Obtained |
|  | Uttar Pradesh Power Corporation Limited |  | Connection No/ --- |  |
| 3. | Fire Safety Clearance | Firefighting | 07/02/2021 | Obtained |
|  | Fire Department, Meerut |  | UPFS/2021/27488/MRT/ MEERUT/300/CFO |  |
| 4. | Architect’s Certificate | Architect’s Certificate | 11/06/2022 | Obtained |
|  | Ar. Vinay Goel |  | --- |  |
| 5. | RERA Permission | Construction Approval | 08/08/2022 | Obtained |
|  | Uttar Pradesh- Real Estate Regulatory and Authority |  | UPRERAPRJ273592 |  |
| 6. | Water Connection | Water | Yes, proposed as per RERA | Not Available |
|  | Ground Water Department, Government of Uttar Pradesh |  |  |  |
| Observations & Comments: - Aashiyana Greenwood has obtained the above-mentioned preliminary & statutory approvals from different government agencies. - Also, no document related to Water Connection and Electricity has been shared with us. |  |  |  |  |

| PART H | DOCUMENTS OF THE PROJECT |
| --- | --- |

RERA Certificate

CA Certificate

Architect’s Certificate:

Engineer’s Certificate:

NOC for Construction of Project

Fire NOC

Environmental Clearance Certificate

| PART I | SITE PHOTOGRAPHS |
| --- | --- |

Block A

Block B

Block C and site development

| PART J | DISCLAIMERS |
| --- | --- |

      - No employee or member of R.K Associates has any direct/ indirect interest in the Project.

      - This report is prepared based on the copies of the documents/ information which interested organization or customer could provide to us out of the standard checklist of documents sought from them and further based on our assumptions and limiting conditions. All such information provided to us has been relied upon and we have assumed that it is true and correct. Verification or cross checking of the documents provided to us has not been done at our end from the originals. If at any time in future, it’s found or came to our knowledge that misrepresentation of facts or incomplete or distorted information has been provided to us then this report shall automatically become null & void.

      - This report is a general analysis of the project and not an audit report. All the information gathered is based on the facts seen on the site during survey, verbal discussion & documentary evidence provided by the client and is believed that information given by the company is true best of their knowledge.

      - All observations mentioned in the report is only based on the visual observation and the documents/ data/ information provided by the client. No mechanical/ technical tests, measurements or any design review have been performed or carried out from our side during Project assessment.

      - Bank/FII should ONLY take this report as an Advisory document from the Financial/ Chartered Engineering firm and it’s specifically advised to the creditor to cross verify the original documents for the facts mentioned in the report which can be availed from the borrowing company directly.

      - In case of any default in loans or the credit facility extended to the borrowing company, R.K Associates shall not be held responsible for whatsoever reason may be and any request for seeking any explanation from the employee/s of R.K Associates will not be entertained at any instance or situation.

      - This Report is prepared by our competent technical team which includes Engineers and financial experts & analysts.

      - This is just an opinion report and doesn’t hold any binding on anyone. It is requested from the concerned Financial Institution which is using this report for taking financial decision on the project that they should consider all the different associated relevant & related factors also before taking any business decision based on the content of this report.

      - All Pages of the report including annexures are signed and stamped from our office. In case any paper in the report is without stamp & signature then this should not be considered a valid paper issued from this office.

      - Defect Liability Period is 30 DAYS. We request the concerned authorized reader of this report to check the contents, data and calculations in the report within this period and intimate us in writing if any corrections are required or in case of any other concern with the contents or opinion mentioned in the report. Corrections only related to typographical, calculation, spelling mistakes will be entertained within the defect liability period. No request for any illegitimate value revision, date change or any other facts & figures changes will be entertained other than the one mentioned above.

      - R.K Associates encourages its customers to give feedback or inform concerns over its services through proper channel at le@rkassociates.org in writing within 30 days of report delivery. After this period no concern/ complaint/ proceedings in connection with the Valuation Services can be entertained due to possible change in situation and condition of the property.

      - Our Data retention policy is of ONE YEAR. After this period, we remove all the concerned records related to the assignment from our repository. No clarification or query can be answered after this period due to unavailability of the data.

      - This Valuation report is governed by our (1) Internal Policies, Processes & Standard Operating Procedures, (2) R.K Associates Quality Policy, (3) Valuation & Survey Best Practices Guidelines formulated by management of R.K Associates, (4) Information input given to us by the customer and (4) Information/ Data/ Facts given to us by our field/ office technical team. Management of R.K Associates never gives acceptance to any unethical or unprofessional practice which may affect fair, correct & impartial assessment and which is against any prevailing law. In case of any indication of any negligence, default, incorrect, misleading, misrepresentation or distortion of facts in the report then it is the responsibility of the user of this report to immediately or atleast within the defect liability period bring all such act into notice of R.K Associates management so that corrective measures can be taken instantly.

      - R.K Associates never releases any report doing alterations or modifications from pen. In case any information/ figure of this report is found altered with pen then this report will automatically become null & void.

      - If this report is prepared for the matter under litigation in any Indian court, no official or employee of R.K Associates will be under any obligation to give in person appearance in the court as a testimony. For any explanation or clarification, only written reply can be submitted on payment of charges by the plaintiff or respondent which will be 10% of the original fees charged where minimum charges will be Rs.15,000/-.

Place	:	Noida

Date	:	21/10/2022

Note	:	This report contains 33 pages

For R.K Associates Valuers & Techno

Engineering Consultants Pvt. Ltd.

| SURVEY ANALYST | VALUATION ENGINEER | L1/ L2 REVIEWER |
| --- | --- | --- |
| Pankaj Goswami | Manas Upmanyu | Adil Afaque |

DEFECT LIABILITY PERIOD - In case of any query/ issue or escalation you may please contact Incident Manager by writing at valuers@rkassociates.org. We ensure 100% accuracy in the Calculations done, Rates adopted and various other data points & information mentioned in the report but still can’t rule out typing, human errors or any other mistakes. In case you find any mistake, variation, discrepancy or inaccuracy in any data point of the report, please help us by bringing all such points into our notice in writing at valuers@rkassociates.orgwithin 30 days of the report delivery, to get these rectified timely, failing which R.K Associates Valuers Techno Engineering Consultants (P) Ltd. won’t be held responsible for any inaccuracy in any manner. Also if we will not hear back anything from you within 30 days, we will assume that report is correct in all respect and no further claim of any sort will be entertained thereafter. We would welcome and appreciate your feedback & suggestions in order to improve our services.

COPYRIGHT FORMAT - This report is prepared on the copyright format of R.K Associates Valuers Techno Engineering Consultants (P) Ltd. to serve our clients in the best possible way. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the organization as mentioned on the cover page of this report. Distribution or use of this format other than R.K Associates will be seen as unlawful act and necessary legal action can be taken against the defaulter.

ANNEXURE

The table below shows the details of the invoices provided by the bank/client:

| Sr. No. | Invoice No. | Date | Supplier Name | Amount (in Rs.) |
| --- | --- | --- | --- | --- |
| 1 | JHR23INV014031 | 05-07-2022 | Wonder Cement Ltd- | 2,60,000 |
| 2 | SSCA/ 530/ 20-21 | 31-12-2020 | Shyam Steel & Cement Agency | 1,31,615 |
| 3 | FGH22/P/17776 | 13-05-2022 | Shree Cement Ltd- | 1,29,600 |
| 4 | FGH/22/P/17775 | 13-05-2022 | Shree Cement Ltd- | 1,58,400 |
| 5 | RST/22-23/164 | 14-06-2022 | Rudra Steel & Traders | 1,31,480 |
| 6 | RST/22-23/109 | 24-05-2022 | Rudra Steel & Traders | 8,54,400 |
| 7 | B66 | 22-09-2022 | Perfect Iron Sales | 3,62,235 |
| 8 | B45 | 19-09-2022 | Perfect Iron Sales | 2,48,302 |
| 9 | B40 | 19-09-2022 | Perfect Iron Sales | 3,29,997 |
| 10 | B64 | 22-09-2022 | Perfect Iron Sales | 3,19,604 |
| 11 | B57 | 21-09-2022 | Perfect Iron Sales | 4,13,728 |
| 12 | 380 | 22-06-2022 | Perfect Iron Sales | 2,59,423 |
| 13 | 375 | 20-06-2022 | Perfect Iron Sales | 2,72,572 |
| 14 | 366 | 20-06-2022 | Perfect Iron Sales | 2,78,233 |
| 15 | 362 | 20-06-2022 | Perfect Iron Sales | 2,64,837 |
| 16 | 092 | 19-04-2022 | Perfect Iron Sales | 4,29,952 |
| 17 | 1873 | 29-03-2022 | Perfect Iron Sales | 22,57,652 |
| 18 | 1837 | 20-03-2022 | Perfect Iron Sales | 1,69,951 |
| 19 | 1789 | 10-03-2022 | Perfect Iron Sales | 1,94,806 |
| 20 | 1620 | 09-02-2022 | Perfect Iron Sales | 16,94,510 |
| 21 | 1612 | 08-02-2022 | Perfect Iron Sales | 2,65,284 |
| 22 | 1453 | 15-01-2022 | Perfect Iron Sales | 15,99,576 |
| 23 | 1231 | 10-12-2021 | Perfect Iron Sales | 16,25,991 |
| 24 | 1110 | 21-11-2021 | Perfect Iron Sales | 1,26,331 |
| 25 | 987 | 29-10-2021 | Perfect Iron Sales | 19,07,431 |
| 26 | 511 | 29-07-2021 | Perfect Iron Sales | 14,39,665 |
| 27 | 377 | 08-07-2021 | Perfect Iron Sales | 21,99,965 |
| 28 | 949 | 18-02-2021 | Perfect Iron Sales | 1,48,422 |
| 29 | 3320 | 23-03-2021 | M/s Vidhyut Sales (2020-21) | 2,04,499 |
| 30 | T22230166 | 05-09-2022 | Mayur International | 2,40,906 |
| 31 | T22230041 | 02-06-2022 | Mayur International | 1,50,947 |
| 32 | T22230037 | 25-05-2022 | Mayur International | 1,00,585 |
| 33 | T20210140 | 31-03-2021 | Mayur International | 1,70,649 |
| 34 | 76 | 08-10-2022 | Maheshwari Timbers | 1,69,989 |
| 35 | 74 | 29-09-2022 | Maheshwari Timbers | 2,92,365 |
| 36 | 70 | 19-09-2022 | Maheshwari Timbers | 2,51,016 |
| 37 | KS/3308/21-22 | 10-03-2022 | Kanti Steel | 2,26,512 |
| 38 | 1779 | 21-11-2021 | Kansal Traders | 1,20,000 |
| 39 | CG/07444/ 2021 | 12-12-2021 | Kanodia Cement Ltd- | 1,81,179 |
| 40 | CG/05990/ 2021 | 20-10-2021 | Kanodia Cement Ltd- | 1,61,263 |
| 41 | 1122/ 22-23 | 19-06-2022 | Ishwar Chandra Kamlesh Kumar | 2,13,451 |
| 42 | 4229/ 21-22 | 27-03-2022 | Ishwar Chandra Kamlesh Kumar | 2,27,138 |
| 43 | 0287/ 21-22 | 28-04-2021 | Ishwar Chandra Kamlesh Kumar | 1,32,150 |
| 44 | IKG22-23/ 636 | 16-05-2022 | IKG Hardware Solutions Pvt- Ltd- | 1,11,315 |
| 45 | IKG22-23/ 615 | 14-05-2022 | IKG Hardware Solutions Pvt- Ltd- | 3,76,874 |
| 46 | IDEAL/ 22-23/0431 | 28-06-2022 | Ideal Laminates Pvt- Ltd- | 1,07,616 |
| 47 | 431 | 15-09-2022 | Harish Marble & Gramotes | 1,27,555 |
| 48 | GE/ 21-22/ 1034 | 01-03-2022 | Gaurav Enterprises | 1,37,754 |
| 49 | 2236 | 26-08-2022 | Flourish Ply & Veneer | 2,10,897 |
| 50 | 1329 | 22-06-2022 | Flourish Ply & Veneer | 1,78,416 |
| 51 | 1186 | 12-06-2022 | Flourish Ply & Veneer | 1,29,897 |
| 52 | 229 | 04-08-2022 | Earth Care (India) Pvt- Ltd- | 1,02,900 |
| 53 | 228 | 04-08-2022 | Earth Care (India) Pvt- Ltd- | 1,71,500 |
| 54 | 888 | 21-03-2022 | Earth Care (India) Pvt- Ltd- | 1,69,000 |
| 55 | 815 | 24-02-2022 | Earth Care (India) Pvt- Ltd- | 1,45,340 |
| 56 | 657 | 31-12-2021 | Earth Care (India) Pvt- Ltd- | 1,69,000 |
| 57 | 581 | 13-12-2021 | Earth Care (India) Pvt- Ltd- | 1,52,100 |
| 58 | 486 | 06-11-2021 | Earth Care (India) Pvt- Ltd- | 1,54,350 |
| 59 | 452 | 25-10-2021 | Earth Care (India) Pvt- Ltd- | 1,37,200 |
| 60 | 145 | 18-05-2022 | Avantika Electricals (2022-23) | 1,98,155 |
| 61 | 720 | 26-02-2022 | Avantika Electricals (2021-22) | 1,27,074 |
| 62 | 2856 | 15-06-2022 | Shree Mahaveer Traders | 46,198 |
| 63 | 2692 | 11-06-2022 | Shree Mahaveer Traders | 46,800 |
| 64 | 2645 | 10-06-2022 | Shree Mahaveer Traders | 44,800 |
| 65 | 2588 | 09-06-2022 | Shree Mahaveer Traders | 42,000 |
| 66 | 2486 | 07-06-2022 | Shree Mahaveer Traders | 48,750 |
| 67 | 2373 | 04-06-2022 | Shree Mahaveer Traders | 48,000 |
| 68 | 2335 | 03-06-2022 | Shree Mahaveer Traders | 49,400 |
| 69 | 2295 | 02-06-2022 | Shree Mahaveer Traders | 48,000 |
| 70 | 2258 | 01-06-2022 | Shree Mahaveer Traders | 49,400 |
| 71 | 2239 | 01-06-2022 | Shree Mahaveer Traders | 48,750 |
| 72 | GE/22-23/0302 | 18-08-2022 | Gaurav Enterprises | 33,742 |
| 73 | GE/22-23/0291 | 10-08-2022 | Gaurav Enterprises | 29,761 |
| 74 | GE/22-23/0263 | 31-07-2022 | Gaurav Enterprises | 18,199 |
| 75 | GE/22-23/0256 | 28-07-2022 | Gaurav Enterprises | 10,161 |
| 76 | GE/22-23/0222 | 06-07-2022 | Gaurav Enterprises | 10,650 |
| 77 | GE/22-23/0221 | 05-07-2022 | Gaurav Enterprises | 46,932 |
| 78 | GE/22-23/0191 | 25-06-2022 | Gaurav Enterprises | 19,713 |
| 79 | GE/22-23/0185 | 23-06-2022 | Gaurav Enterprises | 48,368 |
| 80 | GE/22-23/0383 | 17-09-2022 | Gaurav Enterprises | 11,877 |
| 81 | GE/22-23/0374 | 10-09-2022 | Gaurav Enterprises | 26,901 |
| 82 | GE/22-23/0176 | 21-06-2022 | Gaurav Enterprises | 45,661 |
| 83 | GE/22-23/0141 | 10-06-2022 | Gaurav Enterprises | 10,650 |
| 84 | GE/22-23/0140 | 10-06-2022 | Gaurav Enterprises | 22,433 |
| Total |  |  |  | 2,50,30,700 |