## XLSTART
MACHINE LIST |  | Status | Invoice | Performa Invoice
S.NO | NAME OF MACHINERY
1 | AIR COMPRESSOR (PMGC) | Purchased | 1298000
2 | THERMIC FLUID HEATER (NEOTECH) | Not yet purchased
3 | COOLING TOWER (NORTH STREET) | Not yet purchased
4 | CALENDER LINE (SHANGHAI) | Not yet purchased |  | 31119218 | 407800 | 2022-03-10
5 | CORE CUTTING | Not yet purchased
6 | ONLINE SHEET CUTTING (EN PLAST) | Not yet purchased |  | 1711000
7 | SLITTING MACHINE (GUPTA ENTERPRISES) | Not yet purchased |  | 3363000
8 | DG SET 400KVA (JAKSON) | Purchased & installed | 2950000
9 | DG SET 200KVA (JAKSON) | Purchased & installed | 1475000
10 | EOT CRANE (VENUS ENGINEERS) | Purchased & installed | 1939684
11 | QA TESTING (DEEPAK POLYPLAST) | Not yet purchased
12 | CORONA TREATMENT SYSTEM (IEEC) | Not yet purchased |  | 973500
13 | AIR HANDLING UNIT (INFANITE) | Not yet purchased
14 | FIRE FIGHTING SYSTEM | Purchased
15 | TRANSFORMER 800KVA (JAYBEE INDUSTRIES) | Purchased | 944000
16 | SERVO STABLIZER (RED PHASE) | Purchased | 619500
17 | ELECTRIC PANEL (ZAD) | Not yet purchased |  | 25709.84
18 | MACHINE INSTALLATION (SK ENGINEER) | Not yet purchased
19 | MISC TOOLS (SKARC) | Purchased | 38126
20 | X RAY SCANNER (JASCH) | Not yet purchased |  | 2596000
21 | INDUSTRIAL PROCESS CHILLER (REYNOLD) | Not yet purchased |  | 826000
22 | GRINDER MACHINE (VIJAY ENGINEER) | Not yet purchased
23 | MISC TOOLS (INDUSTRIAL EQUIPMENT SYNDICATE) | Not yet purchased
|  |  | 9264310 | 40614427.84 | 49878737.84
| om enterprises |  | 351257 | 2022-08-23
|  |  | 47731 | 2022-08-24
|  |  | 48380 | 2022-08-25
|  |  | 621130 | 2022-10-14
|  |  | 47200 | 2022-10-15
|  |  | 49501 | 2022-10-17
|  |  | 35400 | 2022-10-29
|  |  | 35400 | 2022-10-31
|  |  | 147500 | 2022-11-01
1383499
10647809

## progress
LIST OF MACHINES AND EQUIPMENTS
S. NO. | NAME OF MACHINERY | STATUS | INVOICES RECEIVED
1 | AIR COMPRESSOR (PMGC) | Purchased | 1298000
2 | THERMIC FLUID HEATER (NEOTECH) | Not yet purchased
3 | COOLING TOWER (NORTH STREET) | Not yet purchased
4 | CALENDER LINE (SHANGHAI) | Not yet purchased
5 | CORE CUTTING | Not yet purchased
6 | ONLINE SHEET CUTTING (EN PLAST) | Not yet purchased
7 | SLITTING MACHINE (GUPTA ENTERPRISES) | Not yet purchased
8 | DG SET 400KVA (JAKSON) | Purchased & installed | 2950000
9 | DG SET 200KVA (JAKSON) | Purchased & installed | 1475000
10 | EOT CRANE (VENUS ENGINEERS) | Purchased & installed | 1939684
11 | QA TESTING (DEEPAK POLYPLAST) | Not yet purchased
12 | CORONA TREATMENT SYSTEM (IEEC) | Not yet purchased
13 | AIR HANDLING UNIT (INFANITE) | Not yet purchased
14 | FIRE FIGHTING SYSTEM | Purchased
15 | TRANSFORMER 800KVA (JAYBEE INDUSTRIES) | Purchased | 944000
16 | SERVO STABLIZER (RED PHASE) | Purchased | 619500
17 | ELECTRIC PANEL (ZAD) | Not yet purchased
18 | MACHINE INSTALLATION (SK ENGINEER) | Not yet purchased
19 | MISC TOOLS (SKARC) | Purchased | 38126
20 | X RAY SCANNER (JASCH) | Not yet purchased
21 | INDUSTRIAL PROCESS CHILLER (REYNOLD) | Not yet purchased
22 | GRINDER MACHINE (VIJAY ENGINEER) | Not yet purchased
23 | MISC TOOLS (INDUSTRIAL EQUIPMENT SYNDICATE) | Not yet purchased
24 | Other Misc. Items (OM ENTERPRISES) | Purchased | 1383499
Total |  |  | 10647809
| om enterprises |  | 351257
47731
48380
621130
47200
49501
35400
35400
147500
1383499
2766998