File No.: VIS(2022-23)-PL533-430-741		          		        Dated: 12/10/2023

INDEPENDENT ENGINEERING REPORT

OF

SECOND EXPANSION PROJECT

OF

STEEL MANUFACTURING PLANT

SITUATED AT

PLOT NO. AL-05, SECTOR-23, GIDA INDUSTRIAL AREA, SAHJANWA, DISTRICT GORAKHPUR - 273209, UTTAR PRADESH

COMPANY/PROMOTER

M/S. GALLANTT ISPAT LIMITED

REPORT PREPARED FOR

THE PRADESHIYA INDUSTRIAL & INVESTMENT CORPORATION OF U.P. LIMITED (PICUP), PICUP BHAWAN, GOMTI NAGAR, LUCKNOW-226010 (INDIA)

**Important - In case of any query/ issue or escalation you may please contact Incident Manager at le@rkassociates.org. We will appreciate your feedback in order to improve our services.

NOTE: Please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct.

IMPORTANT NOTICE

COPYRIGHT FORMAT: This report is prepared on the copyright format of R. K. Associates Valuers & Techno Engineering Consultants (P) Ltd. (R. K. Associates) to serve our clients with the best possible information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format by any organization or individual other than R.K Associates will be seen as an unlawful act and necessary legal action can be taken against the defaulters.

This report is intended for the sole use of the intended recipient/s and contains material that is STRICTLY CONFIDENTIAL AND PRIVATE.

DEFECT LIABILITY PERIOD: In case of any query/ issue or escalation you may please contact Incident Manager at valuers@rkassociates.org. Though adequate care has been taken while preparing this report as per its scope, but still, we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it shall be considered that the report is complete in all respect and has been accepted by the client up to their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

R.K Associates Important Notes and Part G–Disclaimer are integral part of this report and Value is assessment is subject to both of these sections. Reader of the report is advised to read all the points mentioned in these sections carefully.

| TABLE OF CONTENTS |  |  |
| --- | --- | --- |
| SECTIONS | PARTICULARS | PAGE NO. |
| Part A | REPORT SUMMARY | 03 |
| Part B | INTRODUCTION | 05 |
|  | - Name of the Project | 05 |
|  | - Project Overview | 05 |
|  | - Project Location | 08 |
|  | - Scope of the Report | 09 |
|  | - Purpose of the Report | 09 |
|  | - Survey Details | 09 |
|  | - Methodology Adopted | 10 |
| Part C | PROJECT TECHNICAL DETAILS | 11 |
|  | - Plant Capacity | 11 |
|  | - Plant Production Chart | 11 |
| Part D | PROJECT INFRASTRUCTURE SECTIONS & FACILITY DETAILS | 13 |
|  | - Land Details | 13 |
|  | - Building & Structural Details | 14 |
|  | - Plant Machinery & Equipment | 17 |
|  | - Miscellaneous Fixed Assets | 19 |
| Part E | PROJECT CONSULTANTS, CONTRACTORS & SUPPLIERS | 20 |
| Part F | PROJECT COST & EXPENDITURE | 21 |
|  | - Total Project Cost | 21 |
|  | - Current Stratus & Total Expenditure incurred till date | 22 |
| Part G | PHOTOGRAPHS OF THE PLANT | 71 |
| Part H | DISCLAIMER | 74 |

| PART A | REPORT SUMMARY |
| --- | --- |

- Name of the Project                                    :	    Second Expansion Project of Steel Manufacturing Plant for added capacity of 1,98,000 TPA along with Captive Power Plant capacity addition of 25 MW.

- Project Location                           	:      	Plot No. AL-05, Sector-23, GIDA

Industrial Area, Sahjanwa, Gorakhpur

District, Uttar Pradesh

- Name of the Company/Promoter               :      	M/s. Gallantt Ispat Limited

Gallantt Landmark, Bank Road, District

Gorakhpur, 273001, Uttar Pradesh

- Prepared for Organization           	:            The Pradeshiya Industrial & Investment Corporation of U.P. Ltd.  (PICUP)                                                           PICUP Bhawan, Gomti Nagar, Lucknow

- Chartered Engineer Firm                            :            M/s. R.K. Associates Valuers & Techno

Engineering Consultants (P) Ltd.

- Date of Survey			           :	 February 14, 2023

- Date of Report                                	:      	October 12, 2023

- Report Type                                     	:      	Independent Engineering Report

- Purpose of the Report                    	:      	To examine the installation & verification

of Capital expenditure status of the Project

in regard to the special facilities &

incentives given to the companies

Expansion Project under Industrial Investment & Employment Promotion Policy 2017.

- Scope of the Report                         	:      	The scope of this report includes only

the assessment & verification of

installation, commissioning and capital

expenditure incurred in Phase-I, Phase-II & Phase-III (WIP) of the Project namely Gallantt Ispat Limited located at Sahjanwa, Gorakhpur, Uttar Pradesh.

- Documents produced for Perusal	:       	a. Detailed Project Report

b. Copies of Project Contracts

c. List of Invoices with Description of the

Items

d. Invoices of Items

f.  CA Certificate (w.r.t. investment)

g. Information received on e-mail

- Annexure with the Report               	:    	1. Work Orders Copies

2. Detailed List of Items

3. Photographs

4. Other annexures

| PART B | INTRODUCTION |
| --- | --- |

- NAME OF THE PROJECT: Second Expansion Project of Steel Manufacturing Plant for added capacity of 3,23,400 TPA in four phases out of which 1,98,000 TPA along with Captive Power Plant capacity addition of 25 MW which has been set-up by Gallantt Ispat Limited (GIL) at Sahjanwa, Gorakhpur District of Uttar Pradesh.

- PROJECT OVERVIEW: Gallant Ispat Ltd. is presently operating an integrated steel plant at GIDA Industrial area, Sahjawana, Gorakhpur, Uttar Pradesh. Company was granted Letter of Comfort vide Corporation ref. no. PICUP/Mega Project/ Gallant/258 dated: 09.07.2015 for their expansion mega project of existing integrated steel plant/ power plant for increase in production of sponge iron, steel, billets, MS bars, etc. along with captive power production of 25 MW with capital investment of Rs.378 Crore The first expansion assessment upto 31.03.2018 was already covered by us in our report ref. no. RKA/FY18-19/794 dated: 01.04.2019.

Further to it, the company was issued another Letter of Comfort (LoC) dated 14.11.2018 subsequent revised LoC dated 7.1.2022 under Industrial Investment & Employment Promotion Policy 2017 by Govt. of U.P for expansion & backward integration of existing steel plant (hereinafter referred as “the second expansion”) with a capital investment of Rs.850.62 Crore in four phases at Plot No. AL-5, Sector-23, GIDA, Sahjanwa, District- Gorakhpur from 01.04.2018 onwards.

The company informed that they have implemented the Phase-I & Phase-II of the second expansion project and Phase-III is in progress with a total investment of Rs.535.41 Crore during the period 01.04.2018 to 31.03.2022 in the project to PICUP.

Therefore, PICUP has engaged R.K Associates for the assessment and verification of the factual position of investment (phase wise) made by the company from cut-off date 1/04/2018 till achieving the threshold of investment of Rs. 500 Crore or more (for Super Mega category projects) as per provisions/requirements (para 2.3.2 and 2.9) of the GO dated 25/10/2017 pertaining to the scheme.

This is second expansion brown field Project of an existing running unit of Gallantt Ispat Ltd. (GIL). Existing running unit mainly consists of Steel Melt Shop (SMS), Rolling Mill (Rebar Mill), Direct Reduce Iron (DRI) and Captive Power Plant (CPP).

Company has proposed expansion of the capacity of the existing facilities in four phases out of which details of two phases mainly Steel Melt Shop (SMS), Rolling Mill (Rebar Mill) in Phase-I and Direct Reduce Iron (DRI) and Captive Power Plant (CPP) in Phase-II as per the below table. Currently Phase-I & Phase-II have been completed and Phase-III is under progress which includes the Pellet Plant.

Project Summary of the existing Unit and the expansion Project:

Capacity (in Mts.)

| Product (s) Units | Existing Capacity | Proposed Expansion Capacity |  |  |  | Total Capacity after expansion |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Phase-I | Phase-II | Phase-III | Phase-IV |  |
| Steel Billet | 330000 | 1,98,000 | --- | --- | 1,25,400 | 6,53,400 |
| Rolling Mill | 330000 | 1,98,000 | --- | --- | 1,32,000 | 6,60,000 |
| Electricity (Power) | 53 MW | --- | 25 MW | --- | --- | 78 MW |
| Sponge Iron | 297000 | --- | 2,47,500 | --- | 1,15,500 | 6,60,000 |
| Pellet | --- | --- | --- | 7,92,000 | --- | 7,92,000 |

Source: DPR report

Presently, work on Phase-I & Phase-II has been completed and Phase-III work is in progress. Accordingly, it has been analyzed and verified in this report.

As per the Detailed Project Report, the total project cost for second expansion is estimated to be Rs.850.62 Crore in four phases. The amount estimated in Phase I is Rs.188.97 Crore, Rs.241.03 Crore in Phase-II, Rs.190.35 Crore in Phase-III (which is under progress) and Rs.230.27 Crore in Phase-IV (yet to be started).

The Project Cost for Phase-I is Rs.188.97 Crore and for Phase-II is Rs.241.03 Crore out of which the company has shown to have invested Rs.187.95 Crore in Phase-I, Rs.252.64 Crore in Phase-II and Rs.94.82 Crore in Phase-III (CWIP). However, IE has approved the total cost is Rs.504.02 Crore [Rs.175.50 Crore in Phase-I, Rs.242.31 Crore in Phase-II and Rs.86.21 Crore in Phase-III (CWIP)]. Detailed information regarding the expenditure in various heads like Land, Buildings, Plant & Machinery etc. was sought from the company and also cross-verified during the site survey. All these details are enumerated in further sections of the report.

The scope of this report includes only the assessment & verification of installation, commissioning and capital expenditure incurred till achieving the threshold of investment of Rs.500 Crore or more in different phases of the project namely Gallantt Ispat Limited located at Sahjanwa, Gorakhpur, Uttar Pradesh. As per the details provided by the company, the threshold of Rs.500 Crore was achieved on 01.04.2022.

Company has obtained some preliminary statutory, non-statutory approvals & clearances (Petroleum & explosive storage license, Boiler License, etc.) and Building Plan Approval is yet to be obtained from Assistant Director of Factories, Gorakhpur.

GIL is presently operating on the land parcel measuring 112.69 acres (acquired 116.86 acres of land in GIDA Industrial Area in which 4.170 acres of land has been surrendered to the GIDA later) bounded for Plant purpose. This piece of land was already acquired prior to 1.04.2018. The existing plant has already been running on this land and proposed expansion facilities are also setup on the existing portion of this piece of land which was earlier used as a green area. Further, GIL has acquired additional land parcel measuring 6.2 acres in between 01.04.2018 upto 31.03.2021 and 4.47 acres of land upto 31.03.2022 totaling 10.67 acres of land upto 31.03.2022. In replacement of the existing land which is utilised in the present Project, company has bought additional land across the road adjacent to the Plant which will be used for future expansion.

- PROJECT LOCATION: The plant is located in about 112.69 acres of land in GIDA Industrial Area in Gorakhpur District of Uttar Pradesh, India. Further, the company has acquired another 10.67 acres of land in two phases (6.2 acres and 4.47 acres) as on 31.03.2022.

Plant site is around 20 Kms. from Gorakhpur city and the plant boundary is right on National Highway No. 24 (Gorakhpur - Delhi Highway).

The nearest city is Gorakhpur around 20 kms from the plant site. The nearest airport is Gorakhpur Airport which is around 21 kms from plant site. Sahjanwa Railway station is the nearest railway station around 3 kms from the plant for the transportation of raw materials as well as finished products.

- SCOPE OF THE REPORT: To verify and examine the commissioning, installation and capital expenditure incurred till achieving the threshold of investment of Rs.500 Crore or more in different phases of the project established by Gallantt Ispat Limited in regard to availing special facilities & incentives given to Mega Projects under Industrial Investment & Employment Promotion Policy 2017 of Govt. of U.P.

All the assessment carried out for the project is done based on the documents provided to us and its correlation by the Engineering team through site inspection and various other discussions with the project proponents and its able resources and thus forming an opinion out of it.

- PURPOSE OF THE REPORT:  To provide a comprehensive overview of the current status of the project in terms of its physical progress and capital expenditure incurred to help PICUP to take informed business decision on the project in relation to special facilities & incentives given to Mega Projects under Industrial Investment & Employment Promotion Policy 2017 of Govt. of U.P.

- SURVEY DETAILS: This plant has been surveyed by our Engineering team comprising of Civil & Mechanical Engineers on February 14, 2023. Site inspection was done in the presence of the plant representatives. All the details pertaining to physical setup and progress of the plant have been cross checked as per the documents/ information provided to us.

Team visited different sections of the plant such as SMS, DRI, CPP, Rolling, Pellet etc. The plant and all its installed machinery equipments are found to be operational and in working condition.

The photographs have been taken of all different sections of the plant to give a clear visual representation of the plant establishment.

Comparison has also been drawn that what was already established prior to 01.04.2018 and physical changes and progress in the Plant post 01.04.2018.

As per the discussion during the survey, the Phase-I was completed on 01.04.2021 and Phase-II was completed on 01.04.2022. Also, at the time of survey, the part of the plant under expansion of Phase-I & Phase-II was found operational and the expansion of Phase-III is in progress.

- METHADOLOGY ADOPTED:

- Study of Detailed Project Report to know the Project proposed plan & estimates.

- Study of Project Work Orders, Purchase Orders & Invoices.

- Site visit by our engineering team to assess the project execution status on the ground at the site.

- Various documents and information collected from the company through e-mail.

- Study and analysis of the documents and information obtained from the company and their correlation with the observations during site survey.

- Other information obtained regarding the project from the sources in the public domain.

| PART C | PROJECT TECHNICAL DETAILS |
| --- | --- |

- PLANT CAPACITY: Total steel manufacturing capacity of the plant is distributed among several sections for the manufacturing of different products. After expansion and upgradation this plant will be elevated to the following capacity as described in the below table:

Capacity (in Mts.)

| Product (s) Units | Existing Capacity | Proposed Expansion Capacity |  |  |  | Total Capacity after expansion |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Phase-I | Phase-II | Phase-III | Phase-IV |  |
| Steel Billet | 330000 | 1,98,000 | --- | --- | 1,25,400 | 6,53,400 |
| Rolling Mill | 330000 | 1,98,000 | --- | --- | 1,32,000 | 6,60,000 |
| Electricity (Power) | 53 MW | --- | 25 MW | --- | --- | 78 MW |
| Sponge Iron | 297000 | --- | 2,47,500 | --- | 1,15,500 | 6,60,000 |
| Pellet | --- | --- | --- | 7,92,000 | --- | 7,92,000 |

Source: DPR report

- PLANT PRODUCTION CHART: During the survey, we have taken the plant production chart from the company as mentioned below:

| PART D | PLANT INFRASTRUCTURE SECTIONS & FACILITY DETAILS |
| --- | --- |

- LAND DETAILS: GIL is presently operating on the land parcel measuring 112.69 acres (acquired 116.86 acres of land in GIDA Industrial Area in which 4.170 acres of land has been surrendered to the GIDA later) bounded for Plant purpose. This piece of land was already acquired prior to 1.04.2018. The existing plant has already been running on this land and proposed expansion facilities are also setup on the existing portion of this piece of land which was earlier used as a green area. Further, GIL has acquired additional land parcel measuring 6.2 acres in between 01.04.2018 upto 31.03.2021 and 4.47 acres of land upto 31.03.2022 totaling 10.67 acres of land upto 31.03.2022. In replacement of the existing land which is utilised in the present Project, company has bought additional land across the road adjacent to the Plant which will be used for future expansion.

| PARTICULARS | DETAILS |
| --- | --- |
| Total Land Area purchased in expansion | Phase-I: 6.2 Acres Phase-II: 4.47 Acres Total: 10.67 Acres |
| Location | GIDA Industrial Area, Sahjanwa, Gorakhpur, Uttar Pradesh |
| Total Estimated Cost allocated | Phase-I: Rs.3.25 Crore Phase-II: Rs.11.75 Crore Total: Rs.15 Crore |
| Total Money shown by the company during April’18 to March’22 | Phase-I: Rs.3.25 Crore Phase-II: Rs.1.23 Crore Total: Rs.4.48 Crore |
| Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 3.21 Crore Phase-II: 1.09 Crore TOTAL: 4.30 Crore |

Observation & Comments: - The company has shown to have acquired 6.2 acres of land as on 31.03.2021 amounting to Rs.3.25 Crore and 4.47 acres of land as on 31.03.2022 amounting to Rs.1.23 Crore totalling 10.67 acres of land as on 31.03.2022 amounting to Rs.4.48 Crore. - However, the amount approved is as per the sale amount mentioned in the provided Deeds including the Stamp charges and Registration charges are taken as 1% (as per https://igrsup.gov.in). - As per the details of the deeds provided to us, copy of one land deed dated 10.06.2021 which amounts to Rs.17,33,794/- is not available. As per the discussion the GIL team, that particular deed is at the registrar office due to some official reason. IE have considered only those deeds whose copies are available and mentioned in the list.

- BUILDING & STRUCTURAL DETAILS: As per the proposed expansion plan following blocks & sections have been built Phase wise in processing sections as shown below:

For Phase-I

| S. No. | Factory Building | Length (in mtr.) | Width (in mtr.) | Height (in mtr.) | Area (in sq.mtr.) |
| --- | --- | --- | --- | --- | --- |
| SMS |  |  |  |  |  |
|  | Main Shed | 42.00 | 90.00 | 21.14 | 3,780.00 |
|  | Billet Shed | 24.00 | 88.65 | 15.00 | 2,127.60 |
|  | CCM Pulpit | 5.46 | 7.46 | 3.80 | 40.73 |
|  | Panel & Control Building | 60.00 | 8.40 | 4.60 | 504.00 |
|  | VFD Panel Room | 14.50 | 7.70 | 5.40 | 111.65 |
|  | Bag Store | 16.30 | 16.18 | 6.80 | 263.73 |
|  | LRF Building | 35.60 | 8.15 | 11.30 | 290.14 |
|  | Tundish Room | 8.00 | 7.85 | 5.40 | 62.80 |
|  | Lab -1 | 3.20 | 3.20 | 3.00 | 10.24 |
|  | Lab -2 | 8.00 | 5.00 | 5.35 | 40.00 |
|  | Workshop | 24.30 | 8.00 | 8.00 | 194.40 |
| SLAG CIRCUIT |  |  |  |  |  |
| 1 | Slag Circuit Control Room (Sqm) | 22.3 | 8.4 | 5.6 | 187.32 |
| ROLLING MILL |  |  |  |  |  |
| 1 | Rolling Mill Shed | 130.50 | 26.65 | 17.83 | 3,477.83 |
| 2 | Rolling Mill Shed | 130.50 | 29.60 | 17.83 | 3,862.80 |
| 3 | Rolling Mill Shed | 130.50 | 26.65 | 17.83 | 3,477.83 |
| 4 | Rolling Mill Shed | 45.00 | 25.25 | 17.83 | 1,136.25 |
| 5 | Air Handling Unit Room | 12.30 | 4.30 | 4.00 | 52.89 |
| 6 | East Side Panel Room GF | 14.50 | 4.80 | 2.65 | 69.60 |
| 7 | East ECR Panel Room 1st Floor | 29.10 | 4.80 | 4.13 | 139.68 |
| 8 | West ECR Panel Room G+ 1st Floor | 78.30 | 7.40 | 8.20 | 579.42 |
| 9 | Block Mill Panel & Control Room | 11.55 | 6.53 | 3.65 | 75.42 |
| 10 | CNC Machine Room | 20.00 | 5.20 | 2.75 | 104.00 |
| 11 | Lab | 8.40 | 4.45 | 3.20 | 37.38 |
| 12 | Panel Room on Lab | 11.46 | 4.46 | 3.80 | 51.11 |
| 13 | Reheating Furnace Shed | 29.30 | 15.50 | 8.00 | 454.15 |
| MISCELLANEOUS |  |  |  |  |  |
| 1 | Meter Room | 3.25 | 3.25 | 3.00 | 10.56 |
| 2 | Cement Storage Shed (2Nos) | 13.85 | 12.30 | 4.80 | 333.39 |
|  |  | 13.70 | 11.90 | 4.80 |  |
| 3 | Substation (1.5) | 20.10 | 13.80 | 6.60 | 416.07 |
| 4 | RMC Panel Room | 6.50 | 5.07 | 3.00 | 32.96 |
| 5 | Guard Room Main Gate | 10 | 4.15 | 3.3 | 41.50 |

For Phase-II

| S. No. | Factory Building | Length (in mtr.) | Width (in mtr.) | Height (in mtr.) | Area (in sq.mtr.) |
| --- | --- | --- | --- | --- | --- |
| SPONGE- 600TPD |  |  |  |  |  |
| 1 | CONTROL ROOM (4 FLOORS) | 29,23.93 | 8.48,8.48 | 4.6 | 919.69 |
| 2 | RMHS ROOM | 8 | 10 | 4.6 | 200.00 |
| 3 | DG ROOM SHED | 10.43 | 7.86 | 5 | 81.98 |
| POWER PLANT |  |  |  |  |  |
| 1 | RICE HUSK SHED | 101 | 32 | 14.6 | 3,232.00 |
| 2 | BED MATERIAL SHED | 17 | 4.4 | 4.5 | 74.80 |
| 3 | AIR PRESSURIZATION SYSTEM BUILDING-1 | 13 | 8 | 6.3 | 104.00 |
| 4 | AIR PRESSURIZATION SYSTEM BUILDING- 2 | 13 | 8 | 6.3 | 104.00 |
| 5 | MAINTATANCE SHED | 15.15 | 7.75 | 6.3 | 117.41 |
| 6 | COMPRESOR ROOM | 24.9 | 10.5 | 4.6 | 261.45 |
| MISCELLANEOUS |  |  |  |  |  |
| 19 | COAL SHED | 80.85 | 52.70 | 24.37 | 4,260.80 |
| 20 | WAGON TIPPLER MCC BULDING (3 FLOORS) | 15.40 | 5.50 | 3.80 | 254.10 |

For Phase-III (CWIP)

| S. No. | Factory Building | Length (in mtr.) | Width (in mtr.) | Height (in mtr.) | Area (in sq.mtr.) |
| --- | --- | --- | --- | --- | --- |
| PELLET |  |  |  |  |  |
| 1 | PGP COAL SHED (41X10.6) |  |  | 12.35 | 434.60 |
| 2 | FILTER CAKE STORAGE (66 X 20 MTRS) | 66.00 | 20 | 8.00 | 1,320.00 |
| 3 | PCI COAL STORAGE SHED (20X24) | 20.00 | 24 | 7.00 | 480.00 |

Gallantt Ispat Limited has shown to have incurred an amount of Rs.133.55 Crore to construct basic infrastructure like the factory buildings, non-factory buildings, boundary wall etc. bifurcated in Civil structures and foundation works. Civil work for foundation of setting up machines are considered in Building & Civil works head.

Provided site plan doesn’t show area chart of the covered area. However, drawings of buildings are provided and has been cross-checked on sample basis during the site survey.

| Total allocated amount | Phase-I: 55.71 Crore Phase-II: 50.12 Crore Phase-III: 45.05 Crore TOTAL: 150.88 Crore |
| --- | --- |
| Expenses shown by the company | Phase-I: 55.71 Crore Phase-II: 51.41 Crore Phase-III (CWIP): 26.44 Crore TOTAL: 133.56 Crore |
| Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 49.82 Crore Phase-II: 43.88 Crore Phase-III (CWIP): 22.43 Crore TOTAL: 116.13 Crore |
| Observations & Remarks: - As shown by the company Building & Civil works cost is distributed into 2 parts: Buildings and Foundation work. - Building cost is evaluated based on type of structure and its area. For Foundation work, company has provided the RCC quantity and its rate and accordingly it is evaluated. - Area of the Buildings is cross-checked on sample basis against the drawings during the site visit as provided by the company. - For verifying the quantity of RCC, certificates from the consultants have been taken and have to be relied upon who have prepared the drawings in the absence of AutoCad / StaadPro drawings which are enclosed in annexure with this report. - We have verified the cost based on the rates as per the market industry standards. Calculation and working of Civil & Structure Works and Foundation Works rates is shown in later section Part-F of the report below along with the remarks/ comments and the detailed breakup of the same. - Area measurement of some of the buildings are cross verified at the site either manually or through digital google measurement which was found to be similar as provided by the company and as per the site plan based on which the assessment is done. - As per the details shared by the PICUP, an investment of Rs.75,00,000/- is shown related to construction before April 2018. The same has been deducted from the approved amount. |  |

- PLANT MACHINERY & EQUIPMENT: GIL has established following facilities as new & expanding the existing units:

| Expansion & Upgraded Production Units |  |  |  |  |
| --- | --- | --- | --- | --- |
| S. No. | Production Units | Unit Capacity | Product | Annual Production (TPD) |
| 1. | Steel Melting Shop |  |  |  |
|  | Induction Furnace | 2 Nos. with 30 Ton crucible per heat | Liquid Steel | 600 |
|  | Continuous Casting Machine (CCM) for Billet | 1 New Strand | Billets | 600 |
|  | Material handling system for EAF & LF: | NA | Cranes / Scrap Transfer Trolley | NA |
| 2. | Rebar Mill | Total 14 new strands with complete line of rolling along with cooling bed etc. | TMT Rebars | 600 |
| 3. | DRI | One new Kiln installed with 750 TPD Capacity | Sponge Iron | 750 |
| 4. | Captive Power Plant (CPP) | New Turbine of 25 MW Capacity is installed of Siemens | Electricity | 25 MW |
|  |  | Boiler Capacity & Nos.: 1- WHRB Boiler - 70 TPH |  |  |
| Total allocated amount |  | Phase-I: 128.33 Crore Phase-II: 161.67 Crore Phase-III: 124.36 Crore TOTAL: 414.36 Crore |  |  |
| Expenses shown by the company |  | Phase-I: 128.33 Crore (inclusive of Miscellaneous Fixed Assets cost of Rs.20.52 Crore) Phase-II: 147.99 Crore Phase-III (CWIP): 64.70 Crore TOTAL: 341.02 Crore |  |  |
| Approved by IE incurred in the period (April’ 2018 – March’ 2022) |  | Phase-I: 101.96 Crore (after transferring Rs.20.52 Crore of Miscellaneous Fixed Assets to Miscellaneous Fixed Assets head) Phase-II: 147.28 Crore Phase-III (CWIP): 63.77 Crore TOTAL: 313.01 Crore |  |  |
| Observations & Remarks: - As shown by the company Plant & Machinery cost is distributed into 2 parts: Machinery cost as purchased and Steel fabrication for inhouse built machines. - For purchased machinery, the company has provided us the detailed cost sheet having list of assets/ works of different sections along with the description of assets, supplier name, invoice number, date of invoice etc. Steel fabrication list is separately provided which included the section wise steel quantity and rates. - As per these sheets only review of the cost has been done. The working of the same is shown in the later section of the report in Part-F in the table below. - For Phase – 1, as per IE analysis, the amount shown to have completely incurred into Plant & Machinery includes Miscellaneous Fixed Assets as well. For Phase-2, GIL has shown Plant & Machinery and Miscellaneous Fixed Assets separately. - During IE review, for Phase-I cost analysis, we have separated Miscellaneous Fixed Assets amounting of Rs.20.52 Crore from Plant & Machinery cost. - The amount related to Repair & Maintenance shown in the detailed excel sheet has not been considered in the approved amount. - The quantity of steel has been considered as per the drawings and the certificate provided by the CE. - For Captive Power Plant (CPP), the cost approved for the Plant & Machinery, Civil Structures, Foundation Work and Steel structures is Rs.70.52 Crore which is the cost incurred in Phase-II. - Amount considered is based on the Break-up of expenditure, Copy of Bills/ invoices provided to us. - As per the List of the items, Break-up of expenditure provided by the company, some of the items are capitalized before April 2018 related to Rolling Section which amounts to Rs.2,26,82,000/-. The same has not been included in the approved amount. |  |  |  |  |

- MISCELLANEOUS FIXED ASSETS: The items capitalized under miscellaneous fixed assets includes Factory equipments, Electrical Installation, Pollution Equipments, Furniture & Fixtures, Office Equipments, Railway Siding & Wagon Tippler.

| Total allocated amount | Phase-I: 0.00 Phase-II: 0.00 Phase-III: 0.00 TOTAL: 0.00 |
| --- | --- |
| Expenses shown by the company | Phase-I: 0.00 (Rs.20.52 Crore shown under P&M head which is considered by us in Miscellaneous Fixed Assets) Phase-II: 52.01 Crore Phase-III (CWIP): 3.69 Crore TOTAL: 55.70 Crore |
| Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 20.52 Crore (after transferring Rs.20.52 Crore of Miscellaneous Fixed Assets to Miscellaneous Fixed Assets head) Phase-II: 50.06 Crore Phase-III (CWIP): 0.00 TOTAL: 70.58 Crore |
| Observations & Remarks: - As per IE analysis, the amount incurred under Plant & Machinery section in Phase-I also includes some amount that contains assets related to Miscellaneous items, so the same has been shown under this head instead of Plant & Machinery section in Phase-I which equates to Rs.20.52 Crore. - Miscellaneous Fixed asset items mainly includes Factory equipments, Electrical Installation, Pollution Equipments, Furniture & Fixtures, Office Equipments, Railway Siding & Wagon Tippler. The cost incurred under Furniture & Fixtures and Office Equipments amounting Rs.21,568/- in Phase-I and Rs.1,47,29,617/- in Phase-II has not been considered in the approved cost as per the IIEPP Rules-2017. - Since, no bifurcation of the amount is provided to us for the amount incurred under Miscellaneous (CWIP) in Phase-III amounting of Rs.3.69 Crore, therefore, we have not considered the same in the approved amount. - Amount considered is based on the List of the items, Break-up of expenditure, Copy of Bills/ invoices provided to us. - The amount related to Repair & Maintenance shown in the detailed excel sheet has not been considered in the approved amount. - As per the List of the items, Break-up of expenditure provided by the company, some of the items are capitalized before April 2018 related to Railway Siding which amounts to Rs.1,85,20,963/-. The same has not been included in the approved amount. |  |

| PART E | PROJECT CONSULTANTS, CONTRACTORS & SUPPLIERS |
| --- | --- |

GIL has engaged many OEM, Contractors & Suppliers during the inception of the project which includes Supply, Erection, Construction, Testing & Commissioning. Supplier’s details with their scope of work are given below:

| S. No. | Supplier Name | Details |
| --- | --- | --- |
| 1 | M/s Bharat Heavy Electricals Ltd | Supply & Supervision of Electron & Commissioning with 2 Years Operational Spares |
| 2 | M/s Rail Udyog | Railway Siding |
| 3 | M/s Thermax Babcock & Wilcox Energy Solution Pvt Ltd | WHRB for 600 TPD |
| 4 | M/s. Electrotherm (India) Limited | Medium Frequency Induction Furnace for SMS Project at Gorakhpur |
| 5 | M/s. Asian Cranes & Elevators | Double Beam E.O.T Cranes |
| 6 | M/s SV Control Systems | PLC and VFD Panel |
| 7 | M/s Onlead Energy Concentrix | Copper Busduct & WRM Pump House Panel |
| 8 | M/s Concast India Private Ltd | Continuous Casting Machine |
| 9 | M/s Komatsu India Pvt Ltd | Hydraulic Excavator |
| 10 | M/s Airtech Engineers | Kaeser Make Rotary Screw Air Comp |
| 11 | M/s Armech Engineers Pvt Ltd | Equipments for Wire Rod Block Mill |
| 12 | M/s Shanthi Gears Limited | Double Helical Gear Box |
| 13 | M/s Brokk Ab | Remote Controlled Electro Hydraulically Driven Demolition Machine |
| 14 | M/s Newfield Engineers Pvt Ltd | Roll Stand Cassettes |
| 15 | M/s Precision Automation & Robotics India Ltd | Automatic Bar Bundling |
| 16 | M/s Metcon Water System Pvt Ltd | Pac Dosing System & Automatic Mill |
| 17 | M/s Grip Impex Private Limited | Forging & Casting Component for 600 TPD Kiln |
| 18 | M/s Breslau Infrastructure & Technology Pvt Ltd | Design & Consultancy For 0.8 Mtpa Pellet Plant |
| 19 | M/s Xiamen Roma Machinery Co Ltd | Container Shear Machine & Pares |
| 20 | M/s Gemscab Industries Limited | Cables 600 TPD |
| 21 | M/s Nitin Castings Limited | SS Casting Items |
| 22 | M/s Elecon Engineering Co. Ltd | Rotary Kiln Drive & Cooler Drive 600 TPD |
| 23 | M/s Technocraft Switch Gear P Ltd | 11 KV HT Panel for MRSS & CPP |
| 24 | M/s Jiangsu Hongda Special Steel Machinery Plant Co Ltd | Equipment for Pellet Plant |
| 25 | M/s International Combustion (India) Limited | Double Deck Wet Screen & Single Deck Product Screen |
| 26 | M/s Saurashtra Marine Traders | MS Greating |

| PART F | PROJECT COST & EXPENDITURE |
| --- | --- |

- TOTAL PROJECT COST: As per DPR Report, total cost of the project for Phase-I is estimated to be at Rs.188.97 Crore, for Phase-II is Rs.241.03 Crore, for Phase-III is Rs.190.35 Crore and for Phase-IV is Rs.230.27 Crore, adding a total of Rs.850.62 Crore, distributed broadly under following heads:

(In Rs. Crore)

- CURRENT STATUS & TOTAL EXPENDITURE INCURRED TILL DATE: Details of the expenditure in the table below is recorded for the expenditure incurred in the period (April’ 2018 – March’ 2022).

| S. NO. | PARTICULARS | TYPE OF AMOUNT | AMOUNT INCURRED TILL DATE (All figures in Rs. Crore) | CURRENT STATUS OF WORK AND REMARKS |
| --- | --- | --- | --- | --- |
| ## 1. | Land & Site Development | Total allocated amount | Phase-I: 3.25 Phase-II: 11.75 TOTAL: 15.00 | GIL has shown that the amount of Rs.3.25 Crore has been incurred under this head during Phase-I and Rs.1.23 Crore for Phase-II in the period April’ 2018 – March’ 2022 for the purchase of 6.2 acres and 4.47 acres respectively. However, the amount approved by IE is as per the amount mentioned in the Deeds including the Stamp charges and Reg. charges are taken as 1% (as per the details available on the public domain) amounting of Rs.4.30 Crore. The cost considered does not include the site development charges. As per the details of the deeds provided to us, copy of one land deed dated 10.06.2021 which amounts to Rs.17,33,794/- is not available. As per the discussion the GIL team, that particular deed is at the registrar office due to some official reason. IE have considered only those deeds whose copies are available and mentioned in the list. |
|  |  | Expenses shown by the company | Phase-I: 3.25 Phase-II: 1.23 TOTAL: 4.48 |  |
|  |  | Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 3.21 Phase-II: 1.09 TOTAL: 4.30 |  |
| ## 2. | Civil & Structure Works | Total allocated amount | Phase-I: 55.71 Phase-II: 50.12 Phase-III: 45.05 TOTAL: 150.88 | GIL has shown Rs.133.56 Crore incurred under this head (Civil & Structure Works and Foundation Works) in the period (Jan., 2018 – March, 2022). Total cost approved by IE is Rs.116.13 Crore. Cost is approved based on below analysis: For Buildings: - Area measurement is taken as per area sheet provided by the company. Area of some of the buildings are cross verified at the site either manually or through digital google measurement which was found to be similar as provided by the company based on which the assessment is done. - Plinth Area rates as prescribed by CPWD and market rates are adopted for each building based on its type & height as shown in the Table nos. 1,4 & 7 below to estimate the cost of the building construction. For Foundation: - Quantity is taken based on the certificates obtained by drawing consultants which are annexed with the report. - RCC rates are calculated using CPWD rates for scheduled items and market rates for non-schedule items. - Working sheet for foundation cost is shown in Table nos. 10 & 11 below. - The working of cost taken for RCC is shown in Table nos. 2,5 & 8 below along with detailed breakup of the same. |
|  |  | Expenses shown by the company | Phase-I: 55.71 Phase-II: 51.41 Phase-III (CWIP): 26.44 TOTAL: 133.56 |  |
|  |  | Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 49.82 Phase-II: 43.88 Phase-III (CWIP): 22.43 TOTAL: 116.13 |  |
| ## 3. | Plant & Machinery | Total allocated amount | Phase-I: 128.33 Phase-II: 161.67 Phase-III: 124.36 TOTAL: 414.36 | GIL has shown Rs.341.02 Crore to have incurred under this head (for plant & machinery and steel fabrication works) in the period (April’ 2018 – March’ 2022). Total cost approved by IE is Rs.313.01 Crore. For Machinery: - In Phase-1, company has shown Rs.20.52 Crore of Miscellaneous Fixed Assets also under P&M, which is separated from this head and considered in Miscellaneous Fixed Assets below. - Cost of Plant & Machines is verified from the detailed inventory sheet provided to us related to plant & machinery having description of assets, supplier name, invoice number, date of invoice etc. Major machines have been cross checked and due to voluminous nature, bills/ invoices of the amount more than Rs.50 lakhs are verified at the site. For Steel Fabrication Work: - Quantity is taken based on the certificate obtained from CE for verification of quantity which is annexed with the report. - The rates for steel are taken based on the market analysis in the respective periods as per the industry standards. For this purchase Bills for the steel is also taken from the customer. On the Steel rate, fabrication labor charges are also added to reach at final rate. - Working sheet for steel fabrication cost is shown in Table no. 12 below. |
|  |  | Expenses shown by the company | Phase-I: 128.33 Phase-II: 147.99 Phase-III (CWIP): 64.70 TOTAL: 341.02 |  |
|  |  | Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 101.96 Phase-II: 147.28 Phase-III (CWIP): 63.77 TOTAL: 313.01 |  |
| ## 4. | Miscellaneous Fixed Assets | Total allocated amount | Phase-I: 0.00 Phase-II: 0.00 Phase-III: 0.00 TOTAL: 0.00 | GIL has shown Rs.55.70 Crore to have incurred under this head in the period (April’ 2018 – March’ 2022) as per below details: - Rs.0.00 Crore incurred in Phase-I. - Rs.52.01 Crore incurred in Phase-II. - Rs.3.69 Crore incurred in Phase-III (CWIP). - Total cost approved by IE is Rs.70.58 Crore which includes Rs.20.52 Crore which has been transferred from P&M to this head under Phase-I. - The amount incurred under Miscellaneous (CWIP) is Rs.3.69 Crore. Since, no bifurcation of the amount is provided to us, therefore, we have not considered the same in the approved amount. - Cost of Miscellaneous Fixed Assets is verified from the detailed inventory sheet provided to us related to Miscellaneous Fixed Assets having description of assets, supplier name, invoice number, date of invoice etc. - The cost incurred under Furniture & Fixtures and Office Equipments amounting Rs.21,568/- in Phase-I and Rs.1,47,29,617/- in Phase-II has not been considered in the approved cost as per the IIEPP Rules-2017. For Steel Fabrication Work: - Quantity is taken based on the certificate obtained from CE for verification of quantity which is annexed with the report. - The rates for steel are taken based on the market analysis in the respective periods as per the industry standards. For this purchase Bills for the steel is also taken from the customer. On the Steel rate, fabrication labor charges are also added to reach at final rate. - Working sheet for steel fabrication cost is shown in Table no. 12 below. |
|  |  | Expenses shown by the company | Phase-I: 0.00 Phase-II: 52.01 Phase-III (CWIP): 3.69 TOTAL: 55.70 |  |
|  |  | Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 20.52 Phase-II: 50.06 Phase-III (CWIP): 0.00 TOTAL: 70.58 |  |
| ## 5. | Prelim and Pre-operative Expense | Total allocated amount | Phase-I: 0.67 | GIL has shown that the amount of Rs.0.67 Crore has been incurred under this head during Phase-I in the period April’ 2018 – March’ 2021. The bifurcation of pre-liminary and pre-operative expenses incurred under Phase-I is shown below: S. No.; Particulars; Amount incurred in Phase-I (In Rs.). 1; SMS; 23,55,579. 2; Rolling; 32,53,979. 3; Miscellaneous Factory Equipment; 2,94,777. 4; Office Equipment; 127. 5; Electric Installation; 2,87,230. 6; Pollution Equipment; 5,03,780. Total; 66,95,472. As per the IIEPP Rules-2017, the amount incurred in this head is not considered in the approved cost. |
|  |  | Expenses shown by the company | Phase-I: 0.67 |  |
|  |  | Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 0.00 |  |
| 6. | Total | Total allocated amount | Phase-I: 188.97 Phase-II: 241.03 Phase-III: 190.35 TOTAL: 620.35 | GIL has shown to have incurred Rs.535.41 Crore in the period (April’ 2018 – March’ 2022). As per IE, the total cost approved is Rs.504,02,16,286/- (Rupees Five Hundred and Four Crore Two Lacs Sixteen Thousand Two Hundred and Eighty-Six Only) All expenses are verified based on invoices/ bills shown by the company and for the market rates as per the industry standards. |
|  |  | Expenses shown by the company | Phase-I: 187.95 Phase-II: 252.64 Phase-III (CWIP): 94.82 TOTAL: 535.41 |  |
|  |  | Approved by IE incurred in the period (April’ 2018 – March’ 2022) | Phase-I: 175.50 Phase-II: 242.31 Phase-III (CWIP): 86.21 TOTAL: 504.02 |  |

CONSOLIDATED SUMMARY OF THE ABOVE FIGURES IS SHOWN IN THE TABLE BELOW:

(All figures in Rs. Cr.)

TABLE 1: ASSESSMENT OF BUILDING CONSTRUCTION (PHASE I)

TABLE 2: ASSESSMENT OF FOUNDATION WORK (PHASE I)

TABLE 3: ASSESSMENT OF STEEL FABRICATION WORK (PHASE I)

TABLE 4: ASSESSMENT OF BUILDING CONSTRUCTION (PHASE II)

TABLE 5: ASSESSMENT OF FOUNDATION (PHASE II)

TABLE 6: ASSESSMENT OF STEEL FABRICATION WORK (PHASE II)

TABLE 7: ASSESSMENT OF BUILDING CONSTRUCTION (CWIP)

TABLE 8: ASSESSMENT OF FOUNDATION WORK (CWIP)

TABLE 9: ASSESSMENT OF STEEL FABRICATION WORK (CWIP)

## Analysis of Rates for M25 Design Mix Concrete as per the industry standards:

## TABLE 10: Rate of RCC with M-25 Design Concrete Work for foundation up to Plinth level For Phase-I

| ## S. No. | ## Particulars | ## Rates |
| --- | --- | --- |
| ## 1 | ## M-25 Design mix concrete | ## Rs.7000.00 per cu.mtr. |
| ## 2 | ## Steel @ 1.25% per cu.mtr. ## (Total 95 Kg @ Rs.58 per kg) | ## Rs.5510.00 |
| ## 3 | ## Add for Bending, Cutting of Steel, Shuttering & layering of PCC etc. | ## Rs.500.00 |
| ## 4 | ## Establishment & Overhead charges @5% | ## Rs.651.00 |
| ## 5 | ## Rate for RCC per cu.mtr. | ## Rs.13,661 per cu.mtr. |
|  | ## Say | ## Rs.14,000 per cu.mtr. |

## TABLE 11: Rate of RCC with M-25 Design Concrete Work for foundation up to Plinth level For Phase-II & CWIP

| ## S. No. | ## Particulars | ## Rates |
| --- | --- | --- |
| ## 1 | ## M-25 Design mix concrete | ## Rs.7300.00 per cu.mtr. |
| ## 2 | ## Steel @ 1.25% per cu.mtr. ## (Total 95 Kg @ Rs.62 per kg) | ## Rs.5890.00 |
| ## 3 | ## Add for Bending, Cutting of Steel, Shuttering & layering of PCC etc. | ## Rs.550.00 |
| ## 4 | ## Establishment & Overhead charges @5% | ## Rs.687.00 |
| ## 5 | ## Rate for RCC per cu.mtr. | ## Rs.14,427 per cu.mtr. |
|  | ## Say | ## Rs.14,500 per cu.mtr. |

## TABLE 12: Rates for Steel Fabrication as per the industry standards

| ## S. No. | ## Particulars | ## Rates |
| --- | --- | --- |
| ## For Phase-I |  |  |
| ## 1 | ## Rate of Structural steel | ## Rs.57.00 per kg |
| ## 2 | ## Fabrication work including cutting/bending | ## Rs.13.00 per kg |
| ## Total |  | ## Rs.70.00 per kg |
| ## For Phase-II & CWIP |  |  |
| ## 1 | ## Rate of Structural steel | ## Rs.62.00 per kg |
| ## 2 | ## Fabrication work including cutting/bending | ## Rs.15.00 per kg |
| ## Total |  | ## Rs.77.00 per kg |

## CERTIFICATES FROM RESPECTIVE CONSULTANTS FOR QUANTITY VERIFICATION OF RCC IN FOUNDATION WORKS:

## CERTIFICATE FROM RESPECTIVE CONSULTANTS FOR QUANTITY VERIFICATION OF STEEL USED IN FABRICATION WORKS:

| PART G | PHOTOGRAPHS OF THE PLANT |
| --- | --- |

| PART H | DISCLAIMER |
| --- | --- |

      - No employee or member of R.K Associates has any direct/ indirect interest in the Project.

      - This report is prepared based on the copies of the documents/ information which interested organization or customer could provide to us out of the standard checklist of documents sought from them and further based on our assumptions and limiting conditions. All such information provided to us has been relied upon and we have assumed that it is true and correct. Verification or cross checking of the documents provided to us has not been done at our end from the originals. If at any time in future it’s found or came to our knowledge that misrepresentation of facts or incomplete or distorted information has been provided to us then this report shall automatically become null & void.

      - This report is a general analysis of the project and not an audit report. All the information gathered is based on the facts seen on the site during survey, verbal discussion & documentary evidence provided by the client and is believed that information given by the company is true best of their knowledge.

      - All observations mentioned in the report is only based on the visual observation and the documents/ data/ information provided by the client. No mechanical/ technical tests, measurements or any design review have been performed or carried out from our side during Project assessment.

      - User of this report should ONLY take this report as an Advisory document from the Financial/ Chartered Engineering firm and it’s specifically advised to the creditor to cross verify the original documents for the facts mentioned in the report which can be availed from the borrowing company directly.

      - In case of any default in loans or the credit facility extended to the borrowing company, R.K Associates shall not be held responsible for whatsoever reason may be and any request for seeking any explanation from the employee/s of R.K Associates will not be entertained at any instance or situation.

      - This Report is prepared by our competent technical team which includes Engineers and financial experts & analysts.

      - This is just an opinion report and doesn’t hold any binding on anyone. It is requested from the concerned Financial Institution which is using this report for taking financial decision on the project that they should consider all the different associated relevant & related factors also before taking any business decision based on the content of this report.

      - All Pages of the report including annexures are signed and stamped from our office. In case any paper in the report is without stamp & signature then this should not be considered a valid paper issued from this office.

      - Defect Liability Period is 30 DAYS. We request the concerned authorized reader of this report to check the contents, data and calculations in the report within this period and intimate us in writing if any corrections are required or in case of any other concern with the contents or opinion mentioned in the report. Corrections only related to typographical, calculation, spelling mistakes will be entertained within the defect liability period. No request for any illegitimate value revision, date change or any other facts & figures changes will be entertained other than the one mentioned above.

      - R.K Associates encourages its customers to give feedback or inform concerns over its services through proper channel at le@rkassociates.org in writing within 30 days of report delivery. After this period no concern/ complaint/ proceedings in connection with the Valuation Services can be entertained due to possible change in situation and condition of the property.

      - Our Data retention policy is of ONE YEAR. After this period, we remove all the concerned records related to the assignment from our repository. No clarification or query can be answered after this period due to unavailability of the data.

      - This Valuation report is governed by our (1) Internal Policies, Processes & Standard Operating Procedures, (2) R.K Associates Quality Policy, (3) Valuation & Survey Best Practices Guidelines formulated by management of R.K Associates, (4) Information input given to us by the customer and (4) Information/ Data/ Facts given to us by our field/ office technical team. Management of R.K Associates never gives acceptance to any unethical or unprofessional practice which may affect fair, correct & impartial assessment and which is against any prevailing law. In case of any indication of any negligence, default, incorrect, misleading, misrepresentation or distortion of facts in the report then it is the responsibility of the user of this report to immediately or atleast within the defect liability period bring all such act into notice of R.K Associates management so that corrective measures can be taken instantly.

      - R.K Associates never releases any report doing alterations or modifications from pen. In case any information/ figure of this report is found altered with pen then this report will automatically become null & void.

      - If this report is prepared for the matter under litigation in any Indian court, no official or employee of R.K Associates will be under any obligation to give in person appearance in the court as a testimony. For any explanation or clarification, only written reply can be submitted on payment of charges by the plaintiff or respondent which will be 10% of the original fees charged where minimum charges will be Rs.15,000/-.

Place	:	New Delhi					FOR INTERNAL USE

Date	:	12.10.2023					SURVEYED BY:  Er. Manas Upmanyu &

Er. Arup Banerjee

Note	:	This report contains 76 pages		PREPARED BY: PE Team

REVIEWED BY: MA

For R.K Associates

Project Engineering Team

DEFECT LIABILITY PERIOD - In case of any query/ issue or escalation you may please contact Incident Manager by writing at valuers@rkassociates.org. We ensure 100% accuracy in the Calculations done, Rates adopted and various other data points & information mentioned in the report but still can’t rule out typing, human errors or any other mistakes. In case you find any mistake, variation, discrepancy or inaccuracy in any data point of the report, please help us by bringing all such points into our notice in writing at valuers@rkassociates.org within 30 days of the report delivery, to get these rectified timely, failing which R.K Associates Valuers Techno Engineering Consultants (P) Ltd. won’t be held responsible for any inaccuracy in any manner. Also, if we will not hear back anything from you within 30 days, we will assume that report is correct in all respect and no further claim of any sort will be entertained thereafter. We would welcome and appreciate your feedback & suggestions in order to improve our services.

COPYRIGHT FORMAT - This report is prepared on the copyright format of R.K Associates Valuers Techno Engineering Consultants (P) Ltd. to serve our clients in the best possible way. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the organization as mentioned on the cover page of this report. Distribution or use of this format other than R.K Associates will be seen as unlawful act and necessary legal action can be taken against the defaulter