## CASH FLOW
Cash Flow and time line planning for Matkota projects of EWS Housing in UK
EWS Units
Land | Sq Mtrs | 20235
Land in Hectare | Hectare | 2.0235
Land in Acres |  | 5
Total No Of Units | INR | 928
Project Life | Months | 30
Carpet Area | Per Unit | 24.22
Built Up Area Per Unit |  | 30
Total Built up Area | 10.764 | 299669.76
Revenue Share of Land owner |  | 77500000
Cost of Construction | INR | 900
Infrastructure Development | Per Acre | 6000000
Overheads | Per Unit | 50000
Selling price | Per Unit | 600000
COST OF THE PROJECT
Revenue Share of Land Owner |  | 77500000
Cost of Construction |  | 269702784
Infrastructure Development |  | 30000000
Overheads |  | 46400000
Interst on Bank Loan |  | 20625000
TOTAL COST | INR |  | 444227784
Revenue from the Residential Area |  | 556800000
Revenue from the Commercial |  | 40000000 | 596800000
SURPLUS |  |  |  | 152572216
Interest rate for loan | 10%
| 2022-23 |  |  | 2023-24 |  |  |  | 2024-25
Cash Flow | As on Date | 3rd Qt | 4th Qt | 1st Qtr | 2nd Qt | 3rd Qt | 4th Qtr | 1st Qtr | 2nd Qt | 3rd Qt | 4th Qtr | TOTAL
REVENUE FROM THE PROJECTS
Capital | 363640 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | -363640 | 0
OCD from Share Holders | 54000000 | [9 empty] | -54000000 | 0
Loan |  | 30000000 | 50000000 | 50000000 |  |  |  | -32500000 | -32500000 | -32500000 | -32500000 | 0
Unsecured Loans | 496500 | [9 empty] | -496500
Sale Proceeds | 0 | 4640000 | 16640000 | 42448000 | 89712000 | 73072000 | 106480000 | 84640000 | 72352000 | 33408000 | 33408000 | 556800000
Commercial | [10 empty] | 40000000 | 40000000
Total | 54860140 | 34640000 | 66640000 | 92448000 | 89712000 | 73072000 | 106480000 | 52140000 | 39852000 | 908000 | -13952140 | 596800000
COST OF PROJECT
Land Cost including stamp paper Exp | 26776250 | 25575000 | 25148750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77500000
Cost of Construction | 13309470.72 | 3306700.8 | 31537658.88 | 57453926.4 | 44433792 | 40300416 | 39267072 | 29553638.4 | 10540108.8 | 0 | 0 | 269702784
Infrastructure Development | 0 | 0 | 1500000 | 1500000 | 3000000 | 3000000 | 3000000 | 3000000 | 4500000 | 6000000 | 4500000 | 30000000
Overheads | 14421120 | 4640000 | 4640000 | 4640000 | 4640000 | 2320000 | 2320000 | 2320000 | 2320000 | 2320000 | 1818880 | 46400000
Interest on Loan | 0 | 750000 | 2000000 | 3250000 | 3250000 | 3250000 | 3250000 | 2437500 | 1625000 | 812500 | 0 | 20625000
TOTAL | 54506840.72 | 34271700.8 | 64826408.88 | 66843926.4 | 55323792 | 48870416 | 47837072 | 37311138.4 | 18985108.8 | 9132500 | 6318880 | 444227784
CASH FLOW
Cash in Hand
Opening Balance | 0 | 353299.28 | 721598.48 | 2535189.6 | 28139263.2 | 62527471.2 | 86729055.2 | 145371983.2 | 160200844.8 | 181067736 | 172843236 | 152572216
Surplus during the Period | 353299.28 | 368299.2 | 1813591.12 | 25604073.6 | 34388208 | 24201584 | 58642928 | 14828861.6 | 20866891.2 | -8224500 | -20271020
Closing balance | 353299.28 | 721598.48 | 2535189.6 | 28139263.2 | 62527471.2 | 86729055.2 | 145371983.2 | 160200844.8 | 181067736 | 172843236 | 152572216
PROJECT DSCR | 1.5141
EXPENSES
Land Payments | 34.55% | 33% | 32.45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Infrastructure Development | 0% | 0% | 5% | 5% | 10% | 10% | 10% | 10% | 15% | 20% | 15% | 100%
Overheads | 31.08% | 10% | 10% | 10% | 10% | 5% | 5% | 5% | 5% | 5% | 3.92% | 100%
Sanctioned and Other Cost | 0% | 0% | 8% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 22% | 100%
No of Units to Construct | 928
Qtrly Units to Construct |  | 0 | 0 | 128 | 256 | 544 | 0 | 0 | 0 | 0 | 0 | 928
Area to be Construct |  | 0 | 0 | 41333.76 | 82667.52 | 175668.48 | 0 | 0 | 0 | 0 | 0 | 299669.76
Cost of Construction | 900
Plinth Level | 200 | 900 | 22.22%
Slabs | 400 | 900 | 44.44%
Internal Develepment | 300 | 900 | 33.33%
| As on Date | 3rd Qt | 4th Qt | 1st Qtr | 2nd Qt | 3rd Qt | 4th Qtr | 1st Qtr | 2nd Qt | 3rd Qt | 4th Qtr | TOTAL
Plinth Level | 0 | [10 empty] | 0
Plinth Level | [11 empty] | 0
Plinth Level | 8266752 | [10 empty] | 8266752
Plinth Level | 5042718.72 | 1653350.4 | 9837434.88 | [8 empty] | 16533504
Plinth Level |  |  | 14053478.4 | 21080217.6 | [7 empty] | 35133696
Plinth Level |  |  |  | 0 | [7 empty] | 0
Plinth Level |  |  |  |  | 0 | [6 empty] | 0
Total Plinth | [11 empty] | 59933952
Slabs |  | 0 | 0 | [8 empty] | 0
Slabs |  | 0 | 0 | 0 | [7 empty] | 0
Slabs |  | 1653350.4 | 4133376 | 6613401.6 | 4133376 | [6 empty] | 16533504
Slabs |  |  | 1653350.4 | 8266752 | 8266752 | 8266752 | 6613401.6 |  |  |  |  | 33067008
Slabs |  |  |  | 14053478.4 | 14053478.4 | 14053478.4 | 14053478.4 | 14053478.4 |  |  |  | 70267392
Slabs |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
Slabs | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0
Total Slabs | [11 empty] | 119867904
Internal Develepment |  | 0 | 0 | 0 | 0 | [6 empty] | 0
Internal Develepment |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
Internal Develepment |  |  | 1860019.2 | 2480025.6 | 2480025.6 | 2480025.6 | 3100032 |  |  |  |  | 12400128
Internal Develepment |  |  |  | 4960051.2 | 4960051.2 | 4960051.2 | 4960051.2 | 4960051.2 |  |  |  | 24800256
Internal Develepment |  |  |  |  | 10540108.8 | 10540108.8 | 10540108.8 | 10540108.8 | 10540108.8 |  |  | 52700544
Internal Develepment | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0
Total Internal Development | [11 empty] | 89900928
Grand Total | 13309470.72 | 3306700.8 | 31537658.88 | 57453926.4 | 44433792 | 40300416 | 39267072 | 29553638.4 | 10540108.8 | 0 | 0 | 269702784
Receipt | Beneficiary | State & Center
Booking | 5000 |  |  | 4640000
Plinth | 70000 | 60000 |  | 120640000
Slabs | 70000 | 60000 |  | 120640000
Internal & Extrernal Development | 105000 | 50000 |  | 143840000
Completion | 100000 | 80000 |  | 167040000
Recovery
Booking |  | 4640000 | [9 empty] | 4640000
Plinth |  |  | 5546666.6667 | 5546666.6667 | 5546666.6667 | [6 empty] | 16640000
Plinth |  |  | 11093333.3333 | 11093333.3333 | 11093333.3333 | [6 empty] | 33280000
Plinth |  |  |  | 17680000 | 17680000 | 17680000 | 17680000 |  |  |  |  | 70720000
Plinth | [11 empty] | 0
Slabs |  |  |  | 4160000 | 4160000 | 4160000 | 4160000 |  |  |  |  | 16640000
Slabs |  |  |  |  | 8320000 | 8320000 | 8320000 | 8320000 |  |  |  | 33280000
Slabs |  |  |  |  | 14144000 | 14144000 | 14144000 | 14144000 | 14144000 |  |  | 70720000
Slabs | [11 empty] | 0
Internal & Extrernal Development |  |  |  | 3968000 | 3968000 | 3968000 | 3968000 | 3968000 |  |  |  | 19840000
Internal & Extrernal Development |  |  |  |  | 7936000 | 7936000 | 7936000 | 7936000 | 7936000 |  |  | 39680000
Internal & Extrernal Development |  |  |  |  | 16864000 | 16864000 | 16864000 | 16864000 | 16864000 |  |  | 84320000
Internal & Extrernal Development | [11 empty] | 0
Completion | [6 empty] | 33408000 | 33408000 | 33408000 | 33408000 | 33408000 | 167040000
Total Recovery | 0 | 4640000 | 16640000 | 42448000 | 89712000 | 73072000 | 106480000 | 84640000 | 72352000 | 33408000 | 33408000 | 556800000
No of Units to Construct | As on Date | 3rd Qt | 4th Qt | 1st Qtr | 2nd Qt | 3rd Qt | 4th Qtr | 1st Qtr | 2nd Qt | 3rd Qt | 4th Qtr | TOTAL
Matkota |  |  | 128 | 256 | 544 | [6 empty] | 928
Total | 0 | 0 | 128 | 256 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 928

## COP MOF
S. No. | Particulars | Amount (Rs.) | %
Cost of the Project at Matkota
1 | Land Cost including stamp paper Exp | 77500000 | 17.446
2 | Cost of Construction | 269702784 | 60.7127
3 | Infrastructure Development | 30000000 | 6.7533
4 | Overheads | 46400000 | 10.4451
5 | Interest on Loan | 20625000 | 4.6429
| Total | 444227784 | 100
Means of Finance of project at Matkota
1 | Capital | 860140 | 0.19363
2 | OCD from Share Holders | 54000000 | 12.1559
3 | Loan | 130000000 | 29.2643
4 | Sale Proceeds | 259367644 | 58.3862
| Total | 444227784 | 100