## Status
Kashipur (Kanakpur) Blockwise Status
|  |  | 4 | 3 | 7 | 3 | 10 | 3 | 6 | 3 | 14 | 14 | 14 |  | 10 |  | 45
Sr. No. | Block | Units | Excavation | PCC | Footing casting | Column up to plinth beam | Back filling | PCC of plinth beam | Plinth beam casting | Start of Shuttering | Ground Floor | First Floor | Second Floor | Third Floor | Mumty | Structure end date | Finishing end date | Project end date
1 | A | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [6 empty] | 2023-12-31
2 | B | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [6 empty] | 2023-12-31
3 | C | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [7 empty] | 2023-12-31
4 | G | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [7 empty] | 2023-12-31
5 | J | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [7 empty] | 2023-12-31
6 | L | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [7 empty] | 2023-12-31
7 | N | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [7 empty] | 2023-12-31
8 | F | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [8 empty] | 2023-12-31
9 | E | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [8 empty] | 2023-12-31
10 | D | 64 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [8 empty] | 2023-12-31
11 | T | 64 | Complete | [14 empty] | 2023-12-31
12 | R | 64 | Complete | [14 empty] | 2023-12-31
13 | H | 64 | Complete | Complete | [13 empty] | 2023-12-31
14 | K | 64 | Complete | Complete | [13 empty] | 2023-12-31
15 | M | 64 | Complete | Complete | [13 empty] | 2023-12-31
16 | S | 64 | Complete | [14 empty] | 2023-12-31
17 | Q | 64 | Complete | [14 empty] | 2023-12-31
18 | U | 40 | Complete | [14 empty] | 2023-12-31
19 | P | 64 | Complete | [14 empty] | 2023-12-31
20 | O | 64 | Complete | [14 empty] | 2023-12-31
1256