## Sheet1
24859000
|  | 20235 | 8000 | 161880000
700000 |  | 1228.5149
58333.3333
2000000
| 1.25 |  |  | 494.1932
2

## Sheet1 (2)
1%
S. No. | Different Parameters |  | Tower-A | Tower-B | Tower-C | Tower-D | Tower-E | Tower-F | Tower-G | Tower-H | Tower-J | Tower-K | Tower-L | Tower-M | Tower-N | Tower-O | Tower-P | Tower-Q | Tower-R | Tower-S
1 | Cutting, Filling and Levelling | 1% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Footings | 6% | 0% | 100% | 50% | 100% | 25% | 25% | 25% | 25% | 25% | 25% | 37.5% | 25% | 25% | 25% | 25% | 25% | 25% | 0%
4 | Slab Casting | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 37.5% | 12.5% | 0% | 0% | 12.5% | 0% | 12.5% | 0% | 0% | 0% | 0% | 0%
5 | Common Staircase, lift and lobby etc. | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Brickwork | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | Plaster | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | Flooring | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | MEP Services | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | Door/ Window | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | Finishing | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Completion status (in %) | 100% | 1% | 7% | 4% | 7% | 2.5% | 2.5% | 11.88% | 5.625% | 2.5% | 2.5% | 6.375% | 2.5% | 5.625% | 2.5% | 2.5% | 2.5% | 2.5% | 1%
| Average Completion Status (in %) |  | 4%
|  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  |  | Tower-A | Tower-B | Tower-C | Tower-D | Tower-E | Tower-F | Tower-G | Tower-H | Tower-J | Tower-K | Tower-L | Tower-M | Tower-N | Tower-O | Tower-P | Tower-Q | Tower-R | Tower-S
| Cutting, Filling and Levelling |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Footings |  | 0 | 4 | 2 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Slab Casting |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| Common Staircase, lift and lobby etc. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Brickwork |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plaster |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Flooring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MEP Services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Door/ Window |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Finishing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Basic structure construction cost | 850 | 37.69%
ii | Project sanctioning/ approval, Architectural, structural stability Fees, etc. | 50 | 2.217%
iii | Finishing Work (Flooring, white washing, fittings & fixtures, etc.) | 300 | 13.3%
iv | MEP Works (Mechanical, Electrical & Plumbing) | 200 | 8.869%
v | Internal & External Development charges | 200 | 8.869%
vi | Other expenses (Firefighting, intercom & etc.) @ 1.5% of total cost (i+ii+iii+iv+v) | 24 | 1.064%
vii | Pre-operative & Administrative expenses @ 5% of total cost (i+ii+iii+iv+v+vi) | 81 | 3.592%
viii | Marketing & Selling charges @ 3% of Rs.2,800/- & Rs.7,500/- | 70 | 3.104%
ix | Institutional Borrowing for 03 years @ 12.5% on 75% of total cost (i+ii+iii+iv+v+vi+vii+viii) | 479 | 21.24%
Total |  | 2255