## CA Certificate
(amount in Lakhs)
Particulars | Original | Present position as on 31-12-2022 | Revised Cost of Project | Escalation in Cost of Project
Land | 834.36 | 834.36 | 834.36 | 0
Construction of Building | 4458.5 | 3642.06 | 7432.73 | 2974.23 | 3438.5 | 2.0356
Pre-Operative and Preliminary expenses & other Misc. | 181.18 | 324.92 | 585.12 | 403.94
Total | 5474.04 | 4801.34 | 8852.21 | 3378.17

## Cost Assessment
Amount in Rs. Cr. till 13/12/2022
|  |  |  | As per CA Certificate |  | As per RKA
S. No. | Particulars | Sanctioned dated 31/8/2019 | Revised Project Cost | 2022-12-31 |  | As on 13/12/22 |  | As on
HARD COST
A | Cost of Land & Land Development | 8.3436 | 8.3436 | 8.3436 | 100% | 8.34 | 99.96%
B | Cost of construction | 38.4745 | 63.7017 | 36.4206 | 57.17% | 29.87 | 46.89%
|  | 46.8181 | 72.0453 | 44.7642 | 62.13% | 38.21 | 53.04%
SOFT COST
C | Legal Consultation & Other Charges | 0.8176 | 0.3975 | 0.1598 | 40.2% | 0.1598 | 40.2%
D | Costof Approvals | 2.9 | 2.9 | 2.9 | 100% | 2.9 | 100%
E | Marketing Expenses & Others | 1.1911 | 3.4951 | 0.5988 | 17.13% | 0.5988 | 17.13%
F | Pre-Operative and preliminary expenses | 0.8589 | 6.2178 | 0.345 | 5.549% | 0.345 | 5.549%
G | Bank Interest | 2.1547 | 3.4664 | 2.0251 | 58.42% | 2.0251 | 58.42%
|  | 7.9223 | 16.4768 | 6.0287 | 36.59% | 6.0287 | 36.59%
| Total | 54.7404 | 88.5221 | 50.7929 | 57.38% | 44.2387 | 49.97%
S. No. | Particulars | Figure | UOM
1 | Built-up area | 2.27 | Lakh sq. ft.
2 | Construction Rate adopted | 2000 | Rs. Per sq. ft.
3 | % Completion (as estimated by us) | 66.04%
4 | Estimated Cost incurred as per RKA | 2998.2917 | Rs. Lakhs
5 | Actual cost incurred as per CA certificate | 3363.7 | Rs. Lakhs
10.86%
S. No. | Particulars | Revised Cost | Present position
|  | of Project | as on 31-12-2022
1 | Cost of Land & Land Development | 834.36 | 834.36
2 | Cost of construction | 6370.17 | 3363.7
3 | Legal Consultation & Other Charges | 39.75 | 15.98
4 | Cost of Approvals | 290 | 290
5 | Marketing Expenses & Others | 349.51 | 59.88
6 | Pre-Operative and preliminary expenses | 621.78 | 34.92
7 | Bank Interest | 346.64 | 202.51
Total |  | 8852.21 | 4801.35

## Progress Calc.
[5 empty] | 12 | 12
S. No. | Different Parameters |  | Tower-1 | Tower-2 | Tower-1 | Tower-2
1 | Cutting, Filling and Levelling | 1% | 100% | 100% | 12 | 12
3 | Footings | 6% | 100% | 100% | 12 | 12
4 | Slab Casting | 25% | 100% | 100% | 12 | 12
5 | Common Staircase, lift and lobby etc. | 2% | 100% | 100% | 12 | 12
7 | Brickwork | 6% | 100% | 100% | 12 | 12
9 | Plaster | 5% | 91.67% | 50% | 11 | 6
10 | Flooring | 10% | 58.33% | 41.67% | 7 | 5
11 | MEP Services | 20% | 91.67% | 83.33% | 11 | 10
12 | Door/ Window | 10% | 0% | 0% | 0 | 0
13 | Finishing | 15% | 0% | 0% | 0 | 0
| Completion status (in %) | 100% | 68.75% | 63.33%
| Average Completion Status (in %) |  | 66.04%
i | Basic structure construction cost | 800 | 35.48%
ii | Project sanctioning/ approval, Architectural, structural stability Fees, etc. | 50 | 2.217%
iii | Finishing Work (Flooring, white washing, fittings & fixtures, etc.) | 300 | 13.3%
iv | MEP Works (Mechanical, Electrical & Plumbing) | 200 | 8.869%
v | Internal & External Development charges | 200 | 8.869%
vi | Other expenses (Firefighting, intercom & etc.) @ 1.5% of total cost (i+ii+iii+iv+v) | 24 | 1.064%
vii | Pre-operative & Administrative expenses @ 5% of total cost (i+ii+iii+iv+v+vi) | 81 | 3.592%
viii | Marketing & Selling charges @ 3% of Rs.2,800/- & Rs.7,500/- | 70 | 3.104%
ix | Institutional Borrowing for 03 years @ 12.5% on 75% of total cost (i+ii+iii+iv+v+vi+vii+viii) | 479 | 21.24%
Total |  | 2255

## Means of Finance
Particular | Revised Cost of Project | CURRENT STATE OF INVESTMENT UP TO 31/12/22 | Balance
Capital | 2.5 | 2.5 | 0
Unsecured Loan | 14.46 | 16.6396 | -2.1796
Advance from Customers | 59.6672 | 18.4991 | 41.1681
Term Loan | 10 | 8.4786 | 1.5214
GECL-1 & 2 | 1.8949 | 1.8949 | 0
Total | 88.5221 | 48.0122 | 40.5099
10.3735

## Rough
12450 | covered area
134011.8
| 1964.0969 | 445850000
227000 | 3274.3304 | 743273000
490560180
743273000 | 1100 | 249700000 | 255000000
3274.3304 |  |  | 1.0212
| 445850000 | 343850000 | 1514.7577
|  | 452945000 | 1995.3524
| 1500 | 340500000 |  | 298943700
224730000
86.02
1.26
168
9.41
| Cost of Construction |  |  | 4529.45 |  | 264.69
| External Development and other costs |  |  | 623.93 |  | 6370.17
| Common Areas |  |  | 509.15
| Recreation Floors |  |  | 442.95
|  |  |  | 6105.48 | 610548000 | 227000 | 2689.6388
1775.1616
| 6370.17 | [5 empty] | 402961680
| 637017000 |  | 5481.55
| 2806.2423 |  | 548155000
|  |  | 2414.7797 |  | 4597.37
|  |  | 2300 |  | 834.36
|  |  | 344586000 |  | 3160.14
15.98
59.88
| 227000 | 2000 | 454000000 |  | 34.5
|  |  | 65.79% |  | 202.51
| 1315.859 | 1315.8333 | 298694166.6667 | 2986.9417 | 290
| 298700000 | 1392.1322 | 316014000
1.058
361.41
1439.95
13230
1148.52
1150.53
171
1776.72
[8 empty] | 18916.72 | 203619.5741
[8 empty] | 2110.1 | 22713.1164
[8 empty] | 135.34 | 1456.7998
[8 empty] | 21162.16 | 227789.4902

## Project Schedule
S. No. | Task Name | Duration (in days) | Start | Finish | Actual Start | Actual Finish | Status
1 | Foundation | 169 | 2019-08-05 | 2019-05-30 | 2019-08-05 | 2020-01-20 | Completed
2 | Slab Casting | 1118 | 2019-12-20 | 2023-01-10 | 2019-12-20 | NA | In Progress (Mumty and OHT left)
3 | Brick Work | 848 | 2020-06-06 | 2022-10-01 | 2020-06-06 | 2022-10-01 | Completed
4 | Electrical Conduit & Wiring | 451 | 2021-10-10 | 2023-01-03 | 2021-10-10 | NA | In Progress (10th Floor Left)
5 | Waterproofing Works | 295 | 2022-03-01 | 2022-12-20 | 2022-03-01 | NA | In Progress (10th Floor Left)
6 | Plumbing Works | 451 | 2021-10-10 | 2023-01-03 | 2021-10-10 | NA | In Progress (10th Floor Left)
7 | Railing Works | 191 | 2022-07-15 | 2023-01-21 | 2022-07-15 | NA | In Progress (7th - 10th Floor Left)
8 | HVAC Works | 163 | 2022-07-01 | 2022-12-10 | 2022-07-01 | 2022-12-10 | Completed
9 | False Ceiling & Wall Punning | 170 | 2022-08-04 | 2023-01-20 | 2022-08-04 | NA | In Progress (8th - 10th Floor Left)
10 | Flooring Works | 181 | 2022-09-01 | 2023-02-28 | 2022-09-01 | NA | In Progress (6th - 10th Floor Left)
11 | Whitewash & Painting Works | 153 | 2022-11-01 | 2023-04-02 | 2022-11-01 | NA | In Progress (3rd - 10th Floor Left)
12 | Door Frame, Shutter, Modular Kitchen & CB Works | 150 | 2023-01-01 | 2023-05-30 | NA | NA | Yet to start
13 | External Works | 147 | 2022-12-05 | 2023-04-30 | NA | NA | Yet to start
14 | Project Completion |  | 2023-05-30 | 2023-05-30 | NA | NA | Yet to start