## Sheet1 (2)
S. No. | Different Parameters |  | Block-A | Block-B | Block-C | Power House | Tower-D
1 | Cutting, Filling and Levelling | 15% | 100% | 100% | 100% | 100% | 35% | 40%
3 | Footings | 5% | 100% | 100% | 100% | 100% | 35%
4 | Slab Casting | 25% | 100% | 100% | 100% | 100% | 35%
5 | Common Staircase and lobby etc. | 2% | 100% | 33.33% | 100% | 100% | 35%
7 | Brickwork | 6% | 100% | 33.33% | 100% | 100% | 35%
9 | Plaster | 5% | 100% | 33.33% | 100% | 100% | 35%
10 | Flooring | 10% | 100% | 33.33% | 100% | 100% | 35%
11 | MEP Services | 10% | 100% | 16.67% | 100% | 100% | 35%
12 | Door/ Window | 10% | 100% | 16.67% | 100% | 100% | 35%
13 | Finishing | 12% | 100% | 0% | 100% | 100% | 35%
| Completion status (in %) | 100% | 100% | 56% | 100% | 100% | 35%
| Average Completion Status (in %) |  | 78.2%
|  |  | 2 | 3 | 1 | 1
|  |  | Block-A | Block-B | Block-C | Power House | Tower-D
| Cutting, Filling and Levelling |  | 2 | 3 | 1 | 1 | 0
| Footings |  | 2 | 3 | 1 | 1 | 0
| Slab Casting |  | 2 | 3 | 1 | 1 | 0
| Common Staircase, lift and lobby etc. |  | 2 | 1 | 1 | 1 | 0
| Brickwork |  | 2 | 1 | 1 | 1 | 0
| Plaster |  | 2 | 1 | 1 | 1 | 0
| Flooring |  | 2 | 1 | 1 | 1 | 0
| MEP Services |  | 2 | 0.5 | 1 | 1 | 0
| Door/ Window |  | 2 | 0.5 | 1 | 1 | 0
| Finishing |  | 2 | 0 | 1 | 1 | 0
i | Basic structure construction cost | 850 | 37.69%
ii | Project sanctioning/ approval, Architectural, structural stability Fees, etc. | 50 | 2.217%
iii | Finishing Work (Flooring, white washing, fittings & fixtures, etc.) | 300 | 13.3%
iv | MEP Works (Mechanical, Electrical & Plumbing) | 200 | 8.869%
v | Internal & External Development charges | 200 | 8.869%
vi | Other expenses (Firefighting, intercom & etc.) @ 1.5% of total cost (i+ii+iii+iv+v) | 24 | 1.064%
vii | Pre-operative & Administrative expenses @ 5% of total cost (i+ii+iii+iv+v+vi) | 81 | 3.592%
viii | Marketing & Selling charges @ 3% of Rs.2,800/- & Rs.7,500/- | 70 | 3.104%
ix | Institutional Borrowing for 03 years @ 12.5% on 75% of total cost (i+ii+iii+iv+v+vi+vii+viii) | 479 | 21.24%
Total |  | 2255

## Sheet1
Actual Work | [7 empty] | 38.79%
|  |  |  | BUA |  | sqft | CoC/sqft | 25325920.776
|  | Power House |  |  |  | 486 | 700 | 340200 | 45.1505 | 45.1505
Block-B | GF | Hall MD Office, GM Office | UC | 323.97 |  | 3487.2131 | 800 | 2789770.464 |  | 323.97
| FF | Hall | Complete | 323.97 |  | 3487.2131 | 1400 | 4882098.312 |  | 323.97
| SF |  | UC | 70 | 717.94 | 753.48 | 750 | 565110 |  | 70
Block-A | GF | Hall | Complete | 48.7737 |  | 525 | 1400 | 735000 |  | 48.7737
| FF | Hall | Complete | 48.7737 | 97.5474 | 525 | 1400 | 735000 |  | 48.7737
Block-C | GF | Kitechn, Restaurant | Complete | 320.5128 | 320.5128 | 3450 | 1200 | 4140000 |  | 320.5128
Block-D | GF | Huts-1 | Complete | 73.6 |  | 792.2304 | 1500 | 1188345.6 |  | 73.6
|  | Huts-2 | Complete | 73.6 |  | 792.2304 | 1500 | 1188345.6 |  | 73.6
|  | Huts-3 | Complete | 73.6 |  | 792.2304 | 1500 | 1188345.6 |  | 73.6
|  | Huts-4 | Collumn |  |  | 0 |  | 7573705.2
|  | Huts-5 | Foundation |  |  | 0
|  | Huts-6 | Foundation |  | 220.8 | 0
1356.8002
45.1505
1401.9507

## Sheet2
A | 534.85 | 3 | 1604.55
B | 323.97 | 3 | 971.91
C | 145.07 | 2 | 290.14
D | 736.05 | 1 | 736.05
3602.65
1604.55
971.91
|  |  |  | Particulars | Area of Work | Amount |  |  |  |  | 290.14
|  |  |  | Site development | Cutting levelling & construction of retaining walls | 9467131.5 | 9467131.5 |  |  |  | 736.05
|  |  |  | Block-A (Yoga Hall) | Ground Floor | 5115334.8
[5 empty] | First Floor | 4301312.7 |  | sqn | sqft
[5 empty] | Second Floor | 4336368.7 | 13753016.2 | 1604.55 | 17271.3762 | 796.2895
|  |  |  | Block-B | Ground Floor | 3794635.3
[5 empty] | First Floor | 3058131
[5 empty] | Second Floor | 3149927.1 | 10002693.4 | 971.91 | 10461.6392 | 956.1306
|  |  |  | Block-C | Ground Floor | 1625831.25
[5 empty] | First Floor | 2965492 | 4591323.25 | 290.14 | 3123.067 | 1470.1328
|  |  |  | Block-D | 10 nos. of Hut (1 x 13,38,838.50) | 13388385 | 13388385 | 736.05 | 7922.8422 | 1689.8462 |  | 1338838.5
|  |  |  | Amenities & Miscellaneous items | Amenities & Miscellaneous items | 6839563
[6 empty] | 58042112.35 | 41735417.85
[5 empty] | 12.5% | 7255264.0438 | 23562582.15
65298000

## Sheet3
Details of Retaining Wall
| ft | ft | ft | ft | total height
| Length | Height | Foundation | Top
Wall of Block B | 259 | 13 | 6 | 3 | 9
New Wall | 30 | 7 | 2 | 2 | 4
Yoga Hall Building Backside | 100 | 22 | 6 | 3 | 9
Front Side of Kitchen Wall | 342 | 10 | 6 | 3 | 9
Dining side front wall | 211 | 28 | 8 | 3 | 11
back side of kitchen | 210 | 25 | 6 | 3 | 9
backside wall of hut 2&3 | 115 | 20 | 6 | 3 | 9
backside wall of hut 1 | 482 | 22 | 6 | 3 | 9
top wall under construction (Hut) | 258 | 22 | 6 | 3 | 9