## Project Brief
Name of the Project | Kasturi Van
Project Location
Contruction Area |  | Square Feet | Freehold Owned Land |  | SRA
Sale Area - RERA Carpet |  | Square Feet |  |  | Private SRA
Cost | Estimated Total Cost (Actuals) | Incurred up to Oct 2022 | To be Incurred | % of Total Cost | Society Redevelopment
Land Acquisition Cost | 4.07 | 4.07 | 0 | 5.918% | Freehold Owned Land
Rent and Hardship Compensation | 0 | 0 | 0 | 0% | Joint Venture
Fungible FSI Premium | 0 | 0 | 0 | 0%
TDR | 0 | 0 | 0 | 0%
Approvals and Other Premiums |  |  | 0 | 0%
Construction Cost - Rehab Building | 0 | 0 | 0 | 0%
Construction Cost - Sale Building | 47.34 | 1.44 | 45.9 | 68.83%
Selling and Marketing | 7 | 0 | 7 | 10.18%
Professional Fees and Admin expenses | 5 |  | 5 | 7.27%
Contingency | 2.367 | 0 | 2.367 | 3.442%
Finance Cost | 3 | 0 | 3 | 4.362%
Total Project Cost | 68.777 | 5.51 | 63.267 | 100%
Means of Finance | Amount | Incurred | To be incurred | Margin
Equity / Partnership Capital | 6.88 | 5.51 | 1.37 | 10%
Unsecured Loans from promoters | 0 | 0 | 0 | 0%
Advance from Units already sold | 27.37 | 0.23 | 27.14 | 39.8%
Advance from Future bookings | 24.527 | 0 | 24.527 | 35.66%
Bank Finance - Working Capital | 10 | 0 | 10 | 14.54%
Total | 68.777 | 5.74 | 63.037 | 100%

## UNIT LIST BUILDING NO 1 (hidden)
Sr. No | Unit Type | Unit No | RERA Carpet Area (SQ.MT) | BALCONY AREA (SQ.MT) | RERA Carpet Area (SQ.FT) | BALCONY AREA (SQ.FT) | TOTAL AREA IN SQ.MT | TOTAL AREA IN SQ.FT | Saleable Area |  | BHK | Sale Value
1 | Shop | 1 | 164.85 |  | 1774.4454 |  |  |  | 3548.8908
2 | Shop | 2 | 146.31 |  | 1574.8808 |  |  |  | 3149.7617
3 | Shop | 3 | 146.31 |  | 1574.8808 |  |  |  | 3149.7617
4 | Shop | 4 | 164.85 |  | 1774.4454 |  |  |  | 3548.8908
5 | Shop | 5 | 48.6 |  | 523.1304 |  |  |  | 1046.2608
6 | Shop | 6 | 29.68 |  | 319.4755 |  |  |  | 638.951
7 | Shop | 7 | 27.72 |  | 298.3781 |  |  |  | 596.7562
8 | Office P1 | S-1 | 164.85 |  | 1774.4454 |  |  |  | 3105.2794
9 | Office P1 | S-2 | 146.31 |  | 1574.8808 |  |  |  | 2756.0415
10 | Office P1 | S-3 | 146.31 |  | 1574.8808 |  |  |  | 2756.0415
11 | Office P1 | S-4 | 164.85 |  | 1774.4454 |  |  |  | 3105.2794
12 | Office P1 | S-5 | 373.21 |  | 4017.2324 |  |  |  | 7030.1568
13 | Office P2 | S-1 | 278.16 |  | 2994.1142 |  |  |  | 5239.6999
14 | Office P3 | S-1 | 95.02 |  | 1022.7953 |  |  |  | 1789.8917
15 | Office P3 | S-2 | 70.41 |  | 757.8932 |  |  |  | 1326.3132
16 | Office P3 | S-3 | 73.24 |  | 788.3554 |  |  |  | 1379.6219
17 | Office P3 | S-4 | 95.02 |  | 1022.7953 |  |  |  | 1789.8917
18 | Office P3 | S-5 | 278.16 |  | 2994.1142 |  |  |  | 5239.6999
19 | Flat | 101 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
20 | Flat | 102 | 87.9 | 3.81 | 946.1556 | 41.0108 | 91.71 | 987.1664 | 1555 | 615.0011
21 | Flat | 103 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
22 | Flat | 104 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
23 | Flat | 105 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
24 | Flat | 106 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
25 | Flat | 107 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
26 | Flat | 108 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
27 | Flat | 109 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
28 | Flat | 110 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
29 | Flat | 111 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
30 | Flat | 112 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
31 | Flat | 201 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
32 | Flat | 202 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
33 | Flat | 203 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
34 | Flat | 206 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
35 | Flat | 207 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
36 | Flat | 208 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
37 | Flat | 209 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
38 | Flat | 210 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
39 | Flat | 211 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
40 | Flat | 212 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
41 | Flat | 301 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
42 | Flat | 302 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
43 | Flat | 303 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
44 | Flat | 304 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
45 | Flat | 305 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
46 | Flat | 306 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
47 | Flat | 307 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
48 | Flat | 308 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
49 | Flat | 309 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
50 | Flat | 310 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
51 | Flat | 311 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
52 | Flat | 312 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
53 | Flat | 401 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
54 | Flat | 402 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
55 | Flat | 403 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
56 | Flat | 404 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
57 | Flat | 405 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
58 | Flat | 406 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
59 | Flat | 407 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
60 | Flat | 408 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
61 | Flat | 409 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
62 | Flat | 410 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
63 | Flat | 411 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
64 | Flat | 412 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
65 | Flat | 501 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
66 | Flat | 502 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
67 | Flat | 503 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
68 | Flat | 504 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
69 | Flat | 505 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
70 | Flat | 506 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
71 | Flat | 507 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
72 | Flat | 508 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
73 | Flat | 509 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
74 | Flat | 510 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
75 | Flat | 511 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
76 | Flat | 512 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
77 | Flat | 601 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
78 | Flat | 602 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
79 | Flat | 603 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
80 | Flat | 604 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
81 | Flat | 605 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
82 | Flat | 606 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
83 | Flat | 607 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
84 | Flat | 608 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
85 | Flat | 609 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
86 | Flat | 610 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
87 | Flat | 611 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
88 | Flat | 612 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
89 | Flat | 701 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
90 | Flat | 702 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
91 | Flat | 703 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
92 | Flat | 706 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
93 | Flat | 707 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
94 | Flat | 708 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
95 | Flat | 709 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
96 | Flat | 710 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
97 | Flat | 711 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
98 | Flat | 712 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
99 | Flat | 801 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
100 | Flat | 802 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
101 | Flat | 803 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
102 | Flat | 804 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
103 | Flat | 805 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
104 | Flat | 806 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
105 | Flat | 807 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
106 | Flat | 808 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
107 | Flat | 809 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
108 | Flat | 810 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
109 | Flat | 811 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
110 | Flat | 812 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
111 | Flat | 901 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
112 | Flat | 902 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
113 | Flat | 903 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
114 | Flat | 904 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
115 | Flat | 905 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
116 | Flat | 906 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
117 | Flat | 907 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
118 | Flat | 908 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
119 | Flat | 909 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
120 | Flat | 910 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
121 | Flat | 911 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
122 | Flat | 912 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
123 | Flat | 1001 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
124 | Flat | 1002 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
125 | Flat | 1003 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
126 | Flat | 1004 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
127 | Flat | 1005 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
128 | Flat | 1006 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
129 | Flat | 1007 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
130 | Flat | 1008 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
131 | Flat | 1009 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
132 | Flat | 1010 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
133 | Flat | 1011 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
134 | Flat | 1012 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
135 | Flat | 1101 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
136 | Flat | 1102 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
137 | Flat | 1103 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
138 | Flat | 1104 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
139 | Flat | 1105 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
140 | Flat | 1106 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
141 | Flat | 1107 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
142 | Flat | 1108 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
143 | Flat | 1109 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
144 | Flat | 1110 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
145 | Flat | 1111 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
146 | Flat | 1112 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
147 | Flat | 1201 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
148 | Flat | 1202 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
149 | Flat | 1203 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
150 | Flat | 1206 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
151 | Flat | 1207 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
152 | Flat | 1208 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
153 | Flat | 1209 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
154 | Flat | 1210 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
155 | Flat | 1211 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
156 | Flat | 1212 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
157 | Flat | 1301 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
158 | Flat | 1302 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
159 | Flat | 1303 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
160 | Flat | 1304 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
161 | Flat | 1305 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
162 | Flat | 1306 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
163 | Flat | 1307 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
164 | Flat | 1308 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
165 | Flat | 1309 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
166 | Flat | 1310 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
167 | Flat | 1311 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
168 | Flat | 1312 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
169 | Flat | 1401 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
170 | Flat | 1402 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
171 | Flat | 1403 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
172 | Flat | 1404 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
173 | Flat | 1405 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
174 | Flat | 1406 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
175 | Flat | 1407 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
176 | Flat | 1408 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
177 | Flat | 1409 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
178 | Flat | 1410 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
179 | Flat | 1411 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
180 | Flat | 1412 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
181 | Flat | 1501 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
182 | Flat | 1502 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
183 | Flat | 1503 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
184 | Flat | 1504 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
185 | Flat | 1505 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
186 | Flat | 1506 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
187 | Flat | 1507 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
188 | Flat | 1508 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
189 | Flat | 1509 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
190 | Flat | 1510 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
191 | Flat | 1511 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
192 | Flat | 1512 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
193 | Flat | 1601 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
194 | Flat | 1602 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
195 | Flat | 1603 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
196 | Flat | 1606 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
197 | Flat | 1607 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
198 | Flat | 1608 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
199 | Flat | 1609 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
200 | Flat | 1610 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
201 | Flat | 1611 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
202 | Flat | 1612 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
203 | Flat | 1701 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
204 | Flat | 1702 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
205 | Flat | 1703 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
206 | Flat | 1704 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
207 | Flat | 1705 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
208 | Flat | 1706 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
209 | Flat | 1707 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
210 | Flat | 1708 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
211 | Flat | 1709 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
212 | Flat | 1710 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
213 | Flat | 1711 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
214 | Flat | 1712 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
215 | Flat | 1801 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
216 | Flat | 1802 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
217 | Flat | 1803 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
218 | Flat | 1804 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
219 | Flat | 1805 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
220 | Flat | 1806 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
221 | Flat | 1807 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
222 | Flat | 1808 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
223 | Flat | 1809 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
224 | Flat | 1810 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
225 | Flat | 1811 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
226 | Flat | 1812 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
227 | Flat | 1901 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
228 | Flat | 1902 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
229 | Flat | 1903 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
230 | Flat | 1904 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
231 | Flat | 1905 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
232 | Flat | 1906 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
233 | Flat | 1907 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
234 | Flat | 1908 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
235 | Flat | 1909 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
236 | Flat | 1910 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
237 | Flat | 1911 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
238 | Flat | 1912 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
239 | Flat | 2001 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
240 | Flat | 2002 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
241 | Flat | 2003 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
242 | Flat | 2004 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
243 | Flat | 2005 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
244 | Flat | 2006 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
245 | Flat | 2007 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
246 | Flat | 2008 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
247 | Flat | 2009 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
248 | Flat | 2010 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
249 | Flat | 2011 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
250 | Flat | 2012 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
251 | Flat | 2101 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
252 | Flat | 2102 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
253 | Flat | 2103 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
254 | Flat | 2106 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
255 | Flat | 2107 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
256 | Flat | 2108 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
257 | Flat | 2109 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
258 | Flat | 2110 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
259 | Flat | 2111 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
260 | Flat | 2112 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
261 | Flat | 2201 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
262 | Flat | 2202 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
263 | Flat | 2203 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
264 | Flat | 2204 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
265 | Flat | 2205 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
266 | Flat | 2206 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
267 | Flat | 2207 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
268 | Flat | 2208 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
269 | Flat | 2209 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
270 | Flat | 2210 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
271 | Flat | 2211 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
272 | Flat | 2212 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
273 | Flat | 2301 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
274 | Flat | 2302 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
275 | Flat | 2303 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
276 | Flat | 2304 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
277 | Flat | 2305 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
278 | Flat | 2306 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
279 | Flat | 2307 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
280 | Flat | 2308 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
281 | Flat | 2309 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
282 | Flat | 2310 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
283 | Flat | 2311 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
284 | Flat | 2312 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
285 | Flat | 2401 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
286 | Flat | 2402 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
287 | Flat | 2403 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
288 | Flat | 2404 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
289 | Flat | 2405 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
290 | Flat | 2406 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
291 | Flat | 2407 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
292 | Flat | 2408 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
293 | Flat | 2409 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
294 | Flat | 2410 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
295 | Flat | 2411 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
296 | Flat | 2412 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
297 | Flat | 2501 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
298 | Flat | 2502 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
299 | Flat | 2503 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
300 | Flat | 2504 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
301 | Flat | 2505 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
302 | Flat | 2506 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
303 | Flat | 2507 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
304 | Flat | 2508 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
305 | Flat | 2509 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
306 | Flat | 2510 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
307 | Flat | 2511 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
308 | Flat | 2512 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
309 | Flat | 2601 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
310 | Flat | 2602 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
311 | Flat | 2603 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
312 | Flat | 2606 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
313 | Flat | 2607 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
314 | Flat | 2608 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
315 | Flat | 2609 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
316 | Flat | 2610 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
317 | Flat | 2611 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
318 | Flat | 2612 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
319 | Flat | 2701 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
320 | Flat | 2702 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
321 | Flat | 2703 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
322 | Flat | 2704 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
323 | Flat | 2705 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
324 | Flat | 2706 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
325 | Flat | 2707 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
326 | Flat | 2708 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
327 | Flat | 2709 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
328 | Flat | 2710 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
329 | Flat | 2711 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
330 | Flat | 2712 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
331 | Flat | 2801 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
332 | Flat | 2802 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
333 | Flat | 2803 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
334 | Flat | 2804 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
335 | Flat | 2805 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
336 | Flat | 2806 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
337 | Flat | 2807 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
338 | Flat | 2808 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
339 | Flat | 2809 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
340 | Flat | 2810 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
341 | Flat | 2811 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
342 | Flat | 2812 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
343 | Flat | 2901 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
344 | Flat | 2902 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
345 | Flat | 2903 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
346 | Flat | 2904 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
347 | Flat | 2905 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
348 | Flat | 2906 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
349 | Flat | 2907 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
350 | Flat | 2908 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
351 | Flat | 2909 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
352 | Flat | 2910 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
353 | Flat | 2911 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
354 | Flat | 2912 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
355 | Flat | 3002 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
356 | Flat | 3003 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
357 | Flat | 3006 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
358 | Flat | 3007 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
359 | Flat | 3009 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
360 | Flat | 3010 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
361 | Flat | 3011 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
362 | Flat | 3012 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
|  |  | 19280.57 | 1286.2 | 207536.0555 | 13844.6568 | 20566.77 | 221380.7123 | 346315
KASTURI VAN BUILDING NO 1
Carpet Area Saleable Area
Ground Floor Shops area= 728.32 sq.mt 15679 sq.ft
Office P2 floor area= 1723.85 sq.mt 18752 sq.ft
Office P2 floor area= 278.16 sq.mt 5240 sq.ft
Office P3 floor area= 890.01 sq.mt 11525 sq.ft
Total Flats area= 19288.1 sq.mt 346315 sq.ft
Grand Total 22900.94 sq.mt 397511 sq.ft

## Implementation and Revenue
Inflow bifurcation from unsold units
Particulars | Average RERA Carpet (SqF) | Numbr of units | Expected Rate PSF | Total Inflow
1BHK | 386.5106 | 94 | 10000 | 36.332
2 BHK | 577.8034 | 117 | 10000 | 67.603
3 BHK |  |  |  | 0
Shops | 1369 | 2 | 15000 | 4.107 |  | Total Inflow
Offices |  |  |  | 0 |  | 135.412
Total estimated Cash inflow |  |  |  | 108.042
Indicative Implementation and Payment Schedule for Sale Building
Sr No | Timeline | Stages | Payment Schedule | Cumulative Payment Schedule | Financial Year
1 | 2022-12-01 | Excavation & Piling | 10% | 10% | 2022-2023
2 | 2023-03-01 | Plinth | 5% | 15% | 2022-2023
3 | 2023-06-01 | Podium | 5% | 20% | 2023-2024
4 | 2023-09-01 | Podium 2nd Slab | 2.5% | 22.5% | 2023-2024
5 | 2023-12-01 | Podium 4th Slab | 2.5% | 25% | 2023-2024
6 | 2024-03-01 | 3rd Slab | 2.5% | 27.5% | 2023-2024
7 | 2024-06-01 | 6th Slab | 2.5% | 30% | 2024-2025
8 | 2024-09-01 | 9th Slab | 2.5% | 32.5% | 2024-2025
9 | 2024-12-01 | 12th Slab | 2.5% | 35% | 2024-2025
10 | 2025-03-01 | 15th Slab | 2.5% | 37.5% | 2024-2025
11 | 2025-06-01 | 18th Slab | 2.5% | 40% | 2025-2026
12 | 2025-09-01 | 21st Slab | 2.5% | 42.5% | 2025-2026
13 | 2025-12-01 | 24th Slab | 2.5% | 45% | 2025-2026
14 | 2026-03-01 | 27th Slab | 2.5% | 47.5% | 2025-2026
15 | 2026-06-01 | 30th Slab | 2.5% | 50% | 2026-2027
16 | 2026-09-01 | 32nd Slab | 2.5% | 52.5% | 2026-2027
17 | 2026-12-01 | Plumbing and Electrical | 2.5% | 55% | 2026-2027
18 | 2027-03-01 | Plumbing and Electrical | 2.5% | 57.5% | 2026-2027
19 | 2027-06-01 | Internal Finishing | 2.5% | 60% | 2027-2028
20 | 2027-09-01 | Internal Finishing | 2.5% | 62.5% | 2027-2028
21 | 2027-12-01 | Doors & Windows | 2.5% | 65% | 2027-2028
22 | 2028-03-01 | Lift and Other fittings | 5% | 70% | 2027-2028
23 | 2028-06-01 | External Painting and Finishing | 5% | 75% | 2028-2029
24 | 2028-09-01 | External Painting and Finishing | 5% | 80% | 2028-2029
25 | 2028-12-01 | OC Application | 0% | 80% | 2028-2029
26 | 2029-03-01 | OC Ready to occupy | 10% | 90% | 2028-2029
27 | 2029-06-01 | OC Ready to occupy | 10% | 100% | 2029-2030
28 | 2029-09-01 | OC Ready to occupy | 0% | 100% | 2029-2030
29 | 2029-12-01 | OC Ready to occupy | 0% | 100% | 2029-2030
30 | 2030-03-01 | OC Ready to occupy | 0% | 100% | 2029-2030

## Inflow Calculation
Cashflow Timeline
Sr No | Timeline | Financial Year | Construction Stage | 1BHK | 2 BHK | 3 BHK | Shops | Offices | Total Area Sold | Cumulative Area sold | Booking Value | Cum. Sale Value | Payment Due | Cum. Payment Due | Booking Amount due | Receivables from Area Sold
1 | 2022-12-01 | 2022-2023 | Excavation & Piling | [5 empty] | 0 | 0 | 0 | 0 | 10% | 10% | 0 | 0
2 | 2023-03-01 | 2022-2023 | Plinth |  | 1 |  |  |  | 577.8034 | 577.8034 | 0.5778 | 0.5778 | 5% | 15% | 0.086671 | 0.086671
3 | 2023-06-01 | 2023-2024 | Podium |  | 1 |  |  |  | 577.8034 | 1155.6068 | 0.5778 | 1.1556 | 5% | 20% | 0.23112 | 0.14445
4 | 2023-09-01 | 2023-2024 | Podium 2nd Slab | 2 | 1 |  |  |  | 1350.8247 | 2506.4315 | 1.3508 | 2.5064 | 2.5% | 22.5% | 0.56395 | 0.33283
5 | 2023-12-01 | 2023-2024 | Podium 4th Slab | 4 | 3 | 1 |  |  | 3279.4528 | 5785.8843 | 3.2795 | 5.7859 | 2.5% | 25% | 1.4465 | 0.88252
6 | 2024-03-01 | 2023-2024 | 3rd Slab | 3 | 2 | 2 |  |  | 2315.1388 | 8101.0231 | 2.3151 | 8.101 | 2.5% | 27.5% | 2.2278 | 0.78131
7 | 2024-06-01 | 2024-2025 | 6th Slab | 4 | 2 | 3 |  |  | 2701.6494 | 10802.6725 | 2.7016 | 10.8027 | 2.5% | 30% | 3.2408 | 1.013
8 | 2024-09-01 | 2024-2025 | 9th Slab | 5 | 5 | 3 |  |  | 4821.5703 | 15624.2428 | 4.8216 | 15.6242 | 2.5% | 32.5% | 5.0779 | 1.8371
9 | 2024-12-01 | 2024-2025 | 12th Slab | 5 | 3 | 3 |  |  | 3665.9634 | 19290.2062 | 3.666 | 19.2902 | 2.5% | 35% | 6.7516 | 1.6737
10 | 2025-03-01 | 2024-2025 | 15th Slab | 6 | 3 | 1 |  |  | 4052.4741 | 23342.6803 | 4.0525 | 23.3427 | 2.5% | 37.5% | 8.7535 | 2.0019
11 | 2025-06-01 | 2025-2026 | 18th Slab | 4 | 2 | 2 |  |  | 2701.6494 | 26044.3297 | 2.7016 | 26.0443 | 2.5% | 40% | 10.4177 | 1.6642
12 | 2025-09-01 | 2025-2026 | 21st Slab | 4 | 2 | 1 |  |  | 2701.6494 | 28745.9791 | 2.7016 | 28.746 | 2.5% | 42.5% | 12.217 | 1.7993
13 | 2025-12-01 | 2025-2026 | 24th Slab | 5 | 1 | 2 |  |  | 2510.3566 | 31256.3357 | 2.5104 | 31.2563 | 2.5% | 45% | 14.0654 | 1.8483
14 | 2026-03-01 | 2025-2026 | 27th Slab | 2 | 4 |  |  |  | 3084.235 | 34340.5706 | 3.0842 | 34.3406 | 2.5% | 47.5% | 16.3118 | 2.2464
15 | 2026-06-01 | 2026-2027 | 30th Slab | 7 | 2 | 1 |  |  | 3861.1813 | 38201.752 | 3.8612 | 38.2018 | 2.5% | 50% | 19.1009 | 2.7891
16 | 2026-09-01 | 2026-2027 | 32nd Slab | 5 | 3 | 1 |  |  | 3665.9634 | 41867.7154 | 3.666 | 41.8677 | 2.5% | 52.5% | 21.9806 | 2.8797
17 | 2026-12-01 | 2026-2027 | Plumbing and Electrical | 4 | 3 | 2 |  |  | 3279.4528 | 45147.1682 | 3.2795 | 45.1472 | 2.5% | 55% | 24.8309 | 2.8504
18 | 2027-03-01 | 2026-2027 | Plumbing and Electrical | 2 | 3 | 2 |  |  | 2506.4315 | 47653.5997 | 2.5064 | 47.6536 | 2.5% | 57.5% | 27.4008 | 2.5699
19 | 2027-06-01 | 2027-2028 | Internal Finishing | 2 | 3 | 2 |  |  | 2506.4315 | 50160.0313 | 2.5064 | 50.16 | 2.5% | 60% | 30.096 | 2.6952
20 | 2027-09-01 | 2027-2028 | Internal Finishing | 5 | 2 | 1 |  |  | 3088.16 | 53248.1913 | 3.0882 | 53.2482 | 2.5% | 62.5% | 33.2801 | 3.1841
21 | 2027-12-01 | 2027-2028 | Doors & Windows |  | 3 |  | 1 |  | 3102.4103 | 56350.6016 | 3.7869 | 57.0351 | 2.5% | 65% | 37.0728 | 3.7927
22 | 2028-03-01 | 2027-2028 | Lift and Other fittings | 2 | 1 |  |  |  | 1350.8247 | 57701.4263 | 1.3508 | 58.3859 | 5% | 70% | 40.8701 | 3.7973
23 | 2028-06-01 | 2028-2029 | External Painting and Finishing | 3 | 1 | 2 |  |  | 1737.3353 | 59438.7616 | 1.7373 | 60.1233 | 5% | 75% | 45.0924 | 4.2223
24 | 2028-09-01 | 2028-2029 | External Painting and Finishing | 6 | 2 | 3 |  |  | 3474.6707 | 62913.4323 | 3.4747 | 63.5979 | 5% | 80% | 50.8783 | 5.7859
25 | 2028-12-01 | 2028-2029 | OC Application | 13 |  | 1 |  | 2 | 5024.6383 | 67938.0706 | 5.0246 | 68.6226 | 0% | 80% | 54.8981 | 4.0197
26 | 2029-03-01 | 2028-2029 | OC Ready to occupy | 9 | 1 | 6 | 1 | 1 | 5425.3992 | 73363.4697 | 6.1099 | 74.7325 | 10% | 90% | 67.2592 | 12.3612
27 | 2029-06-01 | 2029-2030 | OC Ready to occupy | 35 | 1 | 6 | 1 | 2 | 15474.6758 | 88838.1455 | 16.1592 | 90.8916 | 10% | 100% | 90.8916 | 23.6324
28 | 2029-09-01 | 2029-2030 | OC Ready to occupy | 44 | 1 | 7 | 2 | 3 | 20322.2715 | 109160.417 | 21.6913 | 112.5829 | 0% | 100% | 112.5829 | 21.6913
29 | 2029-12-01 | 2029-2030 | OC Ready to occupy | 45 | 2 | 8 | 2 | 3 | 21286.5856 | 130447.0025 | 22.6556 | 135.2385 | 0% | 100% | 135.2385 | 22.6556
|  |  |  | 226 | 58 | 60 | 7 | 11 | [7 empty] | 135.2385

## Cashflow
Kasturi Van
| Financial Year | 2022-2023 | 2022-2023 | 2023-2024 | 2023-2024 | 2023-2024 | 2023-2024 | 2024-2025 | 2024-2025 | 2024-2025 | 2024-2025 | 2025-2026 | 2025-2026 | 2025-2026 | 2025-2026 | 2026-2027 | 2026-2027 | 2026-2027 | 2026-2027 | 2027-2028 | 2027-2028 | 2027-2028 | 2027-2028 | 2028-2029 | 2028-2029 | 2028-2029 | 2028-2029 | 2029-2030 | 2029-2030 | 2029-2030
|  | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-01 | 2024-03-01 | 2024-06-01 | 2024-09-01 | 2024-12-01 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-01 | 2026-06-01 | 2026-09-01 | 2026-12-01 | 2027-03-01 | 2027-06-01 | 2027-09-01 | 2027-12-01 | 2028-03-01 | 2028-06-01 | 2028-09-01 | 2028-12-01 | 2029-03-01 | 2029-06-01 | 2029-09-01 | 2029-12-01 | Total
Actual
Opening Balance |  |  | 4.73 | 4.7826 | 4.7155 | 4.4425 | 3.7264 | 2.6009 | 0.59217 | -1.8931 | -4.4495 | -6.6209 | -8.9378 | -11.1774 | -13.9185 | -15.8192 | -18.7206 | -21.8103 | -25.4437 | -29.372 | -33.1895 | -36.7825 | -39.6313 | -43.69 | -49.9025 | -58.3303 | -67.7732 | -68.7257 | -59.046 | -51.4465
Booking from Sold Units | [30 empty] | 0
Bookngs from Unsold Units |  | 0 | 0.086671 | 0.14445 | 0.33283 | 0.88252 | 0.78131 | 1.013 | 1.8371 | 1.6737 | 2.0019 | 1.6642 | 1.7993 | 1.8483 | 2.2464 | 2.7891 | 2.8797 | 2.8504 | 2.5699 | 2.6952 | 3.1841 | 3.7927 | 3.7973 | 4.2223 | 5.7859 | 4.0197 | 12.3612 | 23.6324 | 21.6913 | 22.6556 | 135.2385
Total Inflow | 135.2385 | 0 | 0.086671 | 0.14445 | 0.33283 | 0.88252 | 0.78131 | 1.013 | 1.8371 | 1.6737 | 2.0019 | 1.6642 | 1.7993 | 1.8483 | 2.2464 | 2.7891 | 2.8797 | 2.8504 | 2.5699 | 2.6952 | 3.1841 | 3.7927 | 3.7973 | 4.2223 | 5.7859 | 4.0197 | 12.3612 | 23.6324 | 21.6913 | 22.6556 | 135.2385
Land Acquisition Cost | 4.07 | 2022-12-01: 4.07; 2029-03-01: 0.5; 2029-06-01: 0.5; 2029-09-01: 1; 2029-12-01: 1.59 | 7.66
Rent and Hardship Compensation | 0 | 2022-12-01: 0 | 0
Fungible FSI Premium | 0 | 2022-12-01: 0 | 0
TDR | 0 | 2022-12-01: 0 | 0
Approvals and Other Premiums | 0 | 0 | 0.2 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 0.20417 | 8.4342 |  |  |  |  | 13.1258
Construction Cost - Rehab Building | 0 | 2022-12-01: 0 | 0
Construction Cost - Sale Building | 47.34 | 1.44 | 6.5 | 6.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.25 | 5.75 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 4.37 |  |  |  |  | 134.31
Selling and Marketing | 7 | 0 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.23084 | 0.76721 | 7
Professional Fees and Admin expenses | 5 | 0 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.06 |  |  |  |  | 4.2
Contingency | 2.367 | 0 |  |  |  | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 | 0.11271 |  |  |  |  | 2.367
Finance Cost | 3 | 0 | 0.17325 | 0.3465 | 0.49088 | 0.62081 | 0.72909 | 0.79406 | 0.84459 | 0.90234 | 0.94566 | 1.0034 | 1.0612 | 1.1117 | 1.1694 | 1.2127 | 1.2416 | 1.2561 | 1.2705 | 1.2849 | 1.2994 | 1.3138 | 1.3283 | 1.3571 | 1.386 | 1.4149 | 1.0828 | 0.72188 | 0.36094 | 0 | 26.7238
DSRA |  | 2026-06-01: 1; 2028-03-01: 1.25; 2028-06-01: 4; 2028-09-01: 7.75; 2029-12-01: -14 | 0
Cash Outflow | 68.777 | 5.51 | 7.2841 | 7.4615 | 6.6059 | 6.8485 | 6.9568 | 7.0218 | 7.0723 | 7.1301 | 7.1734 | 7.2311 | 7.2889 | 7.3394 | 7.3972 | 8.1905 | 7.7194 | 7.4838 | 7.4982 | 7.5127 | 7.5271 | 7.5415 | 8.806 | 11.5849 | 15.3637 | 14.6226 | 1.8137 | 1.4527 | 1.5918 | -11.6428 | 195.3866
Deficit / Surplus |  | -5.51 | -2.4674 | -2.5345 | -1.5575 | -1.5236 | -2.4491 | -3.4078 | -4.6431 | -7.3495 | -9.6209 | -12.1878 | -14.4274 | -16.6685 | -19.0692 | -21.2206 | -23.5603 | -26.4437 | -30.372 | -34.1895 | -37.5325 | -40.5313 | -44.64 | -51.0525 | -59.4803 | -68.9332 | -57.2257 | -46.546 | -38.9465 | -17.1481
Fund-flow
NOF |  | 10.24 | 10.24 | 11.49 | 12.74 | 13.74 | 14.49 | 15.79 | 17.54 | 18.54 | 19.44 | 20.94 | 22.19 | 23.44 | 24.44 | 25.69 | 26.69 | 27.44 | 27.94 | 28.44 | 28.94 | 29.19 | 29.59 | 30.04 | 30.19 | 30.34 | 30.5 | 30.5 | 30.5 | 30.5 | 10.24
Addition in NOF |  |  | 1.25 | 1.25 | 1 | 0.75 | 1.3 | 1.75 | 1 | 0.9 | 1.5 | 1.25 | 1.25 | 1 | 1.25 | 1 | 0.75 | 0.5 | 0.5 | 0.5 | 0.25 | 0.4 | 0.45 | 0.15 | 0.15 | 0.16 |  |  |  |  | 20.26
NOF Closing Balance |  | 10.24 | 11.49 | 12.74 | 13.74 | 14.49 | 15.79 | 17.54 | 18.54 | 19.44 | 20.94 | 22.19 | 23.44 | 24.44 | 25.69 | 26.69 | 27.44 | 27.94 | 28.44 | 28.94 | 29.19 | 29.59 | 30.04 | 30.19 | 30.34 | 30.5 | 30.5 | 30.5 | 30.5 | 30.5 | 30.5
Loan Disbursed |  | 0 | 6 | 6 | 5 | 4.5 | 3.75 | 2.25 | 1.75 | 2 | 1.5 | 2 | 2 | 1.75 | 2 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 |  |  |  |  | 49
Loan Repaid |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11.5 | -12.5 | -12.5 | -12.5 | -49
Net fund-flow |  | 10.24 | 7.25 | 7.25 | 6 | 5.25 | 5.05 | 4 | 2.75 | 2.9 | 3 | 3.25 | 3.25 | 2.75 | 3.25 | 2.5 | 1.75 | 1 | 1 | 1 | 0.75 | 0.9 | 0.95 | 1.15 | 1.15 | 1.16 | -11.5 | -12.5 | -12.5 | -12.5 | 30.5
Closing Balance |  | 4.73 | 4.7826 | 4.7155 | 4.4425 | 3.7264 | 2.6009 | 0.59217 | -1.8931 | -4.4495 | -6.6209 | -8.9378 | -11.1774 | -13.9185 | -15.8192 | -18.7206 | -21.8103 | -25.4437 | -29.372 | -33.1895 | -36.7825 | -39.6313 | -43.69 | -49.9025 | -58.3303 | -67.7732 | -68.7257 | -59.046 | -51.4465 | -29.6481
Loan Outstanding |  | 0 | 6 | 12 | 17 | 21.5 | 25.25 | 27.5 | 29.25 | 31.25 | 32.75 | 34.75 | 36.75 | 38.5 | 40.5 | 42 | 43 | 43.5 | 44 | 44.5 | 45 | 45.5 | 46 | 47 | 48 | 49 | 37.5 | 25 | 12.5 | 0
Bank Finance : NOF |  | 0 | 0.52219 | 0.94192 | 1.2373 | 1.4838 | 1.5991 | 1.5678 | 1.5777 | 1.6075 | 1.564 | 1.566 | 1.5678 | 1.5753 | 1.5765 | 1.5736 | 1.5671 | 1.5569 | 1.5471 | 1.5377 | 1.5416 | 1.5377 | 1.5313 | 1.5568 | 1.5821 | 1.6066 | 1.2295 | 0.81967 | 0.40984 | 0
Bank Finance to Peak Deficit Ratio |  | 0% | 75.21% | 114.2% | 140.9% | 158.2% | 157.4% | 141.4% | 121.4% | 99.39% | 79.75% | 65.26% | 54.3% | 45.64% | 39.16% | 33.7% | 29.02% | 24.91% | 21.46% | 18.6% | 16.26% | 14.34% | 12.71% | 11.38% | 10.16% | 9.051%
Loan to Construction % |  | 0% | 75.57% | 83.1% | 85.26% | 84.51% | 81.61% | 75.47% | 69.74% | 65.87% | 61.86% | 59.46% | 57.48% | 55.44% | 54.04% | 52.38% | 50.03% | 47.57% | 45.39% | 43.44% | 41.69% | 40.11% | 38.67% | 37.77% | 36.94% | 36.48% | 27.92% | 18.61% | 9.307% | 0%
Loan Disbursement % : Promoter Margin % |  | 0 | 0.35927 | 0.64804 | 0.85124 | 1.0208 | 1.1002 | 1.0787 | 1.0854 | 1.106 | 1.076 | 1.0774 | 1.0787 | 1.0838 | 1.0846 | 1.0827 | 1.0781 | 1.0712 | 1.0644 | 1.0579 | 1.0606 | 1.0579 | 1.0535 | 1.0711 | 1.0885 | 1.1053 | 0.8459 | 0.56393 | 0.28197 | 0

## Loan - SBI
11.55%
Sr No. | Financial Year | Quarter | Disbursement | Repayment | Interest | POS
1 | 2022-2023 | 2022-12-01 | 0 | 0 | 0 | 0
2 | 2022-2023 | 2023-03-01 | 6 | 0 | 0.17325 | 6
3 | 2023-2024 | 2023-06-01 | 6 | 0 | 0.3465 | 12
4 | 2023-2024 | 2023-09-01 | 5 | 0 | 0.49088 | 17
5 | 2023-2024 | 2023-12-01 | 4.5 | 0 | 0.62081 | 21.5
6 | 2023-2024 | 2024-03-01 | 3.75 | 0 | 0.72909 | 25.25
7 | 2024-2025 | 2024-06-01 | 2.25 | 0 | 0.79406 | 27.5
8 | 2024-2025 | 2024-09-01 | 1.75 | 0 | 0.84459 | 29.25
9 | 2024-2025 | 2024-12-01 | 2 | 0 | 0.90234 | 31.25
10 | 2024-2025 | 2025-03-01 | 1.5 | 0 | 0.94566 | 32.75
11 | 2025-2026 | 2025-06-01 | 2 | 0 | 1.0034 | 34.75
12 | 2025-2026 | 2025-09-01 | 2 | 0 | 1.0612 | 36.75
13 | 2025-2026 | 2025-12-01 | 1.75 | 0 | 1.1117 | 38.5
14 | 2025-2026 | 2026-03-01 | 2 | 0 | 1.1694 | 40.5
15 | 2026-2027 | 2026-06-01 | 1.5 | 0 | 1.2127 | 42
16 | 2026-2027 | 2026-09-01 | 1 | 0 | 1.2416 | 43
17 | 2026-2027 | 2026-12-01 | 0.5 | 0 | 1.2561 | 43.5
18 | 2026-2027 | 2027-03-01 | 0.5 | 0 | 1.2705 | 44
19 | 2027-2028 | 2027-06-01 | 0.5 | 0 | 1.2849 | 44.5
20 | 2027-2028 | 2027-09-01 | 0.5 | 0 | 1.2994 | 45
21 | 2027-2028 | 2027-12-01 | 0.5 | 0 | 1.3138 | 45.5
22 | 2027-2028 | 2028-03-01 | 0.5 | 0 | 1.3283 | 46
23 | 2028-2029 | 2028-06-01 | 1 | 0 | 1.3571 | 47
24 | 2028-2029 | 2028-09-01 | 1 | 0 | 1.386 | 48
25 | 2028-2029 | 2028-12-01 | 1 | 0 | 1.4149 | 49
26 | 2028-2029 | 2029-03-01 | 0 | -11.5 | 1.0828 | 37.5
27 | 2029-2030 | 2029-06-01 | 0 | -12.5 | 0.72188 | 25
28 | 2029-2030 | 2029-09-01 | 0 | -12.5 | 0.36094 | 12.5
29 | 2029-2030 | 2029-12-01 | 0 | -12.5 | 0 | 0
Total |  |  | 49 | -49 | 26.7238

## FACR
Sr No | Calculations | Amount in Cr
A | Realizable Value of the land | 79.75
B | Cost of approvals at peak disbursement level | 13.1258
C | Cost of Construction at Peak Disbursement Level | 134.31
D | Adances at Peak Disbursement Level | 54.8981
E | DSRA | 14
F = A+B+C-D+E | Net Security Available | 186.2878
G | Peak Disbursement | 49
H = F/G | FACR | 3.8018

## Annualised Cashflow
Particulars | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030
Advance from the bookings | 0.086671 | 2.1411 | 6.5257 | 7.5583 | 11.089 | 13.4693 | 26.3891 | 67.9793
Land Acquisition | 4.07 | 0 | 0 | 0 | 0 | 0 | 0.5 | 3.09
Construction Expenses - Outflow | 8.14 | 23.8167 | 22.8167 | 22.8167 | 22.8167 | 22.8167 | 24.2125 | 0
Selling and Administration Cost | 0.41084 | 1.6434 | 1.6434 | 1.6434 | 1.6434 | 1.6434 | 1.3434 | 1.2289
Finance Cost | 0.17325 | 2.1873 | 3.4867 | 4.3457 | 4.9809 | 5.2264 | 5.2408 | 1.0828
Contingencies | 0 | 0.22543 | 0.45086 | 0.45086 | 0.45086 | 0.45086 | 0.33814 | 0
DSRA | 0 | 0 | 0 | 0 | 1 | 1.25 | 11.75 | -14
Area Sold | 577.8034 | 7523.2197 | 15241.6572 | 10997.8903 | 13313.0291 | 10047.8265 | 15662.0435 | 57083.5328
% Area Sold | 0.4429% | 5.767% | 11.68% | 8.431% | 10.21% | 7.703% | 12.01% | 43.76%
Project Completion | 5.521% | 21.67% | 37.15% | 52.63% | 68.1% | 83.58% | 100% | 100%
Sale Value | 0.5778 | 7.5232 | 15.2417 | 10.9979 | 13.313 | 10.7323 | 16.3465 | 60.506
Cumulative Direct Cost | 12.7941 | 40.6668 | 69.0644 | 98.321 | 128.2128 | 158.3501 | 189.9849 | 195.3866
Promoter contribution | 11.49 | 15.79 | 20.94 | 25.69 | 28.44 | 30.04 | 30.5 | 30.5
Loan Disbursement | 6 | 19.25 | 7.5 | 7.75 | 3.5 | 2 | 3 | 0
Cumulative Loan Disbursement | 6 | 25.25 | 32.75 | 40.5 | 44 | 46 | 49 | 49
Loan Repayment | 0 | 0 | 0 | 0 | 0 | 0 | -11.5 | -37.5
Cumulative Loan Repayment | 0 | 0 | 0 | 0 | 0 | 0 | -11.5 | -49
Loan Outstanding | 6 | 25.25 | 32.75 | 40.5 | 44 | 46 | 37.5 | 0

## CMA
Operating Statement
Particulars | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030
Revenue from the project | 0 | 0 | 0 | 0 | 0 | 0 | 74.7325 | 60.506
Costs
Land Acquisition Cost | 4.07 | 0 | 0 | 0 | 0 | 0 | 0.5 | 3.09
Construction Expenses - Outflow | 8.14 | 24.0421 | 23.2675 | 23.2675 | 23.2675 | 23.2675 | 24.5506 | 0
Selling and Administration Cost | 0.41084 | 1.6434 | 1.6434 | 1.6434 | 1.6434 | 1.6434 | 1.3434 | 1.2289
Finance Cost | 0.17325 | 2.1873 | 3.4867 | 4.3457 | 4.9809 | 5.2264 | 5.2408 | 1.0828
Opening WIP |  | 12.7941 | 40.6668 | 69.0644 | 98.321 | 128.2128 | 158.3501 | 83.1373
Closing WIP | 12.7941 | 40.6668 | 69.0644 | 98.321 | 128.2128 | 158.3501 | 83.1373 | 0
Profit | 0 | 0 | 0 | 0 | 0 | 0 | -32.1152 | -28.033
Taxes | 0 | 0 | 0 | 0 | 0 | 0 | -9.6346 | -8.4099
PAT | 0 | 0 | 0 | 0 | 0 | 0 | -22.4806 | -19.6231
Balance Sheet
Current Liabilities
CC
Advance from Customers | 0.086671 | 2.2278 | 8.7535 | 16.3118 | 27.4008 | 40.8701 | 0 | 0
Provision for taxes | 0 | 0 | 0 | 0 | 0
Loan to be repaid in next 12 months | 0 | 0 | 0 | 0 | 0 | 11.5 | 37.5 | 0
Term Liabilities
Term Loan Outstanding | 6 | 25.25 | 32.75 | 40.5 | 44 | 34.5 | 0 | 0
USL From Promoters
TNW
Equity Capital | 11.49 | 15.79 | 20.94 | 25.69 | 28.44 | 30.04 | 30.5 | 30.5
Reserves and Surplus | 0 | 0 | 0 | 0 | 0 | 0 | -22.4806 | -42.1037
Total Liabilities | 17.5767 | 43.2678 | 62.4435 | 82.5018 | 99.8408 | 116.9101 | 45.5194 | -11.6037
Current Assets
Cash and Bank Balance | 4.7826 | 2.6009 | -6.6209 | -15.8192 | -29.372 | -43.69 | -68.7257 | -29.6481
DSRA | 0 | 0 | 0 | 0 | 1 | 1.25 | 11.75 | 0
Receivables from Sold Units | 0 | 0 | 0 | 0 | 0
Work in Process | 12.7941 | 40.6668 | 69.0644 | 98.321 | 128.2128 | 158.3501 | 83.1373 | 0
Finished Goods
Total Assets | 17.5767 | 43.2678 | 62.4435 | 82.5018 | 99.8408 | 115.9101 | 26.1616 | -29.6481
Mismatch | 0 | 0 | 0 | 0 | 0

## Bar Chart Construction - Sale (hidden)
Kasturi Van
Cost Break-up | % of Total Cost | Cost | 2020-03-01 | 2020-06-01 | 2020-09-01 | 2020-12-01 | 2021-03-01 | 2021-06-01 | 2021-09-01 | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-01 | Total
% |  |  | 2020-03-01: 100% | 100%
Substructure Cost | 25.61% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  | 2020-03-01: 16.4%; 2020-06-01: 4.85%; 2020-09-01: 15%; 2020-12-01: 15%; 2021-03-01: 15%; 2021-06-01: 15%; 2021-09-01: 10%; 2021-12-01: 5%; 2022-03-01: 3.75% | 100%
Brick Work / Block Work | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 20% | 15% | 20% | 15% | 10% | 10% | 2.5% | 5% | 2.5% | [5 empty] | 100%
RCC | 20% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 15% | 15% | 10% | 10% | 10% | 10% | 10% | 5% | 5% | 5% | 5% |  |  |  | 100%
POP, White wash and plastering | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 15% | 15% | 20% | 15% | 10% | 5% | 5% | 5% | 5% | 5% |  |  |  |  | 100%
Tiling (Italian Marble) | 5.22% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  | 2020-06-01: 0%; 2020-09-01: 15%; 2020-12-01: 15%; 2021-03-01: 20%; 2021-06-01: 15%; 2021-09-01: 20%; 2021-12-01: 5%; 2022-06-01: 5%; 2022-09-01: 5% | 100%
Doors and Windows | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
% |  |  | 2020-06-01: 0%; 2020-09-01: 10%; 2020-12-01: 10%; 2021-03-01: 20%; 2021-06-01: 20%; 2021-09-01: 20%; 2021-12-01: 15%; 2022-03-01: 5% | 100%
Water Supply, electrification and Sanitory work | 3% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
% |  |  | 2021-09-01: 25%; 2021-12-01: 25%; 2022-03-01: 10%; 2022-12-01: 10%; 2023-03-01: 15%; 2023-06-01: 15% | 100%
Painting | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  | 2021-12-01: 25%; 2022-09-01: 0%; 2022-12-01: 15%; 2023-03-01: 20%; 2023-06-01: 20%; 2023-09-01: 10%; 2023-12-01: 10% | 100%
Elevators | 6.168% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
% |  |  | 2022-12-01: 40%; 2023-03-01: 25%; 2023-06-01: 25%; 2023-09-01: 5%; 2023-12-01: 5% | 100%
Fire Fighting | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  | 2023-03-01: 50%; 2023-06-01: 50% | 100%
Landscape and outside infrastructure | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
TOTAL | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!