## Dashboard (hidden)
Dashboard
 | time axis 2016-12-31 to 2023-02-01
Total Area in Project |  | 8375604
Total Area Launch in Project | Sq Ft | 5075860
Total Units Launch in Project | Units | 4508
Sales In the Month | Area |  | 9460 | 15815 | 17640 | 26910 | 38710 | 19915 | 96285 | 135470 | 152695 | 24040 | 15065 | 24505 | 21575 | 39970 | 60795 | 102895 | 17960 | 23545 | 28270 | 77515 | 60530 | 69300 | 51400 | 45870 | 43185 | 62815 | 62725 | 28665 | 122420 | 63025 | 72890 | 43605 | 15050 | 23255 | 71395 | 41865 | 19340 | 12765 | 32265 | 19845 | 0 | 14105 | 13225 | 13650 | 22185 | 7355 | 7185 | 13690 | 19710 | 43250 | 21340 | 16020 | 8735 | 2760 | 14195 | 41600 | 26175 | 770 | 34155 | 10080 | 25555 | 34305 | 28565 | 51790 | 43385 | 44893 | 22810 | 38630 | 26590 | 41985 | 19860 | 29165 | 37270 | 13780 | 22595
Sold Units | Units |  | 7 | 13 | 14 | 21 | 32 | 17 | 83 | 121 | 133 | 21 | 13 | 20 | 18 | 34 | 53 | 88 | 17 | 16 | 25 | 68 | 53 | 58 | 42 | 37 | 35 | 50 | 56 | 22 | 104 | 62 | 66 | 39 | 14 | 21 | 63 | 38 | 17 | 10 | 29 | 18 | 0 | 12 | 12 | 13 | 20 | 7 | 7 | 12 | 17 | 39 | 21 | 13 | 9 | 2 | 14 | 35 | 25 | 1 | 31 | 10 | 15 | 30 | 26 | 45 | 39 | 37 | 20 | 33 | 22 | 35 | 19 | 22 | 31 | 13 | 18
Value of Sold Area | Rs. Cr |  | 3.88 | 6.76 | 7.2 | 11.14 | 15.95 | 8.37 | 41.53 | 60.02 | 67.46 | 9.94 | 6.47 | 11.375 | 9.82 | 18.65 | 29.62 | 49.52 | 8.35 | 12.01 | 14.7 | 39.67 | 31.02 | 35.35 | 26.28 | 25.83 | 21.05 | 31.97 | 31.38 | 14.11 | 61.87 | 31.63 | 37.42 | 20.82 | 7.61 | 12.22 | 36.55 | 21.64 | 9.69 | 6.55 | 15.78 | 10.14 | 0 | #REF! | 7.24 | 7.04 | 11.68 | 3.78 | 4 | 7.26 | 10.23 | 22.55 | 11.07 | 8.71 | 4.94 | 1.61 | 7.87 | 22.84 | 11.44 | 0.41 | 18.93 | 5.28 | 12.67 | 18.96 | 16.87 | 28.87 | 24.13 | 25.13 | 12.7 | 21.69 | 16.05 | 25.33 | 11.33 | 17.26 | 21.6 | 8.35 | 14.31
Cancellations (if any) | Sq Ft |  | 0 | 10320 | 4705 | 5300 | 4050 | 970 | 5020 | 2535 | 19865 | 28825 | 21855 | 8005 | 970 | 13750 | 1940 | 7995 | 7040 | 0 | 16415 | 4120 | 8180 | 21640 | 8065 | 6215 | 7145 | 9110 | 15195 | 3170 | 14495 | 20645 | 11695 | 5880 | 29765 | 19360 | 34180 | 20260 | 8775 | 6745 | 21150 | 2510 | 0 | 770 | 13080 | 1380 | 9520 | 11235 | 5885 | 6650 | 2695 | 23225 | 6985 | 5975 | 5655 | 0 | 0 | 970 | 4850 | 0 | 8605 | 4250 | 6670 | 14235 | 9935 | 19150 | 19250 | 48993 | 46200 | 62385 | 8735 | 53165 | 0 | 4330 | 0 | 0 | 2555
Cancellations (if any) | Units |  | 0 | 9 | 4 | 4 | 4 | 1 | 5 | 2 | 18 | 24 | 18 | 7 | 1 | 11 | 2 | 7 | 6 | 0 | 15 | 3 | 8 | 19 | 6 | 6 | 8 | 9 | 14 | 2 | 12 | 16 | 11 | 5 | 29 | 18 | 30 | 18 | 8 | 8 | 17 | 3 | 0 | 1 | 12 | 1 | 9 | 11 | 5 | 6 | 3 | 21 | 7 | 6 | 5 | 0 | 0 | 1 | 4 | 0 | 8 | 4 | 5 | 12 | 9 | 16 | 19 | 49 | 39 | 57 | 8 | 45 | 0 | 3 | 0 | 0 | 2
Value of Cancellations | Rs. Cr |  | 0 | 4.4 | 2.16 | 2.26 | 1.81 | 0.41 | 2 | 1.04 | 8.28 | 12.82 | 9.17 | 3.41 | 0.48 | 6.22 | 0.92 | 3.45 | 3.45 | 0 | 7.53 | 2.03 | 3.28 | 10.77 | 3.94 | 2.97 | 7.24 | 4.04 | 7.44 | 1.11 | 7.67 | 10.52 | 6.05 | 3.03 | 15.03 | 10.1 | 16.94 | 9.8 | 4.06 | 3.23 | 10.06 | 1.21 | 0 | 0.37856 | 6.58 | 0.72 | 4.72 | 5.64 | 3.08 | 3.34 | 1.4 | 10.53 | 3.69 | 3.09 | 3.03 | 0 | 0 | 0.55 | 2.44 | 0 | 4.27 | 2.38 | 3.13 | 7.08 | 5.08 | 9.96 | 11.07 | 23.13 | 24.39 | 32.25 | 4.38 | 28.25 | 0 | 2.39 | 0 | 0 | 1.09
Refunds/Cancellations / Forfeited (if any)/ | Rs. Cr |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.03 | 1.06 | 1.76 | 0 | 1.55 | 0.79 | 0 | 3.68 | 1.01 | 0.46 | 0.47 | 0.97 | 0.43 | 0.94 | 2.49 | 0.92 | 0.49 | 0.78 | 0.45 | 0 | 0 | 0.62 | 0 | 0.83 | 1.24 | 0.11 | 0.39 | 0.65 | 2.48 | 0.18 | 0.59 | 0.11 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.05 | 0.05 | 0.25 | 5 | 5 | 1 | 0.1 | 0.2 | 1.2 | 0
Collections from old sales | Rs. Cr |  | 21.78 | 14.14 | 15.28 | 13.07 | 16.36 | 15.91 | 9.8 | 15.29 | 19.17 | 30.49 | 24.07 | 24.18 | 18.97 | 17.78 | 21.21 | 13.55 | 17.52 | 13.94 | 14.74 | 15.99 | 19.3 | 20.17 | 23.13 | 19.19 | 17.39 | 14.44 | 27.28 | 23.28 | 23.27 | 24.35 | 19.99 | 15.96 | 24.17 | 22.77 | 14.64 | 25.61 | 15.83 | 14.69 | 21.02 | 11.88 | 1.22 | 2.59 | 5.2 | 19.96 | 16.22 | 17.68 | 14.91 | 7.87 | 8.35 | 3.33 | 17.6 | 45.82 | 22.64 | 7.48 | 14.88 | 26.61 | 16.53 | 31.49 | 13.59 | 9.91 | 9.72 | 5.82 | 7.94 | 11.26 | 12.89 | 12.53 | 9.13 | 10.93 | 8.86 | 7.13 | 8.35 | 6.95 | 9.19 | 10.28 | 8.11
Collections from fresh sales (this month) | Rs. Cr |  | 0.09 | 0.92 | 0.45 | 0.44 | 0.81 | 0.56 | 6.21 | 2.02 | 3.19 | 0.42 | 0.33 | 0.58 | 0.36 | 0.83 | 1.13 | 0.78 | 0.49 | 0.55 | 0.23 | 0.36 | 1.27 | 0.46 | 1.81 | 0.69 | 3.13 | 4.19 | 0.728 | 0.26 | 2.44 | 1.39 | 2.22 | 0.87 | 0.51 | 0.3 | 4.34 | 2.36 | 1.48 | 1.11 | 2.44 | 0.42 | 0 | 0.21 | 0.4 | 0.81 | 0.97 | 0.39 | 0.12 | 0.31 | 0.79 | 1.39 | 0.9 | 0.83 | 0.58 | 0.09 | 0.2 | 0.88 | 0.69 | 0.38 | 1.84 | 0.7 | 0.53 | 2.44 | 1.97 | 3.02 | 2.15 | 4.8 | 0.44 | 3.05 | 1.38 | 1.02 | 2.42 | 2.49 | 3.27 | 0.53 | 0.33
Total Collection (customer/Allotees) |  |  | 21.87 | 15.06 | 15.73 | 13.51 | 17.17 | 16.47 | 16.01 | 17.31 | 22.36 | 30.91 | 24.4 | 24.76 | 19.33 | 18.61 | 22.34 | 14.33 | 18.01 | 14.49 | 14.97 | 16.35 | 20.57 | 18.6 | 23.88 | 18.12 | 20.52 | 17.08 | 27.218 | 23.54 | 22.03 | 24.73 | 21.75 | 16.36 | 23.71 | 22.64 | 18.04 | 25.48 | 16.39 | 15.31 | 22.68 | 11.85 | 1.22 | 2.8 | 4.98 | 20.77 | 16.36 | 16.83 | 14.92 | 7.79 | 8.49 | 2.24 | 18.32 | 46.06 | 23.11 | 7.57 | 15.08 | 27.48 | 17.22 | 31.87 | 15.43 | 10.61 | 10.25 | 8.26 | 9.91 | 14.28 | 15.04 | 17.33 | 9.57 | 13.98 | 10.24 | 8.15 | 10.77 | 9.44 | 12.46 | 10.81 | 8.44
GST Rebate, Subvention Interest and TDS | [18 empty] | 1.44 | 0.77 | 0.87 | 0.91 | 2.15 | 1.38 | 1.37 | 1.33 | 0.98 | 1.57 | 2.24 | 1.829 | 4.47 | 4.89 | 2.82 | 3.17 | 2.81 | 1.82 | 1.66 | 3.57 | 1.69 | 1.8 | 2.72 | 1.57 | 0.1 | 0.51 | 0.25 | 2.24 | 10.41 | 1.7 | 1.43 | 1.09 | 0.66 | 0.7 | 7.12 | 0.13 | 0.88 | 0.17 | 0.07 | 2.78 | 0.97 | 3.1 | 1.64 | 0.34 | 0.64 | 0.78 | 0.86 | 1.42 | 1.11 | 1.11 | 0.69 | 1.05 | 0.89 | 0.33 | 0.26 | 0.15 | 0.53 | 0.54 | 0.18
Net Collection (in Bank) | [18 empty] | 16.57 | 13.72 | 14.1 | 15.44 | 18.42 | 17.22 | 22.51 | 16.79 | 19.54 | 15.51 | 24.978 | 21.711 | 17.56 | 19.84 | 18.93 | 13.19 | 20.9 | 20.82 | 16.38 | 21.91 | 14.7 | 13.51 | 19.96 | 10.28 | 1.12 | 2.29 | 4.73 | 18.53 | 5.95 | 15.13 | 13.49 | 6.7 | 7.83 | 1.54 | 11.2 | 45.93 | 22.23 | 7.4 | 15.01 | 24.7 | 16.25 | 28.77 | 13.79 | 10.27 | 9.61 | 7.48 | 9.05 | 12.86 | 13.93 | 16.22 | 8.88 | 12.93 | 9.35 | 7.82 | 10.51 | 9.29 | 11.93 | 10.27 | 8.26
Escrow Account Balance | Rs. Cr |  |  | 0.59 | 1.52 | 0.97 | 0.75 | 0.73 | 0.78 | 0.57 | 0.78 | 3.26 | 0.84 | 1.27 | 3.22 | 2.09 | 2.22 | 1.03 | 2.51 | 2.02 | 1.14 | 1.59 | 1.36 | 1.04 | 2.96 | 2.2 | 1.05 | 0.87 | 4.07 | 2.49 | 3.51 | 1.45 | 1.95 | 1.91 | 0.26 | 1.55 | 0.94 | 0.58 | 2.47 | 0.78 | 0.57 | 0.45 | 0.45 | 0.45 | 0.43 | 2.16 | 2.16 | 1.29 | 1.29 | 0.12 | 0.72 | 0.72 | 0 | 2.27 | 2.27 | 0.44 | 1.18 | 1.45 | 2.43 | 1.71 | 0.14 | 0.03 | 0 | 0.05 | 0.12 | 0.98 | 0.45 | 0 | 0.01 | 0.31 | 0 | 1.52 | 1.33 | 0 | 0 | 0 | 0
HDFC Escrow Balance + Operating A/c | Rs. Cr |  |  | 0.59 | 1.52 | 0.97 | 0.75 | 0.73 | 0.78 | 0.57 | 0.78 | 3.26 | 0.84 | 1.27 | 3.22 | 2.09 | 2.22 | 1.03 | 2.51 | 2.02 | 1.14 | 1.59 | 1.36 | 1.04 | 2.96 | 2.2 | 1.05 | 0.87 | 4.07 | 2.49 | 3.51 | 1.45 | 1.95 | 1.91 | 0.26 | 1.55 | 0.94 | 0.58 | 2.47 | 0.78 | 0.57 | 0.45 | 0.45 | 0.45 | 0.43 | 2.16 | 2.16 | 1.29 | 1.29 | 0.12 | 0.72 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Existing Bank Escrow (If Any ) Balance | Rs. Cr |  | 2018-06-30: 0; 2018-07-31: 0; 2018-08-31: 0; 2018-09-30: 0; 2018-10-31: 0; 2018-11-30: 0; 2018-12-31: 0; 2019-01-31: 0; 2019-02-28: 0; 2019-03-31: 0; 2019-04-30: 0; 2019-05-31: 0
Cumulative sold | Sq Ft | 2253090 | 2262550 | 2268045 | 2280980 | 2302590 | 2337250 | 2356195 | 2447460 | 2581550 | 2714380 | 2709595 | 2702805 | 2719305 | 2739910 | 2766130 | 2824985 | 2919885 | 2930805 | 2954350 | 2966205 | 3039600 | 3091950 | 3139610 | 3182945 | 3222610 | 3258650 | 3312355 | 3359885 | 3385380 | 3493305 | 3536295 | 3597490 | 3635215 | 3620500 | 3624395 | 3661610 | 3683215 | 3693780 | 3699800 | 3710915 | 3728250 | 3728250 | 3741585 | 3741730 | 3754000 | 3766665 | 3762785 | 3764085 | 3771125 | 3788140 | 3808165 | 3822520 | 3832565 | 3835645 | 3838405 | 3852600 | 3893230 | 3914555 | 3915325 | 3940875 | 3946705 | 3965590 | 3985660 | 4004290 | 4036930 | 4061065 | 4056965 | 4033575 | 4009820 | 4027675 | 4016495 | 4036355 | 4061190 | 4098460 | 4112240 | 4132280
Cumulative sold | units | 1996 | 2003 | 2007 | 2017 | 2034 | 2062 | 2078 | 2156 | 2276 | 2391 | 2388 | 2383 | 2396 | 2413 | 2436 | 2487 | 2568 | 2579 | 2595 | 2605 | 2670 | 2715 | 2754 | 2790 | 2821 | 2848 | 2889 | 2931 | 2951 | 3043 | 3089 | 3144 | 3178 | 3163 | 3166 | 3199 | 3219 | 3228 | 3230 | 3242 | 3257 | 3257 | 3268 | 3268 | 3280 | 3291 | 3287 | 3289 | 3295 | 3309 | 3327 | 3341 | 3348 | 3352 | 3354 | 3368 | 3402 | 3423 | 3424 | 3447 | 3453 | 3463 | 3481 | 3498 | 3527 | 3547 | 3535 | 3516 | 3492 | 3506 | 3496 | 3515 | 3534 | 3565 | 3578 | 3594
Area unsold | Sq Ft | 2822770 | 2813310 | 2807815 | 2794880 | 2773270 | 2738610 | 2719665 | 2628400 | 2494310 | 2361480 | 2366265 | 2373055 | 2356555 | 2335950 | 2309730 | 2250875 | 2155975 | 2152815 | 2129270 | 2109655 | 2036260 | 1983910 | 1936250 | 1892915 | 1853250 | 1817210 | 1763505 | 1715975 | 1690480 | 1582555 | 1539565 | 1478370 | 1440645 | 1455360 | 1451465 | 1414250 | 1392645 | 1382080 | 1376060 | 1364945 | 1347610 | 1347610 | 1334275 | 1334130 | 1321860 | 1309195 | 1313075 | 1311775 | 1304735 | 1287720 | 1267695 | 1253340 | 1243295 | 1240215 | 1237455 | 1223260 | 1182630 | 1161305 | 1160535 | 1134985 | 1129155 | 1110270 | 1090200 | 1071570 | 1038930 | 1014795 | 1018895 | 1042285 | 1066040 | 1048185 | 1059365 | 1039505 | 1014670 | 977400 | 963620 | 943580
Units unsold | Units | 2512 | 2505 | 2501 | 2491 | 2474 | 2446 | 2430 | 2352 | 2232 | 2117 | 2120 | 2125 | 2112 | 2095 | 2072 | 2021 | 1940 | 1937 | 1921 | 1903 | 1838 | 1793 | 1754 | 1718 | 1687 | 1660 | 1619 | 1577 | 1557 | 1465 | 1419 | 1364 | 1330 | 1345 | 1342 | 1309 | 1289 | 1280 | 1278 | 1266 | 1251 | 1251 | 1240 | 1240 | 1228 | 1217 | 1221 | 1219 | 1213 | 1199 | 1181 | 1167 | 1160 | 1156 | 1154 | 1140 | 1106 | 1085 | 1084 | 1061 | 1055 | 1045 | 1027 | 1010 | 981 | 961 | 973 | 992 | 1016 | 1002 | 1012 | 993 | 974 | 943 | 930 | 914
Cumulative Value of Sold | Rs. Cr | 991.19 | 995.07 | 997.43 | 1002.47 | 1011.35 | 1025.49 | 1033.45 | 1072.98 | 1131.96 | 1191.14 | 1188.26 | 1185.56 | 1193.525 | 1202.865 | 1215.295 | 1267.255 | 1313.325 | 1318.225 | 1330.235 | 1337.405 | 1375.045 | 1402.785 | 1427.365 | 1449.705 | 1472.565 | 1486.375 | 1514.305 | 1538.245 | 1551.245 | 1605.445 | 1617.905 | 1649.275 | 1667.065 | 1659.645 | 1661.765 | 1681.375 | 1693.215 | 1698.845 | 1702.165 | 1707.885 | 1716.815 | 1716.815 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cumulative Collections |  | 532.82 | 554.69 | 569.47 | 584.56 | 598.16 | 615.32 | 631.64 | 647.53 | 664.36 | 686.01 | 715.64 | 737.19 | 761.455 | 780.825 | 798.705 | 820.985 | 834.865 | 852.875 | 867.365 | 881.465 | 897.815 | 918.385 | 936.985 | 960.865 | 978.985 | 999.505 | 1016.585 | 1043.803 | 1067.343 | 1092.473 | 1117.203 | 1138.953 | 1155.313 | 1179.993 | 1203.063 | 1222.043 | 1247.523 | 1263.913 | 1279.223 | 1301.903 | 1313.753 | 1314.973 | 1317.773 | 1322.753 | 1343.523 | 1359.883 | 1376.713 | 1391.113 | 1398.903 | 1407.393 | 1409.633 | 1427.953 | 1474.013 | 1497.123 | 1504.693 | 1519.773 | 1547.253 | 1564.473 | 1596.343 | 1611.773 | 1622.383 | 1632.633 | 1640.893 | 1650.703 | 1664.983 | 1680.023 | 1697.303 | 1706.823 | 1720.553 | 1725.793 | 1728.943 | 1738.713 | 1748.053 | 1760.313 | 1769.923 | 1778.363
Receivables book (total sold but not received) | Rs. Cr |  | 440.38 | 427.96 | 417.91 | 413.19 | 410.17 | 401.81 | 425.45 | 467.6 | 505.13 | 472.62 | 448.37 | 432.07 | 422.04 | 416.59 | 446.27 | 478.46 | 465.55 | 463.07 | 455.94 | 477.23 | 483.91 | 490.38 | 488.84 | 493.58 | 488.54 | 497.72 | 494.442 | 483.902 | 512.972 | 500.702 | 510.322 | 511.472 | 479.652 | 458.702 | 459.332 | 445.692 | 434.932 | 422.942 | 405.982 | 403.062 | 401.842 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Value of unsold (as per business plan) | Rs. Cr |  | 1406.655 | 1403.9075 | 1397.44 | 1386.635 | 1369.305 | 1359.8325 | 1314.2 | 1247.155 | 1180.74 | 1183.1325 | 1186.5275 | 1178.2775 | 1167.975 | 1154.865 | 1125.4375 | 1077.9875 | 1076.4075 | 1064.635 | 1054.8275 | 1018.13 | 991.955 | 968.125 | 946.4575 | 926.625 | 908.605 | 881.7525 | 857.9875 | 845.24 | 791.2775 | 769.7825 | 739.185 | 720.3225 | 727.68 | 725.7325 | 707.125 | 696.3225 | 691.04 | 688.03 | 682.4725 | 673.805 | 673.805 | 667.1375 | 667.065 | 660.93 | 654.5975 | 656.5375 | 655.8875 | 652.3675 | 643.86 | 633.8475 | 664.2702 | 658.9464 | 657.3139 | 655.8511 | 648.3278 | 626.7939 | 615.4917 | 615.0835 | 601.5421 | 598.4521 | 588.4431 | 577.806 | 567.9321 | 550.6329 | 537.8414 | 540.0144 | 625.371 | 639.624 | 628.911 | 635.619 | 623.703 | 608.802 | 635.31 | 674.534 | 660.506
Receivables + value of unsold | Rs. Cr |  | 1847.035 | 1831.8675 | 1815.35 | 1799.825 | 1779.475 | 1761.6425 | 1739.65 | 1714.755 | 1685.87 | 1655.7525 | 1634.8975 | 1610.3475 | 1590.015 | 1571.455 | 1571.7075 | 1556.4475 | 1541.9575 | 1527.705 | 1510.7675 | 1495.36 | 1475.865 | 1458.505 | 1435.2975 | 1420.205 | 1397.145 | 1379.4725 | 1352.4295 | 1329.142 | 1304.2495 | 1270.4845 | 1249.507 | 1231.7945 | 1207.332 | 1184.4345 | 1166.457 | 1142.0145 | 1125.972 | 1110.972 | 1088.4545 | 1076.867 | 1075.647 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cost |  | Total Cost As Per B Plan
Construction Cost Paid | Rs. Cr | 1492 | 338.7 | 352.17 | 363.23 | 380.59 | 384.39 | 398.17 | 412.94 | 424.53 | 437.11 | 446.736 | 456.97 | 468.22 | 480.03 | 492.07 | 504.03 | 515.78 | 528.02 | 537.69 | 547.08 | 559.34 | 572.47 | 584.56 | 597.98 | 610.15 | 621.11 | 635.72 | 651.23 | 667.21 | 682.31 | 696.21 | 707.4 | 717.1 | 727.43 | 734.41 | 747.25 | 755.18 | 765.5 | 775.18 | 789.8 | 806.11 | 806.66 | 811.05 | 820.29 | 836.01 | 849.7 | 864.44 | 883.51 | 895.86 | 910.84 | 922.43 | 934.95 | 950.42 | 962.4 | 968.94 | 972.41 | 978.72 | 984.88 | 993.12 | 1000.13 | 1004.3 | 1010.7 | 1014.02 | 1019.74 | 1026.92 | 1032.99 | 1038.49 | 1042.79 | 1047.74 | 1050.24 | 1053.29 | 1057.29 | 1061.79 | 1066.29 | 1071.29 | 1074.29
Land Cost (Including Interest) | Rs. Cr | 958.48 | 265.16 | 265.16 | 265.16 | 265.16 | 269.16 | 269.16 | 314.21 | 314.21 | 314.21 | 314.21 | 314.21 | 324.21 | 365.27 | 365.27 | 365.27 | 365.27 | 366.27 | 373.77 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 444.25 | 464.39 | 466.89 | 468.89
Land Cost (Other Exp.) | Rs. Cr | 175 | 2016-12-31: 160; 2022-12-01: 160; 2023-01-01: 160; 2023-02-01: 160
Marketing & Selling overheads | Rs. Cr | 190.51 | 75.52 | 76.77 | 77.56 | 78.97 | 78.99 | 79.2 | 80.55 | 80.99 | 81.54 | 82.8 | 83.51 | 84.6 | 85.85 | 86.81 | 86.91 | 89.2 | 89.39 | 89.95 | 92.38 | 93.85 | 95 | 96.26 | 98.4 | 100.94 | 103.36 | 105.16 | 107.95 | 112 | 114.85 | 116.67 | 120.42 | 122.26 | 123.16 | 123.95 | 124.73 | 125.51 | 127.02 | 129.09 | 129.77 | 131.07 | 131.15 | 131.25 | 131.83 | 133.11 | 133.21 | 133.68 | 133.84 | 134.24 | 134.65 | 134.906 | 135.92 | 137.12 | 137.78 | 137.83 | 137.97 | 138.17 | 138.62 | 139.17 | 139.43 | 139.81 | 140.61 | 140.81 | 140.81 | 141.25 | 141.35 | 141.85 | 142.19 | 142.67 | 143.67 | 144.67 | 145.92 | 146.17 | 146.42 | 146.77 | 147.12
Admin Cost including taxes | Rs. Cr | 78.28 | 23.22 | 23.85 | 24.45 | 25.02 | 25.62 | 26.31 | 26.87 | 27.39 | 27.72 | 28.2 | 28.86 | 29.73 | 30.6 | 31.27 | 31.75 | 32.25 | 32.93 | 33.43 | 33.43 | 33.43 | 34.96 | 37.19 | 37.84 | 38.44 | 39.48 | 40.38 | 41.34 | 41.34 | 42.54 | 43.2 | 44.31 | 45.54 | 46.97 | 49.57 | 50.42 | 52.33 | 54.83 | 56.94 | 58.3 | 59.68 | 60.08 | 60.28 | 60.88 | 62.41 | 63.03 | 63.91 | 64.22 | 65.67 | 67.48 | 68.42 | 69.42 | 70.95 | 71.71 | 72.15 | 73.12 | 73.64 | 74.55 | 75.8 | 76.91 | 77.94 | 78.59 | 79.59 | 80.23 | 80.4 | 81.25 | 82.5 | 84.75 | 86 | 86.75 | 88.25 | 90.5 | 91.25 | 92 | 92.75 | 93.5
Financing Cost (Interest on Loan) | Rs. Cr | 513 | 79.89 | 79.89 | 79.89 | 91.12 | 91.12 | 91.12 | 102.52 | 102.54 | 102.54 | 115.88 | 115.88 | 115.88 | 128.39 | 128.39 | 128.39 | 141.71 | 141.71 | 141.71 | 157.04 | 157.04 | 157.04 | 173.74 | 173.74 | 173.74 | 190.48 | 190.48 | 190.48 | 190.48 | 208.49 | 208.49 | 227.87 | 227.87 | 227.87 | 242.38 | 248.46 | 248.46 | 268.46 | 268.46 | 268.46 | 268.46 | 279.64 | 279.64 | 279.64 | 285.68 | 285.68 | 298.3 | 298.32 | 307.76 | 310 | 312.88 | 313.64 | 334.04 | 338.78 | 347.18 | 355.58 | 364.16 | 372.74 | 372.74 | 372.74 | 381.48 | 390.22 | 400.82 | 411.42 | 422.02 | 432.28 | 442.54 | 452.8 | 463.06 | 473.32 | 483.58 | 493.84 | 504.1 | 514.36 | 524.62 | 534.88
Total Cost | Rs. Cr | 3407.27 | 942.49 | 797.84 | 810.29 | 840.86 | 849.28 | 863.96 | 937.09 | 949.66 | 963.12 | 987.826 | 999.43 | 1022.64 | 1090.14 | 1103.81 | 1116.35 | 1144.21 | 1158.32 | 1176.55 | 1274.18 | 1287.91 | 1303.72 | 1336 | 1352.21 | 1367.52 | 1398.68 | 1415.99 | 1435.25 | 1455.28 | 1492.44 | 1508.82 | 1544.25 | 1557.02 | 1569.68 | 1594.56 | 1615.11 | 1625.73 | 1660.06 | 1673.92 | 1690.58 | 1709.57 | 1721.78 | 1726.47 | 1736.89 | 1761.46 | 1775.87 | 1804.58 | 1824.14 | 1847.78 | 1867.22 | 1882.886 | 1898.18 | 1936.78 | 1954.92 | 1970.35 | 1983.33 | 1998.94 | 2015.04 | 2025.08 | 2033.46 | 2047.78 | 2064.37 | 2079.49 | 2096.45 | 2114.84 | 2132.12 | 2149.63 | 2166.78 | 2183.72 | 2198.23 | 2214.04 | 2231.8 | 2247.56 | 2443.46 | 2462.32 | 2478.68

## Customer MIS
Customer MIS
[18 empty] | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
Flat No. | Tower | CUSTOMER | Date of Booking | AREA | TYPE | CARPET AREA | Sold or Unsold | Payment Plan | Home Loan Taken ( Yes/ NO) | Name of lender | BASIC COST | COST OF CAR PARK | EXTRA CHARGES | Total Sales Consideration | IFMS | TOTAL TAX | Total Sale Value | Total Received till Nov 30, 2016 | Demand Raised in Dec 2016 | Collection in Dec 2016 | Demand Raised in Jan 2017 | Collection in jan 2017 | Demand Raised in Feb 2017 | Collection in Feb 2017 | Demand Raised in Mar 2017 | Collection in Mar 2017 | Demand Raised in Apr 2017 | Collection in Apr 2017 | Demand Raised in May 2017 | Collection in May 2017 | Demand Raised in June 2017 | Collection in June 2017 | Demand Raised in July 2017 | Collection in July 2017 | Demand Raised in Aug 2017 | Collection in Aug 2017 | Demand Raised in Sep 2017 | Collection in Sep 2017 | Demand Raised in Oct 2017 | Collection in Oct 2017 | Collection in Nov 2017 | Collection in Dec 2017 | Collection in Jan-18 | Collection in Feb-18 | Collection in MAR-18 | Collection in April-18 | Collection in May-18 | Collection in June-18 | Demand Raised in July 2018 | Collection in July-18 | Demand Raised in Aug 2018 | Collection in Aug-18 | Demand Raised in Sept 2018 | Collection in Sept-18 | Demand Raised in Oct 2018 | Collection in Oct-18 | Demand Raised in Nov 2018 | Collection in Nov-18 | Demand Raised in Dec 2018 | Collection in Dec-18 | Demand Raised in Jan-19 | Collection in Jan-19 | Demand Raised in Feb-19 | Collection in Feb-19 | Demand Raised in Mar-19 | Collection in Mar-19 | Demand Raised in April-19 | Collection in April-19 | Demand Raised in May-19 | Collection in May-19 | Demand Raised in June-19 | Collection in June-19 | Demand Raised in July-19 | Collection in July-19 | Demand Raised in Aug-19 | Collection in Aug-19 | Demand Raised in Sep-19 | Collection in Sep-19 | Demand Raised in Oct-19 | Collection in Oct-19 | Demand Raised in Nov-19 | Collection in Nov-19 | Demand Raised in Dec-19 | Collection in Dec-19 | Demand Raised in Jan-2020 | Collection in Jan-2020 | Demand Raised in Feb-2020 | Collection in Feb-2020 | Collection in Mar-2020 | Collection in Apr-2020 | Demand Raised in May-2020 | Collection in May-2020 | Demand Raised in June-2020 | Collection in June-2020 | Demand Raised in July-2020 | Collection in July-2020 | Demand Raised in Aug-2020 | Collection in Aug-2020 | Demand Raised in Sep-2020 | Collection in Sep-2020 | Demand Raised in Oct-2020 | Collection in Oct-2020 | Demand Raised in Nov-2020 | Collection in Nov-2020 | Demand Raised in Dec-2020 | Collection in Dec-2020 | Demand Raised in Jan-2021 | Collection in Jan-2021 | Demand Raised in Feb-2021 | Collection in Feb-2021 | Demand Raised in Mar-2021 | Collection in Mar-2021 | Demand Raised in Apr-2021 | Collection in Apr-2021 | Demand Raised in May-2021 | Collection in May-2021 | Demand Raised in June-2021 | Collection in June-2021 | Demand Raised in July-2021 | Collection in July-2021 | Demand Raised in August-2021 | Collection in August-2021 | Demand Raised in September-2021 | Collection in September-2021 | Demand Raised in October-2021 | Collection in October-2021 | Demand Raised in November-2021 | Collection in November-2021 | Demand Raised in December-2021 | Collection in December-2021 | Demand Raised in January-2022 | Collection in January-2022 | Demand Raised in February-2022 | Collection in February-2022 | Demand Raised in March-2022 | Collection in March-2022 | Demand Raised in April-2022 | Collection in April-2022 | Demand Raised in May-2022 | Collection in May-2022 | Demand Raised in June -2022 | Collection in June -2022 | Demand Raised in JULY -2022 | Collection in JULY -2022 | Demand Raised in AUGUST -2022 | Collection in AUGUST -2022 | Demand Raised in SEPTEMBER -2022 | Collection in SEPTEMBER -2022 | Demand Raised in OCTOBER -2022 | Collection in OCTOBER -2022 | Demand Raised in NOVEMBER -2022 | Collection in NOVEMBER-2022 | Demand Raised in December -2022 | Collection in December-2022 | Demand Raised in January -2023 | Collection in January-2023 | Demand Raised in February -2023 | Collection in February-2023 | Receivables | FLAT HANDOVER UPTO 15.03.2023
C16-907 | C16 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-1903 | C10 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2108 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-107 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2007 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2403 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2608 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2502 | C2 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-106 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-2606 | C3 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-8 | C4 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2303 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2304 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2507 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2306 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-403 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-803 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2606 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2304 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2702 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2104 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-1004 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-1907 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2808 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-1701 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2605 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2403 | C10 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-1506 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2501 | C10 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2503 | C10 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2602 | C10 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2603 | C10 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2604 | C10 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1401 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1402 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1406 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1507 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2503 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2404 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1601 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1607 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1706 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2006 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2106 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2107 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2407 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2506 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2507 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2508 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2601 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2602 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2605 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2606 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2607 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2608 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-607 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-807 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1002 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1005 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-107 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1105 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1107 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1205 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1207 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1208 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1405 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1407 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1408 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1503 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1507 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1605 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1607 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1802 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1803 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1805 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1602 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-903 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2504 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2704 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-605 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-606 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2406 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1707 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1508 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2308 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-102 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-202 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-401 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-708 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-502 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1807 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1902 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1903 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1907 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2005 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2007 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-207 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2102 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2103 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2107 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2203 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2205 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2302 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2303 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2305 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2402 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2403 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2502 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2503 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2505 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2507 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2508 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2602 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2603 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2604 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2605 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2607 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2608 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2702 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2703 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2705 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2707 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2708 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2801 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2802 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2803 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2804 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2805 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2807 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2808 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-3 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-302 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-407 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-602 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-607 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-703 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2705 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-706 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2706 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-1803 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-707 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2802 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-803 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2803 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2804 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-805 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2805 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2806 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-807 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2807 | C1 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-905 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-907 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-1604 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-1904 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2004 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2504 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2601 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2701 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-1104 | C3 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-506 | C3 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2703 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2704 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-1001 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2501 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-1804 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2404 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2001 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2301 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2803 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2804 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2901 | C14 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-2904 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-1503 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2003 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2103 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2203 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2502 | C15 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2503 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2601 | C15 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2602 | C15 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2603 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C15-2604 | C15 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2407 | C16 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2503 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-806 | C16 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-1201 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-1204 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-608 | C16 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-903 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2302 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2604 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-1406 | C16 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2601 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2602 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2603 | C16 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C16-2605 | C16 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2306 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2601 | C2 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2602 | C2 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2603 | C2 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2606 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2607 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2608 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-1005 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-1105 | C2 |  |  | 1380 |  |  | unsold | [147 empty] | 0 | 0 | 0
C2-2103 | C2 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-1204 | C3 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-2607 | C3 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1002 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-101 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-103 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1502 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1601 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2701 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2801 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2002 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1602 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-501 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2807 | C4 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1603 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1803 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1901 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-601 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-801 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1104 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2804 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2004 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2001 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-203 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2103 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2203 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2301 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-2604 | C3 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-2605 | C3 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-1904 | C3 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-2603 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-3 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-802 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1601 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-104 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1104 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-106 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1701 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1202 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1402 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1403 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1404 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1503 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1602 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1603 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1604 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1702 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1802 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2502 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-803 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2003 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1904 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1101 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1804 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1902 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1903 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C3-1502 | C3 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2004 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-202 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-204 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2102 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2104 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2402 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2602 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2606 | C5 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2607 | C5 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-302 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-303 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-402 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-403 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-404 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-503 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-504 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-602 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-603 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-604 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-101 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-103 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-104 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1102 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1103 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1502 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1503 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1504 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1601 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1602 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1603 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1604 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1701 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1703 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1704 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1801 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1802 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1803 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2302 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-106 | C6 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1804 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1901 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1902 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1903 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1904 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2001 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2002 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2003 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2004 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-201 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-202 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2101 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2102 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2103 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2201 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2203 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2204 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2301 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2303 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2402 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2403 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2503 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2504 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2603 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2604 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1105 | C6 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2703 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2802 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2803 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2806 | C6 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-301 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-302 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-304 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-401 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-402 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-501 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-502 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1102 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-504 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-601 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-602 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-603 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-604 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-902 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-101 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-102 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-103 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1401 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1402 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1403 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1601 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1602 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1603 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1701 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1702 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1801 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1802 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1803 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1901 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1902 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1903 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2001 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2002 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2003 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-201 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-202 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-203 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2004 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2505 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2101 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2102 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2201 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2207 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2301 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2302 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-4 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-902 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-1001 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2304 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2401 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2402 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2403 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2406 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2407 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2501 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2502 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2503 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2601 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2602 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2603 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2605 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2606 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2607 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-2608 | C7 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-3 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-301 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-302 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-401 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-402 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-403 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-501 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-502 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-503 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-601 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-603 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1006 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1007 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-107 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1106 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1107 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1203 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1402 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1403 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1406 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1407 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1506 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1602 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1207 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2207 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2103 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1202 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1502 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2105 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2106 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1606 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1607 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1702 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1707 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1802 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1803 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1902 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1906 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1907 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2002 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2003 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2007 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-203 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-207 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2107 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2206 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2302 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1103 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2203 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2303 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-406 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1706 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2307 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2406 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2407 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2502 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2503 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2504 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2506 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2507 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-2508 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-302 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-303 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-307 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-407 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-502 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-506 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-507 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-606 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-607 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-702 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-706 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-707 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-802 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-2003 | C10 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C10-101 | C10 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-806 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-807 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-906 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-907 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-1604 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2103 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-1804 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-1904 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2004 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2304 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2404 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2504 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2604 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2704 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2801 | C9 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2804 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2901 | C9 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2902 | C9 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C9-2904 | C9 |  |  | 1795 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-103 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1401 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C4-1402 | C4 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-904 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-503 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C7-803 | C7 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-603 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-303 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-107 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-306 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-1003 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-206 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-404 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2501 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-403 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-503 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1006 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1901 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-1003 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1707 | C11 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-3 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-1608 | C5 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1001 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-1002 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C1-2103 | C1 |  |  | 1155 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-102 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-601 | C12 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C11-2604 | C11 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C14-4 | C14 |  |  | 1585 |  |  | unsold | [147 empty] | 0 | 0 | 0
C5-2202 | C5 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C8-1003 | C8 |  |  | 970 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-2407 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-2 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-3 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-4 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C6-303 | C6 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-5 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-205 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-405 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0
C12-505 | C12 |  |  | 770 |  |  | unsold | [147 empty] | 0 | 0 | 0

## Construction Update (hidden)
Construction Update
| C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | C14 | C15 | C16 | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9
Total Area | 23490 | 16815 | 7730 | 25040 | 31970 | 49880 | 52050 | 68870 | 26295 | 15525 | 20340 | 76330 | 34965 | 16480 | 19830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485610
Sold Area | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Start Date
Target End Date
Total Sold area | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sold Receivables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2016-11-01 | C1: Discription Of Status : Any Major Issues:
2016-12-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-01-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-02-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-03-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-04-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-05-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-06-01 | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached | Attached
2017-07-01 | P1: Attached; P2: Attached; P3: Attached; P4: Attached; P5: Attached; P6: Attached; P7: Attached; P8: Attached; P9: Attached
2017-08-01 | P1: Attached; P2: Attached; P3: Attached; P4: Attached; P5: Attached; P6: Attached; P7: Attached; P8: Attached; P9: Attached
2017-09-01 | P1: Attached; P2: Attached; P3: Attached; P4: Attached; P5: Attached; P6: Attached; P7: Attached; P8: Attached; P9: Attached
22400
831600
268423
831138
889547
1067053
917952
826166
89094
602089
1050089
437984
520674
772871
536198
844635
776231
833276
814728
510973
728504
501271
825216
693840
529200
690371
529200
693840
529200
607936
498120
652680
498120
630000
490560
493024
491646
689696
678497
501424
487193
675428
501424
493024
487193
725536
501424
487193
501424
501816
487193
372862
494789
487845
541932
666904
679112
493277
493669
487845
493277
487845
653016
690088
493277
705544
493277
702296
471222
471222
479696
590728
685060
485128
485128
479696
655312
485128
423914
479696
636560
694624
476981
467419
654920
463237
463237
471549
591192
468581
471549
654920
463400
469224
463400
579600
468832
463400
479976
470344
455253
614376
463400
463400
463400
624400
463400
463400
463400
636608
468832
463400
457968
457968
452536
457968
464704
457968
407568
732018
82823
824040
521640
626640
401464
718200
848904
700224
968856
776538
622104
790720
613200
613200
840757
906696
472584
450240
626640
622104
688800
968856
968856
611561
611561
980448
656544
621600
699720
700224
506101
462000
707784
1139125
462000
672000
632311
632311
158491
251720
1313760
1129045
1174573
246400
733824
733320
733320
733320
1152704
730564
723004
496104
991200
2133264
902917
534744
666960
668304
516264
668304
737520
1313760
1251600
1007698
1008000
785400
988512
927696
729960
668304
1010016
951216
1313845
5331496
2133264
532156
532156
785317
785317
534744
902917
1010016
714000
1255045
2009245
951216
726264
1009290
1894816
2845696
301392
1043616
1043616
305835
294253

## Construction Status (hidden)
PRATEEK REALTORS INDIA PVT. LTD.
PRATEEK GRAND CITY
CONSTRUCTION PROGRAMME FOR THE MONTH OF FEBRUARY - 2020
SR. NO. | TOWER | CURRENT STATUS | TARGET (1-15) | TARGET (16-30)
1 | C1 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
2 | C2 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
3 | C3 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
4 | C4 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
5 | C5 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
6 | C6 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
7 | C7 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
8 | C8 | TERRACE FLOOR | PARAPET/MUMTY MACHINE ROOM
9 | C9 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
10 | C10 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
11 | C11 | 10TH FLOOR ROOF SLAB | 11TH FLOOR ROOF SLAB | 12TH FLOOR ROOF SLAB
12 | C12 | MUMTY MACHINE ROOM CASTING | TOP ELEVATION WORK
13 | C14 | 27th FLOOR ROOF SLAB | TERRACE FLOOR ROOF SLAB / PARAPET / MUMTY MACHINE ROOM
14 | C15 | TERRACE FLOOR | PARAPET / MUMTY MACHINE ROOM
15 | C16 | MUMTY MACHINE ROOM CASTING | TOP ELEVATION WORK
16 | P1 | 15TH FLOOR ROOF SLAB | 16TH FLOOR ROOF SLAB | 17TH FLOOR ROOF SLAB
17 | P2 | 17TH FLOOR ROOF SLAB | 18TH FLOOR ROOF SLAB | 19TH FLOOR ROOF SLAB
18 | P3 | 12TH FLOOR ROOF SLAB | 13TH FLOOR ROOF SLAB | 14TH FLOOR ROOF SLAB
19 | P4 | 19TH FLOOR ROOF SLAB | 20TH FLOOR ROOF SLAB | 21ST FLOOR ROOF SLAB
20 | P5 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
21 | P6 | TOP FLOOR ROOF SLAB | TOP ELEVATION WORK
22 | P7 | TERRACE FLOOR ROOF SLAB | CASTING OF OVER HEAD WATER TANK
23 | P8 | 17TH FLOOR ROOF SLAB | 18TH FLOOR ROOF SLAB | 19TH FLOOR ROOF SLAB
24 | P9 | 16TH FLOOR ROOF SLAB | 17TH FLOOR ROOF SLAB | 18TH FLOOR ROOF SLAB
25 | EWS/LIG/NTA | TOWER RAFT CASTING | NON TOWER ZONE - I , II & III + COMMERCIAL. + STP + WTP

## Payment Details (hidden)
Payment Details
S No. | Nature of payment | Due date | Gross Amount | Amount due (Net Of TDS) | Amount paid | Date paid | Remarks
1 | Processing Fee | 2016-12-06 | 42500000 | 44625000 | 44625000 | 2016-12-07 | On time
2 | Interest | 2016-12-31 | 34420492 | 30978443 | 30978443 | 2016-12-29 | On time
3 | Interest | 2017-03-31 | 112364384 | 101127945 | 101127945 | 2017-03-31 | On time
4 | Interest | 2017-06-30 | 114015617 | 102614055 | 102614055 | 2017-06-30 | On time
5 | Interest | 2017-09-30 | 133387397 | 120048658 | 120048658 | 2017-09-28 | On time
6 | Interest | 2017-12-31 | 125013699 | 112512329 | 112512329 | 2017-12-29 | On time
7 | Interest | 2018-03-31 | 133150685 | 119835616 | 119835616 | 2018-03-28 | On time
8 | Interest | 2018-06-30 | 139501230 | 125634327 | 125634327 | 2018-06-29 | On time
9 | Interest | 2018-09-30 | 167017809 | 150316028 | 150316028 | 2018-09-28 | On time
10 | Interest | 2018-12-31 | 167490411 | 150741370 | 150741370 | 2018-12-31 | On time
11 | Interest | 2019-02-27 | 111300000 | 111300000 | 111300000 | 2019-02-27 | Before Time
12 | Interest | 2019-04-05 | 180024288 | 162021859.2 | 162021859 | 2019-03-26 | Before Time
13 | Interest | 2019-07-05 | 193810963 | 174429866 | 174429866 | 2019-06-29 | Before Time
| Total |  | 1280161724 | 1169733771 | 1169733771
FD Details
S No. | FD No. | Amount | Purpose (ISRA / Interest) | Start Date | Tenor | End Date | Maturity Amount | Status ( Active / Closed)
1 | 50300149302812 | 96335342 | ISRA | 2016-12-02 | 5 Years |  |  | Active
2 | 50300149303087 | 18526027 | ISRA | 2016-12-27 | 5 Years |  |  | Active
3 | 50300180854290 | 16900000 | INTEREST | 2017-01-19 |  | 2017-03-30 | 17029389 | Closed
4 | 50300184540450 | 9100000 | INTEREST | 2017-02-14 |  | 2017-03-30 | 9153066 | Closed
5 | 50300194439781 | 21300000 | INTEREST | 2017-04-25 | 59 Days | 2017-06-23 | 21454936 | Closed
6 | 50300194582671 | 9800000 | INTEREST | 2017-04-26 | 63 Days | 2017-06-28 | 9897262 | Closed
7 | 50300196862016 | 11200000 | INTEREST | 2017-05-09 | 45 Days | 2017-06-23 | 11258685 | Closed
8 | 50300197118478 | 5500000 | INTEREST | 2017-05-11 | 48 Days | 2017-06-28 | 5541589 | Closed
9 | 50300199524202 | 10000000 | INTEREST | 2017-05-30 | 29 Days | 2017-06-28 | 10033767 | Closed
10 | 50300200189328 | 20000000 | INTEREST | 2017-06-02 | 24 Days | 2017-06-26 | 20055890 | Closed
11 | 50300203763827 | 18526027 | ISRA | 2017-06-29 | 5 Years |  |  | Active
12 | 50300213075129 | 25000000 | INTEREST | 2017-08-31 | 28 Days | 2017-09-28 | 25081507 | Closed
13 | 50300221155663 | 30000000 | INTEREST | 2017-10-30 | 58 Days | 2017-12-27 | 30286027 | Closed
14 | 50300223979705 | 27000000 | INTEREST | 2017-11-17 | 41 Days | 2017-12-27 |  | Closed
15 | 50300229031880 | 2722192 | ISRA | 2017-12-26 | 2 Years | 2019-12-26 |  | Active
16 | 50300233308497 | 30000000 | INTEREST | 2018-01-22 | 67 Days | 2018-03-29 |  | Closed
17 | 50300238328357 | 25000000 | INTEREST | 2018-02-26 | 3 Days | 2018-03-29 |  | Closed
19 | 50300247804271 | 30000000 | INTEREST | 2018-04-24 | 64 days | 2018-06-26 | 30298109 | Closed
20 | 50300250024112 | 10000000 | INTEREST | 2018-05-03 | 54 days | 2018-06-26 | 20095547 | Closed
21 | 50300254696218 | 20000000 | INTEREST | 2018-05-28 | 31 days | 2018-06-28 | 10089753 | Closed
22 | 50300260815966 | 8599315 | ISRA | 2018-06-28 | 3 Years | 2021-06-28 |  | Closed
23 | 50300266236609 | 25000000 | INTEREST | 2018-07-24 | 64 days | 2018-09-26 |  | Closed
24 | 50300269265631 | 10000000 | INTEREST | 2018-08-06 | 51 days | 2018-09-26 |  | Closed
25 | 50300273803763 | 25000000 | INTEREST | 2018-08-28 | 30 days | 2018-09-26 |  | Closed
26 | 50300286448072 | 30000000 | INTEREST | 2018-10-22 | 67 Days | 2018-12-28 |  | Closed
27 | 50300288526971 | 20000000 | INTEREST | 2018-11-01 | 58 days | 2018-12-28 |  | Closed
28 | 50300306726276 | 30000000 | INTEREST | 2019-01-18 | 68 Days | 2019-03-27 |  | Closed
29 | 50300308675373 | 20000000 | INTEREST | 2019-01-28 | 58 Days | 2019-03-27 |  | Closed
|  | 605508903 |  |  |  |  | 220275527
| Disbursement | Amount | Date
| Tranche 1 | 2600000000 | 2016-11-30
| Tranche 2 | 500000000 | 2016-12-27
| Tranche 3 | 500000000 | 2017-06-29
| Tranche 4 | 200000000 | 2017-12-04
| Tranche 5 | 200000000 | 2017-12-26
| Tranche 6 | 10000000 | 2018-03-28
| Tranche 7 | 90000000 | 2018-04-13
| Tranche 8 | 50000000 | 2018-05-04
| Tranche 9 | 750000000 | 2018-06-28
| Tranche 10 | 50000000 | 2019-01-11
| Tranche 11 | 50000000 | 2019-02-05
| Tranche 12 | 50000000 | 2019-03-12
| Tranche 13 | 50000000 | 2019-04-15
| Tranche 14 | 50000000 | 2019-06-18
| Tranche 15 | 120000000 | 2019-06-28
Tranche 16
Tranche 17
Tranche 18
Tranche 19
| Total | 5270000000
| Prepayment | Amount | Date
Tranche 1
Tranche 2
Tranche 3
Tranche 4
Tranche 5
Tranche 6
Tranche 7
Tranche 8
Tranche 9
Tranche 10
Tranche 11
Tranche 12
Tranche 13
Tranche 14
Tranche 15
Tranche 16
Tranche 17
Tranche 18
Tranche 19
| Total | 0

## Approvals Status (hidden)
Approval Status
S No. | Name of Approval | Receiving Date | Valid Till | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## NOC (hidden)
Sales NOC
S No. | Customer Name | Date Of Booking | Unit No. | Tower No. | Area | Total Sales Consideration (Exculting IFMS and Service Tax) | Price (Per Sqft) | MSP per sqft | Shortfall (If any) | NOC Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
[5 empty] | 0 | 0 |  |  | 0