## Sheet1 (2)
CONSTRUCTION PROGRESS REPORT OF BASTI CARE HOSPITAL & EYE CENTRE ¦ BASTI, UTTAR PRADESH
300%
S. No. | Different Parameters |  | % progress in Basement | % progress in Ground Floor | % progress in First Floor | Overall Progress
1 | Cutting, Filling and Levelling | 5% | 100% | 100% | 100% | 5%
2 | Footings | 10% | 100% | 100% | 100% | 10%
3 | Slab Casting | 30% | 100% | 100% | 100% | 30%
4 | Brickwork | 15% | 100% | 100% | 100% | 15%
5 | Plaster | 10% | 75% | 100% | 50% | 7.5%
6 | Flooring | 10% | 80% | 100% | 50% | 7.667%
7 | MEP Services | 5% | 100% | 100% | 0% | 3.333%
8 | Door/ Window | 5% | 100% | 100% | 0% | 3.333%
9 | Finishing | 10% | 90% | 100% | 0% | 6.333%
| Completion status (in %) | 100% |  |  |  | 88.17%
100%
i | Basic structure construction cost | 850 | 56.89% | only for reference purpose.
ii | Project sanctioning/ approval, Architectural, structural stability Fees, etc. | 50 | 3.347%
iii | Finishing Work (Flooring, white washing, fittings & fixtures, etc.) | 300 | 20.08%
iv | MEP Works (Mechanical, Electrical & Plumbing) | 200 | 13.39%
vi | Other expenses (Firefighting, intercom & etc.) @ 1.5% of total cost (i+ii+iii+iv+v) | 24 | 1.606%
viii | Marketing & Selling charges @ 3% of Rs.2,800/- & Rs.7,500/- | 70 | 4.685%
Total |  | 1494

## Sheet2
shed
Cutting, Filling and Levelling | 5%
Footings | 10%
Slab Casting/Shed Work | 50%
Brickwork | 5%
Plaster | 3%
Flooring | 12%
MEP Services | 10%
Door/ Window | 5%
100%

## invoices total
Invoice Details
S.no | Date | Supplier | Amount in INR
1 | 2022-09-08 | Nilam Engg | 1287746
2 | 2022-08-30 | Konart Steel | 2180000
3 | 2022-09-08 | Anupan Steel | 18880
4 | 2022-09-01 | Nilam Engg | 1328018
5 | 2022-10-08 | Konart Steel | 3269550
6 | 2022-10-03 | Konart Steel | 5450000
7 | 2022-10-08 | Nilam Engg | 245330
8 | 2022-10-17 | Nilam Engg | 1212964
9 | 2022-11-14 | Mohan Engg | 100000
10 | 2022-08-03 | Mohan Engg | 415360
11 | 2022-12-08 | Konart Steel | 3270000
12 | 2022-11-29 | Nilam Engg | 184219
13 | 2022-11-29 | Konart Steel | 6806523
14 | 2023-01-06 | Anupam Sale Service | 18880
15 | 2023-01-27 | Nilam Engg | 361483
16 | 2023-02-06 | Konart Steel | 1054379
17 | 2023-02-06 | Konart Steel | 348000
18 | 2023-02-06 | Konart Steel | 2098684
19 | 2023-02-10 | Nilam Engg | 239341
20 | 2023-02-20 | A.S Enterprises | 600000
21 | 2023-02-23 | Nilam Engg | 259341
22 | 2023-03-09 | Nilam Engg | 2497752
23 | 2023-02-22 | Nilam Engg | 6445830
|  | Total | 39692280 | #DIV/0!