## EPC Claims
Ranchi Expressways Limited
EPC Contractor claims on REL
S. No. | Description | Amount Provided by REL (In Rs.) | Remarks |  | Amount after Assessment (In Rs.)
1 | Compensation for delay in handing over of land as per clause 10.3.4 of the Agreement | 1908724965 | As per Article 4 of the concession agreement there are certain condition precedent required to be fulfilled by NHAI. The 100% land required to be handed over within 90 days of the Appointment date as per clause 10.3.4 of CA, which is not available even as on date. Hence, NHAI is in default as per the terms of the clause 4.1.2 condition precedent of the CA. Therefore EPC contractor's work got delayed and accordingly they have filed this claim. The value of this claim has been provided by REL. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. | 80% | 1526979972 | The Project suffered adversely due to delay in statutory clearance such as environmental, forest etc, delay in grant of mining permission for Stone Quarries, borrow areas for soil, entirely beyond the control of REL.
2 | Compensation for Idling of Manpower due to Non Availability of Land | 132944171.64 | As per CA this claim comes under Article 35 and therefore it has been considered accordingly. The value of this claim has been provided by REL. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. | 80% | 106355337.312 | NHAI did not declare the appointment date as the Forest/Wild Life/Environmental Clearances for the entire project highway were not available. Also in the reply to termination letter by REL, it is mentioned that Hon’ble High Court of Jharkhand order dated 07.01.2019, which was pointed out that even as on date the entire ROW is not available and also the Environmental/Wild Life Clearance are not available.
3 | Compensation for Idling of Machinery due to Non Availability of Land | 3297162186 | As per CA this claim comes under Article 35 and therefore it has been considered accordingly. The value of this claim has been provided by REL. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. | 80% | 2637729748.8 | As per Article 4 of the concession agreement there are certain condition precedent required to be fulfilled by NHAI. The minimum Right of way i.e. 80% of the total Right Of Way (ROW), which was acquired for construction of the highway as per Article 10.3.1 and 10.3.2 had not been acquired by the NHAI. Similarly, the 100% land required to be handed over within 90 days of the Appointment date as per clause 10.3.4 of CA, which is not available even as on date. Hence, NHAI is also in default as per the terms of the clause 4.1.2 condition precedent of the CA. Therefore NHAI can not claim benefit out of its own failure.
4 | Reimbursement of Additional cost of Maintenance works carried out | 980933659.4 | As per Article 5 of CA the concessionary was obliged to perform various obligations inter-alia pertaining to construction, maintenance, operation and development of the project highway. In the same way, EPC contractor coordinates all design, procurement and construction work and ensures that the whole project is completed as required and in time. But due to lack of funds and due to non availability of lands and Forest/Wild Life/Environmental Clearances for the entire project highway, concessionaire and EPC contractor failed to achieve the required progress in undertaking the construction of the project highway on time and additional cost of maintenance work arises. There is a lack of supporting documentary evidence or detailed calculations for this claim. To address the uncertainty surrounding the claim's value, there is a recognition that the reassessment process might reveal a lower value than the initially provided claim amount. This recognition of potential variability or discrepancy prompts the decision to apply a 25% discount to the claim amount. Here we have considered 25% discount in the claim amount due to non-compliance of article 5.1.1. | 75% | 735700244.55 | As per article 5 of CA the concessionary was obliged to complete the project with in the stipulated time and also obliged to perform various obligations inter-alia pertaining to construction, maintenance, operation and development of the project highway.
5 | Termination payments as per clause 37 of the contract | 511415382 | As per CA this claim comes under Article 37. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 409132305.6 | Concessionaire outsource the wrok to EPC contractor. Hence most of the maintenance work was done by the the contractor. Therefore we have given a discount of 25% to this claim.
6 | Loss of overheads on the works which could not be commenced | 601429920 | As per CA this claim comes under article 35, which says that compensation shall not include loss of annuity or debt repayment obligations or other consequentional losses. Hence we have not considered this amount of claim. | 0% | 0
7 | Losses incurred due to Bank Guarantees | 767626085.44 | As per CA this claim comes under Article 9. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 762000868.352
a) | Return of Bank Guarantee | 739500000
b) | BG Commission charges | 28126085.44
8 | Loss of Business Oppurtunities due to Non Release of Bank Guarantee | 369750000 | As per CA this claim comes under article 35, which says that compensation shall not include loss of annuity or debt repayment obligations or other consequentional losses. Hence we have not considered this amount of claim. | 0% | 0
9 | Compensation due to Change in Law under " Force Majeure" clause -- of the Agreement | 67138990.68 | As per CA this claim comes under Article 34.4 and 41.1. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 53711192.544
10 | Expenditure for additional works to the EPC contract | 635401879 | The EPC contractor coordinates all design, procurement and construction work and ensures that the whole project is completed as required and in time. But due to prolongation of the Project and non availability of lands and Forest/Wild Life/Environmental Clearances for the entire project highway, EPC contractor failed to achieve the required progress in undertaking the construction of the project highway on time and additional cost of work arises. Here we have considered 25% discount in the claim amount due to various material breach and non-compliance of CA. | 75% | 476551409.25
11 | Presuite, Pendente Lite and Future interest
a) | Presuite Interest from date of preclosure to date of formation of AT | To be assessed later
b) | Pendente lite interest from formation of AT to Date of Award | To be assessed later
c) | Future interest | To be assessed later
12 | Cost of Arbitration Proceedings | 5000000 | Due to lack any documentary evidence to support the claim amount, and according to the Concession Agreement (CA), there is no available information or means to ascertain the validity of this claim. Therefore, we have chosen not to include or consider this amount. |  | 0
Total Claim Amount |  | 9277527239.16 |  |  | 6708161078.408

## REL Claims
Ranchi Expressways Limited
REL claims against NHAI
| S. No. | Description | Amount Provided by REL (In Rs.) | Remarks |  | Amount after Assessment (In Rs.)
| A | Payment of the Amount of Expenditure incurred for the execution of the Works
| 1 | Payment towards the value of work done. | 9195846176 | In the meeting held between REL, Lenders and NHAI dated 16.11.2022, as per the Independant Engineer assessment it is certified, that the value of work done by REL is 458.20 Crs. As per Article 35 for compensation for breach of agreement of CA all the construction / Direct costs involved while working on the project highway will be paid by NHAI to the contractor, therefore it has been considered accordingly. |  | 4582000000
| 2 | Payment of amount expended on the works of stone pitching. | 5398050 | As per CA this claim comes under Article 10.2 and 10.3. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 4318440
| 3 | Payment of amount expended on the works of Median Plantation and filling. | 38378771 |  | 80% | 30703016.8
| 4 | Payment of amount spent on Scarification/Dismantling of existing Pavement. | 9810171 |  | 80% | 7848136.8
| 5 | Refund of amount expended on the maintenance of the existing road. | 1196375602 | This claim comes under Article 17.1 of CA. During the construction period, concessionaire has to maintain the project highway by itself. The construction of the highway was scheduled to be completed within a period of 912 days (2 n 1/2 Years) and the concessionaire was expected to maintain the existing road for a period of not more than 1 year. However, even after a lapse of more than 5 years and 5 months the disjointed streach of 128.87 Km (78.87% ROW) only out of the total lenght of 163.5 Km could be made available by the NHAI, with the result that the concessionaire had to maintain the existing road for more than 5 years. Hence, due to shortage of funds, concessionaire was not able to maintain the project highway after 5 years. Here we have considered 20% discount in the claim amount due to non-compliance of article 17 and article 5.1.1 by the concessionaire. | 80% | 957100481.6
| 6 | Refund of amount expended on the work for construction of temporary diversion roads. | 117900000 | As per CA this claim comes under Article 10.3 Procurement of site. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 94320000
| 7 | Refund of amount expended on the work done towards removal of slush and dewatering. | 38983800 | As per CA this claim comes under Schedule K article 17. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 31187040
| 8 | Refund of amount expended on the works of Pond filling. | 170765350 |  | 80% | 136612280
| 9 | Refund of amount expended on Preparation and Implementation of the environmental plan. | 12017183 | As per CA this claim comes under Article 10.2. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 9613746.4
| 10 | Refund of amount expended on the works of Back Filling in the areas where Stumps were removed. | 254165738 | As per CA this claim comes under Schedule K article 17. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 203332590.4
| 11 | Refund of amount expended towards Design of works under Change of Scope viz EUPs and redesign of PUPs, VUPs ROBs, etc. | 53919517 | As per CA this claim comes under Article 16.1 Change of Scope. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 43135613.6
| 12 | Refund of amount expended on Tree Cutting (balance payments). | 135529815 | As per CA this claim comes under Article 11.4. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 108423852
| 13 | Refund of Retention Money withheld towards utility shifting. | 15113164 | As per CA this claim comes under article 11.1 of CA. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 12090531.2
| 14 | Refund of amount expended on the works of Dismantling of Structures and Removal & Relocation of Temples. | 25600000 | As per CA this claim comes under Schedule K article 17. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 20480000
| 15 | Refund of amount spent on Installation of Emergency Sign Boards (1033 nos.) on specific instructions of Authority. | 5465478 |  | 80% | 4372382.4
| 16 | Refund of amount expended towards payment of Independent Engineer’s fee. | 107356074 | In the meeting held between REL, Lenders and NHAI dated 16.11.2022, as per the Independant Engineer assessment it is certified, that the value of Independent Engineer’s fee is 14.20 Crs. |  | 142000000
| 17 | Refund of amount expended towards payment of Lender’s Independent Engineer’s fees. | 11306700 | In the meeting held between REL, Lenders and NHAI dated 16.11.2022, as per the Independant Engineer assessment it is certified, that the value of Lendere's Independent Engineer’s fee is 1.13 Crs. | 100% | 11306700
Finance charge is a fee charged for the use of credit or the extension of existing credit. | 18 | Refund of amount expended towards Financial Charges. | 78109135 | In the meeting held between REL, Lenders and NHAI dated 16.11.2022, as per the Independant Engineer assessment it is certified, that the value of financial expenses as Rs. 4.84 Crs. As per CA this claim comes under Article 38.6. |  | 48400000
These are expenses for the services availed from the bank. | 19 | Refund of amount expended on bank charges. | 93915854 | These are the expenses for the services availed from the bank by REL. As we don't have any bifurcation and proof rerarding the bank charges claimed by REL, Thereforewe cannot consider this amount. |  | -
| 20 | Refund of amount expended on Insurance Premium (CAR policy etc.) | 61671125 | As per CA this claim comes under article 32. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 49336900
Overhead expenses are what it costs to run the business, including rent, insurance, and utilities. | 21 | Refund of amount incurred on OH & Running expenditure. | 132443970 | As per CA this claim comes under Article 11 and 32. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 105955176
| 22 | Refund of BG amount encashed. | 739500000 | As per CA this claim comes under Article 9.1 of CA Performance security. And therefore it has been considered accordingly. | 100% | 739500000
|  | Sub Total (A) | 12499571673
| B | Concessionaire’s Losses
| 23 | Interest amount on non-refund of BG. | 687066411 | As per CA this claim comes under Article 9.1 of CA Performance security. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 549653128.8
| 24 | Refund of interest on BG Encashed amount. | 269037488 | As per CA this claim comes under Article 9. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 215229990.4
| 25 | Compensation payable due to delay in handing over of land. | 1775027678 | As per CA this claim comes under Article 35. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 1420022142.4
| 26 | Refund of the extra expenditure incurred due to Change in law (viz. Goods and Services Tax) | 67138991 | As per CA this claim comes under Article 41.1. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 53711192.8
| 27 | Extra expenditure due to escalation of cost of work. | 1728844393 | As per CA this claim comes under Article 35. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 1383075514.4
| 28 | Loss incurred on Idling of Machinery due to prolongation of project. | 4034651432 |  | 80% | 3227721145.6
| 29 | Loss of Overheads due to prolongation of the Project. | 1678286842 |  | 80% | 1342629473.6
| 30 | Loss of Return on Investment (Equity /Unsecured loan infused in the project) for the period since SCOD upto 30.01.2019. | 3195589333 | As per article 35, compensation shall not include loss of annuity or debt repayment obligations or other consequentional losses. Hence we have not considered this amount of claim. |  | -
| 31 | Loss of Return on Investment (Equity /Unsecured loan infused in the project) for the period since 31.01.2019 to End of the Concession Period. | 7723471525
| 32 | Claim on Loss of OH & Profit on balance value of work due to illegal termination. | 2355786000
| 33 | Claim for amount of Revenue loss (loss of Annuity) | 33300000000
| 34 | Loss of investment on plant and machinery equipment due to idling | 2640310000
| 35 | Refund of Amount Deducted as Interest During Construction (IDC). | 3785251346 | As per CA this claim comes under article 35.2. As we do not possess any documentary evidence or calculation for this claim, it is possible that upon reassessment by authority, its value may turn out to be lower than the initially provided amount. Therefore, we have applied a 20% discount to account for this uncertainty. And therefore it has been considered accordingly. | 80% | 3028201076.8
| 36 | Refund of interest amount incurred on unsecured loan infused in the project | 6906538954 |  | 80% | 5525231163.2
|  | Sub Total (B) | 36847000393 |  |  | 24087511715.2
| 37 | Pre-suit interest on all Claims. | To be ascertained after conclusion of proceedings.
| 38 | Pendent lite & future interest on all claims. | To be ascertained after conclusion of proceedings.
| 39 | Cost of Arbitration and litigation. | To be ascertained after conclusion of proceedings.
| Total Claim Amount |  | 49346572066

## NHAI Claims
Ranchi Expressways Limited
NHAI counter claims against REL
S. No. | Description | Amount Provided by REL (In Rs.) | Remarks |  | Amount after Assessment (In Rs.)
1 | Loss of toll revenue suffered by NHAI due to non complation of the Project in Schdule time | 9899618950 | As per CA article 10 clause no. 10.3.1 and 10.3.2, 80% ROW was not acquired by NHAI on the appointed date. 80% ROW is not available even as on date. As per Article 4 of the concession agreement there are certain condition precedent about ROW are required to be fulfilled by NHAI. Hence, NHAI is in default as per the terms of the clause 4.1.2 condition precedent of the CA. Hence we have not considered this claim. | 0% | 0
2 | Liquidated damages for non achivement of project Mile stone upto 29.01.2019 | 3013500000 | As per Schedule (G) Project completion Schedule of the concession agreement, concessionaire had to achieve Milestone-II on the date falling on the 365th day from the appointment date. For the achievement of Milestone II, the work on all the structures has to commence, which is not possible as on date, as in some cases/structures either the land over which the structure is to come up is not available or the drawing for these structures have not been finalized/approved by the NHAI. Hence Milestone II could not have been achieved. Therefore, we have considered 50% discount on this claim due non compliance of CA. | 50% | 1506750000
3 | Non payment of Independent Engineer fee | 47593724.0313 | As per CA this claim comes under Article 23.3. There is a lack of supporting documentary evidence or detailed calculations for this claim. To address the uncertainty surrounding the claim's value, there is a recognition that the reassessment process might reveal a lower value than the initially provided claim amount. This recognition of potential variability or discrepancy prompts the decision to apply a 20% discount to the claim amount. | 80% | 38074979.2251
4 | Non maintainance of Highway | 201005014 | As per CA this claim comes under Article 17.9.1. There is a lack of supporting documentary evidence or detailed calculations for this claim. To address the uncertainty surrounding the claim's value, there is a recognition that the reassessment process might reveal a lower value than the initially provided claim amount. This recognition of potential variability or discrepancy prompts the decision to apply a 20% discount to the claim amount. | 80% | 160804011.2
5 | Excess payment on account of tree cutting | 93772233 | As per CA this claim comes under Article 11.4. There is a lack of supporting documentary evidence or detailed calculations for this claim. To address the uncertainty surrounding the claim's value, there is a recognition that the reassessment process might reveal a lower value than the initially provided claim amount. This recognition of potential variability or discrepancy prompts the decision to apply a 20% discount to the claim amount. | 80% | 75017786.4
6 | Value of work having non confirmation report | 34400000 | As per CA this claim comes under Article 13.1 for monthly progress report. There is a lack of supporting documentary evidence or detailed calculations for this claim. To address the uncertainty surrounding the claim's value, there is a recognition that the reassessment process might reveal a lower value than the initially provided claim amount. This recognition of potential variability or discrepancy prompts the decision to apply a 20% discount to the claim amount. | 80% | 27520000
7 | Account of due for shifting and laying of pipeline | 40821517 | As per CA this claim comes under Article 11.1. There is a lack of supporting documentary evidence or detailed calculations for this claim. To address the uncertainty surrounding the claim's value, there is a recognition that the reassessment process might reveal a lower value than the initially provided claim amount. This recognition of potential variability or discrepancy prompts the decision to apply a 20% discount to the claim amount. | 80% | 32657213.6
8 | On account of completion of balance works | 13087300000 | Balance work of the project highway will be given to some other company, as the current concession agreement has been terminated. Hence, NHAI cannot apply for the claim on account of completion of balance work. | 0% | 0
9 | 18% interest on awarded amount | To be assessed later |  |  | 1840823990.4251
10 | Cost of Arbitration proceedings | Actual
Total Claim Amount |  | 26418011438.0313

## Arbitration Method RK
Ranchi Expressways Limited
| Particulars | Amount (In Crs) | Remarks |  |  | No. of Years | 7 |  |  |  |  | 5
| Total Claim filed by the Company (A) | 2408.7512 |  | 1553.8527 | [7 empty] | 7
| Less: Award received so far out of (A) above (B) | 0 |  |  |  | Discount Rate
| Total Award Claimed (C) =(A-B) | 2408.7512 |  |  |  | Nifty 50 10-year return |  | 12% | https://kunaldesai.blog/nifty-returns/
| Less: Claims filed by EPC against the company (D) | 670.8161 |  |  |  | Company Risk Premium |  | 4%
| Less: Counter claims by NHAI against the company ('E) | 184.0824 |  |  |  | Appropriate Discount Rate |  | 16%
| Total Amount Claimed (F) =(C-D-E) | 1553.8527
90% | Expected Realization out of F (G) | 1398.4674
| Net Claim Realization available for lenders (G-H) | 1398.4674
| NPV as on date @ 13% | 0 | Rolling Nifty CAGR for 10 years
| Total Available balance. | #REF! | As a proxy of Enterprise Value
| Enterprise Value | #REF!
| NPV(As a proxy of Enterprise Value) | 578.2126 | It is assumed that this will take around 7 years to get realized.
[5 empty] | Year | 1 | 2 | 3 | 4 | 5 | 6 | 7
[5 empty] | Net Recovery | 1: 1398.4674
% | 578.2126 |  |  |  | Yearly Recovery | 0 | 0 | 0 | 0 | 466.1558 | 466.1558 | 466.1558
90% |  |  |  |  | Discount period | 1 | 2 | 3 | 4 | 5 | 6 | 7
80% |  |  |  |  | Discount Factor | 0.86207 | 0.74316 | 0.64066 | 0.55229 | 0.47611 | 0.41044 | 0.35383
50% |  |  |  |  | Discount Rate | 1: 16%
30% |  |  |  |  | Present Value | 0 | 0 | 0 | 0 | 221.9428 | 191.33 | 164.9397
[5 empty] | Net Present Value (NPV) | 1: 578.2126
NPV(As a proxy of Enterprise Value) | 578.2126
Debt Due: Outstanding Liability | 2068.29
Performance Security | 14.79
Enterprise Value | 2661.2926

## Physical Work
Physical Progress of Work
S.No | Dates | Land Available (Km) | Handing over of ROW by NHAI (In %) | Physical Work Completed by REL (In %)
1 | 04.12.2012 (Appointed Date) | 34.84 | 21.31 | 0
2 | 04.03.2013 | 66.29 | 40.54 | 0.292
3 | 02.06.2013 | 75.12 | 45.94 | 0.782
4 | 29.11.2013 | 99.59 | 60.89 | 3.828
5 | 17.05.2016 | 100.29 | 61.34 | 28.19
6 | 11.02.2017 | 128.87 | 78.82 | 40.54
7 | 15.02.2018 | 130.37 | 79.74 | 53.148
2012-12-04
2018-02-15
No. of days | 1899
In Crs
Annuity | 133.2
Average Daily Annuity | 0.74
Total Expenses | 1405.26