## Sheet1
List of Statutory Permit / Clearance Status
SN | Description | Authority | Status | One Time Approval / Validity
1 | Registration of the Company | Registrar of Companies | Obtained on 18-Dec-2015. | One Time
2 | Environmental and forest clearance | Ministry of Environment & Forests (MoEF) | Obtained on 31-Aug-2017, validity for 7 years to start operation & Amendment dated 3-Sept-2019. | One Time
3 | Consent to Operate | Jharkhand State Pollution Control Board | Obtained vide letter ref no JSPCB/HO/RNC/CTO-16603125/2023/1463 dated 19th Aug 2023 | 2027-09-30
4 | Civil aviation clearance for Chimney height | Airport authority of India | Obtained on 26-Oct-2016 and valid for five years for construction | One Time
5 | NOC for Construction of Chimney | Ministry of Defence (MoD) | Obtained on 11-June-2017 and valid for seven years for construction | One Time
6 | Approval of Construction Power | JUSNL, GoJ | Obtained on 09-Oct-2017 | One Time
7 | In-principle approval for construction of Pvt Railway Siding | Eastern Railway, Ministry of Railways | Obtained on 06-Aug-2016. | One Time
8 | DPR approval for Railway connectivity | Eastern Railway, Ministry of Railways | Obtained on 17-Sep-2018. | One Time
9 | IEM (Industrial Entrepreneurs Memorandum) | Ministry of Commerce and Industry, GoI | Obtained on 21-Aug-2017 | One Time
10 | Permission for withdrawal of Water from river Ganga | National Mission for Clean Ganga | Obtained on 08-Aug-2018 | One Time
11 | Approval of water drawl from Ganga River | WRD, Government of Jharkhand (GoJ) | Approval obtained on 15- Jan-2018 and Agreement signed on with WRD made on 19-Mar-2019 valid for 5 years | 2024-03-18
12 | Transmission line Section 164 | CEA | Obtained on 31-Aug-2018 and validity for 25 years. | One Time
13 | Transmission line Section 68 | CEA | Obtained on 27-Nov-2017 | One Time
14 | Import Export Code | Ministry of Commerce and Industry | Obtained on 17 March 2016. | One Time
15 | Cross Border Trade of Electricity Approval | Central Electricity Authority(CEA) of India | Obtained on Oct 27, 2017. | One Time
16 | SEZ Approval | Ministry of Commerce and Industry, GoI | Obtained. Gazette Notification done on 16/09/2019 | One Time
17 | FALTA SEZ | Ministry of Commerce and Industry, GoI | Obtained and renewed on 08.09.2021 | Yearly Renewal – Valid till 25.09.2022
18 | Permission for LDO storage (Petroleum class C.) | Petroleum & Explosive Safety Organization | Obtained vide license no P/EC/JH/15/1104 (P489744) , Dated July 13, 2022 | Dec 31, 2024
19 | Grant of Licence for Chlorine Storage for Main Plant | Petroleum & Explosive Safety Organization | Obtained (for 38 nos Cylinders) vide license no G/EH/JH/06/292(G102659) , Dated Jan 16 , 2023 | Sept 30. 2032
20 | Grant of Licence for Chlorine Storage for Intake Area | Petroleum & Explosive Safety Organization | Obtained (for 10 nos Cylinders) vide license no G/EH/JH/06/293(G102594), Dated Jan 16 , 202 | Sept 30. 2032
21 | Grant of Licence for Chlorine Storage for Intermediate Area Reservoir | Petroleum & Explosive Safety Organization | Obtained vide license no G/EH/JH/06/294(G102593), Dated Jan 17 , 2023 | Sept 30. 2032
22 | Grant of Licence for filling and storage of Hydrogen | Petroleum & Explosive Safety Organization | Obtained vide license no G/HO/JH/05/103(G108597), Dated Jan 06 , 2023 | Sept 30. 2032