## IECCL
Details of Projects and the corresponding arbitration claims and their progress
S.NO | Project | Client | Project Value | Claim Amount | Claim / Award Value | Counter Claim Value | Award Received | Remarks | AWARD DATE
1 | AS-17 - NH-36 in Assam on East West Corridor under Ph-II programme of NHDP | NHAI | 202.18 | 150.94 | 263.84 | 0 | 41.82 | 42.72 Award value | 2018-05-31
2 | AS-19 - NH-37 in Assam on East West Corridor under Ph-II programme of NHDP (1st Reference) | NHAI | 173.14 | 135.5 | 367.15 | 0 | 108.33 | 160.7193 Award value | 2014-12-23
3 | PVVNL Moradabad | PVVNL | 145.55 | 231.9 | 231.9 | 0 | 109.31 |  | 2019-02-28
4 | MSEDCL, Akola Project | MSEDCL | 51.705 | 13.38 | 9.12 | 0 | 7.39 |  | 2019-09-17
| TOTAL |  | 572.575 |  | 872.01 | 0 | 266.85
84.71
203.44

## SPVs
Details of SPVs and JVs the corresponding arbitration claims and their progress
S.No | Project Name | SPV Name | Client Name | Contract value | Award Value | IECCL's Share | IECCL's share of award | Received | Balance | Remarks | AWARD DATE
1 | Nagaland Road Project | Maytas -Gayatri JV | National Highways Authority of India (NHAI) | 1130.67 | 703.37 | 62% | 436.0894 | 0 | 436.0894 | It is a B2B project and IECCL margin is 20%; lready in Books | 2019-08-10
2 | Hyderabad Expressway (HEL): Eight line access controlled expressway from Bongalur to Tukkuguda | Maytas -Gayatri JV | Hyderabad Growth Corridor Ltd (HGCL) | 362 | 99 | 50% | 49.5 | 0 | 49.5 | Part of MIT | 2022-02-24
3 | Cyberabad Exressway (CEL): Eight line access controlled expressway from Kollur to Patancheru | Maytas -Gayatri JV | Hyderabad Growth Corridor Ltd (HGCL) | 415 | 241 | 50% | 120.5 | 0 | 120.5 | Part of MIT | 2019-02-27
4 | Pondicherry Tindivanam Tollways Limited (PTTL) | Maytas-NCC JV | National Highways Authority of India (NHAI) | 229.18 | 183.82 | 51% | 93.7482 | 0 | 93.7482 | *Rs 94 Cr is only for PTTPL, which is a loss asset. It is not a claim per se but a case for handing over of project and settlement of Lender dues | 2018-10-16
5 | Bangalore Elevated Tollways Ltd (BETL): Elevated Highway from Silk Board Junction to Electronic City Junction | SOMA-NCC-IECCL | National Highways Authority of India (NHAI) | 450 | 492 | 33.33% | 163.9836 | 0 | 163.9836 | Part of MIT | 2019-11-27
6 | Brindavan Infrastructure Co. Ltd (BICL): Upgradation of existing 2 lane to 4 lane divided carriage way Bangalore-Maddur Section of Bangalore Mysore State Highway | NCC-KMC-IECCL JV | Karnata Road Development Corporation Ltd (KRDCL) | 216 | 88.16 | 33.33% | 29.3837 | 0 | 29.3837 | Resondent has appealed in the court aginst the award and the award has been rejected | 2013-08-09 | Award Rejected
7 | MRTS, Phase I&II - Mundakanniamman Koil Station building | Maytas - CTR JV | MTP Railways- Chennai |  | 4.38 | 100% | 4.38 | 3.66 | 0.72 | Amount released by client was credited in JV Bank A/c, JV partner has issued letter with bank | 2018-12-26 | total claim amount = 21.27 Crs.
| TOTAL (Rs. In Crs.) |  |  |  | 1811.73 |  | 897.5849 | 3.66 | 893.9249
Note on D8: Bangalore State Highway

## Brindavan
Vivad se Vishwash is applicable=65% with 9% interest per annum | Brindavan Infrastructure Co. Ltd |  | Award Rejected
Aweard Date | 2007-04-21
| Particulars | Amount (In Crs) | Remarks | [7 empty] | 5
| Contract value | 216 | [8 empty] | 7
| Claim Value | 85
| Award Value | 88.1673
| IECCL's Share (%) | 33.33%
| IECCL's share of award | 29.3862
65%% payable as per Vivad se Vishwas II Scheme+9% Interest | Award Value as per Vivad se vishwas | 46.5039
15% | Less: Expected Expenses to be incurred to realize the award amount (15%) | 6.9756
| Net Award Amount | 39.5283
| NPV as on date @ 13% | #REF! | Rolling Nifty CAGR for 10 years
| Total Available balance. | #REF! | As a proxy of Enterprise Value
| Enterprise Value | #REF!
| NPV(As a proxy of Enterprise Value) | 25.5864 | It is assumed that this will take around 5 years to get realized.
| No. of Years | 5 |  |  | Year | 1 | 2 | 3 | 4 | 5
[5 empty] | Net Recovery | 39.5283
| Discount Rate |  |  |  | Yearly Recovery | 7.9057 | 7.9057 | 7.9057 | 7.9057 | 7.9057
| Nifty 50 5-year return |  | 14% | https://kunaldesai.blog/nifty-returns/ | Discount period | 1 | 2 | 3 | 4 | 5
| Company Risk Premium |  | 2.5% |  | Discount Factor | 0.85837 | 0.7368 | 0.63244 | 0.54287 | 0.46598
[5 empty] | Discount Rate | 16.5%
[5 empty] | Present Value | 6.786 | 5.8249 | 4.9999 | 4.2917 | 3.6839
| Appropriate Discount Rate |  | 16.5% |  | Net Present Value (NPV) | 25.5864

## AS-17
Vivad se Vishwash is not applicable | AS-17 - NH-36 in Assam on East West Corridor under Ph-II programme of NHDP
Aweard Date | 2018-05-31
| Particulars | Award Amount (In Crs) | Intertest | [7 empty] | 5
| Project value | 202.18 | [8 empty] | 7
Page no. 174 | Claims Award Value as per letter of awards | 42.7276 | 1.6022 | As per award 10% Future Interest rate
| Award Value | 44.3298
15% | Less: Expected Expenses to be incurred to realize the award amount (15%) | 6.6495
| Net Award Amount | 37.6803
| NPV as on date @ 13% | 17.5584 | Rolling Nifty CAGR for 10 years
| Total Available balance. | #REF! | As a proxy of Enterprise Value
| Enterprise Value | #REF!
| NPV(As a proxy of Enterprise Value) | 24.3902 | It is assumed that this will take around 5 years to get realized.
| No. of Years | 5 |  |  | Year | 1 | 2 | 3 | 4 | 5
[5 empty] | Net Recovery | 37.6803
| Discount Rate |  |  |  | Yearly Recovery | 7.5361 | 7.5361 | 7.5361 | 7.5361 | 7.5361
| Nifty 50 5-year return |  | 14% | https://kunaldesai.blog/nifty-returns/ | Discount period | 1 | 2 | 3 | 4 | 5
| Company Risk Premium |  | 2.5% |  | Discount Factor | 0.85837 | 0.7368 | 0.63244 | 0.54287 | 0.46598
[5 empty] | Discount Rate | 16.5%
[5 empty] | Present Value | 6.4687 | 5.5526 | 4.7661 | 4.0911 | 3.5117
| Appropriate Discount Rate |  | 16.5% |  | Net Present Value (NPV) | 24.3902
|  | 37.6803 | 0.46598
| NPV | 17.5584

## AS-19
Vivad se Vishwash is not applicable | AS-19 - NH-37 in Assam on East West Corridor under Ph-II programme of NHDP (1st Reference)
Aweard Date | 2014-12-23
| Particulars | Award Amount (In Crs) | Intertest | [7 empty] | 5
| Project value | 173.14 | [8 empty] | 7
Page no. 92 | Claims Award Value as per letter of awards | 160.7194 | 109.689 | As per award 18% Future Interest rate
| Award Value | 270.4084
15% | Less: Expected Expenses to be incurred to realize the award amount (15%) | 40.5613
| Net Award Amount | 229.8471
| NPV as on date @ 13% | 107.1049 | Rolling Nifty CAGR for 10 years
| Total Available balance. | #REF! | As a proxy of Enterprise Value
| Enterprise Value | #REF!
| NPV(As a proxy of Enterprise Value) | 148.7784 | It is assumed that this will take around 5 years to get realized.
| No. of Years | 5 |  |  | Year | 1 | 2 | 3 | 4 | 5
[5 empty] | Net Recovery | 229.8471
| Discount Rate |  |  |  | Yearly Recovery | 45.9694 | 45.9694 | 45.9694 | 45.9694 | 45.9694
| Nifty 50 5-year return |  | 14% | https://kunaldesai.blog/nifty-returns/ | Discount period | 1 | 2 | 3 | 4 | 5
| Company Risk Premium |  | 2.5% |  | Discount Factor | 0.85837 | 0.7368 | 0.63244 | 0.54287 | 0.46598
[5 empty] | Discount Rate | 16.5%
[5 empty] | Present Value | 39.4587 | 33.8702 | 29.0731 | 24.9554 | 21.421
| Appropriate Discount Rate |  | 16.5% |  | Net Present Value (NPV) | 148.7784
|  | 229.8471 | 0.46598
| NPV | 107.1049

## Summary
Details as on 15th October 2018
Description | Net Award Amount
Figures in INR Crore
IECCL | 267.5275
Net Award Amount | 267.5275