## Status
S. No | Particulars | Supplier/Vendor | Purchase Basic Amount(In CR.) | Status Achieved
|  |  |  | Quotation (Y/N) | Purchased (Y/N) | Received on site(Y/N) | Installed(Y/N)
1 | Water Plant | Netsol Water Solutions Pvt Ltd
2 | DSI Automatic Cage 4 Row 5 tier(one growing and 4 layer house) | DS ISPAT
3 | Mash feed Plant | Sai Durga Agrotech Industries
4 | Silos | Sai Durga Industries
S. No | Particulars | Supplier/Vendor | Purchase Basic Amount In Rs.(In CR.) | Status Achieved
|  |  |  | Quotation (Y/N) | Purchased (Y/N) | Received on site(Y/N) | Installed(Y/N)
1 | Water Plant | Netsol Water Solutions Pvt Ltd | 0.11 | YES | NO | NO | NO
2 | DSI Automatic Cage 4 Row 5 tier(one growing and 4 layer house) | DS ISPAT | 7.72 | YES | YES | NO | NO
3 | Mash feed Plant | Sai Durga Agrotech Industries | 0.24 | YES | YES | NO | NO
4 | Silos | Sai Durga Industries | 0.59 | YES | YES | NO | NO
| Total |  | 8.66

## % completion
Boundary wall | 100%
Land development | 50%
Administrative Building | 0%
Grooming and Breeding Shed | 40%
Layer 1 Shed | 35%
Layer 2 Shed | 0%
Layer 3 Shed | 0% | Parameter | Limits
Layer 4 Shed | 0% | Total Dissolved Solids (TDS) | Upto 3500ppm(mg/L)
Food Mill Shed | 0% | Temperature | 40-100F(4-38Degree C)
Store | 100% | pH | 4-11
Labour Quarter | 70% | Hardness | <280mg/L
Silo | 5% | Free Chlorine | <1mg/L
|  | Turbidity | <1NTU
|  | Iron (Fe) | <0.1mg/L
|  | SDI | < 2.5
|  | Hydrogen Sulphide | Not Allowed
|  | Organics | <1mg/L

## Building Sheet
Building Sheet For Riya Diya Agro Farms LLP, Village Baranata, Chakulia, Purbi Singbhum, Jharkhand
SR. No. | Particulars | Floors | Type of Structure | L | B | Area (in sq.ft) | Height (in feet) | Year of Construction | Year of Valuation | Total Life Consumed (in years) | Total Economical Life (in years) | Salvage value | Depreciation Rate | Plinth Area Rate (in per sq.ft) | Gross Replacement Value (INR) | Depreciation | Depreciated Value (INR) | Discounting Factor | Depreciated Replacement Market Value (INR)
1 | Administrative Building | G+1 | R.C.C | 18.099 | 43.43 | 16921.7027 | 10 | 2023 | 2023 | 0 | 65 | 10% | 0.013846 | 1500 | 25382553.9826 | 0 | 0 |  | 25382553.9826 | 86 | 56 | 4816
2 | Grooming and Breeding Shed | 1 | Tin Shed | 12.806 | 77.751 | 10717.3925 | 45 | 2023 | 2023 | 0 | 45 | 10% | 0.02 | 800 | 8573913.9855 | 0 | 0 |  | 8573913.9855 | 70 | 31 | 2170
3 | Layer 1 | 1 | Tin Shed | 12.4 | 108.241 | 14447.1817 | 45 | 2023 | 2023 | 0 | 45 | 10% | 0.02 | 800 | 11557745.375 | 0 | 0 |  | 11557745.375 |  |  | 262362
4 | Layer 2 | 1 | Tin Shed | 12.806 | 108.241 | 14920.2104 | 45 | 2023 | 2023 | 0 | 45 | 10% | 0.02 | 800 | 11936168.3284 | 0 | 0 |  | 11936168.3284 |  |  | 262362 | 10.764
5 | Layer 3 | 1 | Tin Shed | 12.806 | 108.241 | 14920.2104 | 45 | 2023 | 2023 | 0 | 45 | 10% | 0.02 | 800 | 11936168.3284 | 0 | 0 |  | 11936168.3284 |  |  |  | 2824064.568
6 | Layer 4 | 1 | Tin Shed | 12.806 | 108.241 | 14920.2104 | 45 | 2023 | 2023 | 0 | 45 | 10% | 0.02 | 800 | 11936168.3284 | 0 | 0 |  | 11936168.3284
7 | Food Mill | 1 | Tin Shed | 19.223 | 29.293 | 6061.145 | 45 | 2023 | 2023 | 0 | 45 | 10% | 0.02 | 800 | 4848915.98 | 0 | 0 |  | 4848915.98 |  |  |  | 53654.59 | 14000 | 751164260
[6 empty] | 92908.0531 | [8 empty] | 86171634.3084 |  |  | 0 | 86171634.3084 | 329450000 | 415621634.3084 | 444100000
Remarks: | [19 empty] | 751164260 | 2800000 | 840135894.3084
1. All the details pertaing to the building area statement such as area, floor, etc has been taken from the sanctioned building sheet provided by the company only. | [21 empty] | 911700000 | 0.85 | 774945000
2. All the structure that has been taken in the area statemnet belonging to M/S. Riya Diya Agro Farm LLP | [21 empty] | 285992600 | 0.75 | 214494450
3. The valuation is done by considering the depreciated replacement cost approach.
68937307.4467
| Land |  | 11.98 | 22600000 | 270748000 | 2.26
| Building |  |  |  | 86171634.3084
| Boundary |  |  |  | 14500000
371419634.3084
403000000
403000000
|  |  |  | 0.85 | 342550000
|  |  |  | 0.75 | 302250000 | [5 empty] | 516
7700
|  |  | 11.98 | 22625000 | 271047500
86171634.3084
14000000
371219134.3084
742438268.6167
350000000
|  |  |  | 0.85 | 297500000
|  |  |  | 0.75 | 262500000

## Construction Cost
Building Sheet For Riya Diya Agro Farms LLP, Village Baranata, Chakulia, Purbi Singbhum, Jharkhand
SR. No. | Particulars | Floors | Type of Structure | L | B | Unit | QTY | Rate | Year of Construction | Year of Valuation | Total Life Consumed (in years) | Total Economical Life (in years) | Salvage value | Depreciation Rate | Amount | Rate Approved | Amount Approved | Remarks | Depreciated Value (INR) | Discounting Factor | Depreciated Replacement Market Value (INR)
1 | Boundary Wall(RCC Slab Boundary) | [5 empty] | 2250 | 1200 | [6 empty] | 2700000 | [8 empty] | 25074
2 | Land Survey | [5 empty] | 1 | [7 empty] | 100000 | [8 empty] | 0.0025074
3 | Land Dressing | [5 empty] | 210000 | 50 | [6 empty] | 10500000 | [9 empty] | 13.92
4 | Staff quarters | [5 empty] | 4000 | 2000 | [6 empty] | 8000000 | [9 empty] | 3.4
5 | Office | [5 empty] | 1500 | 2000 | [6 empty] | 3000000 | [9 empty] | 0.2
6 | Breading And Grooming Shed | [5 empty] | 10500 | 800 | [6 empty] | 8400000 | [9 empty] | 17.52
7 | Layer Sheds | [5 empty] | 60000 | 800 | [6 empty] | 48000000
8 | Labour Huts | [5 empty] | 2000 | 1500 | [6 empty] | 3000000
9 | Boring | [5 empty] | 3 | [7 empty] | 800000
10 | Underground Water storage & Over head tank | [5 empty] | 200000 | 10 | [6 empty] | 2000000
11 | Security Room | [5 empty] | 200 | 1500 | [6 empty] | 300000
12 | Generator Room | [5 empty] | 500 | 1000 | [6 empty] | 500000
13 | Food meal storage | [5 empty] | 9000 | 800 | [6 empty] | 7200000
14 | Elec Sub Station Room | [5 empty] | 320 | 1250 | [6 empty] | 400000
15 | Misc Room | [5 empty] | 500 | 1200 | [6 empty] | 600000
16 | Lab | [5 empty] | 150 | 2000 | [6 empty] | 300000
17 | Mess and kitchen | [5 empty] | 400 | 2000 | [6 empty] | 800000
18 | Silo civil work | [13 empty] | 1500000
19 | Parking Shed | [5 empty] | 800 | 500 | [6 empty] | 400000
20 | Toilet | [5 empty] | 400 | 3000 | [6 empty] | 1200000
21 | Changing Room | [5 empty] | 200 | 2000 | [6 empty] | 400000
22 | Entry and exit gate | G+1 | Tin Shed | 18.099 | 43.43 |  |  | LS | 1990 | 2023 | 33 | 45 | 10% | 0.02 | 600000 |  | 0 | 0.66 | 0 |  | 0 | 86 | 56 | 4816
23 | Safety tank | [6 empty] | LS | [6 empty] | 1000000
24 | Wastage water storage | [6 empty] | LS | [6 empty] | 500000
25 | Temple | [5 empty] | 100 | 2000 | [6 empty] | 200000
26 | Pump room | [5 empty] | 200 | 1500 | [6 empty] | 300000
27 | Egg store | [5 empty] | 1000 | 2000 | [6 empty] | 2000000
28 | Guest House | [5 empty] | 2000 | 2000 | [6 empty] | 4000000
29 | First Aid Room | 1 | Tin Shed | 12.806 | 77.751 |  | 100 | 2000 | 1990 | 2023 | 33 | 45 | 10% | 0.02 | 200000 |  | 20000000 | 0.66 | 13200000 |  | 6800000 | 70 | 31 | 2170
30 | Green Development | 1 | Tin Shed | 12.4 | 108.241 |  | 20000 | 50 | 1994 | 2023 | 29 | 45 | 10% | 0.02 | 1000000 |  | 20000000000 | 0.58 | 11600000000 |  | 8400000000 |  |  | 262362
31 | Disinfectant Area | 1 | Tin Shed | 12.806 | 108.241 |  |  | LS | 1996 | 2023 | 27 | 45 | 10% | 0.02 | 200000 |  | 0 | 0.54 | 0 |  | 0 |  |  | 262362 | 10.764
32 | Drain for waste water | 1 | Tin Shed | 12.806 | 108.241 |  | 1000 | 1000 | 1985 | 2023 | 38 | 45 | 10% | 0.02 | 1000000 |  | 1000000000 | 0.76 | 760000000 |  | 240000000 |  |  |  | 2824064.568
33 | Drain for rain water | 1 | Tin Shed | 12.806 | 108.241 |  | 1000 | 1000 | 2006 | 2023 | 17 | 45 | 10% | 0.02 | 1000000 |  | 1000000000 | 0.34 | 340000000 |  | 660000000
34 | Internal Boundary | 1 | Tin Shed | 19.223 | 29.293 |  | 1250 | 1200 | 1985 | 2023 | 38 | 45 | 10% | 0.02 | 1500000 |  | 1875000000 | 0.76 | 1425000000 |  | 450000000 |  |  |  | 53654.59 | 14000 | 751164260
35 | Internal road | [5 empty] | 40000 | 75 | [6 empty] | 3000000
36 | Chimney | [6 empty] | LS | [6 empty] | 300000
37 | Water Purifing Plant | [6 empty] | LS | [6 empty] | 500000
Total(Rs.) | [14 empty] | 117400000
[7 empty] | 26650 | [9 empty] | 23895000000 |  |  | 0 | 9756800000 | 329450000 | 10086250000 | 444100000
[22 empty] | 751164260 | 2800000 | 10510764260
[24 empty] | 911700000 | 0.85 | 774945000
[24 empty] | 911700000 | 0.75 | 683775000
[24 empty] | 285992600 | 0.75 | 214494450
19116000000
| Land |  | 11.98 | 22600000 | 270748000 |  | 2.26
| Building |  |  |  | 9756800000
| Boundary |  |  |  | 14500000
10042048000
403000000
403000000
|  |  |  | 0.85 | 342550000
|  |  |  | 0.75 | 302250000 | [6 empty] | 516
7700
|  |  | 11.98 | 22625000 | 271047500
9756800000
14000000
10041847500
20083695000
350000000
|  |  |  | 0.85 | 297500000
|  |  |  | 0.75 | 262500000

## Expenses
Construction Cost
| Unit | L | B | H | Qty | Rate | Amount
Earth Work | m3 |  |  |  | 37332.2835 | 200 | 7466456.7
Precast(Boundary Wall) | Sqft | 2478 | 7 |  | 17346 | 100 | 1734600
Chain Link Fencing(Boundary Wall) | Sqft | 1074 | 7 |  | 7518 | 90 | 676620
Grooming Shed | Sqft | 253 | 44 |  | 11132 | 400 | 4452800
Layer Shed | Sqft | 354 | 45 |  | 15930 | 450 | 7168500
Silo Excavation | Sqft |  |  |  | 0 |  | 300000
Labour Quarter | Sqft | 80 | 22 |  | 1760 | 1000 | 1760000
Store | Sqft | 50 | 30 |  | 1500 | 450 | 675000
24233976.7
132588000
[7 empty] | 2.4234 |  |  | 150266400
P & M | [9 empty] | 176784000
Particulars | Amount Finalised | % Advance | Advance amount |  |  |  |  | 33411.858 | 5291.0556 | 21412055.6408
Sai Durga | 11726000 | 25% | 2931500 | [5 empty] | 8.2563
DS Ispat | 61268480 | 50% | 7658560
DS Ispat | 15270528 | 50% | 7635264
18225324

## Sheet1
PARTICULARS | TOTAL ESTIMATED COST (In Rs. In Cr.) | EXPENDITURE SHOWN BY COMPANY(In Rs. In Cr.) | AMOUNT OF WORK DONE ON SITE | ADVANCES PAID | AMOUNT INCURRED TILL 30.06.2023 | REMARKS
Land Development, Building and other civil works. | 11.72 | 2.41 |  | No information available
Plant, Machinery and equipment. | 8.66 | 0.79 |  | No information available
Pre-operative Expenses |  | 0.215 |  | No information available
Interest During Construction |  | 0.0025 |  | No information available
Total | 20.38 | 3.4175

## Cost Summary
Particulars | In Rs. In Cr.
Land Development/Building/Other Civil Works | 11.72
Plant & Machinery | 8.66
Electrical Installation | 0.41
Furniture & Fixture | 0.06
Security Deposit | 0.02
Others | 1.42
Working Capital Margin | 1.66
Total | 23.95
Start Date | Start Date | End Date
| 2023-01-03 | 31/12/2024