## Project Brief
Name of the Project | Shreeji Angarika
Project Location
Contruction Area |  | Square Feet | Freehold Owned Land |  |  | SRA
Sale Area - RERA Carpet |  | Square Feet |  |  |  | Private SRA
Cost | Estimated Total Cost (Actuals) | Incurred up to April 2023 | To be Incurred | % of Total Cost |  | Society Redevelopment
Land Acquisition Cost | 5.25 | 1.94 | 3.31 | 15.62% |  | Freehold Owned Land
Rent and Hardship Compensation | 0 | 0 | 0 | 0% |  | Joint Venture
Fungible FSI Premium | 0 | 0 | 0 | 0%
TDR | 1 | 0.2 | 0.8 | 2.974%
Approvals and Other Premiums | 1.87 | 1.87 | 0 | 5.562%
Construction Cost - Rehab Building | 0 | 0 | 0 | 0%
Construction Cost - Sale Building | 19.28 | 0 | 19.28 | 57.35%
Selling and Marketing | 1.3 | 0 | 1.3 | 3.867% | 6.743%
Professional Fees and Admin expenses | 1.35 | 0.4 | 0.95 | 4.015% | 7.002%
Contingency | 0 | 0 | 0 | 0%
Finance Cost | 3.5706 | 0 | 3.5706 | 10.62%
Total Project Cost | 33.6206 | 4.41 | 29.2106 | 100%
Means of Finance | Amount | Brought in | To be incurred | Margin
Equity / Partnership Capital | 0.24 | 0.24 | 0 | 0.7138%
Unsecured Loans from promoters | 8 | 4.17 | 3.83 | 23.79%
Advance from Units already sold |  | 0 | 0 | 0%
Advance from Future bookings | 10.8806 | 0 | 10.8806 | 32.36%
Bank Finance - Term Loan | 14.5 | 0 | 14.5 | 43.13%
Total | 33.6206 | 4.41 | 29.2106 | 100%

## UNIT LIST BUILDING NO 1 (hidden)
Sr. No | Unit Type | Unit No | RERA Carpet Area (SQ.MT) | BALCONY AREA (SQ.MT) | RERA Carpet Area (SQ.FT) | BALCONY AREA (SQ.FT) | TOTAL AREA IN SQ.MT | TOTAL AREA IN SQ.FT | Saleable Area |  | BHK | Sale Value
1 | Shop | 1 | 164.85 |  | 1774.4454 |  |  |  | 3548.8908
2 | Shop | 2 | 146.31 |  | 1574.8808 |  |  |  | 3149.7617
3 | Shop | 3 | 146.31 |  | 1574.8808 |  |  |  | 3149.7617
4 | Shop | 4 | 164.85 |  | 1774.4454 |  |  |  | 3548.8908
5 | Shop | 5 | 48.6 |  | 523.1304 |  |  |  | 1046.2608
6 | Shop | 6 | 29.68 |  | 319.4755 |  |  |  | 638.951
7 | Shop | 7 | 27.72 |  | 298.3781 |  |  |  | 596.7562
8 | Office P1 | S-1 | 164.85 |  | 1774.4454 |  |  |  | 3105.2794
9 | Office P1 | S-2 | 146.31 |  | 1574.8808 |  |  |  | 2756.0415
10 | Office P1 | S-3 | 146.31 |  | 1574.8808 |  |  |  | 2756.0415
11 | Office P1 | S-4 | 164.85 |  | 1774.4454 |  |  |  | 3105.2794
12 | Office P1 | S-5 | 373.21 |  | 4017.2324 |  |  |  | 7030.1568
13 | Office P2 | S-1 | 278.16 |  | 2994.1142 |  |  |  | 5239.6999
14 | Office P3 | S-1 | 95.02 |  | 1022.7953 |  |  |  | 1789.8917
15 | Office P3 | S-2 | 70.41 |  | 757.8932 |  |  |  | 1326.3132
16 | Office P3 | S-3 | 73.24 |  | 788.3554 |  |  |  | 1379.6219
17 | Office P3 | S-4 | 95.02 |  | 1022.7953 |  |  |  | 1789.8917
18 | Office P3 | S-5 | 278.16 |  | 2994.1142 |  |  |  | 5239.6999
19 | Flat | 101 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
20 | Flat | 102 | 87.9 | 3.81 | 946.1556 | 41.0108 | 91.71 | 987.1664 | 1555 | 615.0011
21 | Flat | 103 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
22 | Flat | 104 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
23 | Flat | 105 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
24 | Flat | 106 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
25 | Flat | 107 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
26 | Flat | 108 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
27 | Flat | 109 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
28 | Flat | 110 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
29 | Flat | 111 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
30 | Flat | 112 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
31 | Flat | 201 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
32 | Flat | 202 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
33 | Flat | 203 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
34 | Flat | 206 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
35 | Flat | 207 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
36 | Flat | 208 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
37 | Flat | 209 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
38 | Flat | 210 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
39 | Flat | 211 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
40 | Flat | 212 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
41 | Flat | 301 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
42 | Flat | 302 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
43 | Flat | 303 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
44 | Flat | 304 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
45 | Flat | 305 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
46 | Flat | 306 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
47 | Flat | 307 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
48 | Flat | 308 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
49 | Flat | 309 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
50 | Flat | 310 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
51 | Flat | 311 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
52 | Flat | 312 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
53 | Flat | 401 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
54 | Flat | 402 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
55 | Flat | 403 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
56 | Flat | 404 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
57 | Flat | 405 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
58 | Flat | 406 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
59 | Flat | 407 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
60 | Flat | 408 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
61 | Flat | 409 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
62 | Flat | 410 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
63 | Flat | 411 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
64 | Flat | 412 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
65 | Flat | 501 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
66 | Flat | 502 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
67 | Flat | 503 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
68 | Flat | 504 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
69 | Flat | 505 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
70 | Flat | 506 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
71 | Flat | 507 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
72 | Flat | 508 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
73 | Flat | 509 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
74 | Flat | 510 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
75 | Flat | 511 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
76 | Flat | 512 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
77 | Flat | 601 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
78 | Flat | 602 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
79 | Flat | 603 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
80 | Flat | 604 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
81 | Flat | 605 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
82 | Flat | 606 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
83 | Flat | 607 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
84 | Flat | 608 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
85 | Flat | 609 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
86 | Flat | 610 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
87 | Flat | 611 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
88 | Flat | 612 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
89 | Flat | 701 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
90 | Flat | 702 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
91 | Flat | 703 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
92 | Flat | 706 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
93 | Flat | 707 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
94 | Flat | 708 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
95 | Flat | 709 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
96 | Flat | 710 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
97 | Flat | 711 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
98 | Flat | 712 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
99 | Flat | 801 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
100 | Flat | 802 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
101 | Flat | 803 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
102 | Flat | 804 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
103 | Flat | 805 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
104 | Flat | 806 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
105 | Flat | 807 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
106 | Flat | 808 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
107 | Flat | 809 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
108 | Flat | 810 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
109 | Flat | 811 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
110 | Flat | 812 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
111 | Flat | 901 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
112 | Flat | 902 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
113 | Flat | 903 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
114 | Flat | 904 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
115 | Flat | 905 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
116 | Flat | 906 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
117 | Flat | 907 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
118 | Flat | 908 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
119 | Flat | 909 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
120 | Flat | 910 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
121 | Flat | 911 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
122 | Flat | 912 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
123 | Flat | 1001 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
124 | Flat | 1002 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
125 | Flat | 1003 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
126 | Flat | 1004 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
127 | Flat | 1005 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
128 | Flat | 1006 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
129 | Flat | 1007 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
130 | Flat | 1008 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
131 | Flat | 1009 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
132 | Flat | 1010 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
133 | Flat | 1011 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
134 | Flat | 1012 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
135 | Flat | 1101 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
136 | Flat | 1102 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
137 | Flat | 1103 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
138 | Flat | 1104 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
139 | Flat | 1105 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
140 | Flat | 1106 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
141 | Flat | 1107 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
142 | Flat | 1108 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
143 | Flat | 1109 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
144 | Flat | 1110 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
145 | Flat | 1111 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
146 | Flat | 1112 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
147 | Flat | 1201 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
148 | Flat | 1202 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
149 | Flat | 1203 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
150 | Flat | 1206 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
151 | Flat | 1207 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
152 | Flat | 1208 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
153 | Flat | 1209 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
154 | Flat | 1210 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
155 | Flat | 1211 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
156 | Flat | 1212 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
157 | Flat | 1301 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
158 | Flat | 1302 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
159 | Flat | 1303 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
160 | Flat | 1304 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
161 | Flat | 1305 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
162 | Flat | 1306 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
163 | Flat | 1307 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
164 | Flat | 1308 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
165 | Flat | 1309 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
166 | Flat | 1310 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
167 | Flat | 1311 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
168 | Flat | 1312 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
169 | Flat | 1401 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
170 | Flat | 1402 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
171 | Flat | 1403 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
172 | Flat | 1404 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
173 | Flat | 1405 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
174 | Flat | 1406 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
175 | Flat | 1407 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
176 | Flat | 1408 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
177 | Flat | 1409 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
178 | Flat | 1410 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
179 | Flat | 1411 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
180 | Flat | 1412 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
181 | Flat | 1501 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
182 | Flat | 1502 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
183 | Flat | 1503 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
184 | Flat | 1504 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
185 | Flat | 1505 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
186 | Flat | 1506 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
187 | Flat | 1507 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
188 | Flat | 1508 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
189 | Flat | 1509 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
190 | Flat | 1510 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
191 | Flat | 1511 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
192 | Flat | 1512 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
193 | Flat | 1601 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
194 | Flat | 1602 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
195 | Flat | 1603 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
196 | Flat | 1606 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
197 | Flat | 1607 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
198 | Flat | 1608 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
199 | Flat | 1609 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
200 | Flat | 1610 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
201 | Flat | 1611 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
202 | Flat | 1612 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
203 | Flat | 1701 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
204 | Flat | 1702 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
205 | Flat | 1703 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
206 | Flat | 1704 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
207 | Flat | 1705 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
208 | Flat | 1706 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
209 | Flat | 1707 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
210 | Flat | 1708 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
211 | Flat | 1709 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
212 | Flat | 1710 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
213 | Flat | 1711 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
214 | Flat | 1712 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
215 | Flat | 1801 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
216 | Flat | 1802 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
217 | Flat | 1803 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
218 | Flat | 1804 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
219 | Flat | 1805 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
220 | Flat | 1806 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
221 | Flat | 1807 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
222 | Flat | 1808 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
223 | Flat | 1809 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
224 | Flat | 1810 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
225 | Flat | 1811 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
226 | Flat | 1812 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
227 | Flat | 1901 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
228 | Flat | 1902 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
229 | Flat | 1903 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
230 | Flat | 1904 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
231 | Flat | 1905 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
232 | Flat | 1906 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
233 | Flat | 1907 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
234 | Flat | 1908 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
235 | Flat | 1909 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
236 | Flat | 1910 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
237 | Flat | 1911 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
238 | Flat | 1912 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
239 | Flat | 2001 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
240 | Flat | 2002 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
241 | Flat | 2003 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
242 | Flat | 2004 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
243 | Flat | 2005 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
244 | Flat | 2006 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
245 | Flat | 2007 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
246 | Flat | 2008 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
247 | Flat | 2009 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
248 | Flat | 2010 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
249 | Flat | 2011 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
250 | Flat | 2012 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
251 | Flat | 2101 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
252 | Flat | 2102 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
253 | Flat | 2103 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
254 | Flat | 2106 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
255 | Flat | 2107 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
256 | Flat | 2108 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
257 | Flat | 2109 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
258 | Flat | 2110 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
259 | Flat | 2111 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
260 | Flat | 2112 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
261 | Flat | 2201 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
262 | Flat | 2202 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
263 | Flat | 2203 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
264 | Flat | 2204 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
265 | Flat | 2205 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
266 | Flat | 2206 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
267 | Flat | 2207 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
268 | Flat | 2208 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
269 | Flat | 2209 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
270 | Flat | 2210 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
271 | Flat | 2211 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
272 | Flat | 2212 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
273 | Flat | 2301 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
274 | Flat | 2302 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
275 | Flat | 2303 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
276 | Flat | 2304 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
277 | Flat | 2305 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
278 | Flat | 2306 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
279 | Flat | 2307 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
280 | Flat | 2308 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
281 | Flat | 2309 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
282 | Flat | 2310 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
283 | Flat | 2311 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
284 | Flat | 2312 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
285 | Flat | 2401 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
286 | Flat | 2402 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
287 | Flat | 2403 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
288 | Flat | 2404 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
289 | Flat | 2405 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
290 | Flat | 2406 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
291 | Flat | 2407 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
292 | Flat | 2408 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
293 | Flat | 2409 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
294 | Flat | 2410 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
295 | Flat | 2411 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
296 | Flat | 2412 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
297 | Flat | 2501 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
298 | Flat | 2502 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
299 | Flat | 2503 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
300 | Flat | 2504 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
301 | Flat | 2505 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
302 | Flat | 2506 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
303 | Flat | 2507 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
304 | Flat | 2508 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
305 | Flat | 2509 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
306 | Flat | 2510 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
307 | Flat | 2511 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
308 | Flat | 2512 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
309 | Flat | 2601 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
310 | Flat | 2602 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
311 | Flat | 2603 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
312 | Flat | 2606 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
313 | Flat | 2607 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
314 | Flat | 2608 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
315 | Flat | 2609 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
316 | Flat | 2610 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
317 | Flat | 2611 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
318 | Flat | 2612 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
319 | Flat | 2701 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
320 | Flat | 2702 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
321 | Flat | 2703 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
322 | Flat | 2704 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
323 | Flat | 2705 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
324 | Flat | 2706 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
325 | Flat | 2707 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
326 | Flat | 2708 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
327 | Flat | 2709 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
328 | Flat | 2710 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
329 | Flat | 2711 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
330 | Flat | 2712 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
331 | Flat | 2801 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
332 | Flat | 2802 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
333 | Flat | 2803 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
334 | Flat | 2804 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
335 | Flat | 2805 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
336 | Flat | 2806 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
337 | Flat | 2807 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
338 | Flat | 2808 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
339 | Flat | 2809 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
340 | Flat | 2810 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
341 | Flat | 2811 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
342 | Flat | 2812 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
343 | Flat | 2901 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
344 | Flat | 2902 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
345 | Flat | 2903 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
346 | Flat | 2904 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
347 | Flat | 2905 | 44.35 | 3.78 | 477.3834 | 40.6879 | 48.13 | 518.0713 | 795 | 310.2992
348 | Flat | 2906 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
349 | Flat | 2907 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
350 | Flat | 2908 | 67.02 | 3.94 | 721.4033 | 42.4102 | 70.96 | 763.8134 | 1210 | 468.9121
351 | Flat | 2909 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
352 | Flat | 2910 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
353 | Flat | 2911 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
354 | Flat | 2912 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
355 | Flat | 3002 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
356 | Flat | 3003 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
357 | Flat | 3006 | 44.09 | 3.96 | 474.5848 | 42.6254 | 48.05 | 517.2102 | 795 | 308.4801
358 | Flat | 3007 | 95.39 | 3.81 | 1026.778 | 41.0108 | 99.2 | 1067.7888 | 1690 | 667.4057
359 | Flat | 3009 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
360 | Flat | 3010 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
361 | Flat | 3011 | 41.3 | 3.39 | 444.5532 | 36.49 | 44.69 | 481.0432 | 750 | 288.9596
362 | Flat | 3012 | 41.9 | 3.57 | 451.0116 | 38.4275 | 45.47 | 489.4391 | 760 | 293.1575
|  |  | 19280.57 | 1286.2 | 207536.0555 | 13844.6568 | 20566.77 | 221380.7123 | 346315
KASTURI VAN BUILDING NO 1
Carpet Area Saleable Area
Ground Floor Shops area= 728.32 sq.mt 15679 sq.ft
Office P2 floor area= 1723.85 sq.mt 18752 sq.ft
Office P2 floor area= 278.16 sq.mt 5240 sq.ft
Office P3 floor area= 890.01 sq.mt 11525 sq.ft
Total Flats area= 19288.1 sq.mt 346315 sq.ft
Grand Total 22900.94 sq.mt 397511 sq.ft

## Implementation and Revenue
Inflow bifurcation from unsold units
Particulars | Average RERA Carpet (SqF) | Numbr of units | Expected Rate PSF | Total Inflow
1BHK | 419 | 11 | 11000 | 5.0699
2 BHK | 623 | 13 | 11000 | 8.9089
2 Large BHK | 707 | 26 | 11000 | 20.2202
Shops | 243 | 6 | 25000 | 3.645
Offices | 1224 | 4 | 20000 | 9.792
Total estimated Cash inflow |  |  |  | 47.636
Indicative Implementation and Payment Schedule for Sale Building
Sr No | Timeline | Stages | Payment Schedule | Cumulative Payment Schedule | Financial Year
1 | 2023-03-01 | Excavation & Piling | 10% | 10% | 2022-2023
2 | 2023-06-01 | Plinth | 15% | 25% | 2023-2024
3 | 2023-09-01 | 3rd Slab | 5% | 30% | 2023-2024
4 | 2023-12-01 | 6th Slab | 5% | 35% | 2023-2024
5 | 2024-03-01 | 9th Slab | 5% | 40% | 2023-2024
6 | 2024-06-01 | 12th Slab | 5% | 45% | 2024-2025
7 | 2024-09-01 | 15th Slab | 5% | 50% | 2024-2025
8 | 2024-12-01 | Finishing | 5% | 55% | 2024-2025
9 | 2025-03-01 | Internal Finishing | 10% | 65% | 2024-2025
10 | 2025-06-01 | Project Complete | 10% | 75% | 2025-2026
11 | 2025-09-01 | Ready to Occupy | 25% | 100% | 2025-2026
12 | 2025-12-01 | Ready to Occupy | 0% | 100% | 2025-2026
13 | 2026-03-01 | Ready to Occupy | 0% | 100% | 2025-2026
14 | 2026-06-01 | Ready to Occupy | 0% | 100% | 2026-2027
15 | 2026-09-01 |  | 0% | 100% | 2026-2027
16 | 2026-12-01 |  | 0% | 100% | 2026-2027
17 | 2027-03-01 |  | 0% | 100% | 2026-2027
18 | 2027-06-01 |  | 0% | 100% | 2027-2028
19 | 2027-09-01 |  | 0% | 100% | 2027-2028
20 | 2027-12-01 |  | 0% | 100% | 2027-2028
21 | 2028-03-01 |  | 0% | 100% | 2027-2028
22 | 2028-06-01 |  | 0% | 100% | 2028-2029
23 | 2028-09-01 |  | 0% | 100% | 2028-2029
24 | 2028-12-01 |  | 0% | 100% | 2028-2029
25 | 2029-03-01 |  | 0% | 100% | 2028-2029
26 | 2029-06-01 |  | 0% | 100% | 2029-2030
27 | 2029-09-01 |  | 0% | 100% | 2029-2030
28 | 2029-12-01 |  | 0% | 100% | 2029-2030
29 | 2030-03-01 |  | 0% | 100% | 2029-2030

## Inflow Calculation
Cashflow Timeline
Sr No | Timeline | Financial Year | Construction Stage | 1BHK | 2 BHK | 2 Large BHK | Shops | Offices | Total Area Sold | Cumulative Area sold | Booking Value | Cum. Sale Value | Payment Due | Cum. Payment Due | Booking Amount due | Receivables from Area Sold
1 | 2023-03-01 | 2022-2023 | Excavation & Piling | [5 empty] | 0 | 0 | 0 | 0 | 10% | 10% | 0 | 0
2 | 2023-06-01 | 2023-2024 | Plinth | [5 empty] | 0 | 0 | 0 | 0 | 15% | 25% | 0 | 0
3 | 2023-09-01 | 2023-2024 | 3rd Slab | 1 | 0 |  | 0 |  | 419 | 419 | 0.4609 | 0.4609 | 5% | 30% | 0.13827 | 0.13827
4 | 2023-12-01 | 2023-2024 | 6th Slab | 2 | 1 | 1 | 1 |  | 2411 | 2830 | 2.9923 | 3.4532 | 5% | 35% | 1.2086 | 1.0703
5 | 2024-03-01 | 2023-2024 | 9th Slab | 2 | 2 | 2 | 1 |  | 3741 | 6571 | 4.4553 | 7.9085 | 5% | 40% | 3.1634 | 1.9548
6 | 2024-06-01 | 2024-2025 | 12th Slab | 1 | 2 | 2 | 2 |  | 3565 | 10136 | 4.6019 | 12.5104 | 5% | 45% | 5.6297 | 2.4663
7 | 2024-09-01 | 2024-2025 | 15th Slab | 1 | 2 | 1 |  |  | 2372 | 12508 | 2.6092 | 15.1196 | 5% | 50% | 7.5598 | 1.9301
8 | 2024-12-01 | 2024-2025 | Finishing | 3 | 1 | 2 | 0 |  | 3294 | 15802 | 3.6234 | 18.743 | 5% | 55% | 10.3086 | 2.7489
9 | 2025-03-01 | 2024-2025 | Internal Finishing | 1 |  |  |  |  | 419 | 16221 | 0.4609 | 19.2039 | 10% | 65% | 12.4825 | 2.1739
10 | 2025-06-01 | 2025-2026 | Project Complete | [5 empty] | 0 | 16221 | 0 | 19.2039 | 10% | 75% | 14.4029 | 1.9204
11 | 2025-09-01 | 2025-2026 | Ready to Occupy |  |  | 2 | 1 |  | 1657 | 17878 | 2.1629 | 21.3668 | 25% | 100% | 21.3668 | 6.9639
12 | 2025-12-01 | 2025-2026 | Ready to Occupy |  | 1 | 6 |  |  | 4865 | 22743 | 5.3515 | 26.7183 | 0% | 100% | 26.7183 | 5.3515
13 | 2026-03-01 | 2025-2026 | Ready to Occupy |  | 2 | 5 | 1 | 4 | 9920 | 32663 | 15.6586 | 42.3769 | 0% | 100% | 42.3769 | 15.6586
14 | 2026-06-01 | 2026-2027 | Ready to Occupy |  | 2 | 5 |  |  | 4781 | 37444 | 5.2591 | 47.636 | 0% | 100% | 47.636 | 5.2591
15 | 2026-09-01 | 2026-2027 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
16 | 2026-12-01 | 2026-2027 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
17 | 2027-03-01 | 2026-2027 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
18 | 2027-06-01 | 2027-2028 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
19 | 2027-09-01 | 2027-2028 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
20 | 2027-12-01 | 2027-2028 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
21 | 2028-03-01 | 2027-2028 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
22 | 2028-06-01 | 2028-2029 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
23 | 2028-09-01 | 2028-2029 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
24 | 2028-12-01 | 2028-2029 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
25 | 2029-03-01 | 2028-2029 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
26 | 2029-06-01 | 2029-2030 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
27 | 2029-09-01 | 2029-2030 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
28 | 2029-12-01 | 2029-2030 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
29 | 2030-03-01 | 2029-2030 | 0 | [5 empty] | 0 | 37444 | 0 | 47.636 | 0% | 100% | 47.636 | 0
|  |  |  | 11 | 13 | 26 | 6 | 4 | [7 empty] | 47.636 | 17.3395

## Cashflow
Shreeji Angarika
| Financial Year | 2022-2023 | 2023-2024 | 2023-2024 | 2023-2024 | 2023-2024 | 2024-2025 | 2024-2025 | 2024-2025 | 2024-2025 | 2025-2026 | 2025-2026 | 2025-2026 | 2025-2026 | 2026-2027 | 2026-2027 | 2026-2027 | 2026-2027 | 2027-2028 | 2027-2028 | 2027-2028 | 2027-2028 | 2028-2029 | 2028-2029 | 2028-2029 | 2028-2029 | 2029-2030 | 2029-2030 | 2029-2030 | 2029-2030
|  | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-01 | 2024-03-01 | 2024-06-01 | 2024-09-01 | 2024-12-01 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-01 | 2026-06-01 | 2026-09-01 | 2026-12-01 | 2027-03-01 | 2027-06-01 | 2027-09-01 | 2027-12-01 | 2028-03-01 | 2028-06-01 | 2028-09-01 | 2028-12-01 | 2029-03-01 | 2029-06-01 | 2029-09-01 | 2029-12-01 | 2030-03-01 | Total
Actual
Opening Balance |  |  | 0 | 0.22887 | 0.020082 | 0.037432 | 0.043275 | 0.037205 | 0.2646 | 0.48035 | 0.67139 | 0.83134 | 4.7607 | 5.6992 | 17.0663 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554
Booking from Sold Units | [30 empty] | 0
Bookngs from Unsold Units |  | 0 | 0 | 0.13827 | 1.0703 | 1.9548 | 2.4663 | 1.9301 | 2.7489 | 2.1739 | 1.9204 | 6.9639 | 5.3515 | 15.6586 | 5.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.636
Total Inflow | 47.636 | 0 | 0 | 0.13827 | 1.0703 | 1.9548 | 2.4663 | 1.9301 | 2.7489 | 2.1739 | 1.9204 | 6.9639 | 5.3515 | 15.6586 | 5.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.636
Land Acquisition Cost | 5.25 | 1.94 |  |  | 0.56 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | [20 empty] | 5.25
Rent and Hardship Compensation | 0 | 0 | [28 empty] | 0
Fungible FSI Premium | 0 | 0 | [28 empty] | 0
TDR | 1 | 0.2 |  |  |  | 0.8 | [24 empty] | 1
Approvals and Other Premiums | 1.87 | 1.87 | [24 empty] | 0 |  |  |  | 1.87
Construction Cost - Rehab Building | 0 | 0 | [28 empty] | 0
Construction Cost - Sale Building | 19.28 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0.78 | 0.5 | [19 empty] | 19.28
Selling and Marketing | 1.3 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | [15 empty] | 1.3
Professional Fees and Admin expenses | 1.35 | 0.4 | 0.08 | 0.08 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | [15 empty] | 1.35
Contingency | 0 | [29 empty] | 0
Finance Cost | 3.5706 | 0 | 0.091125 | 0.16706 | 0.243 | 0.31894 | 0.35235 | 0.38272 | 0.4131 | 0.43284 | 0.44044 | 0.3645 | 0.243 | 0.1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5706 | 0
DSRA | [8 empty] | 1 | 1 | 1.3 |  |  |  | -3.3 | [15 empty] | 0 | 0
Cash Outflow | 33.6206 | 4.41 | 3.2711 | 3.3471 | 3.983 | 4.8489 | 4.0724 | 3.1027 | 3.1331 | 2.9328 | 2.4104 | 0.5345 | 0.413 | 0.2915 | -3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.6206 | 0
Deficit / Surplus |  | -4.41 | -3.2711 | -2.9799 | -2.8926 | -2.8567 | -1.5628 | -1.1354 | -0.11965 | -0.27861 | 0.18134 | 7.2607 | 9.6992 | 21.0663 | 25.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554
Fund-flow
NOF |  | 4.41 | 4.41 | 4.91 | 5.41 | 5.84 | 6.24 | 6.74 | 7.14 | 7.54 | 7.84 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 4.41
Addition in NOF |  |  | 0.5 | 0.5 | 0.43 | 0.4 | 0.5 | 0.4 | 0.4 | 0.3 | 0.4 | [19 empty] | 3.83
NOF Closing Balance |  | 4.41 | 4.91 | 5.41 | 5.84 | 6.24 | 6.74 | 7.14 | 7.54 | 7.84 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24
Loan Disbursed |  | 0 | 3 | 2.5 | 2.5 | 2.5 | 1.1 | 1 | 1 | 0.65 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 14.5
Loan Repaid |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5 | -4 | -4 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.5
Net fund-flow |  | 4.41 | 3.5 | 3 | 2.93 | 2.9 | 1.6 | 1.4 | 0.6 | 0.95 | 0.65 | -2.5 | -4 | -4 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.44
Closing Balance |  | 0 | 0.22887 | 0.020082 | 0.037432 | 0.043275 | 0.037205 | 0.2646 | 0.48035 | 0.67139 | 0.83134 | 4.7607 | 5.6992 | 17.0663 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554 | 21.4554
Loan Outstanding |  | 0 | 3 | 5.5 | 8 | 10.5 | 11.6 | 12.6 | 13.6 | 14.25 | 14.5 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bank Finance : NOF |  | 0 | 0.611 | 1.0166 | 1.3699 | 1.6827 | 1.7211 | 1.7647 | 1.8037 | 1.8176 | 1.7597 | 1.4563 | 0.97087 | 0.48544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bank Finance to Peak Deficit Ratio |  | 0% | 39.06% | 51.59% | 59.02% | 63.98% | 64.54% | 65.94% | 70.73% | 73.05% | 75.03% | 99.46% | 338.2% | -21.39% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Loan to Construction % |  | 0% | 100% | 91.67% | 88.89% | 87.5% | 77.33% | 74.12% | 75.56% | 75.88% | 75.21% | 62.24% | 41.49% | 20.75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Loan Disbursement % : Promoter Margin % |  | 0 | 0.34722 | 0.57773 | 0.77846 | 0.95623 | 0.97804 | 1.0028 | 1.025 | 1.0329 | 1 | 0.82759 | 0.55172 | 0.27586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Working
Particulars | Figures | Unit | Remark
Residential
Total Built-up Area | 0 | Sq. ft. | As per layout Plan
Total Carpet Area | 37552.6897 | Sq. ft. | As per Inventory Details provided by the company
Total Booked Carpet Area | 0 | Sq. ft.
Number of Booked Apartment | 0
Total unbooked carpet area
Residential | 31200.3151 | Sq. ft.
654
Commercial | 6352.3746 | Sq. ft.
9
Average selling price
Residential | 13000 | Per sq feet | RKA Research
Commercial | 22000 | Per sq feet | RKA Research
Parking | 0 | per parking | RKA Research
Amount Received from sold units | 0 | INR. Cr. | Provided by company
Amount to be received from Sold Units | 47.636 | Cr. | Provided by company
Construction completion | 0% | % | As per Company
| 0 | Sq. ft. | As per Company
Balance to be constructed | 100% |  | As per Company
| 0 | Sq. ft. | As per Company
Rate of Construction | 0 | per Sq. ft. | RKA Analysis
Inflation on construction cost | 3% | per year | RKA Research
Amount to be incurred on Completion of project | 33.6206 | INR. Cr. | RKA Research
Discount Rate | 15% |  | RKA Research
Inflation on sale price year | 7% | % | RKA Research
|  |  |  | 50% | 50%
Particulars | FY-23 | FY-24 | FY-25 | FY-26 | FY-27 | Total
Outflow
Amount to be incurred on completion of project (In Rs. Cr.) | 330.6822
Phase | 0% | 15% | 25% | 35% | 25% | 100%
Cost to be incurred in phase-Super Structure (INR Cr.) | 9 | 9 | 1.28 | 0 | 73.962 | 93.242
Cost to be incurred in phase-Sub Structure (Cr.) | 0 | 0.83212 | 3.3285 | 4.1606 | 0 | 8.3212
Loan Interest Repayment (Cr.) | 0 | 0 | 0 | 100.9626 | 100.9626 | 201.9253
Total Outflow -A (INR Cr.) | 9 | 9.8321 | 4.6085 | 105.1232 | 174.9247 | 303.4885
Inflow
Residential
Total unbooked carpet area (sq. ft.) | 37552.6897 |  |  |  |  | 37552.6897
Selling Phase (%) | 0% | 15% | 20% | 30% | 35% | 100%
Total area to be sold in phase (sq feet) | 0 | 0 | 0 | 0 | 0 | 0
Average market rate (Rs. Per sq feet)(residential) | 13000 | 13910 | 14883.7 | 15925.559 | 17040.3481
Average market rate (Rs. Per sq feet)(commercial) | 22000 | 23540 | 25187.8 | 26950.946 | 28837.5122
Amount to be Received (upfront) | 0 | 65099457.4979 | 92875226.0303 | 149064737.7786 | 186082480.9937 | 493121902.3005
Amount to be Received (on possession) |  |  |  | 0 | 0 | 0
Sale consideration (In Rs. Cr.) | 0 | 65099457.4979 | 92875226.0303 | 149064737.7786 | 186082480.9937 | 493121902.3005
Commercial
Total unbooked carpet area (sq feet) | 9
Selling Phase (%) | 0 | 20% | 20% | 30% | 30% | 100%
Total area to be sold in phase (sq feet) | 0 | 0 | 0 | 0 | 0
Average market rate (Rs. Per sq feet) | 0 | 0 | 0 | 0 | 0
Amount to be Received (upfront) | 0 | 0 | 0 | 0 | 0
Amount to be Received (on possession) |  |  |  | 0 | 0
Sale consideration (In Rs. Cr.) | 0 | 0 | 0 | 0 | 0 | 0
Receiving Phase | 0% | 0% | 0% | 45% | 55% | 100%
Amount to be Received (in Phases) | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Discount Period | 0.5 | 1.5 | 2.5 | 3.5 | 4.5
Discount Factor | 0.9325 | 0.81087 | 0.70511 | 0.61314 | 0.53316
| #REF! | #REF! | #REF! | #REF! | #REF!
Net Present Value NPV (Rs. Cr.) | #REF!

## Assessment Tables
Sr No | Quarter | Implementation Schedule | Financial Year | Physical Progress of the project | Physical Progess % | Cumulative Disbursement | Disbursement % | Dibursemnt % to Physical Progress | Committed Margin | Committed Margin % | D/E Ratio | Project Deficit | Promoter Contribution to Physical Defcit % | Loan to Physical Defcit % | Cumulative Promoters Contribution | Promoter % B/A | Loan D/A
1 | 2023-03-01 | Excavation & Piling | 2022-2023 | 0 | 0% | 0 | 0% | #DIV/0! | 4.41 | 53.52% | 0 | -4.41 | 100% | 0% | 4.41 | -100% | 0%
2 | 2023-06-01 | Plinth | 2023-2024 | 3 | 15.56% | 3 | 20.69% | 100% | 4.91 | 59.59% | 0.611 | -7.6811 | 63.92% | 39.06% | 4.91 | -63.92% | -39.06%
3 | 2023-09-01 | 3rd Slab | 2023-2024 | 6 | 31.12% | 5.5 | 37.93% | 91.67% | 5.41 | 65.66% | 1.0166 | -10.661 | 50.75% | 51.59% | 5.41 | -50.75% | -51.59%
4 | 2023-12-01 | 6th Slab | 2023-2024 | 9 | 46.68% | 8 | 55.17% | 88.89% | 5.84 | 70.87% | 1.3699 | -13.5536 | 43.09% | 59.02% | 5.84 | -43.09% | -59.02%
5 | 2024-03-01 | 9th Slab | 2023-2024 | 12 | 62.24% | 10.5 | 72.41% | 87.5% | 6.24 | 75.73% | 1.6827 | -16.4103 | 38.02% | 63.98% | 6.24 | -38.02% | -63.98%
6 | 2024-06-01 | 12th Slab | 2024-2025 | 15 | 77.8% | 11.6 | 80% | 77.33% | 6.74 | 81.8% | 1.7211 | -17.9731 | 37.5% | 64.54% | 6.74 | -37.5% | -64.54%
7 | 2024-09-01 | 15th Slab | 2024-2025 | 17 | 88.17% | 12.6 | 86.9% | 74.12% | 7.14 | 86.65% | 1.7647 | -19.1085 | 37.37% | 65.94% | 7.14 | -37.37% | -65.94%
8 | 2024-12-01 | Finishing | 2024-2025 | 18 | 93.36% | 13.6 | 93.79% | 75.56% | 7.54 | 91.5% | 1.8037 | -19.2282 | 39.21% | 70.73% | 7.54 | -39.21% | -70.73%
9 | 2025-03-01 | Internal Finishing | 2024-2025 | 18.78 | 97.41% | 14.25 | 98.28% | 75.88% | 7.84 | 95.15% | 1.8176 | -19.5068 | 40.19% | 73.05% | 7.84 | -40.19% | -73.05%
10 | 2025-06-01 | Project Complete | 2025-2026 | 19.28 | 100% | 14.5 | 100% | 75.21% | 8.24 | 100% | 1.7597 | -19.3254 | 42.64% | 75.03% | 8.24 | -42.64% | -75.03%
11 | 2025-09-01 | Ready to Occupy | 2025-2026 | 19.28 | 100% | 12 | 82.76% | 62.24% | 8.24 | 100% | 1.4563 | -12.0647 | 68.3% | 99.46% | 8.24 | -68.3% | -99.46%
12 | 2025-12-01 | Ready to Occupy | 2025-2026 | 19.28 | 100% | 8 | 55.17% | 41.49% | 8.24 | 100% | 0.97087 | -2.3655 | 348.3% | 338.2% | 8.24 | -348.3% | -338.2%
13 | 2026-03-01 | Ready to Occupy | 2025-2026 | 19.28 | 100% | 4 | 27.59% | 20.75% | 8.24 | 100% | 0.48544 | 18.7008 | -44.06% | -21.39% | 8.24 | 44.06% | 21.39%
14 | 2026-06-01 | Ready to Occupy | 2026-2027 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 44.1562 | -18.66% | 0% | 8.24 | 18.66% | 0%
15 | 2026-09-01 | 0 | 2026-2027 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 65.6116 | -12.56% | 0% | 8.24 | 12.56% | 0%
16 | 2026-12-01 | 0 | 2026-2027 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 87.0671 | -9.464% | 0% | 8.24 | 9.464% | 0%
17 | 2027-03-01 | 0 | 2026-2027 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 108.5225 | -7.593% | 0% | 8.24 | 7.593% | 0%
18 | 2027-06-01 | 0 | 2027-2028 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 129.9779 | -6.34% | 0% | 8.24 | 6.34% | 0%
19 | 2027-09-01 | 0 | 2027-2028 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 151.4333 | -5.441% | 0% | 8.24 | 5.441% | 0%
20 | 2027-12-01 | 0 | 2027-2028 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 172.8887 | -4.766% | 0% | 8.24 | 4.766% | 0%
21 | 2028-03-01 | 0 | 2027-2028 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 194.3442 | -4.24% | 0% | 8.24 | 4.24% | 0%
22 | 2028-06-01 | 0 | 2028-2029 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 215.7996 | -3.818% | 0% | 8.24 | 3.818% | 0%
23 | 2028-09-01 | 0 | 2028-2029 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 237.255 | -3.473% | 0% | 8.24 | 3.473% | 0%
24 | 2028-12-01 | 0 | 2028-2029 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 258.7104 | -3.185% | 0% | 8.24 | 3.185% | 0%
25 | 2029-03-01 | 0 | 2028-2029 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 280.1658 | -2.941% | 0% | 8.24 | 2.941% | 0%
26 | 2029-06-01 | 0 | 2029-2030 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 301.6213 | -2.732% | 0% | 8.24 | 2.732%
27 | 2029-09-01 | 0 | 2029-2030 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 323.0767 | -2.55% | 0% | 8.24 | 2.55%
28 | 2029-12-01 | 0 | 2029-2030 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 344.5321 | -2.392% | 0% | 8.24 | 2.392%
29 | 2030-03-01 | 0 | 2029-2030 | 19.28 | 100% | 0 | 0% | 0% | 8.24 | 100% | 0 | 365.9875 | -2.251% | 0% | 8.24 | 2.251%
Formulas:
Implementation Schedule = VLOOKUP([Quarter],'Implementation and Revenue'!$D12:E40,2,FALSE)

## Loan - SBI
0.1215
Sr No. | Financial Year | Quarter | Disbursement | Repayment | Interest | POS
1 | 2022-2023 | 2023-03-01 | 0 | 0 | 0 | 0
2 | 2023-2024 | 2023-06-01 | 3 | 0 | 0.091125 | 3
3 | 2023-2024 | 2023-09-01 | 2.5 | 0 | 0.16706 | 5.5
4 | 2023-2024 | 2023-12-01 | 2.5 | 0 | 0.243 | 8
5 | 2023-2024 | 2024-03-01 | 2.5 | 0 | 0.31894 | 10.5
6 | 2024-2025 | 2024-06-01 | 1.1 | 0 | 0.35235 | 11.6
7 | 2024-2025 | 2024-09-01 | 1 | 0 | 0.38272 | 12.6
8 | 2024-2025 | 2024-12-01 | 1 | 0 | 0.4131 | 13.6
9 | 2024-2025 | 2025-03-01 | 0.65 | 0 | 0.43284 | 14.25
10 | 2025-2026 | 2025-06-01 | 0.25 | 0 | 0.44044 | 14.5
11 | 2025-2026 | 2025-09-01 | 0 | -2.5 | 0.3645 | 12
12 | 2025-2026 | 2025-12-01 | 0 | -4 | 0.243 | 8
13 | 2025-2026 | 2026-03-01 | 0 | -4 | 0.1215 | 4
14 | 2026-2027 | 2026-06-01 | 0 | -4 | 0 | 0
15 | 2026-2027 | 2026-09-01 | 0 | 0 | 0 | 0
16 | 2026-2027 | 2026-12-01 | 0 | 0 | 0 | 0
17 | 2026-2027 | 2027-03-01 | 0 | 0 | 0 | 0
18 | 2027-2028 | 2027-06-01 | 0 | 0 | 0 | 0
19 | 2027-2028 | 2027-09-01 | 0 | 0 | 0 | 0
20 | 2027-2028 | 2027-12-01 | 0 | 0 | 0 | 0
21 | 2027-2028 | 2028-03-01 | 0 | 0 | 0 | 0
22 | 2028-2029 | 2028-06-01 | 0 | 0 | 0 | 0
23 | 2028-2029 | 2028-09-01 | 0 | 0 | 0 | 0
24 | 2028-2029 | 2028-12-01 | 0 | 0 | 0 | 0
25 | 2028-2029 | 2029-03-01 | 0 | 0 | 0 | 0
26 | 2029-2030 | 2029-06-01 | 0 | 0 | 0 | 0
27 | 2029-2030 | 2029-09-01 | 0 | 0 | 0 | 0
28 | 2029-2030 | 2029-12-01 | 0 | 0 | 0 | 0
29 | 2029-2030 | 2030-03-01 | 0 | 0 | 0 | 0
Total |  |  | 14.5 | -14.5 | 3.5706

## FACR
Sr No | Calculations | Amount in Cr
A | Realizable Value of the land | 72.48
B | Cost of approvals at peak disbursement level | 1.87
C | Cost of Construction at Peak Disbursement Level | 19.28 |  | 49.294
D | Advances at Peak Disbursement Level | 47.636 | 44.336
E | DSRA | 3.3
F = A+B+C-D+E | Net Security Available | 49.294
G | Peak Disbursement | 14.5
H = F/G | FACR | 3.3996

## Annualised Cashflow
Particulars | 2022-23 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030
Advance from the bookings | 0 | 3.1634 | 9.3191 | 29.8944 | 5.2591 | 0 | 0 | 0
Land Acquisition | 0 | 1.11 | 2.2 | 0 | 0 | 0 | 0 | 0
Construction Expenses - Outflow | 0 | 12.8 | 6.78 | 0.5 | 0 | 0 | 0 | 0
Selling and Administration Cost | 0 | 0.72 | 0.68 | 0.68 | 0.17 | 0 | 0 | 0
Contingencies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finance Cost | 0 | 0.82012 | 1.581 | 1.1694 | 0 | 0 | 0 | 0
DSRA | 0 | 0 | 2 | 1.3 | -3.3 | 0 | 0 | 0
Area Sold | 0 | 6571 | 9650 | 16442 | 4781 | 0 | 0 | 0
% Area Sold | 0% | 17.55% | 25.77% | 43.91% | 12.77% | 0% | 0% | 0%
Project Completion | 0% | 63.75% | 97.51% | 100% | 100% | 100% | 100% | 100%
Sale Value | 0 | 7.9085 | 11.2954 | 23.173 | 5.2591 | 0 | 0 | 0
Cumulative Direct Cost | 0 | 15.4501 | 26.6911 | 29.0406 | 29.2106 | 29.2106 | 29.2106 | 29.2106
Promoter contribution | 4.41 | 6.24 | 7.84 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24
Loan Disbursement | 0 | 10.5 | 3.75 | 0.25 | 0 | 0 | 0 | 0
Cumulative Loan Disbursement | 0 | 10.5 | 14.25 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
Loan Repayment | 0 | 0 | 0 | -10.5 | -4 | 0 | 0 | 0
Cumulative Loan Repayment | 0 | 0 | 0 | -10.5 | -14.5 | -14.5 | -14.5 | -14.5
Loan Outstanding | 0 | 10.5 | 14.25 | 4 | 0 | 0 | 0 | 0

## CMA
Operating Statement
Particulars | 2022-23 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030
Revenue from the project | 0 | 0 | 0 | 42.3769 | 5.2591 | 0 | 47.636 | 0
Costs
Land Acquisition Cost | 0 | 1.11 | 2.2 | 0 | 0 | 0 | 0 | 0
Construction Expenses - Outflow | 0 | 12.8 | 6.78 | 0.5 | 0 | 0 | 0 | 0
Selling and Administration Cost | 0 | 0.72 | 0.68 | 0.68 | 0.17 | 0 | 0 | 0
Finance Cost | 0 | 0.82012 | 1.581 | 1.1694 | 0 | 0 | 0 | 0
Opening WIP |  | 0 | 15.4501 | 26.6911 | 3.708 | 0 | 29.2106 | 0
Closing WIP | 0 | 15.4501 | 26.6911 | 3.708 | 0 | 29.2106 | 0 | 29.2106
Profit | 0 | 0 | 0 | 17.0443 | 1.3811 | 29.2106 | 18.4254 | 29.2106
Taxes | 0 | 0 | 0 | 5.1133 | 0.41432 | 8.7632 | 5.5276 | 8.7632
PAT | 0 | 0 | 0 | 11.931 | 0.96676 | 20.4474 | 12.8978 | 20.4474
Balance Sheet
Current Liabilities
CC
Advance from Customers | 0 | 3.1634 | 12.4825 | 0 | 0 | 47.636 | 0 | 47.636
Provision for taxes | 0 | 0 | 0 | 5.1133 | 5.5276 | 14.2908 | 19.8184 | 28.5816
Loan to be repaid in next 12 months | 0 | 0 | 10.5 | 4 | 0 | 0 | 0 | 0
Term Liabilities
Term Loan Outstanding | 0 | 10.5 | 3.75 | 0 | 0 | 0 | 0 | 0
USL From Promoters
TNW
Equity Capital | 4.41 | 6.24 | 7.84 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24
Reserves and Surplus | 0 | 0 | 0 | 11.931 | 12.8978 | 33.3452 | 46.243 | 66.6904
Total Liabilities | 4.41 | 19.9034 | 34.5725 | 29.2843 | 26.6654 | 103.512 | 74.3014 | 151.148
Current Assets
Cash and Bank Balance | 4.41 | 4.4533 | 5.8814 | 22.2763 | 26.6654 | 26.6654 | 26.6654 | 26.6654
DSRA | 0 | 0 | 2 | 3.3 | 0 | 0 | 0 | 0
Receivables from Sold Units | 0 | 0 | 0 | 1.4211e-14 | 2.1316e-14 | 0 | 2.1316e-14 | 0
Work in Process | 0 | 15.4501 | 26.6911 | 3.708 | 0 | 29.2106 | 0 | 29.2106
Finished Goods
Total Assets | 4.41 | 19.9034 | 34.5725 | 29.2843 | 26.6654 | 55.876 | 26.6654 | 55.876
Mismatch | 0 | 0 | 0 | 0 | 0 | -47.636 | -47.636 | -95.272
Cash Buffer Ratio | 2022-23 | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | 2027-2028 | 2028-2029 | 2029-2030 | Total
Net Cashflow | 0 | -11.4666 | -0.34087 | 28.7144 | 5.0891 | 0 | 0 | 0 | 21.996
Debt Service Obligation | 0 | 0.82012 | 1.581 | 11.6694 | 4 | 0 | 0 | 0 | 18.0706
Cashflow from promoters | 4.41 | 1.83 | 1.6 | 0.4 | 0 | 0 | 0 | 0 | 8.24
Release of Bank Debt | 0 | 10.5 | 3.75 | 0.25 | 0 | 0 | 0 | 0 | 14.5
Total Cashflow from Promoters and Bank Loan | 4.41 | 12.33 | 5.35 | 0.65 | 0 | 0 | 0 | 0 | 22.74
Cash Surplus | 4.41 | 5.2734 | 9.4624 | 35.2458 | 27.3654 | 26.6654 | 26.6654 | 26.6654 | 44.736
Cash Buffer Ratio | #DIV/0! | 6.43 | 5.985 | 3.0203 | 6.8414 | #DIV/0! | #DIV/0! | #DIV/0! | 2.4756

## Residual Method
RESIDUAL WITHOUT NPV FOR FILE NO. VIS(2023-24)-PL361-291-459
Particulars | Plot Area (Sq. mtr.) | Permissible built up area (Sq. mtr.) | Carpet Area (Sq. Ft.) | Proposed BUA to be Constructed (Sq. ft.) | SR. NO. | Category | Floor | RERA CARPET (Sq. mtr.) | SBUA (sq. ft.) | CARPET AREA (sq. ft.)
Residential Area | 1003.07 | 4524.99 | 31200.3151 | 54152.6076 | 1 | Shops | G | 134.79 | 3220 | 1450.8796
Commercial Shop | 5030.9 |  | 4901.495 |  | 2 | Offices | 1 & 2 | 455.36 | 9804 | 4901.495
Commercial Office | 10.764 |  | 1450.8796 |  | 3 | Residential | 3 to 15 | 2898.58 | 52967 | 31200.3151
TOTAL | 1013.834 | 4524.99 | 37552.6897 | 54152.6076 | Total |  |  | 3488.73 | 65991 | 37552.6897 |  |  |  | #REF!
* note: BUA is included stilt, refuge & recreational area
RATE ESCALATION PER SQ. FT. ON CARPET AREA
REVENUE FROM SALE OF INVENTORY | 534743857.5289 |  |  |  | Year | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28
Construction cost | 162051109.6406 |  |  |  | Rate of escalation |  | 5% | 5% | 5% | 5%
PROJECT COST ACCORDING TO THE CLIENT(including soft cost) |  |  | 19.28 |  | RESIDENTIAL | 12000 | 12600 | 13230 | 13891.5 | 14586.075
TDR | 10000000 |  | 3560.3087 |  | COMMERCIAL SHOP | 22000 | 23100 | 24255 | 25467.75 | 26741.1375
Approvals and Other Premiums | 18700000 |  |  |  | OFFICE | 15000 | 15750 | 16537.5 | 17364.375 | 18232.5938
Selling and Marketing | 13000000 |  |  |  | Sale out Phasing
Professional Fees and Admin expenses | 13500000 |  |  |  | Year | 2023-24 | 2024-25 | 2025-26 | 2023-27 | 2023-28 | Total
Residual Project Value as on the date of valution | 317492747.8883 |  |  |  | RESIDENTIAL | 20% | 40% | 40% | 0 | 0 | 100% | 12%
[5 empty] | COMMERCIAL SHOP | 20% | 40% | 40% | 0 | 0 | 100%
[5 empty] | OFFICE | 20% | 40% | 40% | 0 | 0 | 100%
Inflow (in Cr.)
[5 empty] | Income from sale (in Cr.) | 10.08 | 21.168 | 22.2264 | 0 | 0 | 53.4744
[5 empty] | Outflow (in Cr.) | [5 empty] | 0 |  | 55000
[5 empty] | Land Acquisition Cost | 2.5 | 2.2 | 0.55
[5 empty] | Construction cost | 9 | 9 | 1.28 | 0 | 0 | 19.28
[5 empty] | TDR | 0.2 | 0.8 |  |  |  | 1
[5 empty] | Approvals and Other Premiums | 1.87 |  |  |  |  | 1.87
[5 empty] | Selling and Marketing | 0.3 | 0.4 | 0.5 | 0 |  | 1.2
[5 empty] | Professional Fees and Admin expenses | 0.64 | 0.29 | 0.42 |  |  | 1.35
[5 empty] | Total (In cr.) | 14.51 | 12.69 | 2.75 | 0 | 0 | 29.95
[5 empty] | Net Cash Flow | -4.43 | 8.478 | 19.4764 | 0 | 0 | 23.5244
[5 empty] | Discount factor | 12%
[5 empty] | Time Factor | 2024-03-31 | 2025-03-31 | 2026-03-31
|  |  |  | 2023-10-04 |  | -4.1905 | 7.1604 | 14.6871
[5 empty] | Net Present Value (in Cr.) | 17.657
176600000
150110000
[6 empty] | 132450000 |  |  | =
`=cf/(1+wacc)^t
Formulas:
Floor = EDATE([Category],12)
RERA CARPET (Sq. mtr.) = EDATE([Floor],12)

## Sheet1
| 1984.25 | -4034.75 | 6134.25 | -4083.75
| B | A | D | V
7124.25 | 5140 | 11159 | 990 | 11208 | 28497

## Sheet2
SR. NO. | Category | Floor | Rera Carpet area (Sq.mtr.) | Super built up area (sq. ft.) | Carpet area (sq. ft.)
1 | Shops | G | 134.79 | 3220 | 1450.8796
2 | Offices | 1 & 2 | 455.36 | 9804 | 4901.495
3 | Residential | 3 to 15 | 2898.58 | 52967 | 31200.3151
Total |  |  | 3488.73 | 65991 | 37552.6897

## Cost of construction
| BUA | 54152.6076 | sq. ft.
Sr. No. | Description | Average Cost for Residential (per sq.ft.) | T1 = Average Cost x BUA Area
i | Basic structure construction cost | 1550 | 83936541.78
ii | Project sanctioning/ approval, Architectural, structural stability Fees, etc. | 0 | 0
iii | Finishing Work (Flooring, white washing, fittings & fixtures, etc.) | 500 | 27076303.8
iv | MEP Works (Mechanical, Electrical & Plumbing) | 300 | 16245782.28
v | Internal & External Development charges | 400 | 21661043.04 | Construction cost inflation | 3%
vi | Other expenses (Firefighting, intercom & etc.) @ 5% of total cost (i+ii+iii+iv+v) | 137.5 | 7445983.545
vii | Pre-operative & Administrative expenses @ 10% of total cost (i+ii+iii+iv+v+vi) | 0 | 0
Total |  | 2887.5 | 156365654.445 | 20% | 40% | 40%
|  |  | 15.6366 | 2023 | 2024 | 2025 | 2026 | 2027
|  |  |  | 15.6366 | 16.1057 | 16.5888 | 17.0865 | 17.5991
|  |  |  | 3.1273 | 6.4423 | 6.6355 | 0 | 0

## Bar Chart Construction - Sale (hidden)
Shreeji Angarika
Cost Break-up | % of Total Cost | Cost | 2020-03-01 | 2020-06-01 | 2020-09-01 | 2020-12-01 | 2021-03-01 | 2021-06-01 | 2021-09-01 | 2021-12-01 | 2022-03-01 | 2022-06-01 | 2022-09-01 | 2022-12-01 | 2023-03-01 | 2023-06-01 | 2023-09-01 | 2023-12-01 | Total
% |  |  | 100% | [15 empty] | 100%
Substructure Cost | 25.61% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  | 16.4% | 4.85% | 15% | 15% | 15% | 15% | 10% | 5% | 3.75% | [7 empty] | 100%
Brick Work / Block Work | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 20% | 15% | 20% | 15% | 10% | 10% | 2.5% | 5% | 2.5% | [5 empty] | 100%
RCC | 20% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 15% | 15% | 10% | 10% | 10% | 10% | 10% | 5% | 5% | 5% | 5% |  |  |  | 100%
POP, White wash and plastering | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 15% | 15% | 20% | 15% | 10% | 5% | 5% | 5% | 5% | 5% |  |  |  |  | 100%
Tiling (Italian Marble) | 5.22% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% |  |  |  | 0% | 15% | 15% | 20% | 15% | 20% | 5% |  | 5% | 5% | [5 empty] | 100%
Doors and Windows | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
% |  |  |  | 0% | 10% | 10% | 20% | 20% | 20% | 15% | 5% | [7 empty] | 100%
Water Supply, electrification and Sanitory work | 3% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
% | [8 empty] | 25% | 25% | 10% |  |  | 10% | 15% | 15% |  |  | 100%
Painting | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% | [9 empty] | 25% |  |  | 0% | 15% | 20% | 20% | 10% | 10% | 100%
Elevators | 6.168% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
% | [13 empty] | 40% | 25% | 25% | 5% | 5% | 100%
Fire Fighting | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
% | [14 empty] | 50% | 50% |  |  | 100%
Landscape and outside infrastructure | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
TOTAL | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!