## RA017F
| Vincom Cost Management Pvt Ltd. |  |  |  |  | Change
| CERTIFICATE OF PAYMENT No. 18 (PAYMENT AGAINST PBG) |  |  |  | Bill No.18 | FINAL BILL
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-10-19
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-10-14
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-09-23 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 750000
Amount Recommended : |  |  | 749998
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 20% Advance against ABG |  |  | 3000000 | 0 | 3000000 | 6
A2 | 65% Payment against delivery of material |  |  | 9750002 | 0 | 9750002
A3 | 10% Payment after Installation complete fit out |  |  | 1500000 | 0 | 1500000
A4 | 5% Payment shall be retained from each running bill same shall be release after completion work & 5% Against PBG |  |  |  | 749998 | 749998
| Sub Total - (A) |  |  | 14250002 | 749998 | 15000000
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 14250002 | 749998 | 15000000
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 14250002 | 749998 | 15000000
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 14250002 | 749998 | 15000000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA016F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 16 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-16
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-08-08
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-04
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-25 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 544018
Amount Recommended : |  |  | 353611.7
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 20% Advance against ABG |  |  | 3000000 | 0 | 3000000 | 6
A2 | 65% Payment against delivery of material ( 544018 @ 65%) |  |  | 9363886 | 353611.7 | 9717497.7
A3 | 5% Payment after Installation complete fit out |  |  |  | 0
A4 | 5% Payment shall be retained from each running bill same shall be release after completion work & 5% Against PBG
| Sub Total - (A) |  |  | 12363886 | 353611.7 | 12717497.7
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 12363886 | 353611.7 | 12717497.7
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 12363886 | 353611.7 | 12717497.7
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 12363886 | 353611.7 | 12717497.7
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA015F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 15 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-15
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-29
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-29
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-22 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1203901
Amount Recommended : |  |  | 1203901
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA023/16 |  |  | 13252075 | 1203901 | 14455976
A2
A3
| Sub Total - (A) |  |  | 13252075 | 1203901 | 14455976
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 13252075 | 1203901 | 14455976
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 13252075 | 1203901 | 14455976
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 13252075 | 1203901 | 14455976
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA014F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 14 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-14
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-27
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-26
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-21 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1014472
Amount Recommended : |  |  | 1014472
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA022/16 |  |  | 12237603 | 1014472 | 13252075
A2
A3
| Sub Total - (A) |  |  | 12237603 | 1014472 | 13252075
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 12237603 | 1014472 | 13252075
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 12237603 | 1014472 | 13252075
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 12237603 | 1014472 | 13252075
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA013F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 13 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-13
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-27
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-26
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-21 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1129934
Amount Recommended : |  |  | 1129934
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA021/16 |  |  | 11107669 | 1129934 | 12237603
A2
A3
| Sub Total - (A) |  |  | 11107669 | 1129934 | 12237603
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 11107669 | 1129934 | 12237603
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 11107669 | 1129934 | 12237603
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 11107669 | 1129934 | 12237603
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA012F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 12 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-12
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-27
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-26
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-20 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1484346
Amount Recommended : |  |  | 1484346
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA020/16 |  |  | 9623323 | 1484346 | 11107669
A2
A3
| Sub Total - (A) |  |  | 9623323 | 1484346 | 11107669
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 9623323 | 1484346 | 11107669
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 9623323 | 1484346 | 11107669
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 9623323 | 1484346 | 11107669
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA011F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 11 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-11
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-23
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-22
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-16 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 891888
Amount Recommended : |  |  | 891888
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA019/16 |  |  | 8731435 | 891888 | 9623323
A2
A3
| Sub Total - (A) |  |  | 8731435 | 891888 | 9623323
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 8731435 | 891888 | 9623323
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 8731435 | 891888 | 9623323
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 8731435 | 891888 | 9623323
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA010F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 10 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-10
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-23
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-22
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-16 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1295924
Amount Recommended : |  |  | 1295924
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA018/16 |  |  | 7435511 | 1295924 | 8731435
A2
A3
| Sub Total - (A) |  |  | 7435511 | 1295924 | 8731435
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 7435511 | 1295924 | 8731435
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 7435511 | 1295924 | 8731435
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 7435511 | 1295924 | 8731435
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA09F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 09 (MATERIAL SUPPLY) |  |  |  | Bill No. | M.S.-09
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-23
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-22
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-14 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1027788
Amount Recommended : |  |  | 1027788
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA017/16 |  |  | 6407723 | 1027788 | 7435511
A2
A3
| Sub Total - (A) |  |  | 6407723 | 1027788 | 7435511
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 6407723 | 1027788 | 7435511
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 6407723 | 1027788 | 7435511
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 6407723 | 1027788 | 7435511
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA08F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 08 (MATERIAL SUPPLY) |  |  |  | Bill No.8 | M.S.-08
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-15
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-14
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 3000000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-10 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 893881
Amount Recommended : |  |  | 893881
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA015/16 |  |  | 5513842 | 893881 | 6407723
A2
A3
| Sub Total - (A) |  |  | 5513842 | 893881 | 6407723
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 5513842 | 893881 | 6407723
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 5513842 | 893881 | 6407723
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 5513842 | 893881 | 6407723
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA07F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 07 (MATERIAL SUPPLY) |  |  |  | Bill No.7 | M.S.-07
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-15
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-14
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-11 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 937562
Amount Recommended : |  |  | 937562
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA016/16 |  |  | 4576280 | 937562 | 5513842
A2
A3
| Sub Total - (A) |  |  | 4576280 | 937562 | 5513842
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 4576280 | 937562 | 5513842
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 4576280 | 937562 | 5513842
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 4576280 | 937562 | 5513842
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA06F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 06 (MATERIAL SUPPLY) |  |  |  | Bill No.6 | M.S.-06
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-15
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-14
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-23 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 956970
Amount Recommended : |  |  | 956970
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA010/16 |  |  | 3619310 | 956970 | 4576280
A2
A3
| Sub Total - (A) |  |  | 3619310 | 956970 | 4576280
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 3619310 | 956970 | 4576280
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 3619310 | 956970 | 4576280
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  | 3619310 | 956970 | 4576280
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA05F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 05 (MATERIAL SUPPLY) |  |  |  | Bill No.5 | M.S.-05
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-06
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-05
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid |  | 50000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-27 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 878309
Amount Recommended : |  |  | 878309
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA012/16 |  |  |  | 878309
A2
A3
| Sub Total - (A) |  |  |  | 878309 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 878309 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  |  | 878309
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 878309
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA04F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (MATERIAL SUPPLY) |  |  |  | Bill No.4 | M.S.-04
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-01
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-01
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-17 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 1007579
Amount Recommended : |  |  | 1007579
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA011/16 |  |  |  | 1007579
A2
A3
| Sub Total - (A) |  |  |  | 1007579 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 1007579 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  |  | 1007579
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 1007579
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA03F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (MATERIAL SUPPLY) |  |  |  | Bill No.3 | M.S.-03
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-06-24
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-06-24
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-17 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 698812.2
Amount Recommended : |  |  | 984610
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY(INVOICE NO. JA009/16 |  |  |  | 984610
A2 | Non-Scheduled Work
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  |  | 984610 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 984610 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  |  | 984610
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 984610
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## Advance
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 (MOCK UP) |  |  |  | Bill No.1 | Mock up-01
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-06-08
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor |  | 2016-06-08
|  |  |  | Received by Vincom |  | 2016-06-08
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-26 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 3000000
Amount Recommended : |  |  | 3000000
Service Tax No. :
TIN NO
PAN of Contractor :
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work Done |  |  |  | 3000000
A2 | Non-Scheduled Work
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  |  | 3000000 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 3000000 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  |  | 3000000
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 3000000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 (MATERIAL SUPPLY) |  |  |  | Bill No.1 | M.S.-01
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-06-23
Contractor : | M/S JAMES ANDREW NEWTON ART EXPORTS PVT LIMTED |  |  | Date of 70% Certificate
Service : | SUPPLY FURNITURE AND INSTALLATION |  |  | Submission by Contractor |  | 2016-06-23
|  |  |  | Received by Vincom |  | 2016-06-23
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150043 |  | 2016-06-03 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 15000000 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-17 | Mobilisation Advance - Balance
Contractor's Invoice Amount :- |  |  | 698812.2
Amount Recommended : |  |  | 698812.2
Service Tax No. :
TIN NO |  |  | 08222553326
PAN of Contractor : |  |  | AAACJ5769Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | MATERIAL SUPPLY (INVOICE NO:- JA008/16 |  |  |  | 698812.2
A2 | Non-Scheduled Work
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  |  | 698812.2 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 698812.2 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  |  | 698812.2
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 698812.2
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02_70% (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 |  |  |  | Bill No. | RA-002
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-05-17
Contractor : | D. K. Buildcon Pvt. Ltd. |  |  | Date of Adhoc Certificate |  | 2016-05-17
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 2016-05-12
|  |  |  | Received by Vincom |  | 2016-05-12
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CS/PSJ/15-16/150019A | 03.02.2016 | Work Done Up to
Date of Agreement : |  |  | 03.03.2016
Completion Date :
Contract Value : |  |  | 58347484 | Mobilisation Paid |  | 5834750
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-05-01
Invoice Amount : |  |  | 3708968 | Material Advance Paid |  | 954858
Amount Recommended : |  |  | 1830159 | Material Advance Recovered
Service Tax No. : |  |  | AACCD6742P ST001
TIN No. |  |  | 6841325968
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  | 3250165 | 3702261 | 6952426
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  | 3250165 | 3702261 | 6952426
B | Add Taxes
B1 | Service Tax 14.50 % of 40% of (A)
B2 | W.C.T. i.e. VAT on Contracts 5.8% on (A) - Included in above |  |  |  | 214731.13
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 3916992.13
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Recover@ 5% of Rs. 6952426 Recovery @ |  |  |  | -347621.3
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Recovery Advance against Material at Site @ 80% of Value (Ref. S.A-01 ) |  |  |  | -954858
| Sub Total - (C) |  |  |  | -1302479.3
| Total - (A+B+C) |  |  |  | 2614512.83
| Allow an adhoc payment 70% against 2nd ra bill |  |  |  | 1830159
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A) |  |  |  | 0
D2 | W.C.T. @ 6% on (A) |  |  |  | 0
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  |  | 0
D4 | Labour Cess @ 1% on (A) |  |  |  | 0
| Sub Total - (D) |  |  |  | 0
| Net Amount Payable (A+B+C-D) |  |  |  | 1830159 | 0
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil singla |  | Vinay kumar | R.K.Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments

## RA01_F (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (70% Of Billed payment) |  |  |  | Bill No. | RA-003
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-06-05
Contractor : | D. K. Buildcon Pvt. Ltd. |  |  | Date of Adhoc Certificate |  | 2016-06-05
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 2016-06-02
Received by Vincom
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CS/PSJ/15-16/150019A | 03.02.2016 | Work Done Up to
Date of Agreement :
Completion Date :
Contract Value : |  |  | 58347484 | Mobilisation Paid |  | 5834750
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-06-01
Invoice Amount : |  |  | 4304809 | Material Advance Paid
Amount Recommended : |  |  | 1772396 | Material Advance Recovered
Service Tax No. : |  |  | AACCD6742P ST001
TIN No. |  |  | 6841325968
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  | 6697341 | -3447176 | 3250165
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate |  |  | 65704 | 0 | 65704
| Sub Total - (A) |  |  | 6763045 | -3447176 | 3315869
B | Add Taxes
B1 | Service Tax 5.8% of (A) |  |  | 392257 | -199937 | 192320
B2 | W.C.T. i.e. VAT on Contracts 5.25% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 7155302 | -3647113 | 3508189
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Payable 5% of Rs. 5,83,47,484 Recovery @ |  |  | 794954 | 5039796 | 5834750
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Advance against Material at Site @ 80% of Value |  |  |  | 954858 | 954858
| Sub Total - (C) |  |  | 794954 | 5994654 | 6789608
| Total - (A+B+C) |  |  | 7950256 | 2347541 | 10297797
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A) |  |  |  | 165793 | 165793
D2 | W.C.T. @ 5.25% on (A) |  |  |  | 174083 | 174083
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  |  | 202110 | 202110
D4 | Labour Cess @ 1% on (A) |  |  |  | 33159 | 33159
| Sub Total - (D) |  |  | 0 | 575145 | 575145
| Net Amount Payable (A+B+C-D) |  |  |  | 1772396 | 9722652
Recommended by
Vincom Cost Management Pvt. Ltd.
Sanjeev Kumar |  | Mukesh Gupta | Vinod Markanda
Approved by
Thapar University Patiala
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments