## INVOICE
Zamil Air Conditioners India Pvt.Ltd.
(Formerly known as ADVANTEC COILS PVT. LTD.)
SCO-20, 1st Floor, Kalgidhar Enclave,
Kalka Road, Baltana, Zirakpur,Punjab.
PROFORMA INVOICE
|  |  | Running Bill | Supplementery Bill
M/s. Thapar University |  |  | Invoice No. : T/PB/022/PI/10
Bhadson Road, Thapar Technology Campus |  |  | Date: 31.05.2019
Patiala-147004 (Punjab) |  |  | Job No.: T/PB/022
LOI Ref No.:-TU/CS/PSJ/15-16/150022 Dated 23.02.2016
Project:MEP Work for Boy's Hostel & Girl's Hostel at Thapar University, Patiala
Sr. No | Description | Previous Amount | Current Amount | Cummulative Amount
1 | Whereas due @100% against pro-rata Supply and Installation of Material at site as per attached annexure and MB Summary |  | 1540020.3743 | 1540020.3743
2 | Whereas due payable amount as per Extra work
Bank Information :-
Beneficiary's Name:- Zamil Air Conditionders India Pvt. Ltd.
Bank Name-DBS Bank Ltd.
Cash Credit A/c No-820200178723
IFSC Code-DBSSOIN0811
Branch-Capitol point, cannaught palace baba kharak singh marg, cannaught palce, new delhi- 110001, main branch - Mumbai
| Total Due Payment |  | 1540020.3743 | 1540020.3743
CIN No. :U74899DL1992PTC050416
PAN No. : AAACA0907F |  | for Zamil Air Conditioners India Pvt.Ltd
Service Tax No. :AAACA0907FSD008
TIN No. :'03112070603
Authorized Signatory
Regd. Office : 1St Floor,H-9/B-1,Mohan Cooperative Industrial Estate,Mathura Road,New Delhi-110044

## Summary Sch Item
THAPAR UNIVERSITY PATIALA
Supplementery Bill
PROJECT : BOYS HOSTEL AND GIRLS HOSTEL
BILL : SUPPLEMENTERY BILL
M/s. Zamil Airconditioners India Pvt. Ltd
GRAND SUMMARY
|  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT |  |  | SITC AMOUNT
Sub Head | DESCRIPTION |  | PREVIOUS | THIS BILL | CUMMULATIVE | PREVIOUS | THIS BILL | CUMMULATIVE | PREVIOUS | THIS BILL | CUMMULATIVE
A | BOY'S HOSTEL (A)
1 | ELECTRICAL | Rs. | 0 | 334288.69 | 334288.69 |  | 717219 | 717219 |  | 1051507.69 | 1051507.69
2 | PLUMBING | Rs. |  | 0 |  |  | 102925 | 102925 |  | 102925 | 102925
3 | MATERIAL SUPPLY TO CLIENT | Rs. |  | 0 | 0
| BOYS HOSTEL TOTAL | Rs. |  | 334288.69 | 334288.69 |  | 820144 | 820144 |  | 1154432.69 | 1154432.69
B | GIRL'S HOSTEL (B)
1 | ELECTRICAL | Rs. |  | 50207.93 | 50207.93 |  | 52464.59 | 52464.59 |  | 102672.52 | 102672.52
2 | PLUMBING | Rs. |  | 0 | 0 |  | 35075 | 35075 |  | 35075 | 35075
| GIRLS HOSTEL TOTAL | Rs. |  | 50207.93 | 50207.93 |  | 87539.59 | 87539.59 |  | 137747.52 | 137747.52
| GRAND TOTAL (A+B) | Rs. | 0 | 384496.62 | 384496.62 | 0 | 907683.59 | 907683.59 | 0 | 1292180.21 | 1292180.21
| VAT @ 15.95% |  | 0 |  | 0 |  |  |  | 0 |  | 0
| Service Tax @ 15% |  |  |  |  | 0 |  | 0 | 0 |  | 0
| Labour Cess @ 1% | [7 empty] | 0 |  | 0
| TOTAL | [7 empty] | 0 | 1292180.21 | 1292180.21
| IGST @18% | [8 empty] | 232592.4378 | 232592.4378
| Labour Cess @ 1% | [8 empty] | 15247.7265 | 15247.7265
| Now Payble Amount | [7 empty] | 0 | 1540020.3743 | 1540020.3743

## GRAND SUMMARY (hidden)
PROJECT : THAPAR EXTENSION PATIALA
GRAND SUMMARY OF BOYS HOSTEL & GIRLS HOSTEL UPTO RA-09 Stamement
|  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT |  |  | SITC AMOUNT
Sub Head | DESCRIPTION |  | PREVIOUS | THIS BILL | CUMMULATIVE | PREVIOUS | THIS BILL | CUMMULATIVE | PREVIOUS | THIS BILL | CUMMULATIVE
A | BOY'S HOSTEL (A)
I | ELECTRICAL | Rs. | 22068730.34 | -0.34 | 22068730 | 1120336.65 | 0.35 | 1120337 | 23189066.99 | 0.01 | 23189067
II | HVAC | Rs. | 46891588 | 0 | 46891588 | 0 | 0 | 0 | 46891588 | 0 | 46891588
III | PLUMBING | Rs. | 14987511 | 0 | 14987511 | 5674124 | 0 | 5674124 | 20661635 | 0 | 20661635
| BOYS HOSTEL TOTAL | Rs. | 83947823.44 | 0 | 83947829 | 6794460.65 | 0 | 6794461 | 90742289.99 | 0.01 | 90742290
B | GIRL'S HOSTEL (B)
I | ELECTRICAL | Rs. | 5793154 | 0 | 5793154 | 592529.47 | -0.47 | 592529 | 6385683.47 | -0.47 | 6385683
II | HVAC | Rs. | 12930944 | 0 | 12930944 | 209680 | 0 | 209680 | 13140623.82 | 0 | 13140623.82
III | PLUMBING | Rs. | 6251844 | 0 | 6251844 | 1373283 | 0 | 1373283 | 7625127.22 | 0 | 7625127.22
| GIRLS HOSTEL TOTAL | Rs. | 24975942 | 0 | 24975942 | 2175492.47 | 0 | 2175492 | 27151434.51 | 0 | 27151434.51
| GRAND TOTAL (A+B) | Rs. | 108923765.44 | 0 | 108923771 | 8969953.12 | 0 | 8969953 | 117893724.51 | 0 | 117893724.51
| VAT @ 15.95% |  | 17373341 | 0 | 17373341 |  |  |  | 17373342 | 0 | 17373342
| Service Tax @ 15% |  |  |  |  | 1345493 | 0 | 1345493 | 1345493 | 0 | 1345493
| Labour Cess @ 1% | [7 empty] | 1366126 | 0 | 1366126
| GRAND TOTAL WITH TAX | [7 empty] | 137978685.51 | 0 | 137978685.51
| Now Payble Amount | [7 empty] | 137978685.51 | 0 | 137978685.51
[9 empty] | 137978685.51 | 0 | 137978685.51

## NON Schedual (hidden)
PROJECT : THAPAR EXTENSION PATIALA
GRAND SUMMARY OF NON- SCHEDULE ITEMS
BOYS HOSTEL & GIRLS HOSTEL UPTO RA-09
Sub Head | DESCRIPTION |  | SUPPLY AMOUNT |  |  | ITC AMOUNT |  |  | SITC AMOUNT
|  |  | PREVIOUS | THIS BILL | CUMMULATIVE | PREVIOUS | THIS BILL | CUMMULATIVE | PREVIOUS | THIS BILL | CUMMULATIVE
A | BOY'S HOSTEL
I | ELECTRICAL | Rs. | 293811 | 40477.69 | 334288.69 |  |  |  | 293811 | 40477.69 | 334288.69
II | HVAC | Rs. | 1078971 | 0 | 1078971 |  |  |  | 1078971 | 0 | 1078971
III | PLUMBING | Rs. | 35112 | 90342 | 125454 | 291963.6 | 181841 | 473804.6 | 327075 | 272183 | 599258.6
| TOTAL |  | 1407894 | 130819.69 | 1538713.69 | 291963.6 | 181841 | 473804.6 | 1699857 | 312660.69 | 2012518.29
B | GIRL'S HOSTEL | [7 empty] | 0 | 0 | 0
I | ELECTRICAL | Rs. | 42763 | 7444.93 | 50207.93 |  |  |  | 42763 | 7444.93 | 50207.93
II | HVAC | Rs. | 527421 | 0 | 527421 |  |  |  | 527421 | 0 | 527421
III | PLUMBING | Rs. | [6 empty] | 0 | 0 | 0
| TOTAL | Rs. | 570184 | 7444.93 | 577628.93 | 0 | 0 | 0 | 570184 | 7444.93 | 577628.93
| GRAND TOTAL | Rs. | 1978078 | 138264.62 | 2116342.62 | 291963.6 | 181841 | 473804.6 | 2270041 | 320105.62 | 2590147.22
| VAT @ 15.95% |  | 315503.441 | 22053.2069 | 337557 |  |  |  | 315503.441 | 0 | 337557
| Service Tax @ 15% |  |  |  |  | 43795 | 27276 | 71071 | 43795 | 27276 | 71071
| Labour Cess @ 1% | [7 empty] | 26293 | 3695 | 29988
| GRAND TOTAL WITH TAX | [7 empty] | 2655632.441 | 0 | 3028763.22
| Now Payble Amount | [7 empty] | 2655632.441 | 0 | 3028763.22
[6 empty] | Payable Amount |  |  | 2655633 | 0 | 3028763.22

## PLUMBING SUMMARY (hidden)
PROJECT : THAPAR UNIVERSITY EXPANSION AT PATIALA
S.No | Description | SUPPLY AMOUNT |  |  | ITC AMOUNT |  |  | SITC AMOUNT
| GRAND SUMMARY FOR PLUMBING AND FIREFIGHTING WORKS FOR BOYS HOSTEL | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT
I | TOTAL FOR SANITARY FIXTURES (FIXING) | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
2 | TOTAL FOR SOIL, WASTE,VENT & FITTINGS | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF!
3 | TOTAL FOR RAIN WATER PIPE & FITTINGS | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF!
4 | TOTAL FOR WATER SUPPLY SYSTEM | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF!
5 | TOTAL FOR HYDRANT SYSTEM | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF!
6 | TOTAL FOR HAND APPLIANCES | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF!
7 | TOTAL FOR EXTERNAL WATER SUPPLY SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | TOTAL FOR GARDEN HYDRANT SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | TOTAL FOR EXTERNAL SEWERAGE SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | TOTAL FOR STORM WATER DRAINAGE SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TOTAL EXTERNAL FIRE HYDRANT | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| TOTAL | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Grand Total
| VAT @ 15.95% | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF!
| Service Tax @ 15% |  |  |  | 0 | #REF! | #REF! | 0 | #REF! | #REF!
| Labour Cess @ 1% | [6 empty] | #REF! | #REF! | #REF!
| GRAND TOTAL WITH TAX | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF!
| Now Payble Amount | [6 empty] | #REF! | #REF! | #REF!
| Rounded Off | #REF! | #REF! | #REF!
Zamil Airconditioners Pvt. Ltd.
Authorized Signatory

## ELECTRICAL BH
PROJECT : THAPAR EXPANSION AT PATIALA
S.No. | DESCRIPTION | Unit | QTY. | SUPPLY RATE | ITC RATE | GST Rate |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT |  |  | Remarks | Remarks
[6 empty] | Supply Rate | ITC Rate | PREV. | NOW | CUMM. | PREV. | NOW | CUMM. | PREV. | NOW | CUMM. | PREV. | NOW | CUMM. | Pg No | Pg No
[16 empty] | 0 |  |  | 0 |  | 0 | 0
SUB HEAD IV – DISTRIBUTION SYSTEM
Supply, erection, testing and commissioning of the following sheet steel clad wall recess mounting dust and vermin proof distribution boards constructed from 16 SWG sheet steel IP 42 construction, finished with rust proof powder coated paint with hinged gasketted door and housing the following complete with suitably rated PVC insulated copper busbars with interconnections and neutral bar assembly, earthing terminals complete as approved by Architects. Padlocking facility shall be provided on the door.
a) | 8 way SPN (Type-1) |  |  |  |  | 4216.38 | 406.55 |  | 1 | 1 |  | 1 | 1 |  | 4216.38 | 4216.38 |  | 406.55 | 406.55 |  |  | DONE
| 1-40 amp TPN incoming with 2 nos MCB out goings. | [7 empty] | 0 |  |  | 0
b) | 8 way SPN(Type-2) |  |  |  |  | 6006 | 465 |  | 8 | 8 |  | 8 | 8 |  | 48048 | 48048 |  | 3720 | 3720 |  |  | DONE
4 pole 40 amp ELCB 300mA incoming with 1-25 amp DP 30 mA ELCB incoming and 1 nos 16 amps DP MCB with thermal magnetic protective releases out goings.
c) | 12 way SPN(Type-1)DD |  |  |  |  | 7742.75 | 522.85 |  | 3 | 3 |  | 3 | 3 |  | 23228.25 | 23228.25 |  | 1568.55 | 1568.55 |  |  | DONE
| 1-40 amp ELCB TPN 300mA with 1-25 amp DP 30 mA ELCB incoming and 1 DP MCB 16 Amp 8 nos 6/16/20 amps SP 10 kA MCB with thermal magnetic protective releases out goings. | [7 empty] | 0 |  |  | 0
d) | 16 way SPN |  |  |  |  | 9320.37 | 580.5 |  | 4 | 4 |  | 4 | 4 |  | 37281.48 | 37281.48 |  | 2322 | 2322 |  |  | DONE
| 1-32 amp DP MCB,5 Nos. DP MCB 16-32 Amp, 1 no. Timer contractor3 pole, 1 No.40 Amp watch | [7 empty] | 0 |  |  | 0
[9 empty] | 0 |  |  | 0
e) | 12 Way VTPN |  |  |  |  | 41295.29 | 2496.95 |  | 2 | 2 |  | 2 | 2 |  | 82590.58 | 82590.58 |  | 4993.9 | 4993.9 |  |  | DONE
| 4 pole 125 A MCCB incoming with 12 nos 32 TP MCB outgoings | [7 empty] | 0 |  |  | 0
SUB HEAD X : FIXTURES AND FITTINGS
1 | Receiving, assembling, erection, connecting, testing and commissioning of the following light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
f) | 300 mm sweep heavy duty Exhaust fans | NOS | 492 |  |  |  | 300 |  |  |  |  | 432 | 432 |  |  |  |  | 129600 | 129600 |  |  | done
NS-3 | BOYS HOSTEL- GYM Panel | [14 empty] | 0 |  |  | 0 |  | 0 | 0
| Modification in above panel |  |  | 159 | [11 empty] | 0 |  |  | 0 |  | 0 | 0
| 1 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection(Deleted) | NOS | 1 | 2897 |  | 2897 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
| 4 nos 63 amps 10 kA SPN MCB with thermal magnetic protective releases (Deleted) | [19 empty] | 0 | 0
| 1 nos 160 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection(Added) | [19 empty] | 0 | 0
| 4 nos 63 amps 10 kATPN MCB with thermal magnetic protective releases (Added) | [19 empty] | 0 | 0
[16 empty] | 0 |  |  | 0 |  | 0 | 0
NS-14 | Kitchen equipment panel | NoS | 1 |  |  | 80500 | 4945 |  | 1 | 1 |  | 1 | 1 | 0 | 80500 | 80500 | 0 | 4945 | 4945 |  | 0 | done
[16 empty] | 0 |  |  | 0 |  | 0 | 0
NS-21 | FEEDER PILLAR | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
(A) | Feeder pillar 1 | NOS | 1 |  |  | 58423.5 | 4830 |  | 1 | 1 |  | 1 | 1 | 0 | 58424 | 58424 | 0 | 4830 | 4830 |  | 0 | done
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| FIXTURES AND FITTINGS | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
NS | Receiving, assembling, erection, connecting, testing and commissioning of the following light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | Hanging / down light at double/Triple height/Podium Light | nos |  |  |  |  | 372 |  | 0 |  |  | 766 | 766 | 0 | 0 | 0 | 0 | 284952 | 284952 |  | -766 | done
2 | LED strip light at podium leval | MTR |  |  |  |  | 35 |  | 0 |  |  | 480 | 480 | 0 | 0 | 0 | 0 | 16800 | 16800 |  | -480 | done
3 | Wall washer light | nos |  |  |  |  | 186 |  | 0 |  |  | 40 | 40 | 0 | 0 | 0 | 0 | 7440 | 7440 |  | -40 | done
4 | Spike and planter light | nos |  |  |  |  | 197 |  | 0 |  |  | 160 | 160 | 0 | 0 | 0 | 0 | 31520 | 31520 |  | -160 | done
5 | Ground light at hard scape area | nos |  |  |  |  | 337 |  | 0 |  |  | 214 | 214 | 0 | 0 | 0 | 0 | 72118 | 72118 |  | -214 | done
6 | Enterance light | nos |  |  |  |  | 488 |  | 0 |  |  | 48 | 48 | 0 | 0 | 0 | 0 | 23424 | 23424 |  | -48 | done
7 | Step light | nos |  |  |  |  | 279 |  | 0 |  |  | 135 | 135 | 0 | 0 | 0 | 0 | 37665 | 37665 |  | -135 | done
8 | 3mtr height pole light | nos |  |  |  |  | 755 |  | 0 |  |  | 12 | 12 | 0 | 0 | 0 | 0 | 9060 | 9060 |  | -12 | done
[12 empty] | 0 | [6 empty] | 0
NS | Voice Recorder | nos |  |  |  |  | 7334 |  |  |  |  | 1 | 1 |  |  |  |  | 7334 | 7334 |  |  | DONE
0
NS | Receiving, installation of ACP sheets for installing exhaust fan | nos |  |  |  |  | 172.5 |  |  |  |  | 432 | 432 | 0 | 0 | 0 | 0 | 74520 | 74520 |  | -432 | done
| Total Electrical Extra Items | [12 empty] | 0 | 334288.69 | 334288.69 | 0 | 717219 | 717219 |  | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## ELECTRICAL GH
PROJECT : THAPAR EXPANSION AT PATIALA
GIRLS HOSTEL ELECTRICAL Final Bill
SNO. | DESCRIPTION | QTY | UNIT | SUPPLY RATE | ITC RATE | SITC RATE | GST Rates |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[7 empty] | Supply Rate | ITC Rate | PREV | NOW | CUMM. | PREV | NOW | CUMM. | PREV | NOW | CUMM. | PREV | NOW | CUMM.
[21 empty] | 0 | 0
SUB HEAD X : FIXTURES AND FITTINGS
1 | Receiving, assembling, erection, connecting, testing and commissioning of the following light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required
e) | 300 mm sweep heavy duty Exhaust fans | NOS | 190 |  |  |  |  | 300 |  |  |  |  | 238 | 238 |  |  |  |  | 71400 | 71400 |  | done
Main Panel
Modification in above panel
2 nos 100 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted. 4 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added
| 4 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added | Nos | 2 | 6308 | [5 empty] | 0 | 0 |  |  |  |  | 0 | 0
NT 05 | MODIFICATION IN ABOVE PANEL
1 NOS 100 amp TPN Switch isolator Complete with (Deleted)
| 1 NOS 200amp TPN Switch isolator Complete with ( ADDED) | Nos | 1 |  |  |  | 10473 |  |  | 0 | 0 |  |  |  |  | 0 | 0
d) | 12 way SPN(Type-2)DD | [5 empty] | 4456.32 | 406.55 |  | 2 | 2 |  | 2 | 2 | 0 | 8912.64 | 8912.64 | 0 | 8912.64 | 8912.64 | -2 | DONE
| 1-40 amp TPN 300mA incoming and 2 MCB 16 Amp with thermal magnetic protective releases out goings. | [7 empty] | 0 |  |  | 0
| 12 Way VTPN | [5 empty] | 41295.29 | 2496.95 |  | 1 | 1 |  | 1 | 1 |  | 41295.29 | 41295.29 |  | 2496.95 | 2496.95 |  | DONE
| 4 pole 125 A MCCB incoming with 12 nos 32 TP MCB outgoings | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FIXTURES AND FITTINGS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
NS | Receiving, assembling, erection, connecting, testing and commissioning of the following light fixtures complete with housing, reflectors, all accessories i.e. copper wound ballast, HPF condensors, starters, holders etc. complete as required | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Hanging / down light at double/Triple height/Podium Light | nos | [5 empty] | 372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
2 | LED strip light at podium leval | MTR | [5 empty] | 35 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
3 | Wall washer light | nos | [5 empty] | 186 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
4 | Spike and planter light | nos | [5 empty] | 197 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
5 | Ground light at hard scape area | nos | [5 empty] | 337 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
6 | Enterance light | nos | [5 empty] | 488 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
7 | Step light | nos | [5 empty] | 279 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
[20 empty] | 0 | 0
NS | Receiving, installation of ACP sheets for installing exhaust fan | nos | [5 empty] | 172.5 |  |  |  |  | 238 | 238 |  |  |  |  | 41055 | 41055 | #VALUE! | done
| Total Amount of Electrical Extra Items | [13 empty] | 0 | 50207.93 | 50207.93 | 0 | 52464.59 | 52464.59 | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## PLUMBING EXTERNAL BH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
BOYS HOSTEL EXTERNAL PLUMBING RA-10
S No. | DESCRIPTION | Unit | Total Qty | SUPPLY RATE | ITC RATE | SITC RATE | GST Rates |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[7 empty] | Supply Rates | ITC Rates | PREV. | THIS BILL | CUMM. | PREV. | THIS BILL | CUMM. | PREV. | THIS BILL | CUMM. | PREV. | THIS BILL | CUMM.
A | EXTERNAL WATER SUPPLY SYSTEM
1 | Excavating trenches of required width for pipes, cables, etc including excavation for sockets also including for cement concrete cradles, and dressing of sides, ramming of bottoms, depth up to 1.5m including getting out the excavated soil, and then returning the soil as required, in layers not exceeding 20 cm in depth including consolidating each deposited layer with minimum 95% by ramming, watering etc. and disposing off surplus excavated soil as directed, within a lead of 50 m.
a) | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm OD. | RM | 400 |  | 881 | 881 |  | 861 |  |  |  | 293.75 | 490.5 | 784.25 |  |  |  | 258793.75 | 422320.5 | 681114.25
2 | Supply, installation, testing & commissioning of G.I. Pipes Class 'C' (Heavy grade) conforming to I.S. 1239 with G.I. Fittings conforming to IS : 1879 (Part I to X) such as tees, crosses, plug, socket, elbows, reducers, flange, check nut, flanges & clamps, hanger, structural steel supports as required/directed at Site including wrapping alround (PYPKOTE) etc. complete in all respect .
a) | 20 mm dia | RM | 0 | 250 | 205 | 455 | 244 | 200
b) | 25 mm dia | RM | 0 | 322 | 221 | 543 | 314 | 216
c) | 32 mm dia | RM | 0 | 384 | 271 | 655 | 375 | 265 | 78 | 0 | 78 |  |  |  | 29952 | 0 | 29952
d) | 40 mm dia | RM | 0 | 430 | 324 | 754 | 420 | 316 | 286 | 0 | 286 |  | 190.4 | 190.4 | 122980 | 0 | 122980 | 0 | 60166.4 | 60166.4
e) | 50 mm dia | RM | 200 | 543 | 377 | 920 | 530 | 368 | 200 | 0 | 200 |  | 174.6 | 174.6 | 108600 | 0 | 108600 | 0 | 64252.8 | 64252.8
f) | 65 mm dia | RM | 200 | 658 | 512 | 1170 | 643 | 500 | 24 | 0 | 24 |  |  |  | 15792 | 0 | 15792
| Reduced by 24 mtr | [8 empty] | -24 | -24 |  |  |  |  | -15792 | -15792
3 | Providing and fixing wafer end type cast iron butterfly valves conforming to IS : 13095 & BS : 5155 tested to 16 kg/sq.cm pressure (including flanges) (for bore well discharge pipe & water meter).
a) | 50mm dia | Each | 0 | 1277 | 936 | 2213 | 1248 | 915
b) | 65 mm dia | Each | 0 | 1428 | 1208 | 2636 | 1396 | 1181
c) | 80 mm dia | Each | 0 | 1578 | 1555 | 3133 | 1543 | 1520
d) | 100 mm dia | Each | 0 | 2029 | 2175 | 4204 | 1984 | 2126
e) | 150 mm dia | Each | 0 | 2856 | 2959 | 5815 | 2792 | 2893
4 | Providing, fixing, testing and commissioning of dual plated Non Return Valve PN 16 rating (16 kg/cm2 pressure rating) conforming to IS :5312 complete with nuts, bolts & washers & matching flanges.
a) | 50 mm dia | Each | 4 | 3228 | 936 | 4164 | 3156 | 915
b) | 65 mm dia | Each | 4 | 5561 | 1208 | 6769 | 5437 | 1181
c) | 80 mm dia | Each | 0 | 8373 | 1555 | 9928 | 8187 | 1520
5 | Making connection to existing city water main by tapping to gunmetal ferrule of 25 mm dia including excavation, bailing out water and filling back the excavated earth & C.I. water meter chamber cover, cutting & threading the pipe etc. getting approval from concerned authorities. | Each | 4 | 2339 | 35084 | 37423 | 2287 | 34307
6 | Constructing brick masonry chamber (for housing valves, meters etc.) with 75 class designation brick work in cement mortar 1:5 (1 cement :5 fine sand) for valves cement conc. top slab 1:2:4 (1 cement :2 coarse sand :4 graded stone aggregate 20 mm nominal size) necessary excavation, foundation conc. 1:5:10 (1 cement :5 fine sand :10 graded stone aggregate 40 mm nominal size) & inside plastering with cement mortar 1:3 (1 cement :3 coarse sand) 12 mm thick finished with a floating coat of neat cement complete as per standard design:
For valve/ meter chamber
a) | 300x300x600 mm size (inside) chamber with D.I. cover (lockable) size 250x250 mm (inside) with DI frame fixed in cement conc. Slab. | Each | 8 | 1014 | 4619 | 5633 | 991 | 4516
b) | 450x450x750 mm size (inside) chamber with D.I. lockable 300 x 300 mm (inside) with D.I. frame fixed in cement conc. slab. | Each | 0 | 2624 | 7017 | 9641 | 2565 | 6861 |  | 0 | 0 |  | 0 | 0
7 | Providing, fixing, testing & commissioning of cast iron air release valve conforming to IS : 14845 : 2000 including all fitting & accessories.
a) | 40mm dia | Each | 4 | 4056 | 175 | 4231 | 3966 | 171
b) | 50mm dia | Each | 4 | 4294 | 234 | 4528 | 4198 | 228
TOTAL FOR EXTERNAL WATER SUPPLY SYSTEM
B | GARDEN HYDRANT SYSTEM
1 | Providing & laying UPVC pressure pipes of 10Kg/Sq.cm pressure rating class V (IS : 4985-2000) including fittings, tees, bends, clamps, coupling and adaptors supports, and jointing with solvent joint, testing and necessary earth work in excavation, backfilling, disposal of surplus earth with a lead up to 100m complete, compaction and consolidation Including sand bedding all around UPVC pipe & fittings and thrust blocks at bends as per standard design (For garden hydrants).
a) | 32 OD | RM | 200 |  |  |  | 68 | 297
b) | 63 OD | RM | 0 |  |  |  | 263 | 331
2 | Providing and fixing forged brass body quarter turn lever operated ball valve with forged brass hard chrome plated ball, disc & gland packing shall be PTEF tested to 25 Kg/Sq.cm pressure including GI nipple and threaded hose receiver complete as required.
a) | 25 mm nominal bore | Each | 20 |  |  |  | 724 | 222
b) | 32 mm nominal bore | Each | 0 |  |  |  | 1122 | 290
3 | Construction brick masonry chamber with 75 class designation brick work in cement mortar 1:5 (1 cement : 5 find sand) for valve, with CI surface box 100 x 100 x 75 mm (inside) with hinged cover fixed in cement concrete slab 1:2:4 mix (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) necessary excavation foundation concrete 1:5:10 (1 cement : 5 fine sand : 10 graded stone aggregate 40mm nominal size) and inside plastering with cement mortar 1:3 (1 cement : 3 coarse sand) 12 mm thick finished with a floating coat of neat cement complete as per standard design.
(For Housing Lawn hydrant)
a) | 300 x 300 x 600 mm deep | Each | 20 |  |  |  | 1166 | 4516
b) | 600 x 600 x 750 mm deep | Each | 0 |  |  |  | 1166 | 8004
TOTAL FOR GARDEN HYDRANT SYSTEM
C | EXTERNAL SEWERAGE SYSTEM
1 | Excavating trenches of required width for pipes, cables, etc including excavation for sockets also including for cement concrete cradles, and dressing of sides, ramming of bottoms, depth up to 1.5m including getting out the excavated soil, and then returning the soil as required, in layers not exceeding 20 cm in depth including consolidating each deposited layer with minimum 95% by ramming, watering etc. and disposing off surplus excavated soil as directed, within a lead of 50 m.
a) | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm dia and depth as required . | RM | 1720 | 0 | 269 | 269 |  | 263 |  |  | 0 | 708.5 | 1000.75 | 1709.25 |  |  | 0 | 190586.5 | 263197.25 | 459788.25
b) | Pipes, cables etc. exceeding 300 mm dia but not exceeding 600mm dia.and depth as required . | RM | 0 | 0 | 403 | 403 |  | 394 |  |  | 0 | 30.6 | 0 | 30.6 |  |  |  | 12331.8 | 0 | 12331.8
2 | Providing, fixing, jointing, testing and commissioning of UPVC Drainage Pipe conforming to IS : 15328-2000 with all fittings such as bends, tees, elbow. The wall thickness of pipe and technical characteristic conforms to IS : 15328-2000 type SN4 & SN8. The fitting dimension conforming to BS : EN 1401-1998. The jointing to be completed with rubber ring/solvent weld joint.
a) | 110 mm OD U-Drain Pipe (SN8) | RM | 480 | 414 | 146 | 560 | 404 | 142 |  |  | 0 | [8 empty] | 0
b) | 160 mm OD U-Drain Pipe (SN4) | RM | 440 | 747 | 187 | 934 | 730 | 182 |  |  | 0 | [8 empty] | 0
c) | 200 mm OD U-Drain Pipe (SN4) | RM | 800 | 1719 | 234 | 1953 | 1680 | 228 | 498 | 161 | 659 | 413.22 | 245.55 | 658.77 | 856062 | 270480 | 1126542 | 96693.48 | 55985.4 | 154152.18
d) | 250 mm OD U-Drain Pipe (SN4) | RM | 0 | 1807 | 292 | 2099 | 1766 | 285 | [11 empty] | 0
3 | Providing and laying 150 mm thick cement concrete 1:5:10 mix ( 1 cement : 5 coarse Sand : 10 graded stone aggregate 40 mm nominal size) all-round S.W pipe including bed concrete 150 mm as per standard design.
a) | 100 mm dia | RM | 480 | 0 | 898 | 898 |  | 878
b) | 150 mm dia | RM | 440 | 0 | 1116 | 1116 |  | 1091 |  |  |  | 194.56 | 330 | 524.56 |  |  |  | 217128.96 | 360030 | 585408.96
c) | 200 mm dia | RM | 800 | 0 | 1369 | 1369 |  | 1338 |  |  |  | 352.2 | 184.038 | 536.238 |  |  |  | 482213.822 | 246242.844 | 734109.822
d) | 250 mm dia. | RM | 0 | 0 | 2171 | 2171 |  | 2122 | [10 empty] | 0 | 0
4 | Providing and fixing square mouth (S.W) gully trap grade `A' complete with C.I. grating brick masonry chamber with bricks of class designation 75 and water tight double seal C.I. cover with frame of 300 x 300 mm internal size. The weight of cover to be not less than 4.5 kg and frame to be not less than 2.70 kg. as per standard design.
a) | 100 x 100 mm size ‘P’ type. (Hold 30% ITC Payment of C.I. Cover work pending) | Each | 0 | 417 | 4549 | 4966 | 407 | 4448 | 48 | 0 | 48 | 10 | 30 | 40 | 20016 | 0 | 20016 | 31843 | 133440 | 127372 | 45490
| Released 30% | [11 empty] | 10 | 10 |  |  |  |  | 13647 | 13647
| Supply reduced by 8 Nos and shifted to GH | [8 empty] | -8 | -8 |  |  |  |  | -3256 | -3256
b) | 150 x 150 mm size 'P' type | Each | 48 | 417 | 4549 | 4966 | 407 | 4448 | [7 empty] | 0 | 0 |  | 0 | 0
c) | 180 x 150 mm size 'P' type | Each | 0 | 417 | 4549 | 4966 | 407 | 4448 | [7 empty] | 0 | 0 |  | 0 | 0
5 | Constructing brick masonry Rectangular manhole in cement mortar 1:4 mix (1cement: 4 coarse sand) RCC slab with 1:2:4 mixed (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size)and foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement making channels in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) finished with a floating coat of neat cement complete as per standred design.With ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (light duty ) internal size 450 mm x 600mm ,conforming to I.S. 12592 specifications of the brand as approved .
| Insize 90 x80 cms x depth beyond 550 cms to 750 cm | Each | 60 | 1134 | 11110 | 12244 | 1108 | 10864 |  |  |  | 5 | 3 | 8 |  | 0 | 0 | 55550 | 32592 | 88142
6 | Constructing brick masonry circular type manhole 75 class designation bricks in cement mortar 1:5 mix (1cement: 5 coarse sand) inside and outside cement plaster 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement, fixing manhole frame, foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and making channels and haunchig in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) including excavation, back filling and disposal of surplus earth, providing and embedding 12mm dia M.S polypropylene coated manhole steps centre to centre distnce 300 mm embedded in cement concrete block size 200x200x100 mm using cement concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) neatly finished complete as per standred design.
a. | 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . (Hold 30% Payment cover and frame work pending) | Each | 0 | 2011 | 16372 | 18383 | 1966 | 16009 | 70 | 7 | 77 | 50 | 27 | 77 | 139870 |  | 139870 | 573020 | 432243 | 1005263
[13 empty] | 50 | 50 |  |  |  |  | 245580 | 245580
7 | Making connection of sewer line existing manhole including breaking into and making good the walls, floors with cement concrete 1:2:4 mix (1 cement :2 coarse sand : 4 graded stone aggregate 20 mm nominal size) cement plastered on both sides with cement mortar 1:3 (1cement: 3 Coarse sand) finished with a floating coat of neat cement and making necessary channels for the drain etc. complete. | Each | 4 | 0 | 29236 | 29236 |  | 28588 |  |  | 0 |  | 3 | 3 |  | 0 | 0 |  | 85764 | 85764
TOTAL FOR EXTERNAL SEWERAGE SYSTEM
D | STORM WATER DRAINAGE SYSTEM
1 | Earth Work in Excavation of required width for storm water drainage pipes including excavation for sockets and dressing of sides, ramming of bottom depth up to 1.5 m including getting out the excavated soil and then returning the soil as required in layer not exceeding 20 cms in depth including consolidating each deposited layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 50 m for all kinds of soil.
a) | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM | 1800 | 0 | 269 | 269 |  | 263 |  |  | 0 | 373.6 | 915.855 | 1289.455 |  |  | 0 | 100484.95 | 240869.865 | 341354.815
b) | Pipes, exceeding 300 mm dia but not exceeding 600 mm dia.depth as required . | RM | 0 | 0 | 403 | 403 |  | 394 |  |  | 0 |  | 0 |  |  |  | 0
2 | Providing, fixing & testing of UPVC rain water pipes (IS : 4985-1983 class-5 10 Kg/cm2 pressure) including injection moulded fittings (heavy duty) (plain or door) e.g. bends, junction, cowls, tees, offsets, access pieces etc. Clamps/Supports jointing with rubber ring/solvent cement joints including cutting chase or holes in walls and floors and making good as required at Site [Podium drainage].
a) | 110 mm OD | RM | 600 | 613 | 146 | 759 | 599 | 142 |  |  | 0 |  | 0 |  |  |  | 0
3 | Providing, laying and jointing light duty non-pressure NP2 class S/S R.C.C. pipes with collars jointing with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including curing, testing of joints etc.
a) | 250 mm dia | RM | 1200 | 447 | 585 | 1032 | 437 | 572 | 350 | 0 | 350 | 147 | 119.95 | 266.95 | 156050 |  | 156050 | 85995 | 70170.75 | 156165.75
| Qty shifted to GH by 89 mtr | [8 empty] | 83 | -83 |  |  | 83 |  | -36271 | -36271
b) | 300 mm dia | RM | 0 | 578 | 702 | 1280 | 565 | 686 | 255 | 19 | 274 | 255 | 19.335 | 274.335 | 147390 | 10735 | 158125 | 179245 | 13263.81 | 192508.81
4 | Providing and laying 150 mm thick cement concrete 1:5:10 mix ( 1 cement : 5 coarse Sand : 10 graded stone aggregate 40 mm nominal size) upto haunches RCC pipe including bed concrete 150 mm as per standard design.
a) | 250 mm dia | RM | 1200 | 0 | 1153 | 1153 |  | 1127 |  | 0 | 0 | 20 | 119.95 | 139.95 |  |  |  | 23060 | 135183.65 | 158243.65
b) | 300 mm dia | RM | 0 | 0 | 1354 | 1354 |  | 1324 |  |  | 0 | 263.335 | 11 | 274.335 |  |  |  | 356555.59 | 14564 | 371449.59
5 | Constructing brick masonry road gully chamber unit brick of class designated 75 in cement mortar 1:4 (1 cement :4 coarse sand) including 500 x 450 mm precast RCC horizontal grating with frame complete as per standard design.
| Inside size 50 x 45 x 60 cm | Each | 80 | 1343 | 7017 | 8360 | 1313 | 6861 | 9 | 55 | 64 | 9 | 55 | 64 | 12087 | 72215 | 85952 | 63153 | 377355 | 449088
6 | Providing and fixing square mouth (S.W) gully trap grade `A' complete with C.I. grating brick masonry chamber with bricks of class designation 75 and water tight double seal C.I. cover with frame of 300 x 300 mm internal size. The weight of cover to be not less than 4.5 kg and frame to be not less than 2.70 kg. as per standard design.
b) | 150 x 150 mm size 'P' type | Each | 0 | 755 | 4549 | 5304 | 738 | 4448 |  |  | 0 |  | 0
7 | Constructing brick masonry Rectangular manhole in cement mortar 1:4 mix (1cement: 4 coarse sand) RCC slab with 1:2:4 mixed (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size)and foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement making channels in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) finished with a floating coat of neat cement complete as per standred design.With ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (light duty ) internal size 450 mm x 600mm ,conforming to I.S. 12592 specifications of the brand as approved .
b. | Insize 90 x80 cms x depth beyond 550 cms to 750 cm | Each | 80 | 1134 | 12864 | 13998 | 1108 | 12579 |  |  | 0 |  | 0
8 | Constructing brick masonry circular type manhole 75 class designation bricks in cement mortar 1:5 mix (1cement: 5 coarse sand) inside and outside cement plaster 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement, fixing manhole frame, foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and making channels and haunchig in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) including excavation, back filling and disposal of surplus earth, providing and embedding 12mm dia M.S polypropylene coated manhole steps centre to centre distnce 300 mm embedded in cement concrete block size 200x200x100 mm using cement concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) neatly finished complete as per standred design.
a. | 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . | Each | 0 | 2011 | 16372 | 18383 | 1966 | 16009 | 55 | 0 | 55 | 29 | 20 | 49 | 110065 |  | 110065 | 474788 | 320180 | 794968
9 | Rain Water Harvesting system :
| Construction of rain water harvesting pit as per Approved Drawing | Each |  | 0 | 177757 | 177757 |  | 173821 |  |  | 0 |  | 0
10 | Making connection of storm water line with external manhole including breaking into and making good the walls, floors with cement concrete 1:2:4 mix (1 cement :2 coarse sand : 4 graded stone aggregate 20 mm nominal size) cement plastered on both sides with cement mortar 1:3 (1cement: 3 Coarse sand) finished with a floating coat of neat cement and making necessary channels for the drain etc. complete. | Each | 4 | 0 | 64320 | 64320 |  | 62895 |  |  | 0 |  | 0
TOTAL FOR STORM WATER DRAINAGE SYSTEM
E | EXTERNAL FIRE HYDRANT SYSTEM
1 | Supply, Installation, Testing & Commissioning of the following size of Black Mild Steel Class `C' (heavy class) pipes conforming to IS : 1239 Part-I including cutting, threading, welding & all fittings like flanges, tees, elbows, bends junctions, reducers etc. welded or screwed joints, clamps & structural steel supports or as required/ directed at site including cutting & making good the walls, floors, RCC work etc cutting chases & filling the same with cement concrete 1:3:6 (1 cement :3 coarse sand :6 graded stone aggregate 20 mm nominal size) including Providing painting the pipes with 2 coats of desired shade of synthetic enamel paint over 2 coats of Red oxide primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. including Providing painting of legend both direction arrow as per the approved of project manager (For External Hydrant system) [Exposed Pipe].
a) | 80 mm dia | RM | 80 | 499 | 288 | 787 | 487 | 281 |  | 0 | [5 empty] | 0 | 0
b) | 100 mm dia | RM | 200 | 736 | 394 | 1130 | 719 | 385 |  | 0 | [5 empty] | 0 | 0
c) | 150 mm dia | RM | 0 | 1076 | 585 | 1661 | 1052 | 572
2 | Supply, Installation, Testing & Commissioning of the following size of Gun Metal two way fire brigade inlet connection to external hydrant ring/hydrant riser with 63 mm dia instantaneous type inlet and 100 mm dia flanges outlet conforming to IS:904 with blank cap and chain including 100 mm dia butterfly valve (PN 16 rating) and wafter type non-return valve complete with nuts, bolts, flanges and complete in all respect. Cost shall include a wall mounted box of M.S. construction (16 SWG) with glass door (4.0 mm thick) of adequate size (approx 0.6 m x 0.6 m x 0.45 m) to house the above mentioned component. | Each | 8 | 13479 | 6310 | 19789 | 13180 | 6170
3 | Providing and applying one coat of 4 mm thick 'PYPKOTE' or COATEK anti rust pipe protection conforming to IS: 10221 including PYPKOTE primer as per manufactures specifications and lap of 25 mm to make an impermeable layer on M.S. Pipes running underground /burried/in trenches complete including surface preparation including conducting holiday test. The application process shall be strictly according to manufacturers specification /recommendation.
a) | 80 mm dia | RM | 80 | 0 | 302 | 302 |  | 295 | [9 empty] | 0 | 0 | 0
b) | 100 mm dia | RM | 200 | 0 | 451 | 451 |  | 441
c) | 150 mm dia | RM | 0 | 0 | 651 | 651 |  | 636
4 | Stainless steel single headed ISI marked oblique pattern hydrant landing valve with 80mm dia flanged inlet & 63 mm dia instantaneous type female outlet complete with stainless steel cap and GI chain twist release type plugh and all accessories as per IS : 5290 -1983 (Type 'A') including fixing with anchor fasteners and flanged tapping from hydrant valve/Landing valve. (For External Hydrant) | Each | 8 | 5964 | 1035 | 6999 | 5831 | 1012
5 | Supply, Installation, Testing & Commissioning of the following size of 63 mm dia 15 m long non-percolating flexible hose (RRL- type A) as per IS : 636. Type "A" with Stainless Steel male & female instantaneous type coupling (IS 903) bound and riveted to hose pipe with copper rivets and 1.5 mm copper wire. | Each | 16 | 4533 | 58 | 4591 | 4432 | 56
6 | Supply, Installation, Testing & Commissioning of the following size of Standard Stainless Steel short size branch pipe with nozzle of 20 mm nominal bore outlet as per IS:903 suitable to fit with standard instantaneous type 63mm dia coupling ISI marked (IS:903) complete. | Each | 8 | 1730 | 35 | 1765 | 1691 | 34
7 | Supply, Installation, Testing & Commissioning of the following size of Weather proof standard fire hose cabinet (750 mm x 600 mm x 300 mm deep) made of 16 SWG powder coated M.S. sheet having single or double opening glazed (4.0 mm thick glass) shutter including necessary locking arrangement by allan key, stove enamelled Fire red finish (as per IS : 5, shade no. 536) with " Fire Hose" marked on front, suitable for housing 2 nos. 15m long 63 mm dia Hose pipe, 1 No. branch pipe & nozzle spanner. | Each | 8 | 4771 | 877 | 5648 | 4665 | 857
8 | Supply, Installation, Testing & Commissioning of the following size of C.I. Butterfly valve conforming to IS : 13095 with nut, bolts and washers complete. [PN -1.6 rating (16kg/cm2)]
a) | 150 mm dia | Each | 0 | 2856 | 2959 | 5815 | 2792 | 2893
b) | 100 mm dia | Each | 8 | 2029 | 2175 | 4204 | 1984 | 2126 | [10 empty] | 0 | 0
c) | 80 mm dia | Each | 0 | 1578 | 1631 | 3209 | 1543 | 1594 | [10 empty] | 0 | 0
9 | Supply, Installation, Testing & Commissioning of the following size of Gun Metal four way fire brigade inlet connection to external hydrant ring/hydrant riser with 4 Nos. 63 mm dia instantaneous type inlet and 150 mm dia flanges outlet conforming to IS:904 with blank cap and chain including 150 mm dia butterfly valve (PN 16 rating) and wafter type non-return valve complete with nuts, bolts, flanges and complete in all respect. Cost shall include a wall mounted box of M.S. construction (16 SWG) with glass door (4.0 mm thick) of adequate size (approx 0.6 m x 0.6 m x 0.45 m) to house the above mentioned component.[Location Outside the Building for External Fire Ring & Internal Fire Hydrant System]. | Each | 0 | 26600 | 9063 | 35663 | 26011 | 8862
10 | Supply, Installation, Testing & Commissioning of the following size of 150 mm dia gun metal fire brigade suction hose coupling of (gunmetal draw off connection) with 150 mm dia M.S. 'C’ Class suction pipe with 150 mm dia C.I. foot valve.Cost shall include a wall mounted box of M.S. construction (16 SWG) of adequate size with glass door (4.0 mm thick) to house the above mentioned component to be connected to static water tank. | Set | 0 | 16103 | 5286 | 21389 | 15746 | 5168
11 | Providing & fixing cast iron air release valve of 25 mm dia including 25 mm dia Ball valve with fittings etc. as per the requirement. | Each | 0 | 2982 | 117 | 3099 | 2915 | 114
12 | Supply, Installation, Testing & Commissioning of the following size of Bourdon type Stainless Steel dial type pressure gauge with brass isolation valve and pipe.
Dial Diameter : 100 mm
| Caliberation : 0-15 Kg/cm2 | Each | 0 | 1431 | 175 | 1606 | 1399 | 171
13 | Constructing brick masonry chamber with 75 class designation brick work in cement mortar 1:5 (1 cement :5 fine sand) for butterfly valve, with C.I. medium duty manhole cover fixed in concrete slab 1:2:4 mix (1 cement :2 coarse sand :4 graded stone aggregate 20 mm nominal size), necessary excavation, foundation concrete 1:5:10 (1 cement :5 fine sand :10 graded stone aggregate 40 mm nominal size) and 12 mm thick inside plastering with cement mortar 1:3 (1 cement :3 coarse sand) finished with a floating coat of neat cement complete as per standard design.(For External Hydrant system).
a) | 1200 x 1200 x 1500 mm internal dimensions | Each | 0 | 59642 | 0 | 59642 |  | 58321 |  |  |  |  | 3 | 3 |  |  |  |  | 174963 | 174963
TOTAL OF FIRE HYDRANT (EXTERNAL)
| TOTAL AMOUNT (EXTERNAL) | [13 empty] | 1718864 | 298111 | 2018625 | 3201442.852 | 3762011.269 | 6955834.077
EXTRA ITEMS
1 | Providing, laying and jointing light duty non-pressure NP2 class S/S R.C.C. pipes with collars jointing with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including curing, testing of joints etc. |  |  | 836 | 1053 | 1889 |  |  | 42 | 0 | 42 | 30.6 | 0 | 30.6 | 35112 | 0 | 35112 | 32221.8 | 0 | 32221.8
a) | 450 mm dia | [17 empty] | 0 | 0
Providing and laying 150 mm thick cement concrete 1:5:10 mix ( 1 cement : 5 coarse Sand : 10 graded stone aggregate 40 mm nominal size) all-round S.W pipe including bed concrete 150 mm as per standard design.
a) | 450 mm dia |  |  |  | 1758 | [6 empty] | 30.6 | 0 | 30.6 |  |  |  | 53794.8 | 0 | 53794.8
Constructing brick masonry circular type manhole 75 class designation bricks in cement mortar 1:5 mix (1cement: 5 coarse sand) inside and outside cement plaster 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement, fixing manhole frame,
[13 empty] | 0 | [5 empty] | 0 | 0
a) | 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . | Each | 0 | [9 empty] | 0 | [5 empty] | 0 | 0
a) | 1200 mm dia |  |  |  | 22883 | [6 empty] | 9 | 0 | 9 |  |  |  | 205947 | 0 | 205947
NS | CP Grating 63 dia | Nos |  |  |  |  | 59 | 131 |  | 376 | 376 |  | 376 | 376 |  | 22184 | 22184 |  | 49256 | 49256
NS | CP Grating 160dia | [5 empty] | 166 | 230 |  | 40 | 40 |  | 40 | 40 |  | 6640 | 6640 |  | 9200 | 9200
[19 empty] | 0 | 0
NS | SS FCO 200 dia | Nos |  |  |  |  | 3536 | 230 | [10 empty] | 0 | 0
| SS FCO 160 dia | Nos |  |  |  |  | 2048 | 230 |  |  |  |  | 10 | 10 |  |  |  |  | 2300 | 2300
| SS FCO 100 dia | Nos |  |  |  |  | 580 | 230 |  |  |  |  | 12 | 12 |  |  |  |  | 2760 | 2760
NS | Y Strainer 100mm | Nos |  |  |  |  | 4632 | 2300 |  | 6 | 6 |  |  |  |  | 27792 | 27792
| Y Strainer 80mm | Nos |  |  |  |  | 3088 | 2300 |  | 6 | 6 |  |  |  |  | 18528 | 18528
| Y Strainer 65mm | Nos |  |  |  |  | 2533 | 2300 |  | 6 | 6 |  |  |  |  | 15198 | 15198
NS | Toilet Rework | Nos | [5 empty] | 575 |  |  |  |  | 179 | 179 |  |  |  |  | 102925 | 102925
NS | Uninol | Nos | [5 empty] | 1100 |  |  |  |  | 14 | 14 |  |  |  |  | 15400 | 15400
Rates in PB
| TOTAL OF NS ITEMS | [13 empty] | 35112 | 90342 | 125454 | 291963.6 | 181841 | 473804.6
Note on O86: Author: we claim 19

## PLUMBING INTERNAL BH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
BOYS HOSTEL INTERNAL PLUMBING RA-10
S No. | DESCRIPTION | Unit | Total Qty. | SUPPLY RATE | ITC RATE | SITC RATE | GST Rates |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[7 empty] | Supply Rate | ITC Rates | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm.
A | SANITARY FIXTURES (Fixing only )
Sizes of all Sanitary fixtures given are for identification purpose only. and may vary depending on the makes & models as per final approval of Architect / Client.Specification of vitreous china sanitary wares, Accessories, Bath tubs, Kitchen sinks, , C.P. brass fittings & accessories will be provided at site by client at site .It will be supplied free of cost to the contractor at site. The supply will be made by the manufacturer/ Vendors as standard supply. Contractor will include providing and fixing of all other accessories like extension piece etc,for fixtures connection, any other device / accessories to complete the work under respective items for the same in the tender. No extra payment on this account shall be made .
1 | Providing ,Fixing, testing and commissioning of vitreous china Wall/floor mounting type (European type) water closet with C.P.Bolts, nuts other fixing arrangement solid plastic seat with lid, C.P. brass hinges and rubber buffers, concealed dual flushing cistern ( 3-6 liters/flush) with flush pipe , clamp with adaptor, WC flexible connector, C.P. brass screws and washers complete, including cutting and making good the walls floors where required complete in all respects.
| Supply | Each
| Installation Full rate 1403/ |  | 504 |  | 1403 |  |  | 1371
| Hold 50% Amount due to testing report not submited | Each | 504 |  | 701.5 | [6 empty] | 180 | 339 | 519 |  |  |  | 126270 | 464769 | 591039
| Released 50% amount | [11 empty] | 180 | 180 |  |  |  |  | 126270 | 126270
2 | Fixing shower with 2 valves, divertor including pillar tap and shower head including cutting and making good the walls and floors where required complete in all respects.
| Supply | Each
Installation Full rate 819/
| Hold 50% Amount due to testing report not submited | Each | 504 |  | 409.5 |  |  | 800 |  |  |  | 180 | 333 | 513 |  |  |  | 73710 | 266400 | 340110
[13 empty] | 180 | 180 |  |  |  |  | 73710 | 73710
3 | Providing ,Fixing, testing and commissioning of vitreous china wash basin Under Water Counter round/oval with waste coupling fitting,32mm CP cast brass bottle trap and pipe to wall with CP wall flange and rubber adopter for waste connection, CP deck mounted mixer with battery operated and built in sensor for auto cut in/cut off operation complete including cutting and making good the walls where required complete in all respects.
| Supply | Each |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
Installation Full rate 936/
| Hold 50% Amount due to testing report not submited | Each | 504 |  | 468 |  |  | 915 |  |  |  | 180 | 351 | 531 |  |  |  | 84240 | 321165 | 405405
[13 empty] | 180 | 180 |  |  |  |  | 84240 | 84240
4 | Providing ,Fixing, testing and commissioning of grab bar fabricated from 32 mm dia seamless stainless steel tube in washroom facilities for physically handicapped, with non-slip gripping surface complete including cutting and making good the walls and floors where required. |  |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
| Supply | Each |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
| Installation | Each | 0 |  | 117 |  |  | 114 |  |  |  |  | 0 | [5 empty] | 0
5 | Providing ,Fixing, testing and commissioning of 15 mm C.P. brass long body bib cock with C.P.brass flange complete including cutting and making good the walls where required. (AHU, J.sink)
| Supply | Each |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
| Installation | Each | 80 |  | 88 |  |  | 86 |  |  |  |  | 0 | [5 empty] | 0
6 | Providing ,Fixing, testing and commissioning of C.P brass ablution health faucet assembly with 1.2 m long braided PVC hose with mounting bracket fixed on wall complete.
| Supply | Each |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
| Installation | Each | 0 |  | 88 |  |  | 86 |  |  |  | 180 | 354 | 534 |  |  |  | 15840 | 30444 | 46284
7 | Providing and fixing Stainless Steel finish toilet paper holder with stainless steel roller complete, including cutting and making good the walls where required.
| Supply | Each |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
| Installation | Each | 504 |  | 88 |  |  | 86 |  |  |  |  | 0 | [5 empty] | 0
8 | Providing ,Fixing, testing and commissioning ofapproved make lavatory mounted liquid soap dispenser with auto sensor suitable for operation with less than 5 pounds of force complete with spout, shank, and fluid bottle complete in all respects including cutting and making good the walls required.
| Supply | Each |  |  | 0 | [7 empty] | 0 | [5 empty] | 0
| Installation | Each | 504 |  | 117 |  |  | 114 |  |  |  |  | 0 | [5 empty] | 0
9 | Providing ,Fixing, testing and commissioning of 15 mm dia angle valve with flanges including 450 mm long copper connecting pipe with nuts complete.
| Supply | Each
Installation Full rate 88/
| Hold 50% Amount due to testing report not submited | Each | 2520 |  | 44 |  |  | 86 |  |  |  | 900 | 1836 | 2736 |  |  |  | 39600 | 157896 | 197496
[5 empty] | 0 | [7 empty] | 900 | 900 |  |  |  |  | 39600 | 39600
10 | Providing ,Fixing, testing and commissioning of Stainless steel twin coat hooks fixed on toilet door with C.P. brass screws. |  |  |  | 0
| Supply | Each |  |  | 0
| Installation | Each | 504 |  | 58 |  |  | 56 |  |  |  |  | 508 | 508 |  |  |  |  | 28448 | 28448
11 | Providing ,Fixing, testing and commissioning of wall mounted auto aerosol dispenser with digital display fixed with brackets and rowl plug complete in all respects. |  |  |  | 0
| Supply | Each |  |  | 0
| Installation | Each | 504 |  | 117 |  |  | 114 |  |  |  |  | 516 | 516 |  |  |  |  | 58824 | 58824
TOTAL FITTINGS
B | SOIL, WASTE,VENT & FITTINGS
1 | Providing, Fixing & testing of uPVC SWR (Type-B) pipes conforming to IS 13592 along with all required fittings like tees, bends, cowls, crosses with or without access doors jointed with approved solvent cement fixed to walls and ceilings including angle supports with clamps and structural support as per good practice /manufacturers recomandation and complete including core cut in R.C.C/brick work (slab/beam/wall) and making good the same whatever required. Soil, Waste and Vent pipe)
I | Vertical Pipe
a) | 75 mm OD | RM | 2160 | 278 | 105 | 383 | 271 | 102 | 1641 | 656 | 2297 | 1565 | 732.13 | 2297.13 | 456198 | 177776 | 633974 | 163043 | 74677.26 | 237720.26
b) | 110 mm OD | RM | 4320 | 350 | 146 | 496 | 342 | 142 | 4320 | 0 | 4320 | 4088 | 231.68 | 4319.68 | 1512000 | 0 | 1512000 | 594372 | 32898.56 | 627270.56
c) | 160 mm OD | RM | 80 | 386 | 187 | 573 | 377 | 182 | 80 | 0 | 80 | 80 | 0 | 80 | 30880 | 0 | 30880 | 14960 | 0 | 14960
II | Pipe at Ceiling | [5 empty] | 0 |  |  | 0 | [8 empty] | 0
a) | 75 mm OD | RM | 200 | 262 | 105 | 367 | 256 | 102 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0
b) | 110mm OD | RM | 200 | 301 | 146 | 447 | 294 | 142 | 742 | 0 | 742 | 755 | 0 | 755 | 223370 |  | 223370 | 107210 |  | 107210
| Increased the qty by 3500 rmt | [7 empty] | 3500 | 0 | 3500 |  | 3487 | 3487 | 1029000 |  | 1029000 |  | 495154 | 495154
c) | 160mm OD | RM | 280 | 360 | 187 | 547 | 352 | 182 | 280 | 252 | 532 | 354 | 362.43 | 716.43 | 189504 |  | 189504 | 65823 | 65962.26 | 131785.26
III | Pipe at Floor | [8 empty] | 0
a) | 75 mm OD | RM | 0 | 244 | 105 | 349 | 238 | 102 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0
| 110mm OD | RM | 4032 | 279 | 146 | 425 | 272 | 142 | 4062 | 0 | 4062 | 457.46 | 0 | 457.46 | 1133298 | 0 | 1133298 | 66789.16 | 0 | 66789.16
| Reduced the Qty by 3500 Rmt | [7 empty] | -3500 |  | -3500 |  |  |  | -952000 | 0 | -952000
0
2 | Providing, Fixing & testing of f uPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia. | [8 empty] | 0
a) | 40 mm OD | RM | 2080 | 47 | 47 | 94 | 45 | 45 | 1240 | 0 | 1240 | 337 | 260.379 | 597.379 | 58280 | 0 | 58280 | 15576 | 11717.055 | 27293.055
| Reduced by 643 mtr and shifted 289 in GH | [8 empty] | 643 | -643 |  |  |  |  | -28935 | -28935
b) | 50 mm OD | RM | 1040 | 71 | 58 | 129 | 69 | 56 | [6 empty] | 0 | 0 | 0 | 0 | 0
c) | 63 mm OD | RM | 2600 | 112 | 74 | 186 | 109 | 72 | 2010 | 599 | 2609 | 1253 | 1351.6 | 2604.6 | 225120 | 67088 | 292208 | 91715 | 187531.2 | 279246.2
0
3 | Providing and laying cement concrete 1:2:4 mix (1 cement:2 coarse sand: 4 graded stone aggregate 20 mm nominal size) 75 mm in bed and alround uPVC soil & waste pipes including excavation, refilling where required complete in all respect as per standard design. | [8 empty] | 0
a) | Pipe 90 to 110 mm OD | RM | 4032 | 0 | 628 | 628 |  | 614 |  | 0 |  | 663.68 | 100.9 | 764.58 | 0 |  | 0 | 416791.04 | 61952.6 | 480156.24
b) | Pipe 40 to 63 mm OD | RM | 3812 | 0 | 381 | 381 |  | 372 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0
0
4 | Providing, Fixing & testing of uPVC P or S trap including jointing with solvent cement and making good the walls, floors etc., complete of nominal size. | Each | 520 | 193 | 117 | 310 | 188 | 114 | 720 | 124 | 844 | 652 | 192 | 844 | 137960 |  | 137960 | 75708 | 21888 | 97596
a) | 110x 110mm
5 | Providing, Fixing & testing of uPVC SWR inlet fittings with two or three saddle inlets of 40, 50 or 63 mm size, fabricated from 110 mm outer dia uPVC pipes and fixed to uPVC traps with solvent cement joint complete. | Each | 520 | 232 | 117 | 349 | 226 | 114 | 200 | 268 | 468 | 200 | 268 | 468 | 46400 | 62176 | 108576 | 23367 | 30552 | 53919
6 | Providing, Fixing & testing of uPVC reducing elbow as floor drain in cement concrete 1:2:4 float with floor complete in all respects. | [8 empty] | 0
| 110 x63 mm outlet | Each | 524 | 262 | 117 | 379 | 256 | 114 | 228 | 0 | 228 | 73 | 48 | 121 | 59736 | 0 | 59736 | 8541 | 5616 | 14157
7 | Providing, Fixing & testing of 125 mm dia, 1 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete. | [8 empty] | 0
| 125mm dia over Floor Trap & floor Drain | Each | 1040 | 539 | 117 | 656 | 527 | 114 | 1040 | 165 | 1205 |  | 1205 | 1205 | 560560 | 86955 | 647515 | 0 | 137370 | 137370
TOTAL COST FOR SOIL, WASTE,VENT & FITTINGS
C | RAIN WATER PIPES & FITTINGS
1 | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects.
a) | 75 mm OD | RM | 60 | 194 | 88 | 282 | 189 | 86 |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0
b) | 110 mm OD | RM | 100 | 406 | 129 | 535 | 397 | 126 | 1026 | 0 | 1026 | 419 | 831.2 | 1250.2 | 416556 | 0 | 416556 | 52807 | 104731.2 | 157525.2
| With referance to GH 191 mtr | [8 empty] | 191 | 191 |  |  |  |  | 75827 | 75827
c) | 160 mm OD | RM | 840 | 858 | 187 | 1045 | 839 | 182 | 738 | 482 | 1220 | 566 | 654.305 | 1220.305 | 633204 | 404398 | 1037602 | 104496 | 119083.51 | 223579.51
d) | 210 mm OD | RM | 100 | 1183 | 246 | 1429 | 1156 | 240 | 142 | 122 | 264 | 117 | 147.1 | 264.1 | 167986 | 141032 | 309018 | 28565 | 35304 | 63869
e) | 260 mm OD | RM | 0 | 1935 | 304 | 2239 | 1892 | 297 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
2 | Providing, Fixing & testing of cast iron grating with S.S screw for rain water outlet including making joint to uPVC rain water pipe as per manufacturer's recommendations, complete making good the walls and floors wherever requiered.
a) | 150mm x150 mm | Each | 16 | 89 | 89 | 178 | 87 | 87 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
b) | 300 mm x300 mm | Each | 32 | 249 | 117 | 366 | 243 | 114 | [6 empty] | 0 |  | 0 | 0 |  | 0
TOTAL COST OF RAIN WATER PIPE & FITTINGS
D | WATER SUPPLY SYSTEM
1 | Providing, Fixing & testing of CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493. With fabricated & subssequently epoxy painted clamps/ structural steel supports as required for directed at site including cutting chases and fitting the same with cement concrete /cement mortar as required. All termination points for installation of faucets shall have brass termination fittings.
a) | 15 mm nominal bore | RM | 7560 | 115 | 94 | 209 | 112 | 91 | 7560 | 1256 | 8816 | 5718 | 3829.17 | 9547.17 | 869400 | 140672 | 1010072 | 533479 | 348454.47 | 881933.47
b) | 20 mm nominal bore | RM | 2520 | 150 | 94 | 244 | 146 | 91 | 2520 | 0 | 2520 | 1060 | 571.15 | 1631.15 | 378000 | 0 | 378000 | 98587 | 51974.65 | 150561.65
| Less Qty by 889 | [8 empty] | 889 | -889 |  |  |  |  | -129794 | -129794
c) | 25 mm nominal bore | RM | 0 | 206 | 94 | 300 | 201 | 91 | 1280 | 725 | 2005 | 563 | 1441.86 | 2004.86 | 263680 | 145725 | 409405 | 52551 | 131209.26 | 183760.26
d) | 32 mm nominal bore | RM | 0 | 249 | 110 | 359 | 243 | 107 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
e) | 40 mm nominal bore | RM | 0 | 319 | 126 | 445 | 311 | 123 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
2 | Providing, Fixing & testing of GI medium class pipe conforming to IS:1239, including all fittings couplings, adapters & two or more coats of synthetic enamel paint over a coat of primer of approved quality and shade (shade as per pipe colour code)complete in all respect as directed by the Engineer-in-Charge ( terrace & shaft)
a) | 15 mm nominal boe | RM | 0 | 142 | 113 | 255 | 138 | 110 | 158.6 | 0.4 | 159 | 120 | 120.6 | 240.6 | 22578 | 0 | 22578 | 13491 | 13266 | 26757
b) | 20 mm nominal bore | RM | 960 | 166 | 117 | 283 | 162 | 114 | 813.39 | 0 | 813.39 | 135 | 263.3 | 398.3 | 135022.74 | 0 | 135022.74 | 15768 | 30016.2 | 45784.2
| Qty Reduced by 415 and shifted to GH by 286 | [8 empty] | -415 | -415 |  |  |  |  | -67230 | -67230
c) | 25 mm nominal bore | RM | 1920 | 236 | 120 | 356 | 230 | 117 | 597.8 | 1024 | 1621.8 | 465 | 1156.85 | 1621.85 | 141080.8 | 235520 | 376600.8 | 55788 | 135351.45 | 191139.45
d) | 32 mm nominal bore | RM | 1920 | 290 | 150 | 440 | 283 | 146 | 1920 | 0 | 1920 | 219.6 | 731.6 | 951.2 | 556800 | 0 | 556800 | 32940 | 106813.6 | 139753.6
| Qty Reduced by 969 and shifted to GH by 664 | [8 empty] | -969 | -969 |  |  |  |  | -274227 | -274227
e) | 40 mm nominal bore | RM | 1920 | 337 | 180 | 517 | 329 | 176 | 1406 | 0.1 | 1406.1 | 315.68 | 649.2 | 964.88 | 473960 | 0 | 473960 | 56822.4 | 114259.2 | 171081.6
| Qty Reduced by 441 and shifted to GH by 441 | [8 empty] | -441 | -441 |  |  |  |  | -145089 | -145089
f) | 50 mm nominal bore | RM | 960 | 449 | 234 | 683 | 439 | 228 | 531 | 332.5 | 863.5 | 82.84 | 781.3 | 864.14 | 238194.4 | 145967.5 | 384161.9 | 19384.56 | 178136.4 | 197520.96
g) | 65 mm nominal bore | RM | 400 | 565 | 294 | 859 | 552 | 287 | 100 | 0 | 100 |  | 105.5 | 105.5 | 56500 | 0 | 56500 | 0 | 30278.5 | 30278.5
h) | 80 mm nominal bore | RM | 800 | 732 | 351 | 1083 | 715 | 343 | 518.14 | -0.04 | 518.1 |  | 147.2 | 147.2 | 379249 | 0.2 | 379249.2 | 0 | 50489.6 | 50489.6
| Qty Reduced by 371 and shifted to GH by 57 | [8 empty] | -371 | -371 |  |  |  |  | -265265 | -265265
i) | 100 mm nominal bore | RM | 200 | 1062 | 468 | 1530 | 1038 | 457 | 300.74 | 0 | 300.74 |  | 20.4 | 20.4 | 319385.88 | 0 | 319385.88 | 0 | 9322.8 | 9322.8
3 | Providing, Fixing & testing of stainless steel ball valve working pressure of 10 Kg/cm2 with wheel & female screwed ends of approved quality to I complete in all respects.
a) | 15 mm nominal bore | Each | 520 | 436 | 181 | 617 | 426 | 176 | 542 | 0 | 542 |  | 484 | 484 | 236312 | 0 | 236312 | 0 | 85184 | 85184
b) | 20 mm nominal bore | Each | 1040 | 686 | 205 | 891 | 670 | 200 | 265 | -248 | 17 |  |  | 0 | 181790 | -170128 | 11662 | 0 |  | 0
| Reduced by 265 nos | [8 empty] | -265 | -265 |  |  |  |  | -181790 | -181790
c) | 25 mm nominal bore | Each | 8 | 981 | 228 | 1209 | 959 | 222 | 519 | 310 | 829 |  | 655 | 655 | 509139 | 304110 | 813249 | 0 | 145410 | 145410
d) | 32 mm nominal bore | Each | 12 | 1451 | 297 | 1748 | 1418 | 290 | 94 | 49 | 143 |  | 68 | 68 | 136394 | 71099 | 207493 | 0 | 19720 | 19720
e) | 40 mm nominal bore | Each | 12 | 2346 | 366 | 2712 | 2294 | 357 | 27 | 51 | 78 |  | 4 | 4 | 63342 | 119646 | 182988 | 0 | 1428 | 1428
4 | Providing and fixing C.I. double flanged butterfly valve working pressure of 10 Kg/cm2 complete with bolts, nuts, washers 3 mm thick insertion neoprene gasket.
a) | 50 mm nominal bore | Each | 80 | 1277 | 936 | 2213 | 1248 | 915 |  |  |  |  | 40 | 40 | 0 |  | 0 | 0 | 36600 | 36600
b) | 65 mm nominal bore | Each | 40 | 1428 | 1208 | 2636 | 1396 | 1181 | 5 | 0 | 5 |  | 4 | 4 | 6980 | 0 | 6980 | 0 | 4724 | 4724
c) | 80 mm dia | Each | 20 | 1578 | 1555 | 3133 | 1543 | 1520 | 20 | 0 | 20 |  | 20 | 20 | 30860 | 0 | 30860 | 0 | 30400 | 30400
d) | 100 mm dia | Each | 8 | 2029 | 2175 | 4204 | 1984 | 2126 | 18 | 0 | 18 |  | 12 | 12 | 35712 | 0 | 35712 | 0 | 25512 | 25512
[10 empty] | 6 | -6 |  |  |  |  | -11904 | -11904
5 | Providing and fixing motorized solenoid valve/rotary actuator (CI body, SS316 disc, EPDM boot seat, SS416 shaft, RPTEF bushing @PN10rating) for filling of overhead water tank complete with electrical water level control panel, including by-pass connection for the same dia with manually operated butterfly valve and all piping and accessories complete in all respects.
a) | Size of valve 25 mm | Each | 0 | 4271 | 716 | 4987 | 4176 | 700 | [6 empty] | 0 |  | 0 | 0 |  | 0
b) | Size of valve 32 mm | Each | 4 | 7157 | 895 | 8052 | 6998 | 875 | [6 empty] | 0 |  | 0 | 0 |  | 0
c) | Size of valve 40 mm | Each | 4 | 7717 | 1134 | 8851 | 7546 | 1108 | [6 empty] | 0 |  | 0 | 0 |  | 0
d | Size of valve 50 mm | Each | 4 | 8648 | 1462 | 10110 | 8456 | 1429 | [6 empty] | 0 |  | 0 | 0 |  | 0
6 | Providing and fixing forged brass auto air vent with forge brass isolation ball valve .Working pressure of 10 Kg/cm2 including all fitting & accessories.
a) | 15 mm dia |  | 20 | 836 | 105 | 941 | 817 | 102 | [6 empty] | 0 |  | 0 | 0 |  | 0
7 | Providing and fixing float valve (brass) with copper float of approved quality suitable for high or low pressure complete in all respects.
a) | Suitble for 25mm dia riser | Each | 0 | 2540 | 358 | 2898 | 2483 | 350 | [6 empty] | 0 |  | 0 | 0 |  | 0
b) | Suitble for 32mm dia riser | Each | 4 | 3386 | 448 | 3834 | 3311 | 438 | [6 empty] | 0 |  | 0 | 0 |  | 0
c) | Suitble for 40mm dia riser | Each | 4 | 3681 | 567 | 4248 | 3599 | 554 | [6 empty] | 0 |  | 0 | 0 |  | 0
d) | Suitble for 50mm dia riser | Each | 4 | 6424 | 731 | 7155 | 6281 | 714 | [6 empty] | 0 |  | 0 | 0 |  | 0
8 | Providing and fixing M.S fabricated hot dipped galvanized coating puddle flange comprising of 600 mm dia long/As per requirement M.S class 'C' pipe (screwed end up to 50 mm & flange for more than 50 mm dia) with 6 mm thick M.S plates of required size including cutting holes in centre of plate, inserting pipe & making welded (Arc) joint complete. Same shall be installed with TEC welded joint in position with reinforcement bars of RCC tank wall/slab including making cutout in shuttering during concrete casting of tank of following diameter. (Location: underground/ overhead tanks.)
a) | 25 mm dia | Each | 12 | 1236 | 292 | 1528 | 1208 | 285 | 32 | 0 | 32 |  | 32 | 32 | 39552 | 0 | 39552 | 0 | 9120 | 9120
b) | 32 mm dia | Each | 12 | 1383 | 395 | 1778 | 1352 | 386 | 1 | 0 | 1 |  | 0 |  | 1383 | 0 | 1383 | 0 | 0 | 0
c) | 40 mm dia | Each | 0 | 1527 | 497 | 2024 | 1493 | 485 | 4 | 0 | 4 |  | 4 | 4 | 6108 | 0 | 6108 | 0 | 1940 | 1940
d) | 50 mm dia | Each | 48 | 1768 | 643 | 2411 | 1728 | 628 | 20 | 0 | 20 |  | 20 | 20 | 35360 | 0 | 35360 | 0 | 12560 | 12560
e) | 65 mm dia | Each | 20 | 2175 | 789 | 2964 | 2126 | 771 | 7 | 0 | 7 |  | 4 | 4 | 15225 | 0 | 15225 | 0 | 3084 | 3084
f) | 80 mm dia | Each | 8 | 2568 | 936 | 3504 | 2511 | 915 | 39 | 0 | 39 |  | 36 | 36 | 100152 | 0 | 100152 | 0 | 32940 | 32940
g) | 100 mm dia | Each | 8 | 3196 | 1169 | 4365 | 3125 | 1143 | 28 | 0 | 28 |  | 28 | 28 | 89488 | 0 | 89488 | 0 | 32004 | 32004
h) | 150 mm dia | Each | 8 | 4596 | 1637 | 6233 | 4494 | 1600 | 16 | 0 | 16 |  | 16 | 16 | 73536 | 0 | 73536 | 0 | 25600 | 25600
9 | Providing and fixing 500 mm dia M.S. water tank cover with 10 mm seat with epoxy coated and lockable arrangement complete in all respects including all fitting & accessories. | Each | 12 | 4251 | 292 | 4543 | 4156 | 285 | [6 empty] | 0 |  | 0 | 0 |  | 0
10 | Providing and fixing G.I. Vent Pipe class 'B' (medium duty) for R.C.C water storage tanks comprising of 600 mm long/as per requirement vertical pipe, return bend with mosquito grating & cast brass perforated coupling including all associated civil work. | Each | 12 | 1789 | 211 | 2000 | 1749 | 206 | [6 empty] | 0 |  | 0 | 0 |  | 0
| 80 mm dia |  |  | 0 | 0 | 0 | [8 empty] | 0 |  | 0 | 0 |  | 0
11 | Providing and fixing of mosquito overflow grating /Jali of the following pipe diameters including all fittings & accessories :-
| 80 mm dia | Each | 12 | 596 | 117 | 713 | 582 | 114 | [6 empty] | 0 |  | 0 | 0 |  | 0
12 | Providing & fixing thermal insulation on hot water pipes a flexible elastomeric foam of closed cells structure having thermal conductivity of 0.038 W/M.K at 40o C, water vapour permeability fire propagation including all accessories e.g. adhesive and tape on joint complete as per specification. All joints shall be sealed with adhesive & cotton tape ,shall be applied to give uniform appearance & finished with polished protective coating.
a) | 15 mm dimeter (6mm thick insulation ) | RM | 2160 | 21 | 18 | 39 | 20 | 17 | [6 empty] | 0 |  | 0 | 0 |  | 0
TOTAL COST OF WATER SUPPLY SYSTEM
E | FIRE HYDRANT SYSTEM
1 | Providing & fixing fully glazed M.S fully welded construction single leaf door shutter for fire hydrant station fabricated from M.S. 50x50x6 mm angle iron frame, fixed to wall and hinged M.S 40x40x5 mm angle iron door shutter with required M.S. sash bards for glazing complete with locking arrangements, stove enamelled fire red finish with 'FIRE HYDRANT' written in front.
| Size 2100x900x600 mm deep. | Each | 72 | 11809 | 877 | 12686 | 11547 | 857 | [6 empty] | 0 |  | 0 | 0 |  | 0
2 | Supply,Installation, Testing & Commissioning of Gun-metal ISI marked oblique pattern hydrant landing valve with 80 mm dia flanged inlet and 63 mm dia instantaneous type female outlet complete with gunmetal cap and G.I. chain, twist release type plug and all accessories as per 13:5290-1983 (Type 'A') | Each | 72 | 5964 | 998 | 6962 | 5831 | 975 | 56 | 0 | 56 |  | 56 | 56 | 333984 | 0 | 333984 | 0 | 54600 | 54600
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
3 | Providing & Fixing of burden type Stainless Steel dial type pressure gauge with brass isolation valve and pipe. (For each internal Fire hose cabinet) | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Dial diameter 100 mm, calibration 0-15 kg | Each | 72 | 1431 | 175 | 1606 | 1399 | 171 | 32 | 0 | 32 |  | 56 | 56 | 44768 | 0 | 44768 | 0 | 9576 | 9576
[13 empty] | 0 | [5 empty] | 0 | 0
4 | Providing & Fixing of wall mounting swinging type first aid fire hose reel with drum, hanging bracket, 36.5 Mtr. length x 20 mm dia high pressure hose reel tubing as per IS: 444 with gun metal (GM) shut off nozzle having 5 mm dia orifice. The hose reel shall be conforming to IS : 884-1985. Rate shall include 25 mm dia M.S. pipe connection from Riser to hose reel, sockets, nipples, elbows,Union and ball valve (25 mm dia). Drum shall be fixed on adjoining wall through anchor fasteners / cement concrete block as and when required. (For internal hydrant system). | Each | 72 | 7753 | 877 | 8630 | 7581 | 857 | 56 | 0 | 56 |  | 56 | 56 | 434168 | 0 | 434168 | 0 | 47992 | 47992
[13 empty] | 0 | [5 empty] | 0 | 0
5 | Providing & Fixing of 63 mm dia 15 m long non-percolating flexible hose (RRL- type A) as per IS : 636. Type A with Gunmetal male & female instantaneous type coupling (IS 903) (For internal hydrant system). | Each | 144 | 4533 | 58 | 4591 | 4432 | 56 | 140 | 0 | 140 |  | 56 | 56 | 634620 | 0 | 634620 | 0 | 3136 | 3136
[13 empty] | 0 | [5 empty] | 0 | 0
6 | Providing & Fixing of standard S.S. 63 mm dia branch pipe with nozzle of 20 mm nominal bore outlet as per IS:903 suitable to fit with standard instantaneous type 63mm dia coupling ISI marked (IS:903) complete. | Each | 72 | 1730 | 35 | 1765 | 1691 | 34 | 56 | 0 | 56 |  | 56 | 56 | 96880 | 0 | 96880 | 0 | 1904 | 1904
7 | Supply, Installation testing & commissioning of Black Mild Steel Class 'C' (Heavy Duty) pipes conforming to IS : 1239 Part-I including cutting, threading, welding & all MS fittings like flanges, tees, elbows, bends junctions, reducers etc. welded or screwed joints, clamps structural steel supports (as per TAC norms) or as required/ directed at site including cutting & making good the walls, floors, RCC work etc cutting chases & filling the same with cement concrete 1:3:6 (1 cement :3 coarse sand :6 graded stone aggregate 20 mm nominal size) (For Internal work).(Supports will be measured extra.) Note: Pipes upto and 50 mm dia shall be threaded joints, above 50 mm shall be welded joints.
a) | 25 mm dia (Nominal Bore) | RM | 100 | 186 | 88 | 274 | 181 | 86 | [6 empty] | 0 |  | 0 | 0 |  | 0
b) | 80 mm dia (Nominal Bore) | RM | 80 | 499 | 211 | 710 | 487 | 206 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
c) | 100 mm dia (Nominal Bore) | RM | 400 | 734 | 281 | 1015 | 717 | 274 | 300 | 228 | 528 | 82.95 | 482.9 | 565.85 | 220200 | 163476 | 383676 | 23308.95 | 132314.6 | 155623.55
d) | 150 mm dia (Nominal Bore) | RM | 200 | 1076 | 421 | 1497 | 1052 | 411 |  | 24 | 24 |  | 23.8 | 23.8 | 0 | 25248 | 25248 | 0 | 9781.8 | 9781.8
0
8 | Providing and making drainage provision for dia MS (Medium Class"B") pipe, with required fittings etc.complete in all respect. (Drainage pipe) | [9 empty] | 37.85
a) | 80 mm dia | RM | 280 | 502 | 211 | 713 | 490 | 206 | 200 | 120.47 | 320.47 | 87.47 | 232.1 | 319.57 | 100400 | 59030.3 | 159430.3 | 18456.17 | 47812.6 | 66268.77
9 | Supply and painting for M.S. Pipe with a coat of red oxide Primer and two or more coats of synthetic enamel paint of approved colour to give an even shade including surface preparation and cleaning of pipe from all external material.
a) | 25 mm dia (Nominal Bore) | RM | 100 | 0 | 33 | 33 |  | 32 | [6 empty] | 0 |  | 0 | 0 |  | 0
b) | 80 mm dia (Nominal Bore) | RM | 80 | 0 | 88 | 88 |  | 86 |  |  |  |  | 319.57 | 319.57 | 0 |  | 0 | 0 | 27483.02 | 27483.02
c) | 100 mm dia (Nominal Bore) | RM | 400 | 0 | 113 | 113 |  | 110 |  |  |  |  | 565.85 | 565.85 | 0 |  | 0 | 0 | 62243.5 | 62243.5
d) | 150 mm dia (Nominal Bore) | RM | 200 | 0 | 164 | 164 |  | 160 |  |  |  |  | 23.8 | 23.8 | 0 |  | 0 | 0 | 3808 | 3808
10 | Providing & fixing single acting air valve of 25 mm dia as per IS : 14845 including 25 mm dia Ball valve and all fitting etc. as per the requirement. | Each | 8 | 2982 | 117 | 3099 | 2915 | 114 | 8 | 0 | 8 |  | 4 | 4 | 23320 | 0 | 23320 | 0 | 456 | 456
0
11 | Supply, Installation, Testing & Commissioning of CI Slim seal Butterfly valves, PN :1.0 rating conforming to IS : 13095 with complete with 2 Nos. matching flanges rubber insertion, nuts. bolts and washer etc. of following sizes. | [15 empty] | 0
| 150 mm dia | Each | 8 | 2856 | 2959 | 5815 | 2792 | 2893 | 8 | 0 | 8 |  | 8 | 8 | 22336 | 0 | 22336 | 0 | 23144 | 23144
12 | Supply, Installation, Testing & Commissioning of CI dual plate type non-return valves ,PN 1.1rating conforming to IS :5312 complete with nuts, bolts & washers. complete with 2 Nos. matching flanges,rubber insertion, nuts, bolts and washer etc. of following sizes.
a) | 80 mm dia | Each | 0 | 3963 | 1555 | 5518 | 3875 | 1520 | [6 empty] | 0 |  | 0 | 0 |  | 0
b) | 100 mm dia | Each | 8 | 5288 | 2175 | 7463 | 5170 | 2126 |  | 4 | 4 |  | 4 | 4 | 0 | 20680 | 20680 | 0 | 8504 | 8504
c) | 150 mm dia | Each | 8 | 10602 | 2959 | 13561 | 10367 | 2893 | [6 empty] | 0 |  | 0 | 0 |  | 0
Providing and fixing fire booster pump comprisiong of mono block pump and 3 Phase 440 volts/50 cycles per second with TEFC induction motor of the following capacity with mechanical seal including electric panel , cablling ,foundation ,scution,and devilivery header ,valve and fittings etc,and complete in all respect as per good praatice .location at terrace.
Capacity: 900 LPM
Head : 30 Metre
HP -9 (Approx.) or as required.
Impeller- Bronze
Shaft : S.S- 410
RPM - 2900
Mover : Electric Motor
| Quantity : eachset (1 w +1 s) | Set | 4 | 139446 | 11904 | 151350 | 136358 | 11640 | 4 | 0 | 4 |  | 4 | 4 | 557784 | 0 | 557784 | 0 | 46560 | 46560
TOTAL COST OF FIRE HYDRANT SYSTEM
F | HAND APPLIANCES
1 | Providing and fixing water based CO2 type extinguishers confirming to IS:15683 consisting of welded M.S. cylinderical body, squeeze lever discharge valve 30 cms long high pressure discharge hose, discharge nozzle, suspension braket, ISI marked as per IS:15683 finished externally with red enamel paint and fixed to wall with brackets complete with internal charges.
a) | Capacity 2 kg. | Each | 72 | 3994 | 117 | 4111 | 3905 | 114 | [6 empty] | 0 |  | 0 | 0 |  | 0
b) | Capacity 5 kg. | Each | 8 | 8321 | 117 | 8438 | 8136 | 114 | 56 | 0 | 56 |  | 56 | 56 | 457096 |  | 457096 | 0 | 6384 | 6384
2 | Providing and fixing stored pressure type mechanical foam based type fire extinguisher confirming to IS:15683 complete with pressure indicating gauge ,cylinder hose, discharge open nozzle, suspension bracket and externallyfinished with red enamel paint and fixedto wall with brackets complete with initial charges.
a) | Capacity 9 litres | Each | 0 | 2663 | 117 | 2780 | 2604 | 114 | [6 empty] | 0 |  | 0 | 0 |  | 0
3 | Providing and fixing ABC stored pressure dry chemical powder (mono ammonium phosphate) Fire Extinguisher IS : 13849 latest revision manufacturer and of CRCA sheet in welded construction, finish with epoxy polyster powder coated complete with brass forged ball valve, gun metal cap and nozzle, including initial filled and wall suspension bracket (suitable for fighting in class 'A', B & 'C' that is wood, textile, flammable liquid, electric and gases.
| Capacity 2 kg. | Each | 36 | 1220 | 117 | 1337 | 1192 | 114 | [6 empty] | 0 |  | 0 | 0 |  | 0
| Capacity 5 kg. | Each | 36 | 2218 | 117 | 2335 | 2168 | 114 | 56 | 0 | 56 |  | 56 | 56 | 121408 | 0 | 121408 | 0 | 6384 | 6384
TOTAL COST OF HAND APPLIANCES
TOTAL AMOUNT (INTERNAL PLUMBING) | [14 empty] | 14370199.82 | 1172064 | 15542263.82 | 3089999.28 | 5194085.295 | 8285484.175

## PLUMBING INTERNAL GH (hidden)
PROJECT : THAPAR EXPANSION AT PATIALA
GIRLS HOSTEL INTERNAL PLUMBING RA-10
S No. | DESCRIPTION | Unit | Qty | SUPPLY RATE | SUPPLY AMOUNT | ITC RATE | ITC AMOUNT | SITC RATE | SITC AMOUNT | GST Rates |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[10 empty] | Supply Rate | ITC Rate | Prev. | Now | Cumm. | Prev. | Now | Cumm. | Prev. | Now | Cumm. | Prev. | Now | Cumm.
A | SANITARY FIXTURES (Fixing only )
Sizes of all Sanitary fixtures given are for identification purpose only. and may vary depending on the makes & models as per final approval of Architect / Client.Specification of vitreous china sanitary wares, Accessories, Bath tubs, Kitchen sinks, , C.P. brass fittings & accessories will be provided at site by client at site .It will be supplied free of cost to the contractor at site. The supply will be made by the manufacturer/ Vendors as standard supply. Contractor will include providing and fixing of all other accessories like extension piece etc,for fixtures connection, any other device / accessories to complete the work under respective items for the same in the tender. No extra payment on this account shall be made .
1 | Providing ,Fixing, testing and commissioning of vitreous china Wall/floor mounting type (European type) water closet with C.P.Bolts, nuts other fixing arrangement solid plastic seat with lid, C.P. brass hinges and rubber buffers, concealed dual flushing cistern ( 3-6 liters/flush) with flush pipe , clamp with adaptor, WC flexible connector, C.P. brass screws and washers complete, including cutting and making good the walls floors where required complete in all respects.
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0
| Installation | Each | 205 | 0 | 0 | 1403 | 287615 | 1403 | 287615 |  | 1371 |  |  |  |  | 251 | 251 |  |  |  |  | 344121 | 344121
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
2 | Fixing shower with 2 valves, divertor including pillar tap and shower head including cutting and making good the walls and floors where required complete in all respects. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 192 | 0 | 0 | 819 | 157248 | 819 | 157248 |  | 800 |  |  |  |  | 240 | 240 |  |  |  |  | 192000 | 192000
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
3 | Providing ,Fixing, testing and commissioning of vitreous china wash basin Under Water Counter round/oval with waste coupling fitting,32mm CP cast brass bottle trap and pipe to wall with CP wall flange and rubber adopter for waste connection, CP deck mounted mixer with battery operated and built in sensor for auto cut in/cut off operation complete including cutting and making good the walls where required complete in all respects. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 200 | 0 | 0 | 936 | 187200 | 936 | 187200 |  | 915 |  |  |  |  | 255 | 255 |  |  |  |  | 233325 | 233325
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
4 | Providing ,Fixing, testing and commissioning of grab bar fabricated from 32 mm dia seamless stainless steel tube in washroom facilities for physically handicapped, with non-slip gripping surface complete including cutting and making good the walls and floors where required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each |  | 0 | 0 | 117 | 0 | 117 | 0 |  | 114 |  |  |  |  | 0 | [5 empty] | 0 | 0
[16 empty] | 0 | [5 empty] | 0 | 0
5 | Providing ,Fixing, testing and commissioning of 15 mm C.P. brass long body bib cock with C.P.brass flange complete including cutting and making good the walls where required. (AHU, J.sink) | [14 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 15 | 0 | 0 | 88 | 1320 | 88 | 1320 |  | 86 |  |  |  |  | 0 | [5 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
6 | Providing ,Fixing, testing and commissioning of C.P brass ablution health faucet assembly with 1.2 m long braided PVC hose with mounting bracket fixed on wall complete. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each |  | 0 | 0 | 88 | 0 | 88 | 0 |  | 56 |  |  |  |  | 267 | 267 |  |  |  |  | 14952 | 14952
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
7 | Providing and fixing Stainless Steel finish toilet paper holder with stainless steel roller complete, including cutting and making good the walls where required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 205 | 0 | 0 | 88 | 18040 | 88 | 18040 |  | 86 |  |  |  |  | 0 | [5 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
8 | Providing ,Fixing, testing and commissioning ofapproved make lavatory mounted liquid soap dispenser with auto sensor suitable for operation with less than 5 pounds of force complete with spout, shank, and fluid bottle complete in all respects including cutting and making good the walls required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 205 | 0 | 0 | 117 | 23985 | 117 | 23985 |  | 114 |  |  |  |  | 246 | 246 |  |  |  |  | 28044 | 28044
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
9 | Providing ,Fixing, testing and commissioning of 15 mm dia angle valve with flanges including 450 mm long copper connecting pipe with nuts complete. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 1025 | 0 | 0 | 88 | 90200 | 88 | 90200 |  | 86 |  |  |  |  | 1334 | 1334 |  |  |  |  | 114724 | 114724
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
10 | Providing ,Fixing, testing and commissioning of Stainless steel twin coat hooks fixed on toilet door with C.P. brass screws. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 205 | 0 | 0 | 58 | 11890 | 58 | 11890 |  | 56 |  |  |  |  | 0 | [5 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 240 | 240 |  |  |  |  | 0 | 0
11 | Providing ,Fixing, testing and commissioning of wall mounted auto aerosol dispenser with digital display fixed with brackets and rowl plug complete in all respects. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Supply | Each |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0
| Installation | Each | 205 | 0 | 0 | 117 | 23985 | 117 | 23985 |  | 114 |  |  |  |  | 0 | [5 empty] | 0 | 0
0
| TOTAL COST FOR SANITARY FIXTURES |  |  |  | 0 |  | 801483 |  | 801483
B | SOIL, WASTE,VENT & FITTINGS
1 | Providing, Fixing & testing of uPVC SWR (Type-B) pipes conforming to IS 13592 along with all required fittings like tees, bends, cowls, crosses with or without access doors jointed with approved solvent cement fixed to walls and ceilings including angle supports with clamps and structural support as per good practice /manufacturers recomandation and complete including core cut in R.C.C/brick work (slab/beam/wall) and making good the same whatever required. Soil, Waste and Vent pipe)
I | Vertical Pipe
a) | 75 mm OD | RM | 1080 | 278 | 300240 | 105 | 113400 | 383 | 413640 | 271 | 102 | 750 | 159 | 909 | 601 | 307.5 | 908.5 | 208500 | 43089 | 251589 | 63147 | 31365 | 94512
b) | 110 mm OD | RM | 1080 | 350 | 378000 | 146 | 157680 | 496 | 535680 | 342 | 142 | 1683 | 0 | 1683 | 1589 | -0.26 | 1588.74 | 589050 | 0 | 589050 | 231611 |  | 231611
c) | 160 mm OD | RM | 20 | 386 | 7720 | 187 | 3740 | 573 | 11460 | 377 | 182 | 416 | 0 | 416 | 424 | -0.47 | 423.53 | 160576 | 0 | 160576 | 78839 |  | 78839
II | Pipe at Ceiling | [8 empty] | 0 | 0
a) | 75 mm OD | RM | 50 | 262 | 13100 | 105 | 5250 | 367 | 18350 | 256 | 102 | [10 empty] | 0 | 0
b) | 110mm OD | RM | 50 | 301 | 15050 | 146 | 7300 | 447 | 22350 | 294 | 142 | 2146 | 0 | 2146 | 1013 | 0.31 | 1013.31 | 645946 | 0 | 645946 | 147943 | 0.26 | 147943.26
c) | 160mm OD | RM | 70 | 360 | 25200 | 187 | 13090 | 547 | 38290 | 351 | 182 | 70 | 0 | 70 | 70 |  | 70 | 25200 | 0 | 25200 | 13090 | 0 | 13090
III | Pipe at Floor | [8 empty] | 0 | 0
a) | 75 mm OD | RM |  | 244 | 0 | 105 | 0 | 349 | 0 | 238 | 102 |  |  |  |  | 0 |  | 0 |  |  |  | 0 | 0
b) | 110mm OD | RM | 1008 | 279 | 281232 | 146 | 147168 | 425 | 428400 | 272 | 142 | 1578 | 0 | 1578 |  | 1489.69 | 1489.69 | 440262 | 0 | 440262 |  | 211535.98 | 211535.98
2 | Providing, Fixing & testing of f uPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia.
a) | 40 mm OD | RM | 1040 | 47 | 48880 | 47 | 48880 | 94 | 97760 | 45 | 45 | 320 | 0 | 320 | 320 | 288.92 | 608.92 | 15040 | 0 | 15040 | 15040 | 13001.4 | 28041.4
| Added with referance in BH | [11 empty] | 289 | 289 |  |  |  |  | 13005 | 13005
b) | 50 mm OD | RM | 520 | 71 | 36920 | 58 | 30160 | 129 | 67080 | 69 | 56 | 300 | 222 | 522 | 244 | 277.86 | 521.86 | 21300 | 15318 | 36618 | 14152 | 15560.16 | 29712.16
c) | 63 mm OD | RM | 130 | 112 | 14560 | 74 | 9620 | 186 | 24180 | 109 | 72 | 1200 | 0 | 1200 | 783 | 196.01 | 979.01 | 134400 | 0 | 134400 | 57946 | 14112.72 | 72058.72
| Reduced Qty By and Added in BH | [8 empty] | 0 |  |  | 221 | -221 |  |  |  |  | -24089 | -24089
3 | Providing and laying cement concrete 1:2:4 mix (1 cement:2 coarse sand: 4 graded stone aggregate 20 mm nominal size) 75 mm in bed and alround uPVC soil & waste pipes including excavation, refilling where required complete in all respect as per standard design. | [8 empty] | 0
a) | Pipe 90 to 110 mm OD | RM | 1008 | 0 | 0 | 628 | 633024 | 628 | 633024 | 0 | 613 |  |  |  | 81.17 | 128.28 | 209.45 |  |  |  | 50974.76 | 78635.64 | 129610.4
b) | Pipe 40 to 63 mm OD | RM | 1127 | 0 | 0 | 381 | 429387 | 381 | 429387 | 0 | 372 | [10 empty] | 0 | 0
0
4 | Providing, Fixing & testing of uPVC P or S trap including jointing with solvent cement and making good the walls, floors etc., complete of nominal size. | Each | 205 | 193 | 39565 | 117 | 23985 | 310 | 63550 | 188 | 114 | 316 | 12 | 328 | 210 | 118 | 328 | 60458 |  | 60458 | 24570 | 13452 | 38022
a) | 110x 110mm |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0
5 | Providing, Fixing & testing of uPVC SWR inlet fittings with two or three saddle inlets of 40, 50 or 63 mm size, fabricated from 110 mm outer dia uPVC pipes and fixed to uPVC traps with solvent cement joint complete. | Each | 205 | 232 | 47560 | 117 | 23985 | 349 | 71545 | 226 | 114 | 94 | 154 | 248 | 200 | 48 | 248 | 21808 | 35728 | 57536 | 23400 | 5472 | 28872
[10 empty] | 0 | 0
6 | Providing, Fixing & testing of uPVC reducing elbow as floor drain in cement concrete 1:2:4 float with floor complete in all respects. | [8 empty] | 0 | 0
| 110 x63 mm outlet | Each | 205 | 262 | 53710 | 117 | 23985 | 379 | 77695 | 256 | 114 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
7 | Providing, Fixing & testing of 125 mm dia, 1 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete. | [8 empty] | 0 | 0
| 125mm dia over Floor Trap & floor Drain | Each | 410 | 539 | 220990 | 117 | 47970 | 656 | 268960 | 526 | 114 | 460 | 161 | 621 |  | 621 | 621 | 247940 | 84686 | 332626 |  | 70794 | 70794
TOTAL COST FOR SOIL, WASTE,VENT & FITTINGS
C | RAIN WATER PIPES & FITTINGS
1 | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects.
a) | 75 mm OD | RM | 60 | 194 | 11640 | 88 | 5280 | 282 | 16920 | 189 | 86
b) | 110 mm OD | RM | 50 | 406 | 20300 | 129 | 6450 | 535 | 26750 | 396 | 126 | 254 | 0 | 254 |  | 62.9 | 62.9 | 103124 | 0 | 103124 |  | 7925.4 | 7925.4
| Reduced Qty by 191 mtr | [11 empty] | -191 | -191 |  |  |  |  | -75636 | -75636
c) | 160 mm OD | RM |  | 858 | 0 | 187 | 0 | 1045 | 0 | 838 | 182 | 552 | 0 | 552 | 193 | 325.18 | 518.18 | 473616 | 0 | 473616 | 36054 | 59182.76 | 95236.76
d) | 210 mm OD | RM | 300 | 1183 | 354900 | 246 | 73800 | 1429 | 428700 | 1156 | 240 | 200 | 28 | 228 | 167 | 68.91 | 235.91 | 236600 | 32368 | 268968 | 41096 | 16538.4 | 57634.4
e) | 260 mm OD | RM |  | 1935 | 0 | 304 | 0 | 2239 | 0 | 1891 | 297
[10 empty] | 0 | 0
2 | Providing, Fixing & testing of cast iron grating with S.S screw for rain water outlet including making joint to uPVC rain water pipe as per manufacturer's recommendations, complete making good the walls and floors wherever requiered. | [8 empty] | 0 | 0
a) | 150mm x150 mm | Each | 4 | 89 | 356 | 88 | 352 | 177 | 708 | 87 | 86
b) | 300 mm x300 mm | Each | 8 | 249 | 1992 | 117 | 936 | 366 | 2928 | 243 | 114
0
TOTAL COST OF RAIN WATER PIPE & FITTINGS
D | WATER SUPPLY SYSTEM
1 | Providing, Fixing & testing of CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493. With fabricated & subssequently epoxy painted clamps/ structural steel supports as required for directed at site including cutting chases and fitting the same with cement concrete /cement mortar as required. All termination points for installation of faucets shall have brass termination fittings.
a) | 15 mm nominal bore |  | 350 | 115 | 40250 | 94 | 32900 | 209 | 73150 | 112 | 91 | 4940 | 0 | 4940 | 2752 | 932.36 | 3684.36 | 568100 | 0 | 568100 | 258718 | 87611.84 | 346329.84
| Less Qty by 1256 | [11 empty] | 1256 | -1256 |  |  |  |  | -140672 | -140672
b) | 20 mm nominal bore |  | 1225 | 150 | 183750 | 94 | 115150 | 244 | 298900 | 146 | 91 | 1320 | 0 | 1320 | 485 | 52.89 | 537.89 | 198000 | 0 | 198000 | 45598 | 4963.66 | 50561.66
| Less Qty by 782 | [11 empty] | 782 | -782 |  |  |  |  | -114172 | -114172
c) | 25 mm nominal bore |  |  | 206 | 0 | 94 | 0 | 300 | 0 | 201 | 91 | 1000 | 0 | 1000 | 212 | 857.05 | 1069.05 | 206000 | 0 | 206000 | 19919 | 80571.7 | 100490.7
d) | 32 mm nominal bore |  |  | 249 | 0 | 110 | 0 | 359 | 0 | 243 | 107
e) | 40 mm nominal bore |  |  | 319 | 0 | 126 | 0 | 445 | 0 | 311 | 123
2 | Providing, Fixing & testing of GI medium class pipe conforming to IS:1239, including all fittings couplings, adapters & two or more coats of synthetic enamel paint over a coat of primer of approved quality and shade (shade as per pipe colour code)complete in all respect as directed by the Engineer-in-Charge ( terrace & shaft)
a) | 15 mm nominal boe | [8 empty] | 138 | 110 |  | 219 | 219 |  | 218.9 | 218.9 |  | 30222 | 30222 |  | 24079 | 24079
b) | 20 mm nominal bore | RM | 480 | 142 | 68160 | 113 | 54240 | 255 | 122400 | 162 | 114 |  | 286 | 286 |  | 285.5 | 285.5 |  | 46332 | 46332 |  |  | 32547
c) | 25 mm nominal bore | RM | 960 | 166 | 159360 | 117 | 112320 | 283 | 271680 | 230 | 117 |  | 526 | 526 |  | 525.99 | 525.99 |  | 120980 | 120980 |  |  | 61540.83
d) | 32 mm nominal bore | RM | 960 | 236 | 226560 | 120 | 115200 | 356 | 341760 | 283 | 146 |  | 664 | 664 | 21.8 | 641.8 | 663.6 |  | 187912 | 187912 | 2616 | 93702.8 | 96318.8
e) | 40 mm nominal bore | RM | 960 | 290 | 278400 | 150 | 144000 | 440 | 422400 | 329 | 175 |  | 489 | 489 | 22 | 671.2 | 693.2 |  | 160881 | 160881 | 3300 | 117460 | 120760
f) | 50 mm nominal bore | RM | 480 | 337 | 161760 | 180 | 86400 | 517 | 248160 | 438 | 228 |  | 265 | 265 |  | 265.1 | 265.1 |  | 116070 | 116070 |  | 60442.8 | 60442.8
g) | 65 mm nominal bore | RM | 200 | 449 | 89800 | 234 | 46800 | 683 | 136600 | 552 | 287 |  | 137 | 137 |  | 138.7 | 138.7 |  | 75624 | 75624
h) | 80 mm nominal bore | RM | 400 | 565 | 226000 | 294 | 117600 | 859 | 343600 | 715 | 343 |  | 57 | 57 | 12.1 | 45 | 57.1 |  | 40755 | 40755 | 3557.4 | 13230 | 16787.4
i) | 100 mm nominal bore | RM | 100 | 732 | 73200 | 351 | 35100 | 1083 | 108300 | 1038 | 457 |  |  | 0
3 | Providing, Fixing & testing of stainless steel ball valve working pressure of 10 Kg/cm2 with wheel & female screwed ends of approved quality to I complete in all respects.
a) | 15 mm nominal bore | Each | 260 | 436 | 113360 | 181 | 47060 | 617 | 160420 | 426 | 176 | 260 | 17 | 277 |  | 277 | 277 | 113360 | 7412 | 120772 |  | 48752 | 48752
b) | 20 mm nominal bore | Each | 260 | 686 | 178360 | 205 | 53300 | 891 | 231660 | 670 | 200 |  | 17 | 17 |  | 17 | 17 |  | 11390 | 11390 |  | 3400 | 3400
c) | 25 mm nominal bore | Each | 4 | 981 | 3924 | 228 | 912 | 1209 | 4836 | 959 | 222 |  | 310 | 310 |  | 310 | 310 |  | 297290 | 297290 |  | 68820 | 68820
d) | 32 mm nominal bore | Each | 25 | 1451 | 36275 | 297 | 7425 | 1748 | 43700 | 1418 | 290 |  | 49 | 49 |  | 49 | 49 |  | 69482 | 69482 |  | 14210 | 14210
e) | 40 mm nominal bore | Each | 25 | 2346 | 58650 | 366 | 9150 | 2712 | 67800 | 2293 | 357 |  | 51 | 51 |  | 51 | 51 |  | 116943 | 116943 |  | 18207 | 18207
4 | Providing and fixing C.I. double flanged butterfly valve working pressure of 10 Kg/cm2 complete with bolts, nuts, washers 3 mm thick insertion neoprene gasket.
a) | 50 mm nominal bore | Each | 4 | 1277 | 5108 | 936 | 3744 | 2213 | 8852 | 1248 | 915
b) | 65 mm nominal bore | Each | 10 | 1428 | 14280 | 1208 | 12080 | 2636 | 26360 | 1396 | 1180
c) | 80 mm dia | Each | 5 | 1578 | 7890 | 1555 | 7775 | 3133 | 15665 | 1542 | 1520
d) | 100 mm dia | Each | 2 | 2029 | 4058 | 2175 | 4350 | 4204 | 8408 | 1983 | 2126 |  | 0 | 0 |  |  |  |  | 0 | 0
5 | Providing and fixing motorized solenoid valve/rotary actuator (CI body, SS316 disc, EPDM boot seat, SS416 shaft, RPTEF bushing @PN10rating) for filling of overhead water tank complete with electrical water level control panel, including by-pass connection for the same dia with manually operated butterfly valve and all piping and accessories complete in all respects.
a) | Size of valve 25 mm | Each |  | 4271 | 0 | 716 | 0 | 4987 | 0 | 4175 | 699
b) | Size of valve 32 mm | Each | 1 | 7157 | 7157 | 895 | 895 | 8052 | 8052 | 6996 | 874
c) | Size of valve 40 mm | Each | 1 | 7717 | 7717 | 1134 | 1134 | 8851 | 8851 | 7544 | 1108
d | Size of valve 50 mm | Each | 1 | 8648 | 8648 | 1462 | 1462 | 10110 | 10110 | 8454 | 1429
0
6 | Providing and fixing forged brass auto air vent with forge brass isolation ball valve .Working pressure of 10 Kg/cm2 including all fitting & accessories.
a) | 15 mm dia |  | 3 | 836 | 2508 | 105 | 315 | 941 | 2823 | 817 | 102
7 | Providing and fixing float valve (brass) with copper float of approved quality suitable for high or low pressure complete in all respects.
a) | Suitble for 25mm dia riser | Each |  | 2540 | 0 | 358 | 0 | 2898 | 0 | 2483 | 349
b) | Suitble for 32mm dia riser | Each | 1 | 3386 | 3386 | 448 | 448 | 3834 | 3834 | 3310 | 437
c) | Suitble for 40mm dia riser | Each | 1 | 3681 | 3681 | 567 | 567 | 4248 | 4248 | 3598 | 554
d) | Suitble for 50mm dia riser | Each | 1 | 6424 | 6424 | 731 | 731 | 7155 | 7155 | 6280 | 714
0
8 | Providing and fixing M.S fabricated hot dipped galvanized coating puddle flange comprising of 600 mm dia long/As per requirement M.S class 'C' pipe (screwed end up to 50 mm & flange for more than 50 mm dia) with 6 mm thick M.S plates of required size including cutting holes in centre of plate, inserting pipe & making welded (Arc) joint complete. Same shall be installed with TEC welded joint in position with reinforcement bars of RCC tank wall/slab including making cutout in shuttering during concrete casting of tank of following diameter. (Location: underground/ overhead tanks.)
a) | 25 mm dia | Each | 3 | 1236 | 3708 | 292 | 876 | 1528 | 4584 | 1208 | 285 | 6 | 6 | 12 |  | 12 | 12 | 7416 | 7248 | 14664 |  | 3420 | 3420
b) | 32 mm dia | Each | 3 | 1383 | 4149 | 395 | 1185 | 1778 | 5334 | 1352 | 386 |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | 0
c) | 40 mm dia | Each |  | 1527 | 0 | 497 | 0 | 2024 | 0 | 1492 | 485 | 1 | 1 | 2 |  | 2 | 2 | 1527 | 1492 | 3019 |  | 970 | 970
d) | 50 mm dia | Each | 12 | 1768 | 21216 | 643 | 7716 | 2411 | 28932 | 1728 | 628 | 8 | 8 | 16 |  | 16 | 16 | 14144 | 13824 | 27968 |  | 10048 | 10048
e) | 65 mm dia | Each | 6 | 2175 | 13050 | 789 | 4734 | 2964 | 17784 | 2126 | 771 | 1 | 1 | 2 |  | 2 | 2 | 2175 | 2126 | 4301 |  | 1542 | 1542
f) | 80 mm dia | Each | 4 | 2568 | 10272 | 936 | 3744 | 3504 | 14016 | 2510 | 915 | 2 | 2 | 4 |  | 4 | 4 | 5136 | 5020 | 10156 |  | 3660 | 3660
g) | 100 mm dia | Each | 4 | 3196 | 12784 | 1169 | 4676 | 4365 | 17460 | 3124 | 1142 | 3 | 3 | 6 |  | 6 | 6 | 9588 | 9372 | 18960 |  | 6852 | 6852
h) | 150 mm dia | Each | 2 | 4596 | 9192 | 1637 | 3274 | 6233 | 12466 | 4493 | 1600 | 1 | 1 | 2 |  | 2 | 2 | 4596 | 4493 | 9089 |  | 3200 | 3200
9 | Providing and fixing 500 mm dia M.S. water tank cover with 10 mm seat with epoxy coated and lockable arrangement complete in all respects including all fitting & accessories. | Each | 3 | 4251 | 12753 | 292 | 876 | 4543 | 13629 | 4155 | 285
10 | Providing and fixing G.I. Vent Pipe class 'B' (medium duty) for R.C.C water storage tanks comprising of 600 mm long/as per requirement vertical pipe, return bend with mosquito grating & cast brass perforated coupling including all associated civil work. | Each | 3 | 1789 | 5367 | 211 | 633 | 2000 | 6000 | 1748 | 206
| 80 mm dia |  |  | 0 | 0 | 0 | 0 | 0 | 0
11 | Providing and fixing of mosquito overflow grating /Jali of the following pipe diameters including all fittings & accessories :-
| 80 mm dia | Each | 3 | 596 | 1788 | 117 | 351 | 713 | 2139 | 582 | 114
12 | Providing & fixing thermal insulation on hot water pipes a flexible elastomeric foam of closed cells structure having thermal conductivity of 0.038 W/M.K at 40o C, water vapour permeability fire propagation including all accessories e.g. adhesive and tape on joint complete as per specification. All joints shall be sealed with adhesive & cotton tape ,shall be applied to give uniform appearance & finished with polished protective coating.
a) | 15 mm dimeter (6mm thick insulation ) | RM | 750 | 21 | 15750 | 18 | 13500 | 39 | 29250 | 20 | 17
| TOTAL COST OF WATER SUPPLY SYSTEM |  |  |  | 2078695 |  | 1052623 |  | 3131318 |  |  |  | 466
E | FIRE HYDRANT SYSTEM
1 | Providing & fixing fully glazed M.S fully welded construction single leaf door shutter for fire hydrant station fabricated from M.S. 50x50x6 mm angle iron frame, fixed to wall and hinged M.S 40x40x5 mm angle iron door shutter with required M.S. sash bards for glazing complete with locking arrangements, stove enamelled fire red finish with 'FIRE HYDRANT' written in front.
| Size 2100x900x600 mm deep. | Each | 14 | 11809 | 165326 | 877 | 12278 | 12686 | 177604 | 11544 | 857 |  | 28 | 28 |  | 28 | 28 |  | 323232 | 323232 |  | 23996 | 23996
[10 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0
2 | Supply,Installation, Testing & Commissioning of Gun-metal ISI marked oblique pattern hydrant landing valve with 80 mm dia flanged inlet and 63 mm dia instantaneous type female outlet complete with gunmetal cap and G.I. chain, twist release type plug and all accessories as per 13:5290-1983 (Type 'A') | Each | 14 | 5964 | 83496 | 998 | 13972 | 6962 | 97468 | 5830 | 975 | 28 | 0 | 28 |  | 28 | 28 | 166992 | 0 | 166992 |  | 27300 | 27300
[10 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0
3 | Providing & Fixing of burden type Stainless Steel dial type pressure gauge with brass isolation valve and pipe. (For each internal Fire hose cabinet) | [8 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0
| Dial diameter 100 mm, calibration 0-15 kg | Each | 14 | 1431 | 20034 | 175 | 2450 | 1606 | 22484 | 1398 | 171 | 18 | 0 | 18 |  | 28 | 28 | 25164 | 0 | 25164 |  | 4788 | 4788
[10 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0
4 | Providing & Fixing of wall mounting swinging type first aid fire hose reel with drum, hanging bracket, 36.5 Mtr. length x 20 mm dia high pressure hose reel tubing as per IS: 444 with gun metal (GM) shut off nozzle having 5 mm dia orifice. The hose reel shall be conforming to IS : 884-1985. Rate shall include 25 mm dia M.S. pipe connection from Riser to hose reel, sockets, nipples, elbows,Union and ball valve (25 mm dia). Drum shall be fixed on adjoining wall through anchor fasteners / cement concrete block as and when required. (For internal hydrant system). | Each | 14 | 7753 | 108542 | 877 | 12278 | 8630 | 120820 | 7579 | 857 | 28 | 0 | 28 |  | 28 | 28 | 217084 | 0 | 217084 |  | 23996 | 23996
[10 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0
5 | Providing & Fixing of 63 mm dia 15 m long non-percolating flexible hose (RRL- type A) as per IS : 636. Type A with Gunmetal male & female instantaneous type coupling (IS 903) (For internal hydrant system). | Each | 28 | 4533 | 126924 | 58 | 1624 | 4591 | 128548 | 4431 | 56 | 28 | 0 | 28 |  | 28 | 28 | 126924 | 0 | 126924 |  | 1568 | 1568
[10 empty] | 0 | 0 | [10 empty] | 0 | 0
6 | Providing & Fixing of standard S.S. 63 mm dia branch pipe with nozzle of 20 mm nominal bore outlet as per IS:903 suitable to fit with standard instantaneous type 63mm dia coupling ISI marked (IS:903) complete. | Each | 14 | 1730 | 24220 | 35 | 490 | 1765 | 24710 | 1691 | 34 | 28 | 0 | 28 |  | 28 | 28 | 48440 | 0 | 48440 |  | 952 | 952
[10 empty] | 0 | 0 | [10 empty] | 0 | 0
7 | Supply, Installation testing & commissioning of Black Mild Steel Class 'C' (Heavy Duty) pipes conforming to IS : 1239 Part-I including cutting, threading, welding & all MS fittings like flanges, tees, elbows, bends junctions, reducers etc. welded or screwed joints, clamps structural steel supports (as per TAC norms) or as required/ directed at site including cutting & making good the walls, floors, RCC work etc cutting chases & filling the same with cement concrete 1:3:6 (1 cement :3 coarse sand :6 graded stone aggregate 20 mm nominal size) (For Internal work).(Supports will be measured extra.) Note: Pipes upto and 50 mm dia shall be threaded joints, above 50 mm shall be welded joints. | [8 empty] | 0 | 0 | [10 empty] | 0 | 0
a) | 25 mm dia (Nominal Bore) | RM | 25 | 186 | 4650 | 88 | 2200 | 274 | 6850 | 181 | 86 | [10 empty] | 0 | 0
b) | 80 mm dia (Nominal Bore) | RM | 25 | 499 | 12475 | 211 | 5275 | 710 | 17750 | 487 | 206 | [10 empty] | 0 | 0
c) | 100 mm dia (Nominal Bore) | RM | 200 | 734 | 146800 | 281 | 56200 | 1015 | 203000 | 717 | 274 | 66 | 38 | 104 |  | 103.6 | 103.6 | 48444 | 27246 | 75690 |  | 28386.4 | 28386.4
d) | 150 mm dia (Nominal Bore) | RM | 50 | 1076 | 53800 | 421 | 21050 | 1497 | 74850 | 1051 | 411 | [7 empty] | 0 | 0 |  | 0 | 0
[10 empty] | 0 | 0 | [10 empty] | 0 | 0
8 | Providing and making drainage provision for dia MS (Medium Class"B") pipe, with required fittings etc.complete in all respect. (Drainage pipe) | [8 empty] | 0 | 0 | [10 empty] | 0 | 0
a) | 80 mm dia | RM | 150 | 502 | 75300 | 211 | 31650 | 713 | 106950 | 490 | 206 | 46 | 104 | 150 |  | 150 | 150 | 23092 | 50960 | 74052 |  | 30900 | 30900
[10 empty] | 0 | 0 | [10 empty] | 0 | 0
9 | Supply and painting for M.S. Pipe with a coat of red oxide Primer and two or more coats of synthetic enamel paint of approved colour to give an even shade including surface preparation and cleaning of pipe from all external material. | [8 empty] | 0 | 0 | [10 empty] | 0 | 0
a) | 25 mm dia (Nominal Bore) | RM | 25 | 0 | 0 | 33 | 825 | 33 | 825 | 0 | 32 | [7 empty] | 0 | 0 |  | 0 | 0
b) | 80 mm dia (Nominal Bore) | RM | 25 | 0 | 0 | 88 | 2200 | 88 | 2200 | 0 | 86 |  |  |  |  | 150 | 150 |  | 0 | 0 |  | 12900 | 12900
c) | 100 mm dia (Nominal Bore) | RM | 200 | 0 | 0 | 113 | 22600 | 113 | 22600 | 0 | 110 |  |  |  |  | 103.6 | 103.6 |  | 0 | 0 |  | 11396 | 11396
d) | 150 mm dia (Nominal Bore) | RM | 50 | 0 | 0 | 164 | 8200 | 164 | 8200 | 0 | 160 | [7 empty] | 0 | 0 |  | 0 | 0
[10 empty] | 0 | 0 | [7 empty] | 0 | 0 |  | 0 | 0
10 | Providing & fixing single acting air valve of 25 mm dia as per IS : 14845 including 25 mm dia Ball valve and all fitting etc. as per the requirement. | Each | 4 | 2982 | 11928 | 117 | 468 | 3099 | 12396 | 2915 | 114 | 4 | 0 | 4 |  | 4 | 4 | 11660 | 0 | 11660 |  | 456 | 456
[10 empty] | 0 | 0 | [7 empty] | 0 | 0 |  | 0 | 0
11 | Supply, Installation, Testing & Commissioning of CI Slim seal Butterfly valves, PN :1.0 rating conforming to IS : 13095 with complete with 2 Nos. matching flanges rubber insertion, nuts. bolts and washer etc. of following sizes. | [8 empty] | 0 | 0 | [8 empty] | 0 |  | 0 | 0
| 150 mm dia | Each | 4 | 2856 | 11424 | 2959 | 11836 | 5815 | 23260 | 2792 | 2892 | 4 | 0 | 4 |  | 4 | 4 | 11168 | 0 | 11168 |  | 11568 | 11568
[10 empty] | 0 | 0 | [10 empty] | 0 | 0
12 | Supply, Installation, Testing & Commissioning of CI dual plate type non-return valves ,PN 1.1rating conforming to IS :5312 complete with nuts, bolts & washers. complete with 2 Nos. matching flanges,rubber insertion, nuts, bolts and washer etc. of following sizes. | [8 empty] | 0 | 0 | [10 empty] | 0 | 0
a) | 80 mm dia |  |  | 3963 | 0 | 1555 | 0 | 5518 | 0 | 3874 | 1520 | [10 empty] | 0 | 0
b) | 100 mm dia |  |  | 5288 | 0 | 2175 | 0 | 7463 | 0 | 5169 | 2126 | [10 empty] | 0 | 0
c) | 150 mm dia | Each | 4 | 10602 | 42408 | 2959 | 11836 | 13561 | 54244 | 10364 | 2892 | [10 empty] | 0 | 0
| Providing and fixing fire booster pump comprisiong of mono block pump and 3 Phase 440 volts/50 cycles per second with TEFC induction motor of the following capacity with mechanical seal including electric panel , cablling ,foundation ,scution,and devilivery header ,valve and fittings etc,and complete in all respect as per good praatice .location at terrace. | [8 empty] | 0 | 0
| Capacity: 900 LPM | [8 empty] | 0 | 0
| Head : 30 Metre | [8 empty] | 0 | 0
| HP -9 (Approx.) or as required. | [8 empty] | 0 | 0
| Impeller- Bronze | [8 empty] | 0 | 0
| Shaft : S.S- 410 | [8 empty] | 0 | 0
| RPM - 2900 | [8 empty] | 0 | 0
| Mover : Electric Motor | [8 empty] | 0 | 0
| Quantity : eachset (1 w +1 s) | Set | 1 | 139446 | 139446 | 11904 | 11904 | 151350 | 151350 | 136018 | 11637 | 2 | 0 | 2 |  | 2 | 2 | 278892 | 0 | 278892 |  | 23274 | 23274
| TOTAL COST OF FIRE HYDRANT SYSTEM |  |  |  | 1026773 |  | 229336 |  | 1256109
F | HAND APPLIANCES
1 | Providing and fixing water based CO2 type extinguishers confirming to IS:15683 consisting of welded M.S. cylinderical body, squeeze lever discharge valve 30 cms long high pressure discharge hose, discharge nozzle, suspension braket, ISI marked as per IS:15683 finished externally with red enamel paint and fixed to wall with brackets complete with internal charges.
a) | Capacity 2 kg. | Each | 14 | 3994 | 55916 | 117 | 1638 | 4111 | 57554 | 3904 | 114
b) | Capacity 5 kg. | Each | 14 | 8321 | 116494 | 117 | 1638 | 8438 | 118132 | 8134 | 114 | 28 | 0 | 28 |  | 28 | 28 | 232988 | 0 | 232988 |  | 3192 | 3192
[10 empty] | 0 | 0
2 | Providing and fixing stored pressure type mechanical foam based type fire extinguisher confirming to IS:15683 complete with pressure indicating gauge ,cylinder hose, discharge open nozzle, suspension bracket and externallyfinished with red enamel paint and fixedto wall with brackets complete with initial charges. | [8 empty] | 0 | 0
a) | Capacity 9 litres | Each | 18 | 2663 | 47934 | 117 | 2106 | 2780 | 50040 | 2603 | 114
[10 empty] | 0 | 0
3 | Providing and fixing ABC stored pressure dry chemical powder (mono ammonium phosphate) Fire Extinguisher IS : 13849 latest revision manufacturer and of CRCA sheet in welded construction, finish with epoxy polyster powder coated complete with brass forged ball valve, gun metal cap and nozzle, including initial filled and wall suspension bracket (suitable for fighting in class 'A', B & 'C' that is wood, textile, flammable liquid, electric and gases. | [8 empty] | 0 | 0
| Capacity 2 kg. | Each | 7 | 1220 | 8540 | 117 | 819 | 1337 | 9359 | 1192 | 114
| Capacity 5 kg. | Each | 7 | 2218 | 15526 | 117 | 819 | 2335 | 16345 | 2168 | 114 | 28 | 0 | 28 |  | 28 | 28 | 62104 | 0 | 62104 |  | 3192 | 3192
| TOTAL COST OF HAND APPLIANCES |  |  |  | 244410 |  | 7020 |  | 251430
| TOTAL AMOUNT | [16 empty] | 5766814 | 1595931 | 7362745 | 1131571.16 | 2337748.92 | 3563407.91

## PLUMBING EXTERNAL GH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
RA-09 GIRLS HOSTEL EXTERNAL PLUMBING RA 10
S.No. | Description | Unit | Qty. | SUPPLY RATE | ITC RATE | SITC RATE | GST Rate |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[7 empty] | Supply Rate | ITC Rate | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm.
A | EXTERNAL WATER SUPPLY SYSTEM
1 | Excavating trenches of required width for pipes, cables, etc including excavation for sockets also including for cement concrete cradles, and dressing of sides, ramming of bottoms, depth up to 1.5m including getting out the excavated soil, and then returning the soil as required, in layers not exceeding 20 cm in depth including consolidating each deposited layer with minimum 95% by ramming, watering etc. and disposing off surplus excavated soil as directed, within a lead of 50 m.
a) | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm OD. | RM | 130 | 0 | 881 | 881 |  | 861 |  |  |  | 166.91 | 23 | 189.91 |  |  |  | 147047.71 | 20263 | 167310.71
2 | Supply, installation, testing & commissioning of G.I. Pipes Class 'C' (Heavy grade) conforming to I.S. 1239 with G.I. Fittings conforming to IS : 1879 (Part I to X) such as tees, crosses, plug, socket, elbows, reducers, flange, check nut, flanges & clamps, hanger, structural steel supports as required/directed at Site including wrapping alround (PYPKOTE) etc. complete in all respect . |  |  | 0 | 0 | 0
a) | 20 mm dia | RM |  | 250 | 205 | 455 | 244 | 200
b) | 25 mm dia | RM |  | 322 | 221 | 543 | 314 | 216
c) | 32 mm dia | RM |  | 384 | 271 | 655 | 375 | 264 |  | 118 | 118 |  | 118.4 | 118.4 |  | 44400 | 44400 |  | 31257.6 | 31257.6
d) | 40 mm dia | RM | 65 | 430 | 324 | 754 | 420 | 316 | 122 | 0 | 122 | 26.2 | 104.2 | 130.4 | 52460 | 0 | 52460 | 8279 | 32927.2 | 41206.2
e) | 50 mm dia | RM | 65 | 543 | 377 | 920 | 530 | 368 | 148 | 0 | 148 |  |  |  | 80364 | 0 | 80364
| Reduced by 148 Mtr | [8 empty] | -148 | -148 |  |  |  |  | -80364 | -80364
3 | Providing and fixing wafer end type cast iron butterfly valves conforming to IS : 13095 & BS : 5155 tested to 16 kg/sq.cm pressure (including flanges) (for bore well discharge pipe & water meter).
a) | 50mm dia | Each | 2 | 1277 | 936 | 2213 | 1248 | 915 |  |  |  |  | 6 | 6 |  |  |  |  | 5490 | 5490
b) | 65 mm dia | Each | 2 | 1428 | 1208 | 2636 | 1396 | 1180 |  |  |  |  | 2 | 2 |  |  |  |  | 2360 | 2360
c) | 80 mm dia | Each |  | 1578 | 1555 | 3133 | 1542 | 1520
4 | Providing, fixing, testing and commissioning of dual plated Non Return Valve PN 16 rating (16 kg/cm2 pressure rating) conforming to IS :5312 complete with nuts, bolts & washers & matching flanges.
a) | 50 mm dia | Each | 1 | 3228 | 936 | 4164 | 3155 | 915
b) | 65 mm dia | Each | 1 | 5561 | 1208 | 6769 | 5436 | 1180
c) | 80 mm dia | Each |  | 8373 | 1555 | 9928 | 8185 | 1520
5 | Making connection to existing city water main by tapping to gunmetal ferrule of 25 mm dia including excavation, bailing out water and filling back the excavated earth & C.I. water meter chamber cover, cutting & threading the pipe etc. getting approval from concerned authorities. | Each | 1 | 2339 | 35084 | 37423 | 2286 | 34298
6 | Constructing brick masonry chamber (for housing valves, meters etc.) with 75 class designation brick work in cement mortar 1:5 (1 cement :5 fine sand) for valves cement conc. top slab 1:2:4 (1 cement :2 coarse sand :4 graded stone aggregate 20 mm nominal size) necessary excavation, foundation conc. 1:5:10 (1 cement :5 fine sand :10 graded stone aggregate 40 mm nominal size) & inside plastering with cement mortar 1:3 (1 cement :3 coarse sand) 12 mm thick finished with a floating coat of neat cement complete as per standard design:
For valve/ meter chamber
a) | 300x300x600 mm size (inside) chamber with D.I. cover (lockable) size 250x250 mm (inside) with DI frame fixed in cement conc. Slab. | Each | 2 | 1014 | 4619 | 5633 | 991 | 4515
b) | 450x450x750 mm size (inside) chamber with D.I. lockable 300 x 300 mm (inside) with D.I. frame fixed in cement conc. slab. | Each |  | 2624 | 7017 | 9641 | 2565 | 6859
7 | Providing, fixing, testing & commissioning of cast iron air release valve conforming to IS : 14845 : 2000 including all fitting & accessories.
a) | 40mm dia | Each | 1 | 4056 | 175 | 4231 | 3965 | 171
b) | 50mm dia | Each | 1 | 4294 | 234 | 4528 | 4197 | 228
[7 empty] | 0 | 0
TOTAL FOR EXTERNAL WATER SUPPLY SYSTEM
B | GARDEN HYDRANT SYSTEM
1 | Providing & laying UPVC pressure pipes of 10Kg/Sq.cm pressure rating class V (IS : 4985-2000) including fittings, tees, bends, clamps, coupling and adaptors supports, and jointing with solvent joint, testing and necessary earth work in excavation, backfilling, disposal of surplus earth with a lead up to 100m complete, compaction and consolidation Including sand bedding all around UPVC pipe & fittings and thrust blocks at bends as per standard design (For garden hydrants).
a) | 32 OD | RM | 75 | 70 | 304 | 374 | 68 | 297
b) | 63 OD | RM |  | 269 | 339 | 608 | 262 | 331
[7 empty] | 0 | 0
2 | Providing and fixing forged brass body quarter turn lever operated ball valve with forged brass hard chrome plated ball, disc & gland packing shall be PTEF tested to 25 Kg/Sq.cm pressure including GI nipple and threaded hose receiver complete as required. | [5 empty] | 0 | 0
a) | 25 mm nominal bore | Each | 10 | 741 | 228 | 969 | 724 | 222
b) | 32 mm nominal bore | Each |  | 1148 | 297 | 1445 | 1122 | 290
[7 empty] | 0 | 0
3 | Construction brick masonry chamber with 75 class designation brick work in cement mortar 1:5 (1 cement : 5 find sand) for valve, with CI surface box 100 x 100 x 75 mm (inside) with hinged cover fixed in cement concrete slab 1:2:4 mix (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) necessary excavation foundation concrete 1:5:10 (1 cement : 5 fine sand : 10 graded stone aggregate 40mm nominal size) and inside plastering with cement mortar 1:3 (1 cement : 3 coarse sand) 12 mm thick finished with a floating coat of neat cement complete as per standard design. | [5 empty] | 0 | 0
| (For Housing Lawn hydrant) | [5 empty] | 0 | 0
a) | 300 x 300 x 600 mm deep | Each | 10 | 1193 | 4619 | 5812 | 1166 | 4515
b) | 600 x 600 x 750 mm deep | Each |  | 1193 | 8186 | 9379 | 1166 | 8002
TOTAL FOR GARDEN HYDRANT SYSTEM
C | EXTERNAL SEWERAGE SYSTEM
1 | Excavating trenches of required width for pipes, cables, etc including excavation for sockets also including for cement concrete cradles, and dressing of sides, ramming of bottoms, depth up to 1.5m including getting out the excavated soil, and then returning the soil as required, in layers not exceeding 20 cm in depth including consolidating each deposited layer with minimum 95% by ramming, watering etc. and disposing off surplus excavated soil as directed, within a lead of 50 m.
a) | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm dia and depth as required . | RM | 725 | 0 | 269 | 269 |  | 262 |  |  |  | 35.2 | 589.11 | 624.31 |  |  |  | 9225 | 154346.82 | 163571.82
b) | Pipes, cables etc. exceeding 300 mm dia but not exceeding 600mm dia.and depth as required . | RM |  | 0 | 403 | 403 |  | 393
0
2 | Providing, fixing, jointing, testing and commissioning of UPVC Drainage Pipe conforming to IS : 15328-2000 with all fittings such as bends, tees, elbow. The wall thickness of pipe and technical characteristic conforms to IS : 15328-2000 type SN4 & SN8. The fitting dimension conforming to BS : EN 1401-1998. The jointing to be completed with rubber ring/solvent weld joint. | [6 empty] | 0
a) | 110 mm OD U-Drain Pipe (SN8) | RM | 230 | 414 | 146 | 560 | 404 | 142
b) | 160 mm OD U-Drain Pipe (SN4) | RM | 195 | 747 | 187 | 934 | 730 | 182
c) | 200 mm OD U-Drain Pipe (SN4) | RM | 300 | 1719 | 234 | 1953 | 1680 | 228 | 234 | 0 | 234 | 35.2 | 173.01 | 208.21 | 402246 | 0 | 402246 | 8028 | 39446.28 | 47474.28
0
3 | Providing and laying 150 mm thick cement concrete 1:5:10 mix ( 1 cement : 5 coarse Sand : 10 graded stone aggregate 40 mm nominal size) all-round S.W pipe including bed concrete 150 mm as per standard design. | [6 empty] | 0
a) | 100 mm dia | RM | 230 | 0 | 898 | 898 |  | 877
b) | 150 mm dia | RM | 195 | 0 | 1116 | 1116 |  | 1091 |  |  |  | 37.72 | 114 | 151.72 |  |  |  | 42095.52 | 124374 | 166469.52
c) | 200 mm dia | RM | 300 | 0 | 1369 | 1369 |  | 1338 |  |  |  | 43.8 | 192.01 | 235.81 |  |  |  | 58884 | 256909.38 | 315793.38
d) | 250 mm dia. | RM |  | 0 | 2171 | 2171 |  | 2122
0
4 | Providing and fixing square mouth (S.W) gully trap grade `A' complete with C.I. grating brick masonry chamber with bricks of class designation 75 and water tight double seal C.I. cover with frame of 300 x 300 mm internal size. The weight of cover to be not less than 4.5 kg and frame to be not less than 2.70 kg. as per standard design. | [6 empty] | 0
a) | 100 x 100 mm size ‘P’ type. | Each |  | 417 | 4549 | 4966 | 407 | 4447 |  | 21 | 21 |  | 21 | 21 |  | 8547 | 8547 |  | 93387 | 93387
| referance with BH 8 Nos | [14 empty] | 0 | 0
b) | 150 x 150 mm size 'P' type | Each | 30 | 417 | 4549 | 4966 | 407 | 4447 | [7 empty] | 0 | 0 |  | 0 | 0
c) | 180 x 150 mm size 'P' type | Each |  | 417 | 4549 | 4966 | 407 | 4447
5 | Constructing brick masonry Rectangular manhole in cement mortar 1:4 mix (1cement: 4 coarse sand) RCC slab with 1:2:4 mixed (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size)and foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement making channels in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) finished with a floating coat of neat cement complete as per standred design.With ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (light duty ) internal size 450 mm x 600mm ,conforming to I.S. 12592 specifications of the brand as approved . | [6 empty] | 0
b. | Insize 90 x80 cms x depth beyond 550 cms to 750 cm | Each | 35 | 1134 | 11110 | 12244 | 1108 | 10861
6 | Constructing brick masonry circular type manhole 75 class designation bricks in cement mortar 1:5 mix (1cement: 5 coarse sand) inside and outside cement plaster 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement, fixing manhole frame, foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and making channels and haunchig in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) including excavation, back filling and disposal of surplus earth, providing and embedding 12mm dia M.S polypropylene coated manhole steps centre to centre distnce 300 mm embedded in cement concrete block size 200x200x100 mm using cement concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) neatly finished complete as per standred design. | [6 empty] | 0
a. | 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . | Each |  | 2011 | 16372 |  | 1965 | 16005 | 20 | 0 | 20 | 4 | 15 | 19 | 39300 | 0 | 39300 | 64020 | 240075 | 304095
|  |  |  | 0 | 0 | 0
7 | Making connection of sewer line existing manhole including breaking into and making good the walls, floors with cement concrete 1:2:4 mix (1 cement :2 coarse sand : 4 graded stone aggregate 20 mm nominal size) cement plastered on both sides with cement mortar 1:3 (1cement: 3 Coarse sand) finished with a floating coat of neat cement and making necessary channels for the drain etc. complete. | Each | 1 | 0 | 29236 | 29236 |  | 28581
TOTAL FOR EXTERNAL SEWERAGE SYSTEM
D | STORM WATER DRAINAGE SYSTEM
1 | Earth Work in Excavation of required width for storm water drainage pipes including excavation for sockets and dressing of sides, ramming of bottom depth up to 1.5 m including getting out the excavated soil and then returning the soil as required in layer not exceeding 20 cms in depth including consolidating each deposited layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 50 m for all kinds of soil.
a) | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM | 1000 | 0 | 269 | 269 |  | 262 |  |  |  | 121.3 | 91.13 | 212.43 |  |  |  | 31788 | 23868.66 | 55656.66
b) | Pipes, exceeding 300 mm dia but not exceeding 600 mm dia.depth as required . | RM |  | 0 | 403 | 403 |  | 393
0
2 | Providing, fixing & testing of UPVC rain water pipes (IS : 4985-1983 class-5 10 Kg/cm2 pressure) including injection moulded fittings (heavy duty) (plain or door) e.g. bends, junction, cowls, tees, offsets, access pieces etc. Clamps/Supports jointing with rubber ring/solvent cement joints including cutting chase or holes in walls and floors and making good as required at Site [Podium drainage]. | [6 empty] | 0
a) | 110 mm OD | RM | 300 | 613 | 146 | 759 | 599 | 142
|  |  |  | 0 | 0 | 0 | 0 | 0
3 | Providing, laying and jointing light duty non-pressure NP2 class S/S R.C.C. pipes with collars jointing with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including curing, testing of joints etc. |  |  | 0 | 0 | 0 | 0 | 0
a) | 250 mm dia | RM | 700 | 447 | 585 | 1032 | 436 | 571 | 150 | 0 | 150 | 147.6 | 91.13 | 238.73 | 65840 |  | 65840 | 84577 | 52035.23 | 136612.23
| Referance to BH | [8 empty] | 89 | 89 |  |  |  |  | 38804 | 38804
b) | 300 mm dia | RM |  | 578 | 702 | 1280 | 565 | 686
|  |  |  | 0 | 0 | 0 | 0 | 0
4 | Providing and laying 150 mm thick cement concrete 1:5:10 mix ( 1 cement : 5 coarse Sand : 10 graded stone aggregate 40 mm nominal size) upto haunches RCC pipe including bed concrete 150 mm as per standard design. |  |  | 0 | 0 | 0 | 0 | 0
a) | 250 mm dia | RM | 700 | 0 | 1153 | 1153 | 0 | 1127 |  |  |  | 121.3 | 91.13 | 212.43 |  |  |  | 136739 | 102703.51 | 239442.51
b) | 300 mm dia | RM | 0 | 0 | 1354 | 1354 | 0 | 1323
[7 empty] | 0 | 0
5 | Constructing brick masonry road gully chamber unit brick of class designated 75 in cement mortar 1:4 (1 cement :4 coarse sand) including 500 x 450 mm precast RCC horizontal grating with frame complete as per standard design. | [5 empty] | 0 | 0
| Inside size 50 x 45 x 60 cm | Each | 40 | 1343 | 7017 | 8360 | 1312 | 6859 |  | 18 | 18 |  | 18 | 18 |  | 23616 | 23616 |  | 123462 | 123462
|  |  |  | 0 | 0 | 0 | 0 | 0
6 | Constructing brick masonry Rectangular manhole in cement mortar 1:4 mix (1cement: 4 coarse sand) RCC slab with 1:2:4 mixed (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size)and foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement making channels in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) finished with a floating coat of neat cement complete as per standred design.With ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (light duty ) internal size 450 mm x 600mm ,conforming to I.S. 12592 specifications of the brand as approved . |  |  | 0 | 0 | 0 | 0 | 0
b. | Insize 90 x80 cms x depth beyond 550 cms to 750 cm | Each | 35 | 1134 | 12864 | 13998 | 1108 | 12575
[7 empty] | 0 | 0
7 | Constructing brick masonry circular type manhole 75 class designation bricks in cement mortar 1:5 mix (1cement: 5 coarse sand) inside and outside cement plaster 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) inside with a floating coat of neat cement, fixing manhole frame, foundation concreate 1:4:8 mix (1 cement:4 coarse sand:8 graded stone aggregate 40 mm nominal size) and making channels and haunchig in cement concrete concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) including excavation, back filling and disposal of surplus earth, providing and embedding 12mm dia M.S polypropylene coated manhole steps centre to centre distnce 300 mm embedded in cement concrete block size 200x200x100 mm using cement concrete 1:2:4 mix (1 cement:2 coarse sand:4 graded stone aggregate 20 mm nominal size) neatly finished complete as per standred design. | [5 empty] | 0 | 0
a. | 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . | Each |  | 2011 | 16372 | 18383 | 1965 | 16005 | 15 | 0 | 15 | 7 | 7 | 14 | 29475 | 0 | 29475 | 112035 | 112035 | 224070
|  |  |  | 0 | 0 | 0 | 0 | 0
8 | Rain Water Harvesting system : |  |  | 0 | 0 | 0 | 0 | 0
| Construction of rain water harvesting pit as per approved drawing . | Each |  | 0 | 177757 | 177757 | 0 | 173775
|  |  |  | 0 | 0 | 0 | 0 | 0
9 | Making connection of storm water line with external manhole including breaking into and making good the walls, floors with cement concrete 1:2:4 mix (1 cement :2 coarse sand : 4 graded stone aggregate 20 mm nominal size) cement plastered on both sides with cement mortar 1:3 (1cement: 3 Coarse sand) finished with a floating coat of neat cement and making necessary channels for the drain etc. complete. | Each | 1 | 0 | 64320 | 64320 | 0 | 62879
TOTAL FOR STORM WATER DRAINAGE SYSTEM
E | EXTERNAL FIRE HYDRANT SYSTEM
1 | Supply, Installation, Testing & Commissioning of the following size of Black Mild Steel Class `C' (heavy class) pipes conforming to IS : 1239 Part-I including cutting, threading, welding & all fittings like flanges, tees, elbows, bends junctions, reducers etc. welded or screwed joints, clamps & structural steel supports or as required/ directed at site including cutting & making good the walls, floors, RCC work etc cutting chases & filling the same with cement concrete 1:3:6 (1 cement :3 coarse sand :6 graded stone aggregate 20 mm nominal size) including Providing painting the pipes with 2 coats of desired shade of synthetic enamel paint over 2 coats of Red oxide primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. including Providing painting of legend both direction arrow as per the approved of project manager (For External Hydrant system) [Exposed Pipe].
a) | 80 mm dia | RM | 45 | 499 | 288 | 787 | 487 | 281
b) | 100 mm dia | RM | 35 | 736 | 394 | 1130 | 719 | 385
c) | 150 mm dia | RM |  | 1076 | 585 | 1661 | 1051 | 571
[7 empty] | 0 | 0
2 | Supply, Installation, Testing & Commissioning of the following size of Gun Metal two way fire brigade inlet connection to external hydrant ring/hydrant riser with 63 mm dia instantaneous type inlet and 100 mm dia flanges outlet conforming to IS:904 with blank cap and chain including 100 mm dia butterfly valve (PN 16 rating) and wafter type non-return valve complete with nuts, bolts, flanges and complete in all respect. Cost shall include a wall mounted box of M.S. construction (16 SWG) with glass door (4.0 mm thick) of adequate size (approx 0.6 m x 0.6 m x 0.45 m) to house the above mentioned component. | Each | 2 | 13479 | 6310 | 19789 | 13177 | 6168
[7 empty] | 0 | 0
3 | Providing and applying one coat of 4 mm thick 'PYPKOTE' or COATEK anti rust pipe protection conforming to IS: 10221 including PYPKOTE primer as per manufactures specifications and lap of 25 mm to make an impermeable layer on M.S. Pipes running underground /burried/in trenches complete including surface preparation including conducting holiday test. The application process shall be strictly according to manufacturers specification /recommendation. | [5 empty] | 0 | 0
a) | 80 mm dia | RM | 45 | 0 | 302 | 302 | 0 | 295 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[7 empty] | 0 | 440
b) | 100 mm dia | RM | 35 | 0 | 451 | 451 | 0 | 636
c) | 150 mm dia | RM |  | 0 | 651 | 651 | 0 | 0
4 | Stainless steel single headed ISI marked oblique pattern hydrant landing valve with 80mm dia flanged inlet & 63 mm dia instantaneous type female outlet complete with stainless steel cap and GI chain twist release type plugh and all accessories as per IS : 5290 -1983 (Type 'A') including fixing with anchor fasteners and flanged tapping from hydrant valve/Landing valve. (For External Hydrant) | Each | 4 | 5964 | 1035 | 6999 | 5830 | 1011
[7 empty] | 0 | 0
5 | Supply, Installation, Testing & Commissioning of the following size of 63 mm dia 15 m long non-percolating flexible hose (RRL- type A) as per IS : 636. Type "A" with Stainless Steel male & female instantaneous type coupling (IS 903) bound and riveted to hose pipe with copper rivets and 1.5 mm copper wire. | Each | 8 | 4533 | 58 | 4591 | 4431 | 56
[7 empty] | 0 | 0
6 | Supply, Installation, Testing & Commissioning of the following size of Standard Stainless Steel short size branch pipe with nozzle of 20 mm nominal bore outlet as per IS:903 suitable to fit with standard instantaneous type 63mm dia coupling ISI marked (IS:903) complete. | Each | 4 | 1730 | 35 | 1765 | 1691 | 34
[7 empty] | 0 | 0
7 | Supply, Installation, Testing & Commissioning of the following size of Weather proof standard fire hose cabinet (750 mm x 600 mm x 300 mm deep) made of 16 SWG powder coated M.S. sheet having single or double opening glazed (4.0 mm thick glass) shutter including necessary locking arrangement by allan key, stove enamelled Fire red finish (as per IS : 5, shade no. 536) with " Fire Hose" marked on front, suitable for housing 2 nos. 15m long 63 mm dia Hose pipe, 1 No. branch pipe & nozzle spanner. | Each | 4 | 4771 | 877 | 5648 | 4664 | 857
[7 empty] | 0 | 0
8 | Supply, Installation, Testing & Commissioning of the following size of C.I. Butterfly valve conforming to IS : 13095 with nut, bolts and washers complete. [PN -1.6 rating (16kg/cm2)] | [5 empty] | 0 | 0
a) | 150 mm dia | Each |  | 2856 | 2959 | 5815 | 2792 | 2892 |  | 4 | 4 |  | 4 | 4 |  | 11168 | 11168 |  | 11568 | 11568
b) | 100 mm dia | Each | 4 | 2029 | 2175 | 4204 | 1983 | 2126 |  | 4 | 4 |  | 4 | 4 |  | 7932 | 7932 |  | 8504 | 8504
c) | 80 mm dia | Each |  | 1578 | 1631 | 3209 | 1542 | 1594 |  | 2 | 2 |  | 2 | 2 |  | 3084 | 3084 |  | 3188 | 3188
[7 empty] | 0 | 0
9 | Supply, Installation, Testing & Commissioning of the following size of Gun Metal four way fire brigade inlet connection to external hydrant ring/hydrant riser with 4 Nos. 63 mm dia instantaneous type inlet and 150 mm dia flanges outlet conforming to IS:904 with blank cap and chain including 150 mm dia butterfly valve (PN 16 rating) and wafter type non-return valve complete with nuts, bolts, flanges and complete in all respect. Cost shall include a wall mounted box of M.S. construction (16 SWG) with glass door (4.0 mm thick) of adequate size (approx 0.6 m x 0.6 m x 0.45 m) to house the above mentioned component.[Location Outside the Building for External Fire Ring & Internal Fire Hydrant System]. | Each |  | 26600 | 9063 | 35663 | 26004 | 8859
[7 empty] | 0 | 0
10 | Supply, Installation, Testing & Commissioning of the following size of Bourdon type Stainless Steel dial type pressure gauge with brass isolation valve and pipe. | [5 empty] | 0 | 0
| Dial Diameter : 100 mm | [5 empty] | 0 | 0
| Caliberation : 0-15 Kg/cm2 | Each | 4 | 1431 | 175 | 1606 | 1398 | 171
TOTAL OF FIRE HYDRANT (EXTERNAL)
0
| TOTAL OF EXTERNAL WORK | [13 empty] | 669685 | 57187 | 726872 | 702718.23 | 1438200.68 | 2140918.91
NS | CP Grating 63 dia | Nos |  |  |  |  | 59 | 131 |  | 66 | 66 |  | 66 | 66 |  | 3894 | 3894 |  | 8646 | 8646
NS | CP Grating 160dia | [5 empty] | 166 | 230 |  | 10 | 10 |  | 10 | 10 |  | 1660 | 1660 |  | 2300 | 2300
[13 empty] | 0 |  |  | 0 | 0 |  | 0 | 0
NS | SS FCO 200 dia | Nos |  |  |  |  | 3536 | 230 |  |  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0
| SS FCO 160 dia | Nos |  |  |  |  | 2048 | 230 |  | 5 | 5 |  | 5 | 5 |  | 10240 | 10240 |  | 1150 | 1150
| SS FCO 100 dia | Nos |  |  |  |  | 580 | 230 |  | 8 | 8 |  | 8 | 8 |  | 4640 | 4640 |  | 1840 | 1840
[19 empty] | 0 | 0
NS | Y Strainer 100mm | Nos |  |  |  |  | 4632 | 2300 | [10 empty] | 0 | 0
| Y Strainer 80mm | Nos |  |  |  |  | 3088 | 2300 | [10 empty] | 0 | 0
| Y Strainer 65mm | Nos |  |  |  |  | 2533 | 2300 | [10 empty] | 0 | 0
[19 empty] | 0 | 0
NS | Toilet Rework | Nos | [5 empty] | 575 |  |  |  |  | 61 | 61 |  |  |  |  | 35075 | 35075
[19 empty] | 0 | 0
0
0
| GRAND TOTAL | [14 empty] | 20434 | 20434 |  | 49011 | 49011

## HVAC BH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
BOYS HOSTEL HVAC RA-10
S.No. | DESCRIPTION | Unit | Qty | Supply Rate | Supply Amount | ITC Rate | ITC Amount | SITC Rate | SITC Amount | GST Rates |  | SUPPLY QTY |  |  | SUPPLY AMOUNT |  |  | ITC QTY |  |  | ITC AMOUNT
[10 empty] | Supply Rate | ITC Rate | PREV. | NOW | CUMM. | PREV. | NOW | CUMM. | PREV. | NOW | CUMM. | PREV. | NOW | CUMM.
1 | Outdoor Units
Supply,Receiving ,Handling ,Installation, testing and commissioning of Variable Refrigerant Flow modular type airconditioning system complete with outdoor units and refrigerant piping, control cabling as per detail given in drawing and having following items:
1.1 | Modular type outdoor units equipped with highly efficient scroll/twin rotary type compressors with at least one invertor/digital and other constant speed type compressors, special precoated heat exchanger, low noise condenser fan housed in compact housing duly powder coated. Outdoor units shall have both cooling & heat pump mode, consisting of one/multiple modules with digital vapour injection/inverter scroll technology based compressor and environment friendly refrigerant R-410A/407c. Unit shall be full charged of refrigerant and oil. The unit should have a minimum COP of 3.15 at 100% load in Delhi /gurgaon out door environmental conditions. The unit should have atleast 50% inverter in each units module. The C.O.P confirmation should be from the OEM letter.Complete with discharge cowl having same finish as outdoor unit and MS based frame duly primered and painted, supports etc. The cost shall include the cost of discharge cowl and Cabling from MCB (by others) to the outdoor unit as per the drawing for the following capacities. (Assuming cable length of 1.5 to 2 meter as per drawing)
[7 empty] | 0 | 0 | 0
a) | 14 HP Outdoor unit | Nos. | 1 | 184417 | 184417 | 14159 | 14159 | 198576 | 198576 | 181768 | 13901 | 3 |  | 3 | 553251 | 0 | 553251 |  | 3 | 3 |  | 41703 | 41703
b) | 18 HP Outdoor unit | Nos. | 3 | 236681 | 710043 | 14159 | 42477 | 250840 | 752520 | 232373 | 13901 | 2 |  | 2 | 473362 | 0 | 473362 |  | 2 | 2 |  | 27802 | 27802
c) | 20 HP Outdoor unit | Nos. | 1 | 251580 | 251580 | 14159 | 14159 | 265739 | 265739 | 247001 | 13901 | 5 |  | 5 | 1257900 | 0 | 1257900 |  | 5 | 5 |  | 69505 | 69505
d) | 22 HP Outdoor unit | Nos. | 4 | 276830 | 1107320 | 14159 | 56636 | 290989 | 1163956 | 271791 | 13901 | 3 |  | 3 | 830490 | 0 | 830490 |  | 3 | 3 |  | 41703 | 41703
e) | 24 HP Outdoor unit | Nos. | 4 | 337149 | 1348596 | 18804 | 75216 | 355953 | 1423812 | 331012 | 18461 | 7 |  | 7 | 2360043 | 0 | 2360043 |  | 7 | 7 |  | 129227 | 129227
f) | 26 HP Outdoor unit | Nos. | 1 | 354705 | 354705 | 18804 | 18804 | 373509 | 373509 | 348249 | 18461 | 4 |  | 4 | 1418820 | 0 | 1418820 |  | 4 | 4 |  | 73844 | 73844
g) | 30 HP Outdoor unit | Nos. | 2 | 406968 | 813936 | 18804 | 37608 | 425772 | 851544 | 399561 | 18461 | 13 |  | 13 | 5290584 | 0 | 5290584 |  | 13 | 13 |  | 239993 | 239993
h) | 32 HP Outdoor unit | Nos. | 4 | 421866 | 1687464 | 22202 | 88808 | 444068 | 1776272 | 414188 | 21797 | 2 |  | 2 | 843732 | 0 | 843732 |  | 2 | 2 |  | 43594 | 43594
i) | 34 HP Outdoor unit | Nos. | 2 | 439422 | 878844 | 22202 | 44404 | 461624 | 923248 | 431424 | 21797 | 1 |  | 1 | 439422 | 0 | 439422 |  | 1 | 1 |  | 21797 | 21797
j) | 36 HP Outdoor unit | Nos. | 1 | 445197 | 445197 | 22202 | 22202 | 467399 | 467399 | 437094 | 21797 | 1 |  | 1 | 445197 | 0 | 445197 |  | 1 | 1 |  | 21797 | 21797
k) | 40 HP Outdoor unit | Nos. | 11 | 508849 | 5597339 | 28206 | 310266 | 537055 | 5907605 | 499587 | 27692 | 7 |  | 7 | 3561943 | 0 | 3561943 |  | 7 | 7 |  | 193844 | 193844
l) | 42 HP Outdoor unit | Nos. | 3 | 594895 | 1784685 | 32737 | 98211 | 627632 | 1882896 | 584067 | 32141 | 1 |  | 1 | 594895 | 0 | 594895 |  | 1 | 1 |  | 32141 | 32141
m) | 44 HP Outdoor unit | Nos. | 1 | 609795 | 609795 | 32737 | 32737 | 642532 | 642532 | 598696 | 32141 | 4 |  | 4 | 2439180 | 0 | 2439180 |  | 4 | 4 |  | 128564 | 128564
n) | 46 HP Outdoor unit | Nos. | 3 | 615570 | 1846710 | 32737 | 98211 | 648307 | 1944921 | 604366 | 32141 | 2 |  | 2 | 1231140 | 0 | 1231140 |  | 2 | 2 |  | 64282 | 64282
o) | 50 HP Outdoor unit | Nos. | 2 | 676956 | 1353912 | 36135 | 72270 | 713091 | 1426182 | 664635 | 35477 | 1 |  | 1 | 676956 | 0 | 676956 |  | 1 | 1 |  | 35477 | 35477
p) | 52 HP Outdoor unit | Nos. | 2 | 695955 | 1391910 | 39534 | 79068 | 735489 | 1470978 | 683288 | 38814 |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
q) | 54 HP Outdoor unit | Nos. | 1 | 701730 | 701730 | 41799 | 41799 | 743529 | 743529 | 688958 | 41038 | 1 |  | 1 | 701730 | 0 | 701730 |  | 1 | 1 |  | 41038 | 41038
2 | Indoor Units
a) | Supply, Receiving,Handling,Installation,testing and commissioning of following Wall Mounted/Ductable type units of indoor VRV/VRF Air Conditioners with decorative panel, cordless remote control complete as required.The units shall be suitable for 230V±6%, or 415V±10%, 50 Hz. supply & complete with electrical controls & panels. The cost of indoor unit shall include the cost of wire 3 x 2.5 sqmm in a length of 2 meters with plug top as per details given below.
The fan shall be dual suction, aerodynamically designed turbo, multi blade type, statically & dynamically balanced to ensure low noise and vibration free operation of the system. The fan shall be direct driven type, mounted directly on motor shaft having supported from housing.
The cooling coil shall be made out of seamless copper tubes and have continuous aluminum fins. The fins shall be spaced by collars forming an integral part. The tubes shall be staggered in the direction of airflow. The tubes shall be hydraulically/ mechanically expanded for minimum thermal contact resistance with fins. Each coils shall be factory tested at 21kg/sqm air pressure under water.
Unit shall have cleanable type filter fixed to an integrally moulded plastic frame. The filter shall be slide away type and neatly inserted.
Note: All Ductable units having in-Built Drain Pump for drains.
HI WALL
i | 1.05 TR (335 CFM) | No. | 378 | 12835 | 4851630 | 1812 | 684936 | 14647 | 5536566 | 12601 | 1779 | 370 |  | 370 | 4748950 | 0 | 4748950 | 264 | 106 | 370 | 469656 | 188574 | 658230
ii | 1.33 TR (424 CFM) | No. | 45 | 13644 | 613980 | 1925 | 86625 | 15569 | 700605 | 13395 | 1889 | 30 |  | 30 | 409320 | 0 | 409320 | 18 | 12 | 30 | 34002 | 22668 | 56670
ii | 1.65 TR (530 CFM) | No. | 142 | 15723 | 2232666 | 2039 | 289538 | 17762 | 2522204 | 15436 | 2001 | 139 |  | 139 | 2185497 | 0 | 2185497 | 102 | 36 | 138 | 204102 | 72036 | 276138
ii | 2.07 TR (271 CFM) | No. | 332 | 16358 | 5430856 | 2265 | 751980 | 18623 | 6182836 | 16060 | 2223 | 290 |  | 290 | 4743820 | 0 | 4743820 | 208 | 82 | 290 | 462384 | 182286 | 644670
DUCTABLE TYPE
i | 6.50 TR (2047 CFM) | No. | 2 | 47722 | 95444 | 5097 | 10194 | 52819 | 105638 | 46853 | 5004 | 17 |  | 17 | 811274 | 0 | 811274 |  | 17 | 17 |  | 85068 | 85068
ii | 8.19 TR (2542 CFM) | No. | 5 | 48011 | 240055 | 5663 | 28315 | 53674 | 268370 | 47137 | 5559 | 5 |  | 5 | 240055 | 0 | 240055 |  | 5 | 5 |  | 27795 | 27795
b) | Supplying, installing, testing and commissioning of Modular type Ceiling mounted Double skin Air Handling Unit complete with cooling coil of copper tubes with aluminium fins (12 fins / inch) and condensate drain pan of stainless steel with insulation. Blower section with DIDW backward curved blower impeller drive set with high efficiency motor suitable for 415±10% volt, 3 phase 50 Hz supply to meet LEED requirements. Fine filters MERV 13 as per LEED parameters. .It should consist fan section & canvas connection cooling coils, earthing of motor and unit with necessory wiring vibration isolator and supporting frame.
i | Capacity 6000 CFM, 15.5 TR at 30 mm static pressure, 4 rows deep coil area, motor rating 3.7 KW for Common area of level 3 | Nos | 4 | 376672 | 1506688 | 10195 | 40780 | 386867 | 1547468 | 369816 | 10009 | 4 |  | 4 | 1506688 | 0 | 1506688 |  | 4 | 4 |  | 40036 | 40036
ii | Capacity 7000 CFM, 25 TR at 30 mm static pressure, 4 rows deep coil area, motor rating 3.7 KW for Common area of level 3 | Nos | 1 | 501170 | 501170 | 10195 | 10195 | 511365 | 511365 | 492048 | 10009 | 1 |  | 1 | 501170 | 0 | 501170 |  | 1 | 1 |  | 10009 | 10009
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0
2.1 | Supply, Receiving,tesing and commissioning of Imported Remote controllers (Corded) for operation of indoor units | Nos | 915 | 1132 | 1035780 | 169 | 154635 | 1301 | 1190415 | 1111 | 165 | 852 |  | 852 | 964464 | 0 | 964464 |  | 852 | 852 |  | 140580 | 140580
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Supply,Receiving,tesing and commissioning of Imported fittings Y-joints, distributer and headers for all Indoor units at both the floors layout as per layout drawings | Nos | 915 | 5435 | 4973025 | 509 | 465735 | 5944 | 5438760 | 5336 | 499 | 823 | 6 | 829 | 4473005 | 32016 | 4505021 | 486 | 343 | 829 | 242514 | 171157 | 413671
0
3 | Refrigerant Piping | [21 empty] | 0
| Supply, Receiving, Handling, Installation, testing and commissioning of interconnecting copper refrigerant pipe work duly insulated (13/19 mm thick) with elastomeric nitrile rubber type tubular insulation between indoor & outdoor units. All piping inside the room shall be properly supported with hanger and all external piping shall run in covered cable tray. Only two upper size of refrigerant piping on terrace level are exposed. | [21 empty] | 0
a) | 41.3mm OD with 19 mm thick nitrile rubber insulation | RM | 606 | 1175 | 712050 | 271 | 164226 | 1446 | 876276 | 1153 | 266 | 61.4 | 46.2 | 107.6 | 72145 | 53268.6 | 125413.6 |  | 115.87 | 115.87 |  | 30821.42 | 30821.42
b) | 34.9mm OD with 19 mm thick nitrile rubber insulation | RM | 1044 | 914 | 954216 | 249 | 259956 | 1163 | 1214172 | 897 | 244 | 61.4 | 92.4 | 153.8 | 56119.6 | 82882.8 | 139002.4 |  | 147.4 | 147.4 |  | 35965.6 | 35965.6
c) | 28.6mm OD with 19 mm thick nitrile rubber insulation | RM | 995 | 542 | 539290 | 237 | 235815 | 779 | 775105 | 532 | 232 | 323 | 955.8 | 1278.8 | 174958 | 508485.6 | 683443.6 |  | 1273.58 | 1273.58 |  | 295470.56 | 295470.56
d) | 22.2mm OD with 19 mm thick nitrile rubber insulation | RM | 1340 | 417 | 558780 | 226 | 302840 | 643 | 861620 | 409 | 221 | 216 | 84 | 300 | 89989 | 34356 | 124345 |  | 253.77 | 253.77 |  | 56083.17 | 56083.17
e) | 19.1mm OD with 13 mm thick nitrile rubber insulation | RM | 1045 | 334 | 349030 | 192 | 200640 | 526 | 549670 | 327 | 188 | 400 | 303 | 703 | 133600 | 99081 | 232681 |  | 672.27 | 672.27 |  | 126386.76 | 126386.76
f) | 15.9mm OD with 13 mm thick nitrile rubber insulation | RM | 4270 | 276 | 1178520 | 169 | 721630 | 445 | 1900150 | 270 | 165 | 1694 | 2726.4 | 4420.4 | 467544 | 736128 | 1203672 | 1694 | 2652.38 | 4346.38 | 279510 | 437642.7 | 717152.7
g) | 12.7mm OD with 13 mm thick nitrile rubber insulation | RM | 840 | 184 | 154560 | 135 | 113400 | 319 | 267960 | 180 | 132 | 1386 | 893 | 2279 | 255024 | 160740 | 415764 | 947 | 1213.1 | 2160.1 | 125037 | 160129.2 | 285166.2
h) | 9.5mm OD with 13 mm thick nitrile rubber insulation | RM | 3780 | 139 | 525420 | 124 | 468720 | 263 | 994140 | 136 | 121 | 1927 | 2804 | 4731 | 267853 | 381344 | 649197 | 1927 | 2621 | 4548 | 233167 | 317141 | 550308
i) | 6.4mm OD with 13 mm thick nitrile rubber insulation | RM | 400 | 95 | 38000 | 113 | 45200 | 208 | 83200 | 93 | 110 | 1294 | 0 | 1294 | 122930 | 0 | 122930 | 947 | 314.45 | 1261.45 | 104198 | 34589.5 | 138787.5
0
4 | Transmission & Control Wiring | [21 empty] | 0
| Supply,Providing & fixing control cum transmission wiring in medium duty PVC Conduit between indoor and outdoor units. | [21 empty] | 0
0
a) | 2C x 1.5 Sqmm Cu Cable | RM | 13500 | 87 | 1174500 | 31 | 418500 | 118 | 1593000 | 85 | 30 | 5300 | 3429 | 8729 | 457500 | 291465 | 748965 | 4947 | 3781.73 | 8728.73 | 148401 | 113451.9 | 261852.9
5 | Air Washer for kitchen fresh air
Supply,Receiving,Handling, installation, testing and commissioning of synthetic fill pad type single skin type air washer (at 500 FPM velocity across pads), DIDW Class-I forward curved centrifugal fan with TEFC weather proof motor of IP: 55 protection suitable for 415 +10% Volts, 3 phase, 50 cycles power supply, mounted on a common base with metallistik vibration isolators, multi sheave pullies for fan and fan motor. The fan capacity shall be based on outlet velocity not exceeding 2200 FPM. The cooler shall be complete with 8" thick celdek fill, 1.25mm (18 G) thick FRP(fiber reinforcement plastic) steel reinforced /S.S tank,tank should be 300 mm deep in basin, water pump distribution pipe, distribution pan, filters at air inlet, water piping, make up water connection with ball valve, drain and overflow connection, all housed in 18 G G.I Sheets casing mounted on vibration isolators. The air washer shall come in knock down condition complete in all respects as per specifications and drawings. Capacity of coolers shall be as under:
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| Accessories namely make up, drain, overflow, quick fill valves, float valve, fire retardant flexible connection, volume control dampers at fan outlet, vibration isolators and foundations bolts shall be included. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| Capacity 34000 CFM at 50 mm static pressure for fresh air supply. | Nos | 1 | 354885 | 354885 | 7929 | 7929 | 362814 | 362814 | 348426 | 7784 | [5 empty] | 0
6 | Exhaust Air Scrubbers for Kitchens
Supplying, Installing, Testing and Commissioning of Scrubber (nozzle type double skin air washer). Air washer shall be factory fabricated and complete with fan casing, humidifier section, FRP coated steel tank, DIDW centrifugal backward curved fan with V belt drive motor monbloc pumps, brass spray nozzles and water distribution header, piping with valves and fittings between pumps and air washer, 4 bend PVC/GI eliminator
| Capacity 42600 CFM static pressure 50mm blower | Nos | 1 | 594773 | 594773 | 7929 | 7929 | 602702 | 602702 | 583948 | 7784 | [5 empty] | 0
7 | Condensate Drain Piping
Supply,Providing, fixing and testing uPVC drain piping for condensate from room Indoor unit to nearest suitable drain system as per site conditions as instructed by site engineer complete with all required fittings and providing clean out plug at suitable location for roding the pipe when required complete with 2 layers of 6mm thickness with elastomeric nitrile rubber insulation over uPVC pipe:
a) | 40mm OD | RM | 400 | 114 | 45600 | 113 | 45200 | 227 | 90800 | 111 | 110 | 400 | 0 | 400 | 45600 | 0 | 45600 | 216 | 97.4 | 313.4 | 23738 | 10714 | 34452
b) | 32mm OD | RM | 2200 | 84 | 184800 | 90 | 198000 | 174 | 382800 | 82 | 88 | 2200 | 0 | 2200 | 184800 | 0 | 184800 | 727 | 361.88 | 1088.88 | 63936 | 31845.44 | 95781.44
| Qty Shifted to GH By 1000 mtr | [8 empty] | -82 |  |  | 1111 | 1111 |  | -91102 | -91102
c) | 25mm OD | RM | 3100 | 62 | 192200 | 79 | 244900 | 141 | 437100 | 60 | 77 | 3100 | 0 | 3100 | 192200 | 0 | 192200 | 503 | 213.2 | 716.2 | 38746 | 16416.4 | 55162.4
| Sub Total of Section - II Carried Over to Summary |  |  |  | 50106101 |  | 7104853 | 0 | 57210954
III | Air Distribution System | [5 empty] | 0 | 0 | 0
1 | Ducting: | [5 empty] | 0 | 0 | 0
| Supply, fabricating, installing and testing of G.I. Sheet metal ducts and flanges as per IS specifications complete with supports, Vanes, dampers, links, levers and quadrants etc. as per specifications and drawings. The rates shall include all materials and labour for suspension and supporting arrangement of galvanised steel for Plenums, Ducts, complete with fire retardant factory fabricated flexible connection as per required specifications | Site Facbricated |  |  |  |  | 0 | 0 | 0
a) | 0.63 MM (24 Gauge ) | Sqm | 100 | 431 | 43100 | 226 | 22600 | 657 | 65700 | 423 | 221 | 2450 | 49 | 2499 | 1049950 | 20727 | 1070677 |  | 2499.07 | 2499.07 |  | 552294.47 | 552294.47
b) | 0.80 MM (22 Gauge ) | Sqm | 50 | 517 | 25850 | 260 | 13000 | 777 | 38850 | 507 | 255 | 100 | 0 | 100 | 51440 |  | 51440 |  | 100.25 | 100.25 |  | 25563.75 | 25563.75
c) | 1.00 MM (20 Gauge ) | Sqm | 50 | 618 | 30900 | 294 | 14700 | 912 | 45600 | 606 | 288 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 0
d) | 1.25 MM (18 Gauge ) | Sqm | 0 | 781 | 0 | 328 | 0 | 1109 | 0 | 766 | 322 | 50 | 0.49 | 50.49 | 38960 |  | 38960 |  | 50.39 | 50.39 |  | 16225.58 | 16225.58
[7 empty] | 0 | 0 | 0
2 | Grilles & Diffusers | [5 empty] | 0 | 0 | 0
1 | Providing, fixing, testing and commissioning of powder coated extruded aluminium grills . | [5 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
a) | Supply/Exhaust Grills with Dampers | Sqm | 1 | 6369 | 6369 | 475 | 475 | 6844 | 6844 | 6253 | 466
[10 empty] | 0 | 0
b) | Supply/Exhaust Grills without Dampers | Sqm | 1 | 3380 | 3380 | 475 | 475 | 3855 | 3855 | 3318 | 466
[7 empty] | 0 | 0 | 0
3 | Thermal Insulation: | [5 empty] | 0 | 0 | 0
| Supplying, installation, testing and commissioning of thermal insulation with 9mm thick, 40-60 Kg / M³ density closed cell elastomeric nitrile rubber, class 'O' secured with manufacturer's adhesive. The duct supports should also be of nitrile rubber with PUF/PIR inserts. | Sqm | 150 | 297 | 44550 | 283 | 42450 | 580 | 87000 | 291 | 277 | 792 | 861 | 1653 | 231192 | 250551 | 481743 |  | 1653.36 | 1653.36 |  | 457980.72 | 457980.72
[7 empty] | 0 | 0 | 0
4 | Acoustic Lining of Ducts: | [5 empty] | 0 | 0 | 0
| Supplying, installing, testing & commissioning of duct acoustic lining with 25mm thick, density shall not be less than 48 kg/cu.m of acoustic lining within supply air ducts as per the specifications. All ducts shown cross hatched on the approved shop drawings shall be provided with acoustic lining of fibre glass insulation as per the specifications. | [5 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
a) | Supply air duct with 25mm thick acoustic lining | Sqm | 50 | 161 | 8050 | 962 | 48100 | 1123 | 56150 | 158 | 944 |  | 98 | 98 |  | 15484 | 15484 |  | 97.89 | 97.89 |  | 92408.16 | 92408.16
[7 empty] | 0 | 0 | 0
| Sub Total of Section - II Carried Over to Summary |  |  |  | 162199 |  | 141800 | 0 | 303999
[7 empty] | 0 | 0 | 0
IV | Electrical System | [5 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| MOTOR STARTING PANELS | [5 empty] | 0 | 0 | 0
| Design, manufacture, supply, installation, testing and commissioning of the following front operated cubicle type, front access 2 mm thick steel enclosed free standing, dust and vermin proof, motor starting panels conforming to IP 54 with hinged and lockable doors complete with interconnections, copper crimping lugs, brass glands, bonding to earth and powder coated painting, suitable for use at 415 volts, 3 phase 4 wire 50 Hertz system, and with 25 MVA rupturing capacity at 415 volts complete as per specifications and as required as per enclosed sheet. | [5 empty] | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Necessary interface with BMS contractor for complete integration of the system shall be included.Space provision in all panel shall be made accordingly. |  |  | 0 | 0 | 0 | 0 | 0 | 0
| ACCESS - FRONT ONLY - NO REAR ACCESS |  |  | 0 | 0 | 0 | 0 | 0 | 0
1 | Kitchen Ventilation Panel |  |  | 0 | 0 | 0 | 0 | 0 | 0
| INCOMING |  |  | 0 | 0 | 0 | 0 | 0 | 0
a) | 1 no 100 amp 690 volts Triple pole MCCB. |  |  | 0 | 0 | 0 | 0 | 0 | 0
b) | Square flush mounting 0-150/5 amp scaled ammeter with selector switch & CTs |  |  | 0 | 0 | 0 | 0 | 0 | 0
c) | Three phase indicating lights with control fuses. |  |  | 0 | 0 | 0 | 0 | 0 | 0
d) | Square flush mounting voltmeter scaled 0-500 volt with selector switch |  |  | 0 | 0 | 0 | 0 | 0 | 0
| BUSBAR |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Electrolytic high conductivity aluminium three phase and neutral busbars rated at 100 amps having a maximum current density of 1 amp per sq mm suitable to with stand symmetrical fault level of 25 M.V.A. at 415 volts. | [5 empty] | 0 | 0 | 0
| OUTGOING UNITS | [5 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
| 2 nos Motor Protection Circuit Breakers with short circuit magnetic releases suitable for fan Motor of 18.5 kW rating for Normal Fan complete with | [5 empty] | 0 | 0 | 0
a) | Automatic DOL starter contactor with bimetal overload releases and NO/NC for remote operation. | [5 empty] | 0 | 0 | 0
b) | Single phase preventor | [5 empty] | 0 | 0 | 0
c) | Ammeter | [5 empty] | 0 | 0 | 0
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | Nos. | 1 | 56700 | 56700 | 5663 | 5663 | 62363 | 62363 | 55668 | 5559
4 | Supply, laying testing and commissioning of 1100 volt grade armored XLPE. insulated and sheathed aluminium conductor cables of sizes as below, on cable trays with suitable clamps, saddles, hooks, bolts etc. complete as per specifications and as required. The quoted rate shall include the cost of proper dressing of cables and identification tags as required.
a) | 4 core 16 Sq. mm | RM | 40 | 130 | 5200 | 33 | 1320 | 163 | 6520 | 127 | 32
b) | 4 core 10 Sq. mm | RM | 0 | 114 | 0 | 28 | 0 | 142 | 0 | 111 | 27
[7 empty] | 0 | 0 | 0
5 | Cable termination jointing of the following XLPE cables 1100 Volt grade including cost of crimping tinned copper heavy duty lugs, double compression glands, insulation tape and all requisite material for completion of joints complete as per specifications and as required. | [5 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
a) | 4 core 6 Sq. mm | Nos | 4 | 406 | 1624 | 169 | 676 | 575 | 2300 | 398 | 165
b) | 4 core 4 Sq. mm | Nos | 0 | 319 | 0 | 169 | 0 | 488 | 0 | 313 | 165
| Sub Total of Section - III Carried Over to Summary |  |  |  | 63524 |  | 7659 |  | 71183
| Total Of HVAC | [13 empty] | 47594692.6 | 2575427 | 50170119.6 |  |  |  | 2429391 | 4957650.33 | 7387041.33
EXTRA ITEMS
BOYS HOSTEL HVAC RA-09
S.No. | Description | Unit | Qty | Supply Rate | Supply Amount | ITC Rate | ITC Amount | SITC Rate | SITC Amount | GST Rates |  | SUPPLY QTY |  |  | SUPPLY AMOUNT |  |  | ITC QTY |  |  | ITC AMOUNT
[10 empty] | Supply Rate | ITC Rate | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm.
NS 11 | Air Washer Unit 37000 CFM | 1 |  | 408137 |  | 7929 |  |  |  | 408137 | 7929 | 1 | 0 | 1 | 408137 | 0 | 408137 |  | 1 | 1 |  | 7929 | 7929
[19 empty] | 0 |  |  | 0 | 0
NS 12 | Air Scrubber Unit 20250 | 2 |  | 335417 |  | 6796 |  |  |  | 335417 | 6796 | 2 | 0 | 2 | 670834 | 0 | 670834 |  | 2 | 2 |  | 13592 | 13592
[13 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
NS 13 | Axial Flow Fan 8000 Cfm | 8 |  | 43812 |  | 6325 |  |  |  | 43812 | 6325 |  | 8 | 8 |  | 350496 | 350496 |  | 8 | 8 |  | 50600 | 50600
With referance to GH BOQ no 2(1) in Grilles & diffusers
2 | Grilles & Diffusers
1 | Providing, fixing, testing and commissioning of powder coated extruded aluminium grills .
a) | Supply/Exhaust Grills with Dampers | Sqm | 5 | 6369 | 31845 | 475 |  |  |  | 6247 | 465 | 5 |  | 5 | 31235 | 0 | 31235 |  | 5.085 | 5.085 |  | 2364.525 | 2364.525
[17 empty] | 0 |  |  |  |  | 0 | 0
b) | Supply/Exhaust Grills without Dampers | Sqm | 4 | 3380 | 13520 | 475 |  |  |  | 3315 | 465 | 4 | 89 | 93 | 13260 | 295035 | 308295 |  | 93.325 | 93.325 |  | 43396.125 | 43396.125
[17 empty] | 0 |  | 0 |  |  | 0 | 0
3 | Supply , Installation & testing of GI volume control damper (Box type) within ducts to be provided with suitable links, levers and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per approved shop drawings. | Sqm | 1 | 5589 | 5589 | 475 |  |  |  | 5482 | 465 | 1 | 11 | 12 | 5482 | 60302 | 65784 |  | 11.86 | 11.86 |  | 5514.9 | 5514.9
[17 empty] | 0 |  | 0 |  |  | 0 | 0
4 | Supply,Installing, testing and balancing of square supply air diffusers, air distribution grid for straightening the air flow through the collar and register and removable key-operated volume control dampers. | [11 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[17 empty] | 0 |  | 0 |  |  | 0 | 0
a) | Powder Coated Aluminium square diffuser with volume control damper | Sqm | 3 | 9619 | 28857 | 475 |  |  |  | 9435 | 465 | 3 | 13.64 | 16.64 | 28305 | 128693.4 | 156998.4 |  | 16.53 | 16.53 |  | 7686.45 | 7686.45
[13 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
NS | INLINE FAN | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 1000 CFM | Nos | [7 empty] | 13666.2 | 1380 |  | 2 | 2 |  | 27332.4 | 27332.4 |  | 2 | 2 |  | 2760 | 2760
| 600 CFM | Nos | [7 empty] | 7700.32 | 1150 |  | 1 | 1 |  | 7700.32 | 7700.32 |  | 1 | 1 |  | 1150 | 1150
| 400 CFM | Nos | [7 empty] | 5278.18 | 920 |  | 1 | 1 |  | 5278.18 | 5278.18 |  | 1 | 1 |  | 920 | 920
| 150 CFM | Nos | [7 empty] | 3567.13 | 690 |  | 1 | 1 |  | 3567.13 | 3567.13 |  | 1 | 1 |  | 690 | 690
| 100 CFM | Nos | [7 empty] | 3567.13 | 690 |  | 2 | 2 |  | 7134.26 | 7134.26
NS | 3TR Ducktable unit | Nos | [7 empty] | 53710 | 4600 |  | 7 | 7 |  | 375970 | 375970 |  | 7 | 7 |  | 32200 | 32200
NS | 4TR Ducktable unit | Nos | [7 empty] | 63850 | 5750 |  | 2 | 2 |  | 127700 | 127700 |  | 2 | 2 |  | 11500 | 11500
[16 empty] | 0 | 0 |  |  |  |  | 0
NS 7 | 2.2 KW Dol Starter | [8 empty] | 7564 | 1699 |  | 8 | 8 |  | 60512 | 60512 |  | 8 | 8 |  | 13592 | 13592
NS 7 | 3.7 KW Dol Starter | [8 empty] | 7564 | 1699 |  | 5 | 5 |  | 37820 | 37820 |  | 5 | 5 |  | 8495 | 8495
Referance to BH BOQ no 2.0
NS | HI-WALL AT OTER AREA BH
ii | 1.65 TR (530 CFM) | [8 empty] | 15436 | 2001 | [7 empty] | 3 | 3 |  | 6003 | 6003
TOTAL OF EXTRA ITEMS | [14 empty] | 1157253 | 1487540.69 | 2644793.69 |  |  |  | 0 | 208393 | 208393

## HVAC GH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
GIRLS HOSTEL HVAC RA-10
S.No | DESCRIPTION | Unit | Qty | Supply Rate | Supply Amount | ITC Rate | ITC Amount | SITC Rate | SITC Amount | GST Rates |  | SUPPLY QTY |  |  | SUPPLY AMOUNT |  |  | ITC QTY |  |  | ITC AMOUNT
[10 empty] | Supply Rate | ITC Rate | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm.
0
1 | Air Handling Units & Accessories | [7 empty] | 0
Supplying, Unloading and delivery at site of Modular/Non Modular type ceiling mounted double skin Air Handling Unit complete with Blower, Motor, Drive set, cooling coil 12 fins per inch, Filters capable of filtering upto 10 microns at 90% efficiency and anti-vibration mountings complete as per specifications and drawings of the following capacities.Motor shall be suitable for 415 ± 10 % volts, 3 phase, 50 cycles AC supply. Motor efficiency shall be minimum 70%.
a) | Capacity 3400 CMH (2000 CFM), 3.9 TR at 30 mm static pressure, 4 rows deep coil area, 0.37 sq m.,motor rating 1.1 KW for Reception | nos. | 1 | 46448 | 46448 | 5663 | 5663 | 52111 | 52111 | 45560 | 5554 | 1 | 0 | 1 | 46448 | 0 | 46448 | 1 | 0 | 1 | 5554 | 0 | 5554
[10 empty] | 0 | [11 empty] | 0 | 0
b) | Capacity 2550 CMH (1500 CFM), 3.2 TR at 30 mm static pressure, 4 rows deep coil area, 0.37 sq m.,motor rating 1.1 KW for Reception | nos. | 2 | 44596 | 89192 | 5663 | 11326 | 50259 | 100518 | 43744 | 5554 | 1 | 0 | 1 | 44596 | 0 | 44596 | 1 | 0 | 1 | 5554 | 0 | 5554
[10 empty] | 0 | [11 empty] | 0
c) | Capacity 1700 CMH (1000 CFM), 1.7 TR at 30 mm static pressure, 4 rows deep coil area, 0.18 sq m.,motor rating 0.55 KW for changing room. | nos. | 2 | 36407 | 72814 | 5663 | 11326 | 42070 | 84140 | 35711 | 5554 | 2 | 1 | 3 | 72814 | 35711 | 109221 | 2 | 1 | 3 | 11108 | 5554 | 16662
0
i) | Receiving, storing, installation testing and commissioning of above Controls | nos. | 5 | 0 | 0 | 5663 | 28315 | 5663 | 28315 |  | 5554
0
2 | Tower Type Floor Mounted Indoor Units | [7 empty] | 0
0
| Supplying, Unloading and delivery at site of Modular/Non Modular type Floor mounted Indoor Unit complete with Blower, Motor, Drive set, cooling coil 12 fins per inch, Filters capable of filtering upto 10 microns at 90% efficiency and anti-vibration mountings and drawings of the following capacities.Motor shall be suitable for 415 ± 10 % volts, 3 phase, 50 cycles AC supply. Motor efficiency shall be minimum 70%. | [7 empty] | 0
0
a) | Capacity 1294 CFM, 4.5 TR at , 4 rows deep coil area, 0.37 sq m., for Dinning Hall & Gym | nos. | 19 | 55894 | 1061986 | 3398 | 64562 | 59292 | 1126548 | 54826 | 3333 | 20 | 0 | 20 | 1116812 |  | 1116812 | 20 | 0 | 20 | 66660 | 0 | 66660
3 | Supplying, installing, testing and commissioning of Wall mouted finished type Hi wall unit with blower, motor, cooling coil of 12 fins per inch, filters, insulated drain pan and accessories namely Ball valves, supply/return air-grille and 2 way solonoid valve with thermostate and ON/OFF 3 speed regulator swtich as per specifications and drawings including electrical wiring from socket to FCUs and control wiring. The unit shall be suitable for locating above false ceiling. | [7 empty] | 0
a) | Capacity 1.0 TR (400 CFM) | nos | 192 | 17779 | 3413568 | 2831 | 543552 | 20610 | 3957120 | 17439 | 2776 | 186 | 0 | 186 | 3305874 |  | 3305874 | 186 | 0 | 186 | 516336 | 0 | 516336
b) | Capacity 1.5 TR (600 CFM) | nos | 206 | 21460 | 4420760 | 2831 | 583186 | 24291 | 5003946 | 21050 | 2776 | 205 | 0 | 205 | 4399300 | 0 | 4399300 | 205 | 0 | 205 | 569080 | 0 | 569080
c) | Capacity 2.0 TR (800 CFM) | nos | 2 | 30332 | 60664 | 3738 | 7476 | 34070 | 68140 | 29752 | 3666 | 48 | 0 | 48 | 1455936 | 0 | 1455936 | 48 | 0 | 48 | 175968 | 0 | 175968
d) | Capacity 2.5 TR (1000 CFM) | nos | 2 | 30332 | 60664 | 3738 | 7476 | 34070 | 68140 | 29752 | 3666
3 | Air Washer for kitchen fresh air
Supply,Receiving,Handling, installation, testing and commissioning of synthetic fill pad type single skin type air washer (at 500 FPM velocity across pads), DIDW Class-I forward curved centrifugal fan with TEFC weather proof motor of IP: 55 protection suitable for 415 +10% Volts, 3 phase, 50 cycles power supply, mounted on a common base with metallistik vibration isolators, multi sheave pullies for fan and fan motor. The fan capacity shall be based on outlet velocity not exceeding 2200 FPM. The cooler shall be complete with 8" thick celdek fill, 1.25mm (18 G) thick FRP(fiber reinforcement plastic) steel reinforced /S.S tank,tank should be 300 mm deep in basin, water pump distribution pipe, distribution pan, filters at air inlet, water piping, make up water connection with ball valve, drain and overflow connection, all housed in 18 G G.I Sheets casing mounted on vibration isolators. The air washer shall come in knock down condition complete in all respects as per specifications and drawings. Capacity of coolers shall be as under:
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Accessories namely make up, drain, overflow, quick fill valves, float valve, fire retardant flexible connection, volume control dampers at fan outlet, vibration isolators and foundations bolts shall be included. |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Capacity 11000 CFM , Static pressure 30 mm, | Nos |  | 150122 | 0 | 6796 | 0 | 156918 | 0 | 147254 | 6666
4 | Exhaust Air Scrabbers for Kitchens
Supplying, Installing, Testing and Commissioning of Scrubber (nozzle type double skin air washer). Air washer shall be factory fabricated and complete with fan casing, humidifier section, FRP coated steel tank, DIDW centrifugal backward curved fan with V belt drive motor monbloc pumps, brass spray nozzles and water distribution header, piping with valves and fittings between pumps and air washer, 4 bend PVC/GI eliminator
| Capacity 13500 CFM static pressure 50mm blower | Nos |  | 246735 | 0 | 6796 | 0 | 253531 | 0 | 242022 | 6666
| Sub Total of Section - I Carried Over to Summary | [7 empty] | 10488978
SUB HEAD-II : PIPING
1 | Supply, installation, testing and commissioning of the following Mild Steel heavy class pipes upto 150 mm size as per IS Specification and 6 mm wall thickness upto 250 mm, cut to required lengths and installed with all welded joints including the necessary fittings like supports, elbows/bends tees and reducers.All Pipe shall be rating confirming to PN 10.
Size
a) | 250 mm | m | 20 | 1717 | 34340 | 1019 | 20380 | 2736 | 54720 | 1684 | 999 | 18 | 0 | 18 | 30906 | 0 | 30906
| Less Qty by 18 mtr | [11 empty] | 18 | -18 |  | -30906 | -30906
b) | 200 mm | m | 80 | 1370 | 109600 | 815 | 65200 | 2185 | 174800 | 1343 | 799 | 72 | 0 | 72 | 98640 | 0 | 98640
| Less Qty by 72 mtr | [11 empty] | 72 | -72 |  | -98640 | -98640
c) | 150 mm | m | 40 | 911 | 36440 | 611 | 24440 | 1522 | 60880 | 893 | 599 | 102 | 0 | 102 | 92922 | 0 | 92922 | 90 | 0.34 | 90.34 | 54114 | -0.34 | 54113.66
d) | 125 mm | m | 25 | 766 | 19150 | 509 | 12725 | 1275 | 31875 | 751 | 499 | 30 | 0 | 30 | 22980 | 0 | 22980 | 26 | 0.4 | 26.4 | 13174 | -0.4 | 13173.6
e) | 100 mm | m | 20 | 621 | 12420 | 407 | 8140 | 1028 | 20560 | 609 | 399 | 30 | 0 | 30 | 18630 | 0 | 18630 | 30 | 0.3 | 30.3 | 12090 | -0.3 | 12089.7
f) | 80 mm | m | 250 | 421 | 105250 | 326 | 81500 | 747 | 186750 | 412 | 319 | 258 | 0 | 258 | 108618 | 0 | 108618 | 226 | 38.82 | 264.82 | 71973 | 12383.58 | 84356.58
g) | 65 mm | m | 370 | 352 | 130240 | 265 | 98050 | 617 | 228290 | 345 | 259 | 678 | 0 | 678 | 238656 | 0 | 238656 | 488 | 210 | 698 | 126548 | 54390 | 180938
h) | 50 mm | m | 610 | 268 | 163480 | 203 | 123830 | 471 | 287310 | 262 | 199 | 666 | 0 | 666 | 178488 | 0 | 178488 | 378 | 152.595 | 530.595 | 76048 | 30366.405 | 106414.405
i) | 40 mm | m | 370 | 188 | 69560 | 163 | 60310 | 351 | 129870 | 184 | 159 | 540 | 0 | 540 | 101520 | 0 | 101520 | 287 | 111.49 | 398.49 | 46210 | 17726.91 | 63936.91
j) | 32 mm | m | 735 | 160 | 117600 | 130 | 95550 | 290 | 213150 | 156 | 127 | 738 | 0 | 738 | 118080 | 0 | 118080 | 692 | 153.985 | 845.985 | 88294 | 19556.095 | 107850.095
k) | 25 mm | m | 400 | 124 | 49600 | 101 | 40400 | 225 | 90000 | 121 | 99 | 2094 | 0 | 2094 | 259656 | 0 | 259656 | 1417 | 627.72 | 2044.72 | 140605 | 62144.28 | 202749.28
l) | 20 mm | m | 2500 | 82 | 205000 | 81 | 202500 | 163 | 407500 | 80 | 79 | 2790 | 0 | 2790 | 228780 | 0 | 228780 | 710 | -0.03 | 709.97 | 56088 |  | 56087.63
2 | Providing and fixing, testing and commissioning Butterfly valve will flanges gasket duly insulated with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive.
a) | 65 mm | nos | 0 | 1511 | 0 | 1318 | 0 | 2829 | 0 | 1482 | 1292 | 1 | 0 | 1 | 1511 | 0 | 1511 | 1 | 0 | 1 | 1292 | 0 | 1292
b) | 50 mm | nos | 2 | 1277 | 2554 | 1017 | 2034 | 2294 | 4588 | 1252 | 997 | [5 empty] | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
3 | Providing, fixing, testing and commissioning of GM gate / Ball valve insulated with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | 40 mm | nos | 0 | 1247 | 0 | 833 | 0 | 2080 | 0 | 1223 | 817 | [5 empty] | 0
b) | 32 mm | nos | 4 | 881 | 3524 | 685 | 2740 | 1566 | 6264 | 864 | 671 |  | 1 | 1 |  | 864 | 864 |  | 1 | 1 |  | 671 | 671
c) | 25 mm | nos | 8 | 645 | 5160 | 555 | 4440 | 1200 | 9600 | 632 | 544 | 2 | 0 | 2 | 1290 | 0 | 1290 |  | 24 | 24 |  | 13056 | 13056
4 | Providing, installing, testing and commissioning of Two Way High Rangeabilty Control Valve for fitted with motorised, modulating actuators with linear stroke of minimum 15 mm, in chilled water lines at each air handling unit. The actuator shall have shut off capability of minimum 4 bar rating. The actuator shall be controlled by Building Automation System & should accept a signal of 4–20mA/ 2–10 VDC.The valve shall be suitable duly insulated as with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive.
Supply,installation,testing and commissioning of Digital electronic controller with LCD display capable of accepting 0-10v dc signal and water temperature signals from coil inlet and outlet sensors conforming to detailed specifications.
a) | 40 mm | nos | 3 | 23849 | 71547 | 1583 | 4749 | 25432 | 76296 | 23393 | 1552 |  | 1 | 1 |  | 23393 | 23393 |  | 1 | 1 |  | 1552 | 1552
b) | 32 mm | nos | 0 | 16765 | 0 | 1400 | 0 | 18165 | 0 | 16444 | 1373 |  | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0
c) | 25 mm | nos | 2 | 16723 | 33446 | 1251 | 2502 | 17974 | 35948 | 16403 | 1227 |  | 20 | 20 |  | 328060 | 328060 |  | 20 | 20 |  | 24540 | 24540
d) | 20 mm | nos | 5 | 16686 | 83430 | 1121 | 5605 | 17807 | 89035 | 16367 | 1099 |  | 4 | 4 |  | 65468 | 65468 |  | 4 | 4 |  | 4396 | 4396
5 | Providing and fixing testing and commissioning MS Y type strainer insulated with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive.
a) | 50 mm | nos | 3 | 2326 | 6978 | 1017 | 3051 | 3343 | 10029 | 2281 | 997
b) | 40 mm | nos | 0 | 1652 | 0 | 833 | 0 | 2485 | 0 | 1620 | 817 |  | 0 | [8 empty] | 0 | 0
c) | 32 mm | nos | 2 | 1610 | 3220 | 685 | 1370 | 2295 | 4590 | 1579 | 671 |  | 1 | 1 |  | 1579 | 1579 |  |  | 1 |  | 671 | 671
d) | 25 mm | nos | 5 | 1574 | 7870 | 555 | 2775 | 2129 | 10645 | 1543 | 544 |  | 24 | 24 |  | 37032 | 37032 |  |  | 24 |  | 13056 | 13056
6 | Providing. Fixing, testing and commissioning of Insulation with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive. Manufactured supplied, suitable sized nitrile rubber pipe supports with PUF/PIR inserts shall be used. .
a) | 250 mm with 25mm thick | m | 20 | 550 | 11000 | 550 | 11000 | 1100 | 22000 | 539 | 539 | [5 empty] | 0
a) | 200 mm with 25mm thick | m | 80 | 440 | 35200 | 462 | 36960 | 902 | 72160 | 431 | 453 | [5 empty] | 0
b) | 150 mm with 25mm thick | m | 40 | 330 | 13200 | 370 | 14800 | 700 | 28000 | 323 | 362 |  | 90 | 90 |  | 32580 | 32580 |  | 90.34 | 90.34 |  | 32703.08 | 32703.08
c) | 125 mm with 25mm thick | m | 25 | 275 | 6875 | 326 | 8150 | 601 | 15025 | 269 | 319 |  | 26 | 26 |  | 8294 | 8294 |  | 26.4 | 26.4 |  | 8421.6 | 8421.6
d) | 100 mm with 25mm thick | m | 20 | 501 | 10020 | 282 | 5640 | 783 | 15660 | 491 | 276 |  | 30 | 30 |  | 8280 | 8280 |  | 30.3 | 30.3 |  | 8362.8 | 8362.8
e) | 80 mm with 25mm thick | m | 250 | 374 | 93500 | 246 | 61500 | 620 | 155000 | 366 | 241 | 252 | 15 | 267 | 94248 | 5610 | 99858 | 226 | 38.82 | 264.82 | 54374 | 9355.62 | 63729.62
f) | 65 mm with 25mm thick | m | 370 | 288 | 106560 | 220 | 81400 | 508 | 187960 | 282 | 215 | 480 | 0 | 480 | 138240 | 0 | 138240 | 34.6 | 663.4 | 698 | 7698 | 142631 | 150329
g) | 50 mm with 19mm thick | m | 610 | 175 | 106750 | 173 | 105530 | 348 | 212280 | 171 | 169 | 648 | 0 | 648 | 113400 | 0 | 113400 | 378 | 152.595 | 530.595 | 64708 | 25788.555 | 90496.555
h) | 40 mm with 19mm thick | m | 370 | 142 | 52540 | 156 | 57720 | 298 | 110260 | 139 | 153 | 504 | 0 | 504 | 71568 | 0 | 71568 | 287 | 111.49 | 398.49 | 44334 | 17057.97 | 61391.97
i) | 32 mm with 19mm thick | m | 735 | 116 | 85260 | 141 | 103635 | 257 | 188895 | 113 | 138 | 684 | 0 | 684 | 79128 |  | 79128 | 692 | 153.985 | 845.985 | 95910 | 21249.93 | 117159.93
j) | 25 mm with 19mm thick | m | 400 | 99 | 39600 | 129 | 51600 | 228 | 91200 | 97 | 126 | 2052 | 0 | 2052 | 203148 | 0 | 203148 | 142 | 1902.72 | 2044.72 | 18318 | 239742.72 | 258060.72
k) | 20 mm with 19mm thick | m | 2500 | 87 | 217500 | 120 | 300000 | 207 | 517500 | 85 | 117 | 2744 | 0 | 2744 | 238728 | 0 | 238728 | 710 | -0.03 | 709.97 | 83066 | 0.49 | 83066.49
7 | Pressure Gauges & Thermometers:
Providing and fixing in position dial type pressure gauges (4" Dial) & dial type thermometers (4" Dial) with isolating ball valves complete as per specifications.
a) | Pressure Gauge | nos | 10 | 519 | 5190 | 169 | 1690 | 688 | 6880 | 509 | 165 | [5 empty] | 0
b) | Thermometer | nos | 10 | 1444 | 14440 | 169 | 1690 | 1613 | 16130 | 1416 | 165 | [5 empty] | 0
8 | Air Purging Valve
Providing, fixing, testing and commissioning of mechanical air purging valves with ball valves.
a) | 20mm dia | nos | 12 | 1420 | 17040 | 169 | 2028 | 1589 | 19068 | 1392 | 165 |  | 4 | 4 |  | 5568 | 5568 |  | 4 | 4 |  | 660 | 660
9 | Condensate Drain Piping
Supply,Providing, fixing and testing uPVC drain piping for condensate from room Indoor unit to nearest suitable drain system as per site conditions as instructed by site engineer complete with all required fittings and providing clean out plug at suitable location for roding the pipe when required complete with 2 layers of 6mm thickness with elastomeric nitrile rubber insulation over uPVC pipe:
a) | 40mm OD | RM | 50 | 114 | 5700 | 113 | 5650 | 227 | 11350 | 111 | 110 | [5 empty] | 0
b) | 32mm OD | RM | 200 | 84 | 16800 | 90 | 18000 | 174 | 34800 | 82 | 88 | 102 | 252 | 354 | 8568 | 21168 | 29736 |  | 1643.53 | 1643.53 |  | 144630.64 | 144630.64
| Referance from BH 1000 rmt | [8 empty] | 82 |  |  | 1111 | 1111 |  | 91102 | 91102
c) | 25mm OD | RM | 1800 | 62 | 111600 | 79 | 142200 | 141 | 253800 | 60 | 77 |  |  |  | 0 | 0 | 0
| Sub Total of Section - II Carried Over to Summary | [7 empty] | 4090668
0
III | Air Distribution System | [7 empty] | 0
0
1 | Ducting: | [7 empty] | 0
0
| Supply, fabricating, installing and testing of G.I. Sheet metal ducts and flanges as per IS specifications complete with supports, Vanes, dampers, links, levers and quadrants etc. as per specifications and drawings. The rates shall include all materials and labour for suspension and supporting arrangement of galvanised steel for Plenums, Ducts, complete with fire retardant factory fabricated flexible connection as per required specifications | [7 empty] | 0
0
a) | 0.63 MM (24 Gauge ) | Sqm | 100 | 431 | 43100 | 226 | 22600 | 657 | 65700 | 422 | 221 | 387 | 0.49 | 387.49 | 164421 |  | 164421 |  | 382.25 | 382.25 |  | 84477.25 | 84477.25
b) | 0.80 MM (22 Gauge ) | Sqm | 50 | 517 | 25850 | 260 | 13000 | 777 | 38850 | 507 | 255 | 63 | -0.3 | 62.7 | 32267 |  | 32267 |  | 62.73 | 62.73 |  | 15996.15 | 15996.15
c) | 1.00 MM (20 Gauge ) | Sqm | 50 | 618 | 30900 | 294 | 14700 | 912 | 45600 | 606 | 288 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0
d) | 1.25 MM (18 Gauge ) | Sqm | 0 | 781 | 0 | 328 | 0 | 1109 | 0 | 766 | 321 | 21 | -0.36 | 20.64 | 15810 |  | 15810 |  | 20.64 | 20.64 |  | 6625.44 | 6625.44
0
2 | Grilles & Diffusers
1 | Providing, fixing, testing and commissioning of powder coated extruded aluminium grills .
a) | Supply/Exhaust Grills with Dampers | Sqm | 5 | 6369 | 31845 | 475 | 2375 | 6844 | 34220 | 6247 | 465 |  | 6.3 | 6.3 |  | 39356.1 | 39356.1 |  | 6.15 | 6.15 |  | 2859.75 | 2859.75
[10 empty] | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
b) | Supply/Exhaust Grills without Dampers | Sqm | 4 | 3380 | 13520 | 475 | 1900 | 3855 | 15420 | 3315 | 465 |  | 2.39 | 2.39 |  | 7922.85 | 7922.85 |  | 2.39 | 2.39 |  | 1111.35 | 1111.35
[13 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
3 | Supply , Installation & testing of GI volume control damper (Box type) within ducts to be provided with suitable links, levers and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per approved shop drawings. | Sqm | 1 | 5589 | 5589 | 475 | 475 | 6064 | 6064 | 5482 | 465 |  | 1 | 1 |  | 5482 | 5482 |  | 1 | 1 |  | 465 | 465
[13 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
4 | Supply,Installing, testing and balancing of square supply air diffusers, air distribution grid for straightening the air flow through the collar and register and removable key-operated volume control dampers. | [11 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
a) | Powder Coated Aluminium square diffuser with volume control damper | Sqm | 3 | 9619 | 28857 | 475 | 1425 | 10094 | 30282 | 9435 | 465 |  | 6.3 | 6.3 |  | 59440.5 | 59440.5 |  | 6.3 | 6.3 |  | 2929.5 | 2929.5
[10 empty] | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
b) | Powder Coated Aluminium square diffuser without volume control damper | Sqm | 3 | 6239 | 18717 | 475 | 1425 | 6714 | 20142 | 6119 | 465 |  | 2.39 | 2.39 |  | 14624.41 | 14624.41 |  | 1.55 | 1.55 |  | 720.75 | 720.75
3 | Thermal Insulation:
| Supplying, installation, testing and commissioning of thermal insulation with 9mm thick, 40-60 Kg / M³ density closed cell elastomeric nitrile rubber, class 'O' secured with manufacturer's adhesive. The duct supports should also be of nitrile rubber with PUF/PIR inserts. | Sqm | 150 | 297 | 44550 | 283 | 42450 | 580 | 87000 | 291 | 277 | 288 | 0 | 288 | 85536 | 0 | 85536 |  | 111.54 | 111.54 |  | 30896.58 | 30896.58
| Less Qty | [8 empty] | 291 |  |  | 176 | -176 |  | -51216 | -51216 |  | 0 |  |  | 0 | 0
4 | Acoustic Lining of Ducts: | [17 empty] | 0 |  |  | 0 | 0
[19 empty] | 0 |  |  | 0 | 0
| Supplying, installing, testing & commissioning of duct acoustic lining with 25mm thick, density shall not be less than 48 kg/cu.m of acoustic lining within supply air ducts as per the specifications. All ducts shown cross hatched on the approved shop drawings shall be provided with acoustic lining of fibre glass insulation as per the specifications. | [17 empty] | 0 |  |  | 0 | 0
[19 empty] | 0 |  |  | 0 | 0
a) | Supply air duct with 25mm thick acoustic lining | Sqm | 50 | 161 | 8050 | 962 | 48100 | 1123 | 56150 | 157 | 943 | 96 | 0 | 96 | 15456 | 0 | 15456 |  | 29.16 | 29.16 |  | 27497.88 | 27497.88
[10 empty] | 157 |  |  | 67 | -67 |  | -10519 | -10519
Sub Total of Section - II Carried Over to Summary
III | ELECTRICAL WORKS
| Supply, installation, testing & commissioning of front operated front access cubical type indoor duty floor / wall / recess/ surface mounting, totally enclosed dust and vermin proof (minimum protection IP 54) panels with neoprene gaskets, fabricated from 2 mm thick CRCA sheets with powder coated finish (minimum thickness 50 micron) suitable for 415 volts 3 phase 4 wire 50 Hz system to withstand symmetrical fault level of 35 KA at 415 V including interconnections, bonding to earth etc. and flush doors conforming to relevant IEC/IS (viz. IEC 60439, IS 8623 etc.) standard including the earth leakage protection complete as per specification & drawings as required and as given below. All internal wiring in the panels shall be carried out using high temperature FRLS wires. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | The Switchboards shall be provided with detachable gland plates for entry of cables from the top/bottom as required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
b) | All live accessible parts shall be shrouded and all equipment shall be finger touch proof. The busbars shall be insulated with heat shrinkable sleeves. SMC/DMC shrouds and busbar supports suitably spaced shall be used. Hinged doors with padlocking facility shall be provided on all outgoing feeders with switch handles lockable in OFF position. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
c) | The panel shall have aluminium busbars with bar type feeder connections, spacers etc.and neutral busbar shall be of 50% capacity for busbar of above 630A rating and 100% otherwise. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
d) | Earthing all components, frame etc. to a common internal earth bar of minimum size 50 x 6 mm GI or equivalent copper / aluminium bar |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
e) | All accessories & supporting structures such as channels, ISMC base frame, mounting brackets, lifting lugs, panel heaters, ventilation arrangement etc as required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
f) | Each incomer and outgoing feeder shall be provided with multiple LED/neon type status indication lamps suitable for 230 V, AC as approved |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
g) | Space provision @ 15% for future expansion |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
h) | The makes of components and accessories shall, to the extent practically feasible, be same for panels and boards for uniformity, standardisation and replaceability and shall be applicable to all panels/ boards under the scope of work |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
i) | Switchboard including interconnections, labeling, earthing,associated foundation / masonary work & erection etc. complete as required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
j) | All MCCBs shall be current limiting type microprocessor based, rated for requisite specified Service short circuit breaking capacity (Ics suitable for isolation conforming to latest IEC947-2/IS13947-2 duly marked on MCCB, at operating voltage (Ue) of 415 V, insulation voltage (Ui) 690 V and with trip free mechanism, handle indicating ON/OFF/tripped position. The breaking capacity as mentioned shall be Ics values. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
k) | MCCBs shall be compact (As the Engineer may decide), suitably designed to provide protection of motors, cables, busbars to suit rated current, unbalanced power distribution as required and with front adjustable overload and short circuit releases and minimum electrical endurance of the order of 7000-8000 operation cycles (higher shall be preferred) for capacity of 100-250 amps.. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
l) | All the MCCBs shall be provided with potential free contacts for connectivity to BMS System |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
m) | MCBs shall conform to IEC898/IS 8828 (latest) and, with breaking capacity 9/10 kA at 415 V AC, current limiting type lower powerloss appx 40 -70% of the stipulated value and suitable for magnetic releases operating between 3 to 5 times rated current for normal power distribution application and 5 to 10 times rated current for moter application duty, with minimum Electrical endurance of the order of 20000 operation cycles. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
n) | Panel/board design shall be compact and components / accessories of compact sizes be used to economies the room space available. Employer reserve the right to seek compact items inplace of larger ones |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
o) | All incomer ACB's shall be provided with minimum 2 NO + 2 NC auxiliary contacts and all MCCBs shall be provided with 2 NO+ 2NC auxiliary contacts, and there should be provision to add min. 6 Auxlary contacts. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
p) | All 4-pole ACBs shall have fully rated neutral pole |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
q) | Interface with BMS contractor for complete integration of system shall be included. Space provision in all panels shall be made. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
r) | Various panels/boards as given below: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
A) | AHU Panel for Dinning area |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| 2 nos Motor Protection Circuit Breakers with short circuit magnetic releases suitable for motors 5.5 kW motor complete with automatic direct online complete with bimeticalic overload releasee and NO/NC for remote control,single phase preventer and ammeter |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | Automatic Direct online starter contactor with bimetal overload releases and NO/NC for remote operation. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
b) | Single Phase preventor
c) | Ammeter
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels, interlocking etc. with fire alarm panel system. | nos | 1 | 27452 | 27452 | 5663 | 5663 | 33115 | 33115 | 26927 | 5554 | [5 empty] | 0
B) | AHU Panel for Gym
| 1 nos Motor Protection Circuit Breakers with short circuit magnetic releases suitable for motors 3.7 kW motor complete with automatic direct online complete with bimeticalic overload releasee and NO/NC for remote control,single phase preventer and ammeter |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | Automatic Direct online starter contactor with bimetal overload releases and NO/NC for remote operation. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
b) | Single Phase preventor
c) | Ammeter
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels, interlocking etc. with fire alarm panel system. | nos | 1 | 11153 | 11153 | 4531 | 4531 | 15684 | 15684 | 10939 | 4444 | [5 empty] | 0
C) | Panel for Air washer and Scrubber |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | 1 no 40 amp 690 volts 25 KA Triple pole MCCB. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
b) | Square flush mounting ammeter with selector switch & CTs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
c) | Three phase indicating lamps with control fuses. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
d) | Square flush mounting voltmeter scaled 0-500 volt with selector switch |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| BUSBAR |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| Electrolytic high conductivity aluminium three phase and neutral busbars rated at 40 amps having a maximum current density of 1 amp per sq mm , neutral bus bar 50% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
OUTGOING UNITS
| 2 No. motor protection circuit breaker with short circuit magnetic releases and thermal overload release with type -2 coordination up to 4.0 KW suitable for motor 4.0 kw complete with |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | DOL starter contactor with adequate no of NO/NC for remote operation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
b) | Single phase preventor - current opearted
c) | CT operated square flush mounting ammeter with 3 way and OFF selector switch |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
d) | 1 set of ON/OFF indication lamps |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
e) | Auto/manual selector switch |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
f) | On/Off Push Button |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| The Switchboard shall be complete with all interconnection, rises, internal wiring, labels as required | Nos | 1 | 45781 | 45781 | 5663 | 5663 | 51444 | 51444 | 44906 | 5554 | [5 empty] | 0
2 | Supply, Installation, testing and commissioning wiring etc for single phase starter suitable for following capacities complete as required.(For AHUs) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | 1.5 kW | nos | 2 | 7564 | 15128 | 1699 | 3398 | 9263 | 18526 | 7419 | 1666 | [5 empty] | 0
b) | 1.1 kW | nos | 2 | 7564 | 15128 | 1699 | 3398 | 9263 | 18526 | 7419 | 1666 | [5 empty] | 0
c) | 0.55 kW | nos | 1 | 7564 | 7564 | 1699 | 1699 | 9263 | 9263 | 7419 | 1666 | [5 empty] | 0
0
I | Cables:
| Supply, laying testing and commissioning of 1100 volt grade armored XLPE. insulated and sheathed aluminium conductor cables of sizes as below, on cable trays with suitable clamps, saddles, hooks, bolts etc. complete as per specifications and as required. The quoted rate shall include the cost of proper dressing of cables and also providing identification tags as required. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
a) | 4 core 6 Sq. mm | RM | 80 | 90 | 7200 | 33 | 2640 | 123 | 9840 | 88 | 32 | [5 empty] | 0
b) | 4 core 4 Sq. mm | RM | 100 | 79 | 7900 | 28 | 2800 | 107 | 10700 | 77 | 27 | [5 empty] | 0
J | Cable termination:
0
Cable termination jointing of the following XLPE cables 1100 Volt grade including cost of crimping tinned copper heavy duty lugs, double compression glands, insulation tape and all requisite material for completion of joints complete as per specifications and as required.
a) | 4 core 6 Sq. mm | Nos | 8 | 406 | 3248 | 169 | 1352 | 575 | 4600 | 398 | 165 | [5 empty] | 0
b) | 4 core 4 Sq. mm | Nos | 10 | 319 | 3190 | 169 | 1690 | 488 | 4880 | 312 | 165 | [5 empty] | 0
| Sub Total of Section - IV Carried Over to Summary | [7 empty] | 576006
| TOTAL IN HVAC | [13 empty] | 13202975 | 600253.86 | 13803924.86 |  |  |  | 2405103 | 1084246.285 | 3489349.915
EXTRA ITEMS
S.No | Description | Unit | Qty | Supply Rate | Supply Amount | ITC Rate | ITC Amount | SITC Rate | SITC Amount | GST Rates |  | SUPPLY QTY |  |  | SUPPLY AMOUNT |  |  | ITC QTY |  |  | ITC AMOUNT
[10 empty] | Supply Rate | ITC Rate | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm.
NS 11 | Air Washer Unit 8000 CFM | 1 |  | 130333 |  | 6796 | [5 empty] | 2 |  | 2 | 260666 | 0 | 260666 | 2 | 0 | 2 | 13592 | 0 | 13592
[14 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
NS 12 | Air Scrubber Unit 9000 | 2 |  | 198544 |  | 6796 | [5 empty] | 2 |  | 2 | 397088 | 0 | 397088 | 2 | 0 | 2 | 13592 | 0 | 13592
[16 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0
NS | Axial Flow Fan 8000 Cfm | 2 |  | 43812 |  | 6325 |  |  |  | 43812 | 6325 |  | 2 | 2 |  | 87624 | 87624 |  | 2 | 2 |  | 12650 | 12650
[17 empty] | 0 |  |  |  | 0 |  | 0
| With referance to BH BOQ no 2,b,(i) | [19 empty] | 0
i | Capacity 6000 CFM, 15.5 TR at 30 mm static pressure, 4 rows deep coil area, motor rating 3.7 KW for Common area of level 3 | 1 |  | 376672 | 0 | 10195 |  |  |  | 369816 | 10009 | 1 | 0 | 1 | 369816 | 0 | 369816 | 1 | 0 | 1 | 10009 | 0 | 10009
[16 empty] | 0 |  |  |  |  | 0
[16 empty] | 0 |  |  |  |  | 0
0
NS-09 | Butterfly Valves 150mm | Nos | 2 | 2147 |  | 2588 | [5 empty] | 2 | 0 | 2 | 4294 | 0 | 4294 | 2 | 0 | 2 | 5176 | 0 | 5176
NS-09 | Butterfly Valves 100mm | Nos | 1 | 1630 |  | 1725 | [5 empty] | 1 | 0 | 1 | 1630 | 0 | 1630 | 1 | 0 | 1 | 1725 | 0 | 1725
NS-09 | Butterfly Valves 80mm | Nos | 12 | 1306 |  | 1280 | [5 empty] | 12 | 0 | 12 | 15672 | 0 | 15672 | 12 | 0 | 12 | 15360 | 0 | 15360
NS-10 | Balancing Valve 80 mm | Nos | 12 | 4672 |  | 1280 | [5 empty] | 12 | 0 | 12 | 56064 | 0 | 56064 | 12 | 0 | 12 | 15360 | 0 | 15360
NS-10 | Balancing Valve 100 mm | Nos | 1 | 7657 |  | 1725 | [5 empty] | 1 | 0 | 1 | 7657 | 0 | 7657 | 1 | 0 | 1 | 1725 | 0 | 1725
NS-10 | Balancing Valve 150 mm | Nos | 2 | 16044 |  | 2588 | [5 empty] | 2 | 0 | 2 | 32088 | 0 | 32088 | 2 | 0 | 2 | 5176 | 0 | 5176
NS-10 | Balancing Valve 65 mm | Nos | 1 | 4475 |  | 1127 | [5 empty] | 1 | 0 | 1 | 4475 | 0 | 4475 | 1 | 0 | 1 | 1127 | 0 | 1127
[13 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
[13 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
NS | INLINE FAN | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| 1100 CFM | Nos | [7 empty] | 13666.2 | 1380 |  | 1 | 1 |  | 13666.2 | 13666.2 |  | 1 | 1 |  | 1380 | 1380
| 500 CFM | Nos | [7 empty] | 6055.93 | 1150 |  | 1 | 1 |  | 6055.93 | 6055.93 |  | 1 | 1 |  | 1150 | 1150
0
NS | Ductable 3 TR | NOS | [16 empty] | 0 |  |  | 0 | 0
0
With Referance of BH HVAC Boq num 3. | [18 empty] | 0
1 | 15.9mm OD with 13 mm thick nitrile rubber insulation | Mtr | [7 empty] | 270 | 165 |  | 373.33 | 373.33 |  | 100799.1 | 100799.1 |  | 373.33 | 373.33 |  | 61599.45 | 61599.45
2 | 19.1mm OD with 13 mm thick nitrile rubber insulation | Mtr | [7 empty] | 327 | 188 |  | 29.8 | 29.8 |  | 9744.6 | 9744.6 |  | 29.8 | 29.8 |  | 5602.4 | 5602.4
3 | 9.5mm OD with 13 mm thick nitrile rubber insulation | Mtr | [7 empty] | 136 | 121 |  | 29.8 | 29.8 |  | 4052.8 | 4052.8 |  | 29.8 | 29.8 |  | 3605.8 | 3605.8
[16 empty] | 0 | 0 |  |  |  |  | 0 | 0
NS | 3TR Ducktable unit | [8 empty] | 53710 | 4600 |  | 2 | 2 |  | 107420 | 107420 |  | 2 | 2 |  | 9200 | 9200
[16 empty] | 0 | 0 |  | 0 |  |  | 0 | 0
NS 7 | 2.2 KW Dol Starter | [8 empty] | 7564 | 1699 |  | 4 | 4 |  | 30256 | 30256 |  | 4 | 4 |  | 6796 | 6796
NS 7 | 3.7 KW Dol Starter | [8 empty] | 7564 | 1699 |  | 4 | 4 |  | 30256 | 30256 |  | 4 | 4 |  | 6796 | 6796
0
TOTAL OF EXTRA ITEMS | [14 empty] | 1149450 | 389874.63 | 1539324.63 |  |  |  | 82842 | 108779.65 | 191621.65

## Plumbing Internal, BH
PROJECT : THAPAR UNIVERSITY PATIALA
Boys Hostel EXTERNAL PLUMBING
FINAL BILL
S.No. | DESCRIPTION | Unit | Total Qty | SUPPLY | ITC | SITC RATE | GST Rates |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[7 empty] | Supply | ITC | Prev. | This Bill | Cum. | Prev. | This Bill | Cum. | Previous | This Bill | Cumulative | Previous | This Bill | Cumulative
[14 empty] | . | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
NS | Toilet Rework | Nos |  |  |  |  | 41.47 | 575 |  |  |  |  | 179 | 179 | 0 | 0 | 0 | 0 | 102925 | 102925 | -179 | 179 | DONE
| TOTAL OF NS ITEMS | [13 empty] | 0 | 0 | 0 | 0 | 102925 | 102925 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Plumbing Internal, GH
PROJECT : THAPAR UNIVERSITY PATIALA
Girls Hostel EXTERNAL PLUMBING
FINAL BILL
S.No. | Description | Unit | Qty. | SUPPLY | ITC | SITC RATE | GST Rate |  | SUPPLY QTY |  |  | ITC QTY |  |  | SUPPLY AMOUNT |  |  | ITC AMOUNT
[7 empty] | Supply | ITC | Prev. | This Bill | Cumm. | Prev. | This Bill | Cumm. | Previous | This Bill | Cumulative | Previous | This Bill | Cumulative
NS | Toilet Rework | Nos. |  |  |  |  | 41.47 | 575 |  | 0 |  |  | 61 | 61 | 0 | 0 | 0 | 0 | 35075 | 35075 | -61 | 61 | DONE
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | TOTAL AMOUNT (NS ITEMS) | 0 | 0 | 0 | 0 | 35075 | 35075 | #VALUE! | #VALUE!

## Material Supply to Client
MATERIAL SUPPLY TO THAPAR
Sr. no | Description of Item | Unit | Qty. | Date | Rate | Slip No | Amount
1 | GI Brass Valve-40 mm | mm | 3 | 2018-10-12 | 90 | 231 | 270
2 | GI Brass Valve-32 mm | mm | 6 | 2018-10-19 | 55 | 234 | 330
3 | GI Tee-40mm | mm | 2 | 2018-10-12 | 143 | 231 | 286
4 | GI Tee-20mm | mm | 4 | 2018-11-14 | 47 | 249 | 188
5 | GI Tee-32*25 mm | mm | 10 | 2018-10-19 | 110 | 234 | 1100
6 | GI Elbow-40mm | mm | 6 | 2018-10-12 | 98 | 231 | 588
7 |  | mm | 10 | 2018-10-19 | 98 | 234 | 980
8 | GI Elbow-32mm | mm | 10 | 2018-10-19 | 79 | 234 / 235 | 790
9 | GI Elbow-20mm | mm | 6 | 2018-11-14 | 34 | 249 | 204
10 | GI Socket-40mm | mm | 3 | 2018-10-12 | 73 | 231 | 219
11 | GI Union-40 mm | mm | 3 | 2018-10-12 | 214.5 | 231 | 643.5
12 | GI Union-25 mm | mm | 10 | 2018-10-19 | 120.25 | 234 | 1202.5
13 | GI Union-20 mm | mm | 2 | 2018-11-14 | 92 | 249 | 184
14 | GI Nipple-25*75 mm | mm | 6 | 2018-11-14 | 13 | 249 | 78
15 | GI Nipple-25*100 mm | mm | 6 | 2018-11-14 | 15 | 249 | 90
16 | CPVC Bush 25*20mm | mm | 6 | 2018-11-05 | 9.12 | 245 | 54.72
17 | CPVC Bush 25*15mm | mm | 5 | 2018-11-05 | 7.25 | 245 | 36.25
18 | CPVC Bush 20*15mm | mm | 6 | 2018-11-05 | 4.15 | 245 | 24.9
19 | CPVC Elbow-50 mm | mm | 5 | 2018-11-14 | 173 | 248 | 865
20 | CPVC Elbow-32 mm | mm | 10 | 2018-11-14 | 34.98 | 248 | 349.8
21 | CPVC Elbow-25 mm | mm | 10 | 2018-11-14 | 18.55 | 248 | 185.5
22 | CPVC Socket-50 mm | mm | 10 | 2018-11-14 |  | 248 | 0
23 | CPVC Socket-32 mm | mm | 10 | 2018-11-14 |  | 248 | 0
24 | CPVC Socket-25 mm | mm | 10 | 2018-11-14 | 8.8 | 249 | 88
25 | CPVC Tee-50 mm | mm | 10 | 2018-11-14 | 173.2 | 249 | 1732
26 | CPVC Tee-32 mm | mm | 10 | 2018-11-14 | 44.47 | 249 | 444.7
27 | CPVC Tee-25 mm | mm | 10 | 2018-11-14 | 23.29 | 249 | 232.9
28 | CPVC Socket-40*32 mm | 40mm*32mm | 10 | 2018-11-14 | 45 | 249 | 450
29 | CPVC Socket-32*25 mm | 32mm*25mm | 10 | 2018-11-14 | 31 | 249 | 310
30 | CPVC Socket-25*20 mm | 25mm*20mm | 10 | 2018-11-14 | 14.32 | 249 | 143.2
31 | UPVC Pipe-160 mm | Rmtr | 24.4 | 2018-11-14 | 434 | 248 | 10589.6
32 | UPVC Pipe-110 mm | Rmtr | 45.75 | 2018-10-12 | 185.76 | 231 | 8498.52
33 | UPVC Pipe-75 mm | Rmtr | 15.25 | 2018-11-14 | 89.78 | 248 | 1369.145
34 | UPVC Pipe-50 mm | Rmtr | 73.2 | 2018-11-14 | 43.18 | 248 | 3160.776
35 | UPVC Pipe-32 mm | Rmtr | 12.2 | 2018-11-14 | 28.32 | 248 | 345.504
36 | UPVC Pipe-25 mm | Rmtr | 21.35 | 2018-11-14 | 17.91 | 248 | 382.3785
37 | UPVC Tee-160 mm | mm | 6 | 2018-11-14 |  | 250 | 0
38 | UPVC Elbow-160 mm | mm | 4 | 2018-11-14 | 263 | 250 | 1052
39 | UPVC Elbow-75 mm | mm | 12 | 2018-11-14 | 41.7 | 250 | 500.4
40 | UPVC Elbow-50 mm | mm | 6 | 2018-11-19 | 18.75 | 251 | 112.5
41 | UPVC Solvent | Ltr | 1 | 2018-11-14 | 360 | 250 | 360
42 | UPVC Gali Trap-110mm | mm | 1 | 2018-11-14 | 264.6 | 250 | 264.6
43 |  | mm | 1 | 2018-11-14 | 264.6 | 231 | 264.6
44 | UPVC Bush-50*40 mm | mm | 6 | 2018-11-19 | 11.12 | 251 | 66.72
0

## Supply detail of DB's
Supply detail of DB
S.No. | Description | Units | MH Qty | NH Qty | Invoice no | Qtyt | Gatepass no
1 | 8 way SPN (Type-1) | Nos | 1 |  | 12 | 1 | 15983
2 | 8 way SPN(Type-2) | Nos | 8 |  | 12 | 8 | 15983
3 | 12 way SPN(Type-1)DD | Nos | 3 |  | 12 | 3 | 15983
4 | 12 way SPN(Type-2)DD | Nos |  | 2 | 12 | 2 | 15983
5 | 16 way SPN | Nos | 4 |  | 12 | 4 | 15983
6 | 12 Way VTPN | Nos | 2 | 1 | 12 | 3 | 15983
NS-14 | Kitchen equipment panel | Nos | 1 |  | 9 | 1 | 11750
NS-3 | BOYS HOSTEL- GYM Panel | Nos | 1
NS-21 | FEEDER PILLAR
(A) | Feeder pillar 1 | Nos | 1 |  | 142000184 | 1 | 11564

## Instalation detail of BH
Installation detail of DB
S.No. | Description | Units | MH Qty | Hostel-M | [5 empty] | NH Qty | Hostel-N |  | Remarks
|  |  |  | BH-1 | BH-2 | BH-3 | BH-4 | Kitchen | Reception |  | GH | Kitchen
1 | 8 way SPN (Type-1) | Nos | 1 |  |  |  | 1 | [5 empty] | At 8th Floor for Lift
2 | 8 way SPN(Type-2) | Nos | 8 | 2 | 2 | 2 | 2 | [5 empty] | At 8th Floor for Lift
3 | 12 way SPN(Type-1)DD | Nos | 3 | 1 | 1 | 1 | [6 empty] | At 8th Floor for Lift
4 | 12 way SPN(Type-2)DD | Nos | 0 | [6 empty] | 2 | 2 |  | At 6th Floor for Lift
5 | 16 way SPN | Nos | 4 | 1 | 1 | 1 | 1 | [5 empty] | At 1st Floor for Podium Light
6 | 12 Way VTPN | Nos | 2 |  |  |  |  | 1 | 1 | 1 |  | 1
NS-14 | Kitchen equipment panel | Nos | 1
NS-21 | FEEDER PILLAR
(A) | Feeder pillar 1 | Nos | 1

## Inst. detail of ACP & Exhaust
Installation detail of ACP sheet & Exhaust fan
Hostel-M(BH) | [5 empty] | Hostel-N(GH)
Floors | M1 | M2 | M3 | M4 | Total | N
Ground Floor | 9 | 9 | 9 | 9 |  | 0
1st Floor | 5 | 9 | 9 | 8 |  | 36
2nd Floor | 7 | 9 | 9 | 7 |  | 34
3rd Floor | 8 | 8 | 9 | 4 |  | 34
4th Floor | 15 | 17 | 17 | 14 |  | 34
5th Floor | 14 | 16 | 17 | 15 |  | 54
6th Floor | 15 | 17 | 17 | 12 |  | 46
7th Floor | 11 | 16 | 17 | 13 |  | 0
8th Floor | 19 | 12 | 18 | 12 |  | 0
TOTAL | 103 | 113 | 122 | 94 | 432 | 238

## Installation detail of lights
External Light Detail for Hostel-M(BH)& Hostel-N(GH)
|  |  | Hostel-M | Hostel-N
S.No | Type of Light | units | Qty | Qty | Remarks
1 | Hanging / down light at double/Triple height/Podium Light | Nos | 766 | 43 | At few levels of common area of tower, Kitchen, Gym & podium level
2 | LED strip light | Mtr | 480 |  | At inside podium railing
3 | Wall washer light | Nos | 40 |  | At walls of external double height area
4 | Spike & Planter light | Nos | 160 | 26 | Inside Planter area
5 | Ground light at hard scape area | Nos | 214 | 147 | At all around tower hard scape area
6 | Enterance light | Nos | 48 | 24 | At enterance of all towes
7 | Step light | Nos | 135 | 29 | At staircase of podium
8 | 3mtr height pole light | Nos | 12 |  | At podium level above Gym
Double/Tripal height light fixtures
S.No | Description | Units
| Floors | nos | BH-1 |  | BH-2 | BH-3 | BH-4 | Up and Down light | Down light | 600*600 Grid light | Down light below Podium
1 | Ground floor
2 | 1st floor | nos | 0 |  | 0 | 0 |  |  |  |  | 172
3 | 2st floor | nos | 11 |  | 10 | 12 | 12
4 | 3st floor | nos | 6 |  | 6 | 6 | 6
5 | 4st floor | nos | 0 |  | 0 | 0 | 0
6 | 5st floor | nos | 17 |  | 17 | 16 | 17
7 | 6st floor | nos | 13 |  | 13 | 13 | 13
8 | 7st floor | nos | 17 |  | 16 | 17 | 17
9 | 8st floor | nos | 13 |  | 13 | 12 | 13
10 | Reception | nos | 30 |  | 30 | 30 | 28
11 | Gym | nos | 0 |  | 0 | 0 | 0 | 32
12 | kitchen | nos | 0 |  | 0 | 0 | 0 | 72 | 72 | 66
| Total | nos | 107 |  | 105 | 106 | 106 | 104 | 72 | 66 | 172
|  |  | 424 |  |  |  |  | 104 | 72 | 66 | 172 | 838

## Rework Detail of Toilets
Rework Detail of Toilets
Hostel | No of Toilet
Boy Hostel | 179
Girl Hostel | 61

## Challan Details Electrical BH & (hidden)
PROJECT : THAPAR EXTENSION PATIALA
ELECTRICAL CHALLAN DETAILS BOYS & GIRLS HOSTEL RA-10
S.No. | DESCRIPTION | Unit | Previous Challan No. | Running Bill Challan No. | BOQ Qty. BH | BOQ Qty. GH | Bill Qty BH | Bill Qty GH | Cumm. Qty. BH | Cumm. Qty. GH | Remarks
2 | Other Areas Wiring
3.1 | Providing and fixing of 20 amp SPN MCB 230 volt in flush metal box with moulded front plate in a recessed zinc chromate passivated MS box complete as required. This shall be the Master Switch for the Room Control | Nos | 523835826 |  | 864 | 380 |  | 12 | 832 | 380
2.2 | Supplying and drawing following sizes of FR PVC insulated copper conductor single core stranded cables in existing surface / recessed conduit as required.
b) | 3 x 2.5 sq mm (P+N+E) | RM | 599, 509, |  | 800 | 200 |  |  | 15000 | 10000
c) | 3 x 4.0 sq mm (P+N+E) | RM | 4285, 599, 509 |  | 8640 | 3800 |  |  | 34000 | 20000
SUB HEAD III – SUBMAINS AND CABLES
2 | Supply and laying in cable Tray/clamped to wall with suitable clamps saddles and bolts/ in ground including the cost of digging and back filling with sand and brick protection as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and sheathed aluminium conductor armoured cable complete as required. The costs shall include providing a gap of 1D between all the cables being laid and properl clamping with cable clamps and ties. Prices shall include providing and fixing of Identification tags for all cables and route markers for cables in ground etc. as per specification and or as per direction of Project in-charge.
a | 3 –1/2 core 400 Sq mm | RM
b | 3 –1/2 core 300 Sq mm | RM | 1140 | [5 empty] | 317
c | 3 –1/2 core 240 Sq mm | RM |  |  | 600
d | 3 –1/2 core 185 Sq mm | RM
e | 3 –1/2 core 150 Sq mm | RM |  | 55 | 200 |  | 40 |  | 40
f | 3 –1/2 core 120 Sq mm | RM
g | 3 –1/2 core 95 Sq mm | RM
h | 3 –1/2 core 70 Sq mm | RM | 1140 | 53 |  |  | 15 | 235 | 90 | 235
i | 3 –1/2 core 50 Sq mm | RM |  |  | 300
j | 4 core 35 Sq mm | RM | 1140, 1231 |  | 600 |  |  | 191 | 1910 | 291
k | 4 core 25 Sq mm | RM | 1140, 1231 | 6334 | 800 |  |  | 93 | 2745 | 193
l | 4 core 16 Sq mm | RM | 1231 | 58 | 40 |  | 1212 | 160 | 3059 | 160
m | 4 core 10 Sq mm | RM |  | 6334 | 40 |  |  | 374 |  | 374
n | 3 core 16 Sq mm | RM |  |  | 10
o | 3 core 10 Sq mm | RM |  |  | 10
p | 3 core 6 Sq mm | RM |  |  | 10
q | 2 core 10 Sq mm | RM
3 | Cable end termination XLPE insulated 1100 Volt grade cables including the cost of crimping tinned copper heavy duty lugs, double compression glands, insulation tape etc. complete as required and as below.
a | 3 –1/2 core 400 Sq mm
b | 3 –1/2 core 300 Sq mm |  | 1756 | 1756 |  |  | 2 |  | 2
c | 3 –1/2 core 240 Sq mm | Nos |  |  | 20 |  |  |  | 0
d | 3 –1/2 core 185 Sq mm | Nos | [6 empty] | 0
e | 3 –1/2 core 150 Sq mm | Nos |  | 1756 |  |  | 8 |  | 8
f | 3 –1/2 core 120 Sq mm | Nos | [6 empty] | 0
g | 3 –1/2 core 95 Sq mm | Nos | [6 empty] | 0
h | 3 –1/2 core 70 Sq mm | Nos | 1755 | 1755 |  | 2 | 2 | 14 | 2 | 14
i | 3 –1/2 core 50 Sq mm | Nos | 1756 | 1756 | 58 |  | 126 | 26 | 126
j | 4 core 35 Sq mm | Nos | 1755, 1756 | 1756, 48 | 100 | 20 | 30 |  | 92 | 36
k | 4 core 25 Sq mm | Nos | 1755, 1756 | 1756, 48 | 72 | 12 | 54 |  | 38 | 8
l | 4 core 16 Sq mm | Nos | 1756 | 1756 | 2 |  | 140 |  | 156 | 16
m | 4 core 10 Sq mm | Nos |  | 48 | 2 |  |  |  |  | 12
n | 3 core 16 Sq mm | Nos |  |  | 2
o | 3 core 10 Sq mm | Nos |  |  | 2
p | 3 core 6 Sq mm | Nos |  |  | 2
q | 2 core 10 Sq mm | Nos
5 | Supply and fixing of perforated M.S sheet steel slotted cable trays with vertical sides on both ends as per approved design and MS angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter MS rod hangers, hooks, dash fasteners, painting etc. for suspension from ceiling as required
a) | 150 mm x 50 mm x 50 mm x 1.6 mm |  | 14 |  | 40 | 10 |  |  | 384 | 96
b) | 300 mm x 50 mm x 50 mm x 1.6 mm |  | 14 |  | 15 | 5 |  |  | 272 | 68
c) | 450 mm x 50 mm x 50 mm x 2.0 mm |  | 14 | [5 empty] | 128 | 32
6 | Supply and fixing of perforated GI slotted cable trays (for terrace) with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter GI rod hangers, hooks, dash fasteners, wall brackets etc. for suspension from ceiling / wall as required
a) | 150 mm x 50 mm x 50 mm x 1.6 mm |  | 14 | 76 | 250 | 50 | 175 |  | 425 | 40
b) | 300 mm x 50 mm x 50 mm x 1.6 mm |  | 14 | 76 | 20 | 5 | 304 |  | 536 | 58
| MS Painted ladder Type tray |  |  | 14 |  |  | 120 |  | 120
8 | Supply and fixing of additional length of MS rod hangers / MS Channel duly painted with 2 coats of spray paint for supporting the Cable Trays, complete for extension of the supports. The rate shall be proportionately applicable to the length of rod/channel actually required. | KG | 3376 | 289, 290, 369 | 1600 |  | 379 |  | 4435
SUB HEAD III – SUBMAINS AND CABLES
1 | Wiring for Submains with PVC FRLS insulated stranded copper conductor 1100 volt (P+N+E) grade wires in existing surface/concealed conduit and making suitable end connections complete as required and as below.
d) | 6 x 16 sq mm | RM | 4941 | 4941, 000006 | 2300 | 1200 | 1448 | 1510 | 6148 | 1504
SUB HEAD IV – DISTRIBUTION SYSTEM
d. | 8 way TPN (per phase isolation)
| 1-63 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-63 amp DP 30 mA ELCB incoming and 8 nos 6/16/20/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. | Nos | 761,78 |  | 92 |  |  | 1 | 50 | 43
| 8way VTPN |  |  | 708 |  |  |  | 1 |  | 1
e. | 12 way TPN (per phase isolation)
| 1-63 amp TPN 10 kA MCB with thermal magnetic protective releases incoming with 3 single phase banks each comprising of 1-63 amp DP 30 mA ELCB incoming and 12 nos 6/16/20/32 amps SP 10 kA MCB with thermal magnetic protective releases out goings. | NOS | 761,78 | [5 empty] | 47
SUB HEAD VII : EARTHING
1 | Providing and making plate earthing station including the cost of 600 mm x 600 mm x 6.3 mm GI plate electrode, 15 mm dia GI watering pipe, GI funnel with wiremesh charcoal/coke , salt, all earth work, concrete enclosure with frame, hinged concrete cover plate having locking arrangement, Disconnecting links, complete as per IS 3043:1987 for earthing. | Nos | 1756 |  | 8 | 4 |  |  | 8 | 4
3 | Supplying and laying of the following earthing clamped to wall with suitable clamps saddles and fixing bolts/soldering /riveting in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987. All joints shall be timed.
a) | 50 x 6 mm tinned Cu strip | Rm
b) | 50 mm x 6 mm Cu strip with heat shrinkable sleeve | Rm
c) | 25 mm x 6 mm copper strip | Rm
d) | 25 mm x 6 mm Cu strip with heat shrinkable sleeve | Rm
e) | 65 mm x 8 mm GI strip | Rm
f) | 50 mm x 6 mm GI strip | Rm | 1756 |  | 160 | 40 |  |  | 250 | 100
g) | 25 mm x 6 mm GI strip | Rm | 1756 |  | 800 | 200 |  |  | 1500 | 1250
h) | 25 mm x 3 mm GI strip | Rm | 1756 |  | 160 | 40 |  |  | 1000 | 590
i) | 8 SWG GI Wire | Rm | 1756 |  | 1500 | 500 |  |  | 1000 | 300
1.9 | Wiring with 2 core 1.5 Sqmm standard copper conductor FRLS 660/1100 volts grade wires in 25mm dia 16 SWG concealed/surface MS conduit including cost of cutting and filling chases for concealed conduit/ cost of saddles etc. for surface conduit as required and including the cost of crimped termination's as required, complete | Rm | 4940 |  | 3300 |  |  | 574 | 8000 | 2000
SUB HEAD IX : LIGHTNING PROTECTION
2 | Supplying and laying of the GI horizontal & Vertical conductor of following sizes on surface/wall / parapet/ shaft complete with joints, bimetallic connectors, testing links & other fixing accessories and clamping/ connection with earth terminations as per specifications & drawing as required
2.1 | 25 x 3 mm thick GI tape
2.2 | 32 x 6 mm thick GI tape | RM | 1756 |  | 1150 |  |  |  | 260
2.3 | 25 x 6 mm thick GI tape | RM | 1756 | [5 empty] | 1500 | 0
9 | Supply and laying of the following Hume pipe including excavation, refilling as required for cable entry including the cost of sealing the ends as required complete
a) | 250 mm dia | m |  | 30,34 | 800 | 416 |  |  | 325 | 150
b) | 150 mm dia | m | 31, 1924, | 1170 | 500 | 297 | 84 |  | 397 | 140 |  | 1924 | 1046 | 1020 | 1014 | 1170 | 1047 | 1153
SUPPLY & INSTALLATION OF PANELS
Main Panel
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | NOS | 14200104, 105, |  | 4 | 2 |  |  | 4 | 2 |  | 1951 | 1851 | 1913 | 2006
125
AC outdoor Panel - At Terrace
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | Nos | 14200104, 103, |  | 4 |  |  |  | 4
iv) | Gym Panel
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | no | 14200104 |  | 1 |  |  |  | 1
iv | Ground Floor Panel-Typical for Tower 1,2,3,4
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | Nos | 14200092, 105 | 35 | 4 | 2 |  | 1 | 4 | 2
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | Nos | 14200093, 104, 105, 14200092 |  | 12 | 12 |  |  | 12 | 12
| The Switchboard shall be complete with all interconnections, risers, internal wiring, labels etc complete as required | Nos | 14200092 |  | 20 |  |  |  | 20
1 | ALUMINIUM RISING MAIN
1.1 | Supply, installation, testing and commissioning of the following totally enclosed, dust and vermin proof (IP 42 ingress protection) Low impedance, compact Rising Main system with Aluminium Bus Bars rated for insulation voltage of 690 volts and 50 kA rms fault level having provisions for tapping power as required and including the cost of all required accessories like clamps, elbows, end covers, flexible connections, size reducers to reduce the rising main size as per schematic etc. and including the cost of providing 2 nos 25 x 6 mm GI earthing strips for body earthing and including the cost of support arrangement for fixing along walls and including the cost of expansion joints, and including the cost of Fire barrier of CBRI approved material of 2 hours rating at all fire rated wall/floor/slab/beam crossing. complete as per specifications, as required and as below.
a) | 630 amps | m
b) | 400 amps | m | 14200106, 14200112 |  | 200 |  |  |  | 110.88
c) | 250 amps | m | 14200111 |  |  | 40 |  |  |  | 47
1.2 | Design, manufacture, supplying, fixing in position, testing and commissioning Adopter cum end feed box of the following TPN Isolator with ON/OFF indicating lamp and Voltmeter with Selector switch including interconnections earthing, including adopter box suitable to connect XLPE Aluminium cable etc. to the Rising Mains as in Item 2a above, complete as required.
a) | 400 amp TPN Isolator | Nos | 14200106, 14200111. |  | 4 |  |  |  | 4
b) | 250 amp TPN Isolator | Nos | 14200111 |  |  | 2 |  |  |  | 2
1.3 | Supply, installation, testing and commissioning of following rating TPN plug in type Tap-off Boxes suitable for use with rising mains as per item above, to feed power supply from the rising mains including 35 kA TPN (3P+N) MCCB and including provision to terminate outgoing cables as per schematic, bonding to earth etc. complete as per specifications and as required
a) | 100 amp TPN TAP OFF BOX | nos | 14200111 |  |  | 6 |  |  |  | 12
b) | 125 amp TPN TAP OFF BOX | nos | 14200106. 14200112 |  | 12 |  |  |  | 12
b) | 200 amp TPN TAP OFF BOX | nos | 14200106. 14200112 |  | 20 |  |  |  | 20
SUBHEAD - VIII - FIRE DETECTION AND ALARM SYSTEM
1 | Supply, installation, testing and commissioning of wall or ceiling mounted 240 Volt AC illuminated Signs having on its front a white perspex sheet with the letters 'FIRE EXIT' painted in red including the cost of in-built rechargeable batteries suitable for 30 minute operation and including the cost of accessories for surface or recessed or ceiling suspended mounting complete as required. |  |  | 193 | 72 | 28 | 72 | 54 | 72 | 54
6 | Supply installation testing and commissioning of dust and vermin proof Manual call boxes with push button to initiate audio visual alarm with breakable glass cover as per detailed specifications complete with a steel chain including the cost of accessories for surface mounted as required |  | 81 |  | 72 | 28 |  |  | 72 | 28
7 | Supply installation test and commissioning of the following 8 ohm size speaker-cum-hooter units with line matching transformer suitable for broadcast of speech and alarm siren complete as required suitable for recessed/surface mounting complete with enclosure as approved by Project Manager and as required |  | 81 |  | 72 | 28 |  |  | 72 | 28
8 | Supply installation testing and commissioning of cardoid microphones complete as required |  | 81 |  | 4 | 1 |  |  | 4 | 1
9 | Supply, installation, testing and commissioning of wall recess mounting 8 zone microprocessor based Conventional Fire Control Panel with PA amplifier and 8 potential free contacts as per detailed specifications with alarms, controls and indications as per detailed specifications and with an integral power supply unit and complete with a suitably rated set of batteries and trickle charged from 240 volt AC mains supply, including the cost of mounting accessories as required, complete
|  |  | 81 |  | 4 | 1 |  |  | 4 | 1
SUB HEAD IX : LIGHTNING PROTECTION
1 | Providing and fixing Lightning Conductor Finials made of 25 mm dia 300 mm long GI tube having a single prong at the top with 85 mm dia 6 mm thick GI base plate, fixing accessories and clamping with down conductor as per specifications & drawing complete as required. |  |  | 42 |  |  | 8 | 2 | 8 | 2
4 | Providing and laying of 40 mm dia minimum 3.5 meter long medium class GI pipe. GI funnel with 20 gauge GI wire mesh, concrete chamber 400 x 400 mm with concrete base. hinged GI cover with frame, painted with bitumastic paint and packing with mixtures of charcoal and common salt around plate electrode including digging of pit and suck gilling. GI pipe electrode to be cut tapered at the bottom and provided with holes of 12 mm dia drilled no less than 75 mm from each other upto 2 meter length from bottom complete as required as per IS­3043-1987 for earthing. |  |  | 40 mm GI Pipe |  |  | 20 | 10 | 20 | 10
5 | Supply, installation, testing & commissioning of air craft warning lights complete with non flickering type lights similar to GEC model ZH 752 or WIPRO model no. WAN 20001 or equivalent including lamps, mounting bracket, earthing, painting complete with accessories to automatically switch off lights. (Note: Point wiring shall be done under conduit wiring) |  |  | 17 |  |  | 4 | 1 | 4 | 1
EXTRA ITEMS
Main Panel
Modification in above panel
| 2 nos 100 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted | nos | 14200104, 105, |  | 4 | 2 |  |  | 4 | 2
| 4 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added | nos
AC Panel
Modification in above panel
| 1 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted | TOWER-1 | 14200104 |  | 1 |  |  |  | 1
1 nos 100 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted
4 nos 160 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added
TOWER-2
| 3 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted | TOWER-2 | 14200104 |  | 1 |  |  |  | 1
2nos 100 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added
3nos 160 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added
TOWER-3
| 2nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted | TOWER-3 | 14200104 |  | 1 |  |  |  | 1
1 nos 100 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted
5 nos 160 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added
TOWER-4
| 3 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection deleted | TOWER-4 | 14200104 |  | 1 |  |  |  | 1
4 nos 160 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection Added
GYM Panel
Modification in above panel
| 1 nos 125 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection(Deleted) | NOS | 14200104 |  | 1 | 1 |  |  | 1 | 1
4 nos 63 amps 10 kA SPN MCB with thermal magnetic protective releases (Deleted)
1 nos 160 Amps TPN MCCB 25 kA with thermal magnetic release having overcurrent and short circuit magnetic protection(Added)
4 nos 63 amps 10 kATPN MCB with thermal magnetic protective releases (Added)
|  | NOS | 18 | [5 empty] | 100 | 50
MS Junction Box 600*200*75mm
| Kitchen panel | nos |  | 3 |  | 1 |  | 1 |  | 1
| SWBD AC Panel | nos |  | 14200184 |  |  | 1 |  | 1
| TDBC AC Panel | nos |  | 14200184 |  |  | 1 |  | 1
| Dining hall panel | nos |  | 14200184 |  |  | 1 |  | 1
| Sub AC Panel for Outdoor | Nos |  | 14200100/14200102 |  |  | 16 |  | 16
| Sub AC Panel for gym | Nos |  | 14200101 |  |  | 1 |  | 1
| Feeder pillar 1 | Nos |  | 14200184 |  |  | 1 |  | 1
| Feeder pillar 2 | Nos |  | 14200184 |  |  | 1 |  | 1
| Feeder pillar 3 | Nos |  | 14200184 |  |  |  | 1 |  | 1
| 8 way V TPN | nos |  | 708 |  |  | 1 | 1 | 1 | 1
| Kitchen equipment panel | NOS |  | 9 | 1 |  | 1 |  | 1
| Starter Panel 1 | NOS |  | 8 |  |  | 2 |  | 2
| Starter Panel 2 | NOS |  | 8 |  |  |  | 2 |  | 2
| Starter Panel 3 | NOS |  | 8 |  |  | 1 |  | 1
| Starter Panel 4 | NOS |  | 8 |  |  |  | 2 |  | 2
| Air washer and scrubber panel |  |  | 14200112 |  |  |  | 1 |  | 1
| XLPE Copper Armoured Cable 2core*4 | Mtr |  | 4318 |  |  | 1911 | 1929 | 1911 | 1929
| Supply and fixing of perforated M.S sheet steel slotted cable trays with vertical sides on both ends as per approved design and MS angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter MS rod hangers, hooks, dash fasteners, painting etc. for suspension from ceiling as required | RMT | 25 |  | 570 |  | 570 |  | 570
NS | Industrial Socket
a | 16A socket Single phase | [5 empty] | 1 |  | 1
b | 16A socket Three phase | [6 empty] | 4 |  | 4
c | 16/32 A socket Single phase 20A | [5 empty] | 9 | 1 | 9 | 1
d | 16/32 A socket Three phase 20A | [5 empty] | 7 | 1 | 7 | 1
e | 16/32 A socket Single phase 25A | [5 empty] | 17 |  | 17
f | 16/32 A socket Three phase 32A |  |  | 694, 691, 870, 1131, 557 |  |  |  | 1 |  | 1
g | 63 A socket three phase |  |  | 694, 691, 870, 1131, 557 |  |  |  | 1 |  | 1
h | 125 A socket Three Phase |  |  | 694, 691, 870, 1131, 557 |  |  | 3 |  | 3
MEASUREMENT SUMMARY
S. No | Item Description | Unit |  | Page No. | Measurement Break Up | BH | GH | Cumm BH | Cumm GH
RA-6 | Rcc PIPE 250 BH | RM |  |  | 209.44
Final bill | Rcc PIPE 250 BH | RM |  |  | 252.6 |  |  | 462.04
RA-6 | Rcc PIPE 150 BH | RM |  |  |  | 142.15 |  | 142.15
Final bill. | Rcc PIPE 150 BH | RM |  |  |  | 354.7 |  | 496.85
RA8 | Rcc PIPE 150 GH | RM | [6 empty] | 40
Chamber
RA10 | 750 x 750 x 1000 mm | Nos |  | 297 |  |  | 2 |  | 2
| 600 x 600 x 750 mm |  |  |  |  | 3
| 600 x 600 x 750 mm | nos |  |  |  | 19 |  | 22
Chamber
| 1200*1200 | Nos |  | 69 | 2
Note on E254: Author: pending

## Challan Details HVAC BH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
HVAC CHALLAN DETAILS BOYS HOSTEL RA-10
S.NO. | Unit Capacity as per BOQ | Module Configuration |  | UNIT | BOQ Qty. | Previous bill | Challan No. | PREV. | THIS BILL | CUMM. | Remarks
1 | Outdoor Units
A | 14 HP Outdoor unit | AM140JXVANH/TL |  | Nos. |  | 16817, 19, 20, 14480 |  | 3 | 0 | 3
B | 18 HP Outdoor unit | AM180JXVANH/TL |  | Nos. |  | 16820 |  | 2 | 0 | 2
C | 20 HP Outdoor unit | AM200JXVANH/TL |  | Nos. |  | 16817, 19, 20 |  | 5 | 0 | 5
D | 22 HP Outdoor unit | AM220JXVANH/TL |  | Nos. | 3 | 16820, 14480 |  | 3 | 0 | 3
E | 24 HP Outdoor unit | AM240KXVANH/TL |  | Nos. | 4 | 16817, 19, 14480 |  | 7 | 0 | 7
F | 26 HP Outdoor unit | AM260KXVANH/TL |  | Nos. |  | 16817, 19 |  | 4 | 0 | 4
G | 30 HP Outdoor unit | AM300KXVANH/TL |  | Nos. | 1 | 16817, 19, 14481 |  | 13 | 0 | 13
H | 32 HP Outdoor unit | AM100JXVANH/TL | AM220JXVANH/TL | Nos. |  | 16820 |  | 2 | 0 | 2
I | 34 HP Outdoor unit | AM120JXVANH/TL | AM220JXVANH/TL | Nos. | 1 | 14480 |  | 1 | 0 | 1
J | 36 HP Outdoor unit | AM140JXVANH/TL | AM220JXVANH/TL | Nos. | 1 | 16820 |  | 1 | 0 | 1
K | 40 HP Outdoor unit | AM180JXVANH/TL | AM220JXVANH/TL | Nos. | 2 | 16820 |  | 7 | 0 | 7
L | 42 HP Outdoor unit | AM200JXVANH/TL | AM220JXVANH/TL | Nos. |  | 16820 |  | 1 | 0 | 1
M | 44 HP Outdoor unit | AM220JXVANH/TL | AM220JXVANH/TL | Nos. | 1 |  |  | 4 | 0 | 4
N | 46 HP Outdoor unit | AM160JXVANH/TL | AM300KXVANH/TL | Nos. |  | 16816, 19 |  | 2 | 0 | 2
O | 50 HP Outdoor unit | AM300KXVANH/TL | AM200KXVANH/TL | Nos. |  | 16819 |  | 1 | 0 | 1
P | 54 HP Outdoor unit | AM300KXVANH/TL | AM240KXVANH/TL | Nos. | 1 |  |  | 1 | 0 | 1
b) | Supplying, installing, testing and commissioning of Modular type Ceiling mounted Double skin Air Handling Unit complete with cooling coil of copper tubes with aluminium fins (12 fins / inch) and condensate drain pan of stainless steel with insulation. Blower section with DIDW backward curved blower impeller drive set with high efficiency motor suitable for 415±10% volt, 3 phase 50 Hz supply to meet LEED requirements. Fine filters MERV 13 as per LEED parameters. .It should consist fan section & canvas connection cooling coils, earthing of motor and unit with necessory wiring vibration isolator and supporting frame.
i | Capacity 6000 CFM, 15.5 TR at 30 mm static pressure, 4 rows deep coil area, motor rating 3.7 KW for Common area of level 3 |  |  | Nos | 4 | 469 |  | 4 |  | 4
ii | Capacity 7000 CFM, 25 TR at 30 mm static pressure, 4 rows deep coil area, motor rating 3.7 KW for Common area of level 3 |  |  | Nos | 1 | 469 |  | 1 |  | 1
2 | Indoor Units
2 (i) | HI WALL with individual cordless remote.
A | 1.05 TR (335 CFM) | AM036KNQDEH/TL |  | Nos. | 378 | 16817, 19, 20, 14480 |  | 370 | 0 | 370
B | 1.33 TR (424 CFM) | AM045KNQDEH/TL |  | Nos. | 45 | 16920, 14481 |  | 30 | 0 | 30
C | 1.65 TR (530 CFM) | AM056FNQDEH/TL |  | Nos. | 142 | 16818, 14481 |  | 139 | 0 | 139
D | 2.07 TR (671 CFM) | AM071FNQDEH/TL |  | Nos. | 332 | 16816, 18, 14481 |  | 290 | 0 | 290
DUCTABLE TYPE
i | 6.50 TR (2047 CFM) |  |  | Nos. | 2 | 234567 |  | 17 | 0 | 17
ii | 8.19 TR (2542 CFM) |  |  | Nos. | 5 |  |  | 5 | 0 | 5
4 | Remote Control | MWR-SH00N |  | Nos. | 915 |  |  | 852 | 0 | 852
A |  | MXJ-YA1509M | 440 | Nos.
B |  | MXJ-YA2512M | 198 | Nos.
C |  | MXJ-YA2812M | 41 | Nos.
D |  | MXJ-YA2815M | 76 | Nos.
E |  | MXJ-YA3419M | 21 | Nos.
F |  | MXJ-YA4119M | 20 | Nos.
G |  | MXJ-TA4422M | 1 | Nos.
H |  | MXJ-TA3819M | 7 | Nos.
2.2 | Ref -Joints |  |  | Nos. | 915 | 234567 |  | 823 | 0 | 823
3 | Refrigerant Piping
Supply, Receiving,Handling,Installation,testing and commissioning of interconnecting copper refrigerant pipe work duly insulated (13/19 mm thick) with elastomeric nitrile rubber type tubular insulation between indoor & outdoor units. All piping inside the room shall be properly supported with hanger and all external piping shall run in covered cable tray. Only two upper size of refrigerant piping on terrace level are exposed.
a) | 41.3mm OD with 19 mm thick nitrile rubber insulation |  |  | RMT | 606 | 125, | 3 | 61.4 | 46.2 | 107.6
b) | 34.9mm OD with 19 mm thick nitrile rubber insulation |  |  | RMT | 1044 | 125, | 3 | 61.4 | 92.4 | 153.8
c) | 28.6mm OD with 19 mm thick nitrile rubber insulation |  |  | RMT | 995 | 125, 138, | 3, 5,11 | 322.8 | 956 | 1278.8
d) | 22.2mm OD with 19 mm thick nitrile rubber insulation |  |  | RMT | 1340 | 125, 138, | 5 | 215.8 | 84.2 | 300
e) | 19.1mm OD with 13 mm thick nitrile rubber insulation |  |  | RMT | 1045 | 125 | 3 | 400 | 303 | 703
f) | 15.9mm OD with 13 mm thick nitrile rubber insulation |  |  | RMT | 4270 | 125, 138, | 3, 5, 11 | 1694 | 2726.4 | 4420.4
g) | 12.7mm OD with 13 mm thick nitrile rubber insulation |  |  | RMT | 840 | 125 | 3, 11 | 1386 | 893 | 2279
h) | 9.5mm OD with 13 mm thick nitrile rubber insulation |  |  | RMT | 3780 | 125, 138, | 3, 5, 11 | 1927 | 2804 | 4731
i) | 6.4mm OD with 13 mm thick nitrile rubber insulation |  |  | RMT | 400 | 125 |  | 1294 |  | 1294
7 | Condensate Drain Piping
Supply,Providing, fixing and testing uPVC drain piping for condensate from room Indoor unit to nearest suitable drain system as per site conditions as instructed by site engineer complete with all required fittings and providing clean out plug at suitable location for roding the pipe when required complete with 2 layers of 6mm thickness with elastomeric nitrile rubber insulation over uPVC pipe:
a) | 40mm OD |  |  | RMT | 400 | 1569 |  | 400 | 0 | 400
b) | 32mm OD |  |  | RMT | 2200 | 1573, 1569 |  | 2200 | 0 | 2200
c) | 25mm OD |  |  | RMT | 3100 | 1569 |  | 3100 | 0 | 3100
4 | Transmission & Control Wiring
Supply,Providing & fixing control cum transmission wiring in medium duty PVC Conduit between indoor and outdoor units.
| 2CX15 Sqm Cu Cable |  |  | RMT | 13500 | 5, 6,138 | 4 | 5300 | 3429 | 8729
1 | Ducting:
Supply, fabricating, installing and testing of G.I. Sheet metal ducts and flanges as per IS specifications complete with supports, Vanes, dampers, links, levers and quadrants etc. as per specifications and drawings. The rates shall include all materials and labour for suspension and supporting arrangement of galvanised steel for Plenums, Ducts, complete with fire retardant factory fabricated flexible connection as per required specifications
a) | 0.63 MM (24 Gauge ) |  |  |  | 100 | 39, 70, 71, 84, 3376,3382 |  | 2450 | 49 | 2499
b) | 0.80 MM (22 Gauge ) |  |  |  | 50 | 70, 71, 84,3376,3382 |  | 100 |  | 100
c) | 1.00 MM (20 Gauge ) | [8 empty] | 0
d) | 1.25 MM (18 Gauge ) |  |  |  | 50 | 84, 71,3382 |  | 50.49 |  | 50.49
3 | Thermal Insulation:
| Supplying, installation, testing and commissioning of thermal insulation with 9mm thick, 40-60 Kg / M³ density closed cell elastomeric nitrile rubber, class 'O' secured with manufacturer's adhesive. The duct supports should also be of nitrile rubber with PUF/PIR inserts. |  |  | SQM | 150 |  | 140,153, 46, 11 | 792 | 861 | 1653
| Supply air duct with 25mm thick acoustic lining |  |  | SQM | 50 |  | 46, 11 |  | 98 | 98
N S Items
1 | Air Washer Unit 37000 CFM |  |  | NOS. |  | 577 |  | 1 | 0 | 1
2 | Air Scrubber Unit 20250 |  |  | NOS. |  | 577 |  | 2 | 0 | 2
NS 13 | Axial Flow Fan 8000 Cfm |  |  | NOS. |  |  | 151 |  | 8 | 8
Grilles & Diffusers
1 | Providing, fixing, testing and commissioning of powder coated extruded aluminium grills .
0
a) | Supply/Exhaust Grills with Dampers | [5 empty] | 677 | 5 |  | 5 | 5
0
b) | Supply/Exhaust Grills without Dampers | [5 empty] | 677 | 4 | 89 | 93 | 4
0
3 | Supply , Installation & testing of GI volume control damper (Box type) within ducts to be provided with suitable links, levers and quadrants for manual control of volume of air flow and for proper balancing of the air distribution system as per approved shop drawings. | [5 empty] | 677 | 1 | 11 | 12 | 1
0
4 | Supply,Installing, testing and balancing of square supply air diffusers, air distribution grid for straightening the air flow through the collar and register and removable key-operated volume control dampers. | [8 empty] | 0
0
a) | Powder Coated Aluminium square diffuser with volume control damper | [5 empty] | 677 | 3 | 13.64 | 16.64 | 3
0
NS | 1000 CFM | [5 empty] | 179 |  | 2 | 2
| 600 CFM | [5 empty] | 179 |  | 1 | 1
| 400 CFM | [5 empty] | 179 |  | 1 | 1
| 150 CFM | [5 empty] | 179 |  | 1 | 1
[7 empty] | 179 |  | 2 | 2
NS 7 | 2.2 KW Dol Starter | [5 empty] | 8, 2 |  | 8 | 8 | Electrical invoice
NS 7 | 3.7 KW Dol Starter | [5 empty] | 2 |  | 5 | 5 | Electrical invoice

## Challan Detail HVAC GH (hidden)
PROJECT : THAPAR EXTENSION PATIALA
HVAC CHALLAN DETAILS GIRLS HOSTEL ( RA-10)
S.NO. | DISCRIPTION | Prev. Invoices | Current Invoice | Unit | BOQ Qty. | Prev. Qty | This Bill | Cumm. Qty.
SUB HEAD-II : PIPING
1 | Supply, installation, testing and commissioning of the following Mild Steel heavy class pipes upto 150 mm size as per IS Specification and 6 mm wall thickness upto 250 mm, cut to required lengths and installed with all welded joints including the necessary fittings like supports, elbows/bends tees and reducers.All Pipe shall be rating confirming to PN 10.
Size
a) | 250 mm | 2791 |  | MM | 20 | 18 |  | 18
b) | 200 mm | 3006, 2791 |  | MM | 80 | 72 |  | 72
c) | 150 mm | 3006 |  | MM | 40 | 102 |  | 102
d) | 125 mm | 2791 |  | MM | 25 | 30 |  | 30
e) | 100 mm | 2791 |  | MM | 20 | 30 |  | 30
f) | 80 mm | 2791 |  | MM | 250 | 258 |  | 258
g) | 65 mm | 2791, 5330, 5947 |  | MM | 370 | 678 |  | 678
h) | 50 mm | 2791 |  | MM | 610 | 666 |  | 666
i) | 40 mm | 2791 |  | MM | 370 | 540 |  | 540
j) | 32 mm | 2791, 5947 |  | MM | 735 | 738 |  | 738
k) | 25 mm | 3006, 2791, 5334,5330, 5947 |  | MM | 400 | 2094 |  | 2094
l) | 20 mm | 3089 |  | MM | 2500 | 2790 |  | 2790
0
2 | Providing and fixing, testing and commissioning Butterfly valve will flanges gasket duly insulated with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive. | [6 empty] | 0
a) | 65 mm | 1666 |  | nos |  | 1 |  | 1
b) | 50 mm
0
3 | Providing, fixing, testing and commissioning of GM gate / Ball valve insulated with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive. | [6 empty] | 0
a) | 40 mm | [6 empty] | 0
b) | 32 mm |  | 21 |  |  |  | 1 | 1
c) | 25 mm | 1666 |  | nos |  | 2 |  | 2
0
6 | Providing. Fixing, testing and commissioning of Insulation with Nitrile Rubber pre-slit, pre-glued pipe sleeve or factory pre-cut sheets of Nitrile rubber insulation of 19/25mm thicknesses as specified, with approved adhesive. Manufactured supplied, suitable sized nitrile rubber pipe supports with PUF/PIR inserts shall be used. .
a) | 200 mm with 25mm thick |  |  |  | 20 |  |  | 0
a) | 200 mm with 25mm thick |  |  | MM | 80 |  |  | 0
b) | 150 mm with 25mm thick |  | 11 | MM | 40 |  | 90 | 90
c) | 125 mm with 25mm thick |  | 11 | MM | 25 |  | 26 | 26
d) | 100 mm with 25mm thick |  | 11 | MM | 20 |  | 30 | 30
e) | 80 mm with 25mm thick | 111617 | 11 | MM | 250 | 252 | 15 | 267
f) | 65 mm with 25mm thick | 111617 |  | MM | 370 | 480 |  | 480
g) | 50 mm with 19mm thick | 111617 |  | MM | 610 | 648 | 0 | 648
h) | 40 mm with 19mm thick | 111617 |  | MM | 370 | 504 |  | 504
i) | 32 mm with 19mm thick | 111617, 171800364 |  | MM | 735 | 684 |  | 684
j) | 25 mm with 19mm thick | 111617 |  | MM | 400 | 2052 |  | 2052
k) | 20 mm with 19mm thick | 111617 |  | MM | 2500 | 2744 |  | 2744
| Air Purging Valve 20 mm |  | 95 |  |  |  | 4 | 4
0
3 | Thermal Insulation: | [6 empty] | 0
| Supplying, installation, testing and commissioning of thermal insulation with 9mm thick, 40-60 Kg / M³ density closed cell elastomeric nitrile rubber, class 'O' secured with manufacturer's adhesive. The duct supports should also be of nitrile rubber with PUF/PIR inserts. | 111617 |  | Sqm | 150 | 288 |  | 288
Condensate Drain Piping
| 32 mm drain |  | 1320 |  |  | 102 | 252 | 354
4 | Acoustic Lining of Ducts:
Supplying, installing, testing & commissioning of duct acoustic lining with 25mm thick, density shall not be less than 48 kg/cu.m of acoustic lining within supply air ducts as per the specifications. All ducts shown cross hatched on the approved shop drawings shall be provided with acoustic lining of fibre glass insulation as per the specifications.
a) | Supply air duct with 25mm thick acoustic lining |  |  | Sqm | 50 | 96 |  | 96
1 | Air Handling Units & Accessories
| Supplying, Unloading and delivery at site of Modular/Non Modular type ceiling mounted double skin Air Handling Unit complete with Blower, Motor, Drive set, cooling coil 12 fins per inch, Filters capable of filtering upto 10 microns at 90% efficiency and anti-vibration mountings complete as per specifications and drawings of the following capacities.Motor shall be suitable for 415 ± 10 % volts, 3 phase, 50 cycles AC supply. Motor efficiency shall be minimum 70%. | 36 |  | Nos. | 1 | 1 |  | 1
a) | Capacity 3400 CMH (2000 CFM), 3.9 TR at 30 mm static pressure, 4 rows deep coil area, 0.37 sq m.,motor rating 1.1 KW for Reception | 36 |  | Nos. | 1 | 1 |  | 1
b) | Capacity 2550 CMH (1500 CFM), 3.2 TR at 30 mm static pressure, 4 rows deep coil area, 0.37 sq m.,motor rating 1.1 KW for Reception | [6 empty] | 0
c) | Capacity 1700 CMH (1000 CFM), 1.7 TR at 30 mm static pressure, 4 rows deep coil area, 0.18 sq m.,motor rating 0.55 KW for changing room. | 36 | 670 | Nos. | 2 | 2 | 1 | 3
0
2 | Tower Type Floor Mounted Indoor Units | [6 empty] | 0
| Supplying, Unloading and delivery at site of Modular/Non Modular type Floor mounted Indoor Unit complete with Blower, Motor, Drive set, cooling coil 12 fins per inch, Filters capable of filtering upto 10 microns at 90% efficiency and anti-vibration mountings and drawings of the following capacities.Motor shall be suitable for 415 ± 10 % volts, 3 phase, 50 cycles AC supply. Motor efficiency shall be minimum 70%. | [6 empty] | 0
a) | Capacity 1294 CFM, 4.5 TR at , 4 rows deep coil area, 0.37 sq m., for Dinning Hall & Gym | 86 |  | Nos. | 19 | 20 |  | 20
0
2 | Tower Type Floor Mounted Indoor Units | [6 empty] | 0
3 | Supplying, installing, testing and commissioning of Wall mouted finished type Hi wall unit with blower, motor, cooling coil of 12 fins per inch, filters, insulated drain pan and accessories namely Ball valves, supply/return air-grille and 2 way solonoid valve with thermostate and ON/OFF 3 speed regulator swtich as per specifications and drawings including electrical wiring from socket to FCUs and control wiring. The unit shall be suitable for locating above false ceiling. | [6 empty] | 0
a) | Capacity 1.0 TR (400 CFM) | 473, 476, 11800780 |  | Nos | 192 | 186 |  | 186
b) | Capacity 1.5 TR (600 CFM) | 473, 476 |  | Nos | 206 | 205 |  | 205
c | Capacity 2 TR 800CFM | 482 |  | Nos |  |  |  | 48
III | Air Distribution System
1 | Ducting:
Supply, fabricating, installing and testing of G.I. Sheet metal ducts and flanges as per IS specifications complete with supports, Vanes, dampers, links, levers and quadrants etc. as per specifications and drawings. The rates shall include all materials and labour for suspension and supporting arrangement of galvanised steel for Plenums, Ducts, complete with fire retardant factory fabricated flexible connection as per required specifications
a) | 0.63 MM (24 Gauge ) | 39, 70, 71, 84,3382 |  | Sqm | 100 | 387.49 |  | 387.49
b) | 0.80 MM (22 Gauge ) | 70, 71, 84,3382 |  | Sqm | 50 | 62.7 |  | 62.7
c) | 1.00 MM (20 Gauge ) |  |  | Sqm | 50
d) | 1.25 MM (18 Gauge ) | 84, 71,3376 |  | Sqm |  | 20.64 |  | 20.64
1 | Air Washer Unit 8000 CFM | 577 |  | nos |  | 2 |  | 2
2 | Air Scrubber Unit 9000 | 577 |  | nos |  | 2 |  | 2
NS 13 | Axial Flow Fan 8000 Cfm |  |  | nos |  | 2 |  | 2
NS | Air Handling unit 6000 CFM |  |  | NOS |  | 1 |  | 1
NS | Butterfly Valves 150mm |  |  | NOS |  | 2 |  | 2
| Butterfly Valves 100mm |  |  | NOS |  | 1 |  | 1
| Butterfly Valves 80mm |  |  | NOS |  | 12 |  | 12
| Balancing Valve 80 mm |  |  | NOS |  | 12 |  | 12
| Balancing Valve 100 mm |  |  | NOS |  | 1 |  | 1
| Balancing Valve 150 mm |  |  | NOS |  | 2 |  | 2
| Balancing Valve 65 mm |  |  | NOS |  | 1 |  | 1
NS | 1100 CFM |  | 179 | nos |  |  | 1 | 1
| 500 CFM |  | 179 | nos |  |  | 1 | 1
Anergy 2 way valve
a) | 40 mm | nos | 5243 | NOS |  |  | 1 | 1
b) | 32 mm | nos | 5243 | NOS |  |  |  | 0
c) | 25 mm | nos | 5243 | NOS |  |  | 20 | 20
d) | 20 mm | nos | 5243 | NOS |  |  | 4 | 4
a) | Supply/Exhaust Grills with Dampers |  | 423 |  |  |  | 6.15 | 6.15
0
b) | Supply/Exhaust Grills without Dampers |  | 423 |  |  |  | 2.39 | 2.39
0
| VCD |  | 85 |  |  |  | 1 | 1
0
a) | Powder Coated Aluminium square diffuser with volume control damper |  | 182 |  |  |  | 6.3 | 6.3
0
b) | Powder Coated Aluminium square diffuser without volume control damper |  | 677 |  |  |  | 1.55 | 1.55
Ball valve witch Y stainer
a) | 50 mm | [6 empty] | 1
b) | 40 mm
c) | 32 mm |  | 21 |  |  |  | 1 | 1
d) | 25 mm |  | 11, 26 |  |  |  | 24 | 24
Copper pipe supply
1 | 15.9mm OD with 13 mm thick nitrile rubber insulation |  | 37, 38 |  |  |  | 373.33 | 373.33
2 | 19.1mm OD with 13 mm thick nitrile rubber insulation |  | 37, 38 |  |  |  | 29.8 | 29.8
3 | 9.5mm OD with 13 mm thick nitrile rubber insulation |  | 37, 38 |  |  |  | 29.8 | 29.8
NS-6 | 2.2 KW Dol Starter |  | 2, 8 |  |  |  | 4 | 4
NS-6 | 3.7 KW Dol Starter |  | 2, 8 |  |  |  | 4 | 4

## Challans Details of PLUMBING (hidden)
PROJECT : THAPAR EXTENSION PATIALA
PLUMBING CHALLAN DETAILS RA-10
S.No. | Description | Previous Challan No. | Running Challan No. | Unit | BOQ Qty. in BH | BOQ Qty. in GH | Prev. Qty. | This Bill Qty. BH | This Bill Qty. GH | Cumm. Qty. BH | Cumm. Qty. GH | Remarks
B | TOTAL FOR SOIL, WASTE,VENT & FITTINGS
UPVC SWR (Type-B)
I | Vertical Pipe
a) | 75 mm OD | 1196, 1458, 1457, 1463, vt0438 | 491 | RM | 2160 | 0 | 2391 | 656 | 160 | 2297 | 909 | 17 mtr PB Hostel
b) | 110 mm OD | 1196, 1302, 1384, 1458, 1833 |  | RM | 4320 | 1080 | 6003 |  |  | 4320 | 1683
c) | 160 mm OD | 1196,1659, 1742 |  | RM | 80 | 20 | 496 |  |  | 80 | 416
II | Pipe at Ceiling
a) | 75 mm OD |  |  | RM | 200 | 50 |  |  |  | 0
b) | 110mm OD | 1458, 1823, vt0099, vt128 |  | RM | 200 | 50 | 2346 |  |  | 755 | 2146
c) | 160mm OD | 13131659, vt0456, vt0491 |  | RM | 280 | 70 | 430 |  |  | 532 | 70
III | Pipe at Floor
a) | 75 mm OD | [8 empty] | 0
b) | 110mm OD | 1313 , 1471, 1457, 1455,1463, 1833, 19 |  | RM | 4032 | 1008 | 5640 |  |  | 4062 | 1578
uPVC SWR (6kg/2cm)
a) | 40 mm OD | 1313, 1188, 1455, 1823 |  | RM | 2080 | 1040 | 1560 |  |  | 1240 | 320
b) | 50 mm OD | 1823 | 1823 |  | 1040 | 520 | 300 |  | 222 |  | 522
c) | 63 mm OD | 1313,1196, 1188, 1458, 1455, 438 |  | RM | 2600 | 130 | 3210 | 600 |  | 2609 | 1200
P or S trap
a) | 110x 110mm | 1309 ,1471, 1196, 1189, 1457, 1756 | 438 | Nos | 520 | 205 | 730 | 124 | 12 | 844 | 328
7 | Providing, Fixing & testing of 125 mm dia, 1 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete. | 1310 | 35, 67 |  | 1040 | 410 | 1500 | 165 | 161 | 1205 | 621
125mm dia over Floor Trap & floor Drain
5 | Providing, Fixing & testing of uPVC SWR inlet fittings with two or three saddle inlets of 40, 50 or 63 mm size, fabricated from 110 mm outer dia uPVC pipes and fixed to uPVC traps with solvent cement joint complete. | 3921 | 16627 | Nos | 520 |  | 294 | 268 | 154 | 468 | 248
| uPVC SWR inlet fittings | [8 empty] | 0
5 | Two or three saddle inlets of 40, 50 or 63 mm size, fabricated from 110 mm outer dia uPVC pipes |  |  | Nos | 520 |  |  |  |  | 0
6 | Providing, Fixing & testing of uPVC reducing elbow as floor drain in cement concrete 1:2:4 float with floor complete in all respects.
| 110 x63 mm outlet | 1189, 1458 |  | Each | 524 |  | 228 |  |  | 228
c) | RAIN WATER PIPES & FITTINGS
uPVC pipe (6 kg per sqcm)
a) | 75 mm OD |  |  | RM | 60
b) | 110 mm OD | 1313,1196,1188,1458,1455, 1823 |  | RM | 100 | 50 | 1280 |  |  | 1026 | 254
c) | 160 mm OD | 1313, 1541, 1458, 1823, vt0491 |  | RM | 840 |  | 1290 | 482 |  | 1220 | 552
d) | 210 mm OD | 1313, 1196,1188,1458, 1823 | 559 | RM | 100 | 300 | 342 | 122 | 28 | 264 | 228
GI medium class pipe
a) | 15 mm nominal bore | 951, | 5601 | RM | 0 |  | 368.6 |  | 219 | 159 | 219
b) | 20 mm nominal bore | 885, 951 |  | RM | 960 | 142 | 813.39 | -415 | 286 | 813.39 | 286
c) | 25 mm nominal bore | 951 | 899 | RM | 1920 | 166 | 597.8 | 1024 | 526 | 1621.8 | 526
d) | 32 mm nominal bore | 885 |  | RM | 1920 | 236 | 1958.5 | -969 | 664 | 1920 | 664 | 118
e) | 40 mm nominal bore | 885, 5601 | 2774 | RM | 1920 | 290 | 1526.41 | -441 | 489 | 1406.1 | 489
f) | 50 mm nominal bore | 951, 5601 | 899 | RM | 960 | 337 | 724.5 | 333 | 265 | 863.5 | 265
g) | 65 mm nominal bore | 5601 |  | RM | 400 | 449 | 192 |  | 137 | 100 | 137 | Fitting added
h) | 80 mm nominal bore | 885 |  | RM | 800 | 565 | 518.14 | -371 | 57 | 518.1 | 57
i) | 100 mm nominal bore | 885 |  | RM | 200 | 732 | 300.74 |  |  | 300.74
D | WATER SUPPLY SYSTEM
a) | 15 mm nominal bore | 1188, 1457, 227, 5949 | 559 | RM | 7560 | 350 | 9941 | 1256 |  | 8816 | 4940
b) | 20 mm nominal bore | 1188, 1457 |  | RM | 2520 | 1225 | 3840 |  |  | 2520 | 1320
c) | 25 mm nominal bore | 1188, 1457 | 559 | RM |  |  | 2280 | 725 |  | 2005 | 1000
d) | 32 mm nominal bore |  |  | RM
e) | 40 mm nominal bore |  |  | RM
8 | Providing and fixing M.S fabricated hot dipped galvanized coating puddle flange comprising of 600 mm dia long/As per requirement M.S class 'C' pipe (screwed end up to 50 mm & flange for more than 50 mm dia) with 6 mm thick M.S plates of required size including cutting holes in centre of plate, inserting pipe & making welded (Arc) joint complete. Same shall be installed with TEC welded joint in position with reinforcement bars of RCC tank wall/slab including making cutout in shuttering during concrete casting of tank of following diameter.
a) | 25 mm dia | 430 |  |  | 12 | 3 | 38 |  | 6 | 32 | 12 | Manufacture at site
b) | 32 mm dia | 430 |  |  | 12 | 3 | 1 |  |  | 1 | 0
c) | 40 mm dia | 430 |  |  | 0 |  | 5 |  | 1 | 4 | 2 | Manufacture at site
d) | 50 mm dia | 430 |  |  | 48 | 12 | 28 |  | 8 | 20 | 16 | Manufacture at site
e) | 65 mm dia | 430 |  |  | 20 | 6 | 8 |  | 1 | 7 | 2 | Manufacture at site
f) | 80 mm dia | 430 |  |  | 8 | 4 | 41 |  | 2 | 39 | 4 | Manufacture at site
g) | 100 mm dia | 430 |  |  | 8 | 4 | 31 |  | 3 | 28 | 6 | Manufacture at site
h) | 150 mm dia | 430 |  |  | 8 | 2 | 17 |  | 1 | 16 | 2 | Manufacture at site
E | FIRE HYDRANT SYSTEM
7 | Supply, Installation testing & commissioning of Black Mild Steel Class 'C' (Heavy Duty) pipes conforming to IS : 1239 Part-I including cutting, threading, welding & all MS fittings like flanges, tees, elbows, bends junctions, reducers etc. welded or screwed joints, clamps structural steel supports (as per TAC norms) or as required/ directed at site including cutting & making good the walls, floors, RCC work etc cutting chases & filling the same with cement concrete 1:3:6 (1 cement :3 coarse sand :6 graded stone aggregate 20 mm nominal size) (For Internal work).(Supports will be measured extra.) Note: Pipes upto and 50 mm dia shall be threaded joints, above 50 mm shall be welded joints.
a) | 25 mm dia (Nominal Bore) |  |  |  | 100 | 25
b) | 80 mm dia (Nominal Bore) |  |  |  | 80 | 25
c) | 100 mm dia (Nominal Bore) | 4370 | 580, 1009, 5947 |  | 400 | 200 | 366 | 228 | 38 | 528 | 104
d) | 150 mm dia (Nominal Bore) |  | 413 |  | 200 | 50 |  | 24 |  | 24
8 | Providing and making drainage provision for dia MS (Medium Class"B") pipe (Drainage pipe)
a) | 80 mm dia | 4370 | 1009, 5947 |  | 280 | 150 | 246 | 120.47 | 104 | 320.47 | 150
3 | Providing, Fixing & testing of stainless steel ball valve working pressure of 10 Kg/cm2 with wheel & female screwed ends of approved quality to I complete in all respects.
a) | 15 mm nominal bore | 1225. 1242 | 1393 | Each | 520 | 260 | 802 |  | 17 | 542 | 277
b) | 20 mm nominal bore | 789, 2775, 1225 | 1393 | Each | 1040 | 260 | 265 | -265 | 17 | 17 | 17
c) | 25 mm nominal bore | 1225 | 1393 | Each | 8 | 4 | 519 |  | 310 | 829 | 310
d) | 32 mm nominal bore | 1225 | 1393 | Each | 12 | 25 | 94 |  | 49 | 143 | 49
e) | 40 mm nominal bore | 2775,1225 | 1393 | Each | 12 | 25 | 27 |  | 51 | 78 | 51
8 | Supply, Installation, Testing & Commissioning of the following size of C.I. Butterfly valve conforming to IS : 13095 with nut, bolts and washers complete. [PN -1.6 rating (16kg/cm2)]
a) | 150 mm dia |  | 1394 | [5 empty] | 4 |  | 4 |  | 16
b) | 100 mm dia |  | 1394 | [5 empty] | 4 |  | 4 |  | 28
c) | 80 mm dia |  | 1394 | [5 empty] | 2 |  | 2 |  | 26
A | EXTERNAL WATER SUPPLY SYSTEM
G.I. Pipes Class 'C' (Heavy grade)
a) | 20 mm dia
b) | 25 mm dia
c) | 32 mm dia | 13082774 |  | RM | 0 |  | 78 |  |  | 78
d) | 40 mm dia | 1308, 2346, 2774, 5350 |  | RM | 0 |  | 408 |  |  | 286 | 122
e) | 50 mm dia | 1308, 5350 |  | RM | 200 |  | 348 |  |  | 200 | 148
f) | 65 mm dia | 2346 |  | RM | 200 |  | 24 |  |  | 24
C | EXTERNAL SEWERAGE SYSTEM
UPVC Drainage Pipe
a) | 110 mm OD U-Drain Pipe (SN8)
b) | 160 mm OD U-Drain Pipe (SN4)
c) | 200 mm OD U-Drain Pipe (SN4) | 98, 19 | 794 | RM | 800 | 300 | 732 | 161 |  | 659 | 234
d) | 250 mm OD U-Drain Pipe (SN4)
4 | Providing and fixing C.I. double flanged butterfly valve working pressure of 10 Kg/cm2 complete with bolts, nuts, washers 3 mm thick insertion neoprene gasket.
a) | 50 mm nominal bore
b) | 65 mm nominal bore | 28 |  | nos | [5 empty] | 5
c) | 80 mm dia | 28 |  | nos | [5 empty] | 20
d) | 100 mm dia | 28 |  | nos | [5 empty] | 18
10 | Providing & fixing single acting air valve of 25 mm dia as per IS : 14845 including 25 mm dia Ball valve and all fitting etc. as per the requirement. | 28 |  | Nos | [5 empty] | 8 | 4
11 | Supply, Installation, Testing & Commissioning of CI Slim seal Butterfly valves, PN :1.0 rating conforming to IS : 13095 with complete with 2 Nos. matching flanges rubber insertion, nuts. bolts and washer etc. of following sizes.
| 150 mm dia | 28 |  | nos | [5 empty] | 8 | 4
4 | Providing and fixing square mouth (S.W) gully trap grade `A' complete with C.I. grating brick masonry chamber with bricks of class designation 75 and water tight double seal C.I. cover with frame of 300 x 300 mm internal size. The weight of cover to be not less than 4.5 kg and frame to be not less than 2.70 kg. as per standard design.
a) | 100 x 100 mm size ‘P’ type. | 2038 | 794 |  |  |  | 48 |  | 21 | 48 | 21 | 1 from BH
D | STORM WATER DRAINAGE SYSTEM
Providing, laying and jointing light duty non-pressure NP2 class S/S R.C.C. pipes with collars jointing with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including curing, testing of joints etc.
a) | 250 mm dia | 1472, 1924, 1047, 1170 |  | RM | 1200 |  | 350 |  |  | 350 | 150
b) | 300 mm dia | 1951, 1913, 2006 |  | RM | 0 |  | 255 | 198 |  | 274
| EXTERNAL SEWERAGE SYSTEM | [8 empty] | `
a. | 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . | 35,21 | 6 | Nos. |  |  | 50 |  | 7 | 77 | 20
STORM WATER DRAINAGE SYSTEM
| 90cms dia depth beyond 75 cms to 149cms with ISI marked steel fibre reinforced cement concrete (SFRC) manhole cover and frame (heavi duty )560mm internal diameter ,conforming to I.S. 12592 specifications of the brand as approved . | 35,21 |  |  |  |  | 43 |  |  | 55 | 15
E | FIRE HYDRANT SYSTEM
Providing and fixing fire booster pump comprisiong of mono block pump and 3 Phase 440 volts/50 cycles per second with TEFC induction motor of the following capacity with mechanical seal including electric panel , cablling ,foundation ,scution,and devilivery header ,valve and fittings etc,and complete in all respect as per good praatice .location at terrace.
Capacity: 900 LPM
Head : 30 Metre
HP -9 (Approx.) or as required.
Impeller- Bronze
Shaft : S.S- 410
RPM - 2900
Mover : Electric Motor
| Quantity : eachset (1 w +1 s) | 759 |  | NOS | 4 | 1 | 6 |  |  | 4 | 2
E | EXTERNAL FIRE HYDRANT SYSTEM
1 | Supply, Installation, Testing & Commissioning of the following size of Black Mild Steel Class `C' (heavy class) pipes conforming to IS : 1239 Part-I including cutting, threading, welding & all fittings like flanges, tees, elbows, bends junctions, reducers etc. welded or screwed joints, clamps & structural steel supports or as required/ directed at site including cutting & making good the walls, floors, RCC work etc cutting chases & filling the same with cement concrete 1:3:6 (1 cement :3 coarse sand :6 graded stone aggregate 20 mm nominal size) including Providing painting the pipes with 2 coats of desired shade of synthetic enamel paint over 2 coats of Red oxide primer. Prior to application of primer the surface should be cleaned for any dirt, rusts, rough substance etc. including Providing painting of legend both direction arrow as per the approved of project manager (For External Hydrant system) [Exposed Pipe].
a) | 80 mm dia | 5947 |  | RM | 80 |  |  | 99.75 |  | 99.75
b) | 100 mm dia | 5947 |  |  | 200 |  |  | 90 |  | 90
c) | 150 mm dia
E | FIRE HYDRANT SYSTEM
1 | Providing & fixing fully glazed M.S fully welded construction single leaf door shutter for fire hydrant station fabricated from M.S. 50x50x6 mm angle iron frame, fixed to wall and hinged M.S 40x40x5 mm angle iron door shutter with required M.S. sash bards for glazing complete with locking arrangements, stove enamelled fire red finish with 'FIRE HYDRANT' written in front.
| Size 2100x900x600 mm deep. |  | 1773 | [5 empty] | 28 |  | 28
2 | Supply,Installation, Testing & Commissioning of Gun-metal ISI marked oblique pattern hydrant landing valve with 80 mm dia flanged inlet and 63 mm dia instantaneous type female outlet complete with gunmetal cap and G.I. chain, twist release type plug and all accessories as per 13:5290-1983 (Type 'A') | 137 |  | nos | 72 | 14 | 84 |  |  | 56 | 28
3 | Providing & Fixing of burden type Stainless Steel dial type pressure gauge with brass isolation valve and pipe. (For each internal Fire hose cabinet)
Dial diameter 100 mm, calibration 0-15 kg
4 | Providing & Fixing of wall mounting swinging type first aid fire hose reel with drum, hanging bracket, 36.5 Mtr. length x 20 mm dia high pressure hose reel tubing as per IS: 444 with gun metal (GM) shut off nozzle having 5 mm dia orifice. The hose reel shall be conforming to IS : 884-1985. Rate shall include 25 mm dia M.S. pipe connection from Riser to hose reel, sockets, nipples, elbows,Union and ball valve (25 mm dia). Drum shall be fixed on adjoining wall through anchor fasteners / cement concrete block as and when required. (For internal hydrant system). | 99 |  | nos | 72 | 14 | 84 |  |  | 56 | 28
5 | Providing & Fixing of 63 mm dia 15 m long non-percolating flexible hose (RRL- type A) as per IS : 636. Type A with Gunmetal male & female instantaneous type coupling (IS 903) (For internal hydrant system). | 99 |  | Nos | 144 | 28 | 168 |  |  | 140 | 28
6 | Providing & Fixing of standard S.S. 63 mm dia branch pipe with nozzle of 20 mm nominal bore outlet as per IS:903 suitable to fit with standard instantaneous type 63mm dia coupling ISI marked (IS:903) complete. | 137 |  | Nos | 72 | 14 | 84 |  |  | 56 | 28
INTERNAL
F | HAND APPLIANCES
1 | Providing and fixing water based CO2 type extinguishers confirming to IS:15683 consisting of welded M.S. cylinderical body, squeeze lever discharge valve 30 cms long high pressure discharge hose, discharge nozzle, suspension braket, ISI marked as per IS:15683 finished externally with red enamel paint and fixed to wall with brackets complete with internal charges.
a) | Capacity 2 kg.
b) | Capacity 5 kg. | 99 |  |  | 8 | 14 | 36 |  |  | 56 | 28
2 | Providing and fixing stored pressure type mechanical foam based type fire extinguisher confirming to IS:15683 complete with pressure indicating gauge ,cylinder hose, discharge open nozzle, suspension bracket and externallyfinished with red enamel paint and fixedto wall with brackets complete with initial charges.
a) | Capacity 9 litres
3 | Providing & Fixing of burden type Stainless Steel dial type pressure gauge with brass isolation valve and pipe. (For each internal Fire hose cabinet) | 179 |  | nos | [5 empty] | 32 | 18
Dial diameter 100 mm, calibration 0-15 kg
3 | Providing and fixing ABC stored pressure dry chemical powder (mono ammonium phosphate) Fire Extinguisher IS : 13849 latest revision manufacturer and of CRCA sheet in welded construction, finish with epoxy polyster powder coated complete with brass forged ball valve, gun metal cap and nozzle, including initial filled and wall suspension bracket (suitable for fighting in class 'A', B & 'C' that is wood, textile, flammable liquid, electric and gases.
Capacity 2 kg.
| Capacity 5 kg. | 99 |  | nos | 36 | 7 | 84 |  |  | 56 | 28
EXTRA ITEMS
#VALUE! | Providing, laying and jointing light duty non-pressure NP2 class S/S R.C.C. pipes with collars jointing with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including curing, testing of joints etc.
a) | 450 mm dia | 195,11,194 |  | RMT | 77 |  |  | 77 |  | 42
NS | Y Strainer 100mm | Nos | 54300 |  |  |  |  | 6 |  | 6
| Y Strainer 80mm | Nos | 54300 |  |  |  |  | 6 |  | 6
| Y Strainer 65mm | Nos | 54300 |  |  |  |  | 6 |  | 6
NS | SS FCO 200 dia | Nos
| SS FCO 160 dia | Nos | 67 |  |  |  |  | 5 | 5 | 5 | 5
| SS FCO 100 dia | Nos | 67 |  |  |  |  | 12 | 8 | 12 | 8
NS | CP Grating 63 dia |  | 67, 35 |  |  |  |  | 376 | 66 | 376 | 66
NS | CP Grating 160dia |  | 67, 35 |  |  |  |  | 40 | 10 | 40 | 10
Note on H156: Author: 56 claim they give 8 only

## Measurement Of Plumbing BH (hidden)
BOYS HOSTEL Plumbing Measurement RA-10
BOQ No | Bill No | Item Description | Unit | Page No. | Measurement Break Up | Total Qty. | Prev. Bill | This Bill | Cumm. Bill
SOIL, WASTE,VENT & FITTINGS (Plumbing Internal)
VERTICAL PIPE
1, B. 1, (a) | RA-04 | upvc pipe 75 mm dia | RM |  |  | 392.6
1, B. 1, (a) | RA-05 | upvc pipe 75 mm dia | RM |  |  | 196
1, B. 1, (a) | RA-06 | upvc pipe 75 mm dia | RM |  |  | 392.6
1, B. 1, (a) | RA-07 | upvc pipe 75 mm dia | RM |  |  | 145.23
| RA-10 | upvc pipe 75 mm dia | RM |  |  | 438.9
1, B. 1, (a) | Final bill | upvc pipe 75 mm dia | RM |  |  | 731.8 | 1565.33 | 731.8 | 2297.13
1, B. 1, (b) | RA-02 | Upvc pipe 110 MM dia | RM |  |  | 1004.69
1, B. 1, (b) | RA-04 | Upvc pipe 110 MM dia | RM |  |  | 981.04
1, B. 1, (b) | RA-05 | Upvc pipe 110 MM dia | RM |  |  | 1494.75
1, B. 1, (b) | RA-10 | Upvc pipe 110 MM dia | RM |  |  | 607.2
[6 empty] | 232 | 4087.68 | 232 | 4319.68
1. B, (1), (C) | RA-04 | upvc pipe 160 MM dia | RM |  |  | 80 | 80 |  | 80
PIPE AT CEILING
1. B, (1), (C) | RA-10 | Upvc pipe 110 MM dia | RM |  |  | 902.24 | 755 | 0 | 755
1. B, (1), (C) | FINAL | Upvc pipe 110 MM dia |  |  |  | 3277.65 |  | 3487 | 3487
1. B, (2), (C) | RA-05 | upvc pipe 160 MM dia | RM |  |  | 46.98
1. B, (2), (C) | RA-05 | upvc pipe 160 MM dia | RM |  |  | 223.65
1. B, (2), (C) | RA-10 | upvc pipe 160 MM dia | RM |  |  | 83.6
1. B, (2), (C) | Final bill | upvc pipe 160 MM dia | RM |  |  | 362.2 | 354.23 | 362.2 | 716.43
PIPE AT FLOOR
| RA-07 | Upvc pipe 110 MM dia type | RM |  |  | 218.56
| RA-07 | Upvc pipe 110 MM dia type | RM |  |  | 238.9 | 457.46 | 0 | 457.46
2. A | RA-04 | upvc pipe 40MM | RM |  |  | 62.805
2. A | RA-05 | upvc pipe 40MM | RM |  |  | 89.91
2. A | RA-07 | upvc pipe 40MM | RM |  |  | 43.78
| RA-10 | upvc pipe 40MM | RM |  |  | 140.909
2. A | Final bill | upvc pipe 40MM | RM |  |  | 259.975 | 337.4 | 259.979 | 597.379
2. C | RA-04 | upvc pipe 63 MM | RM |  |  | 198
2. C | RA-05 | upvc pipe 63 MM | RM |  |  | 331.2
2. C | RA-07 | upvc pipe 63 MM | RM |  |  | 209.4
| RA-10 | upvc pipe 63 MM | RM |  |  | 514.7
2. C | Final | upvc pipe 63 MM | RM |  |  | 1351.3 | 1253.3 | 1351.3 | 2604.6
3.a | RA-2 BH | Providing and laying cement concrete 1:2:4 mix (1 cement:2 coarse sand: 4 graded stone aggregate 20 mm nominal size) 75 mm in bed and alround uPVC soil & waste pipes including excavation, refilling where required complete in all respect as per standard design. | RM |  |  | 632.74
3.a | RA-04 | PCC and Honching (110 MM ) Dia | RM |  |  | 13.99
3.a | RA-07 | PCC and Honching (110 MM ) Dia | RM |  |  | 16.95
3.a | Final bill | PCC and Honching (110 MM ) Dia | RM |  |  | 100.9 | 663.68 | 100.9 | 764.58
4, (a) | RA-04 | P TRAP | PIC |  |  | 116
4, (a) | RA-02 | P-Trap | NOS |  |  | 72
4, (a) | RA-05 | P-Trap |  |  |  | 188
4, (a) | RA-06 | P-Trap | NOS |  |  | 12
4, (a) | RA-07 | P-Trap | NOS |  |  | 72
4, (a) | RA-10 | P-Trap | NOS |  |  | 192
4, (a) | Final bill | P-Trap | NOS |  |  | 192 | 652 | 192 | 844
B. 5 | RA-05 | HOPPER | Nos |  |  | 54
B. 5 | RA-05 | HOPPER | Nos |  |  | 90
B. 5 | RA-06 | HOPPER | Nos |  |  | 9
B. 5 | RA-07 | HOPPER | Nos |  |  | 36
B. 5 | RA-10 | HOPPER | Nos |  |  | 92
B. 5 | RA-10 | HOPPER | Nos |  |  | 187 | 200 | 268 | 468 |  | 81
B. 6 | RA-02 | Floor Drain | Nos. |  |  | 72
B. 6 | RA-06 | Floor Drain | Nos. |  |  | 1
B. 6 | Final bill | Floor Drain | Nos. |  |  | 48 | 73 | 48 | 121
RAIN WATER PIPES & FITTINGS ( Plumbing Internal)
| RA-10 | Upvc Pipe 110 | RM |  |  | 419.1 |  |  | 0
| Final bill | Upvc Pipe 110 |  |  |  | 831.1 | 419.1 | 831.1 | 1250.2
1. c | RA-02 | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects. | Rm |  |  | 152.725 |  | 0
1. c | RA-06 | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects. | Rm |  |  | 85.08
1. c | RA-07 | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects. | Rm |  |  | 66
1. c | RA-10 | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects. | Rm |  |  | 262
1. c | Final bill | Providing, Fixing & testing of uPVC pipes, conforming to IS 4985 class III (6 kg per sqcm) including injection moulded fittingswith bosses like bents tee's adopters etc. suitable for rubber ring jointing with solvent cement including cutting, fixing to walls /ceiling with supporting clamps etc. all complete in all respects. | Rm |  |  | 654.5 | 565.81 | 654.495 | 1220.305
1.d | RA-05 | upvc pipe 200 MM dia | RM |  |  | 30.1 |  | 0
1.d | RA-06 | upvc pipe 200 MM dia | RM |  |  | 44.65
1.d | RA-10 | upvc pipe 200 MM dia | RM |  |  | 42.4
1.d | Final bill | upvc pipe 200 MM dia | RM |  |  | 146.95 | 117.15 | 146.95 | 264.1
EXTERNAL WATER SUPPLY SYSTEM
1. a | RA-06 | Excavation | RM |  |  | 293.75
1. a | Final bill | Excavation | RM |  |  | 490.5 | 293.75 | 490.5 | 784.25
TOTAL FOR GARDEN HYDRANT SYSTEM (Plumbing External)
Ext. Plumbing | RA-02 | Haunching 160 | RM |  |  | 132.25
C. 3.(B). Plumbing External | RA-04 | PCC and Honching (160 MM ) Dia | RM |  |  | 8.13
C. 3.(B). Plumbing External | RA-05 | PCC and Honching (160 MM ) Dia | RM |  |  | 1.2
C. 3.(B). Plumbing External | RA-06 | PCC and Honching (160 MM ) Dia | RM |  |  | 52.98
C. 3.(B). Plumbing External | Final bill | PCC and Honching (160 MM ) Dia | RM |  |  | 330 | 194.56 | 330 | 524.56
C. 3.(C). Plumbing External | RA-02 | Honching for SN-4 PIPE 200 MM | RM |  |  | 17
C. 3.(C). Plumbing External | RA-04 | Haunching 200 | RM |  |  | 140.638
C. 3.(C). Plumbing External | RA-05 | Haunching 200 | RM |  |  | 120.32
C. 3.(C). Plumbing External | RA-06 | Haunching 200 | RM |  |  | 52.18
C. 3.(C). Plumbing External | RA-07 | Haunching 200 | RM |  |  | 22.1
C. 3.(C). Plumbing External | RA-07 | Haunching 200 | RM |  |  | 184 | 352.24 | 183.998 | 536.238
STORM WATER DRAINAGE SYSTEM ( Plumbing External)
| RA-02 | Honching for 250 MM Dia for Storm water line | RM |  |  | 20
| Final Bill | Honching for 250 MM Dia for Storm water line | RM |  |  | 119.95 | 20 | 119.95 | 139.95
D, 4 (B) | RA-04 | Haunching 300 | RM |  |  | 114.305
D, 4 (B) | RA-05 | Haunching300 mm | RM |  |  | 115.53
D, 4 (B) | RA-06 | Haunching300 mm | RM |  |  | 33.5
D, 4 (B) | Final bill | Haunching300 mm | RM |  |  | 11 | 263.335 | 11 | 274.335
|  | WATER SUPPLY SYSTEM (Plumbing Internal) | [5 empty] | 0
2. (a) | RA-06 | GI 15 MMBH | RM |  |  | 27.9
2. (a) | RA-07 | GI 15 MMBH | RM |  |  | 83.7
2. (a) | RA-10 | GI 15 MMBH | RM |  |  | 8
2. (a) | Final bill | GI 15 MMBH | RM |  |  | 121 | 119.6 | 121 | 240.6
2.(b) | RA-05 | GI 20 MMBH | RM |  |  | 10.5 |  | 0
2.(b) | RA-06 | GI 20 MMBH | RM |  |  | 27.9
2.(b) | RA-7 | GI 20 MMBH | RM |  |  | 83.7
2.(b) | RA-10 | GI 20 MMBH |  |  |  | 13
2.(b) | Final bill | GI 20 MMBH |  |  |  | 263.2 | 135.1 | 263.2 | 398.3
2.(c) | RA-07 | GI 25 MMBH | RM |  |  | 110.7
2.(c) | RA-07 | GI 25 MMBH | RM |  |  | 334.8
2.(c) | RA-10 | GI 25 MMBH | RM |  |  | 19.9
2.(c) | Final bill | GI 25 MMBH | RM |  |  | 1156.45 | 465.4 | 1156.45 | 1621.85
2.(d) | RA-06 | GI 32 MMBH |  |  |  | 55.8
2.(d) | RA-07 | GI 32 MMBH |  |  |  | 163.8
2.(d) | Final bill | GI 32 MMBH |  |  |  | 731.6 | 219.6 | 731.6 | 951.2
2.(e) | RA-04 | GI 40 MMBH | RM |  |  | 13.3
2.(e) | RA-05 | GI 40 MMBH | RM |  |  | 27.6
2.(e) | RA-06 | GI 40 MMBH | RM |  |  | 77.98
2.(e) | RA-07 | GI 40 MMBH |  |  |  | 196.8
2.(e) | Final bill | GI 40 MMBH |  |  |  | 649.2 | 315.68 | 649.2 | 964.88
2.(f) | RA-05 | GI 50 mm BH | RM |  |  | 27.6 |  | 0
2.(f) | RA-06 | GI 50 mm BH | RM |  |  | 22.24
2.(f) | RA-07 | GI 50 mm BH | RM |  |  | 33
2.(f) | Final bill | GI 50 mm BH | RM |  |  | 781.3 | 82.84 | 781.3 | 864.14
| Final bill | GI 80 mm BH | RM |  |  | 147.2 |  | 147.2 | 147.2
EXTERNAL FIRE HYDRANT SYSTEM (Plumbing External)
E. 3 (B) | RA-05 | Wraping and coating(80 mm and 100 mm M.S. Pipe) | RM |  |  | 58.8 | 58.8 | 0 | 58.8
STORM WATER DRAINAGE SYSTEM
D. 3 (a) | RA-02 | RCC pipe (hume pipe) -250 MM Dia | RM |  |  | 36 |  | 0
D. 3 (a) | RA-05 | RCC 250 | RM |  |  | 111
Final Bill | RA-05 | RCC 250 | RM |  |  | 119.95 | 155.95 | 111 | 266.95
D. 3 (b) | RA-02 | Rcc PIPE 300 | RM |  |  | 114.305 |  | 0
D. 3 (b) | RA-05 | Rcc PIPE 300 | RM |  |  | 115.53 |  | 0
D. 3 (b) | RA-06 | Rcc PIPE 300 | RM |  |  | 33.5
D. 3 (b) | Final bill | Rcc PIPE 300 | RM |  |  | 11 | 263.335 | 11 | 274.335 | 8.33
D. 5 | RA-04 | 450*450Chamber | Nos. |  |  | 5 |  | 0
D. 5 | RA-06 | 450*450Chamber | Nos. |  |  | 4
D. 5 | Final bill | 450*450Chamber | Nos. |  |  | 55 | 9 | 55 | 64
0
D. 8, (a) | RA-04 | MANHOLE STorm Work |  |  |  | 21 |  | 0
D. 8, (a) | RA-05 | MANHOLE STorm Work | Nos. |  |  | 6 |  | 0
D. 8, (a) | RA-06 | MANHOLE STorm Work | Nos. |  |  | 2
D. 8, (a) | Final bill | MANHOLE STorm Work | Nos. |  |  | 20 | 29 | 20 | 49
EXTERNAL SEWERAGE SYSTEM Plumbing External
C.2. © | RA-02 | SN4 200mm. | RM |  |  | 17
C.2. © | RA-05 | UPVC SN-4 PIPE 200dia | RM |  |  | 138.62
C.2. © | RA-05 | UPVC SN-4 PIPE 200dia | RM |  |  | 205.42
C.2. © | RA-06 | UPVC SN-4 PIPE 200dia | RM |  |  | 52.18
C.2. © | Final bill | UPVC SN-4 PIPE 200dia | RM |  |  | 245.55 | 413.22 | 245.55 | 658.77
C. 4 (A) | RA-05 | GT | Nos. |  |  | 5
C. 4 (A) | RA-06 | GT | Nos. |  |  | 5
C. 4 (A) | Final bill | GT | Nos. |  |  | 30 | 10 | 30 | 40
C. 5 | RA-06 | CHAMBER ( 90x80cms) | Nos. |  |  | 2
C. 5 |  | Rectangular manhole ( 90x80cms) |  |  |  | 3
C. 5 | Final bill | Rectangular manhole ( 90x80cms) |  |  |  | 3 | 5 | 3 | 8
C.6.(A) | RA-04 | MANHOLE Sewer Work | Nos. |  |  | 23
C.6.(A) | RA-05 | MANHOLE Sewer | Nos. |  |  | 12
C.6.(A) | RA-06 | MANHOLE Sewer Work | Nos. |  |  | 8
C.6.(A) | RA-06 | MANHOLE Sewer Work | Nos. |  |  | 7
C.6.(A) | Final bill | MANHOLE Sewer Work | Nos. |  |  | 27 | 50 | 27 | 77
N.S.I | RA-05 | MANHOLE 1200*1200 | Nos. |  |  | 9 | 9 | 0 | 9
N.S.I | RA-05 | Haunching 450 mm | RM |  |  | 30.6 | 30.6 | 0 | 30.6
N.S.I | RA-05 | Rcc PIPE 450 | RM |  |  | 30.6 | 30.6 | 0 | 30.6
N.S.I | RA-05 | Excavation 450 | RM |  |  | 30.6 | 30.6 | 0 | 30.6
| Final bill | Chamber 1200 x 1200 x 1500 mm internal dimensions |  |  |  | 3 |  | 3 | 3
| Final bill | Main connnection to sever |  |  |  | 3 |  | 3 | 3
FIRE HYDRANT SYSTEM
7. © | RA-05 | MS PIPE 100MM | RM |  |  | 82.95
7. © | Final bill | MS PIPE 100MM | RM |  |  | 482.9 | 482.9 | 82.95 | 565.85
| Final bill | MS Pipe 150 mm | RM |  |  | 23.8 |  | 23.8 | 23.8
8. (a) | RA-05 | MS PIPE 80MM | RM |  |  | 81.87
8. (a) | RA-06 | MS PIPE 80MM | RM |  |  | 5.6
8. (a) | RA-06 | MS PIPE 80MM | RM |  |  | 232.1 | 87.47 | 232.1 | 319.57
WATER SUPPLY SYSTEM (Plumbing Internal)
D. 1 (a) | RA-02 | CPVC pipe(15 mm dia) | RM |  |  | 322.04
D. 1 (a) | RA-04 | CPVC pipe(15 mm dia) |  |  |  | 1448.48
D. 1 (a) | RA-05 | CPVC pipe(15 mm dia) | RM |  |  | 1294.76
D. 1 (a) | RA-07 | CPVC pipe(15 mm dia) | RM |  |  | 1318.49
D. 1 (a) | RA-10 | CPVC pipe(15 mm dia) | RM |  |  | 1334.12
D. 1 (a) | FinaL bill | CPVC pipe(15 mm dia) | RM |  |  | 3829.28 | 5717.89 | 3829.28 | 9547.17
D. 1 (b) | RA-02 | CPVC pipe(20 mm dia) | RM |  |  | 36.72
D. 1 (b) | RA-4 | CPVC pipe(20 mm dia) |  |  |  | 165.24
D. 1 (b) | RA-05 | CPVC pipe(20 mm dia) |  |  |  | 144.78
D. 1 (b) | RA-07 | CPVC pipe(20 mm dia) | RM |  |  | 357.07
D. 1 (b) | RA-10 | CPVC pipe(20 mm dia) | RM |  |  | 356.36
D. 1 (b) | Final bill | CPVC pipe(20 mm dia) | RM |  |  | 570.98 | 1060.17 | 570.98 | 1631.15
D. 1. © | RA-02 | CPVC pipe(25 mm dia) | RM |  |  | 31.28
D. 1. © | RA-04 | CPVC pipe(25 mm dia) |  |  |  | 140.4
D. 1. © | RA-05 | CPVC pipe(25 mm dia) | RM |  |  | 124.8
D. 1. © | RA-07 | CPVC pipe(25 mm dia) | RM |  |  | 131.4
D. 1. © | RA-10 | CPVC pipe(25 mm dia) | RM |  |  | 135.5
D. 1. © | Final bill | CPVC pipe(25 mm dia) | RM |  |  | 1441.48 | 563.38 | 1441.48 | 2004.86
| RA-02 | Honching for SN-4 PIPE 200 MM | RM |  |  | 17 | 17 | 0 | 17
External Sewerage System Plumbing External
| RA-02 | Excavation |  |  |  | 64
| RA-06 | Excavation 110 Sewer | RM |  |  | 21.05
| RA-06 | Excavation 200 Sewer | RM |  |  | 80.2
| RA-07 |  | RM |  |  | 92.95
| RA-07 | Excavation 80 mm to 300 | RM |  |  | 343.35
| RA-7 | Excavation 80 mm to 300 | RM |  |  | 106.95
| Final bill | Excavation 80 mm to 300 | RM |  |  | 1000.75 | 708.5 | 1000.75 | 1709.25
TOTAL FOR EXTERNAL Strom SYSTEM ( Plumbing External) | [8 empty] | 0
D.1. | RA-06 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 1.9
D.1. | RA-06 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 14.1
D.1. | RA-06 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 23.3
D.1. | RA-06 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 149.03
D.1. | RA-07 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 18.38
| RA-07 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 34
| RA-07 | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 132.84
| Final bill | Pipes, exceeding 80 mm dia but not exceeding 300 mm dia depth as required . | RM |  |  | 915.905 | 373.55 | 915.905 | 1289.455
Note on G63: Author: previous 81 pending
Note on G117: Author: BH-01, BH-02, BH-03 Shafts measurements are not signed.
Note on G122: Author: BH-01, BH-02, BH-03 Shafts measurements are not signed.
Note on G127: Author: BH-01, BH-02, BH-03 Shafts measurements are not signed.
Note on G133: Author: BH-01, BH-02, BH-03 Shafts measurements are not signed.

## Measurement of Plumbing GH (hidden)
MEASUREMENT SUMMARY RA-10
GIRLS HOSTEL PLUMBING
BOQ No | Bill No | Item Description | Unit | Page No. | Measurement Break Up | Total Qty. | Prev. | This Bill | Cumm.
Soil, waste, Vent fitting Plumbing Internal GH
Pipe at Floor
| RA-09 | 75 MM OD Pipe |  |  |  | 601.4
| Final bill | 75 MM OD Pipe |  |  |  | 307.1 | 601.4 | 307.1 | 908.5
B.1.1. (a) | RA-03 | Upvc pipe 110 MM dia type G:H | RM |  |  | 154.12
B.1.1. (a) | RA-04 | Upvc pipe 110 MM dia type G:H | RM |  |  | 724.02
B.1.1. (a) | RA-09 | Upvc pipe 110 MM dia type G:H |  |  |  | 633.6
B.1.1. (a) | RA-10 | Upvc pipe 110 MM dia type G:H | RM |  |  | 77 | 1588.74 |  | 1588.74
Pipe At Ceiling
|  | Upvc pipe 110 MM dia type G:H |  |  |  |  | 1013.31 | 0 | 1013.31
B.1.1.(b) | RA-05 | upvc pipe 160 MM | RM |  |  |  | 423.53 |  | 423.53
B.11.(C) | RA-04 | upvc pipe 160 MM Vertical pipe | RM |  |  | 109.77 | 70 | 0 | 70
B.2.(a) | RA-09 | upvc pipe 40 MM | RM |  |  | 377.2 |  |  | 320 | 57 previous
| Final bill | upvc pipe 40 MM | RM |  |  | 231.92 | 320 | 288.92 | 608.92
| RA-09 | upvc pipe 50 MM | RM |  |  | 244
| Final bill | upvc pipe 50 MM | RM |  |  | 277.86 | 244 | 277.86 | 521.86
B.3.(a) | RA-04 | Haunching 110 GH |  |  |  | 20.82
B.3.(a) | RA-05 | Haunching |  |  |  | 60.35
| Final bill | Haunching |  |  |  | 128.28 | 81.17 | 128.28 | 209.45
| RA 9 | 63 mm Pipe | RM. |  |  | 783.05
| Final | 63 mm Pipe | RM. |  |  | 195.96 | 783.05 | 195.96 | 979.01
| RA 9 | 160 MM Pipe | RM. |  |  | 193 |  |  | 0
| Final bill | 160 MM Pipe | RM. |  |  | 325.18 | 193 | 325.18 | 518.18
| RA-09 | P TRAP | Nos. |  |  | 210
B.4.(a) | Final bill | P TRAP | Nos. |  |  | 118 | 210 | 118 | 328
| RA-05 | HOPPER | Nos. |  |  | 40
B.(5) | RA-05 | HOPPER | Nos. |  |  | 48 | 200 | 48 | 248
B.(6) | RA-05 | Floor Drain | Nos. |  |  | 0 | 0 | 0 | 0
RAIN WATER PIPES & FITTINGS
C.1 (d) | RA-04 | Upvc pipe 200 mm 6kg, GH | RM |  |  | 29.61
C.1 (d) | RA-05 | upvc pipe 200 MM | RM |  |  | 121.35
C.1 (d) | RA-10 | upvc pipe 200 MM | RM |  |  | 16.5
| RA-10 | upvc pipe 200 MM | RM |  |  | 68.45 | 167.46 | 68.45 | 235.91
WATER SUPPLY SYSTEM
D.2(a) | Finalbill | GI 15 mm GH | RM |  |  | 218.9 |  | 218.9 | 218.9
D2.(B) | Finalbill | GI 20 mm GH | RM |  |  | 285.5 |  | 285.5 | 285.5
D.2(C) | Finalbill | GI 25 mm GH | RM |  |  | 525.99 |  | 525.99 | 525.99
D.2(d) | RA-04 | GI 32 mm GH | RM |  |  | 21.8
D.2(d) | Finalbill | GI 32 mm GH | RM |  |  | 641.8 | 21.8 | 641.8 | 663.6
D..2(e) | RA-04 | GI 40 mm GH | RM |  |  | 22
D..2(e) | RA-04 | GI 40 mm GH | RM |  |  | 671.2 | 22 | 671.2 | 693.2
D2F | Finalbill | 50 mm nominal bore | RM |  |  | 265.1 |  | 47.8 | 265.1
| Finalbill | 65 mm nominal bore | RM |  |  | 138.7 |  | 138.7 | 138.7
12
| Finalbill | 80 mm nominal bore | RM |  |  | 45.1 | 12 | 45.1 | 57.1
D.2.(h) | Final bill | 80 mm M.S pipe GH | RM |  |  | 150 |  | 150 | 150
| Final bill | 100mm MS Pipe | RM |  |  | 103.6 |  | 103.6 | 103.6
External stewerge system
|  | 200 mm OD U-Drain Pipe (SN4) | RM |  |  | 35.21
| Final bill | 200 mm OD U-Drain Pipe (SN4) | RM |  |  | 173 | 35.21 | 173 | 208.21
EXTERNAL WATER SUPPLY SYSTEM (Plumbing External )
|  | Grand Total of above Excavation item of 80mm dia to 300 mm dia |  |  |  | 97.76
|  | Excavation |  |  |  | 69.15
A.1. (A) | Final bill | Excavation |  |  |  | 23 | 120.76 | 69.15 | 189.91
EXTERNAL SEWERAGE SYSTEM (Plumbing External)
C.3.B.(C) | RA-04 | Haunching 160 GH |  |  |  | 37.72
| Final bill | Haunching 160 GH |  |  |  | 114 | 37.72 | 114 | 151.72
C.3.B.(d) | RA-010 | Haunching 200 GH |  |  |  | 8.6
| Final bill | Haunching 200 GH |  |  |  | 192 | 43.81 | 192 | 235.81
E |  | EXTERNAL FIRE HYDRANT SYSTEM
3.(A) | RA-04 | Wraping And Coating GH | RM |  |  | 10.3 | 10.3 | 0 | 10.3
STORM WATER DRAINAGE SYSTEM (External)
3.(A) | RA-04 | 250 Rcc hume pipe GH | RM |  |  | 147.63
| Final bill | 250 Rcc hume pipe GH | RM |  |  | 91.1 | 147.63 | 91.1 | 238.73
STORM WATER DRAINAGE
|  | Excavation 80mm to 300 mm |  |  |  | 121.33 | 121.33 |  | 121.33
EXTERNAL WATER SUPPLY SYSTEM
|  | GI 32 mm GH | RM |  |  |  | 26.2 |  | 26.2
|  | GI 40 mm GH | RM |  |  | 26.2
|  | GI 40 mm GH | RM |  |  | 104.2 | 26.2 | 104.2 | 130.4
|  | EXTERNAL SEWERAGE SYSTEM | [6 empty] | 0
| a) | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm dia and depth as required . |  |  |  | 35.21 |  |  | 0
| a) | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm dia and depth as required . |  |  |  | 589.1 | 35.21 | 589.1 | 624.31
| final bill | Gully trap | Nos |  |  | 21 |  | 21 | 21
|  | EXTERNAL SEWERAGE SYSTEM | [6 empty] | 0
|  | Manhole 900 mm |  |  |  | 4
|  | Manhole 900 mm |  |  |  | 15 | 4 | 15 | 19
STORM WATER DRAINAGE
|  | Manhole 900 mm |  |  |  | 7
[6 empty] | 7 | 7 | 7 | 14
|  | STORM WATER DRAINAGE | [6 empty] | 0
| Final bill | Pipes, cables etc. exceeding 80 mm dia but not exceeding 300mm dia and depth as required . |  |  |  | 91.1 | 121.33 | 91.1 | 212.43
|  | STORM WATER DRAINAGE | [6 empty] | 0
|  | Haunching |  |  |  | 121.33
| Final bill | Haunching |  |  |  | 91.1 | 121.33 | 91.1 | 212.43
|  | Chamber 45*45*50 | Nos |  |  | 18 |  | 18 | 18
1 |  | CPVC Pipes | [6 empty] | 0
a) |  | 15 mm nominal bore | RMT
a) | Final bill | 15 mm nominal bore | RMT |  |  | 932.04 | 2752.32 | 932.04 | 3684.36
b) |  | 20 mm nominal bore | RMT
b) | Final bill | 20 mm nominal bore | RMT |  |  | 52.8 | 485.09 | 52.8 | 537.89
c) |  | 25 mm nominal bore | RMT
c) | Final bill | 25 mm nominal bore | RMT |  |  | 857.15 | 211.9 | 857.15 | 1069.05

## Summary Electrical (hidden)
SUMMARY
Sub Head | Description |  | Supply Amount |  |  | ITC Amount
|  |  | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT
I | WIRING | Rs. | #REF! | #REF! | #REF! |  | #REF!
II | COMMUNICATION | Rs
III | SUBMAINS AND CABLES | Rs
IV | DISTRIBUTION SYSTEM | Rs
V | MV DISTRIBUTION SWBD | Rs
VI | RISING MAINS | Rs
VII | EARTHING | Rs
VIII | FIRE DETECTION AND ALARM SYSTEM | Rs
IX | LIGHTNING PROTECTION | Rs
X | FIXTURES AND FITTINGS | Rs
| GRAND TOTAL |  | #REF! | #REF! | #REF! |  | #REF!
VAT @ 15.95%
Service Tax @ 15%
Labour Cess @ 1%
GRAND TOTAL WITH TAX
Now Payble Amount
|  | Round off | #REF! | #REF! | #REF!
Zamil Airconditioners Pvt. Ltd.
Authorized Signatory

## SUMMARY OF HVAC (hidden)
SUMMARY OF HVAC
BOYS HOSTEL & GIRLS HOSTEL
| BOYS HOSTEL |  | Supply Amount |  |  | ITC Amount
S.NO. | DESCRIPTION
|  |  | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMMULATIVE AMOUNT
I) | Air Cooled VRV Equipment | Rs. | 47594692.6 | 0 | 47594692.6
II) | Air Distribution System | Rs.
III) | Electrical Works | Rs.
| TOTAL |  | 47594692.6 | 0 | 47594692.6
GIRLS HOSTEL
I) | Equipment | Rs. | 0 | 0
II) | Air Distribution System | Rs. | 0 | 0
III) | Electrical Works | Rs. | 0 | 0
| TOTAL |  | 0 | 0
| GRAND TOTAL = | Rs. | 47594692.6 | 0
| VAT @15.95% on Supply |  | 7591353.4697 | 0 | 759135346.97
Service Tax @15% on ITC
| Labour cess @1% of the C.V |  | 551860.4607 | 0 | 8067300.3957
| TOTAL WITH TAX |  | 55737906.5304 | 0 | 814797339.9657 |  |  | 0