## RA07F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 07 (Final Payment Against PBG) |  |  |  | Bill No.7 | FINAL BILL
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-11-17
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-11-08
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid (Part Of Payment) |  | 430399.6
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-11-04 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 4303996
Amount Recommended : |  |  | 860799
Service Tax No. :
TIN NO |  |  | 06141923485
PAN of Contractor : |  |  | AACCG1058K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 10% Contract price against ABG |  |  | 430400 | 0 | 430400
A2 | 70% against supply of material |  |  | 3012796.8 | 0 | 3012796.8
A3 | 20 % Of After installation Against PBG |  |  |  | 860799 | 860799
| Sub Total - (A) |  |  | 3443196.8 | 860799 | 4303995.8
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 3443196.8 | 860799 | 4303995.8
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 3443196.8 | 860799 | 4303995.8
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers International (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA06F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 06 (FURNITURE SUPPLY) |  |  |  | Bill No. | MS-06
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-08-05
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-04
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid (Part Of Payment) |  | 430399.6
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-28 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 1271384
Amount Recommended : |  |  | 889968.8
Service Tax No. :
TIN NO |  |  | 06141923485
PAN of Contractor : |  |  | AACCG1058K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 10% Contract price against ABG |  |  | 430400 | 0 | 430400
A2 | 70% against supply of material(Rs .1271384@70%.) INVOICE NO.1157 |  |  | 2122828 | 889968.8 | 3012796.8
A3 | 10% After installation
| Sub Total - (A) |  |  | 2553228 | 889968.8 | 3443196.8
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 2553228 | 889968.8 | 3443196.8
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 2553228 | 889968.8 | 3443196.8
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA05F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 05 (FURNITURE SUPPLY) |  |  |  | Bill No. | MS-05
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-08-04
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-02
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid (Part Of Payment) |  | 430399.6
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-25 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 546478
Amount Recommended : |  |  | 546478
Service Tax No. :
TIN NO |  |  | 06141923485
PAN of Contractor : |  |  | AACCG1058K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work (INVOICE NO:- GKN/2016-17/4355 |  |  | 2486134 | 546478 | 3032612
A2 | Scheduled Work Done
| Sub Total - (A) |  |  | 2486134 | 546478 | 3032612
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 2486134 | 546478 | 3032612
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 2486134 | 546478 | 3032612
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA04F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 04 (FURNITURE SUPPLY) |  |  |  | Bill No. | MS-04
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-23
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-22
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid (Part Of Payment) |  | 430399.6
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-20 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 822136
Amount Recommended : |  |  | 822136
Service Tax No. :
TIN NO |  |  | 06141923485
PAN of Contractor : |  |  | AACCG1058K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work (INVOICE NO:- GKN/2016-17/3951 |  |  | 1663998 | 822136 | 2486134
A2 | Scheduled Work Done
| Sub Total - (A) |  |  | 1663998 | 822136 | 2486134
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 1663998 | 822136 | 2486134
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 1663998 | 822136 | 2486134
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA03F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (FURNITURE SUPPLY) |  |  |  | Bill No.3 | MS-03
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-13
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-12
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid (Part Of Payment) |  | 430399.6
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-07 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 910458
Amount Recommended : |  |  | 910458
Service Tax No. :
TIN NO |  |  | 06141923485
PAN of Contractor : |  |  | AACCG1058K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work (INVOICE NO:- GKN/2016-17/3247 |  |  | 753540 | 910458 | 1663998
A2 | Scheduled Work Done
| Sub Total - (A) |  |  | 753540 | 910458 | 1663998
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 753540 | 910458 | 1663998
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  | 753540 | 910458 | 1663998
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 (FURNITURE SUPPLY) |  |  |  | Bill No.2 | MS-02
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-09
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-07-09
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-07-06 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 753540
Amount Recommended : |  |  | 753540
Service Tax No. :
TIN NO |  |  | 06141923485
PAN of Contractor : |  |  | AACCG1058K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work (INVOICE NO:- GKN/2016-17/3145 |  |  |  | 753540
A2 | Scheduled Work Done
| Sub Total - (A) |  |  |  | 753540 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 753540 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 753540
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA01F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 (Advance against Bank Guarantee) |  |  |  | Bill No.1 | ABG-01
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-07-04
Contractor : | M/S Geeken Seating Collection Pvt. Ltd. |  |  | Date of 70% Certificate
Service : | SUPPLY DINING TABLE & OTHER FURNITURE |  |  | Submission by Contractor |  | 2016-07-04
|  |  |  | Received by Vincom |  | 2016-07-04
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date :- TU/CS/PSJ/16-17/150054 |  |  | 2016-05-31 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 4303996 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-06-27 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 430399.6
Amount Recommended : |  |  | 430399.6
Service Tax No. :
TIN NO
PAN of Contractor :
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work Done |  |  |  | 430399.6
A2 | Scheduled Work Done
| Sub Total - (A) |  |  |  | 430399.6 | 0
B | Add Taxes
B1 | Service Tax @ 5.8% on (A) |  |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 430399.6 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance Payable 20% of Rs. 15000000
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
Sub Total - (C)
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  |  | 0 | 0
| Total - (A+B+C-D) |  |  |  | 430399.6
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02_70% (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 |  |  |  | Bill No. | RA-002
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-05-17
Contractor : | D. K. Buildcon Pvt. Ltd. |  |  | Date of Adhoc Certificate |  | 2016-05-17
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 2016-05-12
|  |  |  | Received by Vincom |  | 2016-05-12
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CS/PSJ/15-16/150019A | 03.02.2016 | Work Done Up to
Date of Agreement : |  |  | 03.03.2016
Completion Date :
Contract Value : |  |  | 58347484 | Mobilisation Paid |  | 5834750
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-05-01
Invoice Amount : |  |  | 3708968 | Material Advance Paid |  | 954858
Amount Recommended : |  |  | 1830159 | Material Advance Recovered
Service Tax No. : |  |  | AACCD6742P ST001
TIN No. |  |  | 6841325968
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  | 3250165 | 3702261 | 6952426
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  | 3250165 | 3702261 | 6952426
B | Add Taxes
B1 | Service Tax 14.50 % of 40% of (A)
B2 | W.C.T. i.e. VAT on Contracts 5.8% on (A) - Included in above |  |  |  | 214731.13
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 3916992.13
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Recover@ 5% of Rs. 6952426 Recovery @ |  |  |  | -347621.3
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Recovery Advance against Material at Site @ 80% of Value (Ref. S.A-01 ) |  |  |  | -954858
| Sub Total - (C) |  |  |  | -1302479.3
| Total - (A+B+C) |  |  |  | 2614512.83
| Allow an adhoc payment 70% against 2nd ra bill |  |  |  | 1830159
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A) |  |  |  | 0
D2 | W.C.T. @ 6% on (A) |  |  |  | 0
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  |  | 0
D4 | Labour Cess @ 1% on (A) |  |  |  | 0
| Sub Total - (D) |  |  |  | 0
| Net Amount Payable (A+B+C-D) |  |  |  | 1830159 | 0
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil singla |  | Vinay kumar | R.K.Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments

## RA01_F (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (70% Of Billed payment) |  |  |  | Bill No. | RA-003
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-06-05
Contractor : | D. K. Buildcon Pvt. Ltd. |  |  | Date of Adhoc Certificate |  | 2016-06-05
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 2016-06-02
Received by Vincom
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CS/PSJ/15-16/150019A | 03.02.2016 | Work Done Up to
Date of Agreement :
Completion Date :
Contract Value : |  |  | 58347484 | Mobilisation Paid |  | 5834750
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-06-01
Invoice Amount : |  |  | 4304809 | Material Advance Paid
Amount Recommended : |  |  | 1772396 | Material Advance Recovered
Service Tax No. : |  |  | AACCD6742P ST001
TIN No. |  |  | 6841325968
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  | 6697341 | -3447176 | 3250165
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate |  |  | 65704 | 0 | 65704
| Sub Total - (A) |  |  | 6763045 | -3447176 | 3315869
B | Add Taxes
B1 | Service Tax 5.8% of (A) |  |  | 392257 | -199937 | 192320
B2 | W.C.T. i.e. VAT on Contracts 5.25% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 7155302 | -3647113 | 3508189
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Payable 5% of Rs. 5,83,47,484 Recovery @ |  |  | 794954 | 5039796 | 5834750
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Advance against Material at Site @ 80% of Value |  |  |  | 954858 | 954858
| Sub Total - (C) |  |  | 794954 | 5994654 | 6789608
| Total - (A+B+C) |  |  | 7950256 | 2347541 | 10297797
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A) |  |  |  | 165793 | 165793
D2 | W.C.T. @ 5.25% on (A) |  |  |  | 174083 | 174083
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  |  | 202110 | 202110
D4 | Labour Cess @ 1% on (A) |  |  |  | 33159 | 33159
| Sub Total - (D) |  |  | 0 | 575145 | 575145
| Net Amount Payable (A+B+C-D) |  |  |  | 1772396 | 9722652
Recommended by
Vincom Cost Management Pvt. Ltd.
Sanjeev Kumar |  | Mukesh Gupta | Vinod Markanda
Approved by
Thapar University Patiala
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments