## FINAL
HITECH ERECTORS PVT. LTD.
Regd.Office:303, Pragati Chambers, Ranjit Nagar, Commercial Complex, New Delhi - 110 008
Phones: 25702463, 25706974 Fax:(91) 11-25709321 Email: hitecherectors@vsnl.net
Name of Work :- ELECTRICAL HIGH SIDE WORK OF ENHANCEMENT OF SUB STATION NO.-3, AT THAPAR UNIVERSITY, PATIALA
Location :- PATIALA , Punjab
Client :- Thapar University , Pataial
Consultant :- Colliers
L.O.I NO. :- TU/CS/PSJ/16-17/160009 DT. 02.05.2016
Date of start : MAY 2, 2016
Date of completion : Contd.
TIN NO.:03581109705 | [11 empty] | FINAL REVISED BILL
Service Tax Code (Registration Number) : AAACH0859BSD001 | [11 empty] | 16/09/2016 (18/11/2016)
PAN NO.:AAACH0859B
S.No. | DESCRIPTION | UNIT | UNIT RATES TENDER /APPROVED |  | QTY AS PER BOQ | QUANTITIES UP TO DATE |  | AMOUNT UP TO DATE |  | AMOUNT SINCE PREV. BILL |  | AMOUNT IN THIS BILL
|  |  | SUPPLY | ERECTION |  | SUPPLY | ERECTION | SUPPLY | ERECTION | SUPPLY | ERECTION | SUPPLY | ERECTION
SUB-HEAD-I 11 KV HT CABLE
1 | Supply, receiving, laying, testing & commissioning of 11 KV XLPE AI.conductor armoured (earthed) cable as in existing Hume pipe / cable tray/trench etc. as required at site of work.
a) | 3 core 300 sqmm 11000 Volts XLPE Cable | R Mtr | 1236 | 46 | 500 | 500 | 500 | 618000 | 23000 | 556200 | 20700 | 61800 | 2300
b) | 3 core 120 sqmm 11000 Volts XLPE Cable | R Mtr | 845 | 36 | 500 | 601 | 601 | 507845 | 21636 | 457061 | 19472 | 50784 | 2164
2 | Supply, installation and Cable termination for following 11000 volt grade aluminium conductor armoured XLPE cable including tinned copper lugs all accessories and material required to make a complete joint. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
a) | 3 core 300 sqmm | Set | 3502 | 558 | 2 | 2 | 2 | 7004 | 1116 | 6303 | 1004 | 701 | 112
b) | Straight through Joint for 3 Core 300 sqmm XLPE | Set | 5768 | 1117 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c) | 3 core 120 sqmm (Outdoor) | Set | 2884 | 558 | 6 | 8 | 8 | 23072 | 4464 | 15573 | 3013 | 7499 | 1451
d) | Straight through Joint for 3 Core 120 sqmm XLPE | Set | 4635 | 1117 | 2 | 3 | 3 | 13905 | 3351 | 4172 | 1005 | 9733 | 2346
[8 empty] | 0 | 0 |  | 0 | 0 | 0
1 | 11 KV HT SYSTEM | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Installation, Testing, Commissioning , loading & unloading up to the foundation of the following 11 KV. 3 phase, 630amp, 50Hz & 350 MVA HT panel (SF6) complete as required. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 11KV, 1 Panel board as described above | Nos |  | 9438 | 1 |  | 1 | 0 | 9438 |  | 8494 | 0 | 944
2 | OIL TYPE TRANSFORMERS | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Installation of 11/0.433KV Oil Type Transformers | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Installation, Testing, Commissioning , loading & unloading of following 11000/433 volts delta/star, vector group DYn11, Outdoor mounting, oil naturally cooled (ONAN) transformer as per instruction of Engineer-in-charge etc.complete as required. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 1250 KVA (The transformer shall be provided with cable box suitable to terminate 11 KV (E) 1R x 3C x 120 sq.mm. XLPE cable on HT side and 1.1 KV 5R x 3.5C x 300 sq.mm cable on LT side.) | Nos |  | 11162 | 1 |  | 1 | 0 | 11162 | 0 | 10046 | 0 | 1116
| DISTRIBUTION PANELS | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Design, fabrication, assembly, wiring, supply and coordination with contractor for installation of the following extensible cubicle type indoor/Outdoor mounting Powder coated, modular compartmentalized IP 42, dead front, dust and vermin proof, floor mounting 2 mm thick sheet steel clad switchboard suitable for use at 415 volts 3 phase 4 wire 50 cycle system and to withstand a symmetrical fault level as indicated in the Panel Annexure. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
A | LT PANEL | Set | 685446 | 11162 | 1 | 1 | 1 | 685446 | 11162 | 616901 | 10046 | 68545 | 1116
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
B | Main Emergency Panel | Set | 265733 | 8321 | 1 | 1 | 1 | 265733 | 8321 | 239160 | 7489 | 26573 | 832
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
C | Capacitor Panel (400 KVAR) | Set | 1009887 | 11162 | 1 | 1 | 1 | 1009887 | 11162 | 908898 | 10046 | 100989 | 1116
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
4 | Supply and laying control cabling with copper conductor PVC insulated and PVC sheathed armoured cables on existing tray including the cost of making connections, complete as required as below: | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
b) | 2 core 2.5 sq mm | R Mtr | 72 | 15 | 200 | 100 | 100 | 7200 | 1500 | 6480 | 0 | 720 | 1500
5 | Supplying, fixing, 22.5 kg CO2 Fire extinguishers with trolley, first filling etc. | Nos | 15965 | 274 | 6 | 6 | 6 | 95790 | 1644 | 86211 | 1480 | 9579 | 164
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
6 | Supplying and fixing of nominal 2.5 mm +/-10% thick insulated synthetic Mat conforming to IS 15652 : 2006 and meeting the requirements of IS 5216 (part 1,2 &3), IS 8437, IEC-479 Pub-1, alongwith suitable adhesive/chemibound, Pu resin, waterproofing compound and sealing material as per in service recommendation of Annexure ‘A’ ‘ Clause C’ of IS :15652 and suitable for class- B upto 11kV | Nos | 1854 | 55 | 50 | 50 | 50 | 92700 | 2750 | 83430 | 2475 | 9270 | 275
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
7 | Supplying and fixing standard shock treatment charts in English & Hindi mounted on wooden frame with glass. | Nos | 1339 | 55 | 4 | 4 | 4 | 5356 | 220 | 4820 | 198 | 536 | 22
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
8 | Supplying and fixing of danger plate of size 250 x 200 mm as per approved sample written in English & Hindi for MV and HV made of 2 mm thick sheet | Nos | 227 | 55 | 4 | 4 | 4 | 908 | 220 | 817 | 198 | 91 | 22
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | Supplying First Aid Box Complete as approved . | Nos | 1751 | 55 | 2 | 2 | 2 | 3502 | 110 | 3152 | 99 | 350 | 11
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
10 | Supplying and fixing fire buckets each painted red with fire written out complete with sand filling, floor/wall mounting brackets complete. | Nos | 227 | 162 | 10 | 10 | 10 | 2270 | 1620 | 2043 | 1458 | 227 | 162
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
11 | Supplying rubber gloves and tool kit as required | 2 | 1236 |  | 2 | 2 | 2 | 2472 | 0 | 2225 | 0 | 247 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| SUB HEAD III - DISTRIBUTION CABLES | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
1 | Supplying and laying in existing Hume Pipe/concrete trench clamped to wall with suitable clamps saddles and fixing bolts/ Directly buried in ground in horizontal / vertical tier formation as per site requirement as required and including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and sheathed aluminium conductor cable complete as required. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
a | 3 -1/2 core 300 Sq mm XLPE | R Mtr | 947 | 55 | 500 | 509 | 509 | 482023 | 27995 | 433820 | 25196 | 48203 | 2799
b | 3 -1/2 core 240 Sq mm XLPE | R Mtr | 773 | 50 | 1200 | 1276 | 1276 | 986348 | 63800 | 802142 | 51885 | 184206 | 11915
c | 3 -1/2 core 185 Sq mm XLPE | R Mtr | 618 | 46 | 800 | 650 | 650 | 401700 | 29900 | 361530 | 26910 | 40170 | 2990
d) | 3 -1/2 core 150 Sq mm XLPE | R Mtr | 494 | 46 | 500 | 585 | 585 | 288990 | 26910 | 240084 | 22356 | 48906 | 4554
e | 4 core 35 Sq mm XLPE | R Mtr | 164 | 41 | Ro | 502 | 502 | 82328 | 20582 | 74095 | 18524 | 8233 | 2058
f | 4 core 25 Sq mm XLPE | R Mtr | 134 | 36 | Ro | 354 | 354 | 47436 | 12744 | 42692 | 11470 | 4744 | 1274
2 | Cable end termination of the following XLPE cables 1100 Volt grade including cost of crimping tinned Aluminium heavy duty lugs, double compression glands, insulation tape and all requisite material for completion of joints as required at site | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
a) | 3 -1/2 core 300 Sq mm XLPE | Set | 2163 | 162 | 18 | 22 | 22 | 47586 | 3564 | 42828 | 3208 | 4758 | 356
b) | 3 -1/2 core 240 Sq mm XLPE | Set | 1854 | 162 | 8 | 38 | 38 | 70452 | 6156 | 30035 | 2624 | 40417 | 3532
c) | 3 -1/2 core 185 Sq mm XLPE | Set | 1236 | 143 | 12 | 6 | 6 | 7416 | 858 | 6675 | 772 | 741 | 86
d) | 3 -1/2 core 150 Sq mm XLPE | Set | 1236 | 143 | 4 | 8 | 8 | 9888 | 1144 | 8899 | 1030 | 989 | 114
h) | 4 core 35 Sq mm XLPE | Set | 453 | 112 | Ro | 4 | 4 | 1812 | 448 | 816 | 202 | 996 | 246
i) | 4 core 25 Sq mm XLPE | Set | 381 | 112 | Ro | 4 | 4 | 1524 | 448 | 1371 | 403 | 153 | 45
3 | Supply and fixing of perforated GI slotted cable trays with vertical sides on both ends as per approved design and GI angle supports spaced 1000 mm apart throughout the length as specified, including the cost of 1 meter GI rod hangers, hooks, dash fasteners, wall brackets etc. for suspension from ceiling / wall as required | [6 empty] | 0 | 0 |  |  | 0 | 0
d) | 450mm x 50 mm x 50 mm x 1.6 mm | Mtr | 587 | 446 | 20 | 6.5 | 6.5 | 3815.5 | 2899 |  | 0 | 3816 | 2899
4 | Supply and laying of the following RCC Hume pipe (NP-3) in ground including excavation, refilling as required for cable entry including the cost of sealing the ends as required complete as required at site. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
b | 250 mm dia | R Mtr | 371 | 143 | 200 | 862.5 | 862.5 | 319987.5 | 123337.5 | 287989 | 111004 | 31999 | 12334
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
6 | Providing and making of manhole chamber with masonry bricks (230mm thick wall) and plastering inside with 1:3:6 and fixing of Heavy duty frame and pre cast RCC cover as required. | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
a) | 910 x 910 x 600 mm deep | Nos |  | 13700 | Ro |  | 27 | 0 | 369900 |  | 0 | 0 | 369900
| SUB HEAD IV : EARTHING | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
1 | Providing and making earthpits including the cost of 600 mm x 600 mm x 3 mm thick copper plate electrodes, 20 mm dia pipe, CI funnel with wiremesh charcoal, salt, all earth work, masonry enclosure with CI frame & cover plate having locking arrangement complete as per IS 3043:1987 | Nos | 17509 | 1320 | 4 | 4 | 4 | 70036 | 5280 | 55833 | 4752 | 14203 | 528
2 | Providing and making earthpits including the cost of 600 mm x 600 mm x 6 mm thick GI plate electrodes, 20 mm dia pipe, CI funnel with wiremesh charcoal, salt, all earth work, masonry enclosure with CI frame & cover plate having locking arrangement complete as per IS 3043:1987 | Nos | 4223 | 1320 | 8 | 12 | 12 | 50676 | 15840 | 45609 | 14256 | 5067 | 1584
4 | Supplying and laying of the following earthing clamp to wall with suitable clamps saddles and fixing bolts/ in ground including the cost of digging and back filling as required and complete as required to comply with IS 3043:1987 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
b) | 50 mm x 6 mm GI strip | RM | 164 | 91 | 40 | 160 | 160 | 26240 | 14560 | 5904 | 3276 | 20336 | 11284
c) | 25 mm x 6 mm GI strip | RM | 82 | 71 | 160 | 29.6 | 29.6 | 2427.2 | 2101.6 | 11808 | 10224 | -9381 | -8122
d) | 25 mm x 6 mm CU strip | RM | 742 | 71 | 120 | 37.8 | 37.8 | 28047.6 | 2683.8 | 80136 | 7668 | -52088 | -4984
| GROSS VALUE Rs. | [6 empty] | 6269822.8 | 844026.9 | 5525712 | 412981 | 744112 | 431045
| TOTAL (Supply+Erection) | [7 empty] | 7113849.7 |  | 5938693 |  | 1175157
| Add W.C.T @ 6.05% on cable Supply & Erection Rs. (31,36,752+1,98,992) | [6 empty] | 3649937 | 220821.1885 | 3600417 | 217825.2285 | 479320 | 28998.86
| Add W.C.T @ 14.5% on balance Supply & Erection Rs. (23,20,400 + 1,50,916) | [6 empty] | 2619885.8 | 379883.441 | 2047155 | 296837.475 | 264792 | 38394.84
| Add labour cess @ 1% on supply + Erection | [7 empty] | 71138.497 |  | 59386.93 |  | 11751.57
| Add Service Tax @ 14.5 % on Erection | [7 empty] | 122383.9005 |  | 60344 |  | 62501.525
| Grand Total (A) | [7 empty] | 7908076.727 |  | 6573086.6335 |  | 1316803.795
SUMMARY OF NON SCHEDULE ITEMS
1 | Excavation of Cable Trenches for shifting of cable at New Girls Hostel | RM | 461 |  |  | 70 |  | 32270 |  |  |  | 32270
2 | 100 Amp Seperatorl Links Make Schneider | Set | 2305 |  |  | 4 |  | 9220 |  |  |  | 9220
3 | Adopter Box suitable for vertical TPN 8Way DBs | Each | 5910 |  |  | 3 |  | 17730 |  |  |  | 17730
4 | Transformer Oil | Drum | 143.5 |  |  | 410 |  | 58835 |  |  |  | 58835
5 | Replacement of Dimmer 80 Amp | Each | 51388 |  |  | 2 |  | 102776 |  |  |  | 102776
6 | UPS Panel | Each | 55534 |  |  | 1 |  | 55534 |  |  |  | 55534
7 | Shifting & Re-Installtion of Servo | Each | 20930 |  |  | 4 |  | 83720 |  |  |  | 83720
8 | Repairing/Replacement of Control Cards | Each | 21000 |  |  | 15 |  | 315000 |  |  |  | 315000
9 | Dismaltling & Shifting of HT Cable Junction Box | Job | 24624 |  |  | 1 |  | 24624 |  |  |  | 24624
10 | Dismaltling & Shifting of HT Cable Cables Including Jointing Kits | Job | 30780 |  |  | 1 |  | 30780 |  |  |  | 30780
11 | Receiving, Unloading & Installation of 7 Way + Metering RMU | Set | 36915 |  |  | 1 |  | 36915 |  |  |  | 36915
12 | Supply & Fixing of MS Channels | Kgs | 68 |  |  | 110 |  | 7480 |  |  |  | 7480
13 | Supply & Fixing of Cable Route markers | each | 666 |  |  | 60 |  | 39960 |  |  |  | 39960
14 | Liasioning | JOB |  |  |  | 0 |  | 0 |  |  |  | 0
| Grand Total (B) | [6 empty] | 814844 |  | 0 |  | 814844
| GRAND TOTAL OF (A+B) | [6 empty] | 8722920.727 |  | 6573086.6335 |  | 2131647.795
1990001

## MB
MEASUREMENT DETAILS OF ELECTRICAL WORKS
ITEM No | DESCRIPTION | LOCATION | UNIT | QTY
2 (a) | 3C X 300 SQ MM JOINTING KIT | Sub-station-1 | Nos | 1
|  | Sub-station-3 | Nos | 1
|  | TOTAL | Nos | 2
(b) | 300 SQ MM STRAIGHT THOUGH JOINTING KIT | between sub station-1 &3 | Nos | 2
|  | TOTAL | Nos | 2
© | 3C X 120SQ MM JOINTING KIT | Sub-station-3 | Nos | 2
|  | New Sub-station | Nos | 2
|  | Transformer | Nos | 2
|  | H-Pole | Nos | 2
|  | TOTAL | Nos | 8
(d) | 120 SQ MM STARIGHT THROUGH JOINTING KIT | between New S/Stn and H-Pole | Nos | 1
|  | Near H Pole PEB-300 | Nos | 2
|  | TOTAL | Nos | 3
SUB-HEAD-II
1 | 11 KV HT SYSTEM | New Sub-station | Nos | 1
2 | Oil Type Transformer | New Sub-station | Nos | 1
3 | Distribution Panel
(a) | Main LT Panel | New Sub-station | Nos | 1
(b) | Main Emergency Panel | New Sub-station | Nos | 1
(C) | Capacitor Panel | New Sub-station | Nos | 1
5 | 22.5 Kgs CO-2 Type Fire Extingushers | New Sub-station | Nos | 6
6 | 2.4 mm Thick insulated synthetic Mat | New Sub-station | RM | 50
7 | Shock Traetmrnt Chart | New Sub-station | Nos | 4
8 | Danger Plates | New Sub-station | Nos | 4
9 | Frist Aid Box | New Sub-station | Nos | 2
10 | Fire Buckets with Stand | New Sub-station | Nos | 10
11 | Rubber Gloves | New Sub-station | Pair | 2
SUB HEAD-III
12 | Cable Tray | servo Incoming & Outgoing cables | Mtr | 6.5
13 | Manhole Chamber | from Sub station-1 to S/stn-3 | Nos | 12
|  | from Sub station-3 to New S/stn- | Nos | 13
|  | from New Sub station to Ring Main | Nos | 2
|  | TOTAL | Nos | 27
NON SCHDULE ITEMS
NS-1 | Excavation of Cable Trenches for shifting of cable at New Girls Hostel | J- HOSTEL & LAUNDARY AREA
NS-2 | 100 Amp Seperatorl Links Make Schneider | PEB-600 | SET | 4
NS-3 | Adopter Box suitable for vertical TPN 8Way DBs | PEB-600 | Nos | 3
NS-4 | Transformer Oil | SUB STATATION No.-4 | DRUM | 2
NS-5 | Replacement of Dimmer 80 Amp | SUB STATATION No.-4 | Nos | 2
NS-6 | UPS DB | SUB STATATION No.-4 | Nos | 1
NS-7 | Shifting & Re-Installtion of Servo | SUB STATATION No.-4 | Nos | 3
NS-8 | Repairing/Replacement of Control Cards | SUB STATATION No.-4 | Nos | 15
NS-9 | Dismaltling & Shifting of HT Cable Junction Box | SUB STATATION No.-3 | Job | 1
NS-10 | Dismaltling & Shifting of HT Cable Cables Including Jointing Kits | SUB STATATION No.-3 | Job | 1
NS-11 | Receiving, Unloading & Installation of 7 Way + Metering RMU | SUB STATATION No.-3 | Job | 1
NS-12 | Supply & Fixing of MS Channels | SUB STATATION No.-3 | Kgs | 68
NS-13 | Supply & Fixing of Cable Route markers | SUB STATION-1 TO S/STN-3, 4, AND PEB HOSTELS | Nos | 60
NS-14 | Liasioning |  | JOB | 1

## Cable Schedule
CABLE SCHEDULE OF PEB SUB STATION HOSTEL
SR | SIZE OF CABLES | FROM | TO | UNIT | No of Run | LENGTH | TOTAL QTY | TERMINATION (SETS)
3 C X 300 SQ MM HT CABLES
1 | 3 C X 300 SQ MM | EXISTING RMUs S/STIN-1 | RMU NEW S/STN-3 | Mtr | 1 | 500 | 500 | 2
3 C X 120 SQ MM HT CABLES |  |  |  |  | TOTAL |  | 500 | 2
2 | 3 C X 120 SQ MM | SUB STATION-3 | PEB SUB STATION | Mtr | 1 | 416 | 416 | 2
3 | 3 C X 120 SQ MM | PEB SUB STATION | H-POLE NEAR PEB-300 | Mtr | 1 | 165 | 165 | 2
4 | 3 C X 120 SQ MM | PEB SUB STATION | TRANSFORMER | Mtr | 1 | 20 | 20 | 2
[5 empty] | TOTAL |  | 601 | 6
3.5 X 300 SQ MM LT CABLES
5 | 3.5 X 300 SQ MM | TRANSFORMER | MAIN LT PANEL | Mtr | 5 | 20.8 | 104 | 10
| 3.5 X 300 SQ MM | TRANSFORMER | MAIN LT PANEL | Mtr | 1 | 21 | 21 | 2
6 | 3.5 X 300 SQ MM | Servo | PEB-600, AC PANEL RIGHT SIDE | Mtr | 1 | 150 | 150 | 2
7 | 3.5 X 300 SQ MM | Servo | PEB-600, AC PANEL CENTRE SIDE | Mtr | 1 | 234 | 234 | 2
[5 empty] | TOTAL |  | 509 | 22
3.5 X 240 SQ MM LT CABLES
8 | 3.5 X 240 SQ MM | MAIN LT PANEL | CAPACITOR PANEL | Mtr | 4 | 15 | 60 | 8
9 | 3.5 X 240 SQ MM | Servo | PEB-300, AC PANEL | Mtr | 2 | 204 | 408 | 4
10 | 3.5 X 240 SQ MM | MAIN LIGHTING PANEL | PEB-300, LIGHT PANEL | Mtr | 1 | 204 | 204 | 2
11 | 3.5 X 240 SQ MM | DG SET | DG AMF PANEL | Mtr | 2 | 20 | 40 | 4
12 | 3.5 X 240 SQ MM | MAIN LT PANEL | DG AMF PANEL | Mtr | 2 | 12 | 24 | 4
13 | 3.5 X 240 SQ MM | DG AMF PANEL | EMG PANEL | Mtr | 2 | 16 | 32 | 4
14 | 3.5 X 240 SQ MM | MAIN LT PANEL | SERVO STABILIZER PEB-300 | Mtr | 2 | 20 | 40 | 4
15 | 3.5 X 240 SQ MM | MAIN LT PANEL | SERVO STABILIZER PEB-600 RIGHT SIDE | Mtr | 1 | 13 | 13 | 2
16 | 3.5 X 240 SQ MM | MAIN LT PANEL | SERVO STABILIZER PEB-600 CENTRE | Mtr | 1 | 15 | 15 | 2
17 | 3.5 X 240 SQ MM | OUT FEEDER PILLER | EMG PANEL | Mtr | 1 | 96 | 96 | 2
16 | 3.5 X 240 SQ MM | R&D SUB STATION | COLLONY FEEDER PILLER | Mtr | 1 | 221 | 221 | 2
17 | 3.5 X 240 SQ MM | PG HOSTEL | MES | Mtr | 1 | 123 | 123 | 2
[5 empty] | TOTAL |  | 1276 | 40
3.5 X 185 SQ MM LT CABLES
18 | 3.5 X 185 SQ MM | MAIN LIGHTING PANEL | PEB-600, LIGHT PANEL RIGHT SIDE | Mtr | 1 | 148 | 148 | 2
19 | 3.5 X 185 SQ MM | MAIN LIGHTING PANEL | PEB-600, LIGHT PANEL CENTRE SIDE | Mtr | 1 | 232 | 232 | 2
20 | 3.5 X 185 SQ MM | MAIN LIGHTING PANEL | PEB-600, LIGHT PANEL LEFT SIDE | Mtr | 1 | 270 | 270 | 2
[5 empty] | TOTAL |  | 650 | 6
3.5 X 150 SQ MM LT CABLES
21 | 3.5 x 150 SQ MM | SERVO | PEB-600, AC PANEL LEFT SIDE | Mtr | 2 | 270 | 540 | 4
22 | 3.5 x 150 SQ MM | MAIN LT PANEL | Servo | Mtr | 2 | 22.5 | 45 | 4
[5 empty] | TOTAL |  | 585 | 8
4 X 35 SQ MM LT CABLES
23 | 4 X 35 SQ MM | PEB UPS MAIN DB | PEB-600, ELECTRICAL ROOM LEFT SIDE | Mtr | 1 | 267 | 267 | 2
24 | 4 X 35 SQ MM | PEB UPS MAIN DB | PEB-600, ELECTRICAL ROOM CENTRE SIDE | Mtr | 1 | 235 | 235 | 2
[5 empty] | TOTAL |  | 502 | 4
4 X 25 SQ MM LT CABLES
25 | 4 X 25 SQ MM | PEB UPS MAIN DB | PEB-600, ELECTRICAL ROOM RIGHT SIDE | Mtr | 1 | 150 | 150 | 2
26 | 4 X 25 SQ MM | PEB UPS MAIN DB | PEB-300, ELECTRICAL ROOM | Mtr | 1 | 204 | 204 | 2
27 | 4 X 25 SQ MM | SUB STATION-2 | PG HOSTEL MESS | Mtr | 1 | 88 | 88 | 2
[5 empty] | TOTAL |  | 442 | 6
2 X 2.5 SQ MM LT CABLES COPPER CONDUCTOR
28 | 2.0 x 2.5 SQ MM COPPER COND ARM CABLE | MAIN LT PANEL | CAPACITOR PANEL | Mtr | 1 | 18 | 18 | 2
29 |  | DG SET | HT RMU | Mtr | 1 | 24 | 24 | 2
30 |  | EMG PANEL | HT RMU | Mtr | 1 | 18 | 18 | 2
31 |  | HT RMU | TRANSFORMER | Mtr | 2 | 20 | 40 | 4
[5 empty] | TOTAL |  | 100 | 10

## HUME PIPE
DETAILS OF 250 MM DIA RCC HUME PIPE FOR HT CABLE
SR | SIZE OF PIPE | FROM | TO | UNIT | No of Run | LENGTH | TOTAL QTY
1 | 250 MM DIA | SUB STATION -1 | SUB STATATION-3 | Mtr | 1 | 377.5 | 377.5
2 | 250 MM DIA | SUB STATION -3 | NEW SUB STATATION- PEB | Mtr | 1 | 340 | 340
3 | 250 MM DIA | NEW SUB STATATION- PEB | PEB-600 HOSTEL ROAD CROSSING | Mtr | 3 | 7.5 | 22.5
4 | 250 MM DIA | NEW SUB STATATION- PEB | EXISTING H-POLE FOR RING MAIN | Mtr | 1 | 122.5 | 122.5
[5 empty] | TOTAL |  | 862.5

## EARTHING
DETAILS OF EARTHING PITS
SR | DESCRIPTION | UNIT | QTY
600X600X6 MM GI PLATE TYPE
1 | DG SET BODY EARTHING | Nos | 2
2 | SERVO BODY AND DG AMF PANEL | Nos | 4
3 | MAIN LT PANELS | Nos | 2
4 | HT PANEL | Nos | 2
5 | TRANSFORMER BODY | Nos | 2
| TOTAL | Nos | 12
600X600X3.15 MM COPPER PLATE TYPE
6 | DG SET NEUTRAL | Nos | 2
7 | TRANSFORMER NEUTRAL | Nos | 2
| TOTAL | Nos | 4