## RA01_F (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 |  |  |  | Bill No. | RA - 01
Project : | PEB 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 21-04-2016
Contractor : | INTERARCH BUILDING PRODUCTS PVT LTD |  |  | Date of Adhoc Certificate
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 21-04-2016
Forward by Vincom
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CSD/PSJ/15-16/150016A | 23.11.2015 | Work Done Up to
Date of Agreement : |  |  | 23.11.2015
Completion Date :
Contract Value : |  |  | 8000000 | Mobilisation Paid |  | 1600000
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-04-21
Invoice Amount : |  |  | 2290000 | Material Advance Paid
Amount Recommended : |  |  | 2119600 | Material Advance Recovered
Service Tax No. : |  |  | AAAC10106J
TIN No. |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  |  | 2000000 | 2000000
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  | 0 | 2000000 | 2000000
B | Add Taxes
B1 | Service (Tax 14.00 %) of 40% of (A) |  |  |  | 280000 | 280000
B2 | W.C.T. i.e. VAT on Contracts 5.25% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 20000 | 20000
| Sub Total - (A+B) |  |  | 0 | 2300000 | 2300000
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Payable@20%, Recovery @ 20% from 2nd RA Bill of (A+B) |  |  | 1600000 |  | 1600000
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Advance against Material at Site @ 80% of Value
| Sub Total - (C) |  |  | 1600000 | 0 | 1600000 | 2300000
| Total - (A+B+C) |  |  | 1600000 | 2300000 | 3900000
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A)
D2 | W.C.T. @ 6% on (A) |  |  | 96000 | 120000 | 216000
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  | 32000 | 40400 | 72400
D4 | Labour Cess @ 1% on (A) |  |  |  | 20000 | 20000
| Sub Total - (D) |  |  | 128000 | 180400 | 308400
| Net Amount Payable (A+B+C-D) |  |  | 1472000 | 2119600 | 3591600
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil singla |  | Vinay kumar | R.K.Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments

## RA03 FINAL
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 (Payment Of Additional Work) |  |  |  | Bill No.1 | Final Bill
Project : | PEB 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-11-17
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
| Additional Work 4 Nos. Walk Way |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-10-10
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : |  |  |  | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  |  | Advance payment - Paid
Amended Contract Value : |  |  |  | Advance - Recovered
Invoice Date : |  |  | 2016-08-16 | Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 453600
Amount Recommended : |  |  | 350500.8
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 25% Advance against corporate guarantee |  |  |  | 0
A1.2 | 65% on Eraction of superstructure |  |  |  | 0 |  | 309192
A1.3 | 10% Shall be released against submission of PBG of 12 month |  |  |  | 0
A1.4 | Additional Work 4 Nos. Walk Way |  |  |  | 350500.8 | 350500.8
| Sub Total - (A) |  |  |  | 350500.8 | 350500.8
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) - Included in above
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 350500.8 | 350500.8
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  |  | 350500.8 | 350500.8
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1) |  |  |  | 0
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  |  | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3. Statuary compliance to be take care at site.
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers International (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by Vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02-FINAL SUPPLY
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 (FINAL PAYMENT AGAINST SUBMISSION PBG) |  |  |  | Bill No. | RA-02
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-08-30
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Material Supply |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-29
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035 (Supply) |  | 2016-02-01 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 29100000 | Advance payment - Paid |  | 7275000
Amended Contract Value : |  |  |  | Advance - Recovered
Invoice Date : |  |  | 2016-08-16 | Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 2910000
Amount Recommended : |  |  | 2910000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 25% Advance against corporate guarantee |  |  | 7275000 | 0 | 7275000
A1.2 | 65% on Eraction of superstructure |  |  | 18915000 | 0 | 18915000
A1.3 | 10% Shall be released against submission of PBG of 12 month |  |  |  | 2910000 | 2910000
| Sub Total - (A) |  |  | 26190000 | 2910000 | 29100000 | 29450500.8
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) - Included in above
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 26190000 | 2910000 | 29100000
C | Mobilisation Advance / Secured Advance / Other Advance | [6 empty] | 2152798.1
C1 | Mobilisation Advance
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 26190000 | 2910000 | 29100000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1) |  |  |  | 0
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  |  | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3. Statuary compliance to be take care at site.
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by Vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA05-Final-ERECTION
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 05 (FINAL PAYMENT AGAINST SUBMISSION PBG) |  |  |  | Bill No. | RA-05
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-08-30
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Erection of superstructure, Deck Roof,Insulation etc. |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-29
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035A (Erection) |  | 2016-01-01 | Work Done Up to
Date of Agreement : |  |  | 2016-01-01
Construction Start Date :
Completion Date : |  |  | In Progress
Initial Contract Value : |  |  | 4100000 | Mobilisation Advance - Paid |  | 820000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered |  | Part of Payment Term
Invoice Date : |  |  | 2016-07-15 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 411791
Amount Recommended : |  |  | 410000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 20% Advance against corporate guarantee |  |  | 820000 | 0 | 820000
A1.2 | 40% on Eraction of superstructure (Released I bill 20%) |  |  | 1640000 | 0 | 1640000
A1.3 | 30% completion of deck work |  |  | 1230000 | 0 | 1230000
A1.4 | 10% Shall be released against submission of PBG of 12 month |  |  |  | 410000 | 410000
| Sub Total - (A) |  |  | 3690000 | 410000 | 4100000
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) Included in above |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 3690000 | 410000 | 4100000
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Advance against corporate guarantee
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 3690000 | 410000 | 4100000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1)
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  | 0 | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3.Statuary compliance to be take care at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA01F (SUPPLY)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 (RAB 01 - MATERAL SUPPLY BILL) |  |  |  | Bill No.1 | RA-01
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-07-26
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Material Supply |  |  | Submission by Contractor
Received by Vincom
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035 (Supply) |  | 2016-02-01 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 29100000 | Advance payment - Paid
Amended Contract Value : |  |  |  | Advance - Recovered
Invoice Date : |  |  |  | Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 29100000
Amount Recommended : |  |  | 29100000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 20% Advance against corporate guarantee |  |  |  | 29100000
A1.2 | 40% on Eraction of superstructure
A1.3 | 30% completion of deck work
A1.4 | 10% Shall be released against submission of PBG of 12 month
| Sub Total - (A) |  |  | 0 | 29100000 | 0
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) - Included in above
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 0 | 29100000 | 0
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Mobilisation Advance
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 0 | 29100000 | 0
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1) |  |  |  | 0
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  |  | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3. Statuary compliance to be takes care at site.
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by Vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA04F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 04 (FINAL PAYMENT) |  |  |  | Bill No. | RA-03
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-08-05
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Erection of superstructure, Deck Roof,Insulation etc. |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-05
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035A (Erection) |  | 2016-01-01 | Work Done Up to
Date of Agreement : |  |  | 2016-01-01
Construction Start Date :
Completion Date : |  |  | In Progress
Initial Contract Value : |  |  | 4100000 | Mobilisation Advance - Paid |  | 820000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered |  | Part of Payment Term
Invoice Date : |  |  | 2016-07-15 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 823581
Amount Recommended : |  |  | 820000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 20% Advance against corporate guarantee |  |  | 820000 | 0 | 820000
A1.2 | 40% on Eraction of superstructure (Released I bill 20%) |  |  | 820000 | 820000 | 1640000
A1.3 | 30% completion of deck work |  |  | 1230000 | 0 | 1230000
A1.4 | 10% Shall be released against submission of PBG of 12 month
| Sub Total - (A) |  |  | 2870000 | 820000 | 3690000
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) Included in above |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 2870000 | 820000 | 3690000
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Advance against corporate guarantee
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 2870000 | 820000 | 3690000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1)
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  | 0 | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3.Statuary compliance to be takes care at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA03F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (RAB 03- FINAL PAYMENT) |  |  |  | Bill No. | RA-03
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-08-05
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Erection of superstructure, Deck Roof,Insulation etc. |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-08-05
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035A (Erection) |  | 2016-01-01 | Work Done Up to
Date of Agreement : |  |  | 2016-01-01
Construction Start Date :
Completion Date : |  |  | In Progress
Initial Contract Value : |  |  | 4100000 | Mobilisation Advance - Paid |  | 820000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered |  | Part of Payment Term
Invoice Date : |  |  | 2016-07-15 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 823581
Amount Recommended : |  |  | 820000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 20% Advance against corporate guarantee |  |  | 820000 | 0 | 820000
A1.2 | 40% on Eraction of superstructure (Released I bill 20%) |  |  | 820000 | 820000 | 1640000
A1.3 | 30% completion of deck work |  |  | 1230000 | 0 | 1230000
A1.4 | 10% Shall be released against submission of PBG of 12 month
| Sub Total - (A) |  |  | 2870000 | 820000 | 3690000
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) Included in above |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 2870000 | 820000 | 3690000
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Advance against corporate guarantee
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 2870000 | 820000 | 3690000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1)
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  | 0 | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3.Statuary compliance to be takes care at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 (RAB 02- FINAL PAYMENT) |  |  |  | Bill No. | RA-02
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-06-19
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Erection of superstructure, Deck Roof,Insulation etc. |  |  | Submission by Contractor |  | 2016-06-17
|  |  |  | Received by Vincom |  | 2016-06-17
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035A (Erection) |  | 2016-01-01 | Work Done Up to
Date of Agreement : |  |  | 2016-01-01
Construction Start Date :
Completion Date : |  |  | In Progress
Initial Contract Value : |  |  | 4100000 | Mobilisation Advance - Paid |  | 820000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered |  | Part of Payment Term
Invoice Date : |  |  | 2016-06-10 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 1235371
Amount Recommended : |  |  | 1230000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 20% Advance against corporate guarantee |  |  | 820000 |  | 820000
A1.2 | 40% on Eraction of superstructure (Released I bill 20%) |  |  | 820000 |  | 820000
A1.3 | 30% completion of deck work |  |  |  | 1230000 | 1230000
A1.4 | 10% Shall be released against submission of PBG of 12 month
| Sub Total - (A) |  |  | 1640000 | 1230000 | 2870000
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) Included in above |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 1640000 | 1230000 | 2870000
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Advance against corporate guarantee
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 1640000 | 1230000 | 2870000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1)
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  | 0 | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3.Statuary compliance to be takes care at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA01F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 (RAB 01- FINAL PAYMENT) |  |  |  | Bill No. | RA-01
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Final Certificate |  | 2016-06-06
Contractor : | INTERARCH BUILDING PRODUCT PVT LTD |  |  | Date of 70% Certificate
Service : | Erection of superstructure, Deck Roof,Insulation etc. |  |  | Submission by Contractor |  | 2016-06-01
|  |  |  | Received by Vincom |  | 2016-06-01
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/15-16/150035A (Erection) |  | 2016-01-01 | Work Done Up to
Date of Agreement : |  |  | 2016-01-01
Construction Start Date :
Completion Date : |  |  | In Progress
Initial Contract Value : |  |  | 4100000 | Mobilisation Advance - Paid |  | 820000
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered |  | Part of Payment Term
Invoice Date : |  |  | 2016-05-25 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 820000
Amount Recommended : |  |  | 820000
Service Tax No. : |  |  | AAAC10106J
TIN NO |  |  | 5000533622
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1.1 | 20% Advance against corporate guarantee |  |  | 820000 |  | 820000
A1.2 | 40% on Eraction of superstructure (Released I bill 20%) |  |  |  | 820000 | 820000
A1.3 | 30% completion of deck work |  |  |  | 0
A1.4 | 10% Shall be released against submission of PBG of 12 month
| Sub Total - (A) |  |  | 820000 | 820000 | 1640000
B | Add Taxes
B1 | Service (Tax 14.00 %) on (A) Included in above |  |  |  | 0
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 820000 | 820000 | 1640000
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Advance against corporate guarantee
C2 | Material Advance Paid in Last Month |  |  |  | 0
C3 | Recovery - Against Material Advance Paid in Last month |  |  |  | 0
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Retention Money
D1 | Retention Money @ 5% (Less) on (A+B)
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 820000 | 820000 | 1640000
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on (A+C1)
E2 | T.D.S. @ 2% on (A+B+C-B1)
E3 | Labour Cess @ 1% on (A)
| Sub Total - (E) |  |  | 0 | 0 | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
3.Statuary compliance to be takes care at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Forward by TU as checked & recommended by vincom
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.