## RA04F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 04 (Final Bill Payment) |  |  |  | Bill No. | RA-03
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2018-02-15
Contractor : | M.S.Fore Solution Pvt.Ltd. |  |  | Date of 70% Certificate
Service : | Networking material supply |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2018-02-13
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150086 |  | 2016-09-06 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 9616968 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  | Against PBG | 2018-01-18 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 2737689
Amount Recommended : |  |  | 2737689
Service Tax No. : |  |  | AAACF6375QST001
TIN NO |  |  | 04520020072
PAN of Contractor : |  |  | AAACF6375Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 70% Payment Against Delivery Of Material |  |  | 9125630 | 0 | 9125630
A2 | 30% Payment Against PBG |  |  |  | 0
0
| Sub Total - (A) |  |  | 9125630 | 0 | 9125630
| 70% Payment Against Delivery Of Material |  |  | 6387941 | 0 | 6387941
| 30% Payment Against PBG |  |  |  | 2737689 | 2737689
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 6387941 | 2737689 | 9125630
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Secured Advance
C2 | Payment Already Paid On Against Bill No. (187 & 188) |  |  | 4650237 | 0 | 4650237
C3 | Adjest Payment Already Paid On Against Bill No. (187 & 188) |  |  | -4650237 | 0 | -4650237
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Late Delivery Clause
D1 | Late Delivery @ 0.2% Per day maximum 5% (Less) on Tender value.
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 6387941 | 2737689 | 9125630
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Dinesh Choudhary
Approved by
Thapar University Patiala
Anil Singla |  | MD ALAM | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA03F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (FOR ADJUESTMENT) |  |  |  | Bill No. | RA-03
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2017-01-21
Contractor : | M.S.Fore Solution Pvt.Ltd. |  |  | Date of 70% Certificate
Service : | Networking material supply |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2017-01-04
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150086 |  | 2016-09-06 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 9616968 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  | 16/17/272 | 2017-01-07 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 905207
Amount Recommended : |  |  | 633645
Service Tax No. : |  |  | AAACF6375QST001
TIN NO |  |  | 04520020072
PAN of Contractor : |  |  | AAACF6375Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 70% Payment Against Delivery Of Material |  |  | 8220423 | 905207 | 9125630
A2 | 30% Payment Against PBG |  |  |  | 0
0
| Sub Total - (A) |  |  | 8220423 | 905207 | 9125630
| 70% Payment Against Delivery Of Material |  |  | 5754296 | 633645 | 6387941
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 5754296 | 633645 | 6387941
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Secured Advance
C2 | Payment Already Paid On Against Bill No. (187 & 188) |  |  | 4650237 | 0 | 4650237
C3 | Adjest Payment Already Paid On Against Bill No. (187 & 188) |  |  | -4650237 | 0 | -4650237
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Late Delivery Clause
D1 | Late Delivery @ 0.2% Per day maximum 5% (Less) on Tender value.
| Sub Total - (D) |  |  | 0 | 0 | 0
| Total - (A+B+C-D) |  |  | 5754296 | 633645 | 6387941
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 |  |  |  | Bill No. | RA-02
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2017-01-21
Contractor : | M.S.Fore Solution Pvt.Ltd. |  |  | Date of 70% Certificate
Service : | Networking material supply |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2017-01-18
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150086 |  | 2016-09-06 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 9616968 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-09-22 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 473802
Amount Recommended : |  |  | 772397
Service Tax No. : |  |  | AAACF6375QST001
TIN NO |  |  | 04520020072
PAN of Contractor : |  |  | AAACF6375Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | 70% Payment Against Delivery Of Material |  |  | 7116998 | 1103425 | 8220423
A2 | 30% Payment Against PBG |  |  |  | 0
0
| Sub Total - (A) |  |  | 7116998 | 1103425 | 8220423
| 70% Payment Against Delivery Of Material |  |  | 4981899 | 772397 | 5754296
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 4981899 | 772397 | 5754296
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Secured Advance
C2 | Payment Already Paid On Against Bill No. (187 & 188) |  |  | 4650237 | 0 | 4650237
C3 | Adjest Payment Already Paid On Against Bill No. (187 & 188) |  |  | -4650237 | 0 | -4650237
| Sub Total - (C) |  |  | 0 | 0 | 0
D | Recovery - Late Delivery Clause
D1 | Late Delivery @ 0.2% Per day maximum 5% (Less) on Tender value. |  |  | 38468
| Sub Total - (D) |  |  | 38468 | 0 | 0
| Total - (A+B+C-D) |  |  | 4943431 | 772397 | 5754296
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA01F
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 01 |  |  |  | Bill No. | RA-01
Project : | PEB 300 & 600 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-10-14
Contractor : | M.S.Fore Solution Pvt.Ltd. |  |  | Date of 70% Certificate
Service : | Networking material supply |  |  | Submission by Contractor
|  |  |  | Received by Vincom |  | 2016-10-05
Send to Account
Cheque Issued
GENERAL INFORMATION
LOI No. & Date : | TU/CS/PSJ/16-17/150086 |  | 2016-09-06 | Work Done Up to
Date of Agreement :
Construction Start Date :
Completion Date :
Initial Contract Value : |  |  | 9616968 | Mobilisation Advance - Paid
Amended Contract Value : |  |  |  | Mobilisation Advance - Recovered
Invoice Date : |  |  | 2016-09-22 | Mobilisation Advance - Balance
Contractor's Invoice Amount : (Work Done - This Bill) |  |  | 473802
Amount Recommended : |  |  | 293194
Service Tax No. : |  |  | AAACF6375QST001
TIN NO |  |  | 04520020072
PAN of Contractor : |  |  | AAACF6375Q
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Payment Againdt delivery of material(INVOICE NO:-187) |  |  |  | 5654350 | 5654350
A2 | Payment Againdt delivery of material(INVOICE NO:-188) |  |  |  | 988846 | 988846
A3 | Payment Againdt delivery of material(INVOICE NO:-200) |  |  |  | 473802 | 473802
| Sub Total - (A) |  |  |  | 7116998 | 7116998
| 70% Payment Against Delivery Of Material |  |  |  | 4981899 | 4981899
B | Add Taxes
B1 | Service Tax @ 5.8% on (A)
B2 | W.C.T. i.e. VAT on Contracts 6.00% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 4981899 | 4981899
C | Mobilisation Advance / Secured Advance / Other Advance | [5 empty] | 2152798.1
C1 | Secured Advance
C2 | Payment Already Paid On Against Bill No. (187 & 188) |  |  | 4650237 | 0 | 4650237
C3 | Adjest Payment Already Paid On Against Bill No. (187 & 188) |  |  |  | -4650237 | -4650237
| Sub Total - (C) |  |  |  | -4650237 | 0
D | Recovery - Late Delivery Clause
D1 | Late Delivery @ 0.2% (Less) on Tender value Per Day |  |  |  | 38468 | 38468
| Sub Total - (D) |  |  |  | 38468 | 38468
| Total - (A+B+C-D) |  |  |  | 293194 | 4943431
E | Other Recoveries/ Tax deductions
E1 | W.C.T. i.e. VAT @ 6.00% on
E2 | T.D.S. @ 2% on
E3 | Labour Cess @ 1% on
| Sub Total - (E) |  |  |  | 0
Net Amount Payable **(A+B+C-D-E)
**Note : | 1. Deduction for WCT, TDS, Labour Cess, Adhoc Payment, Water & Electricity Charges will made by TU Account
2. This Payment is recommended for the work Executed at site
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals (India)
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil Singla |  | Vinay Kumar | R.K. Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions payments released so far before making the payments.

## RA02_70% (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 02 |  |  |  | Bill No. | RA-002
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-05-17
Contractor : | D. K. Buildcon Pvt. Ltd. |  |  | Date of Adhoc Certificate |  | 2016-05-17
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 2016-05-12
|  |  |  | Received by Vincom |  | 2016-05-12
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CS/PSJ/15-16/150019A | 03.02.2016 | Work Done Up to
Date of Agreement : |  |  | 03.03.2016
Completion Date :
Contract Value : |  |  | 58347484 | Mobilisation Paid |  | 5834750
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-05-01
Invoice Amount : |  |  | 3708968 | Material Advance Paid |  | 954858
Amount Recommended : |  |  | 1830159 | Material Advance Recovered
Service Tax No. : |  |  | AACCD6742P ST001
TIN No. |  |  | 6841325968
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  | 3250165 | 3702261 | 6952426
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate
| Sub Total - (A) |  |  | 3250165 | 3702261 | 6952426
B | Add Taxes
B1 | Service Tax 14.50 % of 40% of (A)
B2 | W.C.T. i.e. VAT on Contracts 5.8% on (A) - Included in above |  |  |  | 214731.13
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  |  | 3916992.13
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Recover@ 5% of Rs. 6952426 Recovery @ |  |  |  | -347621.3
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Recovery Advance against Material at Site @ 80% of Value (Ref. S.A-01 ) |  |  |  | -954858
| Sub Total - (C) |  |  |  | -1302479.3
| Total - (A+B+C) |  |  |  | 2614512.83
| Allow an adhoc payment 70% against 2nd ra bill |  |  |  | 1830159
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A) |  |  |  | 0
D2 | W.C.T. @ 6% on (A) |  |  |  | 0
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  |  | 0
D4 | Labour Cess @ 1% on (A) |  |  |  | 0
| Sub Total - (D) |  |  |  | 0
| Net Amount Payable (A+B+C-D) |  |  |  | 1830159 | 0
Recommended by
Vincom Cost Management Pvt. Ltd. |  |  |  |  | Colliers Internationals
Sanjeev Kumar |  | Mukesh Gupta |  |  | Vikas Jangra
Approved by
Thapar University Patiala
Anil singla |  | Vinay kumar | R.K.Nigam
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments

## RA01_F (hidden)
Vincom Cost Management Pvt Ltd.
| CERTIFICATE OF PAYMENT No. 03 (70% Of Billed payment) |  |  |  | Bill No. | RA-003
Project : | PEB 300 Bed Boys Hostel, Thapar University, Patiala |  |  | Date Trackers
Client : | Thapar University Patiala, Punjab |  |  | Date of Certificate |  | 2016-06-05
Contractor : | D. K. Buildcon Pvt. Ltd. |  |  | Date of Adhoc Certificate |  | 2016-06-05
Service : | Civil, Structural & Finishes Works |  |  | Submission by Contractor |  | 2016-06-02
Received by Vincom
Send to Account
Cheque Issued
GENERAL INFORMATION
Date of LOI :
LOI No. & Date : |  | TU/CS/PSJ/15-16/150019A | 03.02.2016 | Work Done Up to
Date of Agreement :
Completion Date :
Contract Value : |  |  | 58347484 | Mobilisation Paid |  | 5834750
Amended Contract Value : |  |  |  | Mobilisation Recovered
Invoice Date : |  |  | 2016-06-01
Invoice Amount : |  |  | 4304809 | Material Advance Paid
Amount Recommended : |  |  | 1772396 | Material Advance Recovered
Service Tax No. : |  |  | AACCD6742P ST001
TIN No. |  |  | 6841325968
PAN of Contractor : |  |  | AACCD6742K
PAYMENT DETAILS (Figures in Indian Rupees)
S. No. | Particulars |  |  | Up to Previous | This Bill | Total Up-to-date
A | Work and contractual payable
A1 | Scheduled Work |  |  | 6697341 | -3447176 | 3250165
A2 | Non-Scheduled Work |  |  |  | 0
A3 | Variation of Basic Rate |  |  | 65704 | 0 | 65704
| Sub Total - (A) |  |  | 6763045 | -3447176 | 3315869
B | Add Taxes
B1 | Service Tax 5.8% of (A) |  |  | 392257 | -199937 | 192320
B2 | W.C.T. i.e. VAT on Contracts 5.25% on (A) - Included in above |  |  |  | 0
B3 | Labour Cess @ 1% on (A) - Included in above |  |  |  | 0
| Sub Total - (A+B) |  |  | 7155302 | -3647113 | 3508189
C | Mobilisation Advance / Secured Advance / Other Advance
C1 | Mobilisation Advance Payable 5% of Rs. 5,83,47,484 Recovery @ |  |  | 794954 | 5039796 | 5834750
C2 | Secured Advance @ 80% of Material Value |  |  |  | 0
C3 | Advance against Material at Site @ 80% of Value |  |  |  | 954858 | 954858
| Sub Total - (C) |  |  | 794954 | 5994654 | 6789608
| Total - (A+B+C) |  |  | 7950256 | 2347541 | 10297797
D | Recoveries/ Tax deductions
D1 | Retention Money @ 5% on (A) |  |  |  | 165793 | 165793
D2 | W.C.T. @ 5.25% on (A) |  |  |  | 174083 | 174083
D3 | T.D.S. @ 2% on (A+B+C-B1) |  |  |  | 202110 | 202110
D4 | Labour Cess @ 1% on (A) |  |  |  | 33159 | 33159
| Sub Total - (D) |  |  | 0 | 575145 | 575145
| Net Amount Payable (A+B+C-D) |  |  |  | 1772396 | 9722652
Recommended by
Vincom Cost Management Pvt. Ltd.
Sanjeev Kumar |  | Mukesh Gupta | Vinod Markanda
Approved by
Thapar University Patiala
Note :-Finance / Accounts shall make / check all statutory & contractual deductions / additions before making the payments