## Invoice-
INVOICE - WORK DONE VALUE
Project : | Thapar University Extension, Patiala |  |  |  | Date | 2017-07-27
Vendor | Gannon Dunkerley & Co., LTD. Patiala |  |  |  | RA Bill No. | RA-5th
Service | HARDSCAPING Civil and finishes works of Boys & Girls Hostelat Thapar University Patiala |  |  |  | Period | 01-07-2017 To 31-07-2017
GENERAL INFORMATION
LOI. |  | TU/CS/PSJ/16-17/150109
Contract Value : |  | Rs.6,84,56,072.00 (Rupees Six Crore Eighty Four Lac Fifty Six Thousand and Seventy Two Only)
Start Date of Construction |  | 2017-01-09
Completion Date of Construction |  | 2017-05-31
Invoice Details |  | RA-5th
Invoice Amount |  | Rupees One Crore Thirty One Lacs Fifty Six Thousand Eight Hundred And Three Only
PAYMENT DETAILS (Figures in Indian Rupees)
SL. NO. | Particulars |  |  | Up to last bill | This Bill | Total up to date
A | Bill Particulars
A1 | Value of work done - BOYS HOSTEL |  |  | 48396290 | 4169464 | 52565754
A2 | Value of work done - GIRLS HOSTEL |  |  | 6356799 | 374938 | 6731737
A3 | Value of work done - EXTRA ITEMS |  |  | 1638599 | 4857744 | 6496343
| Total A |  |  | 56391688 | 9402146 | 65793834
B | Mobilization Advance @5.56% on A |  |  | 3135378 | 522759 | 3721299
C | Total B |  |  | 53256310 | 8879387 | 62072535
D | Recoveries
D1 | Retention Money @5% on A |  |  | 2819584 | 470107 | 3289692
D2 | TDS @ 2% On C |  |  | 1065126 | 177588 | 1241451
D3 | WCT @ 6% On C |  |  | 3195379 | 532763 | 3724352
| Total Recovery D |  |  | 7080089 | 1180458 | 8255495
E | Amount Payable (C-D) |  |  | 46176221 | 7698929 | 53817040
AMOUNT (IN WORDS) - |  | Rupees One Crore Thirty One Lacs Fifty Six Thousand Eight Hundred And Three Only
Recommended by |  |  | Approved by
Rahul Bhardwaj |  | Dinesh Choudhary | Sanjeev Pancholy |  | Rajendra Nigam
Gannon Dunkerley & Co. Ltd. |  | Colliers International(India) Property Services Pvt Ltd | Vincom Cost Management Pvt. Ltd. |  | Thapar University

## SUMMARY
THAPAR UNIVERSITY EXTENSION PROJECT, PATIALA
M/S. GANNON DUNKERLEY & CO. LTD.
RA Bill- | 06 (August'2017)
SUMMARY OF PAYMENT
SL. NO. | NAME OF STRUCTURE | PREV. BILL AMOUNT | THIS BILL AMOUNT | CUMM. AMOUNT | PREV. BILL AMOUNT | THIS BILL AMOUNT | CUMM. AMOUNT
A | HARDSCAPING
i) | BOYS HOSTEL | 48396290 | 4169464 | 52565754 | 48396290 | 4395124 | 52791414
ii) | GIRLS HOSTEL | 6356799 | 374938 | 6731737 | 6356799 | 424578 | 6781377
| TOTAL | 54753089 | 4544402 | 59297491 | 54753089 | 4819702 | 59572791
EXTRA ITEMS |  |  |  |  | 0 | 275300 | 275300
A | HARDCAPING
i) | BOYS HOSTEL | 1090097 | 4374201 | 5464298 | 1090097 | 7212680 | 8302777
ii) | GIRLS HOSTEL | 548502 | 483543 | 1032045 | 548502 | 1124421 | 1672923
| TOTAL | 1638599 | 4857744 | 6496343 | 1638599 | 8337101 | 9975700
GRAND TOTAL |  | 56391688 | 9402146 | 65793834 | 56391688 | 13156803 | 69548491
[6 empty] | 3479357 | 3479357
|  | 0 | 1919065 |  | 0
2455136

## ABS BH (2)
THAPAR UNIVERSITY EXTENSION PROJECT, PATIALA
M/S. GANNON DUNKERLEY & CO. LTD.
RA Bill- | 06 (August'2017)
ABSTRACT - HARDSCAPING |  |  |  |  | "BOYS HOSTEL"
S.No. | DESCRIPTION | UNIT | QUANTITY | RATE | Previous Qty. | This Bill | Cummulative Qty. | Previous Amount | This Bill | Cummulative Amount
GROUND FLOOR
P.C.C
1 | Providing and laying in position under paving,driveways,floors,waterbodies,retaining walls,walls(of any thickness)and in planters,bed blocks etc. cement concrete of specified grade including the cost of centring and shuttering. (a) 1:4:8(1 cement:4 coarse sand:8 graded aggregate 40mm nominal size) as/ structural approval and relevant structural drawings. | Cum | 1283 | 4719 | 1624.9754 | 1.6746 | 1626.65 | 7668259 | 7902 | 7676161
HARDCORE
2 | Providing and laying 100 mm Hardcore sub-base with stome aggregate 63 to 40 mm size as per structural specification and approved binding material including cleaning ,sorting ,spreading, packing and consolidation with half tonne roller to template etc. complete | Cum | 733 | 2111 | 445.9684 | 0.0015877 | 445.97 | 941439 | 4 | 941443
BRICKWORK
3 | Brickwork with bricks of class designation 75 in foundations,plinth and superstructure in cement mortar 1:4(1 cement:4 coarse sand) (Quantity may vary as per actual drawings) | Cum | 190 | 5979 | 994.2142 | -0.044237 | 994.17 | 5944407 | -265 | 5944142
R.C.C
4 | Reinforcement for R.C.C. works including straightening, cutting , bending, placing in position and binding all complete. Cold twisted bars. | MT | 70 | 67995 | 33.79 | 0.133 | 33.923 | 2297821 | 8773 | 2306594
4 | Providing and laying in position ready mixed M-25 grade concrete for reinforced concrete works ,using cement content as per approved design mix manufactured in fully automatic batching plant and transported to site of work in transit mixers for all leads having continious agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete worksincluding pumping of R.M.C. from transit mixer to site of laying excluding the finishing and reinforcement including cost of admixture in recommende proportionas per IS:9103 to accelerate/retard setting of concrete , improve workability without imparing strength and durabilityas per direction of the chief enginner-in charge(min OPC contentto be considered in this item is 300kg/cum or as per design mix) | Cum | 697 | 7151 | 431.7307 | 3.1393 | 434.87 | 3087306 | 22449 | 3109755
WATERPROOFING
5 | Providing & Laying gunited sprayed concrete (40mm thk, minimum) in Waterbody areas. Consisting of mix 1:4 (1 cement : 4 coarse sand) over Chicken Wire Mesh of approved weight per sq.m. using appropriate: a) Cleaning the surface where gunited concrete is to be applied. b) Applying sprayed concrete. d) Finishing the surface with trowel to achieve smooth finish. | SQM | 763 | 1114 | 427.53 | 0 | 427.53 | 476268 | 0 | 476268
WBM LAYER IN FIRE TENDER AND DRIVEWAYS
6 | Supplying and laying sub base course ( water bound macadam) 100 m thick (consolidated thickness) with stone aggregate of size 93 to 45 mm including stone screening,sorting and consolidation with 8 to 10 tonne power road roller etc. and binding material complete all as specified by structural consultant. (Quantity may vary as per structural drawings) | Cum | 858 | 2111 | 1521.5115 | 0.0085391 | 1521.52 | 3211911 | 18 | 3211929
GEO TEXTILE AND DRAINCELL
7 | Providing & laying Drain Cell of 20mm thk. (Ovilite or similar item) composed of high density polythene (HDPE) & Joint to a non woven geotextile of calendered polypropylene of not less than 120g/sqm or equivalent. Joints to overlapping at Nodule height should not be less than 7.3+/-0.2mm | Cum | 980 | 469 |  | 348.23 | 348.23 | 0 | 163320 | 163320
PODIUM LEVEL
WATERPROOFING WORK
4 | Providing & Laying composite built up waterproofing under screed comprising og three coatsof tepecrete polymer, each coat admixed with cement in proportion 1:2 (one part Tepecrete & two parts cement) over a primer coat of neat cement slurry admixed with impermeable chemical CH-09. After the second coat of Tepecrete, all corners, sdges, joints of pipes with concrete/masonry should be seated with epoxy putty. 10mm thk. protective plaster 1:4 (1 cement 4 coarse sand) over treated surface etc. complete. (Quoted rate to include grouting of RCC surface for any cracks/ fissures & cost of grey cement.) (H+V) | SQM | 1391 | 703 | 630.005 | 0.005 | 630.01 | 442894 | 3 | 442897
BOYS HOSTEL-PODIUM LEVEL FINISHES
AGRA RED SANDSTONE- NATURAL FINISH (RAMP & PAVED AREAS)
1.1 | Providing & Fixing 40mm Natural Finish Red Agra Sandstone (Base Rate : 550) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | SQM | 640 | 1406 | 1959.6423 | 366.9277 | 2326.57 | 2618082 | 653075 | 3271157
AGRA RED SANDSTONE- HONED FINISH (IN PLAZZA, ALONG WITH BANDS)
1.2 | Providing & Fixing 40mm Honed Finish Red Agra Sandstone (Base Rate : 750) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | SQM | 1356 | 1759 | 728.759 | 0.001 | 728.76 | 1217756 | 64133 | 1281889
AGRA SANDSTONE- MACHINE CUT FINISH (PAVING BANDS, SEAT AND PLANTER WALL COPING AND CLADDING)
1.3 | Providing & Fixing Machine Cut Finish Agra Red stone machine 20MM THK.(Base rate Rs 550/Sqm) cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 20mm thk Machine Cut Finish Agra-Red Sand Stone (Base rate Rs 550/Sqm) (Planter Wall Cladding & seat Cladding) | SQM | 491 | 1348 | 523.4465 | 73.7635 | 597.21 | 670535 | 134504 | 805039
1.3 | Providing & Fixing Machine Cut 40 mm thk. Finish Agra Red stone machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 40 mm thk. Machine cut Finish Agra Red Sand Stone
| (Base rate Rs 550/Sqm) (Flooring & Seat Coping) | SQM | 413 | 1583 | 261.35 | 0 | 261.35 | 413717 | 0 | 413717
AGRA RED SANDSTONE- SERRATED FINISH (PAVING)
1.4 | Providing & Fixing Serrated Finish Agra Red stone (Base Rate Rs 750/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 20mm thk Machine Cut Finish Agra-Red Sand Stone (Base rate Rs 550/Sqm) (Planter Wall Cladding & seat Cladding) | SQM | 425 | 1817 | 384.23 | 0 | 384.23 | 663181 | 34965 | 698146
BOYS HOSTEL-GROUND FLOOR LEVEL FINISHES
NATURAL FINISH KANDLA GREY SANDSTONE (LARGE PAVED AREA, SEATINGS)
2.1 | Providing & Fixing 40mm natural Finish Kandla Grey Sand Stone (Base Rate Rs 900/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 40mm thk. Natural Finish Kadappa for Paving | SQM | 10886 | 2111 | 8299.48 | 582.18 | 8881.66 | 15769012 | 2980172 | 18749184
[6 empty] | 0 |  | 0 | 0 | 0
2.2 | Providing & Fixing 40mm Leather Finish Kadappa Stone (Base Rate Rs 2000/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels. | SQM | 415 | 4689 | 161.6 | 0 | 161.6 | 757742 | 0 | 757742
2.3 | Providing & Fixing 40mm Polished Kadappa Stone prepolished, machine cut of required size, ne cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels. 40mm thk. Polished finish Kadappa Stone (Base rate Rs 1750/Sqm) (Seater Coping) | SQM | 66 | 4455 | 36.66 | 0.97 | 37.63 | 163320 | 4322 | 167642
2.3 | Providing & Fixing 20mm Polished Finish Kadappa Stone prepolished, machine cut of required size, ne cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels. (Base rate Rs 1500/Sqm) (Waterbody Cladding & water body base) | SQM | 757 | 4103 | 389.93 | 6.97 | 396.9 | 1599883 | 28598 | 1628481
2.5 | Providing & Fixing in Position 40mm thk stone cover of size 600mm x 600mm as per design for catch basin fixed on Precast concrete with M.S. angle. | SQM | 22.68 | 3517 | 127.29 | 19.19 | 146.48 | 447679 | 67491 | 515170
6 | 12mm cement plaster in cement mortar 1:4 on wall etc. with all scaffolding | SQM | 410 | 234 | 21.7 | 0 | 21.7 | 5078 | 0 | 5078
0
| TOTAL AMOUNT (SCHEDULE) | [6 empty] | 48396290 | 4169464 | 52565754
| NON -SCHEDULED ITEMS | [6 empty] | 0 | 0 | 0
NS-01 | Excavation in all types of soil (Poclanable)for footings of columns, Retaining walls, Core walls, catch pits, Lift pits trenches for drains, etc., by mechanical means upto 2 m depth (Using JCB,Poclane etc.,)including levelling, dressing the edges,with all leads and lifts. Rate to include disposing the excess earth and spreading in layers to the required levels within the site wherever specified including watering, ramming,consolidating and dressing etc. working space shall be paid max 600mm extra. | Cum |  | 139 | 2106.33 | 14.32 | 2120.65 | 347544 | -52774 | 294770
NS-02 | Extra item for Supplying and filling in plinth with Ghagaar sand under floors , including watering ,ramming consolidating and dressing complete,as instructed by client. | Cum |  | 1025 | 0 | 812.48 | 812.48 | 0 | 832792 | 832792
NS-03 | Preparation and consolidation of sub grade wirh power r oad roller of8 to l 2 tonne capac ity, dressing to camber up to 225mm by excavation or filling and consolidating with road roller including making goon the undulations etc. | Sqm |  | 58 | 0 | 10795.98 | 10795.98 | 0 | 626167 | 626167
NS-04 | PROVIDING,ERECTING,FIXING IN POSITION AND STRIKING PLY WOOD SHUTTERING & CENTERING FOR FORM WORK IN PLANE,CURVES,SLOPES AT ALL LEVELS,HIGHTG & LOCATIONS FOR ALL SHAPES INCLUDING STRUTTING ,PROPPING AND REMOVAL OF THE SAME ETC, COMPLETE.PROVIDING AND APPLYING APPROVED FORM OIL ON ALL SURFACES OF FORM WORK COMIMG IN CONTACT WITH CONCRETE, COMLETE ASPER SPECEFICATIONS,DRAWING AND AS DIRECTED |  |  |  |  | 0 |  | 0 | 0 | 0
a | For base / raft of planter walls, tie on brick walls etc. all work for hardscape work | sqm | 1777.496 | 305 |  | 1273.5 | 1273.5 |  | 388418 | 388418
b | For side and bottom of seating slab edge,wall of planters etc | sqm | 444.374 | 451 |  | 1207.97 | 1207.97 |  | 544794 | 544794
c | extra over on above for circular surface work | sqm | 259.65 | [6 empty] | 0
| Footing, raft, stitching slab, pedestals,pile caps, etc. | Sqm. |  | 450 | 2062.646 | -2062.646 |  | 742553 | -742553 | 0
NS-05 | brick work with bricks of class designation 75 in (115mmthk.)foundation plinth and | [8 empty] | 0
a) | In Foundation & at Ground level up to 1.5 Mtr Height | Sqm |  | 688 | 0 | 57.4 | 57.4 | 0 | 39491 | 39491
b) | in superstructure above/ podium level | Sqm |  | 807 |  |  |  | 0 |  | 0
NS-06 | Demolishing of PCC (Grade 1:4:8 & Leaner)& Stone Soling including disposal of Malba with in site, all as per instruction of engineer in charge. | Sqm |  | 910 | 0 | 0 | 0 | 0 | 0 | 0
NS-07 | providing and fabricating & fixing structural steel work for manhole/chamber frame work using ms angle flat plate in required pattern asper drawing for different sizes including cost of cutting welding etc. all asper drawing or directed by engineer incharge | Kg |  | 95 | 0 | 9622.68 | 9622.68 | 0 | 914155 | 914155 | 114.4578
NS-08 | Providing & Fixing 230mm long upvc 75mm OD pipe for sleeve in planters including cutting hole in wall, making good with rich cement sand mortar etc. all complete as directed by engineer in charge. | Rmt |  | 268 | 0 | 98 | 98 | 0 | 26264 | 26264
NS-09 | Making hole of different size & shape, by stone cutter machine in stone flooring/cladding for fixing electrical fixtures, passing conduits & wires and making good after fixing fixtures etc. all complete as directed by engineer in charge. | Each |  | 159 | 0 | 717 | 717 | 0 | 114003 | 114003 | 308.1928
NS-10 | Extra over item no. 3.0 for Round, Circular Brick Work with bricks of class designation 75 in foundation, plinth & superstructure in: cement mortar 1:6 (1cement : 6 coarse sand). | Cum |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
NS-13 | Chamfering of edge in stone work wherever required in seating work cladding work etc. in white marble ,kandla grey and kadappa stone | Rmt |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.5542
NS-14 | Making of Groove in Stone wherever required in seating work,cladding work etc. in red sand stone | Rmt |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 267.4096
NS-16 | Extra over on item No. 2.1 for Extra wastage due to Special shape in paving of Kandla Grey Stone. | Sqm |  | 183 | 0 | 8881.66 | 8881.66 | 0 | 1625344 | 1625344
NS-17 | Extra over on item No. 2.3 for Extra wastage due to Special shape in paving of Kadappa Stone. | Sqm |  | 149 | 0 | 389.93 | 389.93 | 0 | 58100 | 58100
0
E.I. 15 | Providing and fixing special type of approved centering, shuttering and scaffolding to produce Foam Finish for exposed concrete surfaces for Columns and Shear Walls. | Sqm. |  | 850 | 0 | 0 |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
E.I.07 | Extra for shuttering in circular work (20% of respective centering and shuttering items) Ref. from D.A.R. Item no. 5.9.14 | Sqm |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E.I. 33 | Backfilling with selected, suitable excavated from outside or adjacent plots in plinths, back of retaining walls, foundations, under floors and trenches and spreading the remaining soil for specified location as directed by the Project Manager and shall be done in layers, not exceeding 20cm in depth and consolidating each deposited layer by mechanical means, ramming and watering till 95% compaction is achieved or as per specifications including re-excavation, transportation, loading, unloading, carriage to dumping spot and all incidentals at all depth, levels, leads and lifts complete. (Net consolidated area fill volume will be computed from the initial and final levels.) | Sqm |  | 210.68 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 |  | 0
[8 empty] | 0 | 0 | 0
| TOTAL AMT (NON SCHEDULE) | [6 empty] | 1090097 | 4374201 | 5464298
[6 empty] | 0 | GRAND `TOTAL | 49486387 | 8543665 | 58030052

## ABS BH (hidden)
THAPAR UNIVERSITY EXTENSION PROJECT, PATIALA
M/S. GANNON DUNKERLEY & CO. LTD.
RA Bill- | 06 (August'2017)
ABSTRACT - HARDSCAPING |  |  |  |  | "BOYS HOSTEL"
S.No. | DESCRIPTION | UNIT | QUANTITY | RATE | Previous Qty. | This Bill | Cummulative Qty. | Previous Amount | This Bill | Cummulative Amount
GROUND FLOOR | [5 empty] | 0
P.C.C | [5 empty] | 0 |  | 0 | 0 | 0
1 | Providing and laying in position under paving,driveways,floors,waterbodies,retaining walls,walls(of any thickness)and in planters,bed blocks etc. cement concrete of specified grade including the cost of centring and shuttering. (a) 1:4:8(1 cement:4 coarse sand:8 graded aggregate 40mm nominal size) as/ structural approval and relevant structural drawings. | Cum | 1283 | 4719 | 1624.9754 | 1.6746 | 1626.65 | 7668259 | 7902 | 7676161
HARDCORE | [5 empty] | 0 |  | 0 | 0 | 0
2 | Providing and laying 100 mm Hardcore sub-base with stome aggregate 63 to 40 mm size as per structural specification and approved binding material including cleaning ,sorting ,spreading, packing and consolidation with half tonne roller to template etc. complete | Cum | 733 | 2111 | 445.9684 | 0.0015877 | 445.97 | 941439 | 4 | 941443
BRICKWORK | [7 empty] | 0
3 | Brickwork with bricks of class designation 75 in foundations,plinth and superstructure in cement mortar 1:4(1 cement:4 coarse sand) (Quantity may vary as per actual drawings) | Cum | 190 | 5979 | 994.2142 | -0.044237 | 994.17 | 5944407 | -265 | 5944142
R.C.C | [5 empty] | 0 |  | 0 | 0 | 0
4 | Reinforcement for R.C.C. works including straightening, cutting , bending, placing in position and binding all complete. Cold twisted bars. | MT | 70 | 67995 | 33.79 | 0.133 | 33.923 | 2297551 | 9043 | 2306594
[6 empty] | 0 |  | 0
4 | Providing and laying in position ready mixed M-25 grade concrete for reinforced concrete works ,using cement content as per approved design mix manufactured in fully automatic batching plant and transported to site of work in transit mixers for all leads having continious agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete worksincluding pumping of R.M.C. from transit mixer to site of laying excluding the finishing and reinforcement including cost of admixture in recommende proportionas per IS:9103 to accelerate/retard setting of concrete , improve workability without imparing strength and durabilityas per direction of the chief enginner-in charge(min OPC contentto be considered in this item is 300kg/cum or as per design mix) | Cum | 697 | 7151 | 431.7307 | 3.1393 | 434.87 | 3087306 | 22449 | 3109755
WATERPROOFING | [5 empty] | 0 |  | 0 | 0 | 0
5 | Providing & Laying gunited sprayed concrete (40mm thk, minimum) in Waterbody areas. Consisting of mix 1:4 (1 cement : 4 coarse sand) over Chicken Wire Mesh of approved weight per sq.m. using appropriate: a) Cleaning the surface where gunited concrete is to be applied. b) Applying sprayed concrete. d) Finishing the surface with trowel to achieve smooth finish. | SQM | 763 | 1114 | 427.53 | 0 | 427.53 | 476268 | 0 | 476268
WBM LAYER IN FIRE TENDER AND DRIVEWAYS | [5 empty] | 0 |  | 0 | 0 | 0
6 | Supplying and laying sub base course ( water bound macadam) 100 m thick (consolidated thickness) with stone aggregate of size 93 to 45 mm including stone screening,sorting and consolidation with 8 to 10 tonne power road roller etc. and binding material complete all as specified by structural consultant. (Quantity may vary as per structural drawings) | Cum | 858 | 2111 | 1521.5115 | 0.0085391 | 1521.52 | 3211911 | 18 | 3211929
GEO TEXTILE AND DRAINCELL | [5 empty] | 0 |  | 0 | 0 | 0
7 | Providing & laying Drain Cell of 20mm thk. (Ovilite or similar item) composed of high density polythene (HDPE) & Joint to a non woven geotextile of calendered polypropylene of not less than 120g/sqm or equivalent. Joints to overlapping at Nodule height should not be less than 7.3+/-0.2mm | Cum | 980 | 469 |  | 348.23 | 348.23 | 0 | 163320 | 163320
PODIUM LEVEL | [5 empty] | 0 |  | 0
WATERPROOFING WORK |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Providing & Laying composite built up waterproofing under screed comprising og three coatsof tepecrete polymer, each coat admixed with cement in proportion 1:2 (one part Tepecrete & two parts cement) over a primer coat of neat cement slurry admixed with impermeable chemical CH-09. After the second coat of Tepecrete, all corners, sdges, joints of pipes with concrete/masonry should be seated with epoxy putty. 10mm thk. protective plaster 1:4 (1 cement 4 coarse sand) over treated surface etc. complete. (Quoted rate to include grouting of RCC surface for any cracks/ fissures & cost of grey cement.) (H+V) | SQM | 1391 | 703 | 630.005 | 0.005 | 630.01 | 442894 | 3 | 442897
BOYS HOSTEL-PODIUM LEVEL FINISHES | [5 empty] | 0 |  | 0
AGRA RED SANDSTONE- NATURAL FINISH (RAMP & PAVED AREAS) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Providing & Fixing 40mm Natural Finish Red Agra Sandstone (Base Rate : 550) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | SQM | 640 | 1406 | 1959.6423 | 366.9277 | 2326.57 | 2618082 | 653075 | 3271157
0
AGRA RED SANDSTONE- HONED FINISH (IN PLAZZA, ALONG WITH BANDS) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Providing & Fixing 40mm Honed Finish Red Agra Sandstone (Base Rate : 750) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | SQM | 1356 | 1759 | 728.759 | 0.001 | 728.76 | 1217756 | 64133 | 1281889
0
AGRA SANDSTONE- MACHINE CUT FINISH (PAVING BANDS, SEAT AND PLANTER WALL COPING AND CLADDING) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Providing & Fixing Machine Cut Finish Agra Red stone machine 20MM THK.(Base rate Rs 550/Sqm) cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 20mm thk Machine Cut Finish Agra-Red Sand Stone (Base rate Rs 550/Sqm) (Planter Wall Cladding & seat Cladding) | SQM | 491 | 1348 | 523.4465 | 73.7635 | 597.21 | 670535 | 134504 | 805039
[6 empty] | 0 |  | 0 | 0 | 0
1.3 | Providing & Fixing Machine Cut 40 mm thk. Finish Agra Red stone machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 40 mm thk. Machine cut Finish Agra Red Sand Stone |  |  |  |  | 0 |  | 0 | 0 | 0
| (Base rate Rs 550/Sqm) (Flooring & Seat Coping) | SQM | 413 | 1583 | 261.35 | 0 | 261.35 | 413717 | 0 | 413717
0
AGRA RED SANDSTONE- SERRATED FINISH (PAVING) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Providing & Fixing Serrated Finish Agra Red stone (Base Rate Rs 750/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 20mm thk Machine Cut Finish Agra-Red Sand Stone (Base rate Rs 550/Sqm) (Planter Wall Cladding & seat Cladding) | SQM | 425 | 1817 | 384.23 | 0 | 384.23 | 663181 | 34965 | 698146
0
BOYS HOSTEL-GROUND FLOOR LEVEL FINISHES | [5 empty] | 0 |  | 0
NATURAL FINISH KANDLA GREY SANDSTONE (LARGE PAVED AREA, SEATINGS) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Providing & Fixing 40mm natural Finish Kandla Grey Sand Stone (Base Rate Rs 900/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 40mm thk. Natural Finish Kadappa for Paving | SQM | 10886 | 2111 | 8299.48 | 582.18 | 8881.66 | 15769012 | 2980172 | 18749184
[6 empty] | 0 |  | 0 | 0 | 0
2.2 | Providing & Fixing 40mm Leather Finish Kadappa Stone (Base Rate Rs 2000/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels. | SQM | 415 | 4689 | 161.6 | 0 | 161.6 | 757742 | 0 | 757742
2.3 | Providing & Fixing 40mm Polished Kadappa Stone prepolished, machine cut of required size, ne cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels. 40mm thk. Polished finish Kadappa Stone (Base rate Rs 1750/Sqm) (Seater Coping) | SQM | 66 | 4455 | 36.66 | 0.97 | 37.63 | 163320 | 4322 | 167642
2.3 | Providing & Fixing 20mm Polished Finish Kadappa Stone prepolished, machine cut of required size, ne cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels. (Base rate Rs 1500/Sqm) (Waterbody Cladding & water body base) | SQM | 757 | 4103 | 389.93 | 6.97 | 396.9 | 1599883 | 28598 | 1628481
2.5 | Providing & Fixing in Position 40mm thk stone cover of size 600mm x 600mm as per design for catch basin fixed on Precast concrete with M.S. angle. | SQM | 22.68 | 3517 | 127.29 | 19.19 | 146.48 | 447679 | 67491 | 515170
6 | 12mm cement plaster in cement mortar 1:4 on wall etc. with all scaffolding | SQM | 410 | 234 | 21.7 | 0 | 21.7 | 5078 | 0 | 5078
0
| TOTAL AMOUNT (SCHEDULE) | [6 empty] | 48396020 | 4169734 | 52565754
| NON -SCHEDULED ITEMS | [6 empty] | 0 | 0 | 0
NS-01 | Excavation in all types of soil (Poclanable)for footings of columns, Retaining walls, Core walls, catch pits, Lift pits trenches for drains, etc., by mechanical means upto 2 m depth (Using JCB,Poclane etc.,)including levelling, dressing the edges,with all leads and lifts. Rate to include disposing the excess earth and spreading in layers to the required levels within the site wherever specified including watering, ramming,consolidating and dressing etc. working space shall be paid max 600mm extra. | Cum |  | 139 | 2106.33 | 14.32 | 2120.65 | 347544 | -52774 | 294770
NS-04 | PROVIDING,ERECTING,FIXING IN POSITION AND STRIKING PLY WOOD SHUTTERING & CENTERING FOR FORM WORK IN PLANE,CURVES,SLOPES AT ALL LEVELS,HIGHTG & LOCATIONS FOR ALL SHAPES INCLUDING STRUTTING ,PROPPING AND REMOVAL OF THE SAME ETC, COMPLETE.PROVIDING AND APPLYING APPROVED FORM OIL ON ALL SURFACES OF FORM WORK COMIMG IN CONTACT WITH CONCRETE, COMLETE ASPER SPECEFICATIONS,DRAWING AND AS DIRECTED |  |  |  |  | 0 |  | 0 | 0 | 0
a | For base / raft of planter walls, tie on brick walls etc. all work for hardscape work | sqm | 1777.496 | 305 |  | 1273.5 | 1273.5 |  | 388418 | 388418
b | For side and bottom of seating slab edge,wall of planters etc | sqm | 444.374 | 451 |  | 1207.97 | 1207.97 |  | 544794 | 544794
c | extra over on above for circular surface work | sqm | 259.65
| Footing, raft, stitching slab, pedestals,pile caps, etc. | Sqm. |  | 450 | 2062.646 | 418.824 | 2481.47 | 742553 | 374109 | 1116662
|  |  |  | -450 |  |  | 2011.076 | 0 | -904984 | -904984
E.I.03 | Suspended floors, roofs, landings balconies, access platform, Lintels, beams, plinth beams, girders, bressumers, Stairs, cantilevers (excluding landing) except spiral staircases.etc | Sqm. |  | 0 | 1.6342e-13 | #REF! | #REF! | 0 | #REF! | #REF!
[5 empty] | 0 | #REF! | #REF! | 0 | #REF! | #REF!
E.I. 15 | Providing and fixing special type of approved centering, shuttering and scaffolding to produce Foam Finish for exposed concrete surfaces for Columns and Shear Walls. | Sqm. |  | 850 | 0 | #REF! | #REF! | 0 | #REF! | #REF!
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
NS-10 | Extra over item no. 3.0 for Round, Circular Brick Work with bricks of class designation 75 in foundation, plinth & superstructure in: cement mortar 1:6 (1cement : 6 coarse sand). | Cum |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
E.I.07 | Extra for shuttering in circular work (20% of respective centering and shuttering items) Ref. from D.A.R. Item no. 5.9.14 | Sqm |  | 110.39 | 0 | #REF! | #REF! | 0 | #REF! | #REF!
0
NS-03 | Preparation and consolidation of sub grade wirh power r oad roller of8 to l 2 tonne capac ity, dr·essing to camber and consolidat ing with road roller inclu ding making good the undulati ons etc. | Sqm |  | 58 | 0 | 10795.98 | 10795.98 | 0 | 626167 | 626167
0
NS-06 | Demolishing of PCC (Grade 1:4:8 & Leaner)& Stone Soling including disposal of Malba with in site, all as per instruction of engineer in charge. | Sqm |  | 910 | 0 | 0 | 0 | 0 | 0 | 0
0
NS-05 | Providing and constructing half brick masonry work using selected quality burnt clay FPS brick of class designation 75 in superstructure laid in cement mortar 1:4(1 cement : 4 sand) mix joints finished flush/ racked to 6mm depth and including required scaffolding curing complete asper specification and drawing or as directed by client
a) | In Foundation & at Ground level up to 1.5 Mtr Height | Sqm |  | 688 | 0 | 57.4 | 57.4 | 0 | 39491 | 39491
b) | in superstructure above/ podium level | Sqm |  | 807 |  |  |  | 0
NS-16 | Extra over on item No. 2.1 for Extra wastage due to Special shape in paving of Kandla Grey Stone. | Sqm |  | 183 | 0 | 8881.66 | 8881.66 | 0 | 1625344 | 1625344
0
NS-17 | Extra over on item No. 2.3 for Extra wastage due to Special shape in paving of Kadappa Stone. | Sqm |  | 149 | 0 | 389.93 | 389.93 | 0 | 58100 | 58100
0
NS-18 | MS Tray Square, 6mm thk. | Kg |  | 95 | 0 | 9622.68 | 9622.68 | 0 | 914155 | 914155 | 114.4578
0
NS 19 | MS Tray Square 6mm thk. (with slot) | Kg |  | 95 | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 114.4578
0
NS-09 | Making hole of different size & shape, by stone cutter machine in stone flooring/cladding for fixing electrical fixtures, passing conduits & wires and making good after fixing fixtures etc. all complete as directed by engineer in charge. | Each |  | 159 | 0 | 717 | 717 | 0 | 114003 | 114003 | 308.1928
0
NS-13 | Champhering at Edges | Rmt |  | 188.55 | 0 | 0 | 0 | 0 | 0 | 0 | 188.5542
0
NS-14 | Making of Groove in Stone wherever required in seating work,cladding work etc. in red sand stone | Rmt |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 267.4096
0
NS-08 | Providing & Fixing 230mm long upvc 75mm OD pipe for sleeve in planters including cutting hole in wall, making good with rich cement sand mortar etc. all complete as directed by engineer in charge. | Rmt |  | 268 | 0 | 98 | 98 | 0 | 26264 | 26264
0
E.I. 33 | Backfilling with selected, suitable excavated from outside or adjacent plots in plinths, back of retaining walls, foundations, under floors and trenches and spreading the remaining soil for specified location as directed by the Project Manager and shall be done in layers, not exceeding 20cm in depth and consolidating each deposited layer by mechanical means, ramming and watering till 95% compaction is achieved or as per specifications including re-excavation, transportation, loading, unloading, carriage to dumping spot and all incidentals at all depth, levels, leads and lifts complete. (Net consolidated area fill volume will be computed from the initial and final levels.) | Sqm |  | 210.68 | 0 | 0 | 0 | 0 | 0 | 0
0
NS-02 | Extra item for Supplying and filling in plinth with Ghagaar sand under floors , including watering ,ramming consolidating and dressing complete,as instructed by client. | Sqm |  | 1025 | 0 | 812.48 | 812.48 | 0 | 832792 | 832792
[8 empty] | 0 | 0 | 0
| TOTAL AMT (NON SCHEDULE) | [6 empty] | 1090097 | #REF! | #REF!
[6 empty] | 0 | GRAND `TOTAL | 49486117 | #REF! | #REF!

## ABS GH (2)
THAPAR UNIVERSITY EXTENSION PROJECT, PATIALA
M/S. GANNON DUNKERLEY & CO. LTD.
RA Bill- | 06 (August'2017)
ABSTRACT - HARDSCAPING |  |  |  |  | "GIRLS HOSTEL"
S.No. | DESCRIPTION | UNIT | QUANTITY | RATE | Previous Qty. | This Bill | Cummulative Qty. | Previous Amount | This Bill | Cummulative Amount
0
2 | Providing and laying in position ready mixed M-25 grade concrete for reinforced concrete works ,using cement content as per approved design mix manufactured in fully automatic batching plant and transported to site of work in transit mixers for all leads having continious agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete worksincluding pumping of R.M.C. from transit mixer to site of laying excluding the finishing and reinforcement including cost of admixture in recommende proportionas per IS:9103 to accelerate/retard setting of concrete , improve workability without imparing strength and durabilityas per direction of the chief enginner-in charge(min OPC contentto be considered in this item is 300kg/cum or as per design mix) | Cum | 14 | 7151 | 28.95 | 0 | 28.95 | 207021 | 0 | 207021
[6 empty] | 0 |  | 0 | 0 | 0
2 | Reinforcement for R.C.C. works including straightening, cutting , bending, placing in position and binding all complete. Cold twisted bars. | MT | 1.4 | 67995 | 3.31 | 0 | 3.31 | 225063 | 0 | 225063
[6 empty] | 0 |  | 0 |  | 0
3 | Providing and laying in position cement concrete of specified grade, 1:4:8 (1 Cement: 4 coarse sand: 8 graded stone aggregate 40mm nominal size) | Cum | 136 | 4719 | 151.63 | 0 | 151.63 | 715542 | 0 | 715542
[8 empty] | 0 |  | 0
4 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation, plinth, superstructure above plinth level up to floor V level in all shapes & sizes with cement mortar 1:4 (1 cement : 4 course sand) | Cum | 68 | 6154 | 122.93 | 0 | 122.93 | 756511 | 0 | 756511
[8 empty] | 0 |  | 0
5 | Providing & Laying gunited sprayed concrete (40mm thk, minimum) in Waterbody areas. Consisting of mix 1:4 (1 cement : 4 coarse sand) over Chicken Wire Mesh of approved weight per sq.m. using appropriate: a) Cleaning the surface where gunited concrete is to be applied. b) Applying sprayed concrete. d) Finishing the surface with trowel to achieve smooth finish. | Sqm | 55 | 1114 | 135.54 | 0 | 135.54 | 150992 | 0 | 150992
[8 empty] | 0 |  | 0
1.1 | Providing & Fixing 40mm Natural Finish Red Agra Sandstone (Base Rate : 550) machine cut of required size, approved shade, colour & Texture laid over 20mm thick base cement mortar 1:4 (1cement : 4 coarse sand), Joints treated with white cement, mixed with matching pigment, epoxy touch ups etc. complete at all levels. | Sqm | 458 | 1406 | 466.464 | 2.386 | 468.85 | 623196 | 36007 | 659203
[8 empty] | 0 |  | 0
1.2 | Providing & Fixing 40/20mm 100mm x 10mm Polished Finish White Marble Cobbles (Base Rate : 1500) Pre-polished, machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | Sqm | 686 | 3517 | 750.7 | 0 | 750.7 | 2508089 | 132123 | 2640212
[8 empty] | 0 |  | 0
1.3 | Providing & Fixing 40/20mm Sawn Finish White Marble (Base Rate : 1200) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | Sqm | 198 | 3165 | 389.22 | 34 | 423.22 | 1170385 | 169106 | 1339491
[8 empty] | 0 |  | 0
1.6 | Providing & Fixing in Position 40mm thk stone cover of size 600mm x 600mm as per design for catch basin fixed on Precast concrete with M.S. angle. | Sqm | 1.44 | 3517 |  | 10.72 | 10.72 | 0 | 37702 | 37702
[8 empty] | 0 |  | 0
| TOTAL AMT (SCHEDULE) | [6 empty] | 6356799 | 374938 | 6731737 | 311198.54
| NON -SCHEDULED ITEMS | [6 empty] | 0 | 0 | 0
NS-01 | Excavation in all types of soil (Poclanable)for footings of columns, Retaining walls, Core walls, catch pits, Lift pits trenches for drains, etc., by mechanical means upto 2 m depth (Using JCB,Poclane etc.,)including levelling, dressing the edges,with all leads and lifts. Rate to include disposing the excess earth and spreading in layers to the required levels within the site wherever specified including watering, ramming,consolidating and dressing etc. working space shall be paid max 600mm extra. | Cum |  | 139 | 331.59 | 0 | 331.59 | 54712 | -8621 | 46091
[8 empty] | 0 |  | 0
NS-03 | Preparation and consolidation of sub grade wirh power r oad roller of8 to l 2 tonne capac ity, dressing to camber up to 225mm by excavation or filling and consolidating with road roller including making goon the undulations etc. | Sqm |  | 58 | 0 | 1397.21 | 1397.21 | 0 | 81038 | 81038
NS-04 | PROVIDING,ERECTING,FIXING IN POSITION AND STRIKING PLY WOOD SHUTTERING & CENTERING FOR FORM WORK IN PLANE,CURVES,SLOPES AT ALL LEVELS,HIGHTG & LOCATIONS FOR ALL SHAPES INCLUDING STRUTTING ,PROPPING AND REMOVAL OF THE SAME ETC, COMPLETE.PROVIDING AND APPLYING APPROVED FORM OIL ON ALL SURFACES OF FORM WORK COMIMG IN CONTACT WITH CONCRETE, COMLETE ASPER SPECEFICATIONS,DRAWING AND AS DIRECTED |  |  |  |  | 0 |  | 0 | 0 | 0
a | For base / raft of planter walls, tie on brick walls etc. all work for hardscape work | sqm | 1777.496 | 305 |  | 125.86 | 125.86 | 0 | 38387 | 38387
b | For side and bottom of seating slab edge,wall of planters etc | sqm | 444.374 | 451 |  | 17.06 | 17.06 | 0 | 7694 | 7694
c | extra over on above for circular surface work | sqm | 259.65 | [6 empty] | 0
E.I.02 | Footing, raft, stitching slab, pedestals,pile caps, etc., | Sqm. |  | 450 | 142.92 | -142.92 | 0 | 51451 | -51451 | 0
NS-07 | providing and fabricating & fixing structural steel work for manhole/chamber frame work using ms angle flat plate in required pattern asper drawing for different sizes including cost of cutting welding etc. all asper drawing or directed by engineer incharge | Kg |  | 95 | 0 | 439.25 | 439.25 | 0 | 41729 | 41729 | 114.4578
NS-09 | Making hole of different size & shape, by stone cutter machine in stone flooring/cladding for fixing electrical fixtures, passing conduits & wires and making good after fixing fixtures etc. all complete as directed by engineer in charge. | Each |  | 159 | 0 | 576 | 576 | 0 | 91584 | 91584 | 114.4578
NS-10 | Extra over item no. 3.0 for Round, Circular Brick Work with bricks of class designation 75 in foundation, plinth & superstructure in: cement mortar 1:6 (1cement : 6 coarse sand). | CUM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304.8193
NS-12 | Extra over on white marble work in pave area for circular stone work for extra wastage extra labour | Sqm. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
NS-13 | Chamfering of edge in stone work wherever required in seating work cladding work etc. in white marble ,kandla grey and kadappa stone | Rmt |  | 188.55 | 0 | 0 | 0 | 0 | 0 | 0 | 188.5542
NS-14 | Making of Groove in Stone wherever required in seating work,cladding work etc. in red sand stone | Rmt |  | 267.4 | 0 | 0 | 0 | 0 | 0 | 0 | 267.4096
NS-15 | Providing & Fixing 20mm thick Polish finish Lakha Red, machine cut of required size, approved shade, colour, texture laid over 20mm 1:4 cement sand mortar for Cladding & flooring etc. all complete as directed by engineer in charge. | Sqm. |  | 5332 | 0 | 53.11 | 53.11 | 0 | 283183 | 283183 | 6424.0964
E.I.07 | Extra for shuttering in circular work (20% of respective centering and shuttering items) Ref. from D.A.R. Item no. 5.9.14 | Sqm. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Item reference BOYS HOSTEL-LANDSCAPE DEVELOPMENT CIVIL WORKS |  |  |  |  | 0 | 0 |  |  |  | 0
6 | Supplying and laying sub base course (water bound macadam) 100 m thick (consolidated thickness) with stone aggregate of size 93 to 45 mm including stone screening,sorting and consolidation with 8 to 10 tonne power road roller etc. and binding material complete all as specified by structural consultant. (Quantity may vary as per structural drawings) | Cum |  | 2111 | 209.54 | 0 | 209.54 | 442339 | 0 | 442339
| TOTAL AMT (NON SCHEDULE) | [6 empty] | 548502 | 483543 | 1032045
[6 empty] | 0 | GRAND `TOTAL | 6905301 | 858481 | 7763782
[7 empty] | 3620 | 434.4 | 917018.4

## ABS GH (hidden)
THAPAR UNIVERSITY EXTENSION PROJECT, PATIALA
M/S. GANNON DUNKERLEY & CO. LTD.
RA Bill- | 06 (August'2017)
ABSTRACT - HARDSCAPING |  |  |  |  | "GIRLS HOSTEL"
S.No. | DESCRIPTION | UNIT | QUANTITY | RATE | Previous Qty. | This Bill | Cummulative Qty. | Previous Amount | This Bill | Cummulative Amount
0
2 | Providing and laying in position ready mixed M-25 grade concrete for reinforced concrete works ,using cement content as per approved design mix manufactured in fully automatic batching plant and transported to site of work in transit mixers for all leads having continious agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete worksincluding pumping of R.M.C. from transit mixer to site of laying excluding the finishing and reinforcement including cost of admixture in recommende proportionas per IS:9103 to accelerate/retard setting of concrete , improve workability without imparing strength and durabilityas per direction of the chief enginner-in charge(min OPC contentto be considered in this item is 300kg/cum or as per design mix) | Cum | 14 | 7151 | 28.95 | 0 | 28.95 | 207021 | 0 | 207021
[6 empty] | 0 |  | 0 | 0 | 0
2 | Reinforcement for R.C.C. works including straightening, cutting , bending, placing in position and binding all complete. Cold twisted bars. | MT | 1.4 | 67995 | 3.31 | 0 | 3.31 | 225063 | 0 | 225063
[6 empty] | 0 |  | 0
3 | Providing and laying in position cement concrete of specified grade, 1:4:8 (1 Cement: 4 coarse sand: 8 graded stone aggregate 40mm nominal size) | Cum | 136 | 4719 | 151.63 | 0 | 151.63 | 715542 | 0 | 715542
0
4 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation, plinth, superstructure above plinth level up to floor V level in all shapes & sizes with cement mortar 1:4 (1 cement : 4 course sand) | Cum | 68 | 6154 | 122.93 | 0 | 122.93 | 756511 | 0 | 756511
0
5 | Providing & Laying gunited sprayed concrete (40mm thk, minimum) in Waterbody areas. Consisting of mix 1:4 (1 cement : 4 coarse sand) over Chicken Wire Mesh of approved weight per sq.m. using appropriate: a) Cleaning the surface where gunited concrete is to be applied. b) Applying sprayed concrete. d) Finishing the surface with trowel to achieve smooth finish. | Sqm | 55 | 1114 | 135.54 | 0 | 135.54 | 150992 | 0 | 150992
0
1.1 | Providing & Fixing 40mm Natural Finish Red Agra Sandstone (Base Rate : 550) machine cut of required size, approved shade, colour & Texture laid over 20mm thick base cement mortar 1:4 (1cement : 4 coarse sand), Joints treated with white cement, mixed with matching pigment, epoxy touch ups etc. complete at all levels. | Sqm | 458 | 1406 | 466.464 | 2.386 | 468.85 | 623196 | 36007 | 659203
0
1.2 | Providing & Fixing 40/20mm 100mm x 10mm Polished Finish White Marble Cobbles (Base Rate : 1500) Pre-polished, machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | Sqm | 686 | 3517 | 750.7 | 0 | 750.7 | 2508089 | 132123 | 2640212
0
1.3 | Providing & Fixing 40/20mm Sawn Finish White Marble (Base Rate : 1200) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. | Sqm | 198 | 3165 | 389.22 | 34 | 423.22 | 1170385 | 169106 | 1339491
0
1.6 | Providing & Fixing in Position 40mm thk stone cover of size 600mm x 600mm as per design for catch basin fixed on Precast concrete with M.S. angle. | Sqm | 1.44 | 3517 |  | 10.72 | 10.72 | 0 | 37702 | 37702
0
| TOTAL AMT (SCHEDULE) | [6 empty] | 6356799 | 374938 | 6731737 | 311198.54
| NON -SCHEDULED ITEMS | [6 empty] | 0 | 0 | 0
| Excavation in all types of soil (Poclanable)for footings of columns, Retaining walls, Core walls, catch pits, Lift pits trenches for drains, etc., by mechanical means upto 2 m depth (Using JCB,Poclane etc.,)including levelling, dressing the edges, with all leads and lifts including back filling in layers of 150mm with watering and compaction. Rate to include disposing the excess earth and spreading in layers to the required levels within the site wherever specified including watering, ramming , consolidating and dressing etc. working space shall be paid max 600mm extra | [6 empty] | 0 | 0 | 0
E.I. 29 | Up to or all kinds of soil below existing excavated level as handed over to the contractor by the Project-in-charge. | Cum |  | 139 | 331.59 | 0 | 331.59 | 54712 | -8621 | 46091
0
| Providing, erecting, fixing in position and striking ply wood shuttering & centering for form work in plane / slopes at all levels, heights & locations for all shapes including strutting, proping, chamfers, splays, keys, wedges, props, bracings, bolting, brackets, cuttings holes for pipes and removal of the same etc.,complete. allow for forming grooves, drops, throats, arrises, chamfers, cutouts, openings, G.I sleeves etc. wherever called for. Providing and applying approved form oil on all surfaces of form work coming in contact with concrete including close hacking of all exposed concrete work after removal of form work all materials, fixing nosing angles, switch boxes, labour etc. complete as per specifications, drawings and as directed.(Area of form work in contact with concrete shall only be measured for payment & stop boards for construction joints will not be measured for payment).Unexposed concrete surface subsequently left untreated (in the condition obtained on removal of form work) shall not constitute exposed concrete work and shall be measured under this item only. | [6 empty] | 0 | 0 | 0
E.I.02 | Footing, raft, stitching slab, pedestals,pile caps, etc., | Sqm. |  | 450 | 142.92 | 0 | 142.92 | 51451 | 12863 | 64314
[5 empty] | 0 | 0 |  | 0 | 0 | 0
NS-03 | Preparation and consolidation of sub grade with power road roller of 8 to 12 tonne capacity, dressing to camber up to 225mm by excavation or filling and consolidating with road roller including making good the undulations etc. | Sqm |  | 58 | 0 | 1397.21 | 1397.21 | 0 | 81038 | 81038
0
E.I.06 | Extra over item no. 3.0 for Round, Circular Brick Work with bricks of class designation 75 in foundation, plinth & superstructure in: cement mortar 1:6 (1cement : 6 coarse sand). | CUM |  | 1304 | 0 | 0 | 0 | 0 | 0 | 0 | 1304.8193
[8 empty] | 0 | 0 | 0
E.I.07 | Extra for shuttering in circular work (20% of respective centering and shuttering items) Ref. from D.A.R. Item no. 5.9.14 | Sqm. |  | 120 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
NS-12 | Extra over on white marble work in pave area for circular stone work for extra wastage extra labour | Sqm. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
NS-15 | Providing & Fixing 20mm thick Polish finish Lakha Red, machine cut of required size, approved shade, colour, texture laid over 20mm 1:4 cement sand mortar for Cladding & flooring etc. all complete as directed by engineer in charge. | Sqm. |  | 5332 | 0 | 53.11 | 53.11 | 0 | 283183 | 283183 | 6424.0964
NS-18 | MS Tray Square, 6mm thk. | Kg |  | 95 | 0 | 439.25 | 439.25 | 0 | 41729 | 41729 | 114.4578
0
NS 19 | MS Tray Square 6mm thk. (with slot) | Kg |  | 95 | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 114.4578
0
NS-09 | Making hole of different size & shape, by stone cutter machine in stone flooring/cladding for fixing electrical fixtures, passing conduits & wires and making good after fixing fixtures etc. all complete as directed by engineer in charge. | Each |  | 299.28 | 0 | 576 | 576 | 0 | 172385 | 172385 | 114.4578
0
NS 21 | Champhering at Edges | Rmt |  | 188.55 | 0 | 0 | 0 | 0 | 0 | 0 | 188.5542
0
NS 23 | Extra for Material wastage for Circular Stone in White Marbles | Rmt |  | 844.4 | 0 | 0 | 0 | 0 | 0 | 0 | 844.4819
0
NS 22 | Making of Groove in Stone Cladding for Architectural Appreance as per direction of Engineer in Charge | Rmt |  | 267.4 | 0 | 0 | 0 | 0 | 0 | 0 | 267.4096
0
Item reference BOYS HOSTEL-LANDSCAPE DEVELOPMENT CIVIL WORKS |  |  |  |  | 0 | 0
6 | Supplying and laying sub base course ( water bound macadam) 100 m thick (consolidated thickness) with stone aggregate of size 93 to 45 mm including stone screening,sorting and consolidation with 8 to 10 tonne power road roller etc. and binding material complete all as specified by structural consultant. (Quantity may vary as per structural drawings) | Cum |  | 2111 | 209.54 | 0 | 209.54 | 442339 | 0 | 442339
[8 empty] | 0 | 0 | 0
| TOTAL AMT (NON SCHEDULE) | [6 empty] | 548502 | #REF! | #REF!
[6 empty] | 0 | GRAND `TOTAL | 6905301 | #REF! | #REF!

## MB BH
Gannon Dunkerley & Co. Ltd.
Construction of Learning Block, Thapar University Patiala
MEASUREMENT SHEET (RA-06)
Name of Structure- "BOYS HOSTEL - HARDSCAPING"
Item No. | Item | Unit | No. | Side/ Nos | L | B | H/D | Qty | Total Qty | Remarks
1 | PCC
1 | Providing and laying in position under paving, driveways, floors, waterbodies, retaining walls, walls (of any thickness) and in planters, bed blocks etc. cement concrete of specified grade including the cost of centring and shuttering.
| Planter BH-01 NORTH SIDE (M7.5) | Cum | 1 |  | 11.91 | 0.61 | 0.15 | 1.09
| G 32-37/1-5 vertical | Cum | 2 |  | 9.3 | 0.61 | 0.15 | 1.7
|  | Cum | 1 |  | 10.54 | 0.61 | 0.15 | 0.96
|  | Cum | 2 |  | 6.9 | 0.61 | 0.15 | 1.26
|  | Cum | 1 |  | 6.6 | 0.61 | 0.15 | 0.6
|  | Cum | 1 |  | 7.21 | 0.61 | 0.15 | 0.66
|  | Cum | 1 |  | 5.04 | 0.61 | 0.15 | 0.46
|  | Cum | 1 |  | 7.65 | 0.61 | 0.15 | 0.7
| Grid 32-37/1-5 horizontal | Cum | 5 |  | 0.615 | 0.61 | 0.15 | 0.28
|  | Cum | 1 |  | 3.36 | 0.61 | 0.15 | 0.31
|  | Cum | 4 |  | 0.91 | 0.61 | 0.15 | 0.33
|  | Cum | 3 |  | 2.145 | 0.61 | 0.15 | 0.59
| BH01-NORTH SIDE | Cum | 1 |  | 6.75 | 0.61 | 0.15 | 0.62
| Bet G 31-28 /1-5 vertical | Cum | 1 |  | 4.75 | 0.61 | 0.15 | 0.43
|  | Cum | 2 |  | 2.33 | 0.61 | 0.15 | 0.43
|  | Cum | 2 |  | 3.55 | 0.61 | 0.15 | 0.65
|  | Cum | 1 |  | 2.04 | 0.61 | 0.15 | 0.19
|  | Cum | 1 |  | 4.65 | 0.61 | 0.15 | 0.43
| Bet. G 31-28/1-5 horizontal | Cum | 5 |  | 0.615 | 0.61 | 0.15 | 0.28
|  | Cum | 3 |  | 2.155 | 0.61 | 0.15 | 0.59
|  | Cum | 3 |  | 0.91 | 0.61 | 0.15 | 0.25
| BH-02 EAST SIDE BET G 20-28/1-6 VERTICAL | Cum | 1 |  | 10.375 | 0.61 | 0.15 | 0.95
|  | Cum | 2 |  | 7.625 | 0.61 | 0.15 | 1.4
|  | Cum | 1 |  | 8.235 | 0.61 | 0.15 | 0.75
|  | Cum | 1 |  | 4.25 | 0.61 | 0.15 | 0.39
|  | Cum | 1 |  | 4.86 | 0.61 | 0.15 | 0.44
|  | Cum | 2 |  | 4.575 | 0.61 | 0.15 | 0.84
|  | Cum | 1 |  | 3.935 | 0.61 | 0.15 | 0.36
|  | Cum | 1 |  | 4.545 | 0.61 | 0.15 | 0.42
|  | Cum | 1 |  | 3.02 | 0.61 | 0.15 | 0.28
|  | Cum | 1 |  | 3.01 | 0.61 | 0.15 | 0.28
|  | Cum | 2 |  | 1.485 | 0.61 | 0.15 | 0.27
|  | Cum | 1 |  | 3.33 | 0.61 | 0.15 | 0.3
| BH-02 EAST SIDE BET G 20-28/1-6 Horizontal | Cum | 5 |  | 0.6 | 0.61 | 0.15 | 0.27
|  | Cum | 6 |  | 0.78 | 0.61 | 0.15 | 0.43
|  | Cum | 1 |  | 3.205 | 0.61 | 0.15 | 0.29
|  | Cum | 4 |  | 1.99 | 0.61 | 0.15 | 0.73
|  | Cum | 1 |  | 2.6 | 0.61 | 0.15 | 0.24
|  | Cum | 1 |  | 3.2 | 0.61 | 0.15 | 0.29
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 10.02 | 0.61 | 0.15 | 0.92
| BET.G 17-21/20-25 | Cum | 1 |  | 8.22 | 0.61 | 0.15 | 0.75
|  | Cum | 1 |  | 9.22 | 0.61 | 0.15 | 0.84
|  | Cum | 1 |  | 8.61 | 0.61 | 0.15 | 0.79
|  | Cum | 2 |  | 8.22 | 0.61 | 0.15 | 1.5
|  | Cum | 1 |  | 5.72 | 0.61 | 0.15 | 0.52
|  | Cum | 2 |  | 5.11 | 0.61 | 0.15 | 0.94
|  | Cum | 1 |  | 8.72 | 0.61 | 0.15 | 0.8
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Cum | 8 |  | 0.615 | 0.61 | 0.15 | 0.45
| BET.G 17-21/20-25 | Cum | 2 |  | 1.225 | 0.61 | 0.15 | 0.22
|  | Cum | 2 |  | 2.13 | 0.61 | 0.15 | 0.39
|  | Cum | 4 |  | 0.91 | 0.61 | 0.15 | 0.33
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 9.22 | 0.61 | 0.15 | 0.84
| BET.G 17-21/25-29 | Cum | 1 |  | 6.81 | 0.61 | 0.15 | 0.62
|  | Cum | 2 |  | 7.42 | 0.61 | 0.15 | 1.36
|  | Cum | 2 |  | 8.42 | 0.61 | 0.15 | 1.54
|  | Cum | 2 |  | 9.22 | 0.61 | 0.15 | 1.69
| PLANTER BET -01 AND WATER BODY Horizontal | Cum | 6 |  | 0.615 | 0.61 | 0.15 | 0.34
| BET.G 17-21/25-29 | Cum | 2 |  | 2.135 | 0.61 | 0.15 | 0.39
|  | Cum | 4 |  | 0.91 | 0.61 | 0.15 | 0.33
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 8 | 0.61 | 0.15 | 0.73
| BET.G 17-21/29-35 | Cum | 1 |  | 5.61 | 0.61 | 0.15 | 0.51
|  | Cum | 1 |  | 4.61 | 0.61 | 0.15 | 0.42
|  | Cum | 2 |  | 5.22 | 0.61 | 0.15 | 0.96
|  | Cum | 3 |  | 3.61 | 0.61 | 0.15 | 0.99
|  | Cum | 1 |  | 5.61 | 0.61 | 0.15 | 0.51
|  | Cum | 1 |  | 4.42 | 0.61 | 0.15 | 0.4
|  | Cum | 1 |  | 6.02 | 0.61 | 0.15 | 0.55
| PLANTER BET -01 AND WATER BODY Horizontal | Cum | 5 |  | 0.615 | 0.61 | 0.15 | 0.28
| BET.G 17-21/29-35 | Cum | 3 |  | 3.36 | 0.61 | 0.15 | 0.92
|  | Cum | 6 |  | 0.91 | 0.61 | 0.15 | 0.5
|  | Cum | 1 |  | 2.135 | 0.61 | 0.15 | 0.2
| PLANTER BET -04 AND BH-05 VERTICAL | Cum | 1 |  | 11.9 | 0.61 | 0.15 | 1.09
| BET.G 32-36/39-47 | Cum | 1 |  | 7.79 | 0.61 | 0.15 | 0.71
|  | Cum | 2 |  | 6.59 | 0.61 | 0.15 | 1.21
|  | Cum | 2 |  | 5.69 | 0.61 | 0.15 | 1.04
|  | Cum | 2 |  | 4.79 | 0.61 | 0.15 | 0.88
|  | Cum | 2 |  | 2.99 | 0.61 | 0.15 | 0.55
|  | Cum | 2 |  | 5.09 | 0.61 | 0.15 | 0.93
|  | Cum | 2 |  | 2.99 | 0.61 | 0.15 | 0.55
|  | Cum | 1 |  | 2.09 | 0.61 | 0.15 | 0.19
|  | Cum | 1 |  | 4.7 | 0.61 | 0.15 | 0.43
| PLANTER BET -04 AND BH-05 VERTICAL | Cum | 3 |  | 0.615 | 0.61 | 0.15 | 0.17
| BET.G 32-36/39-47 | Cum | 1 |  | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 7 |  | 0.91 | 0.61 | 0.15 | 0.58
|  | Cum | 6 |  | 3.36 | 0.61 | 0.15 | 1.84
| PLANTER NEAR ZYM Vertical | Cum | 1 |  | 8.62 | 0.61 | 0.15 | 0.79
| BET.G 2-11/48-52 | Cum | 1 |  | 6.01 | 0.61 | 0.15 | 0.55
|  | Cum | 2 |  | 6.61 | 0.61 | 0.15 | 1.21
|  | Cum | 2 |  | 5.41 | 0.61 | 0.15 | 0.99
|  | Cum | 2 |  | 7.22 | 0.61 | 0.15 | 1.32
|  | Cum | 2 |  | 4.81 | 0.61 | 0.15 | 0.88
|  | Cum | 2 |  | 5.41 | 0.61 | 0.15 | 0.99
|  | Cum | 2 |  | 4.81 | 0.61 | 0.15 | 0.88
|  | Cum | 1 |  | 7.22 | 0.61 | 0.15 | 0.66
|  | Cum | 2 |  | 6.61 | 0.61 | 0.15 | 1.21
|  | Cum | 1 |  | 9.22 | 0.61 | 0.15 | 0.84
| PLANTER NEAR ZYM Horizontal | Cum | 6 |  | 0.615 | 0.61 | 0.15 | 0.34
| BET.G 2-11/48-52 | Cum | 6 |  | 0.91 | 0.61 | 0.15 | 0.5
|  | Cum | 3 |  | 3.36 | 0.61 | 0.15 | 0.92
|  | Cum | 2 |  | 2.135 | 0.61 | 0.15 | 0.39
|  | Cum | 2 |  | 1.83 | 0.61 | 0.15 | 0.33
|  | Cum | 3 |  | 0.605 | 0.61 | 0.15 | 0.17
| PLANTER BET. BH-04 AND BH-07 Vertical | Cum | 1 |  | 10.88 | 0.61 | 0.15 | 1
| BET.G 13-18/48-52 | Cum | 1 |  | 6.27 | 0.61 | 0.15 | 0.57
|  | Cum | 2 |  | 8.77 | 0.61 | 0.15 | 1.6
|  | Cum | 2 |  | 6.77 | 0.61 | 0.15 | 1.24
|  | Cum | 1 |  | 8.77 | 0.61 | 0.15 | 0.8
|  | Cum | 1 |  | 11.38 | 0.61 | 0.15 | 1.04
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 2 |  | 0.615 | 0.61 | 0.15 | 0.11
| BET.G 13-18/48-52 | Cum | 3 |  | 3.36 | 0.61 | 0.15 | 0.92
|  | Cum | 3 |  | 0.91 | 0.61 | 0.15 | 0.25
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 7 |  | 0.615 | 0.61 | 0.15 | 0.39
| BET.G 13-18/48-42 | Cum | 2 |  | 2.13 | 0.61 | 0.15 | 0.39
|  | Cum | 6 |  | 0.91 | 0.61 | 0.15 | 0.5
|  | Cum | 1 |  | 0.3 | 0.61 | 0.15 | 0.03
|  | Cum | 1 |  | 3.36 | 0.61 | 0.15 | 0.31
| PLANTER BET. BH-04 AND BH-07 VERTICAL | Cum | 1 |  | 10.58 | 0.61 | 0.15 | 0.97
| BET.G 13-18/48-42 | Cum | 1 |  | 6.58 | 0.61 | 0.15 | 0.6
|  | Cum | 1 |  | 6.77 | 0.61 | 0.15 | 0.62
|  | Cum | 1 |  | 7.38 | 0.61 | 0.15 | 0.68
|  | Cum | 2 |  | 4.97 | 0.61 | 0.15 | 0.91
|  | Cum | 2 |  | 5.28 | 0.61 | 0.15 | 0.97
|  | Cum | 1 |  | 4.67 | 0.61 | 0.15 | 0.43
|  | Cum | 1 |  | 5.28 | 0.61 | 0.15 | 0.48
|  | Cum | 1 |  | 2.81 | 0.61 | 0.15 | 0.26
|  | Cum | 1 |  | 5.42 | 0.61 | 0.15 | 0.5
PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL HORIZONTAL
| BET.G 35-41/42-48 | Cum | 1 |  | 19.52 | 0.61 | 0.15 | 1.79
|  | Cum | 1 |  | 2.09 | 0.61 | 0.15 | 0.19
|  | Cum | 6 |  | 1.835 | 0.61 | 0.15 | 1.01
|  | Cum | 4 |  | 1.215 | 0.61 | 0.15 | 0.44
|  | Cum | 1 |  | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 |  | 1.145 | 0.61 | 0.15 | 0.1
PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL VERTICAL
| BET.G 35-41/42-48 | Cum | 2 |  | 2 | 0.61 | 0.15 | 0.37
|  | Cum | 2 |  | 3 | 0.61 | 0.15 | 0.55
|  | Cum | 2 |  | 4.645 | 0.61 | 0.15 | 0.85
|  | Cum | 2 |  | 6.12 | 0.61 | 0.15 | 1.12
|  | Cum | 2 |  | 6.95 | 0.61 | 0.15 | 1.27
|  | Cum | 2 |  | 6.38 | 0.61 | 0.15 | 1.17
|  | Cum | 2 |  | 5.345 | 0.61 | 0.15 | 0.98
| BASKET BALL LONG WALL | Cum | 2 |  | 28.37 | 0.61 | 0.15 | 5.19
| BASKET WALL SHORT WALL | Cum | 2 |  | 14.19 | 0.61 | 0.15 | 2.6
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 34.935 | 0.61 | 0.15 | 3.2
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 15 | 0.61 | 0.15 | 1.37
| FIRE TENDER TOE WALL WITH BH-01 | Cum | 1 |  | 31.4 | 0.61 | 0.15 | 2.87
| FIRE TENDER TOE WALL WITH BH-07 | Cum | 1 |  | 42.55 | 0.61 | 0.15 | 3.89
| TOE WALL BH-04 FOR GREEN | Cum | 2 |  | 31.44 | 0.61 | 0.15 | 5.75
| BH-04 RCC PLANTER | Cum | 6 |  | 5 | 1.25 | 0.1 | 3.75
|  | Cum | 2 |  | 5 | 1.5 | 0.1 | 1.5
| BH-03 RCC PLANTER | Cum | 6 |  | 5 | 1.25 | 0.1 | 3.75
|  | Cum | 2 |  | 5 | 1.5 | 0.1 | 1.5
P.C.C. P/L for Planter (2-6/28'-31')
| (28'/2-3) | Cum | 1 | 1 | 4.65 | 0.61 | 0.15 | 0.43
|  | Cum | 1 | 1 | 2.04 | 0.61 | 0.15 | 0.19
| (29'/2-3) | Cum | 0 | 1 | 2.61 | 0.61 | 0.15
|  | Cum | 1 | 1 | 2.04 | 0.61 | 0.15 | 0.19
|  | Cum | 1 | 1 | 2.34 | 0.61 | 0.15 | 0.21
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.15 | 0.11
| (30'/2-3) | Cum | 1 | 2 | 2.34 | 0.61 | 0.15 | 0.43
| (31'/2-3) | Cum | 1 | 1 | 1.81 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 2.94 | 0.61 | 0.15 | 0.27
|  | Cum | 1 | 1 | 6.75 | 0.61 | 0.15 | 0.62
| (2-4/28'-31') | Cum | 1 | 1 | 0.61 | 0.61 | 0.15 | 0.06
12ws |  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 1 | 2.13 | 0.61 | 0.15 | 0.19
| (29'/2-4) | Cum | 1 | 2 | 0.615 | 0.61 | 0.15 | 0.11
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 0 | 1 | 1.535 | 0.61 | 0.15
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 1 | 2.12 | 0.61 | 0.15 | 0.19
| (31'/2-4) | Cum | 1 | 2 | 0.615 | 0.61 | 0.15 | 0.11
P.C.C. P/L for Planter (2-6/31'-37')
| (32'/2-5) | Cum | 1 | 1 | 7.65 | 0.61 | 0.15 | 0.7
|  | Cum | 1 | 1 | 5.04 | 0.61 | 0.15 | 0.46
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.15 | 0.11
| (33'/2-5) | Cum | 1 | 1 | 5.04 | 0.61 | 0.15 | 0.46
|  | Cum | 1 | 1 | 2.17 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 6 | 0.61 | 0.15 | 0.55
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.15 | 0.11
|  | Cum | 1 | 1 | 6.9 | 0.61 | 0.15 | 0.63
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3 | 0.22 | 0.615 | 0.41
|  | Cum | 1 | 1 | 6.9 | 0.61 | 0.15 | 0.63
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.15 | 0.11
| (35'/2-5) | Cum | 1 | 1 | 6.9 | 0.61 | 0.15 | 0.63
|  | Cum | 1 | 1 | 2.41 | 0.61 | 0.15 | 0.22
|  | Cum | 1 | 2 | 9.3 | 0.61 | 0.15 | 1.7
| (37'/2-5) | Cum | 1 | 1 | 11.91 | 0.61 | 0.15 | 1.09
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3.15 | 0.22 | 0.15 | 0.1
| (2-5/32'-37') | Cum | 1 | 1 | 0.615 | 0.61 | 0.15 | 0.06
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 2 | 0.615 | 0.61 | 0.15 | 0.11
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.295 | 0.61 | 0.15 | 0.03
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.615 | 0.61 | 0.15 | 0.06
|  | Cum | 1 | 1 | 3.36 | 0.61 | 0.15 | 0.31
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 1 | 0.615 | 0.61 | 0.15 | 0.06
P.C.C. P/L for Planter (17-21/20-25)
| (20'/17-21) | Cum | 1 | 1 | 10.02 | 0.61 | 0.15 | 0.92
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.15 | 0.44
|  | Cum | 1 | 1 | 3.41 | 0.61 | 0.15 | 0.31
| (21'/17-21) | Cum | 1 | 1 | 2.41 | 0.61 | 0.15 | 0.22
|  | Cum | 1 | 1 | 6.81 | 0.61 | 0.15 | 0.62
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3 | 0.22 | 0.15 | 0.1
|  | Cum | 1 | 1 | 8.46 | 0.61 | 0.15 | 0.77
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.15 | 0.11
|  | Cum | 1 | 1 | 1.61 | 0.61 | 0.15 | 0.15
|  | Cum | 1 | 1 | 6.61 | 0.61 | 0.15 | 0.6
|  | Cum | 1 | 1 | 3.41 | 0.61 | 0.15 | 0.31
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.15 | 0.44
| P.C.C.P/L Work for Sheet | Cum | 1 | 1 | 3.15 | 0.22 | 0.15 | 0.1
|  | Cum | 1 | 1 | 2.41 | 0.61 | 0.15 | 0.22
|  | Cum | 1 | 1 | 3.31 | 0.61 | 0.15 | 0.3
|  | Cum | 1 | 1 | 5.11 | 0.61 | 0.15 | 0.47
| P.C.C.P/L Work for Sheet | Cum | 1 | 1 | 3.15 | 0.22 | 0.15 | 0.1
|  | Cum | 1 | 1 | 1.2 | 0.61 | 0.15 | 0.11
| (24'/17-21) | Cum | 1 | 1 | 8.72 | 0.61 | 0.15 | 0.8
| (17/20'-24') | Cum | 1 | 8 | 0.615 | 0.61 | 0.15 | 0.45
|  | Cum | 1 | 2 | 1.215 | 0.61 | 0.15 | 0.22
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 2 | 0.91 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
P.C.C. P/L for Planter (17-21/25'-29')
| (20'/17-21) | Cum | 1 | 1 | 9.22 | 0.61 | 0.15 | 0.84
|  | Cum | 1 | 1 | 6.81 | 0.61 | 0.15 | 0.62
|  | Cum | 1 | 1 | 5.01 | 0.61 | 0.15 | 0.46
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 3.81 | 0.61 | 0.15 | 0.35
| P.C.C. P/LWork for Sheet | Cum | 1 | 1 | 3.15 | 0.22 | 0.15 | 0.1
|  | Cum | 1 | 1 | 3.61 | 0.61 | 0.15 | 0.33
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3.15 | 0.22 | 0.15 | 0.1
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.15 | 0.44
|  | Cum | 1 | 1 | 3.61 | 0.61 | 0.15 | 0.33
|  | Cum | 0 | 1 | 4.81 | 0.61 | 0.15
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 6.61 | 0.61 | 0.15 | 0.6
|  | Cum | 1 | 1 | 8.61 | 0.61 | 0.15 | 0.79
|  | Cum | 1 | 1 | 11.02 | 0.61 | 0.15 | 1.01
| (17-21/25'-29') | Cum | 1 | 6 | 0.615 | 0.61 | 0.15 | 0.34
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 2 | 0.91 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
P.C.C. P/L for Planter (17-21/29'-35')
| (29'/17-21) | Cum | 1 | 1 | 8 | 0.61 | 0.15 | 0.73
|  | Cum | 1 | 1 | 5.61 | 0.61 | 0.15 | 0.51
|  | Cum | 1 | 1 | 4.61 | 0.61 | 0.15 | 0.42
| P.C.C. P/L for Sheet | Cum | 1 | 1 | 3.15 | 0.22 | 0.15 | 0.1
|  | Cum | 1 | 1 | 1.61 | 0.61 | 0.15 | 0.15
|  | Cum | 1 | 6 | 3.61 | 0.61 | 0.15 | 1.98
|  | Cum | 1 | 1 | 5.61 | 0.61 | 0.15 | 0.51
| P.C.C. P/L for Sheet | Cum | 1 | 3 | 3.15 | 0.22 | 0.15 | 0.31
|  | Cum | 1 | 1 | 4.61 | 0.61 | 0.15 | 0.42
| (35'/17-20) | Cum | 1 | 1 | 6.02 | 0.61 | 0.15 | 0.55
| (17-20/29'-35') | Cum | 1 | 3 | 3.156 | 0.61 | 0.15 | 0.87
|  | Cum | 1 | 3 | 0.91 | 0.61 | 0.15 | 0.25
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 2 | 0.91 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 5 | 0.615 | 0.61 | 0.15 | 0.28
| P.C.C. P/L for Sheet | Cum | 1 | 4 | 3.15 | 0.22 | 0.15 | 0.42
P.C.C. P/L for Planter (20-28/2'-5')
| P.C.C. P/L (2'/20-28) | Cum | 1 | 1 | 3.82 | 0.61 | 0.15 | 0.35
|  | Cum | 1 | 3 | 1.627 | 0.61 | 0.15 | 0.45
|  | Cum | 1 | 1 | 4.42 | 0.61 | 0.15 | 0.4
|  | Cum | 1 | 1 | 3.21 | 0.61 | 0.15 | 0.29
|  | Cum | 1 | 4 | 0.78 | 0.61 | 0.15 | 0.29
P.C.C. P/L (3'/20-28)
| P.C.C. P/L (6'/20-21) | Cum | 1 | 1 | 4.425 | 0.61 | 0.15 | 0.4
|  | Cum | 1 | 2 | 1.495 | 0.61 | 0.15 | 0.27
| P.C.C. P/L (4'/22-23) | Cum | 1 | 3 | 3.21 | 0.61 | 0.15 | 0.88
|  | Cum | 1 | 2 | 2 | 0.61 | 0.15 | 0.37
|  | Cum | 1 | 1 | 2.61 | 0.61 | 0.15 | 0.24
P.C.C. P/L (20/2'-5')
| P.C.C. P/L (20/2'-5') | Cum | 1 | 1 | 9.155 | 0.61 | 0.15 | 0.84
|  | Cum | 1 | 2 | 6.405 | 0.61 | 0.15 | 1.17
| P.C.C. for Sheet | Cum | 1 | 4 | 3.15 | 0.22 | 0.15 | 0.42
|  | Cum | 1 | 1 | 4.88 | 0.61 | 0.15 | 0.45
|  | Cum | 1 | 1 | 0.78 | 0.61 | 0.15 | 0.07
| (23/2'-5') | Cum | 1 | 1 | 1.83 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 0.61 | 0.61 | 0.15 | 0.06
|  | Cum | 1 | 1 | 3.365 | 0.61 | 0.15 | 0.31
|  | Cum | 1 | 2 | 3.355 | 0.61 | 0.15 | 0.61
|  | Cum | 1 | 1 | 3.05 | 0.61 | 0.15 | 0.28
|  | Cum | 1 | 1 | 0.305 | 0.61 | 0.15 | 0.03
|  | Cum | 1 | 1 | 0.915 | 0.61 | 0.15 | 0.08
|  | Cum | 1 | 1 | 2.11 | 0.61 | 0.15 | 0.19
P.C.C. P/L Side of BH-01 (15/23'-35')
| east face (15/23'-35') | Cum | 1 | 2 | 30.47 | 0.61 | 0.15 | 5.58
|  | Cum | 1 | 2 | 0.6 | 0.61 | 0.15 | 0.11
| north face (23'/9-10) | Cum | 1 | 2 | 6.245 | 0.61 | 0.15 | 1.14
|  | Cum | 1 | 2 | 1.195 | 0.61 | 0.15 | 0.22
| north face (23'/11-13) | Cum | 1 | 2 | 7.07 | 0.61 | 0.15 | 1.29
|  | Cum | 1 | 2 | 1.195 | 0.61 | 0.15 | 0.22
P.C.C. P/L for Planter (20-28/2'-5')
| P.C.C. P/L (42'/13-16) | Cum | 1 | 1 | 5.42 | 0.61 | 0.15 | 0.5
|  | Cum | 1 | 1 | 2.81 | 0.61 | 0.15 | 0.26
|  | Cum | 1 | 1 | 4.01 | 0.61 | 0.15 | 0.37
|  | Cum | 1 | 1 | 1.27 | 0.61 | 0.15 | 0.12
|  | Cum | 1 | 2 | 4.67 | 0.61 | 0.15 | 0.85
|  | Cum | 1 | 1 | 0.99 | 0.61 | 0.15 | 0.09
|  | Cum | 1 | 1 | 4.29 | 0.61 | 0.15 | 0.39
| (45'/14-17) | Cum | 1 | 1 | 1.89 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 3.69 | 0.61 | 0.15 | 0.34
|  | Cum | 1 | 1 | 4.89 | 0.61 | 0.15 | 0.45
| (46'/14-17) | Cum | 1 | 1 | 6.17 | 0.61 | 0.15 | 0.56
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.15 | 0.11
|  | Cum | 1 | 2 | 6.77 | 0.61 | 0.15 | 1.24
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 10.58 | 0.61 | 0.15 | 0.97
| P.C.C. P/L for Sheet | Cum | 1 | 5 | 3.05 | 0.22 | 0.15 | 0.5
(15/42'-47')
|  | Cum | 1 | 7 | 0.615 | 0.61 | 0.15 | 0.39
|  | Cum | 1 | 1 | 1.525 | 0.61 | 0.15 | 0.14
|  | Cum | 1 | 1 | 0.3 | 0.61 | 0.15 | 0.03
|  | Cum | 1 | 5 | 0.91 | 0.61 | 0.15 | 0.42
|  | Cum | 1 | 1 | 3.36 | 0.61 | 0.15 | 0.31
|  | Cum | 1 | 2 | 2.135 | 0.61 | 0.15 | 0.39
P.C.C. P/L for Planter (20-28/2'-5')
| P.C.C. P/L (48'/13-16) | Cum | 1 | 1 | 11.38 | 0.61 | 0.15 | 1.04
|  | Cum | 1 | 1 | 8.77 | 0.61 | 0.15 | 0.8
| (49'/13-16) | Cum | 1 | 2 | 6.77 | 0.61 | 0.15 | 1.24
| (50'/14-18) | Cum | 1 | 2 | 9.17 | 0.61 | 0.15 | 1.68
|  | Cum | 1 | 1 | 8.27 | 0.61 | 0.15 | 0.76
| (52'/14-18) | Cum | 1 | 1 | 10.88 | 0.61 | 0.15 | 1
| P.C.C. P/L for Sheet | Cum | 1 | 3 | 3.3 | 0.22 | 0.15 | 0.33
| (15/48'-53') | Cum | 1 | 2 | 0.615 | 0.61 | 0.15 | 0.11
| (17/48'-49') | Cum | 1 | 3 | 0.88 | 0.61 | 0.15 | 0.24
|  | Cum | 1 | 3 | 3.36 | 0.61 | 0.15 | 0.92
P.C.C. P/L outer side of BH-04 (Drg. No. TU/LA-P-206.3)
| P.C.C. P/L Work west side (20/37'-50') | Cum | 1 | 1 | 33.92 | 0.61 | 0.15 | 3.1
|  | Cum | 1 | 1 | 30.13 | 0.61 | 0.15 | 2.76
| P.C.C. P/L south side (49'/19-23) (longitudinal axies) | Cum | 1 | 1 | 1.525 | 0.61 | 0.15 | 0.14
|  | Cum | 1 | 1 | 1.075 | 0.61 | 0.15 | 0.1
|  | Cum | 1 | 1 | 2.6 | 0.61 | 0.15 | 0.24
|  | Cum | 1 | 1 | 1.1 | 0.61 | 0.15 | 0.1
|  | Cum | 1 | 1 | 3.94 | 0.61 | 0.15 | 0.36
| P.C.C. P/L south side (49'/19-23) (transverse axies) | Cum | 1 | 1 | 1.39 | 0.61 | 0.15 | 0.13
|  | Cum | 1 | 1 | 2 | 0.61 | 0.15 | 0.18
|  | Cum | 1 | 1 | -0.22 | 0.61 | 0.15 | -0.02
|  | Cum | 1 | 1 | 1 | 0.61 | 0.15 | 0.09
|  | Cum | 1 | 1 | 1.36 | 0.61 | 0.15 | 0.12
|  | Cum | 1 | 1 | 5.56 | 0.61 | 0.15 | 0.51
| P.C.C. P/L north side (36'/19-21) (longitudianal axies) | Cum | 0 | 1 | 3 | 0.61 | 0.15
| P.C.C. P/L north side (36'/19-21) (transverse axies) | Cum | 0 | 1 | 4.415 | 0.61 | 0.15
| (transverse axies) | Cum | 0 | 1 | 1.61 | 0.61 | 0.15
P.C.C. P/L outer side of BH-04 (Drg. No. TU/LA-P-206.4)
| P.C.C. P/L east side (32/37'-49') | Cum | 1 | 2 | 33.04 | 0.61 | 0.15 | 6.05
|  | Cum | 1 | 2 | 1.36 | 0.61 | 0.15 | 0.25
P.C.C. P/L P/L for Planter (39'-55'/32-36) (Drg. No. TU/LA-P-206.4)
P.C.C. P/L for Planter (39'-47'/32-36)
| longitudianal axies (40'/34-35) | Cum | 1 | 1 | 4.7 | 0.61 | 0.15 | 0.43
|  | Cum | 1 | 1 | 2.09 | 0.61 | 0.15 | 0.19
|  | Cum | 1 | 4 | 2.99 | 0.61 | 0.15 | 1.09
|  | Cum | 1 | 2 | 5.09 | 0.61 | 0.15 | 0.93
|  | Cum | 1 | 2 | 4.79 | 0.61 | 0.15 | 0.88
|  | Cum | 1 | 2 | 5.69 | 0.61 | 0.15 | 1.04
|  | Cum | 1 | 2 | 6.59 | 0.61 | 0.15 | 1.21
|  | Cum | 1 | 1 | 7.79 | 0.61 | 0.15 | 0.71
|  | Cum | 1 | 1 | 2.11 | 0.61 | 0.15 | 0.19
| (47'/32-36) | Cum | 1 | 1 | 11.38 | 0.61 | 0.15 | 1.04
| P.C.C. P/L for Sheet | Cum | 1 | 4 | 3.15 | 0.22 | 0.15 | 0.42
| Transvere axies (34/40'-47') | Cum | 1 | 3 | 0.615 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 6 | 3.36 | 0.61 | 0.15 | 1.84
|  | Cum | 1 | 7 | 0.91 | 0.61 | 0.15 | 0.58
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.15 | 0.2
P.C.C. P/L for Planter (30-39/37-40) near M4 (revised Drg. No. TU/LA-P-206.5 (front of Basket Ball)
| P.C.C. (west side wall) | Cum | 1 | 1 | 19.75 | 0.61 | 0.15 | 1.81
| extra for Sheet | Cum | 1 | 3 | 3.3 | 0.22 | 0.15 | 0.33
| north & south side wall | Cum | 2 | 1 | 2 | 0.61 | 0.15 | 0.37
|  | Cum | 1 | 3 | 2.435 | 0.61 | 0.15 | 0.67
|  | Cum | 1 | 1 | 2.44 | 0.61 | 0.15 | 0.22
|  | Cum | 1 | 1 | 2.13 | 0.61 | 0.15 | 0.19
|  | Cum | 1 | 1 | 2.09 | 0.61 | 0.15 | 0.19
|  | Cum | 1 | 2 | 5.345 | 0.61 | 0.15 | 0.98
|  | Cum | 1 | 2 | 6.38 | 0.61 | 0.15 | 1.17
|  | Cum | 1 | 2 | 6.95 | 0.61 | 0.15 | 1.27
|  | Cum | 1 | 2 | 6.12 | 0.61 | 0.15 | 1.12
|  | Cum | 1 | 2 | 4.645 | 0.61 | 0.15 | 0.85
|  | Cum | 1 | 2 | 3 | 0.61 | 0.15 | 0.55
|  | Cum | 1 | 4 | 0.615 | 0.61 | 0.15 | 0.23
|  | Cum | 1 | 2 | 0.61 | 0.61 | 0.15 | 0.11
P.C.C. P/L P/L for Planter near BH-03 (drg. No. TU/LA-P-206.1) (48-52/2'-11')
P.C.C. P/L for Stepped Foundation (west side wall) (2'/48-52)
| Longitudianal axies (2'/48-52) | Cum | 1 | 1 | 8.62 | 0.61 | 0.15 | 0.79
|  | Cum | 1 | 1 | 6.01 | 0.61 | 0.15 | 0.55
|  | Cum | 1 | 2 | 6.61 | 0.61 | 0.15 | 1.21
|  | Cum | 1 | 3 | 5.41 | 0.61 | 0.15 | 1.49
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 1 | 6.01 | 0.61 | 0.15 | 0.55
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.15 | 0.11
|  | Cum | 1 | 5 | 4.81 | 0.61 | 0.15 | 2.2
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.15 | 0.11
|  | Cum | 1 | 1 | 5.41 | 0.61 | 0.15 | 0.5
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.15 | 0.17
| (10'/49-50) | Cum | 1 | 2 | 6.61 | 0.61 | 0.15 | 1.21
|  | Cum | 1 | 1 | 9.22 | 0.61 | 0.15 | 0.84
| extra for Sheet | Cum | 1 | 8 | 3.15 | 0.22 | 0.15 | 0.83
Transverse axies (49/2'-11')
|  | Cum | 1 | 6 | 0.615 | 0.61 | 0.15 | 0.34
|  | Cum | 1 | 4 | 0.91 | 0.61 | 0.15 | 0.33
|  | Cum | 1 | 2 | 3.36 | 0.61 | 0.15 | 0.61
|  | Cum | 1 | 3 | 0.605 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 2 | 1.83 | 0.61 | 0.15 | 0.33
|  | Cum | 1 | 2 | 2.135 | 0.61 | 0.15 | 0.39
|  | Cum | 1 | 1 | 3.055 | 0.61 | 0.15 | 0.28
|  | Cum | 1 | 1 | 3.165 | 0.61 | 0.15 | 0.29
|  | Cum | 1 | 1 | 0.715 | 0.61 | 0.15 | 0.07
P.C.C. P/L for BH-05 outer side (drg. No. TU/LA-P-206.8)
| P.C.C. P/L for FIRE TENDER TOES Wall (north side wall) | Cum | 1 | 1 | 34.935 | 0.61 | 0.15 | 3.2
| P.C.C. P/L for FIRE TENDER TOES Wall (west side wall) | Cum | 1 | 1 | 15 | 0.61 | 0.15 | 1.37
P.C.C. P/L for Basket Ball Ground Toe Wall
| Basket Ball Long Ball | Cum | 1 | 2 | 28.76 | 0.61 | 0.15 | 5.26
| BASKET WALL SHORT WALL | Cum | 1 | 2 | 14.19 | 0.61 | 0.15 | 2.6
| SEAT | Cum | 1 | 2 | 3.3 | 0.22 | 0.15 | 0.22
P.C.C. P/L for Basket Ball Ground Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 |  | 1 | 1 | 31.4 | 0.61 | 0.15 | 2.87
| FIRE TENDER TOE WALL WITH BH-07 |  | 1 | 1 | 42.55 | 0.61 | 0.15 | 3.89
P.C.C. P/L for Road Toe Wall BH-01
| P.C.C. P/L for Road Toe Wall BH-01 east side towards water body | Cum | 1 | 2 | 30.54 | 0.61 | 0.15 | 5.59
|  | Cum | 1 | 2 | 0.67 | 0.61 | 0.15 | 0.12
P.C.C. P/L for Road Toe Wall BH-01 North side towards GYM
|  | Cum | 1 | 2 | 6.315 | 0.61 | 0.15 | 1.16
|  | Cum | 1 | 2 | 1.265 | 0.61 | 0.15 | 0.23
|  | Cum | 1 | 2 | 7.14 | 0.61 | 0.15 | 1.31
|  | Cum | 1 | 2 | 1.265 | 0.61 | 0.15 | 0.23
P.C.C. P/L for Road Toe Wall back side of Basket Ball (east side)
|  |  | 1 | 3 | 7.625 | 0.61 | 0.15 | 2.09
Excavation for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | 1 | 8 | 7.625 | 0.61 | 0.15 | 5.58
|  | Cum | 1 | 1 | 9.35 | 0.61 | 0.15 | 0.86
P.C.C. P/L in Road
Stone Agg. 90 to 45mm in Basket Ball Ground
|  | Cum | 1 | 1 | 27.54 | 14.19 | 0.075 | 29.31
Stone Agg. 90 to 45mm in Road
| Road between BH-05 & B3 Basket Ground | Cum | 1 | 1 | 29.2 | 6 | 0.075 | 13.14
|  | Cum | 1 | 1 | 8.32 | 6.78 | 0.075 | 4.23
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 23.235 | 6 | 0.075 | 10.46
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 2.275 | 6 | 0.075 | 1.02
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 32.39 | 6 | 0.075 | 14.58
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 5.295 | 6 | 0.075 | 2.38
P.C.C. P/L for Planter between BH-03 & Basket Ball Ground
| Base Footning (4500x1000) | Cum | 1 | 6 | 5 | 1.25 | 0.1 | 3.75
|  | Cum | 1 | 2 | 5 | 1.5 | 0.1 | 1.5
P.C.C. P/L for Planter between BH-04 & Base of Waterbody M3
| Base Footning (4500x1000) | Cum | 1 | 6 | 5 | 1.25 | 0.1 | 3.75
|  | Cum | 1 | 2 | 5 | 1.5 | 0.1 | 1.5
P.C.C. P/L in Planter Area
| Planter Front of Basket Ground (west side) | Cum | 1 | 1 | 6.38 | 1.975 | 0.075 | 0.95
|  | Cum | 1 | 2 | 6.95 | 1.975 | 0.075 | 2.06
|  | Cum | 1 | 1 | 6.12 | 1.67 | 0.075 | 0.77
|  | Cum | 1 | 1 | 4.645 | 1.975 | 0.075 | 0.69
|  | Cum | 1 | 1 | 6.885 | 1.27 | 0.075 | 0.66
|  | Cum | 1 | 1 | 2.385 | 2.26 | 0.075 | 0.4
| space between basket ground & planter | Cum | 1 | 1 | 20.17 | 2.125 | 0.075 | 3.21
| planter front of Bh-05 (west side) | Cum | 1 | 1 | 12.58 | 1.19 | 0.075 | 1.12
|  | Cum | 1 | 1 | 7.09 | 0.9 | 0.075 | 0.48
|  | Cum | 1 | 1 | 1.6 | 5.98 | 0.075 | 0.72
|  | Cum | 1 | 1 | 1.6 | 4.18 | 0.075 | 0.5
|  | Cum | 1 | 2 | 1.6 | 2.38 | 0.075 | 0.57
|  | Cum | 1 | 1 | 1.145 | 0.9 | 0.075 | 0.08
|  | Cum | 1 | 1 | 2.745 | 1.5 | 0.075 | 0.31
|  | Cum | 1 | 1 | 1.6 | 6.675 | 0.075 | 0.8
|  | Cum | 0.5 | 1 | 3.07 | 1.065 | 0.075 | 0.12
|  | Cum | 1 | 1 | 1.6 | 3.9 | 0.075 | 0.47
|  | Cum | 0.5 | 1 | 2.77 | 0.96 | 0.075 | 0.1
|  | Cum | 1 | 1 | 1.6 | 4.09 | 0.075 | 0.49
|  | Cum | 0.5 | 1 | 3.25 | 1.095 | 0.075 | 0.13
|  | Cum | 0.5 | 1 | 8.61 | 4.615 | 0.075 | 1.49
P.C.C. P/L in Ramp Area Front side of Gym (West side)
|  | Cum | 1 | 1 | 21 | 6.2 | 0.075 | 9.77
| Less Previous RA Quantity | Cum | -1 | 1 | 128.47 |  |  | -128.47
P.C.C. P/L for Planter near Reception or west side of Waterbody (drg. No. TU/LA-P-206.1) (30'-35'/32-36)
P.C.C. P/L for Planter
| Longitudianal axies (30'/32-36) | Cum | 1 | 1 | 11.97 | 0.61 | 0.15 | 1.1
|  | Cum | 1 | 1 | 2.01 | 0.61 | 0.15 | 0.18
|  | Cum | 1 | 1 | 7.965 | 0.61 | 0.15 | 0.73
| Longitudianal axies (31'/32-35) | Cum | 1 | 1 | 7.965 | 0.61 | 0.15 | 0.73
|  | Cum | 1 | 1 | 2.01 | 0.61 | 0.15 | 0.18
|  | Cum | 1 | 1 | 6.565 | 0.61 | 0.15 | 0.6
| Longitudianal axies (32'/32-35) | Cum | 1 | 1 | 6.565 | 0.61 | 0.15 | 0.6
|  | Cum | 1 | 1 | 2.14 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 5.035 | 0.61 | 0.15 | 0.46
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 5.035 | 0.61 | 0.15 | 0.46
|  | Cum | 1 | 1 | 2.14 | 0.61 | 0.15 | 0.2
|  | Cum | 1 | 1 | 3.5 | 0.61 | 0.15 | 0.32
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 3.5 | 0.61 | 0.15 | 0.32
|  | Cum | 1 | 1 | 5.5 | 0.61 | 0.15 | 0.5
| Transvere axies (34/30'-35') | Cum | 1 | 6 | 0.615 | 0.61 | 0.15 | 0.34
|  | Cum | 1 | 3 | 2.135 | 0.61 | 0.15 | 0.59
|  | Cum | 1 | 1 | 1.83 | 0.61 | 0.15 | 0.17
|  | Cum | 1 | 3 | 0.91 | 0.61 | 0.15 | 0.25
|  | Cum | 1 | 1 | 0.605 | 0.61 | 0.15 | 0.06
P.C.C. P/L for Planter South sid of BH-02 (drg. No. TU/LA-P-206.1 & 206.2) ( (15'-19'/20-32)
P.C.C. P/L for Planter
| Longitudianal axies (15'/20-32) | Cum | 1 | 1 | 29.85 | 0.61 | 0.15 | 2.73
|  | Cum | 1 | 1 | 1.08 | 0.61 | 0.15 | 0.1
|  | Cum | 1 | 6 | 0.78 | 0.61 | 0.15 | 0.43
|  | Cum | 1 | 1 | 1.03 | 0.61 | 0.15 | 0.09
|  | Cum | 1 | 1 | 0.53 | 0.61 | 0.15 | 0.05
|  | Cum | 1 | 12 | 0.6 | 0.61 | 0.15 | 0.66
| Transvere axies (32/15'-19') | Cum | 1 | 1 | 11.535 | 0.61 | 0.15 | 1.06
| (32/15'-19') | Cum | 1 | 1 | 9.925 | 0.61 | 0.15 | 0.91
| (31/15'-19') | Cum | 1 | 2 | 8.4 | 0.61 | 0.15 | 1.54
| (30/15'-18') | Cum | 1 | 2 | 6.875 | 0.61 | 0.15 | 1.26
| (29/15'-17') | Cum | 0 | 2 | 6.875 | 0.61 | 0.15
|  | Cum | 1 | 2 | 5.35 | 0.61 | 0.15 | 0.98
|  | Cum | 1 | 2 | 4.13 | 0.61 | 0.15 | 0.76
|  | Cum | 6 | 2 | 3.825 | 0.61 | 0.15 | 4.2
|  | Cum | 1 | 1 | 3.825 | 0.61 | 0.15 | 0.35
|  | Cum | 1 | 1 | 5.435 | 0.61 | 0.15 | 0.5
| P.C.C. P/L for Sheat | Cum | 1 | 11 | 3 | 0.115 | 0.15 | 0.57
P.C.C. P/L for Planter South sid of BH-02 & BH-03 (drg. No. TU/LA-P-206.1) ( (19'-21'/35-40)
Brick Work for Planter
| Longitudianal axies (40/19'-20') | Cum | 1 | 2 | 4.2 | 0.61 | 0.15 | 0.77
|  | Cum | 1 | 2 | 6.335 | 0.61 | 0.15 | 1.16
|  | Cum | 1 | 2 | 7.25 | 0.61 | 0.15 | 1.33
|  | Cum | 1 | 2 | 6.64 | 0.61 | 0.15 | 1.22
|  | Cum | 1 | 5 | 0.6 | 0.61 | 0.15 | 0.27
| P.C.C. P/L for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
| P.C.C. P/L for Road Toe Wall (1/F-J) | Cum | 1 | 1 | 4.635 | 0.61 | 0.15 | 0.42
|  | Cum | 1 | 8 | 7.625 | 0.61 | 0.15 | 5.58
|  | Cum | 1 | 1 | 10.14 | 0.61 | 0.15 | 0.93
| P.C.C. P/L for Road Toe Wall (J/1-9) | Cum | 1 | 1 | 14.06 | 0.61 | 0.15 | 1.29
|  | Cum | 1 | 5 | 7.625 | 0.61 | 0.15 | 3.49
|  | Cum | 1 | 1 | 0.265 | 0.61 | 0.15 | 0.02
| P.C.C. P/L for Road Toe Wall (9/H-J) | Cum | 1 | 1 | 7.53 | 0.61 | 0.15 | 0.69
|  | Cum | 1 | 2 | 7.625 | 0.61 | 0.15 | 1.4
| P.C.C. P/L for Planter between BH-01 & Canteen | Cum
Cum
| Base Footning (4500x1000) | Cum | 0 | 6 | 5 | 1.25 | 0.1
|  | Cum | 0 | 3 | 5 | 1.5 | 0.1
| P.C.C. P/L for Planter between BH-02 & GYM | Cum
| Base Footning (4500x1000) | Cum | 1 | 6 | 5 | 1.25 | 0.1 | 3.75
|  | Cum | 1 | 2 | 5 | 1.5 | 0.1 | 1.5
| P.C.C. P/L for Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For P.C.C. =20.12+0.2*2+0.6*2+0.2*2=22.120m) | Cum |  |  | area
|  | Cum | 1 | 1 | 384.0961 |  | 0.1 | 38.41
Cum
| P.C.C. P/L on Road Area | Cum
| Area-1, Road between BH-01 & BH-07 | Cum | 1 | 1 | 514.7 |  | 0.075 | 38.6
| Area-2, Road between BH-04 & west corner of BH-01 | Cum | 1 | 1 | 169.79 |  | 0.075 | 12.73
| deduct area not done | Cum | -1 | 1 | 580.43 | 6 | 0.075 | -261.19
| Area-3, Road between BH-01 west side & waterbody | Cum | 1 | 1 | 584.13 |  | 0.075 | 43.81
| Area-4, Road between BH-04 west side | Cum | 1 | 1 | 628.19 |  | 0.075 | 47.11
| Area-5, Road between BH-05 north side & Basket Ball Ground | Cum | 1 | 1 | 303.47 |  | 0.075 | 22.76
| Area-6, Road front BH-05 east side | Cum | 1 | 1 | 165.9 |  | 0.075 | 12.44
|  | Cum |  |  | L | B | H
| P.C.C. P/L in Ramp Area (1/H-J) | Cum | 1 | 1 | 36.715 | 8.48 | 0.075 | 23.35
| P.C.C. P/L between BH-01 & Canteen | Cum | 1 | 1 | 18.1 | 34.68 | 0.075 | 47.08
|  | Cum |  |  | area
| add area near road junction near canteen east corner | Cum | 1 | 1 | 40.53 |  | 0.075 | 3.04
| deduct R.C.C. Existng Col. | Cum | -1 | 5 | 4.64 |  | 0.075 | -1.74
| deduct R.C.C. Planter Area | Cum | -1 | 6 | 4.49 |  | 0.075 | -2.02
|  | Cum | -1 | 3 | 4.5 |  | 0.075 | -1.01
| deduct sheat area | Cum | -1 | 6 | 1.349 |  | 0.075 | -0.61
| Green Planter | Cum | -1 | 2 | 1.47 | 5.555 | 0.075 | -1.22
Cum
| P.C.C. P/L between BH-01 west side | Cum | 1 | 1 | 364.85 |  | 0.075 | 27.36
| deduct existing Plnater | Cum | -1 | 1 | 34.05 |  | 0.075 | -2.55
|  | Cum | -1 | 1 | 70.8 |  | 0.075 | -5.31
|  | Cum |  |  | area
| P.C.C. P/L between BH-02 & GYM | Cum | 1 | 1 | 478.103 |  | 0.075 | 35.86
| deduction for seat | Cum | -1 | 6 | 1.35 |  | 0.075 | -0.61
| deduction for Green Planter | Cum | -1 | 1 | 2.625 | 1.2 | 0.075 | -0.24
|  | Cum | -1 | 1 | 5.85 | 1.2 | 0.075 | -0.53
|  | Cum | -1 | 1 | 5.025 | 1.2 | 0.075 | -0.45
|  | Cum | -1 | 1 | 2.4 | 1.2 | 0.075 | -0.22
|  | Cum | -4 | 1 | 0.8 | 5.8 | 0.075 | -1.39
|  | Cum | -1 | 1 | 5.92 |  | 0.075 | -0.44
|  | Cum | -7 | 1 | 4.1 | 0.6 | 0.075 | -1.29
|  | Cum | -1 | 1 | 2.137 |  | 0.075 | -0.16
| P.C.C. P/L at Podium Lvl. | Cum
| P.C.C. P/L at Podium Lvl. Ref. tp (drg. No. TU/LA/-P-216) at grid- (H-J/1-2) | Cum | 1 | 1 | 27.915 | 27.775 | 0.1 | 77.53
P.C.C. P/L for Boy's Hostel
P.C.C. P/L for Planter near Waterbody & Reception (22'-26'/32-36) Ref. Drg. No. TU/LA-P-206.1
P.C.C. for Planter
| Longitudianal axies (32/22'-26') | CUM | 1 | 1 | 10.57 | 0.61 | 0.15 | 0.97
|  | CUM | 1 | 1 | 10.155 | 0.61 | 0.15 | 0.93
| (33/22'-26') | CUM | 1 | 2 | 8.935 | 0.61 | 0.15 | 1.64
| (34/22'-26') | CUM | 1 | 2 | 7.41 | 0.61 | 0.15 | 1.36
| (35/22'-26') | CUM | 1 | 2 | 5.58 | 0.61 | 0.15 | 1.02
| (36/22'-26') | CUM | 1 | 1 | 4.055 | 0.61 | 0.15 | 0.37
|  | CUM | 1 | 1 | 4.85 | 0.61 | 0.15 | 0.44
| Transverse Axies | CUM | 1 | 5 | 0.6 | 0.61 | 0.15 | 0.27
| P.C.C. for Ramp B/W for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205 |  |  |  | ht.=0.7=0.7m, =0.5+0.7=1.2m
|  | CUM | 1 | 2 | 6 | 0.645 | 0.15 | 1.16
|  | CUM | 1 | 1 | 2.925 | 0.645 | 0.15 | 0.28
|  | CUM | 1 | 1 | 1.08 | 0.645 | 0.15 | 0.1
|  | CUM | 1 | 1 | 2 | 0.645 | 0.15 | 0.19
| P.C.C. doe Brick Steps | CUM | 1 | 1 | 3 | 1.2 | 0.15 | 0.54
| P.C.C. for brick wall side of step continue | CUM | 1 | 1 | 0.6 | 0.645 | 0.15 | 0.06
| P.C.C. P/L on top of Ramp for R.C.C. Laying | CUM | 1 | 1 | 6 | 1.54 | 0.075 | 0.69
|  | CUM | 1 | 1 | 3.225 | 3 | 0.075 | 0.73
P.C.C. P/L for Entry Area Steps of BH-01
| Steps for Entry | CUM | 1 | 1 | 5.42 | 4.26 | 0.075 | 1.73
area
| P.C.C. P/L for side ramp of entrance | CUM | 1 | 1 | 16 |  | 0.075 | 1.2 |  | area
P.C.C. P/L for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205
|  | CUM | 1 | 2 | 6 | 0.645 | 0.15 | 1.16
|  | CUM | 1 | 1 | 2.925 | 0.645 | 0.15 | 0.28
|  | CUM | 1 | 1 | 1.08 | 0.645 | 0.15 | 0.1
|  | CUM | 1 | 1 | 2 | 0.645 | 0.15 | 0.19
| P.C.C. for Brick Steps | CUM | 1 | 1 | 3 | 1.2 | 0.15 | 0.54
| P.C.C. for brick wall side of step continue | CUM | 1 | 1 | 0.6 | 0.645 | 0.15 | 0.06
| P.C.C. P/L on top of Ramp for R.C.C. Laying | CUM | 1 | 1 | 6 | 1.54 | 0.075 | 0.69
|  | CUM | 1 | 1 | 3.225 | 3 | 0.075 | 0.73
P.C.C. P/L for Entry Area Steps of BH-02
| Steps for Entry | CUM | 1 | 1 | 5.42 | 4.26 | 0.075 | 1.73
area
| P.C.C. P/L for side ramp of entrance | CUM | 1 | 1 | 16 |  | 0.075 | 1.2 |  | area
Brick Work for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205
|  | CUM | 1 | 2 | 6 | 0.645 | 0.15 | 1.16
|  | CUM | 1 | 1 | 3.225 | 0.645 | 0.15 | 0.31
|  | CUM | 1 | 1 | 1.08 | 0.645 | 0.15 | 0.1
|  | CUM | 1 | 1 | 2 | 0.645 | 0.15 | 0.19
| P.C.C. for Brick Steps | CUM | 1 | 1 | 3 | 1.2 | 0.15 | 0.54
| P.C.C. for brick wall side of step continue | CUM | 1 | 1 | 0.6 | 0.645 | 0.15 | 0.06
| P.C.C. P/L on top of Ramp for R.C.C. Laying | CUM | 1 | 1 | 6 | 1.54 | 0.075 | 0.69
|  | CUM | 1 | 1 | 3.225 | 3 | 0.075 | 0.73
P.C.C. P/L for Entry Area Steps of BH-03
| Steps for Entry | CUM | 1 | 1 | 5.42 | 4.26 | 0.075 | 1.73
area
| P.C.C. P/L for side ramp of entrance | CUM | 1 | 1 | 16 |  | 0.075 | 1.2 |  | area
P.C.C. P/L for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205
|  | CUM | 1 | 2 | 6 | 0.645 | 0.15 | 1.16
|  | CUM | 1 | 1 | 2.925 | 0.645 | 0.15 | 0.28
|  | CUM | 1 | 1 | 1.08 | 0.645 | 0.15 | 0.1
|  | CUM | 1 | 1 | 2 | 0.645 | 0.15 | 0.19
| P.C.C. for Brick Steps | CUM | 1 | 1 | 3 | 1.2 | 0.15 | 0.54
| P.C.C. for brick wall side of step continue | CUM | 1 | 1 | 0.6 | 0.645 | 0.15 | 0.06
| P.C.C. P/L on top of Ramp for R.C.C. Laying | CUM | 1 | 1 | 6 | 1.54 | 0.075 | 0.69
|  | CUM | 1 | 1 | 3.225 | 3 | 0.075 | 0.73
P.C.C. for Entry Area Steps of BH-04
| Steps for Entry | CUM | 1 | 1 | 5.42 | 4.26 | 0.075 | 1.73
area
| P.C.C. P/L for side ramp of entrance | CUM | 1 | 1 | 16 |  | 0.075 | 1.2 |  | area
P.C.C. P/L for Brick Work for Road Toe Wall (9/H-J)
|  | CUM | 1 | 1 | 7.625 | 0.76 | 0.15 | 0.87
|  | CUM | 1 | 1 | 1.1 | 0.76 | 0.15 | 0.13
P.C.C P/L for Brick Work for Road Toe Wall (9/F-H) basket ball ground & BH-03
|  | CUM | 1 | 1 | 7.625 | 0.76 | 0.15 | 0.87
|  | CUM | 1 | 1 | 7.125 | 0.76 | 0.15 | 0.81
P.C.C. P/L for Brick work for Seprate Seat
P.C.C. P/L for P.C.C. P/L for Brick work seat under transfer slab of BH-04 towards Waterbody
| TOS lvl. +0.5m | CUM | 1 | 7 | 3.526 | 0.76 | 0.15 | 2.81
P.C.C. P/L for Brick work seat between Waterbody & Reception
| TOS lvl. +0.5m | CUM | 1 | 8 | 3.526 | 0.76 | 0.15 | 3.22
P.C.C. P/L for Brick work seat under transfer slab of BH-01 towards Canteen
| TOS lvl. +0.5m | CUM | 1 | 6 | 3.526 | 0.76 | 0.15 | 2.41
P.C.C. P/L for Fire Tender Wall (parallel to road)
| Fire Tender Wall towards BH-07 | Cum | 1 | 1 | 24.945 | 0.76 | 0.15 | 2.84
|  | Cum | 1 | 1 | 13.605 | 0.76 | 0.15 | 1.55
|  | Cum | 1 | 1 | 4.343 | 0.76 | 0.15 | 0.5
|  | Cum | 1 | 1 | 4.748 | 0.76 | 0.15 | 0.54
|  | Cum | 1 | 1 | 0.374 | 0.76 | 0.15 | 0.04
| Brick work for green Planter wall BH-07 (west side) | Cum | 1 | 1 | 1.359 | 0.76 | 0.15 | 0.15
|  | Cum | 1 | 1 | 26.229 | 0.76 | 0.15 | 2.99
| Fire Tender Wall towards BH-01 | Cum | 1 | 1 | 10.508 | 0.76 | 0.15 | 1.2
|  | Cum | 1 | 1 | 1.608 | 0.76 | 0.15 | 0.18
|  | Cum | 1 | 1 | 2.059 | 0.76 | 0.15 | 0.23
|  | Cum | 1 | 1 | 2.938 | 0.76 | 0.15 | 0.33
|  | Cum | 1 | 1 | 7.795 | 0.76 | 0.15 | 0.89
|  | Cum | 1 | 1 | 2.063 | 0.76 | 0.15 | 0.24
|  | Cum | 1 | 1 | 1.079 | 0.76 | 0.15 | 0.12
|  | Cum | 1 | 1 | 3.273 | 0.76 | 0.15 | 0.37
|  | Cum | 1 | 1 | 5.084 | 0.76 | 0.15 | 0.58
| Fire Tender Wall Brick Work between BH-04 & BH-07 near green Planter (triangle type) | Cum | 0 | 1 | 1.398 | 0.76 | 0.15
|  | Cum | 0 | 1 | 6.182 | 0.76 | 0.15
|  | Cum | 0 | 1 | 0.23 | 0.76 | 0.15
|  | Cum | 0 | 1 | 8.695 | 0.76 | 0.15
|  | CUM | 1 | 1 | 16.409 | 0.76 | 0.15 | 1.87
| brick work for fire tender in green planter between BH-04 & BH-07 | Cum | 0 | 1 | 0.898 | 0.76 | 0.15
|  | Cum | 0 | 1 | 1.497 | 0.76 | 0.15
|  | Cum | 0 | 1 | 1.602 | 0.76 | 0.15
|  | Cum | 0 | 1 | 1.012 | 0.76 | 0.15
|  | Cum | 0 | 1 | 4.172 | 0.76 | 0.15
|  | Cum | 0 | 1 | 10.42 | 0.76 | 0.15
|  | Cum | 0 | 1 | 0.217 | 0.76 | 0.15
|  | Cum | 0 | 1 | 4.011 | 0.76 | 0.15
|  | CUM | 1 | 1 | 23.472 | 0.76 | 0.15 | 2.68
| Fire Tender Wall Brick Work connect to BH-04 to green Planter between BH-01 & waterbody | Cum | 1 | 1 | 15.694 | 0.76 | 0.15 | 1.79
|  | Cum | 1 | 1 | 0.225 | 0.76 | 0.15 | 0.03
| Brick Work for Fire Tender in Green planter between BH-01 & Waterbody | Cum | 1 | 1 | 1.497 | 0.76 | 0.15 | 0.17
|  | Cum | 1 | 1 | 1.6 | 0.76 | 0.15 | 0.18
|  | Cum | 1 | 1 | 3.43 | 0.76 | 0.15 | 0.39
|  | Cum | 1 | 1 | 1.497 | 0.76 | 0.15 | 0.17
|  | Cum | 1 | 1 | 3.735 | 0.76 | 0.15 | 0.43
|  | Cum | 1 | 1 | 4.345 | 0.76 | 0.15 | 0.5
| Fire Tender Wall Brick Work BH-01 west corner to Canteen parallel to road betwee canteen & BH-02 | Cum | 1 | 1 | 2.386 | 0.76 | 0.15 | 0.27
|  | Cum | 1 | 1 | 20.003 | 0.76 | 0.15 | 2.28
| parallel to canteen | Cum | 1 | 1 | 33.031 | 0.76 | 0.15 | 3.77
| parallel to BH-02 towards canteen (east face) | Cum | 1 | 1 | 31.771 | 0.76 | 0.15 | 3.62
|  | Cum | 1 | 1 | 4.373 | 0.76 | 0.15 | 0.5
|  | Cum | 1 | 1 | 0.17 | 0.76 | 0.15 | 0.02
Fire Tender Wall Brick Work for Road between BH-02 & Waterbody
| wall towards BH-02 (BH-02 to Gym toilet) | Cum | 1 | 1 | 18.743 | 0.76 | 0.15 | 2.14
|  | Cum | 1 | 1 | 9.868 | 0.76 | 0.15 | 1.12
|  | Cum | 1 | 1 | 7.05 | 0.76 | 0.15 | 0.8
fire tender wall towards waterbody planter to arround waterbody to Reception
|  | Cum | 0 | 1 | 0.337 | 0.76 | 0.15
|  | Cum | 0 | 1 | 3.183 | 0.76 | 0.15
|  | Cum | 0 | 1 | 33.632 | 0.76 | 0.15
| in planter | Cum | 0 | 1 | 9.063 | 0.76 | 0.15
|  | CUM | 1 | 1 | 8.053 | 0.76 | 0.15 | 0.92
|  | CUM | 1 | 1 | 36.696 | 0.76 | 0.15 | 4.18
| fire tender wall west side of reception | Cum | 1 | 1 | 14.555 | 0.76 | 0.15 | 1.66
Fire Tender Wall Brick Work for Road South side of BH-04 (back side)
|  | Cum | 1 | 1 | 14.343 | 0.76 | 0.15 | 1.64
Fire Tender Wall Brick Work for Road BH-04 (near watebody to basket ball ground planter) to BH-03
|  | Cum | 1 | 1 | 60.78 | 0.76 | 0.15 | 6.93
| basket ball ground planter to BH-03 corner(front of Gym) | Cum | 1 | 1 | 35.253 | 0.76 | 0.15 | 4.02
Deduct Previous Bill Qty. for Revise
Brick Work for Fire Tender Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 |  | -1 | 1 | 31.4 | 0.61 | 0.15 | -2.87
| FIRE TENDER TOE WALL WITH BH-07 |  | -1 | 1 | 42.55 | 0.61 | 0.15 | -3.89
P.C.C. P/L on Floor area & Road for Stone
| P.C.C. P/L for Floor (area side of Road line) Laying of Kandla Stone |  |  |  | Area
| Area-1, area between BH-01 & BH-07 south side of Road | CUM | 1 | 1 | 300.0786 |  | 0.075 | 22.51
| Area-2, BH-01 south side main entrance | CUM | 1 | 1 | 160.0868 |  | 0.075 | 12.01
| deduct Green Planter Area | CUM | -1 | 1 | 19.47 |  | 0.075 | -1.46
| Area-3, BH-01 south side main entrance | CUM | 1 | 1 | 45.5218 |  | 0.075 | 3.41
| Area-4, BH-01 south side main entrance | CUM | 1 | 1 | 241.8989 |  | 0.075 | 18.14
| deduct Green Planter Area | CUM | -1 | 1 | 50.7604 |  | 0.075 | -3.81
| deduct Green Planter Area | CUM | -1 | 1 | 43.292 |  | 0.075 | -3.25
| Area-5, BH-04 south side main entrance | CUM | 1 | 1 | 61.0155 |  | 0.075 | 4.58
| deduct Green Planter Area | CUM | -1 | 1 | 12.2755 |  | 0.075 | -0.92
| Area-6, Area between BH-04 & BH-02 , waterbody surrounding area | CUM | 1 | 1 | 628.5243 |  | 0.075 | 47.14
| deduct Waterbody Area | CUM | -1 | 1 | 341.7578 |  | 0.075 | -25.63
| deduct seat | CUM | -1 | 8 | 2.836 | 0.286 | 0.075 | -0.49
| Area-7, Area under BH-04 transfer Slab towards waterbody | CUM | 1 | 1 | 615.412 |  | 0.075 | 46.16
| deduct Green Planter area | CUM | -1 | 1 | 3.155 | 1.799 | 0.075 | -0.43
|  | CUM | -1 | 1 | 5.85 | 1.799 | 0.075 | -0.79
|  | CUM | -1 | 1 | 5.025 | 1.799 | 0.075 | -0.68
| deduct for Entrance Ramp | CUM | -1 | 1 | 3.823 | 3 | 0.075 | -0.86
| deduct for Entrance Ramp | CUM | -1 | 1 | 6 | 2 | 0.075 | -0.9
| deduct R.C.C. Wall/Col. | CUM | -1 | 5 | 5.8 | 0.8 | 0.075 | -1.74
|  | CUM | -1 | 8 | 4.5 | 1 | 0.075 | -2.7
| deduct seat | CUM | -1 | 7 | 2.836 | 0.286 | 0.075 | -0.43
area
| deduct Green Planter south side of Reception | CUM | -1 | 1 | 40.6167 |  | 0.075 | -3.05
| Area-8, west side of reception (front of Basket ball ground & BH-03) | CUM | 1 | 1 | 23.3075 |  | 0.075 | 1.75
| Area-9, north side of reception | CUM | 1 | 1 | 68.8563 |  | 0.075 | 5.16
| deduct Green Planter area | CUM | -1 | 1 | 9.36 | 0.6 | 0.075 | -0.42
|  | CUM | -1 | 1 | 8.14 | 0.6 | 0.075 | -0.37
|  | CUM | -1 | 1 | 6.616 | 0.6 | 0.075 | -0.3
|  | CUM | -1 | 1 | 4.785 | 0.6 | 0.075 | -0.22
|  | CUM | -1 | 1 | 3.26 | 0.6 | 0.075 | -0.15
| Area-10, area between BH-01 & Canteen, or under transfer slab | CUM | 1 | 1 | 608.4315 |  | 0.075 | 45.63
| deduct green planter of BH-01 north face | CUM | -1 | 1 | 5.025 | 1.194 | 0.075 | -0.45
|  | CUM | -1 | 1 | 5.85 | 1.197 | 0.075 | -0.53
| deduct R.C.C. Planter area under transfer dalb BH-01 | CUM | -1 | 9 | 4.5 | 1 | 0.075 | -3.04
| deduct R.C.C. shear wall | CUM | -1 | 5 | 5.8 | 0.8 | 0.075 | -1.74
| deduct seat | CUM | -1 | 6 | 2.836 | 0.286 | 0.075 | -0.36
|  | CUM | -1 | 3 | 1.2 | 0.375 | 0.075 | -0.1
| deduct for Entrance Ramp | CUM | -1 | 1 | 3.823 | 3 | 0.075 | -0.86
| deduct for Entrance Ramp | CUM | -1 | 1 | 6 | 2 | 0.075 | -0.9
area
| Area-11, at junction of Road near canteen & BH-01 towards waterbody | CUM | 1 | 1 | 77.1675 |  | 0.075 | 5.79 |  | area
| Area-12, area east side of BH-01 | CUM | 1 | 1 | 294.171 |  | 0.075 | 22.06
| deduct Green planter of BH-01 east face | CUM | -1 | 1 | 28.785 |  | 0.075 | -2.16
|  | CUM | -1 | 1 | 23.2452 |  | 0.075 | -1.74
| Area-13, area south side of BH-02 (long Planter) | CUM | 1 | 3 | 2.987 | 1.55 | 0.075 | 1.04
|  | CUM | 1 | 1 | 2.987 | 2 | 0.075 | 0.45
|  | CUM | 1 | 1 | 2.987 | 1.3 | 0.075 | 0.29
|  | CUM | 1 | 1 | 2.987 | 1.8 | 0.075 | 0.4
|  | CUM | 1 | 1 | 5.1077 |  | 0.075 | 0.38 |  | area
|  | CUM | 1 | 1 | 7.194 |  | 0.075 | 0.54 |  | area
|  | CUM | 1 | 1 | 10.7681 |  | 0.075 | 0.81 |  | area
|  | CUM | 1 | 1 | 10.941 |  | 0.075 | 0.82 |  | area
|  | CUM | 1 | 1 | 17.5006 |  | 0.075 | 1.31 |  | area
| Area-14, area south side of Toilet near Gym | CUM | 1 | 1 | 67.2189 |  | 0.075 | 5.04 |  | area
| deduct Green Planter area | CUM | -1 | 2 | 6.639 | 0.6 | 0.075 | -0.6
|  | CUM | -1 | 1 | 5.725 | 0.6 | 0.075 | -0.26
|  | CUM | -1 | 1 | 3.589 | 0.6 | 0.075 | -0.16
| Area-15, area between BH-02 long Planter & Toilet of Gym | CUM | 1 | 1 | 135.0703 |  | 0.075 | 10.13 |  | area
| Area-16, area between BH-02 & GYM Transfer Slab | CUM | 1 | 1 | 500.2299 |  | 0.075 | 37.52 |  | area
| deduct Green Planter | CUM | -1 | 1 | 0.999 | 1.2 | 0.075 | -0.09
|  | CUM | -1 | 1 | 5.85 | 1.2 | 0.075 | -0.53
|  | CUM | -1 | 1 | 5.024 | 1.2 | 0.075 | -0.45
|  | CUM | -1 | 1 | 2.399 | 1.2 | 0.075 | -0.22
| deduct for Entrance Ramp | CUM | -1 | 1 | 3.823 | 3 | 0.075 | -0.86
| deduct for Entrance Ramp | CUM | -1 | 1 | 6 | 2 | 0.075 | -0.9
| deduct R.C.C. wall Col. | CUM | -1 | 5 | 5.8 | 0.8 | 0.075 | -1.74
| deduct R.C.C. Planter area under transfer slab BH-02 | CUM | -1 | 8 | 4.5 | 1 | 0.075 | -2.7
| deduct seat | CUM | -1 | 6 | 2.836 | 0.286 | 0.075 | -0.36
| Area-17, Area north side of BH-02 | CUM | 1 | 1 | 293.7889 |  | 0.075 | 22.03 |  | area
| deduct green planter area | CUM | -1 | 1 | 61.3885 |  | 0.075 | -4.6 |  | area
| Area-18, Area north side of Canteen (J/1'-4') | CUM | 1 | 1 | 31.5 | 1.985 | 0.075 | 4.69
| deduct Col. | CUM | -1 | 4 | 1.2 | 0.375 | 0.075 | -0.14
| Area-19, Area north side gallary of BH-02 corner to Gym corner (J/5-9') | CUM | 1 | 1 | 37.9 | 4.505 | 0.075 | 12.81
| deduct Col. | CUM | -1 | 5 | 1.2 | 0.375 | 0.075 | -0.17
| Area-20, Area west side of canteen or north side of B H-03 | CUM | 1 | 1 | 24.6285 | 13.365 | 0.075 | 24.69
| deduct Col. | CUM | -1 | 5 | 1.2 | 0.375 | 0.075 | -0.17
| deduct Green Planter | CUM | -1 | 1 | 82.6623 |  | 0.075 | -6.2 |  | area
| Area-21, Area south side of Gym (8/H) | CUM | 1 | 1 | 93.578 |  | 0.075 | 7.02 |  | area
| Area-22, Area between Basket Ball Ground & BH-03, under Transfer slab | CUM | 1 | 1 | 508.5971 |  | 0.075 | 38.14 |  | area
| add area near road junction | CUM | 1 | 1 | 47.9965 |  | 0.075 | 3.6 |  | area
| deduct Green Planter | CUM | -1 | 1 | 5.025 | 1.2 | 0.075 | -0.45
|  | CUM | -1 | 1 | 5.85 | 1.2 | 0.075 | -0.53
| deduct for Entrance Ramp | CUM | -1 | 1 | 3.823 | 3 | 0.075 | -0.86
| deduct for Entrance Ramp | CUM | -1 | 1 | 6 | 2 | 0.075 | -0.9
| deduct R.C.C. wall Col. | CUM | -1 | 5 | 5.8 | 0.8 | 0.075 | -1.74
| deduct R.C.C. Planter area under transfer slab BH-02 | CUM | -1 | 8 | 4.5 | 1 | 0.075 | -2.7
| deduct seat | CUM | -1 | 4 | 2.836 | 0.286 | 0.075 | -0.24
| deduct Col. | CUM | -1 | 2 | 1.2 | 0.375 | 0.075 | -0.07
| Area-23, Area east side of BH-03 parallel to road | CUM | 1 | 1 | 103.5326 |  | 0.075 | 7.76 |  | area
| Area-24, Area east side of BH-02 parallel to road (Road between BH-02 & Canteen) | CUM | 1 | 1 | 60.3692 |  | 0.075 | 4.53 |  | area
| Area-24, towards canteen east of road (Road between BH-02 & Canteen) | CUM | 1 | 1 | 17.9818 |  | 0.075 | 1.35 |  | area
| Area-25, area between road of Basket ball ground & BH-05 | CUM | 1 | 1 | 82.809 |  | 0.075 | 6.21 |  | area
P.C.C. P/L for Road Work
| Area-1, Road between Waterbody & BH-02 (remaining portion) | CUM | 1 | 1 | 43.026 |  | 0.075 | 3.23 |  | area
| Area-2, Road between Canteen & BH-02 | CUM | 1 | 1 | 235.971 |  | 0.075 | 17.7 |  | area
| Area-3, Road south side of BH-04 | CUM | 1 | 1 | 229.3859 |  | 0.075 | 17.2 |  | area
| Area-4, Road between BH-03 & Gym | CUM | 1 | 1 | 161.3012 |  | 0.075 | 12.1 |  | area
| P.C.C. P/L for Planter between BH-01 & Canteen | Cum
Cum
| Base Footning (4500x1000) | Cum | 1 | 6 | 5 | 1.25 | 0.1 | 3.75
|  | Cum | 1 | 3 | 5 | 1.5 | 0.1 | 2.25
| P.C.C. P/L for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
P.C.C. P/L for Road Toe Wall (1/E-J)
| Previous bill qty. release 2nos panal | Cum | 1 | 2 | 7.625 | 0.76 | 0.15 | 1.74
P.C.C. Qty. Revise due to correction
P.C.C. P/L for Road Toe Wall back side of Basket Ball (east side)
|  |  | 1 | 3 | 7.625 | 0.76 | 0.15 | 2.61
PCC for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | 1 | 8 | 7.625 | 0.76 | 0.15 | 6.95
|  | Cum | 1 | 1 | 9.35 | 0.76 | 0.15 | 1.07
| P.C.C. P/L for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
| P.C.C. P/L for Road Toe Wall (1/E-J) | Cum | 1 | 1 | 4.635 | 0.76 | 0.15 | 0.53
|  | Cum | 1 | 8 | 7.625 | 0.76 | 0.15 | 6.95
|  | Cum | 1 | 1 | 10.14 | 0.76 | 0.15 | 1.16
| P.C.C. P/L for Road Toe Wall (J/1-9) | Cum | 1 | 1 | 13.91 | 0.76 | 0.15 | 1.59
|  | Cum | 1 | 5 | 7.625 | 0.76 | 0.15 | 4.35
|  | Cum | 1 | 1 | 0.265 | 0.76 | 0.15 | 0.03
| P.C.C. P/L for Road Toe Wall (9/H-J) | Cum | 1 | 1 | 7.38 | 0.76 | 0.15 | 0.84
|  | Cum | 1 | 2 | 7.625 | 0.76 | 0.15 | 1.74
Previous Bill Qty. deduct for revision
P.C.C. P/L for Road Toe Wall back side of Basket Ball (east side)
|  |  | -1 | 3 | 7.625 | 0.61 | 0.15 | -2.09
Excavation for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | -1 | 8 | 7.625 | 0.61 | 0.15 | -5.58
|  | Cum | -1 | 1 | 9.35 | 0.61 | 0.15 | -0.86
| P.C.C. P/L for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
| P.C.C. P/L for Road Toe Wall (1/E-J) | Cum | -1 | 1 | 4.635 | 0.61 | 0.15 | -0.42
|  | Cum | -1 | 8 | 7.625 | 0.61 | 0.15 | -5.58
|  | Cum | -1 | 1 | 10.14 | 0.61 | 0.15 | -0.93
| P.C.C. P/L for Road Toe Wall (J/1-9) | Cum | -1 | 1 | 14.06 | 0.61 | 0.15 | -1.29
|  | Cum | -1 | 5 | 7.625 | 0.61 | 0.15 | -3.49
|  | Cum | -1 | 1 | 0.265 | 0.61 | 0.15 | -0.02
| P.C.C. P/L for Road Toe Wall (9/H-J) | Cum | -1 | 1 | 7.53 | 0.61 | 0.15 | -0.69
|  | Cum | -1 | 2 | 7.625 | 0.61 | 0.15 | -1.4
P.C.C. P/L for Sump in Waterbody
| P.C.C. P/L in Waterbody for Sump (900x900x850) | Cum | 1 | 5 | 1.5 | 1.5 | 0.1 | 1.13
| P.C.C. filling in side loose portion of sump (vertical) | Cum | 5 | 2 | 1.5 | 0.3 | 0.85 | 3.83
|  | Cum | 5 | 2 | 1.9 | 0.3 | 0.85 | 4.85
| Demolishing of P.C.C. or Stone Soling in Waterbody for Filter Pit (2000x2000x1800) | Cum | 0 | 1 | 2.6 | 1.5 | 0.1
| P.C.C. filling in side loose portion of sump (vertical) | Cum | 0 | 2 | 2.6 | 0.3 | 1.8
|  | Cum | 0 | 2 | 3 | 0.3 | 1.8
| P.C.C. P/L for Filter Pit (2000x2000x1800) for Waterbody | Cum | 1 | 1 | 2.83 | 2.83 | 0.1 | 0.8
P.C.C. P/L at Podium Lvl.
|  | Cum |  |  | L | B | H
| P.C.C. P/L at Podium Lvl. Ref. tp (drg. No. TU/LA/-P-216) at grid- (H-J/2) Area-1 | Cum | 1 | 1 | 27.915 | 8 | 0.17 | 37.96
| Area-2, north side podium passage (canteen to Gym) | Cum | 1 | 1 | 37.364 | 1.25 | 0.17 | 7.94
| Area-3, north side podium passage (canteen to Gym) | Cum | 1 | 1 | 96.5296 |  | 0.17 | 16.41 |  | area
| Area-4, P.C.C. P/L for Podium passage (Canteen passage to BH-01) | Cum | 1 | 1 | 46.729 | 1.198 | 0.17 | 9.52
| Area-5, P.C.C. P/L for Podium Passage BH-07 & BH-01 | Cum | 1 | 1 | 6.098 | 3.05 | 0.17 | 3.16
|  | Cum | 1 | 1 | 1.2 | 3.3 | 0.17 | 0.67
|  | Cum | 1 | 1 | 180.194 |  | 0.17 | 30.63 |  | area
|  | Cum | 1 | 1 | 72.8718 |  | 0.17 | 12.39 |  | area
| Area-6, Canteen Roof 8.0 m wide from BH-1 side | Cum | 1 | 1 | 31.5 | 8 | 0.12 | 30.24
| Area-7, Slab near ST-04 (Ramp) Grid H/1~Canteen | Cum | 1 | 1 | 11.775 | 7.28 | 0.12 | 10.29
|  | Cum | 1 | 1 | 24.152 | 2.28 | 0.12 | 6.61 |  | Parallel to St-04
| Area-8, Slab Between Canteen & BH-02 | Cum | 1 | 1 | 160.975 |  | 0.12 | 19.32 |  | Area=160.975 Sqm.
| Area-9, Walkway from Area-8 towards BH-4 (Up to Expansion joint) | Cum | 1 | 1 | 48.375 | 1.5 | 0.17 | 12.34
| Area-10, Walkway from Gym to BH-4 South side | Cum | 1 | 1 | 79.667 | 1.5 | 0.17 | 20.32 |  | 10 Rmt Balance towards Gym
| Area-11, Trapizoidal Slab at South side of BH-04 (Near Spiral staircase) | Cum | 1 | 1 | 140.415 |  | 0.17 | 23.87 |  | Area=140.415 Sqm.
| Area-12, Podium Level Slab Over Gym | Cum | 1 | 1 | 32.165 | 19.715 | 0.12 | 76.1
Revise Qty. due to correction in 3rd R.A.Bill
| add for previous bill correct quantity | Cum | 1 | 1 | 580.43 | 6 | 0.075 | 261.19
| deduct area not done | Cum | -1 | 1 | 4.798 | 6 | 0.075 | -2.16
P.C.C. P/L for Brick Work for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22)
| longitudianal axies | Cum | 1 | 2 | 7.07 | 0.61 | 0.15 | 1.29
| Transverse axies | Cum | 1 | 2 | 1.8 | 0.61 | 0.15 | 0.33
| longitudianal axies | Cum | 1 | 2 | 5.715 | 0.61 | 0.15 | 1.05
| Transverse axies | Cum | 1 | 2 | 1.8 | 0.61 | 0.15 | 0.33
P.C.C. P/L for Brick Work for Green Planter South side of BH-03 towards Basket Ball Ground (Drg. No. TU/LA-P-206.1) (26'-27'/46-51)
| longitudianal axies | Cum | 1 | 2 | 7.07 | 0.61 | 0.15 | 1.29
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.61 | 0.15 | 0.22
| longitudianal axies | Cum | 1 | 2 | 5.715 | 0.61 | 0.15 | 1.05
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.61 | 0.15 | 0.22
P.C.C. P/L for Brick Work for Green Planter West side of BH-02 under transfer slab (Drg. No. TU/LA-P-206.1) (7'-14'/32-33)
| longitudianal axies | Cum | 1 | 2 | 7.07 | 0.61 | 0.15 | 1.29
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.61 | 0.15 | 0.22
| longitudianal axies | Cum | 1 | 2 | 5.715 | 0.61 | 0.15 | 1.05
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.61 | 0.15 | 0.22
| longitudianal axies | Cum | 1 | 2 | 3.845 | 0.61 | 0.15 | 0.7
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.61 | 0.15 | 0.22
| longitudianal axies | Cum | 1 | 2 | 3.62 | 0.61 | 0.15 | 0.66
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.61 | 0.15 | 0.22
P.C.C. P/L at west side of Basket ball ground (34'-39'/51-52)
|  | Cum | 1 | 1 | 14.65 | 0.97 | 0.075 | 1.07
| deduct R.C.C. Col. | Cum | -1 | 2 | 1.2 | 0.375 | 0.075 | -0.07
P.C.C. P/L north side of BH-01, between BH-01 Entrance Door & Green Planter towards canteen
|  | Cum | 1 | 1 | 15 | 0.6 | 0.075 | 0.68
P.C.C. P/L north side of BH-04, between BH-04 Entrance Door & Green Planter towards waterbody
|  | Cum | 1 | 1 | 15 | 0.6 | 0.075 | 0.68
P.C.C. P/L at Waterbody for final finish Lvl. Over waterbody foundation pipe
| Dia. 20.12m | Cum | 1 | 1 | 317.7793 |  | 0.2 | 63.56
P.C.C. P/L at top of Seprate Seat on Podium
| P.C.C. on Seat at Canteen Podium (1000x1000) | Cum | 8 | 3 | 0.94 | 0.94 | 0.1 | 2.12
| UP TO PREVIOUS BILL | Cum | [6 empty] | 1624.9
| P.C.C. P/L for Light Pole Foundation near Basket Ball Ground (900x900) | Cum | 2 | 1 | 1.05 | 1.05 | 0.075 | 0.17
| P.C.C. on top Floor after earth backfilling for Stone Laying | Cum | 2 | 1 | 1.65 | 1.65 | 0.075 | 0.41
| P.C.C. P/L for Basket Ball Ground Pole Foundation (1500x1500) | Cum | 2 | 1 | 1.65 | 1.65 | 0.075 | 0.41
| P.C.C. on top Floor after earth backfilling for Stone Laying | Cum | 2 | 1 | 2.25 | 2.25 | 0.075 | 0.76
| THIS BILL TOTAL → | Cum | [6 empty] | 1.75 | 6th RA
1626.65
HARDCORE
2 | Providing and laying 100 mm Hardcore sub-base with stome aggregate 63 to 40 mm size as per structural specification and approved binding material including cleaning, sorting, spreading, packing and consolidation with half tonne roller to template etc. complete
Stone Agg. 90 to 45mm in Road
| Road between BH-05 & B3 Basket Ground | Cum | 1 | 1 | 29.2 | 6 | 0.1 | 17.52
|  | Cum | 1 | 1 | 8.32 | 6.78 | 0.1 | 5.64
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 23.235 | 6 | 0.1 | 13.94
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 2.275 | 6 | 0.1 | 1.37
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 32.39 | 6 | 0.1 | 19.43
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 5.295 | 6 | 0.1 | 3.18
| Road between BH-01 & Waterboy (east side) | Cum | 1 | 1 | 31.463 | 6 | 0.1 | 18.88
| Road between BH-01 & BH-07 (south side) | Cum | 1 | 1 | 33.193 | 6 | 0.1 | 19.92
|  | Cum | 1 | 1 | 29.854 | 6 | 0.1 | 17.91
|  | Cum | 1 | 1 | 33.667 | 6 | 0.1 | 20.2
|  | Cum | 1 | 1 | 12.3 | 6 | 0.1 | 7.38
WBM in Road Area
| Area-1, Road between BH-01 & BH-07 | Cum | 1 | 1 | 514.7 |  | 0.1 | 51.47
| Area-2, Road between BH-04 & west corner of BH-01 | Cum | 1 | 1 | 169.79 |  | 0.1 | 16.98
| deduct area not done | Cum | -1 | 1 | 6.545 | 6 | 0.1 | -3.93
| Area-3, Road between BH-01 west side & waterbody | Cum | 1 | 1 | 580.43 |  | 0.1 | 58.04
| Area-4, Road between BH-04 west side | Cum | 1 | 1 | 628.19 |  | 0.1 | 62.82
| Area-5, Road between BH-05 north side & Basket Ball Ground | Cum | 1 | 1 | 303.47 |  | 0.1 | 30.35
| Area-6, Road front BH-05 east side | Cum | 1 | 1 | 165.9 |  | 0.1 | 16.59
| 40% | Cum | -1 |  | 151.076 |  |  | -151.08
WBM P/L for Road Work
| Area-1, Road between Waterbody & BH-02 (remaining portion) | Cum | 1 | 1 | 43.026 |  | 0.1 | 4.3 |  | area
| Area-2, Road between Canteen & BH-02 | Cum | 1 | 1 | 235.971 |  | 0.1 | 23.6 |  | area
| Area-3, Road south side of BH-04 | Cum | 1 | 1 | 229.3859 |  | 0.1 | 22.94 |  | area
| Area-4, Road between BH-03 & Gym | Cum | 1 | 1 | 161.3012 |  | 0.1 | 16.13 |  | area
Cum
Revise Qty. due to correction in 3rd R.A.Bill
| Area-2, Road between BH-04 & west corner of BH-01 | Cum | 0
| add area for correction | Cum | 1 | 1 | 6.545 | 6 | 0.125 | 4.91
| deduct area not done (revise measurement) | Cum | -1 | 1 | 4.798 | 6 | 0.125 | -3.6
| release 40% (ref. to previous bill hold qty.) | Cum | 1 | 1 | 151.076 |  |  | 151.08
| UP TO PREVIOUS BILL | Cum | [6 empty] | 445.97
| THIS BILL TOTAL → | Cum | [6 empty] | 0
445.97
BRICKWORK
3 | Brickwork with bricks of class designation 75 in foundations, plinth and superstructure in cement mortar 1:4 (1 cement : 4 coarse sand) (Quantity may vary as per actual drawings)
| Planter BH-01 NORTH SIDE | Cum
| G 32-37/1-5 vertical | Cum | 1 |  | 11.61 | 0.46 | 0.3 | 1.6
|  | Cum | 1 |  | 11.38 | 0.345 | 0.3 | 1.18
|  | Cum | 1 |  | 11.15 | 0.23 | 0.19 | 0.49
|  | Cum | 1 |  | 9.15 | 0.46 | 0.3 | 1.26
|  | Cum | 1 |  | 9.035 | 0.345 | 0.3 | 0.94
|  | Cum | 1 |  | 8.92 | 0.23 | 0.19 | 0.39
|  | Cum | 1 |  | 9.15 | 0.46 | 0.3 | 1.26
|  | Cum | 1 |  | 9.035 | 0.345 | 0.3 | 0.94
|  | Cum | 1 |  | 8.92 | 0.23 | 0.19 | 0.39
|  | Cum | 1 |  | 2.26 | 0.46 | 0.3 | 0.31
|  | Cum | 1 |  | 2.145 | 0.345 | 0.3 | 0.22
|  | Cum | 1 |  | 2.03 | 0.23 | 0.19 | 0.09
|  | Cum | 1 |  | 7.35 | 0.46 | 0.3 | 1.01
|  | Cum | 1 |  | 7.235 | 0.345 | 0.3 | 0.75
|  | Cum | 1 |  | 7.12 | 0.23 | 0.19 | 0.31
|  | Cum | 2 |  | 6.75 | 0.46 | 0.3 | 1.86
|  | Cum | 2 |  | 6.635 | 0.345 | 0.3 | 1.37
|  | Cum | 2 |  | 6.52 | 0.23 | 0.19 | 0.57
|  | Cum | 2 |  | 6.91 | 0.46 | 0.3 | 1.91
|  | Cum | 2 |  | 6.68 | 0.345 | 0.3 | 1.38
|  | Cum | 2 |  | 6.45 | 0.23 | 0.19 | 0.56
|  | Cum | 1 |  | 4.89 | 0.46 | 0.3 | 0.67
|  | Cum | 1 |  | 4.775 | 0.345 | 0.3 | 0.49
|  | Cum | 1 |  | 4.66 | 0.23 | 0.19 | 0.2
|  | Cum | 1 |  | 7.35 | 0.46 | 0.3 | 1.01
|  | Cum | 1 |  | 7.12 | 0.345 | 0.3 | 0.74
|  | Cum | 1 |  | 6.89 | 0.23 | 0.19 | 0.3
| Grid 32-37/1-5 horizontal | Cum | 5 |  | 0.615 | 0.46 | 0.3 | 0.42
|  | Cum | 5 |  | 0.615 | 0.345 | 0.3 | 0.32
|  | Cum | 5 |  | 0.615 | 0.23 | 0.19 | 0.13
|  | Cum | 1 |  | 3.36 | 0.46 | 0.3 | 0.46
|  | Cum | 1 |  | 3.36 | 0.345 | 0.3 | 0.35
|  | Cum | 1 |  | 3.36 | 0.23 | 0.19 | 0.15
|  | Cum | 1 |  | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 |  | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 |  | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 3 |  | 1.21 | 0.46 | 0.3 | 0.5
|  | Cum | 3 |  | 1.44 | 0.345 | 0.3 | 0.45
|  | Cum | 3 |  | 1.67 | 0.23 | 0.19 | 0.22
|  | Cum | 3 |  | 2.285 | 0.46 | 0.3 | 0.95
|  | Cum | 3 |  | 2.4 | 0.345 | 0.3 | 0.75
|  | Cum | 3 |  | 2.515 | 0.23 | 0.19 | 0.33
| SEAT | Cum | 4 |  | 3 | 0.115 | 0.355 | 0.49
|  | Cum | 4 |  | 3 | 0.3 | 0.225 | 0.81
| BH01-NORTH SIDE | Cum
| Bet G 31-28 /1-5 vertical | Cum | 1 |  | 6.45 | 0.46 | 0.3 | 0.89
|  | Cum | 1 |  | 6.22 | 0.345 | 0.3 | 0.64
|  | Cum | 1 |  | 5.99 | 0.23 | 0.19 | 0.26
|  | Cum | 1 |  | 4.45 | 0.46 | 0.3 | 0.61
|  | Cum | 1 |  | 4.22 | 0.345 | 0.3 | 0.44
|  | Cum | 1 |  | 3.99 | 0.23 | 0.19 | 0.17
|  | Cum | 2 |  | 2.19 | 0.46 | 0.3 | 0.6
|  | Cum | 2 |  | 2.075 | 0.345 | 0.3 | 0.43
|  | Cum | 2 |  | 1.96 | 0.23 | 0.19 | 0.17
|  | Cum | 2 |  | 3.25 | 0.46 | 0.3 | 0.9
|  | Cum | 2 |  | 3.02 | 0.345 | 0.3 | 0.63
|  | Cum | 2 |  | 2.79 | 0.23 | 0.19 | 0.24
|  | Cum | 1 |  | 1.89 | 0.46 | 0.3 | 0.26
|  | Cum | 1 |  | 1.775 | 0.345 | 0.3 | 0.18
|  | Cum | 1 |  | 1.66 | 0.23 | 0.19 | 0.07
|  | Cum | 1 |  | 4.35 | 0.46 | 0.3 | 0.6
|  | Cum | 1 |  | 4.12 | 0.345 | 0.3 | 0.43
|  | Cum | 1 |  | 3.89 | 0.23 | 0.19 | 0.17
| Bet. G 31-28/1-5 horizontal | Cum | 5 |  | 0.615 | 0.46 | 0.3 | 0.42
|  | Cum | 5 |  | 0.615 | 0.345 | 0.3 | 0.32
|  | Cum | 5 |  | 0.615 | 0.23 | 0.19 | 0.13
|  | Cum | 3 |  | 1.21 | 0.46 | 0.3 | 0.5
|  | Cum | 3 |  | 1.44 | 0.345 | 0.3 | 0.45
|  | Cum | 3 |  | 1.67 | 0.23 | 0.19 | 0.22
|  | Cum | 3 |  | 2.285 | 0.46 | 0.3 | 0.95
|  | Cum | 3 |  | 2.4 | 0.345 | 0.3 | 0.75
|  | Cum | 3 |  | 2.515 | 0.23 | 0.19 | 0.33
| BH-02 EAST SIDE BET G 20-28/1-6 VERTICAL | Cum | 1 |  | 10.075 | 0.46 | 0.3 | 1.39
|  | Cum | 1 |  | 9.845 | 0.345 | 0.3 | 1.02
|  | Cum | 1 |  | 9.615 | 0.23 | 0.19 | 0.42
|  | Cum | 2 |  | 7.475 | 0.46 | 0.3 | 2.06
|  | Cum | 2 |  | 7.36 | 0.345 | 0.3 | 1.52
|  | Cum | 2 |  | 7.245 | 0.23 | 0.19 | 0.63
|  | Cum | 1 |  | 7.935 | 0.46 | 0.3 | 1.1
|  | Cum | 1 |  | 7.475 | 0.345 | 0.3 | 0.77
|  | Cum | 1 |  | 7.615 | 0.23 | 0.19 | 0.33
|  | Cum | 1 |  | 4.12 | 0.46 | 0.3 | 0.57
|  | Cum | 1 |  | 4.005 | 0.345 | 0.3 | 0.41
|  | Cum | 1 |  | 3.89 | 0.23 | 0.19 | 0.17
|  | Cum | 1 |  | 4.58 | 0.46 | 0.3 | 0.63
|  | Cum | 1 |  | 4.35 | 0.345 | 0.3 | 0.45
|  | Cum | 1 |  | 4.12 | 0.23 | 0.19 | 0.18
|  | Cum | 2 |  | 4.425 | 0.46 | 0.3 | 1.22
|  | Cum | 2 |  | 4.31 | 0.345 | 0.3 | 0.89
|  | Cum | 2 |  | 4.195 | 0.23 | 0.19 | 0.37
|  | Cum | 1 |  | 3.785 | 0.46 | 0.3 | 0.52
|  | Cum | 1 |  | 3.67 | 0.345 | 0.3 | 0.38
|  | Cum | 1 |  | 3.555 | 0.23 | 0.19 | 0.16
|  | Cum | 1 |  | 4.245 | 0.46 | 0.3 | 0.59
|  | Cum | 1 |  | 4.015 | 0.345 | 0.3 | 0.42
|  | Cum | 1 |  | 3.785 | 0.23 | 0.19 | 0.17
|  | Cum | 1 |  | 2.87 | 0.46 | 0.3 | 0.4
|  | Cum | 1 |  | 2.755 | 0.345 | 0.3 | 0.29
|  | Cum | 1 |  | 2.64 | 0.23 | 0.19 | 0.12
|  | Cum | 1 |  | 3.33 | 0.46 | 0.3 | 0.46
|  | Cum | 1 |  | 3.1 | 0.345 | 0.3 | 0.32
|  | Cum | 1 |  | 2.87 | 0.23 | 0.19 | 0.13
|  | Cum | 1 |  | 2.72 | 0.46 | 0.3 | 0.38
|  | Cum | 1 |  | 2.49 | 0.345 | 0.3 | 0.26
|  | Cum | 1 |  | 2.26 | 0.23 | 0.19 | 0.1
|  | Cum | 1 |  | 3.03 | 0.46 | 0.3 | 0.42
|  | Cum | 1 |  | 2.8 | 0.345 | 0.3 | 0.29
|  | Cum | 1 |  | 2.57 | 0.23 | 0.19 | 0.11
| BH-02 EAST SIDE BET G 20-28/1-6 Horizontal | Cum | 5 |  | 0.6 | 0.46 | 0.3 | 0.41
|  | Cum | 5 |  | 0.6 | 0.345 | 0.3 | 0.31
|  | Cum | 5 |  | 0.6 | 0.23 | 0.19 | 0.13
|  | Cum | 6 |  | 1.08 | 0.46 | 0.3 | 0.89
|  | Cum | 6 |  | 1.31 | 0.345 | 0.3 | 0.81
|  | Cum | 6 |  | 1.54 | 0.23 | 0.19 | 0.4
|  | Cum | 1 |  | 3.205 | 0.46 | 0.3 | 0.44
|  | Cum | 1 |  | 3.205 | 0.345 | 0.3 | 0.33
|  | Cum | 1 |  | 3.205 | 0.23 | 0.19 | 0.14
|  | Cum | 4 |  | 2.14 | 0.46 | 0.3 | 1.18
|  | Cum | 4 |  | 2.255 | 0.345 | 0.3 | 0.93
|  | Cum | 4 |  | 2.37 | 0.23 | 0.19 | 0.41
|  | Cum | 1 |  | 3.2 | 0.46 | 0.3 | 0.44
|  | Cum | 1 |  | 3.2 | 0.345 | 0.3 | 0.33
|  | Cum | 1 |  | 3.2 | 0.23 | 0.19 | 0.14
|  | Cum | 1 |  | 2.6 | 0.46 | 0.3 | 0.36
|  | Cum | 1 |  | 2.6 | 0.345 | 0.3 | 0.27
|  | Cum | 1 |  | 2.6 | 0.23 | 0.19 | 0.11
| SEAT | Cum | 4 |  | 3 | 0.115 | 0.355 | 0.49
|  | Cum | 4 |  | 3 | 0.3 | 0.225 | 0.81
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 9.72 | 0.46 | 0.3 | 1.34
| BET.G 17-21/20-25 | Cum | 1 |  | 9.49 | 0.345 | 0.3 | 0.98
|  | Cum | 1 |  | 9.26 | 0.23 | 0.19 | 0.4
|  | Cum | 1 |  | 7.92 | 0.46 | 0.3 | 1.09
|  | Cum | 1 |  | 7.69 | 0.345 | 0.3 | 0.8
|  | Cum | 1 |  | 7.46 | 0.23 | 0.19 | 0.33
|  | Cum | 1 |  | 8.92 | 0.46 | 0.3 | 1.23
|  | Cum | 1 |  | 8.69 | 0.345 | 0.3 | 0.9
|  | Cum | 1 |  | 8.46 | 0.23 | 0.19 | 0.37
|  | Cum | 1 |  | 8.46 | 0.46 | 0.3 | 1.17
|  | Cum | 1 |  | 8.345 | 0.345 | 0.3 | 0.86
|  | Cum | 1 |  | 8.23 | 0.23 | 0.19 | 0.36
|  | Cum | 1 |  | 7.92 | 0.46 | 0.3 | 1.09
|  | Cum | 1 |  | 7.69 | 0.345 | 0.3 | 0.8
|  | Cum | 1 |  | 7.46 | 0.23 | 0.19 | 0.33
|  | Cum | 1 |  | 7.92 | 0.46 | 0.3 | 1.09
|  | Cum | 1 |  | 7.69 | 0.345 | 0.3 | 0.8
|  | Cum | 1 |  | 7.46 | 0.23 | 0.19 | 0.33
|  | Cum | 3 |  | 5.42 | 0.46 | 0.3 | 2.24
|  | Cum | 3 |  | 5.19 | 0.345 | 0.3 | 1.61
|  | Cum | 3 |  | 4.96 | 0.23 | 0.19 | 0.65
|  | Cum | 1 |  | 8.42 | 0.46 | 0.3 | 1.16
|  | Cum | 1 |  | 8.19 | 0.345 | 0.3 | 0.85
|  | Cum | 1 |  | 7.96 | 0.23 | 0.19 | 0.35
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Cum
| BET.G 17-21/20-25 | Cum | 8 |  | 0.615 | 0.46 | 0.3 | 0.68
|  | Cum | 8 |  | 0.615 | 0.345 | 0.3 | 0.51
|  | Cum | 8 |  | 0.615 | 0.23 | 0.19 | 0.22
|  | Cum | 2 |  | 1.515 | 0.46 | 0.3 | 0.42
|  | Cum | 2 |  | 1.745 | 0.345 | 0.3 | 0.36
|  | Cum | 2 |  | 1.975 | 0.23 | 0.19 | 0.17
|  | Cum | 2 |  | 2.285 | 0.46 | 0.3 | 0.63
|  | Cum | 2 |  | 2.4 | 0.345 | 0.3 | 0.5
|  | Cum | 2 |  | 2.515 | 0.23 | 0.19 | 0.22
|  | Cum | 4 |  | 1.21 | 0.46 | 0.3 | 0.67
|  | Cum | 4 |  | 1.44 | 0.345 | 0.3 | 0.6
|  | Cum | 4 |  | 1.67 | 0.23 | 0.19 | 0.29
| SEAT | Cum
|  | Cum | 4 |  | 3 | 0.115 | 0.355 | 0.49
|  | Cum | 4 |  | 3 | 0.3 | 0.225 | 0.81
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum
| BET.G 17-21/25-29 | Cum | 1 |  | 8.92 | 0.46 | 0.3 | 1.23
|  | Cum | 1 |  | 8.69 | 0.345 | 0.3 | 0.9
|  | Cum | 1 |  | 8.46 | 0.23 | 0.19 | 0.37
|  | Cum | 1 |  | 6.66 | 0.46 | 0.3 | 0.92
|  | Cum | 1 |  | 6.545 | 0.345 | 0.3 | 0.68
|  | Cum | 1 |  | 6.43 | 0.23 | 0.19 | 0.28
|  | Cum | 2 |  | 7.12 | 0.46 | 0.3 | 1.97
|  | Cum | 2 |  | 6.89 | 0.345 | 0.3 | 1.43
|  | Cum | 2 |  | 6.66 | 0.23 | 0.19 | 0.58
|  | Cum | 2 |  | 8.12 | 0.46 | 0.3 | 2.24
|  | Cum | 2 |  | 7.89 | 0.345 | 0.3 | 1.63
|  | Cum | 2 |  | 7.66 | 0.23 | 0.19 | 0.67
|  | Cum | 1 |  | 8.46 | 0.46 | 0.3 | 1.17
|  | Cum | 1 |  | 8.345 | 0.345 | 0.3 | 0.86
|  | Cum | 1 |  | 8.23 | 0.23 | 0.19 | 0.36
|  | Cum | 1 |  | 10.72 | 0.46 | 0.3 | 1.48
|  | Cum | 1 |  | 10.49 | 0.345 | 0.3 | 1.09
|  | Cum | 1 |  | 10.26 | 0.23 | 0.19 | 0.45
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Cum
| BET.G 17-21/25-29 | Cum | 6 |  | 0.615 | 0.46 | 0.3 | 0.51
|  | Cum | 6 |  | 0.615 | 0.345 | 0.3 | 0.38
|  | Cum | 6 |  | 0.615 | 0.23 | 0.19 | 0.16
|  | Cum | 2 |  | 2.285 | 0.46 | 0.3 | 0.63
|  | Cum | 2 |  | 2.4 | 0.345 | 0.3 | 0.5
|  | Cum | 2 |  | 2.515 | 0.23 | 0.19 | 0.22
|  | Cum | 4 |  | 1.21 | 0.46 | 0.3 | 0.67
|  | Cum | 4 |  | 1.44 | 0.345 | 0.3 | 0.6
|  | Cum | 4 |  | 1.67 | 0.23 | 0.19 | 0.29
| SEAT | Cum
|  | Cum | 4 |  | 3 | 0.115 | 0.355 | 0.49
|  | Cum | 4 |  | 3 | 0.3 | 0.225 | 0.81
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 7.7 | 0.46 | 0.3 | 1.06
| BET.G 17-21/29-35 | Cum | 1 |  | 7.47 | 0.345 | 0.3 | 0.77
|  | Cum | 1 |  | 7.24 | 0.23 | 0.19 | 0.32
|  | Cum | 1 |  | 5.46 | 0.46 | 0.3 | 0.75
|  | Cum | 1 |  | 5.345 | 0.345 | 0.3 | 0.55
|  | Cum | 1 |  | 5.23 | 0.23 | 0.19 | 0.23
|  | Cum | 1 |  | 4.46 | 0.46 | 0.3 | 0.62
|  | Cum | 1 |  | 4.345 | 0.345 | 0.3 | 0.45
|  | Cum | 1 |  | 4.23 | 0.23 | 0.19 | 0.18
|  | Cum | 1 |  | 4.92 | 0.46 | 0.3 | 0.68
|  | Cum | 1 |  | 4.69 | 0.345 | 0.3 | 0.49
|  | Cum | 1 |  | 4.46 | 0.23 | 0.19 | 0.19
|  | Cum | 3 |  | 3.46 | 0.46 | 0.3 | 1.43
|  | Cum | 3 |  | 3.345 | 0.345 | 0.3 | 1.04
|  | Cum | 3 |  | 3.23 | 0.23 | 0.19 | 0.42
|  | Cum | 1 |  | 5.46 | 0.46 | 0.3 | 0.75
|  | Cum | 1 |  | 5.345 | 0.345 | 0.3 | 0.55
|  | Cum | 1 |  | 5.23 | 0.23 | 0.19 | 0.23
|  | Cum | 1 |  | 5.92 | 0.46 | 0.3 | 0.82
|  | Cum | 1 |  | 5.69 | 0.345 | 0.3 | 0.59
|  | Cum | 1 |  | 5.46 | 0.23 | 0.19 | 0.24
|  | Cum | 1 |  | 4.92 | 0.46 | 0.3 | 0.68
|  | Cum | 1 |  | 4.69 | 0.345 | 0.3 | 0.49
|  | Cum | 1 |  | 4.46 | 0.23 | 0.19 | 0.19
|  | Cum | 1 |  | 4.46 | 0.46 | 0.3 | 0.62
|  | Cum | 1 |  | 4.345 | 0.345 | 0.3 | 0.45
|  | Cum | 1 |  | 4.23 | 0.23 | 0.19 | 0.18
|  | Cum | 1 |  | 5.72 | 0.46 | 0.3 | 0.79
|  | Cum | 1 |  | 5.49 | 0.345 | 0.3 | 0.57
|  | Cum | 1 |  | 5.26 | 0.23 | 0.19 | 0.23
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Cum
| BET.G 17-21/29-35 | Cum | 5 |  | 0.615 | 0.46 | 0.3 | 0.42
|  | Cum | 5 |  | 0.615 | 0.345 | 0.3 | 0.32
|  | Cum | 5 |  | 0.615 | 0.23 | 0.19 | 0.13
Cum
|  | Cum | 3 |  | 3.36 | 0.46 | 0.3 | 1.39
|  | Cum | 3 |  | 3.36 | 0.345 | 0.3 | 1.04
|  | Cum | 3 |  | 3.36 | 0.23 | 0.19 | 0.44
Cum
|  | Cum | 6 |  | 1.21 | 0.46 | 0.3 | 1
|  | Cum | 6 |  | 1.44 | 0.345 | 0.3 | 0.89
|  | Cum | 6 |  | 1.67 | 0.23 | 0.19 | 0.44
|  | Cum | 1 |  | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 |  | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 |  | 2.515 | 0.23 | 0.19 | 0.11
| SEAT | Cum | 4 |  | 3 | 0.115 | 0.355 | 0.49
|  | Cum | 4 |  | 3 | 0.3 | 0.225 | 0.81
| PLANTER BET -04 AND BH-05 VERTICAL | Cum
| BET.G 32-36/39-47 | Cum | 1 |  | 4.76 | 0.46 | 0.3 | 0.66
|  | Cum | 1 |  | 4.53 | 0.345 | 0.3 | 0.47
|  | Cum | 1 |  | 4.3 | 0.23 | 0.19 | 0.19
|  | Cum | 1 |  | 1.94 | 0.46 | 0.3 | 0.27
|  | Cum | 1 |  | 1.825 | 0.345 | 0.3 | 0.19
|  | Cum | 1 |  | 1.71 | 0.23 | 0.19 | 0.07
|  | Cum | 4 |  | 2.84 | 0.46 | 0.3 | 1.57
|  | Cum | 4 |  | 2.725 | 0.345 | 0.3 | 1.13
|  | Cum | 4 |  | 2.61 | 0.23 | 0.19 | 0.46
|  | Cum | 2 |  | 4.94 | 0.46 | 0.3 | 1.36
|  | Cum | 2 |  | 4.825 | 0.345 | 0.3 | 1
|  | Cum | 2 |  | 4.71 | 0.23 | 0.19 | 0.41
|  | Cum | 2 |  | 4.64 | 0.46 | 0.3 | 1.28
|  | Cum | 2 |  | 4.525 | 0.345 | 0.3 | 0.94
|  | Cum | 2 |  | 4.41 | 0.23 | 0.19 | 0.39
|  | Cum | 2 |  | 5.54 | 0.46 | 0.3 | 1.53
|  | Cum | 2 |  | 5.425 | 0.345 | 0.3 | 1.12
|  | Cum | 2 |  | 5.31 | 0.23 | 0.19 | 0.46
|  | Cum | 2 |  | 6.44 | 0.46 | 0.3 | 1.78
|  | Cum | 2 |  | 6.325 | 0.345 | 0.3 | 1.31
|  | Cum | 2 |  | 6.21 | 0.23 | 0.19 | 0.54
|  | Cum | 1 |  | 9.6 | 0.46 | 0.3 | 1.32
|  | Cum | 1 |  | 9.37 | 0.345 | 0.3 | 0.97
|  | Cum | 1 |  | 9.14 | 0.23 | 0.19 | 0.4
|  | Cum | 1 |  | 11.6 | 0.46 | 0.3 | 1.6
|  | Cum | 1 |  | 11.37 | 0.345 | 0.3 | 1.18
|  | Cum | 1 |  | 11.14 | 0.23 | 0.19 | 0.49
| PLANTER BET -04 AND BH-05 HORIZONTAL | Cum | 3 |  | 0.615 | 0.46 | 0.3 | 0.25
| BET.G 32-36/39-47 | Cum | 3 |  | 0.615 | 0.345 | 0.3 | 0.19
|  | Cum | 3 |  | 0.615 | 0.23 | 0.19 | 0.08
|  | Cum | 6 |  | 3.36 | 0.46 | 0.3 | 2.78
|  | Cum | 6 |  | 3.36 | 0.345 | 0.3 | 2.09
|  | Cum | 6 |  | 3.36 | 0.23 | 0.19 | 0.88
|  | Cum | 7 |  | 1.21 | 0.46 | 0.3 | 1.17
|  | Cum | 7 |  | 1.44 | 0.345 | 0.3 | 1.04
|  | Cum | 7 |  | 1.67 | 0.23 | 0.19 | 0.51
|  | Cum | 1 |  | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 |  | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 |  | 2.515 | 0.23 | 0.19 | 0.11
| SEAT | Cum | 4 |  | 3 | 0.115 | 0.355 | 0.49
|  | Cum | 4 |  | 3 | 0.3 | 0.225 | 0.81
| PLANTER NEAR ZYM Vertical | Cum | 1 |  | 8.32 | 0.46 | 0.3 | 1.15
| BET.G 2-11/48-52 | Cum | 1 |  | 8.09 | 0.345 | 0.3 | 0.84
|  | Cum | 1 |  | 7.86 | 0.23 | 0.19 | 0.34
|  | Cum | 1 |  | 5.86 | 0.46 | 0.3 | 0.81
|  | Cum | 1 |  | 5.745 | 0.345 | 0.3 | 0.59
|  | Cum | 1 |  | 5.63 | 0.23 | 0.19 | 0.25
|  | Cum | 2 |  | 6.46 | 0.46 | 0.3 | 1.78
|  | Cum | 2 |  | 6.345 | 0.345 | 0.3 | 1.31
|  | Cum | 2 |  | 6.23 | 0.23 | 0.19 | 0.54
|  | Cum | 2 |  | 5.26 | 0.46 | 0.3 | 1.45
|  | Cum | 2 |  | 5.145 | 0.345 | 0.3 | 1.07
|  | Cum | 2 |  | 5.03 | 0.23 | 0.19 | 0.44
|  | Cum | 2 |  | 6.92 | 0.46 | 0.3 | 1.91
|  | Cum | 2 |  | 6.69 | 0.345 | 0.3 | 1.38
|  | Cum | 2 |  | 6.46 | 0.23 | 0.19 | 0.56
|  | Cum | 2 |  | 4.86 | 0.46 | 0.3 | 1.34
|  | Cum | 2 |  | 4.745 | 0.345 | 0.3 | 0.98
|  | Cum | 2 |  | 4.63 | 0.23 | 0.19 | 0.4
|  | Cum | 1 |  | 5.26 | 0.46 | 0.3 | 0.73
|  | Cum | 1 |  | 5.145 | 0.345 | 0.3 | 0.53
|  | Cum | 1 |  | 5.03 | 0.23 | 0.19 | 0.22
|  | Cum | 1 |  | 5.72 | 0.46 | 0.3 | 0.79
|  | Cum | 1 |  | 5.49 | 0.345 | 0.3 | 0.57
|  | Cum | 1 |  | 5.26 | 0.23 | 0.19 | 0.23
|  | Cum | 2 |  | 4.66 | 0.46 | 0.3 | 1.29
|  | Cum | 2 |  | 4.545 | 0.345 | 0.3 | 0.94
|  | Cum | 2 |  | 4.43 | 0.23 | 0.19 | 0.39
|  | Cum | 2 |  | 6.92 | 0.46 | 0.3 | 1.91
|  | Cum | 2 |  | 6.69 | 0.345 | 0.3 | 1.38
|  | Cum | 2 |  | 6.46 | 0.23 | 0.19 | 0.56
|  | Cum | 1 |  | 6.73 | 0.46 | 0.3 | 0.93
|  | Cum | 1 |  | 6.615 | 0.345 | 0.3 | 0.68
|  | Cum | 1 |  | 6.5 | 0.23 | 0.19 | 0.28
|  | Cum | 1 |  | 8.92 | 0.46 | 0.3 | 1.23
|  | Cum | 1 |  | 8.69 | 0.345 | 0.3 | 0.9
|  | Cum | 1 |  | 8.46 | 0.23 | 0.19 | 0.37
| PLANTER NEAR ZYM HORIZONTAL | Cum
| BET.G 2-11/48-52 | Cum | 6 |  | 0.615 | 0.46 | 0.3 | 0.51
|  | Cum | 6 |  | 0.615 | 0.345 | 0.3 | 0.38
|  | Cum | 6 |  | 0.615 | 0.23 | 0.19 | 0.16
|  | Cum | 4 |  | 1.21 | 0.46 | 0.3 | 0.67
|  | Cum | 4 |  | 1.44 | 0.345 | 0.3 | 0.6
|  | Cum | 4 |  | 1.67 | 0.23 | 0.19 | 0.29
|  | Cum | 2 |  | 3.36 | 0.46 | 0.3 | 0.93
|  | Cum | 2 |  | 3.36 | 0.345 | 0.3 | 0.7
|  | Cum | 2 |  | 3.36 | 0.23 | 0.19 | 0.29
|  | Cum | 3 |  | 0.905 | 0.46 | 0.3 | 0.37
|  | Cum | 3 |  | 1.135 | 0.345 | 0.3 | 0.35
|  | Cum | 3 |  | 1.365 | 0.23 | 0.19 | 0.18
|  | Cum | 1 |  | 1.015 | 0.46 | 0.3 | 0.14
|  | Cum | 1 |  | 1.245 | 0.345 | 0.3 | 0.13
|  | Cum | 1 |  | 1.475 | 0.23 | 0.19 | 0.06
|  | Cum | 2 |  | 1.98 | 0.46 | 0.3 | 0.55
|  | Cum | 2 |  | 2.095 | 0.345 | 0.3 | 0.43
|  | Cum | 2 |  | 2.21 | 0.23 | 0.19 | 0.19
|  | Cum | 1 |  | 3.055 | 0.46 | 0.3 | 0.42
|  | Cum | 1 |  | 3.055 | 0.345 | 0.3 | 0.32
|  | Cum | 1 |  | 3.055 | 0.23 | 0.19 | 0.13
|  | Cum | 2 |  | 3.36 | 0.46 | 0.3 | 0.93
|  | Cum | 2 |  | 3.36 | 0.345 | 0.3 | 0.7
|  | Cum | 2 |  | 3.36 | 0.23 | 0.19 | 0.29
|  | Cum | 2 |  | 2.285 | 0.46 | 0.3 | 0.63
|  | Cum | 2 |  | 2.4 | 0.345 | 0.3 | 0.5
|  | Cum | 2 |  | 2.515 | 0.23 | 0.19 | 0.22
| SEAT | Cum | 8 |  | 3 | 0.115 | 0.355 | 0.98
|  | Cum | 8 |  | 3 | 0.3 | 0.225 | 1.62
| PLANTER BET. BH-04 AND BH-07 Vertical | Cum
| BET.G 13-18/42-52 | Cum | 1 |  | 10.58 | 0.46 | 0.3 | 1.46
|  | Cum | 1 |  | 10.35 | 0.345 | 0.3 | 1.07
|  | Cum | 1 |  | 10.12 | 0.23 | 0.19 | 0.44
Cum
|  | Cum | 1 |  | 8.12 | 0.46 | 0.3 | 1.12
|  | Cum | 1 |  | 8.005 | 0.345 | 0.3 | 0.83
|  | Cum | 1 |  | 7.89 | 0.23 | 0.19 | 0.34
|  | Cum | 2 |  | 9.02 | 0.46 | 0.3 | 2.49
|  | Cum | 2 |  | 8.905 | 0.345 | 0.3 | 1.84
|  | Cum | 2 |  | 8.79 | 0.23 | 0.19 | 0.77
|  | Cum | 2 |  | 6.62 | 0.46 | 0.3 | 1.83
|  | Cum | 2 |  | 6.505 | 0.345 | 0.3 | 1.35
|  | Cum | 2 |  | 6.39 | 0.23 | 0.19 | 0.56
|  | Cum | 1 |  | 8.62 | 0.46 | 0.3 | 1.19
|  | Cum | 1 |  | 8.505 | 0.345 | 0.3 | 0.88
|  | Cum | 1 |  | 8.39 | 0.23 | 0.19 | 0.37
|  | Cum | 1 |  | 11.08 | 0.46 | 0.3 | 1.53
|  | Cum | 1 |  | 10.85 | 0.345 | 0.3 | 1.12
|  | Cum | 1 |  | 10.62 | 0.23 | 0.19 | 0.46
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum
| BET.G 13-18/52-48 | Cum | 2 |  | 0.615 | 0.46 | 0.3 | 0.17
|  | Cum | 2 |  | 0.615 | 0.345 | 0.3 | 0.13
|  | Cum | 2 |  | 0.615 | 0.23 | 0.19 | 0.05
|  | Cum | 3 |  | 3.36 | 0.46 | 0.3 | 1.39
|  | Cum | 3 |  | 3.36 | 0.345 | 0.3 | 1.04
|  | Cum | 3 |  | 3.36 | 0.23 | 0.19 | 0.44
|  | Cum | 3 |  | 2.13 | 0.46 | 0.3 | 0.88
|  | Cum | 3 |  | 2.13 | 0.345 | 0.3 | 0.66
|  | Cum | 3 |  | 2.13 | 0.23 | 0.19 | 0.28
| PLANTER BET. BH-04 AND BH-07 Vertical | Cum
| BET.G 13-18/52-48 | Cum | 1 |  | 10.58 | 0.46 | 0.3 | 1.46
|  | Cum | 1 |  | 10.35 | 0.345 | 0.3 | 1.07
|  | Cum | 1 |  | 10.12 | 0.23 | 0.19 | 0.44
|  | Cum | 1 |  | 8.28 | 0.46 | 0.3 | 1.14
|  | Cum | 1 |  | 8.05 | 0.345 | 0.3 | 0.83
|  | Cum | 1 |  | 7.82 | 0.23 | 0.19 | 0.34
|  | Cum | 1 |  | 6.62 | 0.46 | 0.3 | 0.91
|  | Cum | 1 |  | 6.51 | 0.345 | 0.3 | 0.67
|  | Cum | 1 |  | 6.39 | 0.23 | 0.19 | 0.28
|  | Cum | 1 |  | 7.08 | 0.46 | 0.3 | 0.98
|  | Cum | 1 |  | 6.85 | 0.345 | 0.3 | 0.71
|  | Cum | 1 |  | 6.62 | 0.23 | 0.19 | 0.29
|  | Cum | 1 |  | 4.82 | 0.46 | 0.3 | 0.67
|  | Cum | 1 |  | 4.705 | 0.345 | 0.3 | 0.49
|  | Cum | 1 |  | 4.59 | 0.23 | 0.19 | 0.2
|  | Cum | 1 |  | 5.28 | 0.46 | 0.3 | 0.73
|  | Cum | 1 |  | 5.05 | 0.345 | 0.3 | 0.52
|  | Cum | 1 |  | 4.82 | 0.23 | 0.19 | 0.21
|  | Cum | 2 |  | 4.98 | 0.46 | 0.3 | 1.37
|  | Cum | 2 |  | 4.75 | 0.345 | 0.3 | 0.98
|  | Cum | 2 |  | 4.52 | 0.23 | 0.19 | 0.4
|  | Cum | 2 |  | 4.52 | 0.46 | 0.3 | 1.25
|  | Cum | 2 |  | 4.405 | 0.345 | 0.3 | 0.91
|  | Cum | 2 |  | 4.29 | 0.23 | 0.19 | 0.37
|  | Cum | 1 |  | 2.66 | 0.46 | 0.3 | 0.37
|  | Cum | 1 |  | 2.545 | 0.345 | 0.3 | 0.26
|  | Cum | 1 |  | 2.43 | 0.23 | 0.19 | 0.11
|  | Cum | 1 |  | 5.12 | 0.46 | 0.3 | 0.71
|  | Cum | 1 |  | 4.89 | 0.345 | 0.3 | 0.51
|  | Cum | 1 |  | 4.66 | 0.23 | 0.19 | 0.2
| SEAT | Cum | 5 |  | 3 | 0.115 | 0.355 | 0.61
|  | Cum | 5 |  | 3 | 0.3 | 0.225 | 1.01
| PLANTER BET. BH-04 AND BH-07 Vertical | Cum | 0 |  | 10.28 | 0.46 | 0.3
| BET.G 13-18/42-48 | Cum | 0 |  | 10.05 | 0.345 | 0.3
|  | Cum | 0 |  | 9.82 | 0.23 | 0.19
|  | Cum | 0 |  | 8.28 | 0.46 | 0.3
|  | Cum | 0 |  | 8.05 | 0.345 | 0.3
|  | Cum | 0 |  | 7.82 | 0.23 | 0.19
|  | Cum | 0 |  | 6.62 | 0.46 | 0.3
|  | Cum | 0 |  | 6.505 | 0.345 | 0.3
|  | Cum | 0 |  | 6.39 | 0.23 | 0.19
|  | Cum | 0 |  | 6.02 | 0.46 | 0.3
|  | Cum | 0 |  | 5.905 | 0.345 | 0.3
|  | Cum | 0 |  | 5.79 | 0.23 | 0.19
|  | Cum | 0 |  | 5.28 | 0.46 | 0.3
|  | Cum | 0 |  | 5.05 | 0.345 | 0.3
|  | Cum | 0 |  | 4.82 | 0.23 | 0.19
|  | Cum | 0 |  | 4.98 | 0.46 | 0.3
|  | Cum | 0 |  | 4.75 | 0.345 | 0.3
|  | Cum | 0 |  | 4.52 | 0.23 | 0.19
|  | Cum | 0 |  | 2.66 | 0.46 | 0.3
|  | Cum | 0 |  | 2.545 | 0.345 | 0.3
|  | Cum | 0 |  | 2.43 | 0.23 | 0.19
|  | Cum | 0 |  | 5.12 | 0.46 | 0.3
|  | Cum | 0 |  | 4.89 | 0.345 | 0.3
|  | Cum | 0 |  | 4.66 | 0.23 | 0.19
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 7 |  | 0.615 | 0.46 | 0.3 | 0.59
| BET.G 13-18/42-48 | Cum | 7 |  | 0.615 | 0.345 | 0.3 | 0.45
|  | Cum | 7 |  | 0.615 | 0.23 | 0.19 | 0.19
|  | Cum | 2 |  | 2.285 | 0.46 | 0.3 | 0.63
|  | Cum | 2 |  | 2.395 | 0.345 | 0.3 | 0.5
|  | Cum | 2 |  | 2.515 | 0.23 | 0.19 | 0.22
|  | Cum | 5 |  | 1.21 | 0.46 | 0.3 | 0.83
|  | Cum | 5 |  | 1.44 | 0.345 | 0.3 | 0.75
|  | Cum | 5 |  | 1.67 | 0.23 | 0.19 | 0.36
|  | Cum | 1 |  | 3.36 | 0.46 | 0.3 | 0.46
|  | Cum | 1 |  | 3.36 | 0.345 | 0.3 | 0.35
|  | Cum | 1 |  | 3.36 | 0.23 | 0.19 | 0.15
|  | Cum | 1 |  | 0.6 | 0.46 | 0.3 | 0.08
|  | Cum | 1 |  | 0.83 | 0.345 | 0.3 | 0.09
|  | Cum | 1 |  | 1.06 | 0.23 | 0.19 | 0.05
|  | Cum | 1 |  | 1.675 | 0.46 | 0.3 | 0.23
|  | Cum | 1 |  | 1.79 | 0.345 | 0.3 | 0.19
|  | Cum | 1 |  | 1.905 | 0.23 | 0.19 | 0.08
| SEAT | Cum | 0 |  | 3 | 0.115 | 0.355
|  | Cum | 0 |  | 3 | 0.3 | 0.225
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL HORIZONTAL | Cum
| BET.G 35-41/42-48 | Cum
Cum
|  | Cum | 1 |  | 19.45 | 0.46 | 0.3 | 2.68
|  | Cum | 1 |  | 19.22 | 0.345 | 0.3 | 1.99
|  | Cum | 1 |  | 18.99 | 0.23 | 0.19 | 0.83
Cum
|  | Cum | 1 |  | 1.94 | 0.46 | 0.3 | 0.27
|  | Cum | 1 |  | 1.825 | 0.345 | 0.3 | 0.19
|  | Cum | 1 |  | 1.71 | 0.23 | 0.19 | 0.07
Cum
|  | Cum | 6 |  | 1.535 | 0.46 | 0.3 | 1.27
|  | Cum | 6 |  | 1.305 | 0.345 | 0.3 | 0.81
|  | Cum | 6 |  | 1.075 | 0.23 | 0.19 | 0.28
Cum
|  | Cum | 3 |  | 1.515 | 0.46 | 0.3 | 0.63
|  | Cum | 3 |  | 1.745 | 0.345 | 0.3 | 0.54
|  | Cum | 3 |  | 1.975 | 0.23 | 0.19 | 0.26
Cum
|  | Cum | 2 |  | 1.21 | 0.46 | 0.3 | 0.33
|  | Cum | 2 |  | 1.44 | 0.345 | 0.3 | 0.3
|  | Cum | 2 |  | 1.67 | 0.23 | 0.19 | 0.15
Cum
|  | Cum | 1 |  | 1.76 | 0.46 | 0.3 | 0.24
|  | Cum | 1 |  | 1.645 | 0.345 | 0.3 | 0.17
|  | Cum | 1 |  | 1.53 | 0.23 | 0.19 | 0.07
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL VERTICAL | Cum
| BET.G 35-41/42-48 | Cum | 2 |  | 2 | 0.46 | 0.3 | 0.55
|  | Cum | 2 |  | 2 | 0.345 | 0.3 | 0.41
|  | Cum | 2 |  | 2 | 0.23 | 0.19 | 0.17
|  | Cum | 2 |  | 3 | 0.46 | 0.3 | 0.83
|  | Cum | 2 |  | 3 | 0.345 | 0.3 | 0.62
|  | Cum | 2 |  | 3 | 0.23 | 0.19 | 0.26
|  | Cum | 2 |  | 4.645 | 0.46 | 0.3 | 1.28
|  | Cum | 2 |  | 4.645 | 0.345 | 0.3 | 0.96
|  | Cum | 2 |  | 4.645 | 0.23 | 0.19 | 0.41
|  | Cum | 2 |  | 6.12 | 0.46 | 0.3 | 1.69
|  | Cum | 2 |  | 6.12 | 0.345 | 0.3 | 1.27
|  | Cum | 2 |  | 6.12 | 0.23 | 0.19 | 0.53
|  | Cum | 2 |  | 6.95 | 0.46 | 0.3 | 1.92
|  | Cum | 2 |  | 6.95 | 0.345 | 0.3 | 1.44
|  | Cum | 2 |  | 6.95 | 0.23 | 0.19 | 0.61
|  | Cum | 2 |  | 6.38 | 0.46 | 0.3 | 1.76
|  | Cum | 2 |  | 6.38 | 0.345 | 0.3 | 1.32
|  | Cum | 2 |  | 6.38 | 0.23 | 0.19 | 0.56
|  | Cum | 2 |  | 5.345 | 0.46 | 0.3 | 1.48
|  | Cum | 2 |  | 5.345 | 0.345 | 0.3 | 1.11
|  | Cum | 2 |  | 5.345 | 0.23 | 0.19 | 0.47
| SEAT | Cum | 3 |  | 3 | 0.115 | 0.355 | 0.37
|  | Cum | 3 |  | 3 | 0.3 | 0.225 | 0.61
| BASKET BALL LONG WALL | Cum | 2 |  | 28.46 | 0.46 | 0.3 | 7.85
|  | Cum | 2 |  | 28.23 | 0.345 | 0.3 | 5.84
|  | Cum | 2 |  | 28 | 0.23 | 0.19 | 2.45
| BASKET WALL SHORT WALL | Cum | 2 |  | 15.11 | 0.46 | 0.3 | 4.17
|  | Cum | 2 |  | 14.88 | 0.345 | 0.3 | 3.08
|  | Cum | 2 |  | 14.65 | 0.23 | 0.19 | 1.28
| SEAT | Cum | 2 |  | 3 | 0.46 | 0.355 | 0.98
|  | Cum | 2 |  | 3 | 0.3 | 0.225 | 0.41
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 34.935 | 0.46 | 0.3 | 4.82 |  | JMR NEEDED
|  | Cum | 1 |  | 34.935 | 0.345 | 0.3 | 3.62 |  | JMR NEEDED
|  | Cum | 1 |  | 34.935 | 0.23 | 0.78 | 6.27 |  | JMR NEEDED
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 15 | 0.46 | 0.3 | 2.07 |  | DIMENSION AS PER SITE
|  | Cum | 1 |  | 15 | 0.345 | 0.3 | 1.55 |  | DIMENSION AS PER SITE
|  | Cum | 1 |  | 15 | 0.23 | 0.19 | 0.66 |  | DIMENSION AS PER SITE
| FIRE TENDER TOE WALL WITH BH-01 | Cum | 1 |  | 31.4 | 0.46 | 0.3 | 4.33 |  | DIMENSION AS PER SITE
|  | Cum | 1 |  | 31.4 | 0.345 | 0.3 | 3.25 |  | DIMENSION AS PER SITE
|  | Cum | 1 |  | 31.4 | 0.23 | 0.19 | 1.37 |  | DIMENSION AS PER SITE
| FIRE TENDER TOE WALL WITH BH-07 | Cum | 1 |  | 42.55 | 0.46 | 0.3 | 5.87 |  | DIMENSION AS PER SITE
|  | Cum | 1 |  | 42.55 | 0.345 | 0.3 | 4.4 |  | DIMENSION AS PER SITE
|  | Cum | 1 |  | 42.55 | 0.23 | 0.19 | 1.86 |  | DIMENSION AS PER SITE
| TOE WALL BH-04FOR GREEN | Cum
|  | Cum | 2 |  | 33 | 0.46 | 0.3 | 9.11 |  | DIMENSION AS PER SITE
|  | Cum | 2 |  | 33 | 0.345 | 0.3 | 6.83 |  | DIMENSION AS PER SITE
|  | Cum | 2 |  | 33 | 0.23 | 0.19 | 2.88 |  | DIMENSION AS PER SITE
Brick Work for Planter (2-6/28'-31')
| (28'/2-3) | Cum | 1 | 1 | 4.35 | 0.46 | 0.3 | 0.6
|  | Cum | 1 | 1 | 4.12 | 0.345 | 0.3 | 0.43
|  | Cum | 1 | 1 | 3.89 | 0.23 | 0.19 | 0.17
|  | Cum | 1 | 1 | 1.89 | 0.46 | 0.3 | 0.26
|  | Cum | 1 | 1 | 1.775 | 0.345 | 0.3 | 0.18
|  | Cum | 1 | 1 | 1.66 | 0.23 | 0.19 | 0.07
| (29'/2-3) | Cum | 1 | 1 | 2.46 | 0.46 | 0.3 | 0.34
|  | Cum | 1 | 1 | 2.345 | 0.345 | 0.3 | 0.24
|  | Cum | 1 | 1 | 2.23 | 0.23 | 0.19 | 0.1
|  | Cum | 1 | 1 | 1.89 | 0.46 | 0.3 | 0.26
|  | Cum | 1 | 1 | 1.775 | 0.345 | 0.3 | 0.18
|  | Cum | 1 | 1 | 1.66 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 2.19 | 0.46 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.075 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 1.96 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 1.06 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 0.945 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.19 | 0.04
| (30'/2-3) | Cum | 1 | 2 | 2.19 | 0.46 | 0.3 | 0.6
|  | Cum | 1 | 2 | 2.075 | 0.345 | 0.3 | 0.43
|  | Cum | 1 | 2 | 1.96 | 0.23 | 0.19 | 0.17
| (31'/2-3) | Cum | 1 | 1 | 1.66 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.545 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 2.79 | 0.46 | 0.3 | 0.39
|  | Cum | 1 | 1 | 2.675 | 0.345 | 0.3 | 0.28
|  | Cum | 1 | 1 | 2.56 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 6.45 | 0.46 | 0.3 | 0.89
|  | Cum | 1 | 1 | 6.22 | 0.345 | 0.3 | 0.64
|  | Cum | 1 | 1 | 5.99 | 0.23 | 0.19 | 0.26
| (2-4/28'-31') | Cum | 1 | 1 | 0.61 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.61 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.61 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 2.28 | 0.46 | 0.3 | 0.31
|  | Cum | 1 | 1 | 2.395 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.51 | 0.23 | 0.19 | 0.11
| (29'/2-4) | Cum | 1 | 2 | 0.615 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 2 | 0.615 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 2 | 0.615 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 1.685 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.8 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.915 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 2.27 | 0.46 | 0.3 | 0.31
|  | Cum | 1 | 1 | 2.385 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.5 | 0.23 | 0.19 | 0.11
| (31'/2-4) | Cum | 1 | 2 | 0.615 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 2 | 0.615 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 2 | 0.615 | 0.23 | 0.19 | 0.05
Brick Work for Planter (2-6/31'-37')
| (32'/2-5) | Cum | 1 | 1 | 7.35 | 0.46 | 0.3 | 1.01
|  | Cum | 1 | 1 | 7.12 | 0.345 | 0.3 | 0.74
|  | Cum | 1 | 1 | 6.89 | 0.23 | 0.19 | 0.3
|  | Cum | 1 | 1 | 4.89 | 0.46 | 0.3 | 0.67
|  | Cum | 1 | 1 | 4.775 | 0.345 | 0.3 | 0.49
|  | Cum | 1 | 1 | 4.66 | 0.23 | 0.19 | 0.2
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
| (33'/2-5) | Cum | 1 | 1 | 4.89 | 0.46 | 0.3 | 0.67
|  | Cum | 1 | 1 | 4.775 | 0.345 | 0.3 | 0.49
|  | Cum | 1 | 1 | 4.66 | 0.23 | 0.19 | 0.2
|  | Cum | 1 | 1 | 2.02 | 0.46 | 0.3 | 0.28
|  | Cum | 1 | 1 | 1.905 | 0.345 | 0.3 | 0.2
|  | Cum | 1 | 1 | 1.79 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 5.85 | 0.46 | 0.3 | 0.81
|  | Cum | 1 | 1 | 5.735 | 0.345 | 0.3 | 0.59
|  | Cum | 1 | 1 | 5.62 | 0.23 | 0.19 | 0.25
|  | Cum | 1 | 1 | 1.06 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 0.945 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.19 | 0.04
|  | Cum | 1 | 1 | 6.75 | 0.46 | 0.3 | 0.93
|  | Cum | 1 | 1 | 6.635 | 0.345 | 0.3 | 0.69
|  | Cum | 1 | 1 | 6.52 | 0.23 | 0.19 | 0.28
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 6.75 | 0.46 | 0.3 | 0.93
|  | Cum | 1 | 1 | 6.635 | 0.345 | 0.3 | 0.69
|  | Cum | 1 | 1 | 6.52 | 0.23 | 0.19 | 0.28
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
| (35'/2-5) | Cum | 1 | 1 | 6.75 | 0.46 | 0.3 | 0.93
|  | Cum | 1 | 1 | 6.635 | 0.345 | 0.3 | 0.69
|  | Cum | 1 | 1 | 6.52 | 0.23 | 0.19 | 0.28
|  | Cum | 1 | 1 | 2.26 | 0.46 | 0.3 | 0.31
|  | Cum | 1 | 1 | 2.145 | 0.345 | 0.3 | 0.22
|  | Cum | 1 | 1 | 2.03 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 2 | 9.15 | 0.46 | 0.3 | 2.53
|  | Cum | 1 | 2 | 9.035 | 0.345 | 0.3 | 1.87
|  | Cum | 1 | 2 | 8.92 | 0.23 | 0.19 | 0.78
| (37'/2-5) | Cum | 1 | 1 | 11.61 | 0.46 | 0.3 | 1.6
|  | Cum | 1 | 1 | 11.38 | 0.345 | 0.3 | 1.18
|  | Cum | 1 | 1 | 11.15 | 0.23 | 0.19 | 0.49
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
| (2-5/32'-37') | Cum | 1 | 1 | 0.615 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.615 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.615 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 2 | 0.615 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 2 | 0.615 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 2 | 0.615 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 0.595 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.825 | 0.345 | 0.3 | 0.09
|  | Cum | 1 | 1 | 1.055 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 0.615 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.615 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.615 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 3.36 | 0.46 | 0.3 | 0.46
|  | Cum | 1 | 1 | 3.36 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.36 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 0.615 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.615 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.615 | 0.23 | 0.19 | 0.03
Brick Work for Planter (17-21/20-25)
| (20'/17-21) | Cum | 1 | 1 | 9.72 | 0.46 | 0.3 | 1.34
|  | Cum | 1 | 1 | 9.49 | 0.345 | 0.3 | 0.98
|  | Cum | 1 | 1 | 9.26 | 0.23 | 0.19 | 0.4
|  | Cum | 1 | 1 | 4.66 | 0.46 | 0.3 | 0.64
|  | Cum | 1 | 1 | 4.545 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 1 | 3.26 | 0.46 | 0.3 | 0.45
|  | Cum | 1 | 1 | 3.145 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.03 | 0.23 | 0.19 | 0.13
| (21'/17-21) | Cum | 1 | 1 | 2.26 | 0.46 | 0.3 | 0.31
|  | Cum | 1 | 1 | 2.145 | 0.345 | 0.3 | 0.22
|  | Cum | 1 | 1 | 2.03 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 6.66 | 0.46 | 0.3 | 0.92
|  | Cum | 1 | 1 | 6.545 | 0.345 | 0.3 | 0.68
|  | Cum | 1 | 1 | 6.43 | 0.23 | 0.19 | 0.28
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 8.46 | 0.46 | 0.3 | 1.17
|  | Cum | 1 | 1 | 8.345 | 0.345 | 0.3 | 0.86
|  | Cum | 1 | 1 | 8.23 | 0.23 | 0.19 | 0.36
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 1.46 | 0.46 | 0.3 | 0.2
|  | Cum | 1 | 1 | 1.345 | 0.345 | 0.3 | 0.14
|  | Cum | 1 | 1 | 1.23 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 1 | 6.46 | 0.46 | 0.3 | 0.89
|  | Cum | 1 | 1 | 6.345 | 0.345 | 0.3 | 0.66
|  | Cum | 1 | 1 | 6.23 | 0.23 | 0.19 | 0.27
|  | Cum | 1 | 1 | 3.26 | 0.46 | 0.3 | 0.45
|  | Cum | 1 | 1 | 3.145 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.03 | 0.23 | 0.19 | 0.13
|  | Cum | 1 | 1 | 4.66 | 0.46 | 0.3 | 0.64
|  | Cum | 1 | 1 | 4.545 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.19 | 0.19
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 2.26 | 0.46 | 0.3 | 0.31
|  | Cum | 1 | 1 | 2.145 | 0.345 | 0.3 | 0.22
|  | Cum | 1 | 1 | 2.03 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 3.16 | 0.46 | 0.3 | 0.44
|  | Cum | 1 | 1 | 3.045 | 0.345 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.93 | 0.23 | 0.19 | 0.13
|  | Cum | 1 | 1 | 4.96 | 0.46 | 0.3 | 0.68
|  | Cum | 1 | 1 | 4.845 | 0.345 | 0.3 | 0.5
|  | Cum | 1 | 1 | 4.73 | 0.23 | 0.19 | 0.21
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 1.2 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.2 | 0.345 | 0.3 | 0.12
|  | Cum | 1 | 1 | 1.2 | 0.23 | 0.19 | 0.05
| (24'/17-21) | Cum | 1 | 1 | 8.42 | 0.46 | 0.3 | 1.16
|  | Cum | 1 | 1 | 8.19 | 0.345 | 0.3 | 0.85
|  | Cum | 1 | 1 | 7.96 | 0.23 | 0.19 | 0.35
| (17/20'-24') | Cum | 1 | 8 | 0.615 | 0.46 | 0.3 | 0.68
|  | Cum | 1 | 8 | 0.615 | 0.345 | 0.3 | 0.51
|  | Cum | 1 | 8 | 0.615 | 0.23 | 0.19 | 0.22
|  | Cum | 1 | 2 | 1.515 | 0.46 | 0.3 | 0.42
|  | Cum | 1 | 2 | 1.745 | 0.345 | 0.3 | 0.36
|  | Cum | 1 | 2 | 1.975 | 0.23 | 0.19 | 0.17
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 2 | 1.21 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.44 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 2 | 1.67 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
Brick Work for Planter (17-21/25'-29')
| (20'/17-21) | Cum | 1 | 1 | 8.92 | 0.46 | 0.3 | 1.23
|  | Cum | 1 | 1 | 8.69 | 0.345 | 0.3 | 0.9
|  | Cum | 1 | 1 | 8.46 | 0.23 | 0.19 | 0.37
|  | Cum | 1 | 1 | 6.66 | 0.46 | 0.3 | 0.92
|  | Cum | 1 | 1 | 6.545 | 0.345 | 0.3 | 0.68
|  | Cum | 1 | 1 | 6.43 | 0.23 | 0.19 | 0.28
|  | Cum | 1 | 1 | 4.86 | 0.46 | 0.3 | 0.67
|  | Cum | 1 | 1 | 4.745 | 0.345 | 0.3 | 0.49
|  | Cum | 1 | 1 | 4.63 | 0.23 | 0.19 | 0.2
|  | Cum | 1 | 1 | 1.66 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.545 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 3.66 | 0.46 | 0.3 | 0.51
|  | Cum | 1 | 1 | 3.545 | 0.345 | 0.3 | 0.37
|  | Cum | 1 | 1 | 3.43 | 0.23 | 0.19 | 0.15
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 3.46 | 0.46 | 0.3 | 0.48
|  | Cum | 1 | 1 | 3.345 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.23 | 0.23 | 0.19 | 0.14
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 4.66 | 0.46 | 0.3 | 0.64
|  | Cum | 1 | 1 | 4.545 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 1 | 3.46 | 0.46 | 0.3 | 0.48
|  | Cum | 1 | 1 | 3.345 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.23 | 0.23 | 0.19 | 0.14
|  | Cum | 1 | 1 | 4.66 | 0.46 | 0.3 | 0.64
|  | Cum | 1 | 1 | 4.545 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 1 | 1.66 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.545 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 6.46 | 0.46 | 0.3 | 0.89
|  | Cum | 1 | 1 | 6.345 | 0.345 | 0.3 | 0.66
|  | Cum | 1 | 1 | 6.23 | 0.23 | 0.19 | 0.27
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 8.46 | 0.46 | 0.3 | 1.17
|  | Cum | 1 | 1 | 8.345 | 0.345 | 0.3 | 0.86
|  | Cum | 1 | 1 | 8.23 | 0.23 | 0.19 | 0.36
|  | Cum | 1 | 1 | 10.72 | 0.46 | 0.3 | 1.48
|  | Cum | 1 | 1 | 10.49 | 0.345 | 0.3 | 1.09
|  | Cum | 1 | 1 | 10.26 | 0.23 | 0.19 | 0.45
| (17-21/25'-29') | Cum | 1 | 6 | 0.615 | 0.46 | 0.3 | 0.51
|  | Cum | 1 | 6 | 0.615 | 0.345 | 0.3 | 0.38
|  | Cum | 1 | 6 | 0.615 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 2 | 1.21 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.44 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 2 | 1.67 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
Brick Work for Planter (17-21/29'-35')
| (29'/17-21) | Cum | 1 | 1 | 7.7 | 0.46 | 0.3 | 1.06
|  | Cum | 1 | 1 | 7.47 | 0.345 | 0.3 | 0.77
|  | Cum | 1 | 1 | 7.24 | 0.23 | 0.19 | 0.32
|  | Cum | 1 | 1 | 5.46 | 0.46 | 0.3 | 0.75
|  | Cum | 1 | 1 | 5.345 | 0.345 | 0.3 | 0.55
|  | Cum | 1 | 1 | 5.23 | 0.23 | 0.19 | 0.23
|  | Cum | 1 | 1 | 4.46 | 0.46 | 0.3 | 0.62
|  | Cum | 1 | 1 | 4.345 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 1 | 4.23 | 0.23 | 0.19 | 0.18
| Brick Work for Sheat | Cum | 1 | 1 | 3 | 0.115 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3 | 0.345 | 0.425 | 0.44
|  | Cum | 1 | 1 | 1.46 | 0.46 | 0.3 | 0.2
|  | Cum | 1 | 1 | 1.345 | 0.345 | 0.3 | 0.14
|  | Cum | 1 | 1 | 1.23 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 6 | 3.46 | 0.46 | 0.3 | 2.86
|  | Cum | 1 | 6 | 3.345 | 0.345 | 0.3 | 2.08
|  | Cum | 1 | 6 | 3.23 | 0.23 | 0.19 | 0.85
|  | Cum | 1 | 1 | 5.46 | 0.46 | 0.3 | 0.75
|  | Cum | 1 | 1 | 5.345 | 0.345 | 0.3 | 0.55
|  | Cum | 1 | 1 | 5.23 | 0.23 | 0.19 | 0.23
| Brick Work for Sheat | Cum | 1 | 3 | 3 | 0.115 | 0.19 | 0.2
|  | Cum | 1 | 3 | 3 | 0.345 | 0.425 | 1.32
|  | Cum | 1 | 1 | 4.46 | 0.46 | 0.3 | 0.62
|  | Cum | 1 | 1 | 4.345 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 1 | 4.23 | 0.23 | 0.19 | 0.18
| (35'/17-20) | Cum | 1 | 1 | 5.72 | 0.46 | 0.3 | 0.79
|  | Cum | 1 | 1 | 5.49 | 0.345 | 0.3 | 0.57
|  | Cum | 1 | 1 | 5.26 | 0.23 | 0.19 | 0.23
| (17-20/29'-35') | Cum | 1 | 3 | 3.36 | 0.46 | 0.3 | 1.39
|  | Cum | 1 | 3 | 3.36 | 0.345 | 0.3 | 1.04
|  | Cum | 1 | 3 | 3.36 | 0.23 | 0.19 | 0.44
|  | Cum | 1 | 3 | 1.21 | 0.46 | 0.3 | 0.5
|  | Cum | 1 | 3 | 1.44 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 3 | 1.67 | 0.23 | 0.19 | 0.22
|  | Cum | 1 | 1 | 1.21 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.44 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 2 | 1.21 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.44 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 2 | 1.67 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 5 | 0.615 | 0.46 | 0.3 | 0.42
|  | Cum | 1 | 5 | 0.615 | 0.345 | 0.3 | 0.32
|  | Cum | 1 | 5 | 0.615 | 0.23 | 0.19 | 0.13
| Brick Work for Sheat | Cum | 1 | 4 | 3 | 0.115 | 0.19 | 0.26
|  | Cum | 1 | 4 | 3 | 0.345 | 0.425 | 1.76
Brick Work for Planter (20-28/2'-5')
| Brick Work (2'/20-28) | Cum | 1 | 1 | 3.52 | 0.46 | 0.3 | 0.49
|  | Cum | 1 | 1 | 3.29 | 0.345 | 0.3 | 0.34
|  | Cum | 1 | 1 | 3.06 | 0.23 | 0.19 | 0.13
|  | Cum | 1 | 3 | 1.327 | 0.46 | 0.3 | 0.55
|  | Cum | 1 | 3 | 1.097 | 0.345 | 0.3 | 0.34
|  | Cum | 1 | 3 | 0.867 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 4.12 | 0.46 | 0.3 | 0.57
|  | Cum | 1 | 1 | 3.89 | 0.345 | 0.3 | 0.4
|  | Cum | 1 | 1 | 3.66 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 1 | 3.06 | 0.46 | 0.3 | 0.42
|  | Cum | 1 | 1 | 2.945 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.83 | 0.23 | 0.19 | 0.12
|  | Cum | 1 | 4 | 0.765 | 0.46 | 0.3 | 0.42
|  | Cum | 1 | 4 | 0.65 | 0.345 | 0.3 | 0.27
|  | Cum | 1 | 4 | 0.535 | 0.23 | 0.19 | 0.09
Brick Work (3'/20-28)
| Brick Work (6'/20-21) | Cum | 1 | 1 | 4.125 | 0.46 | 0.3 | 0.57
|  | Cum | 1 | 1 | 3.895 | 0.345 | 0.3 | 0.4
|  | Cum | 1 | 1 | 3.665 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 2 | 1.195 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 0.965 | 0.345 | 0.3 | 0.2
|  | Cum | 1 | 2 | 0.735 | 0.23 | 0.19 | 0.06
| Brick Work (4'/22-23) | Cum | 1 | 3 | 3.06 | 0.46 | 0.3 | 1.27
|  | Cum | 1 | 3 | 2.945 | 0.345 | 0.3 | 0.91
|  | Cum | 1 | 3 | 2.83 | 0.23 | 0.19 | 0.37
|  | Cum | 1 | 2 | 1.195 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 0.965 | 0.345 | 0.3 | 0.2
|  | Cum | 1 | 2 | 0.735 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 2.46 | 0.46 | 0.3 | 0.34
|  | Cum | 1 | 1 | 2.345 | 0.345 | 0.3 | 0.24
|  | Cum | 1 | 1 | 2.23 | 0.23 | 0.19 | 0.1
Brick Work (20/2'-5')
| Brick Work (20/2'-5') | Cum | 1 | 1 | 9.155 | 0.46 | 0.3 | 1.26
|  | Cum | 1 | 1 | 9.155 | 0.345 | 0.3 | 0.95
|  | Cum | 1 | 1 | 9.155 | 0.23 | 0.19 | 0.4
|  | Cum | 1 | 2 | 6.555 | 0.46 | 0.3 | 1.81
|  | Cum | 1 | 2 | 6.67 | 0.345 | 0.3 | 1.38
|  | Cum | 1 | 2 | 6.785 | 0.23 | 0.19 | 0.59
| Brick Work for Sheat | Cum | 1 | 4 | 3 | 0.115 | 0.19 | 0.26
|  | Cum | 1 | 4 | 3 | 0.345 | 0.425 | 1.76
|  | Cum | 1 | 1 | 5.03 | 0.46 | 0.3 | 0.69
|  | Cum | 1 | 1 | 5.145 | 0.345 | 0.3 | 0.53
|  | Cum | 1 | 1 | 5.26 | 0.23 | 0.19 | 0.23
|  | Cum | 1 | 1 | 0.93 | 0.46 | 0.3 | 0.13
|  | Cum | 1 | 1 | 1.045 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.16 | 0.23 | 0.19 | 0.05
| (23/2'-5') | Cum | 1 | 1 | 1.68 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.565 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.45 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 0.6 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.6 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.6 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 3.515 | 0.46 | 0.3 | 0.49
|  | Cum | 1 | 1 | 3.63 | 0.345 | 0.3 | 0.38
|  | Cum | 1 | 1 | 3.745 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 2 | 3.505 | 0.46 | 0.3 | 0.97
|  | Cum | 1 | 2 | 3.62 | 0.345 | 0.3 | 0.75
|  | Cum | 1 | 2 | 3.735 | 0.23 | 0.19 | 0.33
|  | Cum | 1 | 1 | 3.2 | 0.46 | 0.3 | 0.44
|  | Cum | 1 | 1 | 3.315 | 0.345 | 0.3 | 0.34
|  | Cum | 1 | 1 | 3.43 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 2 | 0.455 | 0.46 | 0.3 | 0.13
|  | Cum | 1 | 2 | 0.57 | 0.345 | 0.3 | 0.12
|  | Cum | 1 | 2 | 0.685 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 1.065 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.18 | 0.345 | 0.3 | 0.12
|  | Cum | 1 | 1 | 1.295 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 2.11 | 0.46 | 0.3 | 0.29
|  | Cum | 1 | 1 | 2.11 | 0.345 | 0.3 | 0.22
|  | Cum | 1 | 1 | 2.11 | 0.23 | 0.19 | 0.09
Brick Work Side of BH-01 (15/23'-35')
| east face (15/23'-35') | Cum | 1 | 2 | 30.17 | 0.46 | 0.3 | 8.33
|  | Cum | 1 | 2 | 29.94 | 0.345 | 0.3 | 6.2
|  | Cum | 1 | 2 | 29.71 | 0.23 | 0.19 | 2.6
|  | Cum | 1 | 2 | 0.6 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 2 | 0.6 | 0.345 | 0.3 | 0.12
|  | Cum | 1 | 2 | 0.6 | 0.23 | 0.19 | 0.05
| north face (23'/9-10) | Cum | 1 | 2 | 5.945 | 0.46 | 0.3 | 1.64
|  | Cum | 1 | 2 | 5.715 | 0.345 | 0.3 | 1.18
|  | Cum | 1 | 2 | 5.485 | 0.23 | 0.19 | 0.48
|  | Cum | 1 | 2 | 1.195 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.195 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.195 | 0.23 | 0.19 | 0.1
| north face (23'/11-13) | Cum | 1 | 2 | 6.77 | 0.46 | 0.3 | 1.87
|  | Cum | 1 | 2 | 6.54 | 0.345 | 0.3 | 1.35
|  | Cum | 1 | 2 | 6.31 | 0.23 | 0.19 | 0.55
|  | Cum | 1 | 2 | 1.195 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.195 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.195 | 0.23 | 0.19 | 0.1
Brick Work for Planter (20-28/2'-5')
| Brick Work (42'/13-16) | Cum | 1 | 1 | 5.12 | 0.46 | 0.3 | 0.71
|  | Cum | 1 | 1 | 4.89 | 0.345 | 0.3 | 0.51
|  | Cum | 1 | 1 | 4.66 | 0.23 | 0.19 | 0.2
|  | Cum | 1 | 1 | 2.66 | 0.46 | 0.3 | 0.37
|  | Cum | 1 | 1 | 2.545 | 0.345 | 0.3 | 0.26
|  | Cum | 1 | 1 | 2.43 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 3.86 | 0.46 | 0.3 | 0.53
|  | Cum | 1 | 1 | 3.745 | 0.345 | 0.3 | 0.39
|  | Cum | 1 | 1 | 3.63 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 1 | 1.12 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.005 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 0.89 | 0.23 | 0.19 | 0.04
|  | Cum | 1 | 2 | 4.52 | 0.46 | 0.3 | 1.25
|  | Cum | 1 | 2 | 4.405 | 0.345 | 0.3 | 0.91
|  | Cum | 1 | 2 | 4.29 | 0.23 | 0.19 | 0.37
|  | Cum | 1 | 1 | 0.84 | 0.46 | 0.3 | 0.12
|  | Cum | 1 | 1 | 0.725 | 0.345 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.61 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 4.14 | 0.46 | 0.3 | 0.57
|  | Cum | 1 | 1 | 4.025 | 0.345 | 0.3 | 0.42
|  | Cum | 1 | 1 | 3.91 | 0.23 | 0.19 | 0.17
| (45'/14-17) | Cum | 1 | 1 | 1.74 | 0.46 | 0.3 | 0.24
|  | Cum | 1 | 1 | 1.625 | 0.345 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.51 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3.54 | 0.46 | 0.3 | 0.49
|  | Cum | 1 | 1 | 3.425 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.31 | 0.23 | 0.19 | 0.14
|  | Cum | 1 | 1 | 4.74 | 0.46 | 0.3 | 0.65
|  | Cum | 1 | 1 | 3.425 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.31 | 0.23 | 0.19 | 0.14
| (46'/14-17) | Cum | 1 | 1 | 6.02 | 0.46 | 0.3 | 0.83
|  | Cum | 1 | 1 | 5.905 | 0.345 | 0.3 | 0.61
|  | Cum | 1 | 1 | 5.79 | 0.23 | 0.19 | 0.25
|  | Cum | 1 | 1 | 1.06 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 0.945 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.19 | 0.04
|  | Cum | 1 | 2 | 6.62 | 0.46 | 0.3 | 1.83
|  | Cum | 1 | 2 | 6.505 | 0.345 | 0.3 | 1.35
|  | Cum | 1 | 2 | 6.39 | 0.23 | 0.19 | 0.56
|  | Cum | 1 | 1 | 1.66 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.545 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 10.28 | 0.46 | 0.3 | 1.42
|  | Cum | 1 | 1 | 10.05 | 0.345 | 0.3 | 1.04
|  | Cum | 1 | 1 | 9.82 | 0.23 | 0.19 | 0.43
| Brick Work for Sheat | Cum | 1 | 5 | 3 | 0.115 | 0.19 | 0.33
|  | Cum | 1 | 5 | 3 | 0.345 | 0.425 | 2.2
(15/42'-47')
|  | Cum | 1 | 7 | 0.615 | 0.46 | 0.3 | 0.59
|  | Cum | 1 | 7 | 0.615 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 7 | 0.615 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 1 | 1.675 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.79 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.905 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 0.6 | 0.46 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.83 | 0.345 | 0.3 | 0.09
|  | Cum | 1 | 1 | 1.06 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 5 | 1.21 | 0.46 | 0.3 | 0.83
|  | Cum | 1 | 5 | 1.44 | 0.345 | 0.3 | 0.75
|  | Cum | 1 | 5 | 1.67 | 0.23 | 0.19 | 0.36
|  | Cum | 1 | 1 | 3.36 | 0.46 | 0.3 | 0.46
|  | Cum | 1 | 1 | 3.36 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.36 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 2 | 2.285 | 0.46 | 0.3 | 0.63
|  | Cum | 1 | 2 | 2.17 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 2 | 2.035 | 0.23 | 0.19 | 0.18
Brick Work for Planter (20-28/2'-5')
| Brick Work (48'/13-16) | Cum | 1 | 1 | 11.08 | 0.46 | 0.3 | 1.53
|  | Cum | 1 | 1 | 10.85 | 0.345 | 0.3 | 1.12
|  | Cum | 1 | 1 | 10.62 | 0.23 | 0.19 | 0.46
|  | Cum | 1 | 1 | 8.62 | 0.46 | 0.3 | 1.19
|  | Cum | 1 | 1 | 8.505 | 0.345 | 0.3 | 0.88
|  | Cum | 1 | 1 | 8.39 | 0.23 | 0.19 | 0.37
| (49'/13-16) | Cum | 1 | 2 | 6.62 | 0.46 | 0.3 | 1.83
|  | Cum | 1 | 2 | 6.505 | 0.345 | 0.3 | 1.35
|  | Cum | 1 | 2 | 6.39 | 0.23 | 0.19 | 0.56
| (50'/14-18) | Cum | 1 | 2 | 9.02 | 0.46 | 0.3 | 2.49
|  | Cum | 1 | 2 | 8.905 | 0.345 | 0.3 | 1.84
|  | Cum | 1 | 2 | 8.79 | 0.23 | 0.19 | 0.77
|  | Cum | 1 | 1 | 8.12 | 0.46 | 0.3 | 1.12
|  | Cum | 1 | 1 | 8.005 | 0.345 | 0.3 | 0.83
|  | Cum | 1 | 1 | 7.89 | 0.23 | 0.19 | 0.34
| (52'/14-18) | Cum | 1 | 1 | 10.58 | 0.46 | 0.3 | 1.46
|  | Cum | 1 | 1 | 10.35 | 0.345 | 0.3 | 1.07
|  | Cum | 1 | 1 | 10.12 | 0.23 | 0.19 | 0.44
| Brick Work for Sheat | Cum | 1 | 3 | 3 | 0.115 | 0.19 | 0.2
|  | Cum | 1 | 3 | 3 | 0.345 | 0.425 | 1.32
| (15/48'-53') | Cum | 1 | 2 | 0.615 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 2 | 0.615 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 2 | 0.615 | 0.23 | 0.19 | 0.05
| (17/48'-49') | Cum | 1 | 3 | 1.18 | 0.46 | 0.3 | 0.49
|  | Cum | 1 | 3 | 1.41 | 0.345 | 0.3 | 0.44
|  | Cum | 1 | 3 | 1.64 | 0.23 | 0.19 | 0.22
|  | Cum | 1 | 3 | 3.36 | 0.46 | 0.3 | 1.39
|  | Cum | 1 | 3 | 3.36 | 0.345 | 0.3 | 1.04
|  | Cum | 1 | 3 | 3.36 | 0.23 | 0.19 | 0.44
Brick Work P/L outer side of BH-04 (Drg. No. TU/LA-P-206.3)
| Brick Work west side (20/37'-50') | Cum | 1 | 1 | 33.62 | 0.46 | 0.3 | 4.64
|  | Cum | 1 | 1 | 33.39 | 0.345 | 0.3 | 3.46
|  | Cum | 1 | 1 | 33.16 | 0.23 | 0.19 | 1.45
|  | Cum | 1 | 1 | 30.13 | 0.46 | 0.3 | 4.16
|  | Cum | 1 | 1 | 30.13 | 0.345 | 0.3 | 3.12
|  | Cum | 1 | 1 | 30.13 | 0.23 | 0.19 | 1.32
| Brick Work south side (49'/19-23) (longitudinal axies) | Cum | 1 | 1 | 1.375 | 0.46 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.26 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 1 | 1.145 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 1 | 0.925 | 0.46 | 0.3 | 0.13
|  | Cum | 1 | 1 | 0.81 | 0.345 | 0.3 | 0.08
|  | Cum | 1 | 1 | 0.695 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 2.45 | 0.46 | 0.3 | 0.34
|  | Cum | 1 | 1 | 2.335 | 0.345 | 0.3 | 0.24
|  | Cum | 1 | 1 | 2.22 | 0.23 | 0.19 | 0.1
|  | Cum | 1 | 1 | 0.95 | 0.46 | 0.3 | 0.13
|  | Cum | 1 | 1 | 0.835 | 0.345 | 0.3 | 0.09
|  | Cum | 1 | 1 | 0.72 | 0.23 | 0.19 | 0.03
|  | Cum | 1 | 1 | 3.64 | 0.46 | 0.3 | 0.5
|  | Cum | 1 | 1 | 3.41 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 1 | 3.18 | 0.23 | 0.19 | 0.14
| Brick Work south side (49'/19-23) (transverse axies) | Cum | 1 | 1 | 1.54 | 0.46 | 0.3 | 0.21
|  | Cum | 1 | 1 | 1.655 | 0.345 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.77 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 2 | 0.46 | 0.3 | 0.28
|  | Cum | 1 | 1 | 2 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 0.08 | 0.46 | 0.3 | 0.01
|  | Cum | 1 | 1 | 0.31 | 0.345 | 0.3 | 0.03
|  | Cum | 1 | 1 | 0.54 | 0.23 | 0.19 | 0.02
|  | Cum | 1 | 1 | 1 | 0.46 | 0.3 | 0.14
|  | Cum | 1 | 1 | 1 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 1 | 0.23 | 0.19 | 0.04
|  | Cum | 1 | 1 | 1.51 | 0.46 | 0.3 | 0.21
|  | Cum | 1 | 1 | 1.625 | 0.345 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.74 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 5.71 | 0.46 | 0.3 | 0.79
|  | Cum | 1 | 1 | 5.825 | 0.345 | 0.3 | 0.6
|  | Cum | 1 | 1 | 5.94 | 0.23 | 0.19 | 0.26
| Brick Work north side (36'/19-21) (longitudianal axies) | Cum | 1 | 1 | 2.72 | 0.46 | 0.3 | 0.38
|  | Cum | 1 | 1 | 2.49 | 0.345 | 0.3 | 0.26
|  | Cum | 1 | 1 | 2.26 | 0.23 | 0.19 | 0.1
|  |  | 1 |  |  |  |  | 0
| Brick Work north side (36'/19-21) (transverse axies) | Cum | 1 | 1 | 4.495 | 0.46 | 0.3 | 0.62
|  | Cum | 1 | 1 | 4.495 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.495 | 0.23 | 0.19 | 0.2
|  |  | 1 |  |  |  |  | 0
| (transverse axies) | Cum | 1 | 1 | 2.465 | 0.46 | 0.3 | 0.34
|  | Cum | 1 | 1 | 2.58 | 0.345 | 0.3 | 0.27
|  | Cum | 1 | 1 | 2.695 | 0.23 | 0.19 | 0.12
Brick Work P/L outer side of BH-04 (Drg. No. TU/LA-P-206.4)
| Brick Work east side (32/37'-49') | Cum | 1 | 2 | 32.74 | 0.46 | 0.3 | 9.04
|  | Cum | 1 | 2 | 32.51 | 0.345 | 0.3 | 6.73
|  | Cum | 1 | 2 | 32.28 | 0.23 | 0.19 | 2.82
|  | Cum | 1 | 2 | 1.57 | 0.46 | 0.3 | 0.43
|  | Cum | 1 | 2 | 1.57 | 0.345 | 0.3 | 0.32
|  | Cum | 1 | 2 | 1.57 | 0.23 | 0.19 | 0.14
Brick Work P/L for Planter (39'-55'/32-36) (Drg. No. TU/LA-P-206.4) between BH-05 & BH-04
Brick Work for Planter (39'-47'/32-36)
| longitudianal axies (40'/34-35) | Cum | 1 | 2 | 4.4 | 0.46 | 0.3 | 1.21
|  | Cum | 1 | 2 | 4.17 | 0.345 | 0.3 | 0.86
|  | Cum | 1 | 2 | 3.94 | 0.23 | 0.19 | 0.34
|  | Cum | 1 | 1 | 1.94 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 1.825 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.71 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 4 | 2.84 | 0.46 | 0.3 | 1.57
|  | Cum | 1 | 4 | 2.725 | 0.345 | 0.3 | 1.13
|  | Cum | 1 | 4 | 2.61 | 0.23 | 0.19 | 0.46
|  | Cum | 1 | 2 | 4.94 | 0.46 | 0.3 | 1.36
|  | Cum | 1 | 2 | 4.825 | 0.345 | 0.3 | 1
|  | Cum | 1 | 2 | 4.71 | 0.23 | 0.19 | 0.41
|  | Cum | 1 | 2 | 4.64 | 0.46 | 0.3 | 1.28
|  | Cum | 1 | 2 | 4.525 | 0.345 | 0.3 | 0.94
|  | Cum | 1 | 2 | 4.41 | 0.23 | 0.19 | 0.39
|  | Cum | 1 | 2 | 5.54 | 0.46 | 0.3 | 1.53
|  | Cum | 1 | 2 | 5.425 | 0.345 | 0.3 | 1.12
|  | Cum | 1 | 2 | 5.31 | 0.23 | 0.19 | 0.46
|  | Cum | 1 | 2 | 6.44 | 0.46 | 0.3 | 1.78
|  | Cum | 1 | 2 | 6.325 | 0.345 | 0.3 | 1.31
|  | Cum | 1 | 2 | 6.21 | 0.23 | 0.19 | 0.54
|  | Cum | 1 | 1 | 7.64 | 0.46 | 0.3 | 1.05
|  | Cum | 1 | 1 | 7.525 | 0.345 | 0.3 | 0.78
|  | Cum | 1 | 1 | 7.41 | 0.23 | 0.19 | 0.32
|  | Cum | 1 | 1 | 1.96 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 1.845 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.73 | 0.23 | 0.19 | 0.08
| (47'/32-36) | Cum | 1 | 1 | 11.08 | 0.46 | 0.3 | 1.53
|  | Cum | 1 | 1 | 10.85 | 0.345 | 0.3 | 1.12
|  | Cum | 1 | 1 | 10.62 | 0.23 | 0.19 | 0.46
| Brick Work for Sheat | Cum | 1 | 4 | 3 | 0.115 | 0.19 | 0.26
|  | Cum | 1 | 4 | 3 | 0.345 | 0.425 | 1.76
| Transvere axies (34/40'-47') | Cum | 1 | 3 | 0.615 | 0.46 | 0.3 | 0.25
|  | Cum | 1 | 3 | 0.615 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 3 | 0.615 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 6 | 3.36 | 0.46 | 0.3 | 2.78
|  | Cum | 1 | 6 | 3.36 | 0.345 | 0.3 | 2.09
|  | Cum | 1 | 6 | 3.36 | 0.23 | 0.19 | 0.88
|  | Cum | 1 | 7 | 1.21 | 0.46 | 0.3 | 1.17
|  | Cum | 1 | 7 | 1.44 | 0.345 | 0.3 | 1.04
|  | Cum | 1 | 7 | 1.67 | 0.23 | 0.19 | 0.51
|  | Cum | 1 | 1 | 2.285 | 0.46 | 0.3 | 0.32
|  | Cum | 1 | 1 | 2.4 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.19 | 0.11
Brick Work P/L for Planter (30-39/37-40) near M4 (revised Drg. No. TU/LA-P-206.5 (front of Basket Ball)
| Brick Work for (west side wall) | Cum | 1 | 1 | 19.45 | 0.46 | 0.3 | 2.68
|  | Cum | 1 | 1 | 19.22 | 0.345 | 0.3 | 1.99
|  | Cum | 1 | 1 | 18.99 | 0.23 | 0.19 | 0.83
| Brick Work for Sheat | Cum | 1 | 3 | 3 | 0.115 | 0.19 | 0.2
|  | Cum | 1 | 3 | 3 | 0.345 | 0.425 | 1.32
| north & south side wall | Cum | 2 | 1 | 2 | 0.46 | 0.3 | 0.55
|  | Cum | 2 | 1 | 2 | 0.345 | 0.3 | 0.41
|  | Cum | 2 | 1 | 2 | 0.23 | 0.19 | 0.17
| east side wall | Cum | 1 | 1 | 1.985 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 1.87 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.755 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 3 | 2.435 | 0.46 | 0.3 | 1.01
|  | Cum | 1 | 3 | 2.435 | 0.345 | 0.3 | 0.76
|  | Cum | 1 | 3 | 2.435 | 0.23 | 0.19 | 0.32
|  | Cum | 1 | 1 | 2.44 | 0.46 | 0.3 | 0.34
|  | Cum | 1 | 1 | 2.44 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.44 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 1 | 2.13 | 0.46 | 0.3 | 0.29
|  | Cum | 1 | 1 | 2.13 | 0.345 | 0.3 | 0.22
|  | Cum | 1 | 1 | 2.13 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 1.94 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 1.825 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.71 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 2 | 5.345 | 0.46 | 0.3 | 1.48
|  | Cum | 1 | 2 | 5.345 | 0.345 | 0.3 | 1.11
|  | Cum | 1 | 2 | 5.345 | 0.23 | 0.19 | 0.47
|  | Cum | 1 | 2 | 6.38 | 0.46 | 0.3 | 1.76
|  | Cum | 1 | 2 | 6.38 | 0.345 | 0.3 | 1.32
|  | Cum | 1 | 2 | 6.38 | 0.23 | 0.19 | 0.56
|  | Cum | 1 | 2 | 6.95 | 0.46 | 0.3 | 1.92
|  | Cum | 1 | 2 | 6.95 | 0.345 | 0.3 | 1.44
|  | Cum | 1 | 2 | 6.95 | 0.23 | 0.19 | 0.61
|  | Cum | 1 | 2 | 6.12 | 0.46 | 0.3 | 1.69
|  | Cum | 1 | 2 | 6.12 | 0.345 | 0.3 | 1.27
|  | Cum | 1 | 2 | 6.12 | 0.23 | 0.19 | 0.53
|  | Cum | 1 | 2 | 4.645 | 0.46 | 0.3 | 1.28
|  | Cum | 1 | 2 | 4.645 | 0.345 | 0.3 | 0.96
|  | Cum | 1 | 2 | 4.645 | 0.23 | 0.19 | 0.41
|  | Cum | 1 | 2 | 3 | 0.46 | 0.3 | 0.83
|  | Cum | 1 | 2 | 3 | 0.345 | 0.3 | 0.62
|  | Cum | 1 | 2 | 3 | 0.23 | 0.19 | 0.26
|  | Cum | 1 | 4 | 0.615 | 0.46 | 0.3 | 0.34
|  | Cum | 1 | 4 | 0.615 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 4 | 0.615 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 2 | 0.61 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 2 | 0.61 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 2 | 0.61 | 0.23 | 0.19 | 0.05
Brick Work P/L for Planter near BH-03 (drg. No. TU/LA-P-206.1) (48-52/2'-11') north side
Brick Work for (north side wall) (2'/48-52)
| Longitudianal axies (2'/48-52) | Cum | 1 | 1 | 8.32 | 0.46 | 0.3 | 1.15
|  | Cum | 1 | 1 | 8.09 | 0.345 | 0.3 | 0.84
|  | Cum | 1 | 1 | 7.86 | 0.23 | 0.19 | 0.34
|  | Cum | 1 | 1 | 5.86 | 0.46 | 0.3 | 0.81
|  | Cum | 1 | 1 | 5.745 | 0.345 | 0.3 | 0.59
|  | Cum | 1 | 1 | 5.63 | 0.23 | 0.19 | 0.25
|  | Cum | 1 | 2 | 6.46 | 0.46 | 0.3 | 1.78
|  | Cum | 1 | 2 | 6.345 | 0.345 | 0.3 | 1.31
|  | Cum | 1 | 2 | 6.23 | 0.23 | 0.19 | 0.54
|  | Cum | 1 | 3 | 5.26 | 0.46 | 0.3 | 2.18
|  | Cum | 1 | 3 | 5.145 | 0.345 | 0.3 | 1.6
|  | Cum | 1 | 3 | 5.03 | 0.23 | 0.19 | 0.66
|  | Cum | 1 | 1 | 1.66 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.545 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 5.86 | 0.46 | 0.3 | 0.81
|  | Cum | 1 | 1 | 5.745 | 0.345 | 0.3 | 0.59
|  | Cum | 1 | 1 | 5.63 | 0.23 | 0.19 | 0.25
|  | Cum | 1 | 1 | 1.06 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 0.945 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.19 | 0.04
|  | Cum | 1 | 5 | 4.66 | 0.46 | 0.3 | 3.22
|  | Cum | 1 | 5 | 4.545 | 0.345 | 0.3 | 2.35
|  | Cum | 1 | 5 | 4.43 | 0.23 | 0.19 | 0.97
|  | Cum | 1 | 1 | 1.06 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 0.945 | 0.345 | 0.3 | 0.1
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.19 | 0.04
|  | Cum | 1 | 1 | 5.26 | 0.46 | 0.3 | 0.73
|  | Cum | 1 | 1 | 5.145 | 0.345 | 0.3 | 0.53
|  | Cum | 1 | 1 | 5.03 | 0.23 | 0.19 | 0.22
|  | Cum | 1 | 1 | 1.66 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.545 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.19 | 0.06
| (10'/49-50) | Cum | 1 | 2 | 6.46 | 0.46 | 0.3 | 1.78
|  | Cum | 1 | 2 | 6.345 | 0.345 | 0.3 | 1.31
|  | Cum | 1 | 2 | 6.23 | 0.23 | 0.19 | 0.54
|  | Cum | 1 | 1 | 8.92 | 0.46 | 0.3 | 1.23
|  | Cum | 1 | 1 | 8.69 | 0.345 | 0.3 | 0.9
|  | Cum | 1 | 1 | 8.46 | 0.23 | 0.19 | 0.37
| Brick Work for Sheat | Cum | 1 | 8 | 3 | 0.115 | 0.19 | 0.52
|  | Cum | 1 | 8 | 3 | 0.345 | 0.425 | 3.52
Transverse axies (49/2'-11')
|  | Cum | 1 | 6 | 0.615 | 0.46 | 0.3 | 0.51
|  | Cum | 1 | 6 | 0.615 | 0.345 | 0.3 | 0.38
|  | Cum | 1 | 6 | 0.615 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 4 | 1.21 | 0.46 | 0.3 | 0.67
|  | Cum | 1 | 4 | 1.44 | 0.345 | 0.3 | 0.6
|  | Cum | 1 | 4 | 1.67 | 0.23 | 0.19 | 0.29
|  | Cum | 1 | 2 | 3.36 | 0.46 | 0.3 | 0.93
|  | Cum | 1 | 2 | 3.36 | 0.345 | 0.3 | 0.7
|  | Cum | 1 | 2 | 3.36 | 0.23 | 0.19 | 0.29
|  | Cum | 1 | 3 | 0.905 | 0.46 | 0.3 | 0.37
|  | Cum | 1 | 3 | 1.135 | 0.345 | 0.3 | 0.35
|  | Cum | 1 | 3 | 1.365 | 0.23 | 0.19 | 0.18
|  | Cum | 1 | 2 | 1.98 | 0.46 | 0.3 | 0.55
|  | Cum | 1 | 2 | 2.095 | 0.345 | 0.3 | 0.43
|  | Cum | 1 | 2 | 2.21 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 2 | 2.285 | 0.46 | 0.3 | 0.63
|  | Cum | 1 | 2 | 2.4 | 0.345 | 0.3 | 0.5
|  | Cum | 1 | 2 | 2.515 | 0.23 | 0.19 | 0.22
|  | Cum | 1 | 1 | 3.055 | 0.46 | 0.3 | 0.42
|  | Cum | 1 | 1 | 3.055 | 0.345 | 0.3 | 0.32
|  | Cum | 1 | 1 | 3.055 | 0.23 | 0.19 | 0.13
|  | Cum | 1 | 1 | 3.165 | 0.46 | 0.3 | 0.44
|  | Cum | 1 | 1 | 3.165 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.165 | 0.23 | 0.19 | 0.14
|  | Cum | 1 | 1 | 1.015 | 0.46 | 0.3 | 0.14
|  | Cum | 1 | 1 | 1.245 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 1 | 1.475 | 0.23 | 0.19 | 0.06
Brick Work P/L for BH-05 outer side (drg. No. TU/LA-P-206.8)
| Brick Work for FIRE TENDER TOES Wall (north side wall) | Cum | 1 | 1 | 34.935 | 0.46 | 0.3 | 4.82
|  | Cum | 1 | 1 | 34.935 | 0.345 | 0.3 | 3.62
|  | Cum | 1 | 1 | 34.935 | 0.23 | 0.79 | 6.35
| Brick Work for FIRE TENDER TOES Wall (west side wall) | Cum | 1 | 1 | 15 | 0.46 | 0.3 | 2.07
|  | Cum | 1 | 1 | 15 | 0.345 | 0.3 | 1.55
|  | Cum | 1 | 1 | 15 | 0.23 | 0.19 | 0.66
Brick Work for Basket Ball Ground Toe Wall
| Basket Ball Long Ball | Cum | 1 | 2 | 28.46 | 0.46 | 0.3 | 7.85
|  | Cum | 1 | 2 | 28.23 | 0.345 | 0.3 | 5.84
|  | Cum | 1 | 2 | 28 | 0.23 | 0.19 | 2.45
| BASKET WALL SHORT WALL | Cum | 1 | 2 | 14.74 | 0.46 | 0.3 | 4.07
|  | Cum | 1 | 2 | 14.74 | 0.345 | 0.3 | 3.05
|  | Cum | 1 | 2 | 14.74 | 0.23 | 0.19 | 1.29
| Brick Work for Sheat | Cum | 1 | 2 | 3 | 0.115 | 0.19 | 0.13
|  | Cum | 1 | 2 | 3 | 0.345 | 0.425 | 0.88
Brick Work for Fire Tender Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 (South side) | Cum | 1 | 1 | 31.4 | 0.46 | 0.3 | 4.33
|  | Cum | 1 | 1 | 31.4 | 0.345 | 0.3 | 3.25
|  | Cum | 1 | 1 | 31.4 | 0.23 | 0.19 | 1.37
| FIRE TENDER TOE WALL WITH BH-07 | Cum | 1 | 1 | 42.55 | 0.46 | 0.3 | 5.87
|  | Cum | 1 | 1 | 42.55 | 0.345 | 0.3 | 4.4
|  | Cum | 1 | 1 | 42.55 | 0.23 | 0.19 | 1.86
| Brick Work for Road Toe Wall BH-01 east side towards water body | Cum | 1 | 2 | 30.24 | 0.46 | 0.3 | 8.35
|  | Cum | 1 | 2 | 30.01 | 0.345 | 0.3 | 6.21
|  | Cum | 1 | 2 | 29.78 | 0.23 | 0.19 | 2.6
|  | Cum | 1 | 2 | 0.67 | 0.46 | 0.3 | 0.18
|  | Cum | 1 | 2 | 0.67 | 0.345 | 0.3 | 0.14
|  | Cum | 1 | 2 | 0.67 | 0.23 | 0.19 | 0.06
Brick Work for Road Toe Wall BH-01 North side towards GYM
|  | Cum | 1 | 2 | 6.015 | 0.46 | 0.3 | 1.66
|  | Cum | 1 | 2 | 5.785 | 0.345 | 0.3 | 1.2
|  | Cum | 1 | 2 | 5.555 | 0.23 | 0.19 | 0.49
|  | Cum | 1 | 2 | 1.265 | 0.46 | 0.3 | 0.35
|  | Cum | 1 | 2 | 1.265 | 0.345 | 0.3 | 0.26
|  | Cum | 1 | 2 | 1.265 | 0.23 | 0.19 | 0.11
|  | Cum | 1 | 2 | 6.84 | 0.46 | 0.3 | 1.89
|  | Cum | 1 | 2 | 6.61 | 0.345 | 0.3 | 1.37
|  | Cum | 1 | 2 | 6.38 | 0.23 | 0.19 | 0.56
|  | Cum | 1 | 2 | 1.265 | 0.46 | 0.3 | 0.35
|  | Cum | 1 | 2 | 1.265 | 0.345 | 0.3 | 0.26
|  | Cum | 1 | 2 | 1.265 | 0.23 | 0.19 | 0.11
Brick Work for Road Toe Wall back side of Basket Ball (east side)
|  | Cum | 1 | 3 | 7.625 | 0.46 | 0.3 | 3.16
|  | Cum | 1 | 3 | 7.625 | 0.345 | 0.3 | 2.37
|  | Cum | 1 | 3 | 7.625 | 0.23 | 0.19 | 1
Brick Work for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | 1 | 8 | 7.625 | 0.46 | 0.3 | 8.42
|  | Cum | 1 | 8 | 7.625 | 0.345 | 0.3 | 6.31
|  | Cum | 1 | 8 | 7.625 | 0.23 | 0.19 | 2.67
|  | Cum | 1 | 1 | 9.35 | 0.46 | 0.3 | 1.29
|  | Cum | 1 | 1 | 9.35 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.35 | 0.23 | 0.19 | 0.41
| Less Previous RA Quantity | Cum | -1 | 1 | 392.89 |  |  | -392.89
Brick Work P/L for Planter near Reception or west side of Waterbody (drg. No. TU/LA-P-206.1) (30'-35'/32-36)
Brick Work for Planter
| Longitudianal axies (30'/32-36) | Cum | 1 | 1 | 11.67 | 0.46 | 0.3 | 1.61
|  | Cum | 1 | 1 | 11.44 | 0.345 | 0.3 | 1.18
|  | Cum | 1 | 1 | 11.21 | 0.23 | 0.19 | 0.49
|  | Cum | 1 | 1 | 1.86 | 0.46 | 0.3 | 0.26
|  | Cum | 1 | 1 | 1.745 | 0.345 | 0.3 | 0.18
|  | Cum | 1 | 1 | 1.63 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 7.815 | 0.46 | 0.3 | 1.08
|  | Cum | 1 | 1 | 7.7 | 0.345 | 0.3 | 0.8
|  | Cum | 1 | 1 | 7.585 | 0.23 | 0.19 | 0.33
| Longitudianal axies (31'/32-35) | Cum | 1 | 1 | 7.815 | 0.46 | 0.3 | 1.08
|  | Cum | 1 | 1 | 7.7 | 0.345 | 0.3 | 0.8
|  | Cum | 1 | 1 | 7.585 | 0.23 | 0.19 | 0.33
|  | Cum | 1 | 1 | 1.86 | 0.46 | 0.3 | 0.26
|  | Cum | 1 | 1 | 1.745 | 0.345 | 0.3 | 0.18
|  | Cum | 1 | 1 | 1.63 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 6.415 | 0.46 | 0.3 | 0.89
|  | Cum | 1 | 1 | 6.3 | 0.345 | 0.3 | 0.65
|  | Cum | 1 | 1 | 6.185 | 0.23 | 0.19 | 0.27
| Longitudianal axies (32'/32-35) | Cum | 1 | 1 | 6.415 | 0.46 | 0.3 | 0.89
|  | Cum | 1 | 1 | 6.3 | 0.345 | 0.3 | 0.65
|  | Cum | 1 | 1 | 6.185 | 0.23 | 0.19 | 0.27
|  | Cum | 1 | 1 | 1.99 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 1.875 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.76 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 4.885 | 0.46 | 0.3 | 0.67
|  | Cum | 1 | 1 | 4.77 | 0.345 | 0.3 | 0.49
|  | Cum | 1 | 1 | 4.655 | 0.23 | 0.19 | 0.2
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 4.885 | 0.46 | 0.3 | 0.67
|  | Cum | 1 | 1 | 4.77 | 0.345 | 0.3 | 0.49
|  | Cum | 1 | 1 | 4.655 | 0.23 | 0.19 | 0.2
|  | Cum | 1 | 1 | 1.99 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 1.875 | 0.345 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.76 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 3.35 | 0.46 | 0.3 | 0.46
|  | Cum | 1 | 1 | 3.235 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.12 | 0.23 | 0.19 | 0.14
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 3.35 | 0.46 | 0.3 | 0.46
|  | Cum | 1 | 1 | 3.235 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.12 | 0.23 | 0.19 | 0.14
|  | Cum | 1 | 1 | 5.35 | 0.46 | 0.3 | 0.74
|  | Cum | 1 | 1 | 5.235 | 0.345 | 0.3 | 0.54
|  | Cum | 1 | 1 | 5.12 | 0.23 | 0.19 | 0.22
| Transvere axies (34/30'-35') | Cum | 1 | 6 | 0.615 | 0.46 | 0.3 | 0.51
|  | Cum | 1 | 6 | 0.615 | 0.345 | 0.3 | 0.38
|  | Cum | 1 | 6 | 0.615 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 3 | 2.285 | 0.46 | 0.3 | 0.95
|  | Cum | 1 | 3 | 2.4 | 0.345 | 0.3 | 0.75
|  | Cum | 1 | 3 | 2.515 | 0.23 | 0.19 | 0.33
|  | Cum | 1 | 1 | 1.98 | 0.46 | 0.3 | 0.27
|  | Cum | 1 | 1 | 2.095 | 0.345 | 0.3 | 0.22
|  | Cum | 1 | 1 | 2.21 | 0.23 | 0.19 | 0.1
|  | Cum | 1 | 3 | 1.21 | 0.46 | 0.3 | 0.5
|  | Cum | 1 | 3 | 1.44 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 3 | 1.67 | 0.23 | 0.19 | 0.22
|  | Cum | 1 | 1 | 0.905 | 0.46 | 0.3 | 0.12
|  | Cum | 1 | 1 | 1.135 | 0.345 | 0.3 | 0.12
|  | Cum | 1 | 1 | 1.365 | 0.23 | 0.19 | 0.06
Brick Work P/L for Planter South sid of BH-02 (drg. No. TU/LA-P-206.1 & 206.2) ( (15'-19'/20-32)
Brick Work for Planter
| Longitudianal axies (15'/20-32) | Cum | 1 | 1 | 29.85 | 0.46 | 0.3 | 4.12
|  | Cum | 1 | 1 | 29.85 | 0.345 | 0.3 | 3.09
|  | Cum | 1 | 1 | 29.85 | 0.23 | 0.19 | 1.3
|  | Cum | 1 | 1 | 1.38 | 0.46 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.61 | 0.345 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.84 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 7 | 1.08 | 0.46 | 0.3 | 1.04
|  | Cum | 1 | 7 | 1.31 | 0.345 | 0.3 | 0.95
|  | Cum | 1 | 7 | 1.54 | 0.23 | 0.19 | 0.47
|  | Cum | 1 | 1 | 1.33 | 0.46 | 0.3 | 0.18
|  | Cum | 1 | 1 | 1.56 | 0.345 | 0.3 | 0.16
|  | Cum | 1 | 1 | 1.79 | 0.23 | 0.19 | 0.08
|  | Cum | 1 | 1 | 0.83 | 0.46 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.06 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.29 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 12 | 0.6 | 0.46 | 0.3 | 0.99
|  | Cum | 1 | 12 | 0.6 | 0.345 | 0.3 | 0.75
|  | Cum | 1 | 12 | 0.6 | 0.23 | 0.19 | 0.31
| Transvere axies (32/15'-19') | Cum | 1 | 1 | 11.235 | 0.46 | 0.3 | 1.55
|  | Cum | 1 | 1 | 11.005 | 0.345 | 0.3 | 1.14
|  | Cum | 1 | 1 | 10.775 | 0.23 | 0.19 | 0.47
| (32/15'-19') | Cum | 1 | 1 | 9.315 | 0.46 | 0.3 | 1.29
|  | Cum | 1 | 1 | 9.315 | 0.345 | 0.3 | 0.96
|  | Cum | 1 | 1 | 9.315 | 0.23 | 0.19 | 0.41
| (31/15'-19') | Cum | 1 | 2 | 7.785 | 0.46 | 0.3 | 2.15
|  | Cum | 1 | 2 | 7.785 | 0.345 | 0.3 | 1.61
|  | Cum | 1 | 2 | 7.785 | 0.23 | 0.19 | 0.68
| (30/15'-18') | Cum | 1 | 2 | 6.265 | 0.46 | 0.3 | 1.73
|  | Cum | 1 | 2 | 6.265 | 0.345 | 0.3 | 1.3
|  | Cum | 1 | 2 | 6.265 | 0.23 | 0.19 | 0.55
| (29/15'-17') | Cum | 0 | 2 | 6.725 | 0.46 | 0.3
|  | Cum | 0 | 2 | 6.61 | 0.345 | 0.3
|  | Cum | 0 | 2 | 6.495 | 0.23 | 0.19
|  | Cum | 1 | 2 | 4.74 | 0.46 | 0.3 | 1.31
|  | Cum | 1 | 2 | 4.74 | 0.345 | 0.3 | 0.98
|  | Cum | 1 | 2 | 4.74 | 0.23 | 0.19 | 0.41
|  | Cum | 1 | 2 | 3.52 | 0.46 | 0.3 | 0.97
|  | Cum | 1 | 2 | 3.52 | 0.345 | 0.3 | 0.73
|  | Cum | 1 | 2 | 3.52 | 0.23 | 0.19 | 0.31
|  | Cum | 6 | 2 | 3.215 | 0.46 | 0.3 | 5.32
|  | Cum | 6 | 2 | 3.215 | 0.345 | 0.3 | 3.99
|  | Cum | 6 | 2 | 3.215 | 0.23 | 0.19 | 1.69
|  | Cum | 1 | 1 | 3.215 | 0.46 | 0.3 | 0.44
|  | Cum | 1 | 1 | 3.215 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.215 | 0.23 | 0.19 | 0.14
|  | Cum | 1 | 1 | 5.135 | 0.46 | 0.3 | 0.71
|  | Cum | 1 | 1 | 4.905 | 0.345 | 0.3 | 0.51
|  | Cum | 1 | 1 | 4.675 | 0.23 | 0.19 | 0.2
| Brick Work for Sheat | Cum | 1 | 11 | 3 | 0.115 | 0.19 | 0.72
|  | Cum | 1 | 11 | 3 | 0.345 | 0.425 | 4.84
Brick Work P/L for Planter South sid of BH-02 & BH-03 (drg. No. TU/LA-P-206.1) ( (19'-21'/35-40)
Brick Work for Planter
| Longitudianal axies (40/19'-20') | Cum | 1 | 2 | 4.05 | 0.46 | 0.3 | 1.12
|  | Cum | 1 | 2 | 3.935 | 0.345 | 0.3 | 0.81
|  | Cum | 1 | 2 | 3.82 | 0.23 | 0.19 | 0.33
|  | Cum | 1 | 2 | 6.185 | 0.46 | 0.3 | 1.71
|  | Cum | 1 | 2 | 6.07 | 0.345 | 0.3 | 1.26
|  | Cum | 1 | 2 | 5.955 | 0.23 | 0.19 | 0.52
|  | Cum | 1 | 2 | 7.1 | 0.46 | 0.3 | 1.96
|  | Cum | 1 | 2 | 6.985 | 0.345 | 0.3 | 1.45
|  | Cum | 1 | 2 | 6.87 | 0.23 | 0.19 | 0.6
|  | Cum | 1 | 2 | 6.49 | 0.46 | 0.3 | 1.79
|  | Cum | 1 | 2 | 6.375 | 0.345 | 0.3 | 1.32
|  | Cum | 1 | 2 | 6.26 | 0.23 | 0.19 | 0.55
|  | Cum | 1 | 5 | 0.6 | 0.46 | 0.3 | 0.41
|  | Cum | 1 | 5 | 0.6 | 0.345 | 0.3 | 0.31
|  | Cum | 1 | 5 | 0.6 | 0.23 | 0.19 | 0.13
Brick Work for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J)
| Brick Work for Road Toe Wall (1/F-J) |  | 1 | 1 | 4.635 | 0.46 | 0.3 | 0.64
|  |  | 1 | 1 | 4.635 | 0.345 | 0.3 | 0.48
|  |  | 1 | 1 | 4.635 | 0.23 | 0.19 | 0.2
|  |  | 1 | 10 | 7.625 | 0.46 | 0.3 | 10.52
|  |  | 1 | 10 | 7.625 | 0.345 | 0.3 | 7.89
|  |  | 1 | 10 | 7.625 | 0.23 | 0.19 | 3.33
|  |  | 1 | 1 | 15.765 | 0.46 | 0.3 | 2.18
|  |  | 1 | 1 | 15.765 | 0.345 | 0.3 | 1.63
|  |  | 1 | 1 | 15.765 | 0.23 | 0.19 | 0.69
| Brick Work for Road Toe Wall (J/1-9) |  | 1 | 1 | 14.21 | 0.46 | 0.3 | 1.96
|  |  | 1 | 1 | 14.325 | 0.345 | 0.3 | 1.48
|  |  | 1 | 1 | 14.44 | 0.23 | 0.19 | 0.63
|  |  | 1 | 5 | 7.625 | 0.46 | 0.3 | 5.26
|  |  | 1 | 5 | 7.625 | 0.345 | 0.3 | 3.95
|  |  | 1 | 5 | 7.625 | 0.23 | 0.19 | 1.67
|  |  | 1 | 1 | 0.15 | 0.46 | 0.3 | 0.02
|  |  | 1 | 1 | 0.15 | 0.345 | 0.3 | 0.02
|  |  | 1 | 1 | 0.15 | 0.23 | 0.19 | 0.01
| Brick Work for Road Toe Wall (9/H-J) |  | 1 | 1 | 7.645 | 0.46 | 0.3 | 1.06
|  |  | 1 | 1 | 7.702 | 0.345 | 0.3 | 0.8
|  |  | 1 | 1 | 7.76 | 0.23 | 0.19 | 0.34
|  |  | 1 | 2 | 7.625 | 0.46 | 0.3 | 2.1
|  |  | 1 | 2 | 7.625 | 0.345 | 0.3 | 1.58
|  |  | 1 | 2 | 7.625 | 0.23 | 0.19 | 0.67
Brick Work for Waterbody
| Brick Work outer side of Waterbody (dia.=20.12+0.2*2+0.23*2=20.98) | Cum | 1 | 1 | 64.958 | 0.23 | 0.545 | 8.14
Brick Work P/L for Podium
| Brick Work for Planter at Podium Area Ref. (Drg. No. TU/LA-P-216) grid (H-J/1-2) | Cum | 1 | 2 | 22 | 0.23 | 0.6 | 6.07
|  | Cum | 1 | 2 | 2.4 | 0.23 | 0.6 | 0.66
|  | Cum | 3 | 2 | 4.77 | 0.23 | 0.75 | 4.94
|  | Cum | 3 | 1 | 1.54 | 0.23 | 0.75 | 0.8
|  | Cum | 2 | 2 | 5 | 0.23 | 0.75 | 3.45
|  | Cum | 2 | 2 | 1.54 | 0.23 | 0.75 | 1.06
|  | Cum | 4 | 2 | 3 | 0.23 | 0.6 | 3.31
|  | Cum | 5 | 2 | 5 | 0.23 | 0.75 | 8.63
|  | Cum | 5 | 2 | 1.54 | 0.23 | 0.75 | 2.66
Brick Work for Seat
|  | Cum | 8 | 2 | 5 | 0.23 | 0.55 | 10.12
|  | Cum | 8 | 2 | 1.54 | 0.23 | 0.55 | 3.12
Brick Work P/L for Boy's Hostel
Brick Work for Planter near Waterbody & Reception (22'-26'/32-36) Ref. Drg. No. TU/LA-P-206.1
Brick Work for Planter
| Longitudianal axies (32/22'-26') | Cum | 1 | 1 | 10.27 | 0.46 | 0.3 | 1.42
|  | Cum | 1 | 1 | 10.04 | 0.345 | 0.3 | 1.04
|  | Cum | 1 | 1 | 9.81 | 0.23 | 0.19 | 0.43
|  | Cum | 1 | 1 | 9.855 | 0.46 | 0.3 | 1.36
|  | Cum | 1 | 1 | 9.74 | 0.345 | 0.3 | 1.01
|  | Cum | 1 | 1 | 9.625 | 0.23 | 0.19 | 0.42
| (33/22'-26') | Cum | 1 | 2 | 8.6 | 0.46 | 0.3 | 2.37
|  | Cum | 1 | 2 | 8.485 | 0.345 | 0.3 | 1.76
|  | Cum | 1 | 2 | 8.37 | 0.23 | 0.19 | 0.73
| (34/22'-26') | Cum | 1 | 2 | 7.076 | 0.46 | 0.3 | 1.95
|  | Cum | 1 | 2 | 6.961 | 0.345 | 0.3 | 1.44
|  | Cum | 1 | 2 | 6.846 | 0.23 | 0.19 | 0.6
| (35/22'-26') | Cum | 1 | 2 | 5.245 | 0.46 | 0.3 | 1.45
|  | Cum | 1 | 2 | 5.13 | 0.345 | 0.3 | 1.06
|  | Cum | 1 | 2 | 5.015 | 0.23 | 0.19 | 0.44
| (36/22'-26') | Cum | 1 | 1 | 3.72 | 0.46 | 0.3 | 0.51
|  | Cum | 1 | 1 | 3.605 | 0.345 | 0.3 | 0.37
|  | Cum | 1 | 1 | 3.49 | 0.23 | 0.19 | 0.15
|  | Cum | 0 | 1 | 4.25 | 0.46 | 0.3
|  | Cum | 0 | 1 | 4.02 | 0.345 | 0.3
|  | Cum | 0 | 1 | 3.79 | 0.23 | 0.19
| Transverse Axies | Cum | 1 | 5 | 0.6 | 0.46 | 0.3 | 0.41
|  | Cum | 1 | 5 | 0.6 | 0.345 | 0.3 | 0.31
|  | Cum | 1 | 5 | 0.6 | 0.23 | 0.19 | 0.13
| Brick Work for Ramp for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205 |  |  |  | ht.=0.7=0.7m, =0.5+0.7=1.2m
|  | Cum | 1 | 2 | 6 | 0.345 | 0.3 | 1.24
|  | Cum | 1 | 2 | 6 | 0.23 | 0.35 | 0.97
|  | Cum | 1 | 1 | 2.925 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.925 | 0.23 | 0.5 | 0.34
|  | Cum | 1 | 1 | 1.08 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.08 | 0.23 | 0.5 | 0.12
|  | Cum | 1 | 1 | 2 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2 | 0.23 | 0.1 | 0.05
| Brick Work for Steps | Cum | 1 | 1 | 3 | 0.3 | 0.7 | 0.63
|  | Cum | 1 | 1 | 3 | 0.6 | 0.85 | 1.53
|  | Cum | 1 | 1 | 3 | 0.9 | 1 | 2.7
| brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.6 | 0.23 | 0.6 | 0.08
Brick Work for Entry Area Steps of BH-01
| Steps for Entry | Cum | 1 | 3 | 5.42 | 1.42 | 0.15 | 3.46
| Brick Work for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205 |  |  |  | ht.=0.7=0.7m, =0.5+0.7=1.2m
|  | Cum | 1 | 2 | 6 | 0.345 | 0.3 | 1.24
|  | Cum | 1 | 2 | 6 | 0.23 | 0.35 | 0.97
|  | Cum | 1 | 1 | 2.925 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.925 | 0.23 | 0.5 | 0.34
|  | Cum | 1 | 1 | 1.08 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.08 | 0.23 | 0.5 | 0.12
|  | Cum | 1 | 1 | 2 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2 | 0.23 | 0.1 | 0.05
| Brick Work for Steps | Cum | 1 | 1 | 3 | 0.3 | 0.7 | 0.63
|  | Cum | 1 | 1 | 3 | 0.6 | 0.85 | 1.53
|  | Cum | 1 | 1 | 3 | 0.9 | 1 | 2.7
| brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.6 | 0.23 | 0.6 | 0.08
Brick Work for Entry Area Steps of BH-02
| Steps for Entry | Cum | 1 | 3 | 5.42 | 1.42 | 0.15 | 3.46
| Brick Work for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205 |  |  |  | ht.=0.7=0.7m, =0.5+0.7=1.2m
|  | Cum | 1 | 2 | 6 | 0.345 | 0.3 | 1.24
|  | Cum | 1 | 2 | 6 | 0.23 | 0.35 | 0.97
|  | Cum | 1 | 1 | 2.925 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.925 | 0.23 | 0.5 | 0.34
|  | Cum | 1 | 1 | 1.08 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.08 | 0.23 | 0.5 | 0.12
|  | Cum | 1 | 1 | 2 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2 | 0.23 | 0.1 | 0.05
| Brick Work for Steps | Cum | 1 | 1 | 3 | 0.3 | 0.7 | 0.63
|  | Cum | 1 | 1 | 3 | 0.6 | 0.85 | 1.53
|  | Cum | 1 | 1 | 3 | 0.9 | 1 | 2.7
| brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.6 | 0.23 | 0.6 | 0.08
Brick Work for Entry Area Steps of BH-03
| Steps for Entry | Cum | 1 | 3 | 5.42 | 1.42 | 0.15 | 3.46
| Brick Work for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205 |  |  |  | ht.=0.7=0.7m, =0.5+0.7=1.2m
|  | Cum | 1 | 2 | 6 | 0.345 | 0.3 | 1.24
|  | Cum | 1 | 2 | 6 | 0.23 | 0.35 | 0.97
|  | Cum | 1 | 1 | 2.925 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.925 | 0.23 | 0.5 | 0.34
|  | Cum | 1 | 1 | 1.08 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.08 | 0.23 | 0.5 | 0.12
|  | Cum | 1 | 1 | 2 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2 | 0.23 | 0.1 | 0.05
| Brick Work for Steps | Cum | 1 | 1 | 3 | 0.3 | 0.7 | 0.63
|  | Cum | 1 | 1 | 3 | 0.6 | 0.85 | 1.53
|  | Cum | 1 | 1 | 3 | 0.9 | 1 | 2.7
| brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.345 | 0.3 | 0.06
|  | Cum | 1 | 1 | 0.6 | 0.23 | 0.6 | 0.08
Brick Work for Entry Area Steps of BH-04
| Steps for Entry | Cum | 1 | 3 | 5.42 | 1.42 | 0.15 | 3.46
Brick Work for Road Toe Wall (9/H-J)
|  | Cum | 1 | 1 | 7.625 | 0.46 | 0.3 | 1.05
|  | Cum | 1 | 1 | 7.625 | 0.345 | 0.3 | 0.79
|  | Cum | 1 | 1 | 7.625 | 0.23 | 0.19 | 0.33
|  | Cum | 1 | 1 | 1.1 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.1 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.1 | 0.23 | 0.19 | 0.05
Brick Work for Road Toe Wall (9/F-H) basket ball ground & BH-03
|  | Cum | 1 | 1 | 7.625 | 0.46 | 0.3 | 1.05
|  | Cum | 1 | 1 | 7.625 | 0.345 | 0.3 | 0.79
|  | Cum | 1 | 1 | 7.625 | 0.23 | 0.19 | 0.33
|  | Cum | 1 | 1 | 7.125 | 0.46 | 0.3 | 0.98
|  | Cum | 1 | 1 | 7.125 | 0.345 | 0.3 | 0.74
|  | Cum | 1 | 1 | 7.125 | 0.23 | 0.19 | 0.31
Brick work for Seprate Seat
Brick work seat under transfer slab of BH-04 towards Waterbody
| TOS lvl. +0.5m | Cum | 1 | 7 | 3.526 | 0.46 | 0.3 | 3.41
|  | Cum | 1 | 7 | 3.526 | 0.345 | 0.3 | 2.55
|  | Cum | 1 | 7 | 3.526 | 0.23 | 0.69 | 3.92
Brick work seat between Waterbody & Reception
| TOS lvl. +0.5m | Cum | 1 | 8 | 3.526 | 0.46 | 0.3 | 3.89
|  | Cum | 1 | 8 | 3.526 | 0.345 | 0.3 | 2.92
|  | Cum | 1 | 8 | 3.526 | 0.23 | 0.69 | 4.48
Brick work seat under transfer slab of BH-01 towards Canteen
| TOS lvl. +0.5m | Cum | 1 | 6 | 3.526 | 0.46 | 0.3 | 2.92
|  | Cum | 1 | 6 | 3.526 | 0.345 | 0.3 | 2.19
|  | Cum | 1 | 6 | 3.526 | 0.23 | 0.69 | 3.36
Brick Work P/L for Fire Tender Wall (parallel to road)
| Fire Tender Wall towards BH-07 | Cum | 1 | 1 | 24.945 | 0.46 | 0.3 | 3.44
|  | Cum | 1 | 1 | 24.945 | 0.345 | 0.3 | 2.58
|  | Cum | 1 | 1 | 24.945 | 0.23 | 0.19 | 1.09
|  | Cum | 1 | 1 | 13.605 | 0.46 | 0.3 | 1.88
|  | Cum | 1 | 1 | 13.605 | 0.345 | 0.3 | 1.41
|  | Cum | 1 | 1 | 13.605 | 0.23 | 0.19 | 0.59
|  | Cum | 1 | 1 | 4.343 | 0.46 | 0.3 | 0.6
|  | Cum | 1 | 1 | 4.343 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 1 | 4.343 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 1 | 4.748 | 0.46 | 0.3 | 0.66
|  | Cum | 1 | 1 | 4.748 | 0.345 | 0.3 | 0.49
|  | Cum | 1 | 1 | 4.748 | 0.23 | 0.19 | 0.21
|  | Cum | 1 | 1 | 0.374 | 0.46 | 0.3 | 0.05
|  | Cum | 1 | 1 | 0.374 | 0.345 | 0.3 | 0.04
|  | Cum | 1 | 1 | 0.374 | 0.23 | 0.19 | 0.02
| Brick work for green Planter wall BH-07 (west side) | Cum | 1 | 1 | 1.359 | 0.46 | 0.3 | 0.19
|  | Cum | 1 | 1 | 1.359 | 0.345 | 0.3 | 0.14
|  | Cum | 1 | 1 | 1.359 | 0.23 | 0.19 | 0.06
|  | Cum | 1 | 1 | 26.229 | 0.46 | 0.3 | 3.62
|  | Cum | 1 | 1 | 26.229 | 0.345 | 0.3 | 2.71
|  | Cum | 1 | 1 | 26.229 | 0.23 | 0.19 | 1.15
| Fire Tender Wall towards BH-01 | Cum | 1 | 1 | 10.508 | 0.46 | 0.3 | 1.45
|  | Cum | 1 | 1 | 10.508 | 0.345 | 0.3 | 1.09
|  | Cum | 1 | 1 | 10.508 | 0.23 | 0.19 | 0.46
|  | Cum | 1 | 1 | 1.639 | 0.46 | 0.3 | 0.23
|  | Cum | 1 | 1 | 1.639 | 0.345 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.639 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 2.059 | 0.46 | 0.3 | 0.28
|  | Cum | 1 | 1 | 2.059 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2.059 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 2.938 | 0.46 | 0.3 | 0.41
|  | Cum | 1 | 1 | 2.938 | 0.345 | 0.3 | 0.3
|  | Cum | 1 | 1 | 2.938 | 0.23 | 0.19 | 0.13
|  | Cum | 1 | 1 | 7.795 | 0.46 | 0.3 | 1.08
|  | Cum | 1 | 1 | 7.795 | 0.345 | 0.3 | 0.81
|  | Cum | 1 | 1 | 7.795 | 0.23 | 0.19 | 0.34
|  | Cum | 1 | 1 | 2.063 | 0.46 | 0.3 | 0.28
|  | Cum | 1 | 1 | 2.063 | 0.345 | 0.3 | 0.21
|  | Cum | 1 | 1 | 2.063 | 0.23 | 0.19 | 0.09
|  | Cum | 1 | 1 | 1.079 | 0.46 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.079 | 0.345 | 0.3 | 0.11
|  | Cum | 1 | 1 | 1.079 | 0.23 | 0.19 | 0.05
|  | Cum | 1 | 1 | 3.273 | 0.46 | 0.3 | 0.45
|  | Cum | 1 | 1 | 3.273 | 0.345 | 0.3 | 0.34
|  | Cum | 1 | 1 | 3.273 | 0.23 | 0.19 | 0.14
|  | Cum | 1 | 1 | 5.084 | 0.46 | 0.3 | 0.7
|  | Cum | 1 | 1 | 5.084 | 0.345 | 0.3 | 0.53
|  | Cum | 1 | 1 | 5.084 | 0.23 | 0.19 | 0.22
| Fire Tender Wall Brick Work between BH-04 & BH-07 near green Planter (triangle type) | Cum | 0 | 1 | 1.398 | 0.46 | 0.3
|  | Cum | 0 | 1 | 1.398 | 0.345 | 0.3
|  | Cum | 0 | 1 | 1.398 | 0.23 | 0.19
0
|  | Cum | 0 | 1 | 6.182 | 0.46 | 0.3
|  | Cum | 0 | 1 | 6.182 | 0.345 | 0.3
|  | Cum | 0 | 1 | 6.182 | 0.23 | 0.19
|  | Cum | 0 | 1 | 0.23 | 0.46 | 0.3
|  | Cum | 0 | 1 | 0.23 | 0.345 | 0.3
|  | Cum | 0 | 1 | 0.23 | 0.23 | 0.19
|  | Cum | 0 | 1 | 8.695 | 0.46 | 0.3
|  | Cum | 0 | 1 | 8.695 | 0.345 | 0.3
|  | Cum | 0 | 1 | 8.695 | 0.23 | 0.19
|  | Cum | 1 | 1 | 16.409 | 0.46 | 0.3 | 2.26
|  | Cum | 1 | 1 | 16.409 | 0.345 | 0.3 | 1.7
|  | Cum | 1 | 1 | 16.409 | 0.23 | 0.19 | 0.72
| brick work for fire tender in green planter between BH-04 & BH-07 | Cum | 0 | 1 | 0.898 | 0.46 | 0.3
|  | Cum | 0 | 1 | 0.898 | 0.345 | 0.3
|  | Cum | 0 | 1 | 0.898 | 0.23 | 0.19
|  | Cum | 0 | 1 | 1.497 | 0.46 | 0.3
|  | Cum | 0 | 1 | 1.497 | 0.345 | 0.3
|  | Cum | 0 | 1 | 1.497 | 0.23 | 0.19
|  | Cum | 0 | 1 | 1.602 | 0.46 | 0.3
|  | Cum | 0 | 1 | 1.602 | 0.345 | 0.3
|  | Cum | 0 | 1 | 1.602 | 0.23 | 0.19
|  | Cum | 0 | 1 | 1.012 | 0.46 | 0.3
|  | Cum | 0 | 1 | 1.012 | 0.345 | 0.3
|  | Cum | 0 | 1 | 1.012 | 0.23 | 0.19
|  | Cum | 0 | 1 | 4.172 | 0.46 | 0.3
|  | Cum | 0 | 1 | 4.172 | 0.345 | 0.3
|  | Cum | 0 | 1 | 4.172 | 0.23 | 0.19
|  | Cum | 0 | 1 | 10.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 10.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 10.42 | 0.23 | 0.19
|  | Cum | 0 | 1 | 0.217 | 0.46 | 0.3
|  | Cum | 0 | 1 | 0.217 | 0.345 | 0.3
|  | Cum | 0 | 1 | 0.217 | 0.23 | 0.19
|  | Cum | 0 | 1 | 4.011 | 0.46 | 0.3
|  | Cum | 0 | 1 | 4.011 | 0.345 | 0.3
|  | Cum | 0 | 1 | 4.011 | 0.23 | 0.19
|  | Cum | 1 | 1 | 23.472 | 0.46 | 0.3 | 3.24
|  | Cum | 1 | 1 | 23.472 | 0.345 | 0.3 | 2.43
|  | Cum | 1 | 1 | 23.472 | 0.23 | 0.19 | 1.03
| Fire Tender Wall Brick Work connect to BH-04 to green Planter between BH-01 & waterbody | Cum | 1 | 1 | 15.694 | 0.46 | 0.3 | 2.17
|  | Cum | 1 | 1 | 15.694 | 0.345 | 0.3 | 1.62
|  | Cum | 1 | 1 | 15.694 | 0.23 | 0.19 | 0.69
|  | Cum | 1 | 1 | 0.225 | 0.46 | 0.3 | 0.03
|  | Cum | 1 | 1 | 0.225 | 0.345 | 0.3 | 0.02
|  | Cum | 1 | 1 | 0.225 | 0.23 | 0.19 | 0.01
| Brick Work for Fire Tender in Green planter between BH-01 & Waterbody | Cum | 1 | 1 | 1.497 | 0.46 | 0.3 | 0.21
|  | Cum | 1 | 1 | 1.497 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.497 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 1.6 | 0.46 | 0.3 | 0.22
|  | Cum | 1 | 1 | 1.6 | 0.345 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.6 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3.43 | 0.46 | 0.3 | 0.47
|  | Cum | 1 | 1 | 3.43 | 0.345 | 0.3 | 0.36
|  | Cum | 1 | 1 | 3.43 | 0.23 | 0.19 | 0.15
|  | Cum | 1 | 1 | 1.497 | 0.46 | 0.3 | 0.21
|  | Cum | 1 | 1 | 1.497 | 0.345 | 0.3 | 0.15
|  | Cum | 1 | 1 | 1.497 | 0.23 | 0.19 | 0.07
|  | Cum | 1 | 1 | 3.735 | 0.46 | 0.3 | 0.52
|  | Cum | 1 | 1 | 3.735 | 0.345 | 0.3 | 0.39
|  | Cum | 1 | 1 | 3.735 | 0.23 | 0.19 | 0.16
|  | Cum | 1 | 1 | 4.345 | 0.46 | 0.3 | 0.6
|  | Cum | 1 | 1 | 4.345 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 1 | 4.345 | 0.23 | 0.19 | 0.19
| Fire Tender Wall Brick Work BH-01 west corner to Canteen parallel to road betwee canteen & BH-02 | Cum | 1 | 1 | 2.386 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 1 | 2.386 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 1 | 2.386 | 0.23 | 0.19 | 0.1
|  | Cum | 1 | 1 | 20.003 | 0.46 | 0.3 | 2.76
|  | Cum | 1 | 1 | 20.003 | 0.345 | 0.3 | 2.07
|  | Cum | 1 | 1 | 20.003 | 0.23 | 0.19 | 0.87
| parallel to canteen | Cum | 1 | 1 | 33.331 | 0.46 | 0.3 | 4.6
|  | Cum | 1 | 1 | 33.331 | 0.345 | 0.3 | 3.45
|  | Cum | 1 | 1 | 33.331 | 0.23 | 0.19 | 1.46
| parallel to BH-02 towards canteen (east face) | Cum | 1 | 1 | 31.771 | 0.46 | 0.3 | 4.38
|  | Cum | 1 | 1 | 31.771 | 0.345 | 0.3 | 3.29
|  | Cum | 1 | 1 | 31.771 | 0.23 | 0.19 | 1.39
|  | Cum | 1 | 1 | 4.373 | 0.46 | 0.3 | 0.6
|  | Cum | 1 | 1 | 4.373 | 0.345 | 0.3 | 0.45
|  | Cum | 1 | 1 | 4.373 | 0.23 | 0.19 | 0.19
|  | Cum | 1 | 1 | 0.17 | 0.46 | 0.3 | 0.02
|  | Cum | 1 | 1 | 0.17 | 0.345 | 0.3 | 0.02
|  | Cum | 1 | 1 | 0.17 | 0.23 | 0.19 | 0.01
0.17
Fire Tender Wall Brick Work for Road between BH-02 & Waterbody
| wall towards BH-02 (BH-02 to Gym toilet) | Cum | 1 | 1 | 18.743 | 0.46 | 0.3 | 2.59
|  | Cum | 1 | 1 | 18.743 | 0.345 | 0.3 | 1.94
|  | Cum | 1 | 1 | 18.743 | 0.23 | 0.19 | 0.82
|  | Cum | 1 | 1 | 9.868 | 0.46 | 0.3 | 1.36
|  | Cum | 1 | 1 | 9.868 | 0.345 | 0.3 | 1.02
|  | Cum | 1 | 1 | 9.868 | 0.23 | 0.19 | 0.43
|  | Cum | 1 | 1 | 7.05 | 0.46 | 0.3 | 0.97
|  | Cum | 1 | 1 | 7.05 | 0.345 | 0.3 | 0.73
|  | Cum | 1 | 1 | 7.05 | 0.23 | 0.19 | 0.31
fire tender wall towards waterbody planter to arround waterbody to Reception
|  | CUM | 1 | 1 | 36.696 | 0.46 | 0.3 | 5.06
|  | CUM | 1 | 1 | 36.696 | 0.345 | 0.3 | 3.8
|  | CUM | 1 | 1 | 36.696 | 0.23 | 0.19 | 1.6
|  | Cum | 0 | 1 | 0.337 | 0.46 | 0.3
|  | Cum | 0 | 1 | 0.337 | 0.345 | 0.3
|  | Cum | 0 | 1 | 0.337 | 0.23 | 0.19
0
|  | Cum | 0 | 1 | 3.183 | 0.46 | 0.3
|  | Cum | 0 | 1 | 3.183 | 0.345 | 0.3
|  | Cum | 0 | 1 | 3.183 | 0.23 | 0.19
0
|  | Cum | 0 | 1 | 33.632 | 0.46 | 0.3
|  | Cum | 0 | 1 | 33.632 | 0.345 | 0.3
|  | Cum | 0 | 1 | 33.632 | 0.23 | 0.19
| in planter | Cum | 1 | 1 | 8.053 | 0.46 | 0.3 | 1.11
|  | Cum | 1 | 1 | 8.053 | 0.345 | 0.3 | 0.83
|  | Cum | 1 | 1 | 8.053 | 0.23 | 0.19 | 0.35
| fire tender wall west side of reception | Cum | 1 | 1 | 14.555 | 0.46 | 0.3 | 2.01
|  | Cum | 1 | 1 | 14.555 | 0.345 | 0.3 | 1.51
|  | Cum | 1 | 1 | 14.555 | 0.23 | 0.19 | 0.64
Fire Tender Wall Brick Work for Road South side of BH-04 (back side)
|  | Cum | 1 | 1 | 14.343 | 0.46 | 0.3 | 1.98
|  | Cum | 1 | 1 | 14.343 | 0.345 | 0.3 | 1.48
|  | Cum | 1 | 1 | 14.343 | 0.23 | 0.19 | 0.63
Fire Tender Wall Brick Work for Road BH-04 (near watebody to basket ball ground planter) to BH-03
|  | Cum | 1 | 1 | 60.78 | 0.46 | 0.3 | 8.39
|  | Cum | 1 | 1 | 60.78 | 0.345 | 0.3 | 6.29
|  | Cum | 1 | 1 | 60.78 | 0.23 | 0.19 | 2.66
| basket ball ground planter to BH-03 corner(front of Gym) | Cum | 1 | 1 | 35.253 | 0.46 | 0.3 | 4.86
|  | Cum | 1 | 1 | 35.253 | 0.345 | 0.3 | 3.65
|  | Cum | 1 | 1 | 35.253 | 0.23 | 0.19 | 1.54
Deduct Previous Bill Qty. for Revise
Brick Work for Fire Tender Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 (South side) | Cum | -1 | 1 | 31.4 | 0.46 | 0.3 | -4.33
|  | Cum | -1 | 1 | 31.4 | 0.345 | 0.3 | -3.25
|  | Cum | -1 | 1 | 31.4 | 0.23 | 0.19 | -1.37
| FIRE TENDER TOE WALL WITH BH-07 | Cum | -1 | 1 | 42.55 | 0.46 | 0.3 | -5.87
|  | Cum | -1 | 1 | 42.55 | 0.345 | 0.3 | -4.4
|  | Cum | -1 | 1 | 42.55 | 0.23 | 0.19 | -1.86
Brick Work at Podium
Brick Work P/L at Gym Roof , Ref. Drg. TU/LA-P-216(8-9/H-J)
Brick Work P/L for Long Planter Ref. Drg. TU/LA-P-216 (Lvl. +0.7m) (41-48/1'-14')
| (48-46/1'-13') | CUM | 1 | 1 | 29.035 | 0.23 | 0.65 | 4.34
|  | CUM | 1 | 2 | 2.4 | 0.23 | 0.65 | 0.72
|  | CUM | 1 | 1 | 2.93 | 0.23 | 0.65 | 0.44
|  | CUM | 1 | 4 | 3 | 0.23 | 0.65 | 1.79
|  | CUM | 1 | 1 | 3.735 | 0.23 | 0.65 | 0.56
| inner Brick work for long Planter (48-46/1'-13') | CUM | 5 | 2 | 4.7 | 0.23 | 0.8 | 8.65
|  | CUM | 5 | 2 | 1.54 | 0.23 | 0.8 | 2.83
| Brick Work for Planter (2'/42-45) | CUM | 3 | 2 | 2.685 | 0.23 | 0.6 | 2.22
|  | CUM | 3 | 2 | 1.74 | 0.23 | 0.6 | 1.44
| Brick Work for Planter (41/2'-12') | CUM | 5 | 2 | 2.63 | 0.23 | 0.65 | 3.93
|  | CUM | 5 | 2 | 1.54 | 0.23 | 0.65 | 2.3
| Brick Work for Chess Table | CUM | 10 | 2 | 0.84 | 0.23 | 0.8 | 3.09
|  | CUM | 10 | 2 | 0.38 | 0.23 | 0.8 | 1.4
| Chess Table Seat | CUM | 40 | 1 | 0.345 | 0.345 | 0.31 | 1.48
|  | CUM | 40 | 1 | 0.46 | 0.46 | 0.29 | 2.45
Brick Work for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22)
| longitudianal axies | Cum | 1 | 2 | 6.77 | 0.46 | 0.3 | 1.87
|  | Cum | 1 | 2 | 6.54 | 0.345 | 0.3 | 1.35
|  | Cum | 1 | 2 | 6.31 | 0.23 | 0.19 | 0.55
| Transverse axies | Cum | 1 | 2 | 1.8 | 0.46 | 0.3 | 0.5
|  | Cum | 1 | 2 | 1.8 | 0.345 | 0.3 | 0.37
|  | Cum | 1 | 2 | 1.8 | 0.23 | 0.19 | 0.16
| longitudianal axies | Cum | 1 | 2 | 5.445 | 0.46 | 0.3 | 1.5
|  | Cum | 1 | 2 | 5.215 | 0.345 | 0.3 | 1.08
|  | Cum | 1 | 2 | 4.985 | 0.23 | 0.19 | 0.44
| Transverse axies | Cum | 1 | 2 | 1.8 | 0.46 | 0.3 | 0.5
|  | Cum | 1 | 2 | 1.8 | 0.345 | 0.3 | 0.37
|  | Cum | 1 | 2 | 1.8 | 0.23 | 0.19 | 0.16
Brick Work for Green Planter South side of BH-03 towards Basket Ball Ground (Drg. No. TU/LA-P-206.1) (26'-27'/46-51)
| longitudianal axies | Cum | 1 | 2 | 6.77 | 0.46 | 0.3 | 1.87
|  | Cum | 1 | 2 | 6.54 | 0.345 | 0.3 | 1.35
|  | Cum | 1 | 2 | 6.31 | 0.23 | 0.19 | 0.55
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.2 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.2 | 0.23 | 0.19 | 0.1
| longitudianal axies | Cum | 1 | 2 | 5.445 | 0.46 | 0.3 | 1.5
|  | Cum | 1 | 2 | 5.215 | 0.345 | 0.3 | 1.08
|  | Cum | 1 | 2 | 4.985 | 0.23 | 0.19 | 0.44
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.2 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.2 | 0.23 | 0.19 | 0.1
Brick Work for Green Planter West side of BH-02 under transfer slab (Drg. No. TU/LA-P-206.1) (7'-14'/32-33)
| longitudianal axies | Cum | 1 | 2 | 6.77 | 0.46 | 0.3 | 1.87
|  | Cum | 1 | 2 | 6.54 | 0.345 | 0.3 | 1.35
|  | Cum | 1 | 2 | 6.31 | 0.23 | 0.19 | 0.55
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.2 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.2 | 0.23 | 0.19 | 0.1
| longitudianal axies | Cum | 1 | 2 | 5.445 | 0.46 | 0.3 | 1.5
|  | Cum | 1 | 2 | 5.215 | 0.345 | 0.3 | 1.08
|  | Cum | 1 | 2 | 4.985 | 0.23 | 0.19 | 0.44
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.2 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.2 | 0.23 | 0.19 | 0.1
| longitudianal axies | Cum | 1 | 2 | 3.545 | 0.46 | 0.3 | 0.98
|  | Cum | 1 | 2 | 3.315 | 0.345 | 0.3 | 0.69
|  | Cum | 1 | 2 | 3.085 | 0.23 | 0.19 | 0.27
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.2 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.2 | 0.23 | 0.19 | 0.1
| longitudianal axies | Cum | 1 | 2 | 3.32 | 0.46 | 0.3 | 0.92
|  | Cum | 1 | 2 | 3.09 | 0.345 | 0.3 | 0.64
|  | Cum | 1 | 2 | 2.86 | 0.23 | 0.19 | 0.25
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.46 | 0.3 | 0.33
|  | Cum | 1 | 2 | 1.2 | 0.345 | 0.3 | 0.25
|  | Cum | 1 | 2 | 1.2 | 0.23 | 0.19 | 0.1
Brick Work for Seprate Seat
Brick work for seprate seat under transfer slab of BH-03 towards Basket Ball Ground
| TOS lvl. +0.5m | CUM | 1 | 4 | 2.845 | 0.46 | 0.3 | 1.57
|  | CUM | 1 | 4 | 2.845 | 0.345 | 0.3 | 1.18
|  | CUM | 1 | 4 | 2.845 | 0.23 | 0.615 | 1.61
Brick work for seprate seat near Basket Ball Ground
| TOS lvl. +0.5m | CUM | 1 | 2 | 2.835 | 0.46 | 0.3 | 0.78
|  | CUM | 1 | 2 | 2.835 | 0.345 | 0.3 | 0.59
|  | CUM | 1 | 2 | 2.835 | 0.23 | 0.615 | 0.8
Brick work for seprate seat under transfer slab of BH-02 towards Gym
| TOS lvl. +0.5m | CUM | 1 | 6 | 2.835 | 0.46 | 0.3 | 2.35
|  | CUM | 1 | 6 | 2.835 | 0.345 | 0.3 | 1.76
|  | CUM | 1 | 6 | 2.835 | 0.23 | 0.615 | 2.41
| UP TO PREVIOUS BILL | Cum | [6 empty] | 994.17
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
994.17
RCC
4 | Reinforcement for R.C.C. works including straightening, cutting , bending, placing in position and binding all complete. Cold twisted bars.
| Reinforcement Steel | MT | 1 |  | 10.22 |  |  | 10.22 |  | RA-2
| Reinforcement Steel | MT | 1 |  | 14.4 |  |  | 14.4 |  | RA-3
| Reinforcement Steel | MT | 1 |  | 7.873 |  |  | 7.873
| Reinforcement Steel | MT | 1 |  | 1.304 |  |  | 1.304 |  | RA-5
| UP TO PREVIOUS BILL | MT | [6 empty] | 33.797
| As Per Attached BBS | MT | 1 |  | 0.12562 |  |  | 0.126
| THIS BILL TOTAL → | MT | [6 empty] | 0.126 | 6th RA
33.923
RCC
4 | Providing and laying in position ready mixed M-25 grade concrete for reinforced concrete works, using cement content as per approved design mix manufactured in fully automatic batching plant and transported to site of work in transit mixers for all leads having continious agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete worksincluding pumping of R.M.C. from transit mixer to site of laying excluding the finishing and reinforcement including cost of admixture in recommende proportionas per IS:9103 to accelerate / retard setting of concrete, improve workability without imparing strength and durabilityas per direction of the chief enginner-in charge (min OPC contentto be considered in this item is 300kg/cum or as per design mix)
| Planter BH-01 NORTH SIDE (M25) | Cum | 1 |  | 11.15 | 0.23 | 0.2 | 0.51
| G 32-37/1-5 vertical | Cum | 2 |  | 8.92 | 0.23 | 0.2 | 0.82
|  | Cum | 1 |  | 9.78 | 0.23 | 0.2 | 0.45
|  | Cum | 2 |  | 6.52 | 0.23 | 0.2 | 0.6
|  | Cum | 1 |  | 6.22 | 0.23 | 0.2 | 0.29
|  | Cum | 1 |  | 6.45 | 0.23 | 0.2 | 0.3
|  | Cum | 1 |  | 4.66 | 0.23 | 0.2 | 0.21
|  | Cum | 1 |  | 6.89 | 0.23 | 0.2 | 0.32
| #REF! | Cum | 5 |  | 0.615 | 0.23 | 0.2 | 0.14
|  | Cum | 1 |  | 3.82 | 0.23 | 0.2 | 0.18
|  | Cum | 4 |  | 1.67 | 0.23 | 0.2 | 0.31
|  | Cum | 3 |  | 2.515 | 0.23 | 0.2 | 0.35
| BH01-NORTH SIDE | Cum | 1 |  | 5.99 | 0.23 | 0.2 | 0.28
| Bet G 31-28 /1-5 vertical | Cum | 1 |  | 3.99 | 0.23 | 0.2 | 0.18
|  | Cum | 2 |  | 2.19 | 0.23 | 0.2 | 0.2
|  | Cum | 2 |  | 2.79 | 0.23 | 0.2 | 0.26
|  | Cum | 1 |  | 1.66 | 0.23 | 0.2 | 0.08
|  | Cum | 1 |  | 3.89 | 0.23 | 0.2 | 0.18
| Bet. G 31-28/1-5 horizontal | Cum | 5 |  | 0.615 | 0.23 | 0.2 | 0.14
|  | Cum | 3 |  | 2.515 | 0.23 | 0.2 | 0.35
|  | Cum | 3 |  | 1.67 | 0.23 | 0.2 | 0.23
| BH-02 EAST SIDE BET G 20-28/1-6 VERTICAL | Cum | 1 |  | 9.615 | 0.23 | 0.2 | 0.44
|  | Cum | 2 |  | 7.245 | 0.23 | 0.2 | 0.67
|  | Cum | 1 |  | 7.475 | 0.23 | 0.2 | 0.34
|  | Cum | 1 |  | 3.87 | 0.23 | 0.2 | 0.18
|  | Cum | 1 |  | 4.1 | 0.23 | 0.2 | 0.19
|  | Cum | 2 |  | 4.195 | 0.23 | 0.2 | 0.39
|  | Cum | 1 |  | 3.555 | 0.23 | 0.2 | 0.16
|  | Cum | 1 |  | 3.785 | 0.23 | 0.2 | 0.17
|  | Cum | 1 |  | 2.64 | 0.23 | 0.2 | 0.12
|  | Cum | 1 |  | 2.87 | 0.23 | 0.2 | 0.13
|  | Cum | 2 |  | 2.26 | 0.23 | 0.2 | 0.21
|  | Cum | 1 |  | 2.57 | 0.23 | 0.2 | 0.12
| BH-02 EAST SIDE BET G 20-28/1-6 Horizontal | Cum | 5 |  | 0.6 | 0.23 | 0.2 | 0.14
|  | Cum | 6 |  | 1.54 | 0.23 | 0.2 | 0.43
|  | Cum | 1 |  | 3.205 | 0.23 | 0.2 | 0.15
|  | Cum | 4 |  | 2.37 | 0.23 | 0.2 | 0.44
|  | Cum | 1 |  | 2.6 | 0.23 | 0.2 | 0.12
|  | Cum | 1 |  | 3.2 | 0.23 | 0.2 | 0.15
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 9.26 | 0.23 | 0.2 | 0.43
| BET.G 17-21/20-25 | Cum | 1 |  | 7.46 | 0.23 | 0.2 | 0.34
|  | Cum | 1 |  | 8.46 | 0.23 | 0.2 | 0.39
|  | Cum | 1 |  | 8.23 | 0.23 | 0.2 | 0.38
|  | Cum | 2 |  | 7.46 | 0.23 | 0.2 | 0.69
|  | Cum | 1 |  | 4.96 | 0.23 | 0.2 | 0.23
|  | Cum | 2 |  | 4.73 | 0.23 | 0.2 | 0.44
|  | Cum | 1 |  | 7.96 | 0.23 | 0.2 | 0.37
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Cum | 8 |  | 0.615 | 0.23 | 0.2 | 0.23
| BET.G 17-21/20-25 | Cum | 2 |  | 1.975 | 0.23 | 0.2 | 0.18
|  | Cum | 2 |  | 2.515 | 0.23 | 0.2 | 0.23
|  | Cum | 4 |  | 1.67 | 0.23 | 0.2 | 0.31
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 8.46 | 0.23 | 0.2 | 0.39
| BET.G 17-21/25-29 | Cum | 1 |  | 6.43 | 0.23 | 0.2 | 0.3
|  | Cum | 2 |  | 6.66 | 0.23 | 0.2 | 0.61
|  | Cum | 2 |  | 7.66 | 0.23 | 0.2 | 0.7
|  | Cum | 1 |  | 8.23 | 0.23 | 0.2 | 0.38
|  | Cum | 1 |  | 10.26 | 0.23 | 0.2 | 0.47
| PLANTER BET -01 AND WATER BODY Horizontal | Cum | 6 |  | 0.615 | 0.23 | 0.2 | 0.17
| BET.G 17-21/25-29 | Cum | 2 |  | 2.515 | 0.23 | 0.2 | 0.23
|  | Cum | 4 |  | 1.67 | 0.23 | 0.2 | 0.31
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 7.24 | 0.23 | 0.2 | 0.33
| BET.G 17-21/29-35 | Cum | 1 |  | 5.23 | 0.23 | 0.2 | 0.24
|  | Cum | 2 |  | 4.23 | 0.23 | 0.2 | 0.39
|  | Cum | 3 |  | 4.46 | 0.23 | 0.2 | 0.62
|  | Cum | 3 |  | 3.23 | 0.23 | 0.2 | 0.45
|  | Cum | 1 |  | 5.23 | 0.23 | 0.2 | 0.24
|  | Cum | 0 |  | 3.66 | 0.23 | 0.2
|  | Cum | 1 |  | 5.26 | 0.23 | 0.2 | 0.24
| PLANTER BET -01 AND WATER BODY Horizontal | Cum | 5 |  | 0.615 | 0.23 | 0.2 | 0.14
| BET.G 17-21/29-35 | Cum | 3 |  | 3.36 | 0.23 | 0.2 | 0.46
|  | Cum | 6 |  | 0.91 | 0.23 | 0.2 | 0.25
|  | Cum | 1 |  | 2.135 | 0.23 | 0.2 | 0.1
| SEAT | Cum | 4 |  | 3 | 0.385 | 0.275 | 1.27
| PLANTER BET -04 AND BH-05 VERTICAL | Cum | 1 |  | 11.14 | 0.23 | 0.2 | 0.51
| BET.G 32-36/39-47 | Cum | 1 |  | 8.91 | 0.23 | 0.2 | 0.41
|  | Cum | 2 |  | 6.21 | 0.23 | 0.2 | 0.57
|  | Cum | 2 |  | 5.31 | 0.23 | 0.2 | 0.49
|  | Cum | 2 |  | 4.41 | 0.23 | 0.2 | 0.41
|  | Cum | 2 |  | 2.61 | 0.23 | 0.2 | 0.24
|  | Cum | 2 |  | 4.71 | 0.23 | 0.2 | 0.43
|  | Cum | 2 |  | 2.61 | 0.23 | 0.2 | 0.24
|  | Cum | 1 |  | 1.71 | 0.23 | 0.2 | 0.08
|  | Cum | 1 |  | 3.94 | 0.23 | 0.2 | 0.18
| PLANTER BET -04 AND BH-05 HORIZONTAL | Cum | 3 |  | 0.615 | 0.23 | 0.2 | 0.08
| BET.G 32-36/39-47 | Cum | 1 |  | 2.975 | 0.23 | 0.2 | 0.14
|  | Cum | 7 |  | 1.67 | 0.23 | 0.2 | 0.54
|  | Cum | 6 |  | 3.36 | 0.23 | 0.2 | 0.93
| PLANTER NEAR ZYM Vertical | Cum | 1 |  | 7.86 | 0.23 | 0.2 | 0.36
| BET.G 2-11/48-52 | Cum | 1 |  | 5.63 | 0.23 | 0.2 | 0.26
|  | Cum | 2 |  | 6.23 | 0.23 | 0.2 | 0.57
|  | Cum | 2 |  | 5.03 | 0.23 | 0.2 | 0.46
|  | Cum | 2 |  | 6.46 | 0.23 | 0.2 | 0.59
|  | Cum | 2 |  | 4.43 | 0.23 | 0.2 | 0.41
|  | Cum | 2 |  | 5.03 | 0.23 | 0.2 | 0.46
|  | Cum | 2 |  | 4.43 | 0.23 | 0.2 | 0.41
|  | Cum | 1 |  | 6.46 | 0.23 | 0.2 | 0.3
|  | Cum | 2 |  | 6.23 | 0.23 | 0.2 | 0.57
|  | Cum | 1 |  | 8.46 | 0.23 | 0.2 | 0.39
| PLANTER NEAR ZYM Horizontal | Cum | 6 |  | 0.615 | 0.23 | 0.2 | 0.17
| BET.G 2-11/48-52 | Cum | 4 |  | 1.67 | 0.23 | 0.2 | 0.31
|  | Cum | 1 |  | 1.475 | 0.23 | 0.2 | 0.07
|  | Cum | 3 |  | 3.36 | 0.23 | 0.2 | 0.46
|  | Cum | 4 |  | 2.515 | 0.23 | 0.2 | 0.46
|  | Cum | 3 |  | 1.365 | 0.23 | 0.2 | 0.19
| SAET | Cum | 8 |  | 3 | 0.385 | 0.275 | 2.54
| PLANTER BET. BH-04 AND BH-07 Vertical | Cum | 1 |  | 10.12 | 0.23 | 0.2 | 0.47
| BET.G 13-18/48-52 | Cum | 1 |  | 7.89 | 0.23 | 0.2 | 0.36
|  | Cum | 2 |  | 8.39 | 0.23 | 0.2 | 0.77
|  | Cum | 2 |  | 6.39 | 0.23 | 0.2 | 0.59
|  | Cum | 1 |  | 8.39 | 0.23 | 0.2 | 0.39
|  | Cum | 1 |  | 10.62 | 0.23 | 0.2 | 0.49
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 2 |  | 0.615 | 0.23 | 0.2 | 0.06
| BET.G 13-18/48-52 | Cum | 3 |  | 3.36 | 0.23 | 0.2 | 0.46
|  | Cum | 3 |  | 1.67 | 0.23 | 0.2 | 0.23
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 7 |  | 0.615 | 0.23 | 0.2 | 0.2
| BET.G 13-18/48-42 | Cum | 2 |  | 2.515 | 0.23 | 0.2 | 0.23
|  | Cum | 5 |  | 1.67 | 0.23 | 0.2 | 0.38
|  | Cum | 1 |  | 1.06 | 0.23 | 0.2 | 0.05
|  | Cum | 1 |  | 3.36 | 0.23 | 0.2 | 0.15
| PLANTER BET. BH-04 AND BH-07 VERTICAL | Cum | 1 |  | 9.82 | 0.23 | 0.2 | 0.45
| BET.G 13-18/48-42 | Cum | 1 |  | 7.82 | 0.23 | 0.2 | 0.36
|  | Cum | 1 |  | 6.39 | 0.23 | 0.2 | 0.29
|  | Cum | 1 |  | 6.62 | 0.23 | 0.2 | 0.3
|  | Cum | 2 |  | 4.59 | 0.23 | 0.2 | 0.42
|  | Cum | 1 |  | 4.29 | 0.23 | 0.2 | 0.2
|  | Cum | 1 |  | 4.29 | 0.23 | 0.2 | 0.2
|  | Cum | 1 |  | 4.52 | 0.23 | 0.2 | 0.21
|  | Cum | 1 |  | 2.43 | 0.23 | 0.2 | 0.11
|  | Cum | 1 |  | 4.66 | 0.23 | 0.2 | 0.21
| SEAT | Cum | -41 |  | 3 | 0.23 | 0.2 | -5.66
| SEAT | Cum | 41 |  | 3 | 0.385 | 0.275 | 13.02
PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL HORIZONTAL
| BET.G 35-41/42-48 | Cum | 1 |  | 18.78 | 0.23 | 0.2 | 0.86
|  | Cum | 1 |  | 1.48 | 0.23 | 0.2 | 0.07
|  | Cum | 6 |  | 1.075 | 0.23 | 0.2 | 0.3
|  | Cum | 3 |  | 1.98 | 0.23 | 0.2 | 0.27
|  | Cum | 2 |  | 1.67 | 0.23 | 0.2 | 0.15
|  | Cum | 1 |  | 1.3 | 0.23 | 0.2 | 0.06
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL VERTICAL | Cum |  |  |  | 0.23 | 0.2
| BET.G 35-41/42-48 | Cum | 2 |  | 2 | 0.23 | 0.2 | 0.18
|  | Cum | 2 |  | 3 | 0.23 | 0.2 | 0.28
|  | Cum | 2 |  | 4.645 | 0.23 | 0.2 | 0.43
|  | Cum | 2 |  | 6.12 | 0.23 | 0.2 | 0.56
|  | Cum | 2 |  | 6.95 | 0.23 | 0.2 | 0.64
|  | Cum | 2 |  | 6.38 | 0.23 | 0.2 | 0.59
|  | Cum | 2 |  | 5.345 | 0.23 | 0.2 | 0.49
| SEAT | Cum | -3 |  | 3 | 0.23 | 0.2 | -0.41
| SEAT | Cum | 3 |  | 3 | 0.385 | 0.275 | 0.95
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 34.935 | 0.23 | 0.2 | 1.61
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 15 | 0.23 | 0.2 | 0.69
| FIRE TENDER TOE WALL WITH BH-01 | Cum | 1 |  | 31.4 | 0.23 | 0.2 | 1.44
| FIRE TENDER TOE WALL WITH BH-07 | Cum | 1 |  | 42.55 | 0.23 | 0.2 | 1.96
| TOE WALL BH-04 FOR GREEN | Cum | 2 |  | 31.44 | 0.23 | 0.2 | 2.89
| BH-04 RCC PLANTER | Cum | 6 |  | 4.8 | 1.15 | 0.3 | 9.94
|  | Cum | 2 |  | 4.8 | 1.3 | 0.3 | 3.74
| BH-03 RCC PLANTER | Cum | 6 |  | 4.8 | 1.15 | 0.3 | 9.94
|  | Cum | 2 |  | 4.8 | 1.3 | 0.3 | 3.74
R.C.C. P/L M25 for Tie Beam on Brick Work
R.C.C. P/L for Planter (2-6/28'-31')
| (28'/2-3) (tie Beam=230x200) | Cum | 1 | 1 | 3.89 | 0.23 | 0.2 | 0.18
|  | Cum | 1 | 1 | 1.66 | 0.23 | 0.2 | 0.08
| (29'/2-3) | Cum | 1 | 1 | 2.23 | 0.23 | 0.2 | 0.1
|  | Cum | 1 | 1 | 1.66 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 1.96 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.2 | 0.04
| (30'/2-3) | Cum | 1 | 2 | 1.96 | 0.23 | 0.2 | 0.18
| (31'/2-3) | Cum | 1 | 1 | 1.43 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 2.56 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 5.99 | 0.23 | 0.2 | 0.28
| (2-4/28'-31') | Cum | 1 | 1 | 0.61 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 2.51 | 0.23 | 0.2 | 0.12
| (29'/2-4) | Cum | 1 | 2 | 0.615 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 0 | 1 | 1.915 | 0.23 | 0.2
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 2.5 | 0.23 | 0.2 | 0.12
| (31'/2-4) | Cum | 1 | 2 | 0.615 | 0.23 | 0.2 | 0.06
R.C.C. P/L for Planter (2-6/31'-37')
| (32'/2-5) | Cum | 1 | 1 | 6.89 | 0.23 | 0.2 | 0.32
|  | Cum | 1 | 1 | 4.66 | 0.23 | 0.2 | 0.21
| R.C.C. P/L for Beam Sheat (385x275) | Cum | 1 | 1 | 3.3 | 0.385 | 0.275 | 0.35
| (33'/2-5) | Cum | 1 | 1 | 4.66 | 0.23 | 0.2 | 0.21
|  | Cum | 1 | 1 | 1.79 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 5.62 | 0.23 | 0.2 | 0.26
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.2 | 0.04
|  | Cum | 1 | 1 | 6.52 | 0.23 | 0.2 | 0.3
| R.C.C. P/L for Sheat | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 6.52 | 0.23 | 0.2 | 0.3
| R.C.C. P/L for Sheat | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
| (35'/2-5) | Cum | 1 | 1 | 7.12 | 0.23 | 0.2 | 0.33
|  | Cum | 1 | 1 | 2.03 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 2 | 8.92 | 0.23 | 0.2 | 0.82
| (37'/2-5) | Cum | 1 | 1 | 11.15 | 0.23 | 0.2 | 0.51
| R.C.C. P/L for Sheat | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
| (2-5/32'-37') | Cum | 1 | 1 | 0.615 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 2 | 0.615 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 1.055 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 0.615 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 3.36 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 0.615 | 0.23 | 0.2 | 0.03
R.C.C. P/L for Planter (17-21/20-25)
| (20'/17-21) | Cum | 1 | 1 | 9.26 | 0.23 | 0.2 | 0.43
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 1 | 3.03 | 0.23 | 0.2 | 0.14
| (21'/17-21) | Cum | 1 | 1 | 2.03 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 6.43 | 0.23 | 0.2 | 0.3
| R.C.C. P/L for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 8.23 | 0.23 | 0.2 | 0.38
| R.C.C. P/L for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 1.23 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 6.23 | 0.23 | 0.2 | 0.29
|  | Cum | 1 | 1 | 3.03 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.2 | 0.2
| R.C.C. P/L Work for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 2.03 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 2.93 | 0.23 | 0.2 | 0.13
|  | Cum | 1 | 1 | 4.73 | 0.23 | 0.2 | 0.22
| R.C.C. P/L Work for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 1.2 | 0.23 | 0.2 | 0.06
| (24'/17-21) | Cum | 1 | 1 | 7.96 | 0.23 | 0.2 | 0.37
| (17/20'-24') | Cum | 1 | 8 | 0.615 | 0.23 | 0.2 | 0.23
|  | Cum | 1 | 2 | 1.975 | 0.23 | 0.2 | 0.18
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 2 | 1.67 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
R.C.C. P/L for Planter (17-21/25'-29')
| (20'/17-21) | Cum | 1 | 1 | 8.46 | 0.23 | 0.2 | 0.39
|  | Cum | 1 | 1 | 6.43 | 0.23 | 0.2 | 0.3
|  | Cum | 1 | 1 | 4.63 | 0.23 | 0.2 | 0.21
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 3.43 | 0.23 | 0.2 | 0.16
| R.C.C. P/L Work for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 3.23 | 0.23 | 0.2 | 0.15
| R.C.C. P/L for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 1 | 3.23 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 4.43 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 6.23 | 0.23 | 0.2 | 0.29
|  | Cum | 1 | 1 | 8.23 | 0.23 | 0.2 | 0.38
|  | Cum | 1 | 1 | 10.26 | 0.23 | 0.2 | 0.47
| (17-21/25'-29') | Cum | 1 | 6 | 0.615 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 2 | 1.67 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
R.C.C. P/L for Planter (17-21/29'-35')
| (29'/17-21) | Cum | 1 | 1 | 7.24 | 0.23 | 0.2 | 0.33
|  | Cum | 1 | 1 | 5.23 | 0.23 | 0.2 | 0.24
|  | Cum | 1 | 1 | 4.23 | 0.23 | 0.2 | 0.19
| R.C.C. P/L for Sheet | Cum | 1 | 1 | 3 | 0.385 | 0.275 | 0.32
|  | Cum | 1 | 1 | 1.23 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 6 | 3.23 | 0.23 | 0.2 | 0.89
|  | Cum | 1 | 1 | 5.23 | 0.23 | 0.2 | 0.24
| R.C.C. P/L for Sheet | Cum | 1 | 3 | 3 | 0.385 | 0.275 | 0.95
|  | Cum | 1 | 1 | 4.23 | 0.23 | 0.2 | 0.19
| (35'/17-20) | Cum | 1 | 1 | 5.26 | 0.23 | 0.2 | 0.24
| (17-20/29'-35') | Cum | 1 | 3 | 3.36 | 0.23 | 0.2 | 0.46
|  | Cum | 1 | 3 | 1.67 | 0.23 | 0.2 | 0.23
|  | Cum | 1 | 1 | 1.67 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 2 | 1.67 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 5 | 0.615 | 0.23 | 0.2 | 0.14
| R.C.C. P/L for Sheet | Cum | 1 | 4 | 3 | 0.385 | 0.275 | 1.27
R.C.C. P/L for Planter (20-28/2'-5')
| R.C.C. P/L (2'/20-28) | Cum | 1 | 1 | 3.06 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 3 | 0.867 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 1 | 3.66 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 1 | 2.83 | 0.23 | 0.2 | 0.13
|  | Cum | 1 | 4 | 0.535 | 0.23 | 0.2 | 0.1
R.C.C. P/L (3'/20-28)
| R.C.C. P/L (6'/20-21) | Cum | 1 | 1 | 3.665 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 2 | 0.735 | 0.23 | 0.2 | 0.07
| R.C.C. P/L (4'/22-23) | Cum | 1 | 3 | 2.83 | 0.23 | 0.2 | 0.39
|  | Cum | 1 | 2 | 0.535 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 1 | 2.23 | 0.23 | 0.2 | 0.1
R.C.C. P/L (20/2'-5')
| R.C.C. P/L (20/2'-5') | Cum | 1 | 1 | 9.155 | 0.23 | 0.2 | 0.42
|  | Cum | 1 | 2 | 6.785 | 0.23 | 0.2 | 0.62
| P.C.C. for Sheet | Cum | 1 | 4 | 3 | 0.385 | 0.275 | 1.27
|  | Cum | 1 | 1 | 5.26 | 0.23 | 0.2 | 0.24
|  | Cum | 1 | 1 | 1.16 | 0.23 | 0.2 | 0.05
| (23/2'-5') | Cum | 1 | 1 | 1.45 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 0.6 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 3.745 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 2 | 3.735 | 0.23 | 0.2 | 0.34
|  | Cum | 1 | 1 | 3.43 | 0.23 | 0.2 | 0.16
|  | Cum | 1 | 2 | 0.685 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 1.295 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 2.11 | 0.23 | 0.2 | 0.1
R.C.C. P/L Side of BH-01 (15/23'-35')
| east face (15/23'-35') | Cum | 1 | 2 | 29.71 | 0.23 | 0.2 | 2.73
|  | Cum | 1 | 2 | 0.6 | 0.23 | 0.2 | 0.06
| north face (23'/9-10) | Cum | 1 | 2 | 5.485 | 0.23 | 0.2 | 0.5
|  | Cum | 1 | 2 | 1.195 | 0.23 | 0.2 | 0.11
| north face (23'/11-13) | Cum | 1 | 2 | 6.31 | 0.23 | 0.2 | 0.58
|  | Cum | 1 | 2 | 1.195 | 0.23 | 0.2 | 0.11
R.C.C. P/L for Planter (20-28/2'-5')
| R.C.C. P/L (42'/13-16) | Cum | 1 | 1 | 4.66 | 0.23 | 0.2 | 0.21
|  | Cum | 1 | 1 | 2.43 | 0.23 | 0.2 | 0.11
|  | Cum | 1 | 1 | 3.63 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 1 | 0.89 | 0.23 | 0.2 | 0.04
|  | Cum | 1 | 2 | 4.29 | 0.23 | 0.2 | 0.39
|  | Cum | 1 | 1 | 0.61 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 3.91 | 0.23 | 0.2 | 0.18
| (45'/14-17) | Cum | 1 | 1 | 1.51 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 3.31 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 3.31 | 0.23 | 0.2 | 0.15
| (46'/14-17) | Cum | 1 | 1 | 5.79 | 0.23 | 0.2 | 0.27
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.2 | 0.04
|  | Cum | 1 | 2 | 6.39 | 0.23 | 0.2 | 0.59
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 9.82 | 0.23 | 0.2 | 0.45
| R.C.C. P/L for Sheet | Cum | 1 | 5 | 3 | 0.385 | 0.275 | 1.59
(15/42'-47')
|  | Cum | 1 | 7 | 0.615 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 1 | 1.905 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 1.06 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 5 | 1.67 | 0.23 | 0.2 | 0.38
|  | Cum | 1 | 1 | 3.36 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 2 | 2.035 | 0.23 | 0.2 | 0.19
R.C.C. P/L for Planter (20-28/2'-5')
| R.C.C. P/L (48'/13-16) | Cum | 1 | 1 | 10.62 | 0.23 | 0.2 | 0.49
|  | Cum | 1 | 1 | 8.39 | 0.23 | 0.2 | 0.39
| (49'/13-16) | Cum | 1 | 2 | 6.39 | 0.23 | 0.2 | 0.59
| (50'/14-18) | Cum | 1 | 2 | 8.79 | 0.23 | 0.2 | 0.81
|  | Cum | 1 | 1 | 7.89 | 0.23 | 0.2 | 0.36
| (52'/14-18) | Cum | 1 | 1 | 10.12 | 0.23 | 0.2 | 0.47
| R.C.C. P/L for Sheet | Cum | 1 | 3 | 3 | 0.385 | 0.275 | 0.95
| (15/48'-53') | Cum | 1 | 2 | 0.615 | 0.23 | 0.2 | 0.06
| (17/48'-49') | Cum | 1 | 3 | 1.64 | 0.23 | 0.2 | 0.23
|  | Cum | 1 | 3 | 3.36 | 0.23 | 0.2 | 0.46
R.C.C. P/L outer side of BH-04 (Drg. No. TU/LA-P-206.3)
| R.C.C. P/L Work west side (20/37'-50') | Cum | 1 | 1 | 33.16 | 0.23 | 0.2 | 1.53
|  | Cum | 1 | 1 | 30.13 | 0.23 | 0.2 | 1.39
| R.C.C. P/L south side (49'/19-23) (longitudinal axies) | Cum | 1 | 1 | 1.145 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 1 | 0.695 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 2.22 | 0.23 | 0.2 | 0.1
|  | Cum | 1 | 1 | 0.72 | 0.23 | 0.2 | 0.03
|  | Cum | 1 | 1 | 3.18 | 0.23 | 0.2 | 0.15
| R.C.C. P/L south side (49'/19-23) (transverse axies) | Cum | 1 | 1 | 1.77 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 2 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 0.54 | 0.23 | 0.2 | 0.02
|  | Cum | 1 | 1 | 1 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 1 | 1.74 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 5.94 | 0.23 | 0.2 | 0.27
| R.C.C. P/L north side (36'/19-21) (longitudianal axies) | Cum | 1 | 1 | 2.26 | 0.23 | 0.2 | 0.1
| R.C.C. P/L north side (36'/19-21) (transverse axies) | Cum | 1 | 1 | 4.495 | 0.23 | 0.2 | 0.21
| (transverse axies) | Cum | 1 | 1 | 2.965 | 0.23 | 0.2 | 0.14
R.C.C. P/L outer side of BH-04 (Drg. No. TU/LA-P-206.4)
| R.C.C. P/L east side (32/37'-49') | Cum | 1 | 2 | 32.28 | 0.23 | 0.2 | 2.97
|  | Cum | 1 | 2 | 1.36 | 0.23 | 0.2 | 0.13
R.C.C. P/L for Planter (39'-55'/32-36) (Drg. No. TU/LA-P-206.4)
R.C.C. P/L for Planter (39'-47'/32-36)
| longitudianal axies (40'/34-35) | Cum | 1 | 2 | 3.94 | 0.23 | 0.2 | 0.36
|  | Cum | 1 | 1 | 1.71 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 4 | 2.61 | 0.23 | 0.2 | 0.48
|  | Cum | 1 | 2 | 4.71 | 0.23 | 0.2 | 0.43
|  | Cum | 1 | 2 | 4.41 | 0.23 | 0.2 | 0.41
|  | Cum | 1 | 2 | 5.31 | 0.23 | 0.2 | 0.49
|  | Cum | 1 | 2 | 6.21 | 0.23 | 0.2 | 0.57
|  | Cum | 1 | 1 | 7.41 | 0.23 | 0.2 | 0.34
|  | Cum | 1 | 1 | 1.73 | 0.23 | 0.2 | 0.08
| (47'/32-36) | Cum | 1 | 1 | 10.62 | 0.23 | 0.2 | 0.49
| R.C.C. P/L for Sheet | Cum | 1 | 4 | 3 | 0.385 | 0.275 | 1.27
| Transvere axies (34/40'-47') | Cum | 1 | 3 | 0.615 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 6 | 3.36 | 0.23 | 0.2 | 0.93
|  | Cum | 1 | 7 | 1.67 | 0.23 | 0.2 | 0.54
|  | Cum | 1 | 1 | 2.515 | 0.23 | 0.2 | 0.12
R.C.C. P/L for Planter (30-39/37-40) near M4 (revised Drg. No. TU/LA-P-206.5 (front of Basket Ball)
| R.C.C. P/L (west side wall) | Cum | 1 | 1 | 18.99 | 0.23 | 0.2 | 0.87
| extra for Sheet | Cum | 1 | 3 | 3 | 0.385 | 0.275 | 0.95
| north & south side wall | Cum | 2 | 1 | 2 | 0.23 | 0.2 | 0.18
|  | Cum | 1 | 3 | 2.435 | 0.23 | 0.2 | 0.34
|  | Cum | 1 | 1 | 2.44 | 0.23 | 0.2 | 0.11
|  | Cum | 1 | 1 | 2.13 | 0.23 | 0.2 | 0.1
|  | Cum | 1 | 1 | 1.71 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 2 | 5.345 | 0.23 | 0.2 | 0.49
|  | Cum | 1 | 2 | 6.38 | 0.23 | 0.2 | 0.59
|  | Cum | 1 | 2 | 6.95 | 0.23 | 0.2 | 0.64
|  | Cum | 1 | 2 | 6.12 | 0.23 | 0.2 | 0.56
|  | Cum | 1 | 2 | 4.645 | 0.23 | 0.2 | 0.43
|  | Cum | 1 | 2 | 3 | 0.23 | 0.2 | 0.28
|  | Cum | 1 | 4 | 0.615 | 0.23 | 0.2 | 0.11
|  | Cum | 1 | 2 | 0.61 | 0.23 | 0.2 | 0.06
R.C.C. P/L for Planter near BH-03 (drg. No. TU/LA-P-206.1) (48-52/2'-11')
R.C.C. P/L for Stepped Foundation (west side wall) (2'/48-52)
| Longitudianal axies (2'/48-52) | Cum | 1 | 1 | 7.86 | 0.23 | 0.2 | 0.36
|  | Cum | 1 | 1 | 5.63 | 0.23 | 0.2 | 0.26
|  | Cum | 1 | 2 | 6.23 | 0.23 | 0.2 | 0.57
|  | Cum | 1 | 3 | 5.03 | 0.23 | 0.2 | 0.69
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 5.63 | 0.23 | 0.2 | 0.26
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.2 | 0.04
|  | Cum | 1 | 5 | 4.43 | 0.23 | 0.2 | 1.02
|  | Cum | 1 | 1 | 0.83 | 0.23 | 0.2 | 0.04
|  | Cum | 1 | 1 | 5.03 | 0.23 | 0.2 | 0.23
|  | Cum | 1 | 1 | 1.43 | 0.23 | 0.2 | 0.07
| (10'/49-50) | Cum | 1 | 2 | 6.23 | 0.23 | 0.2 | 0.57
|  | Cum | 1 | 1 | 8.46 | 0.23 | 0.2 | 0.39
| extra for Sheet | Cum | 1 | 8 | 3.3 | 0.22 | 0.15 | 0.87
Transverse axies (49/2'-11')
|  | Cum | 1 | 6 | 0.615 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 4 | 1.67 | 0.23 | 0.2 | 0.31
|  | Cum | 1 | 2 | 3.36 | 0.23 | 0.2 | 0.31
|  | Cum | 1 | 3 | 1.365 | 0.23 | 0.2 | 0.19
|  | Cum | 1 | 2 | 2.21 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 2 | 2.515 | 0.23 | 0.2 | 0.23
|  | Cum | 1 | 1 | 3.055 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 1 | 3.165 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 1.475 | 0.23 | 0.2 | 0.07
R.C.C. P/L for BH-05 outer side (drg. No. TU/LA-P-206.8)
| R.C.C. P/L for FIRE TENDER TOES Wall (north side wall) | Cum | 1 | 1 | 34.935 | 0.23 | 0.2 | 1.61
| R.C.C. P/L for FIRE TENDER TOES Wall (west side wall) | Cum | 1 | 1 | 15 | 0.23 | 0.2 | 0.69
R.C.C. P/L for Basket Ball Ground Toe Wall
| Basket Ball Long Ball | Cum | 1 | 2 | 28 | 0.23 | 0.2 | 2.58
| BASKET WALL SHORT WALL | Cum | 1 | 2 | 14.74 | 0.23 | 0.2 | 1.36
| SEAT | Cum | 1 | 2 | 3.3 | 0.23 | 0.2 | 0.3
R.C.C. P/L for Basket Ball Ground Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 | Cum | 1 | 1 | 31.4 | 0.23 | 0.2 | 1.44
| FIRE TENDER TOE WALL WITH BH-07 | Cum | 1 | 1 | 42.55 | 0.23 | 0.2 | 1.96
R.C.C. P/L for Road Toe Wall BH-01
| R.C.C. P/L for Road Toe Wall BH-01 east side towards water body | Cum | 1 | 2 | 29.78 | 0.23 | 0.2 | 2.74
|  | Cum | 1 | 2 | 0.67 | 0.23 | 0.2 | 0.06
R.C.C. P/L for Road Toe Wall BH-01 North side towards GYM
|  | Cum | 1 | 2 | 5.555 | 0.23 | 0.2 | 0.51
|  | Cum | 1 | 2 | 1.265 | 0.23 | 0.2 | 0.12
|  | Cum | 1 | 2 | 6.38 | 0.23 | 0.2 | 0.59
|  | Cum | 1 | 2 | 1.265 | 0.23 | 0.2 | 0.12
R.C.C. P/L for Road Toe Wall back side of Basket Ball (east side)
|  | Cum | 1 | 4 | 7.625 | 0.23 | 0.2 | 1.4
R.C.C. P/L for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | 1 | 8 | 7.625 | 0.23 | 0.2 | 2.81
|  | Cum | 1 | 1 | 9.95 | 0.23 | 0.2 | 0.46
R.C.C. P/L for Planter between BH-04 & Base of Waterbody M3
| Base Footning (4500x1000) | Cum | 1 | 6 | 4.8 | 1.15 | 0.3 | 9.94
| Base Footning (4500x1000) | Cum | 1 | 2 | 4.8 | 1.3 | 0.3 | 3.74
| R.C.C. Wall for Planter | Cum | 8 | 2 | 4.5 | 0.2 | 1.025 | 14.76
|  | Cum | 8 | 2 | 0.6 | 0.2 | 0.8 | 1.54
| Less Previous Ra Quantity | Cum | -1 | 1 | 93.98 |  |  | -93.98
R.C.C. P/L for Planter near Reception or west side of Waterbody (drg. No. TU/LA-P-206.1) (30'-35'/32-36)
R.C.C. P/L for Planter Tie Beam (230x200)
Longitudianal axies (30'/32-36)
|  | Cum | 1 | 1 | 11.21 | 0.23 | 0.2 | 0.52
|  | Cum | 1 | 1 | 1.63 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 7.585 | 0.23 | 0.2 | 0.35
| Longitudianal axies (31'/32-35) | Cum | 1 | 1 | 7.585 | 0.23 | 0.2 | 0.35
|  | Cum | 1 | 1 | 1.63 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 6.185 | 0.23 | 0.2 | 0.28
| Longitudianal axies (32'/32-35) | Cum | 1 | 1 | 6.185 | 0.23 | 0.2 | 0.28
|  | Cum | 1 | 1 | 1.76 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 4.655 | 0.23 | 0.2 | 0.21
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 4.655 | 0.23 | 0.2 | 0.21
|  | Cum | 1 | 1 | 1.76 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 3.12 | 0.23 | 0.2 | 0.14
| Longitudianal axies (34'/32-35) | Cum | 1 | 1 | 3.12 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 1 | 5.12 | 0.23 | 0.2 | 0.24
| Transvere axies (34/30'-35') | Cum | 1 | 6 | 0.615 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 3 | 2.515 | 0.23 | 0.2 | 0.35
|  | Cum | 1 | 1 | 2.21 | 0.23 | 0.2 | 0.1
|  | Cum | 1 | 3 | 1.67 | 0.23 | 0.2 | 0.23
|  | Cum | 1 | 1 | 1.365 | 0.23 | 0.2 | 0.06
R.C.C. P/L for Planter South sid of BH-02 (drg. No. TU/LA-P-206.1 & 206.2) ( (15'-19'/20-32)
R.C.C. P/L for Planter
| Longitudianal axies (15'/20-32) | Cum | 1 | 1 | 29.85 | 0.23 | 0.2 | 1.37
|  | Cum | 1 | 1 | 1.84 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 7 | 1.54 | 0.23 | 0.2 | 0.5
|  | Cum | 1 | 1 | 1.79 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 1.29 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 12 | 0.6 | 0.23 | 0.2 | 0.33
| Transvere axies (32/15'-19') | Cum | 1 | 1 | 10.775 | 0.23 | 0.2 | 0.5
| (32/15'-19') | Cum | 1 | 1 | 9.315 | 0.23 | 0.2 | 0.43
| (31/15'-19') | Cum | 1 | 2 | 7.785 | 0.23 | 0.2 | 0.72
| (30/15'-18') | Cum | 1 | 2 | 6.265 | 0.23 | 0.2 | 0.58
| (29/15'-17') | Cum | 0 | 2 | 6.495 | 0.23 | 0.2
|  | Cum | 1 | 2 | 4.74 | 0.23 | 0.2 | 0.44
|  | Cum | 1 | 2 | 3.52 | 0.23 | 0.2 | 0.32
|  | Cum | 6 | 2 | 3.215 | 0.23 | 0.2 | 1.77
|  | Cum | 1 | 1 | 3.215 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 4.675 | 0.23 | 0.2 | 0.22
| R.C.C. Beam for Sheat | Cum | 1 | 11 | 3 | 0.385 | 0.275 | 3.49
R.C.C. P/L for Planter South side of BH-02 & BH-03 (drg. No. TU/LA-P-206.1) ( (19'-21'/35-40)
R.C.C. P/L for Planter
| Longitudianal axies (40/19'-20') | Cum | 1 | 2 | 3.82 | 0.23 | 0.2 | 0.35
|  | Cum | 1 | 2 | 5.955 | 0.23 | 0.2 | 0.55
|  | Cum | 1 | 2 | 6.87 | 0.23 | 0.2 | 0.63
|  | Cum | 1 | 2 | 6.26 | 0.23 | 0.2 | 0.58
|  | Cum | 1 | 5 | 0.6 | 0.23 | 0.2 | 0.14
R.C.C. P/L for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J)
| R.C.C. P/L for Road Toe Wall (1/F-J) |  | 1 | 1 | 4.635 | 0.23 | 0.2 | 0.21
|  |  | 1 | 10 | 7.625 | 0.23 | 0.2 | 3.51
|  |  | 1 | 1 | 15.765 | 0.23 | 0.2 | 0.73
| R.C.C. P/L for Road Toe Wall (J/1-9) |  | 1 | 1 | 14.44 | 0.23 | 0.2 | 0.66
|  |  | 1 | 5 | 7.625 | 0.23 | 0.2 | 1.75
|  |  | 1 | 1 | 0.265 | 0.23 | 0.2 | 0.01
| R.C.C. P/L for Road Toe Wall (9/H-J) |  | 1 | 1 | 7.91 | 0.23 | 0.2 | 0.36
|  |  | 1 | 2 | 7.625 | 0.23 | 0.2 | 0.7
R.C.C. P/L for Planter between BH-03 & Basket Ball Ground
| Base Footning (4500x1000) | Cum | 1 | 6 | 4.8 | 1.15 | 0.3 | 9.94
| Base Footning (4500x1000) | Cum | 1 | 2 | 4.8 | 1.3 | 0.3 | 3.74
| R.C.C. Wall for Planter | Cum | 8 | 2 | 4.5 | 0.2 | 1.025 | 14.76
|  | Cum | 8 | 2 | 0.6 | 0.2 | 0.8 | 1.54
R.C.C. P/L for Planter between BH-01 & Canteen
| Base Footning (4500x1000) | Cum | 1 | 6 | 4.8 | 1.15 | 0.3 | 9.94
| Base Footning (4500x1000) | Cum | 1 | 3 | 4.8 | 1.3 | 0.3 | 5.62
| R.C.C. Wall for Planter | Cum | 9 | 2 | 4.5 | 0.2 | 1.025 | 16.61
|  | Cum | 9 | 2 | 0.6 | 0.2 | 0.8 | 1.73
R.C.C. P/L for Planter between BH-02 & GYM
| Base Footning (4500x1000) | Cum | 1 | 6 | 4.8 | 1.15 | 0.3 | 9.94
| Base Footning (4500x1000) | Cum | 1 | 2 | 4.8 | 1.3 | 0.3 | 3.74
| R.C.C. Wall for Planter | Cum | 8 | 2 | 4.5 | 0.2 | 1.025 | 14.76
|  | Cum | 8 | 2 | 0.6 | 0.2 | 0.8 | 1.54
| R.C.C. P/L for Waterbody as per drg. No.(Inner dia. 20.12m), dia. For P.C.C. =20.12+0.2*2+0.6*2=21.720m) |  |  |  | area
| base raft dia. 21.72m | Cum | 1 | 1 | 370.3303 |  | 0.2 | 74.07
| deduction for hold area (dia. 18.32m) | Cum | -1 | 1 | 263.4636 |  | 0.2 | -52.69
| R.C.C. wall 200mm thk. | Cum | 1 | 1 | 64.4328 | 0.23 | 0.545 | 8.08
| R.C.C. wall top beam (390x150) | Cum | 1 | 1 | 64.4328 | 0.39 | 0.15 | 3.77
R.C.C. P/L in Basket Ball Ground
|  | Cum | 1 | 1 | 27.54 | 14.19 | 0.125 | 48.85
| 10% | Cum | -1 |  | 31.987 |  |  | -31.99
| R.C.C. P/L for Tie beam for Planter near Waterbody & Reception (22'-26'/32-36) Ref. Drg. No. TU/LA-P-206.1 | Cum
| R.C.C. Work for Planter Tie Beam (230x200) | Cum
| Longitudianal axies (32/22'-26') | Cum | 1 | 1 | 9.81 | 0.23 | 0.2 | 0.45
|  | Cum | 1 | 1 | 9.625 | 0.23 | 0.2 | 0.44
| (33/22'-26') | Cum | 1 | 2 | 8.37 | 0.23 | 0.2 | 0.77
| (34/22'-26') | Cum | 1 | 2 | 6.846 | 0.23 | 0.2 | 0.63
| (35/22'-26') | Cum | 1 | 2 | 5.015 | 0.23 | 0.2 | 0.46
| (36/22'-26') | Cum | 1 | 1 | 3.49 | 0.23 | 0.2 | 0.16
|  | Cum | 0 | 1 | 3.79 | 0.23 | 0.2
| Transverse Axies | Cum | 1 | 5 | 0.6 | 0.23 | 0.2 | 0.14
Cum
| R.C.C. P/L for Ramp for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205 (on top surface | Cum
|  | Cum | 1 | 1 | 6 | 2 | 0.1 | 1.2
|  | Cum | 1 | 1 | 2.925 | 3 | 0.1 | 0.88
Cum
| R.C.C. P/L for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 2 | 0.1 | 1.2
|  | Cum | 1 | 1 | 2.925 | 3 | 0.1 | 0.88
Cum
| R.C.C. P/L for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 2 | 0.1 | 1.2
|  | Cum | 1 | 1 | 2.925 | 3 | 0.1 | 0.88
Cum
| R.C.C. P/L for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 2 | 0.1 | 1.2
|  | Cum | 1 | 1 | 2.925 | 3 | 0.1 | 0.88
Cum
| R.C.C. P/L for Road Toe Wall (9/H-J) | Cum
|  | Cum | 1 | 1 | 7.625 | 0.23 | 0.2 | 0.35
|  | Cum | 1 | 1 | 1.1 | 0.23 | 0.2 | 0.05
| R.C.C. P/L for Road Toe Wall (9/F-H) basket ball ground & BH-03 | Cum
|  | Cum | 1 | 1 | 7.625 | 0.23 | 0.2 | 0.35
|  | Cum | 1 | 1 | 7.125 | 0.23 | 0.2 | 0.33
Cum
| R.C.C. P/L for Fire Tender Wall (parallel to road) (Tie Beam 230x200) | Cum
| Fire Tender Wall towards BH-07 (Tie Beam 230x200) | Cum | 1 | 1 | 24.945 | 0.23 | 0.2 | 1.15
|  | Cum | 1 | 1 | 13.605 | 0.23 | 0.2 | 0.63
|  | Cum | 1 | 1 | 4.343 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 1 | 4.748 | 0.23 | 0.2 | 0.22
|  | Cum | 1 | 1 | 0.374 | 0.23 | 0.2 | 0.02
| Brick work for green Planter wall BH-07 (west side) | Cum | 1 | 1 | 1.359 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 26.229 | 0.23 | 0.2 | 1.21
| Fire Tender Wall towards BH-01 | Cum | 1 | 1 | 10.508 | 0.23 | 0.2 | 0.48
|  | Cum | 1 | 1 | 1.639 | 0.23 | 0.2 | 0.08
|  | Cum | 1 | 1 | 2.059 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 2.938 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 1 | 7.795 | 0.23 | 0.2 | 0.36
|  | Cum | 1 | 1 | 2.063 | 0.23 | 0.2 | 0.09
|  | Cum | 1 | 1 | 1.079 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 1 | 3.273 | 0.23 | 0.2 | 0.15
|  | Cum | 1 | 1 | 5.084 | 0.23 | 0.2 | 0.23
| Fire Tender Wall Brick Work between BH-04 & BH-07 near green Planter (triangle type) | Cum | 1 | 1 | 1.398 | 0.23 | 0.2 | 0.06
|  | Cum | 1 | 1 | 6.182 | 0.23 | 0.2 | 0.28
|  | Cum | 1 | 1 | 0.23 | 0.23 | 0.2 | 0.01
|  | Cum | 1 | 1 | 8.695 | 0.23 | 0.2 | 0.4
|  | Cum | 1 | 1 | 16.409 | 0.23 | 0.2 | 0.75
| brick work for fire tender in green planter between BH-04 & BH-07 | Cum | 1 | 1 | 0.898 | 0.23 | 0.2 | 0.04
|  | Cum | 1 | 1 | 1.497 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 1.602 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 1.012 | 0.23 | 0.2 | 0.05
|  | Cum | 1 | 1 | 4.172 | 0.23 | 0.2 | 0.19
|  | Cum | 1 | 1 | 10.42 | 0.23 | 0.2 | 0.48
|  | Cum | 1 | 1 | 0.217 | 0.23 | 0.2 | 0.01
|  | Cum | 1 | 1 | 4.011 | 0.23 | 0.2 | 0.18
|  | Cum | 1 | 1 | 23.472 | 0.23 | 0.2 | 1.08
| Fire Tender Wall Brick Work connect to BH-04 to green Planter between BH-01 & waterbody | Cum | 1 | 1 | 15.694 | 0.23 | 0.2 | 0.72
|  | Cum | 1 | 1 | 0.225 | 0.23 | 0.2 | 0.01
| Brick Work for Fire Tender in Green planter between BH-01 & Waterbody | Cum | 1 | 1 | 1.497 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 1.6 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 3.43 | 0.23 | 0.2 | 0.16
|  | Cum | 1 | 1 | 1.497 | 0.23 | 0.2 | 0.07
|  | Cum | 1 | 1 | 3.735 | 0.23 | 0.2 | 0.17
|  | Cum | 1 | 1 | 4.345 | 0.23 | 0.2 | 0.2
| Fire Tender Wall Brick Work BH-01 west corner to Canteen parallel to road betwee canteen & BH-02 | Cum | 1 | 1 | 2.386 | 0.23 | 0.2 | 0.11
|  | Cum | 1 | 1 | 20.003 | 0.23 | 0.2 | 0.92
| parallel to canteen | Cum | 1 | 1 | 33.331 | 0.23 | 0.2 | 1.53
| parallel to BH-02 towards canteen (east face) | Cum | 1 | 1 | 31.771 | 0.23 | 0.2 | 1.46
|  | Cum | 1 | 1 | 4.373 | 0.23 | 0.2 | 0.2
|  | Cum | 1 | 1 | 0.17 | 0.23 | 0.2 | 0.01
| Fire Tender Wall Brick Work for Road between BH-02 & Waterbody | Cum
| wall towards BH-02 (BH-02 to Gym toilet) | Cum | 1 | 1 | 18.743 | 0.23 | 0.2 | 0.86
|  | Cum | 1 | 1 | 9.868 | 0.23 | 0.2 | 0.45
|  | Cum | 1 | 1 | 7.05 | 0.23 | 0.2 | 0.32
| fire tender wall towards waterbody planter to arround waterbody to Reception | Cum
|  | CUM | 1 | 1 | 36.696 | 0.23 | 0.2 | 1.69
|  | Cum | 0 | 1 | 0.337 | 0.23 | 0.2
|  | Cum | 0 | 1 | 3.183 | 0.23 | 0.2
|  | Cum | 0 | 1 | 33.632 | 0.23 | 0.2
| in planter | Cum | 1 | 1 | 8.053 | 0.23 | 0.2 | 0.37
| fire tender wall west side of reception | Cum | 1 | 1 | 14.555 | 0.23 | 0.2 | 0.67
| Fire Tender Wall Brick Work for Road South side of BH-04 (back side) | Cum
|  | Cum | 1 | 1 | 14.343 | 0.23 | 0.2 | 0.66
| Fire Tender Wall Brick Work for Road BH-04 (near watebody to basket ball ground planter) to BH-03 | Cum
|  | Cum | 1 | 1 | 60.78 | 0.23 | 0.2 | 2.8
| basket ball ground planter to BH-03 corner(front of Gym) | Cum | 1 | 1 | 35.253 | 0.23 | 0.2 | 1.62
| Deduct Previous Bill Qty. for Revise | Cum
| Brick Work for Fire Tender Toe Wall | Cum
Cum
| FIRE TENDER TOE WALL WITH BH-01 (South side) | Cum | -1 | 1 | 31.4 | 0.23 | 0.2 | -1.44
| FIRE TENDER TOE WALL WITH BH-07 | Cum | -1 | 1 | 42.55 | 0.23 | 0.2 | -1.96
Cum
| R.C.C. P/L for Waterbody Raft (Hold Portion) | Cum
| R.C.C. P/L for Waterbody as per drg. No.(Inner dia. 20.12m), dia. For P.C.C. =20.12+0.2*2+0.6*2=21.720m) | Cum |  |  | area
| base raft dia. 21.72m | Cum | 0 | 1 | 346.361 |  | 0.2
| release hold area (dia. 18.32m) | Cum | 1 | 1 | 263.4636 |  | 0.2 | 52.69
| R.C.C. for Sump in Waterbody | Cum
| Sump inner size(900x900x850) | Cum | 5 | 2 | 0.9 | 0.2 | 0.85 | 1.53
|  | Cum | 5 | 2 | 1.3 | 0.2 | 0.85 | 2.21
| Filter Pit (2000x2000x1800) | Cum
| Base footing | Cum | 1 | 1 | 2.4 | 2.4 | 0.1 | 0.58
| Wall | Cum | 1 | 2 | 2 | 0.2 | 1.8 | 1.44
|  | Cum | 1 | 2 | 2.4 | 0.2 | 1.8 | 1.73
Cum
| add previous 3rd R.A. Hold Qty. | Cum | 1 | 1 | 31.987 |  |  | 31.99
R.C.C. Tie Beam (230x200) for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22) (230x200)
| longitudianal axies | Cum | 1 | 2 | 6.31 | 0.23 | 0.2 | 0.58
| Transverse axies | Cum | 1 | 2 | 1.8 | 0.23 | 0.2 | 0.17
| longitudianal axies | Cum | 1 | 2 | 4.985 | 0.23 | 0.2 | 0.46
| Transverse axies | Cum | 1 | 2 | 1.8 | 0.23 | 0.2 | 0.17
R.C.C. Tie Beam (230x200) for Green Planter South side of BH-03 towards Basket Ball Ground (Drg. No. TU/LA-P-206.1) (26'-27'/46-51)
| longitudianal axies | Cum | 1 | 2 | 6.31 | 0.23 | 0.2 | 0.58
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.23 | 0.2 | 0.11
| longitudianal axies | Cum | 1 | 2 | 4.985 | 0.23 | 0.2 | 0.46
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.23 | 0.2 | 0.11
R.C.C. Tie Beam (230x200) for Green Planter West side of BH-02 under transfer slab (Drg. No. TU/LA-P-206.1) (7'-14'/32-33)
| longitudianal axies | Cum | 1 | 2 | 6.31 | 0.23 | 0.2 | 0.58
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.23 | 0.2 | 0.11
| longitudianal axies | Cum | 1 | 2 | 4.985 | 0.23 | 0.2 | 0.46
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.23 | 0.2 | 0.11
| longitudianal axies | Cum | 1 | 2 | 3.085 | 0.23 | 0.2 | 0.28
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.23 | 0.2 | 0.11
| longitudianal axies | Cum | 1 | 2 | 2.86 | 0.23 | 0.2 | 0.26
| Transverse axies | Cum | 1 | 2 | 1.2 | 0.23 | 0.2 | 0.11
R.C.C. P/ at Podium Lvl. For Chess Table (GYM Podium)
| Chess Tabel (1500x1500) | Cum | 5 | 2 | 1.44 | 1.44 | 0.1 | 2.07
| R.C.C. band under seat | Cum | 10 | 2 | 0.84 | 0.23 | 0.23 | 0.89
|  | Cum | 10 | 2 | 0.38 | 0.23 | 0.23 | 0.4
R.C.C. Beam (385x275) for Seprate Seat
R.C.C. Beam (385x275) for seprate seat under transfer slab of BH-03 towards Basket Ball Ground
| TOS lvl. +0.5m | CUM | 1 | 4 | 2.835 | 0.385 | 0.275 | 1.2
R.C.C. Beam (385x275) for seprate seat near Basket Ball Ground
| TOS lvl. +0.5m | CUM | 1 | 2 | 2.835 | 0.385 | 0.275 | 0.6
R.C.C. Beam (385x275) for seprate seat under transfer slab of BH-02 towards Gym
| TOS lvl. +0.5m | CUM | 1 | 6 | 2.835 | 0.385 | 0.275 | 1.8
R.C.C. Beam (385x275) for seprate seat under transfer slab of BH-04 towards Waterbody
| TOS lvl. +0.5m | CUM | 1 | 7 | 2.835 | 0.385 | 0.275 | 2.1
R.C.C. Beam (385x275) for seprate seat under transfer slab of BH-01 towards Canteen
| TOS lvl. +0.5m | CUM | 1 | 6 | 2.835 | 0.385 | 0.275 | 1.8
R.C.C. Beam (385x275) for seprate seat at waterbody
| TOS lvl. +0.5m | CUM | 1 | 8 | 2.835 | 0.385 | 0.275 | 2.4
R.C.C. P/L at Waterbody on round Piller
| Piller dia. (d=0.6), R.C.C. thk. 200 on peripheri | CUM | 1 | 2 | 2.512 | 0.2 | 0.75 | 0.75
| UP TO PREVIOUS BILL | Cum | [6 empty] | 431.74
| R.C.C. P/L for Light Pole Foundation near Basket Ball Ground (900x900) | Cum | 2 | 1 | 0.9 | 0.9 | 0.25 | 0.41
| Pedestal (250x250) | Cum | 2 | 1 | 0.25 | 0.25 | 1.2 | 0.15 |  |  |  | 8
| R.C.C. P/L for Basket Ball Ground Pole Foundation (1500x1500) | Cum | 2 | 1 | 1.5 | 1.5 | 0.35 | 1.58
| Pedestal (500x500) | Cum | 2 | 1 | 0.5 | 0.5 | 1.975 | 0.99
| THIS BILL TOTAL → | Cum | [6 empty] | 3.13 | 6th RA
434.87
WATERPROOFING
5 | Providing & Laying gunited sprayed concrete (40mm thk, minimum) in Waterbody areas. Consisting of mix 1:4 (1 cement : 4 coarse sand) over Chicken Wire Mesh of approved weight per sq.m. using appropriate: a) Cleaning the surface where gunited concrete is to be applied. b) Applying sprayed concrete. d) Finishing the surface with trowel to achieve smooth finish.
a | Gunited Sprayed waterproofing for Waterbody
| for Waterbody as per drg. No.(Inner dia. 20.12m), dia. |  |  |  | area
| base raft dia. 20.12m | Sqm | 1 | 1 | 317.7793 |  |  | 317.78 |  | Area
for Sump in Waterbody
| Sump inner size(900x900x850) | Sqm | 5 | 2 | 0.9 |  | 0.85 | 7.65
|  | Sqm | 5 | 2 | 1.3 |  | 0.85 | 11.05
| for Vertical Wall (dia.=20.12m) | Sqm | 1 | 1 | 63.1768 |  | 0.8 | 50.54
| top of wall (dia.=20.12+0.2=20.32m) | Sqm | 1 | 1 | 63.8048 |  | 0.2 | 12.76
| Filter Pit (2000x2000x1800) | Sqm | 1 | 1 | 2.4 | 2.4 |  | 5.76
|  | Sqm | 1 | 4 | 2.4 |  | 1.8 | 17.28
Gunited Spray on Round Piller in Waterbody
| Piller Dia. (0.6m), Guniting on piller (=0.6+0.+0.2=1.0m) | Sqm | 1 | 2 | 3.14 |  | 0.75 | 4.71
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 427.53
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
427.53
WBM LAYER IN FIRE TENDER AND DRIVEWAYS
6 | Supplying and laying sub base course ( water bound macadam) 100 m thick (consolidated thickness) with stone aggregate of size 93 to 45 mm including stone screening,sorting and consolidation with 8 to 10 tonne power road roller etc. and binding material complete all as specified by structural consultant.
Stone Agg. 90 to 45mm in Basket Ball Ground
|  | Cum | 1 | 1 | 27.54 | 14.74 | 0.15 | 60.89
Stone Agg. 90 to 45mm in Road
| Road between BH-05 & B3 Basket Ground | Cum | 1 | 1 | 29.2 | 6 | 0.125 | 21.9
|  | Cum | 1 | 1 | 8.32 | 6.78 | 0.125 | 7.05
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 23.235 | 6 | 0.125 | 17.43
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 2.275 | 6 | 0.125 | 1.71
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 32.39 | 6 | 0.125 | 24.29
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 5.295 | 6 | 0.125 | 3.97
| Road between BH-01 & Waterboy (east side) | Cum | 1 | 1 | 31.463 | 6 | 0.125 | 23.6
| Road between BH-01 & BH-07 (south side) | Cum | 1 | 1 | 33.193 | 6 | 0.125 | 24.89
|  | Cum | 1 | 1 | 29.854 | 6 | 0.125 | 22.39
|  | Cum | 1 | 1 | 33.667 | 6 | 0.125 | 25.25
|  | Cum | 1 | 1 | 12.3 | 6 | 0.125 | 9.23
Stone Agg. 90 to 45mm in Planter Area
| Planter Front of Basket Ground (west side) | Cum | 1 | 1 | 6.38 | 1.975 | 0.15 | 1.89
|  | Cum | 1 | 2 | 6.95 | 1.975 | 0.15 | 4.12
|  | Cum | 1 | 1 | 6.12 | 1.67 | 0.15 | 1.53
|  | Cum | 1 | 1 | 4.645 | 1.975 | 0.15 | 1.38
|  | Cum | 1 | 1 | 6.885 | 1.27 | 0.15 | 1.31
|  | Cum | 1 | 1 | 2.385 | 2.26 | 0.15 | 0.81
| space between basket ground & planter | Cum | 1 | 1 | 20.17 | 2.125 | 0.15 | 6.43
| planter front of Bh-05 (west side) | Cum | 1 | 1 | 12.58 | 1.19 | 0.15 | 2.25
|  | Cum | 1 | 1 | 7.09 | 0.9 | 0.15 | 0.96
|  | Cum | 1 | 1 | 1.6 | 5.98 | 0.15 | 1.44
|  | Cum | 1 | 1 | 1.6 | 4.18 | 0.15 | 1
|  | Cum | 1 | 2 | 1.6 | 2.38 | 0.15 | 1.14
|  | Cum | 1 | 1 | 1.145 | 0.9 | 0.15 | 0.15
|  | Cum | 1 | 1 | 2.745 | 1.5 | 0.15 | 0.62
|  | Cum | 1 | 1 | 1.6 | 6.675 | 0.15 | 1.6
|  | Cum | 0.5 | 1 | 3.07 | 1.065 | 0.15 | 0.25
|  | Cum | 1 | 1 | 1.6 | 3.9 | 0.15 | 0.94
|  | Cum | 0.5 | 1 | 2.77 | 0.96 | 0.15 | 0.2
|  | Cum | 1 | 1 | 1.6 | 4.09 | 0.15 | 0.98
|  | Cum | 0.5 | 1 | 3.25 | 1.095 | 0.15 | 0.27
|  | Cum | 0.5 | 1 | 8.61 | 4.615 | 0.15 | 2.98
| Stone agg. In planter front between Bh-07 & BH-04 | Cum | 1 | 1 | 1.6 | 8.56 | 0.15 | 2.05
|  | Cum | 1 | 1 | 1.6 | 6.85 | 0.15 | 1.64
|  | Cum | 1 | 1 | 1.6 | 7.45 | 0.15 | 1.79
|  | Cum | 1 | 1 | 0.99 | 8.85 | 0.15 | 1.31
|  | Cum | 1 | 1 | 1.6 | 4.89 | 0.15 | 1.17
|  | Cum | 1 | 1 | 1.6 | 5.33 | 0.15 | 1.28
|  | Cum | 1 | 1 | 1.6 | 1.45 | 0.15 | 0.35
|  | Cum | 1 | 1 | 1.6 | 3.83 | 0.15 | 0.92
|  | Cum | 1 | 1 | 1.415 | 2.425 | 0.15 | 0.51
|  | Cum | 1 | 1 | 0.755 | 1.965 | 0.15 | 0.22
|  | Cum | 0.5 | 1 | 5.465 | 4.2 | 0.15 | 1.72
| Stone agg. In planter east side of BH-1 or front of Water Body | Cum | 1 | 1 | 1.6 | 4 | 0.15 | 0.96
|  | Cum | 1 | 1 | 1.6 | 1 | 0.15 | 0.24
|  | Cum | 1 | 1 | 5.49 | 0.965 | 0.15 | 0.79
|  | Cum | 1 | 1 | 7.09 | 1 | 0.15 | 1.06
|  | Cum | 1 | 1 | 1.6 | 3 | 0.15 | 0.72
|  | Cum | 1 | 1 | 4.345 | 1 | 0.15 | 0.65
|  | Cum | 1 | 1 | 1.6 | 4 | 0.15 | 0.96
|  | Cum | 1 | 2 | 1.6 | 3 | 0.15 | 1.44
|  | Cum | 1 | 1 | 20.145 | 2.235 | 0.15 | 6.75
|  | Cum | 1 | 1 | 1.845 | 4.07 | 0.15 | 1.13
|  | Cum | 1 | 1 | 0.685 | 4.13 | 0.15 | 0.42
|  | Cum | 1 | 1 | 3.43 | 1.2 | 0.15 | 0.62
|  | Cum | 1 | 1 | 1.6 | 3 | 0.15 | 0.72
|  | Cum | 1 | 1 | 3.735 | 1.2 | 0.15 | 0.67
|  | Cum | 1 | 1 | 3.43 | 4.235 | 0.15 | 2.18
|  | Cum | 1 | 1 | 1.6 | 1.8 | 0.15 | 0.43
|  | Cum | 1 | 1 | 1.6 | 4.2 | 0.15 | 1.01
|  | Cum | 1 | 1 | 1.6 | 5 | 0.15 | 1.2
|  | Cum | 1 | 1 | 2.135 | 3.235 | 0.15 | 1.04
|  | Cum | 1 | 1 | 3.735 | 3.2 | 0.15 | 1.79
|  | Cum | 1 | 1 | 12.12 | 1.5 | 0.15 | 2.73
|  | Cum | 1 | 1 | 0.99 | 4.13 | 0.15 | 0.61
|  | Cum | 1 | 1 | 1.6 | 4.5 | 0.15 | 1.08
|  | Cum | 1 | 1 | 1.46 | 2.7 | 0.15 | 0.59
|  | Cum | 1 | 1 | 1.6 | 6 | 0.15 | 1.44
|  | Cum | 1 | 1 | 20.97 | 2 | 0.15 | 6.29
|  | Cum | 1 | 1 | 1.905 | 6.235 | 0.15 | 1.78
|  | Cum | 1 | 1 | 1.145 | 2 | 0.15 | 0.34
|  | Cum | 1 | 1 | 4.345 | 1.2 | 0.15 | 0.78
|  | Cum | 1 | 1 | 1.6 | 1.8 | 0.15 | 0.43
|  | Cum | 1 | 1 | 4.65 | 1 | 0.15 | 0.7
|  | Cum | 1 | 1 | 1.905 | 1.8 | 0.15 | 0.51
Stone Agg. 90 to 45mm in Ramp Area Front side of Gym (West side)
|  | Cum | 1 | 1 | 24.135 | 6.2 | 0.15 | 22.45
| Stone Agg. P/L for Waterbody as per drg. No.(inner dia. 20.12m), dia. For P.C.C. =20.12+0.2*2+0.6*2+0.2*2=22.120m) |  |  |  | area
|  | Cum | 1 | 1 | 384.0961 |  | 0.15 | 57.61
WBM in Road Area
| Area-1, Road between BH-01 & BH-07 | Cum | 1 | 1 | 514.7 |  | 0.125 | 64.34
| Area-2, Road between BH-04 & west corner of BH-01 | Cum | 1 | 1 | 169.79 |  | 0.125 | 21.22
| deduct area not done | Cum | -1 | 1 | 6.545 | 6 | 0.125 | -4.91
| Area-3, Road between BH-01 west side & waterbody | Cum | 1 | 1 | 580.43 |  | 0.125 | 72.55
| Area-4, Road between BH-04 west side | Cum | 1 | 1 | 628.19 |  | 0.125 | 78.52
| Area-5, Road between BH-05 north side & Basket Ball Ground | Cum | 1 | 1 | 303.47 |  | 0.125 | 37.93
| Area-6, Road front BH-05 east side | Cum | 1 | 1 | 165.9 |  | 0.125 | 20.74
[5 empty] | L | B | H
| WBM P/L in Ramp Area (1/H-J) | Cum | 1 | 1 | 36.715 | 8.48 | 0.15 | 46.7
| deduct Col. | Cum | -1 | 17 | 1.2 | 0.375 | 0.15 | -1.15
| WBM P/L between BH-01 & Canteen | Cum | 1 | 1 | 18.1 | 33.615 | 0.15 | 91.26
area
| add area near road junction near canteen east corner | Cum | 1 | 1 | 40.53 |  | 0.15 | 6.08
| deduct R.C.C. Existng Col. | Cum | -1 | 5 | 4.64 |  | 0.15 | -3.48
| deduct R.C.C. Planter Area | Cum | -1 | 6 | 4.49 |  | 0.15 | -4.04
|  | Cum | -1 | 3 | 4.5 |  | 0.15 | -2.03
| deduct sheat area | Cum | -1 | 6 | 1.349 |  | 0.15 | -1.21
| Green Planter | Cum | -1 | 2 | 1.47 | 5.555 | 0.15 | -2.45
| DEDUCT SHEAR WALL |  | -4 | 1 | 0.8 | 5.8 | 0.15 | -2.78
|  |  | -1 | 1 | 5.92 |  | 0.15 | -0.89
| WBM P/L between BH-01 west side | Cum | 1 | 1 | 364.85 |  | 0.15 | 54.73
| deduct existing Plnater | Cum | -1 | 1 | 34.05 |  | 0.15 | -5.11
|  | Cum | -1 | 1 | 70.8 |  | 0.15 | -10.62
area
| WBM P/L between BH-02 & GYM | Cum | 1 | 1 | 478.103 |  | 0.15 | 71.72
| deduction for seat | Cum | -1 | 6 | 1.35 |  | 0.15 | -1.22
[5 empty] | L | B | H
| deduction for Green Planter | Cum | -1 | 1 | 2.625 | 1.2 | 0.15 | -0.47
|  | Cum | -1 | 1 | 5.85 | 1.2 | 0.15 | -1.05
|  | Cum | -1 | 1 | 5.025 | 1.2 | 0.15 | -0.9
|  | Cum | -1 | 1 | 2.4 | 1.2 | 0.15 | -0.43
| DEDUCT SHEAR WALL |  | -4 | 1 | 0.8 | 5.8 | 0.15 | -2.78
|  |  | -1 | 1 | 5.92 |  | 0.15 | -0.89
| Deduction for prev. raod qty. & ramp qty. for Revision | Cum | -1 | 1 | 204.16 |  |  | -204.16
| 20% | Cum | -1 |  | 145.03 |  |  | -145.03
WBM for Boy's Hostel
| WBM/Stone Soling for Ramp for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 1.54 | 0.15 | 1.39
|  | Cum | 1 | 1 | 2.925 | 2.54 | 0.15 | 1.11
Cum
| WBM P/L for Entry Area Steps of BH-01 | Cum
| Steps for Entry | Cum | 1 | 1 | 5.42 | 4.26 | 0.15 | 3.46
|  | Cum |  |  | area
| WBM P/L for side ramp of entrance | Cum | 1 | 1 | 16 |  | 0.15 | 2.4 |  | area
Cum
| WBM P/L for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 1.54 | 0.15 | 1.39
|  | Cum | 1 | 1 | 2.925 | 2.54 | 0.15 | 1.11
Cum
| WBM P/L for Entry Area Steps of BH-02 | Cum
| Steps for Entry | Cum | 1 | 1 | 5.42 | 4.26 | 0.15 | 3.46
|  | Cum |  |  | area
| WBM P/L for side ramp of entrance | Cum | 1 | 1 | 16 |  | 0.15 | 2.4 |  | area
Cum
| WBM for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 1.54 | 0.15 | 1.39
|  | Cum | 1 | 1 | 2.925 | 2.54 | 0.15 | 1.11
Cum
| WBM P/L for Entry Area Steps of BH-03 | Cum
| Steps for Entry | Cum | 1 | 1 | 5.42 | 4.26 | 0.15 | 3.46
|  | Cum |  |  | area
| WBM P/L for side ramp of entrance | Cum | 1 | 1 | 16 |  | 0.15 | 2.4 |  | area
Cum
Cum
| WBM. P/L for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205 | Cum
|  | Cum | 1 | 1 | 6 | 1.54 | 0.15 | 1.39
|  | Cum | 1 | 1 | 2.925 | 2.54 | 0.15 | 1.11
Cum
| WBM. for Entry Area Steps of BH-04 | Cum
| Steps for Entry | Cum | 1 | 1 | 5.42 | 4.26 | 0.15 | 3.46
|  | Cum |  |  | area
| WBM P/L for side ramp of entrance | Cum | 1 | 1 | 16 |  | 0.15 | 2.4 |  | area
Cum
Cum
| WBM P/L for Floor (area side of Road line) Laying of Kandla Stone | Cum |  |  | Area
| Area-1, area between BH-01 & BH-07 south side of Road | Cum | 1 | 1 | 300.0786 |  | 0.15 | 45.01
| Area-2, BH-01 south side main entrance | Cum | 1 | 1 | 160.0868 |  | 0.15 | 24.01
| deduct Green Planter Area | Cum | -1 | 1 | 19.47 |  | 0.15 | -2.92
| Area-3, BH-01 south side main entrance | Cum | 1 | 1 | 45.5218 |  | 0.15 | 6.83
| Area-4, BH-01 south side main entrance | Cum | 1 | 1 | 241.8989 |  | 0.15 | 36.28
| deduct Green Planter Area | Cum | -1 | 1 | 50.7604 |  | 0.15 | -7.61
| deduct Green Planter Area | Cum | -1 | 1 | 43.292 |  | 0.15 | -6.49
| Area-5, BH-04 south side main entrance | Cum | 1 | 1 | 61.0155 |  | 0.15 | 9.15
| deduct Green Planter Area | Cum | -1 | 1 | 12.2755 |  | 0.15 | -1.84
Cum
| Area-6, Area between BH-04 & BH-02 , waterbody surrounding area | Cum | 1 | 1 | 628.5243 |  | 0.15 | 94.28
| deduct Waterbody Area | Cum | -1 | 1 | 341.7578 |  | 0.15 | -51.26
| deduct seat | Cum | -1 | 8 | 2.836 | 0.286 | 0.15 | -0.97
Cum
| Area-7, Area under BH-04 transfer Slab towards waterbody | Cum | 1 | 1 | 615.412 |  | 0.15 | 92.31
| deduct Green Planter area | Cum | -1 | 1 | 3.155 | 1.799 | 0.15 | -0.85
|  | Cum | -1 | 1 | 5.85 | 1.799 | 0.15 | -1.58
|  | Cum | -1 | 1 | 5.025 | 1.799 | 0.15 | -1.36
| deduct for Entrance Ramp | Cum | -1 | 1 | 3.823 | 3 | 0.15 | -1.72
| deduct for Entrance Ramp | Cum | -1 | 1 | 6 | 2 | 0.15 | -1.8
| deduct R.C.C. Wall/Col. | Cum | -1 | 5 | 5.8 | 0.8 | 0.15 | -3.48
|  | Cum | -1 | 8 | 4.5 | 1 | 0.15 | -5.4
| deduct seat | Cum | -1 | 7 | 2.836 | 0.286 | 0.15 | -0.85
|  | Cum |  |  | area
| deduct Green Planter south side of Reception | Cum | -1 | 1 | 40.6167 |  | 0.15 | -6.09
| Area-8, west side of reception (front of Basket ball ground & BH-03) | Cum | 1 | 1 | 23.3075 |  | 0.15 | 3.5
| Area-9, north side of reception | Cum | 1 | 1 | 68.8563 |  | 0.15 | 10.33
| deduct Green Planter area | Cum | -1 | 1 | 9.36 | 0.6 | 0.15 | -0.84
|  | Cum | -1 | 1 | 8.14 | 0.6 | 0.15 | -0.73
|  | Cum | -1 | 1 | 6.616 | 0.6 | 0.15 | -0.6
|  | Cum | -1 | 1 | 4.785 | 0.6 | 0.15 | -0.43
|  | Cum | -1 | 1 | 3.26 | 0.6 | 0.15 | -0.29
Cum
| Area-10, area between BH-01 & Canteen, or under transfer slab | Cum | 1 | 1 | 608.4315 |  | 0.15 | 91.26
| deduct green planter of BH-01 north face | Cum | -1 | 1 | 5.025 | 1.194 | 0.15 | -0.9
|  | Cum | -1 | 1 | 5.85 | 1.197 | 0.15 | -1.05
| deduct R.C.C. Planter area under transfer dalb BH-01 | Cum | -1 | 9 | 4.5 | 1 | 0.15 | -6.08
| deduct R.C.C. shear wall | Cum | -1 | 5 | 5.8 | 0.8 | 0.15 | -3.48
| deduct seat | Cum | -1 | 6 | 2.836 | 0.286 | 0.15 | -0.73
|  | Cum | -1 | 3 | 1.2 | 0.375 | 0.15 | -0.2
| deduct for Entrance Ramp | Cum | -1 | 1 | 3.823 | 3 | 0.15 | -1.72
| deduct for Entrance Ramp | Cum | -1 | 1 | 6 | 2 | 0.15 | -1.8
| deduct rcc column area | Cum | -1 | 3 | 1.2 | 0.375 | 0.15 | -0.2
| deduct toe wall area | Cum | -1 | 1 | 16.925 | 0.23 | 0.15 | -0.58
|  | Cum |  |  | area
| Area-11, at junction of Road near canteen & BH-01 towards waterbody | Cum | 1 | 1 | 77.1675 |  | 0.15 | 11.58 |  | area
| Area-12, area east side of BH-01 | Cum | 1 | 1 | 294.171 |  | 0.15 | 44.13
| deduct Green planter of BH-01 east face | Cum | -1 | 1 | 28.785 |  | 0.15 | -4.32
|  | Cum | -1 | 1 | 23.2452 |  | 0.15 | -3.49
|  | Cum | -1 | 3 | 1.2 | 0.375 | 0.15 | -0.2
| Area-13, area south side of BH-02 (long Planter) | Cum | 1 | 3 | 2.987 | 1.55 | 0.15 | 2.08
|  | Cum | 1 | 1 | 2.987 | 2 | 0.15 | 0.9
|  | Cum | 1 | 1 | 2.987 | 1.3 | 0.15 | 0.58
|  | Cum | 1 | 1 | 2.987 | 1.8 | 0.15 | 0.81
|  | Cum | 1 | 1 | 5.1077 |  | 0.15 | 0.77 |  | area
|  | Cum | 1 | 1 | 7.194 |  | 0.15 | 1.08 |  | area
|  | Cum | 1 | 1 | 10.7681 |  | 0.15 | 1.62 |  | area
|  | Cum | 1 | 1 | 10.941 |  | 0.15 | 1.64 |  | area
|  | Cum | 1 | 1 | 17.5006 |  | 0.15 | 2.63 |  | area
| Area-14, area south side of Toilet near Gym | Cum | 1 | 1 | 67.2189 |  | 0.15 | 10.08 |  | area
| deduct Green Planter area | Cum | -1 | 2 | 6.639 | 0.6 | 0.15 | -1.2
|  | Cum | -1 | 1 | 5.725 | 0.6 | 0.15 | -0.52
|  | Cum | -1 | 1 | 3.589 | 0.6 | 0.15 | -0.32
| Area-15, area between BH-02 long Planter & Toilet of Gym | Cum | 1 | 1 | 135.0703 |  | 0.15 | 20.26 |  | area
| Area-16, area between BH-02 & GYM Transfer Slab | Cum | 1 | 1 | 500.2299 |  | 0.15 | 75.03 |  | area
| deduct Green Planter | Cum | -1 | 1 | 0.999 | 1.2 | 0.15 | -0.18
|  | Cum | -1 | 1 | 5.85 | 1.2 | 0.15 | -1.05
|  | Cum | -1 | 1 | 5.024 | 1.2 | 0.15 | -0.9
|  | Cum | -1 | 1 | 2.399 | 1.2 | 0.15 | -0.43
| deduct for Entrance Ramp | Cum | -1 | 1 | 3.823 | 3 | 0.15 | -1.72
| deduct for Entrance Ramp | Cum | -1 | 1 | 6 | 2 | 0.15 | -1.8
| deduct R.C.C. wall Col. | Cum | -1 | 5 | 5.8 | 0.8 | 0.15 | -3.48
| deduct R.C.C. Planter area under transfer slab BH-02 | Cum | -1 | 8 | 4.5 | 1 | 0.15 | -5.4
| deduct seat | Cum | -1 | 6 | 2.836 | 0.286 | 0.15 | -0.73
|  | Cum | -1 | 4 | 7.625 | 0.23 | 0.15 | -1.05
| Area-17, Area north side of BH-02 | Cum | 1 | 1 | 293.7889 |  | 0.15 | 44.07 |  | area
| deduct green planter area | Cum | -1 | 1 | 61.3885 |  | 0.15 | -9.21 |  | area
Cum
| Area-18, Area north side of Canteen (J/1'-4') | Cum | 1 | 1 | 31.5 | 1.985 | 0.15 | 9.38
| deduct Col. | Cum | -1 | 4 | 1.2 | 0.375 | 0.15 | -0.27
| Area-19, Area north side gallary of BH-02 corner to Gym corner (J/5-9') | Cum | 1 | 1 | 37.9 | 4.505 | 0.15 | 25.61
|  | Cum | -1 | 5 | 7.625 | 0.23 | 0.15 | -1.32
| deduct Col. | Cum | -1 | 5 | 1.2 | 0.375 | 0.15 | -0.34
| Area-20, Area west side of canteen or north side of B H-03 | Cum | 1 | 1 | 24.6285 | 13.365 | 0.15 | 49.37
| deduct Col. | Cum | -1 | 5 | 1.2 | 0.375 | 0.15 | -0.34
| deduct Green Planter | Cum | -1 | 1 | 82.6623 |  | 0.15 | -12.4 |  | area
| Area-21, Area south side of Gym (8/H) | Cum | 1 | 1 | 93.578 |  | 0.15 | 14.04 |  | area
| Area-22, Area between Basket Ball Ground & BH-03, under Transfer slab | Cum | 1 | 1 | 508.5971 |  | 0.15 | 76.29 |  | area
| add area near road junction | Cum | 1 | 1 | 47.9965 |  | 0.15 | 7.2 |  | area
| deduct Green Planter | Cum | -1 | 1 | 5.025 | 1.2 | 0.15 | -0.9
|  | Cum | -1 | 1 | 5.85 | 1.2 | 0.15 | -1.05
| deduct for Entrance Ramp | Cum | -1 | 1 | 3.823 | 3 | 0.15 | -1.72
| deduct for Entrance Ramp | Cum | -1 | 1 | 6 | 2 | 0.15 | -1.8
| deduct R.C.C. wall Col. | Cum | -1 | 5 | 5.8 | 0.8 | 0.15 | -3.48
| deduct R.C.C. Planter area under transfer slab BH-02 | Cum | -1 | 8 | 4.5 | 1 | 0.15 | -5.4
| deduct seat | Cum | -1 | 4 | 2.836 | 0.286 | 0.15 | -0.49
| deduct Col. | Cum | -1 | 2 | 1.2 | 0.375 | 0.15 | -0.14
| DEDUCT BRICK WALL | Cum | -1 | 1 | 7.625 | 0.23 | 0.15 | -0.26
|  | Cum | -1 | 1 | 7.125 | 0.23 | 0.15 | -0.25
|  | Cum | -1 | 1 | 1.614 | 0.23 | 0.15 | -0.06
| Area-23, Area east side of BH-03 parallel to road | Cum | 1 | 1 | 103.5326 |  | 0.15 | 15.53 |  | area
| Area-24, Area east side of BH-02 parallel to road (Road between BH-02 & Canteen) | Cum | 1 | 1 | 60.3692 |  | 0.15 | 9.06 |  | area
| Area-24, towards canteen east of road (Road between BH-02 & Canteen) | Cum | 1 | 1 | 17.9818 |  | 0.15 | 2.7 |  | area
| Area-25, area between road of Basket ball ground & BH-05 | Cum | 1 | 1 | 82.809 |  | 0.15 | 12.42 |  | area
Cum
| WBM P/L for Road Work | Cum
Cum
| Area-1, Road between Waterbody & BH-02 (remaining portion) | Cum | 1 | 1 | 43.026 |  | 0.125 | 5.38 |  | area
| Area-2, Road between Canteen & BH-02 | Cum | 1 | 1 | 235.971 |  | 0.125 | 29.5 |  | area
| Area-3, Road south side of BH-04 | Cum | 1 | 1 | 229.3859 |  | 0.125 | 28.67 |  | area
| Area-4, Road between BH-03 & Gym | Cum | 1 | 1 | 161.3012 |  | 0.125 | 20.16 |  | area
Cum
| Revise Qty. due to correction in 3rd R.A.Bill | Cum
| Area-2, Road between BH-04 & west corner of BH-01 | Cum
| add area for correction | Cum | 1 | 1 | 6.545 | 6 | 0.125 | 4.91
| deduct area not done (revise measurement) | Cum | -1 | 1 | 4.798 | 6 | 0.075 | -2.16
Cum
| release 20% (ref. to previous bill hold qty.) | Cum | 1 | 1 | 145.03 |  |  | 145.03
WBM P/L at west side of Basket ball ground (34'-39'/51-52)
|  | Cum | 1 | 1 | 14.65 | 0.97 | 0.15 | 2.13
| deduct R.C.C. Col. | Cum | -1 | 2 | 0.97 | 0.375 | 0.15 | -0.11
WBM P/L north side of BH-01, between BH-01 Entrance Door & Green Planter towards canteen
|  | Cum | 1 | 1 | 15 | 0.6 | 0.15 | 1.35
WBM P/L north side of BH-04, between BH-04 Entrance Door & Green Planter towards waterbody
|  | Cum | 1 | 1 | 15 | 0.6 | 0.15 | 1.35
| UP TO PREVIOUS BILL | Cum | [6 empty] | 1521.52
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
1521.52
GEO TEXTILE AND DRAINCELL
7 | Providing & laying Drain Cell of 20mm thk. (Ovilite or similar item) composed of high density polythene (HDPE) & Joint to a non woven geotextile of calendered polypropylene of not less than 120g/sqm or equivalent. Joints to overlapping at Nodule height should not be less than 7.3+/-0.2mm
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
A | Drain Cell P/L at G.Floor R.C.C. Planter
| drain Cell P/L in R.C.C. Planter under BH-01 Transfer Slab | Sqm | 1 | 6 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 1 | 3 | 4.1 | 0.6 |  | 7.38
| drain Cell P/L in R.C.C. Planter under BH-02 Transfer Slab | Sqm | 1 | 6 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 1 | 2 | 4.1 | 0.6 |  | 4.92
| drain Cell P/L in R.C.C. Planter under BH-03 Transfer Slab | Sqm | 1 | 6 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 1 | 2 | 4.1 | 0.6 |  | 4.92
| drain Cell P/L in R.C.C. Planter under BH-04 Transfer Slab | Sqm | 1 | 6 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 1 | 2 | 4.1 | 0.6 |  | 4.92
B | Drain Cell P/L at Podium Planter
Drain Cell at Canteen Podium
| Long Planter near Stair Case | Sqm | 1 | 1 | 21.4 | 2.4 |  | 51.36
|  | Sqm | 1 | 5 | 4.4 | 1.4 |  | 30.8
| Drain Cell in Planter near Pargola at Canteen | Sqm | 1 | 4 | 3 | 2.4 |  | 28.8
|  | Sqm | 1 | 5 | 4.4 | 1.4 |  | 30.8
Drain Cell at Gym Podium
| long Planter near Pargola | Sqm | 1 | 1 | 28.435 | 2.4 |  | 68.24
| deduction | Sqm | -1 | 5 | 1.765 | 2 |  | -17.65
| Planter | Sqm | 1 | 5 | 4.4 | 1.4 |  | 30.8
| Planter | Sqm | 1 | 3 | 2.085 | 1.6 |  | 10.01
| Planter | Sqm | 1 | 5 | 2.03 | 1.4 |  | 14.21
| THIS BILL TOTAL → | Sqm | [6 empty] | 348.23 | 6th RA
348.23
WATERPROOFING WORK
4 | Providing & Laying composite built up waterproofing under screed comprising og three coatsof tepecrete polymer, each coat admixed with cement in proportion 1:2 (one part Tepecrete & two parts cement) over a primer coat of neat cement slurry admixed with impermeable chemical CH-09. After the second coat of Tepecrete, all corners, sdges, joints of pipes with concrete/masonry should be seated with epoxy putty. 10mm thk. protective plaster 1:4 (1 cement 4 coarse sand) over treated surface etc. complete. (Quoted rate to include grouting of RCC surface for any cracks/ fissures & cost of grey cement.) (H+V)
Waterproofing in R.C.C. Planter under Transfer Slab of BH-03 (between BH-03 & Basket Ball Ground)
| Base | Sqm | 6 | 1 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 2 | 1 | 4.1 | 0.6 |  | 4.92
| Wall | Sqm | 8 | 2 | 0.8 |  | 0.8 | 10.24
| Wall | Sqm | 8 | 2 | 4.1 |  | 1.025 | 67.24
Waterproofing in R.C.C. Planter under Transfer Slab of BH-04 (between BH-04 & Waterbody)
| Base | Sqm | 6 | 1 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 2 | 1 | 4.1 | 0.6 |  | 4.92
| Wall | Sqm | 8 | 2 | 0.8 |  | 0.8 | 10.24
| Wall | Sqm | 8 | 2 | 4.1 |  | 1.025 | 67.24
Waterproofing in R.C.C. Planter under Transfer Slab of BH-01 (between BH-01 & Canteen)
| Base | Sqm | 6 | 1 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 3 | 1 | 4.1 | 0.6 |  | 7.38
| Wall | Sqm | 9 | 2 | 0.8 |  | 0.8 | 11.52
| Wall | Sqm | 9 | 2 | 4.1 |  | 1.025 | 75.65
Waterproofing in R.C.C. Planter under Transfer Slab of BH-02 (between BH-02 & Gym)
| Base | Sqm | 6 | 1 | 4.1 | 0.8 |  | 19.68
|  | Sqm | 2 | 1 | 4.1 | 0.6 |  | 4.92
| Wall | Sqm | 8 | 2 | 0.8 |  | 0.8 | 10.24
| Wall | Sqm | 8 | 2 | 4.1 |  | 1.025 | 67.24
| As per JMR Date -30.05.2017 | Sqm | 1 |  | 177.14 |  |  | 177.14 |  | Page 7
| As per JMR Date -30.05.2017 | Sqm | 1 |  | 32.4 |  |  | 32.4 |  | Page 7
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 630.01
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
630.01
AGRA RED SANDSTONE- NATURAL FINISH (RAMP & PAVED AREAS)
1.1 | Providing & Fixing 40mm Natural Finish Red Agra Sandstone (Base Rate : 550) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls.
Natural Finish Red Agra Sandstone 40mm thk. At Podium Lvl.
| Agra Natural at canteen Podium | Sqm | 1 | 1 | 31.93 | 3.035 |  | 96.91
| stone near stair case area side of long green planter | Sqm | 1 | 1 | 25.035 | 3.795 |  | 95.01
| front of stair | Sqm | 1 | 1 | 6.2 | 4.035 |  | 25.02
|  | Sqm | 1 | 8 | 5 | 2 |  | 80
| deduct Green Planter | Sqm | -1 | 24 | 1 | 1 |  | -24
| Agra Natural at Podium passage Canteen to Gym | Sqm | 1 | 1 | 37.414 | 1.2 |  | 44.9
| Agra Natural at Podium passage Canteen to Gym | Sqm | 1 | 1 | 18.956 | 1.2 |  | 22.75
| Agra Natural at Podium passage Canteen to BH-01 | Sqm | 1 | 1 | 46.729 | 1.24 |  | 57.94
|  | Sqm | 1 | 1 | 6.098 | 3.05 |  | 18.6
|  | Sqm | 1 | 1 | 12 | 3.3 |  | 39.6
| passage BH-01 to BH-04 | Sqm | 1 | 1 | 182.4 |  |  | 182.4 |  | Area
| Agra Red at Gym Podium | Sqm | 1 | 1 | 20.265 | 4.685 |  | 94.94
| deduct Planter Area | Sqm | -1 | 1 | 2.685 | 2.6 |  | -6.98
|  | Sqm | -1 | 1 | 2.685 | 2.2 |  | -5.91
|  | Sqm | -1 | 1 | 2.685 | 2.3 |  | -6.18
|  | Sqm | -1 | 1 | 2.685 | 3 |  | -8.06
Agra Red Sanstone 40mm thk. Natural
| Area-1, Canteen to BH-01 passage (remaining portion) | Sqm | 1 | 1 | 17.506 | 1.2 |  | 21.01
| Area-2, Agra natural at passage canteen to BH-04 connection between BH-02 & BH-01 | Sqm | 1 | 1 | 48.075 | 2 |  | 96.15
| Area-3, Agra natural at podium west side of canteen & Bh-02 east side near Pargola | Sqm | 1 | 1 | 118.6025 |  |  | 118.6
| Area-3.1, Agra at Canteen Podium parallel to BH-01 | Sqm | 1 | 1 | 47.843 | 2.88 |  | 137.79
| Area-4, agra Natural at Podium South side of BH-01 | Sqm | 1 | 1 | 198.277 |  |  | 198.28
| Area-4.1, agra at east side of BH-01 passage parallel to outer road | Sqm | 1 | 1 | 72.872 |  |  | 72.87
| Area-5, Agra natural at Gym Podium | Sqm | 1 | 1 | 72.4537 |  |  | 72.45
| add north side of green planter | Sqm | 1 | 1 | 3 | 2 |  | 6
| deduct Green Planter | Sqm | -1 | 0 | 2.685 | 2.6 |  | 0
| deduct honed stone | Sqm | -1 | 0 | 2.677 | 0.3 |  | 0
| DEDUCT FOR TOP RAILING 50MM | Sqm | -1 | 1 | 0.763 |  |  | -0.76
| PLANTER | Sqm | -1 | 1 | 2.685 | 2.6 |  | -6.98
|  | Sqm | -1 | 1 | 2.685 | 2.2 |  | -5.91
|  | Sqm | -1 | 1 | 2.685 | 2.3 |  | -6.18
| Area-6, Agra at Gym Podium (south side) near at junction of BH-03 | Sqm | 1 | 1 | 47.4366 |  |  | 47.44
| Area-7, Agra Natural 40mm at Podium passage Basket Ball ground to BH-04 south corner | Sqm | 1 | 1 | 180.194 |  |  | 180.19
| Area-8, Agra natural at Podium passage above basket ball corner to BH-03 expansion joint | Sqm | 1 | 1 | 92.7833 |  |  | 92.78
| Ara-9, at Gym podium back side of long planter near pargola | Sqm | 1 | 1 | 68.9107 |  |  | 68.91
| Area-10, gym podium north side of pargola passage | Sqm | 1 | 1 | 12.2199 |  |  | 12.22
| Area-11, Agra Natural Stone at Podium Passage Canteen to Gym (J/4-8) | Sqm | 1 | 1 | 73.2786 |  |  | 73.28
| Area-12, Agra Natural Stone parallel to BH-02 taper side Podium Passage Canteen to Gym | Sqm | 1 | 1 | 74.2492 |  |  | 74.25
| DEDUCT FOR TOP RAILING 50MM | Sqm | -1 | 1 | 56.37 | 0.05 |  | -2.82
|  | Sqm | -1 | 1 | 50.459 | 0.05 |  | -2.52
|  | Sqm | -1 | 1 | 33.133 | 0.05 |  | -1.66
Agra Red Sanstone 40mm thk. Natural at Stair Case Podium
40mm thk. Agra Natural Stone at Coping in Cladding of Podium Stair Case at Canteen
Coping at side cladding in staircase R.H.S.
| 1st, 2nd & 3rd Flight | Sqm | 1 | 3 | 3.822 | 0.21 |  | 2.41
| 4th Flight | Sqm | 1 | 1 | 3.471 | 0.21 |  | 0.73
| 1st, 2nd, 3rd Landing | Sqm | 1 | 3 | 2.794 | 0.21 |  | 1.76
Coping at side cladding in staircase L.H.S.
| 1st, 2nd & 3rd Flight | Sqm | 1 | 3 | 3.822 | 0.08 |  | 0.92
| 4th Flight | Sqm | 1 | 1 | 3.471 | 0.08 |  | 0.28
| 1st, 2nd, 3rd Landing | Sqm | 1 | 3 | 2.794 | 0.08 |  | 0.67
| front face for packing | Sqm | 1 | 2 | 0.3 |  | 0.9 | 0.54
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 1959.64
a | Area-1, Podium Passage parallel to BH-04 West side | Sqm | 1 | 1 | 92.8061 |  |  | 92.81 |  | Area
| Area-1, Podium Passage parallel to BH-04 South side | Sqm | 1 | 1 | 60.9594 |  |  | 60.96 |  | Area
| Area-2, Podium Passage parallel to BH-05 West side (remaining portion) | Sqm | 1 | 1 | 2.25 | 2.05 |  | 4.61
| Area-3, Podium Passage parallel to BH-03 to Gym Podium West side | Sqm | 1 | 1 | 90.633 |  |  | 90.63 |  | Area
| Area-4,Gym Podium east side near Pargola passage | Sqm | 1 | 1 | 83.3326 |  |  | 83.33 |  | Area
b | Agra Natural Sandstone P/L at Canteen Podium for Making of Drain after fixing of Stone (Rework) as per direction of Engineer in Charge
| Drain Stone parallel to BH-02 at Canteen Face | Sqm | 1 | 1 | 12.538 | 0.3 |  | 3.76
| Drain Stone parallel to Pargola at canteen | Sqm | 1 | 1 | 4.16 | 0.3 |  | 1.25
|  | Sqm | 1 | 1 | 15.844 | 0.3 |  | 4.75
| Drain Stone north side of canteen pargola parallel to outer railing | Sqm | 1 | 1 | 31.93 | 0.3 |  | 9.58
| Drain parallel to long planter near stair case at canteen (east face) | Sqm | 1 | 1 | 24.785 | 0.3 |  | 7.44
| south face of planter, Drain | Sqm | 1 | 1 | 8 | 0.3 |  | 2.4
|  |  | -1 |  | 29.18 |  |  | -29.18
Qty. Rewise due to calculation correction
Agra Red Sanstone 40mm thk. Natural
| Area-1, Canteen to BH-01 passage (remaining portion) | Sqm | -1 | 1 | 17.506 | 1.2 |  | -21.01
| Area-2, Agra natural at passage canteen to BH-04 connection between BH-02 & BH-01 | Sqm | -1 | 1 | 48.075 | 2 |  | -96.15
| Area-3, Agra natural at podium west side of canteen & Bh-02 east side near Pargola | Sqm | -1 | 1 | 118.6025 |  |  | -118.6
| Area-3.1, Agra at Canteen Podium parallel to BH-01 | Sqm | -1 | 1 | 47.843 | 2.88 |  | -137.79
| Area-4, agra Natural at Podium South side of BH-01 | Sqm | -1 | 1 | 198.277 |  |  | -198.28
| Area-4.1, agra at east side of BH-01 passage parallel to outer road | Sqm | -1 | 1 | 72.872 |  |  | -72.87
| Area-5, Agra natural at Gym Podium | Sqm | -1 | 1 | 72.4537 |  |  | -72.45
| add north side of green planter | Sqm | -1 | 1 | 3 | 2 |  | -6
| deduct Green Planter | Sqm | -1 | 0 | 2.685 | 2.6 |  | 0
| deduct honed stone | Sqm | -1 | 0 | 2.677 | 0.3 |  | 0
| DEDUCT FOR TOP RAILING 50MM | Sqm | 1 | 1 | 0.763 |  |  | 0.76
| PLANTER | Sqm | 1 | 1 | 2.685 | 2.6 |  | 6.98
|  | Sqm | 1 | 1 | 2.685 | 2.2 |  | 5.91
|  | Sqm | 1 | 1 | 2.685 | 2.3 |  | 6.18
| Area-6, Agra at Gym Podium (south side) near at junction of BH-03 | Sqm | -1 | 1 | 47.4366 |  |  | -47.44
| Area-7, Agra Natural 40mm at Podium passage Basket Ball ground to BH-04 south corner | Sqm | -1 | 1 | 180.194 |  |  | -180.19
| Area-8, Agra natural at Podium passage above basket ball corner to BH-03 expansion joint | Sqm | -1 | 1 | 92.7833 |  |  | -92.78
| Ara-9, at Gym podium back side of long planter near pargola | Sqm | -1 | 1 | 68.9107 |  |  | -68.91
| Area-10, gym podium north side of pargola passage | Sqm | -1 | 1 | 12.2199 |  |  | -12.22
| Area-11, Agra Natural Stone at Podium Passage Canteen to Gym (J/4-8) | Sqm | -1 | 1 | 73.2786 |  |  | -73.28
| Area-12, Agra Natural Stone parallel to BH-02 taper side Podium Passage Canteen to Gym | Sqm | -1 | 1 | 74.2492 |  |  | -74.25
| DEDUCT FOR TOP RAILING 50MM | Sqm | 1 | 1 | 56.37 | 0.05 |  | 2.82
|  | Sqm | 1 | 1 | 50.459 | 0.05 |  | 2.52
|  | Sqm | 1 | 1 | 33.133 | 0.05 |  | 1.66
Agra Red Sanstone 40mm thk. Natural at Stair Case Podium
40mm thk. Agra Natural Stone at Coping in Cladding of Podium Stair Case at Canteen
Coping at side cladding in staircase R.H.S.
| 1st, 2nd & 3rd Flight | Sqm | -1 | 3 | 3.822 | 0.21 |  | -2.41
| 4th Flight | Sqm | -1 | 1 | 3.471 | 0.21 |  | -0.73
| 1st, 2nd, 3rd Landing | Sqm | -1 | 3 | 2.794 | 0.21 |  | -1.76
| deduct Green Planter | Sqm | 1 | 24 | 1 | 1 |  | 24
a | Rewised Corrected Calculation Agra Red Sanstone 40mm thk. Natural
| Area-1, Canteen to BH-01 passage (remaining portion) | Sqm | 1 | 1 | 17.506 | 1.24 |  | 21.71
| Area-2, Agra natural at passage canteen to BH-04 connection between BH-02 & BH-01 | Sqm | 1 | 1 | 48.075 | 2.05 |  | 98.55
| Area-3, Agra natural at podium west side of canteen & Bh-02 east side near Pargola | Sqm | 1 | 1 | 118.6025 |  |  | 118.6 |  | Area
| Area-3.1, Agra at Canteen Podium parallel to BH-01 | Sqm | 1 | 1 | 47.945 | 2.88 |  | 138.08
| Area-4, agra Natural at Podium South side of BH-01 | Sqm | 1 | 1 | 198.28 |  |  | 198.28
| Area-4.1, agra at east side of BH-01 passage parallel to outer road | Sqm | 1 | 1 | 75.5252 |  |  | 75.53 |  | Area
| Area-5, Agra natural at Gym Podium | Sqm | 1 | 1 | 72.4537 |  |  | 72.45 |  | Area
| add north side of green planter | Sqm | 1 | 1 | 3 | 2.05 |  | 6.15
| deduct Green Planter | Sqm | -1 | 1 | 2.685 | 2.6 |  | -6.98
| deduct honed stone | Sqm | -1 | 1 | 2.677 | 0.3 |  | -0.8
| Area-6, Agra at Gym Podium (south side) near at junction of BH-03 | Sqm | 1 | 1 | 47.4366 |  |  | 47.44 |  | Area
| Area-7, Agra Natural 40mm at Podium passage Basket Ball ground to BH-04 south corner | Sqm | 1 | 1 | 180.194 |  |  | 180.19 |  | Area
| Area-8, Agra natural at Podium passage above basket ball corner to BH-03 expansion joint | Sqm | 1 | 1 | 92.7833 |  |  | 92.78 |  | Area
| Ara-9, at Gym podium back side of long planter near pargola | Sqm | 1 | 1 | 68.9107 |  |  | 68.91 |  | Area
| Area-10, gym podium north side of pargola passage | Sqm | 1 | 1 | 12.2199 |  |  | 12.22 |  | Area
| Area-11, Agra Natural Stone at Podium Passage Canteen to Gym (J/4-8) | Sqm | 1 | 1 | 73.2786 |  |  | 73.28 |  | Area
| Area-12, Agra Natural Stone parallel to BH-02 taper side Podium Passage Canteen to Gym | Sqm | 1 | 1 | 74.2492 |  |  | 74.25 |  | Area
b | Agra Red Sanstone 40mm thk. Natural at Stair Case Podium
40mm thk. Agra Natural Stone at Coping in Cladding of Podium Stair Case at Canteen
Coping at side cladding in staircase R.H.S.
| 1st, 2nd & 3rd Flight | Sqm | 1 | 3 | 3.822 | 0.29 |  | 3.33
| 4th Flight | Sqm | 1 | 1 | 3.471 | 0.29 |  | 1.01
| 1st, 2nd, 3rd Landing | Sqm | 1 | 3 | 2.794 | 0.29 |  | 2.43
| deduct Green Planter | Sqm | -1 | 24 | 0.83 | 0.83 |  | -16.53
| THIS BILL TOTAL → | Sqm | [6 empty] | 366.93 | 6th RA
2326.57
AGRA RED SANDSTONE- HONED FINISH (IN PLAZZA, ALONG WITH BANDS)
1.2 | Providing & Fixing 40mm Honed Finish Red Agra Sandstone (Base Rate : 750) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls.
M2 Agra Red Sandstone Honed Finish
| at Canteen Podium | Sqm | 1 | 8 | 24.1 | 1.35 |  | 260.28
|  | Sqm | 1 | 1 | 40.095 | 1.35 |  | 54.13
|  | Sqm | 1 | 1 | 47.845 | 1.35 |  | 64.59
| Honed 40mm at Canteen Podium (long) | Sqm | 1 | 2 | 47.847 | 1.35 |  | 129.19
Honed 40mm at Gym Podium
|  | Sqm | 1 | 1 | 15.265 | 1.35 |  | 20.61
|  | Sqm | 1 | 5 | 15.265 | 3 |  | 228.98
| deduct Chess Table | Sqm | -1 | 10 | 0.84 | 0.84 |  | -7.06
| deduct seat | Sqm | -1 | 40 | 0.345 | 0.345 |  | -4.76
| deduct Agra Red Sandstone Polished Finish | Sqm | -1 | 5 | 2.632 | 0.3 |  | -3.95
|  | Sqm | -1 | 20 | 0.55 | 0.3 |  | -3.3
|  | Sqm | -1 | 5 | 2 | 0.3 |  | -3
|  | Sqm | -1 | 5 | 4.633 | 0.3 |  | -6.95
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 728.76
Sqm
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
728.76
AGRA SANDSTONE- MACHINE CUT FINISH (PAVING BANDS, SEAT AND PLANTER WALL COPING AND CLADDING)
1.3 | Providing & Fixing Machine Cut Finish Agra Red stone machine 20MM THK.(Base rate Rs 550/Sqm) cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 20mm thk Machine Cut Finish Agra-Red Sand Stone (Base rate Rs 550/Sqm) (Planter Wall Cladding & seat Cladding)
Podium Stair Case Agra Red Sanstone 20mm Natural Finish
| Tread | Sqm | 1 | 43 | 5.9 | 0.325 |  | 82.45
| Riser | Sqm | 1 | 44 | 5.9 |  | 0.15 | 38.94
| Landing | Sqm | 1 | 3 | 5.9 | 2.72 |  | 48.14
0
20mm thk. Agra Natural Stone in Cladding of Podium Stair Case at Canteen
Cladding R.H.S. & L.H.S.
| 1st, 2nd & 3rd Flight | Sqm | 2 | 3 | 3.822 |  | 0.44 | 10.09
| 4th Flight | Sqm | 2 | 1 | 3.471 |  | 0.44 | 3.05
| 1st, 2nd, 3rd Landing | Sqm | 2 | 3 | 2.794 |  | 0.44 | 7.38
| Planter near Stiar case (long planter) canteen | Sqm | 1 | 1 | 22.08 |  | 0.5 | 11.04
|  | Sqm | 1 | 2 | 2.7 |  | 0.5 | 2.7
| front face | Sqm | 1 | 2 | 8 |  | 0.5 | 8
| cladding for Planter (5000x2000) attached to long planter | Sqm | 3 | 2 | 5 |  | 0.65 | 19.5
|  | Sqm | 3 | 1 | 2 |  | 0.65 | 3.9
| Planter seprate (5000x2000) at canteen Podium | Sqm | 2 | 2 | 5 |  | 0.65 | 13
|  | Sqm | 2 | 2 | 2 |  | 0.65 | 5.2
| Planter near pargola (long planter) Canteen | Sqm | 4 | 2 | 3 |  | 0.5 | 12
| cladding for Planter (5000x2000) | Sqm | 5 | 2 | 2 |  | 0.65 | 13
|  | Sqm | 2 | 1 | 5 |  | 0.65 | 6.5
|  | Sqm | 8 | 1 | 2 |  | 0.65 | 10.4
inner side clading strip of Planter
| long Planter near Staircase at canteen Podium. (22000x2700) | Sqm | 1 | 2 | 21.4 |  | 0.11 | 4.71
|  | Sqm | 1 | 2 | 2.24 |  | 0.11 | 0.49
| Planter inner side (5000x2000) | Sqm | 5 | 2 | 4.4 |  | 0.11 | 4.84
|  | Sqm | 5 | 2 | 1.4 |  | 0.11 | 1.54
| long Planter near pargola at canteen Podium. (22000x2700) | Sqm | 4 | 2 | 3 |  | 0.11 | 2.64
|  | Sqm | 4 | 2 | 2.4 |  | 0.11 | 2.11
| Planter inner side (5000x2000) | Sqm | 5 | 2 | 4.4 |  | 0.11 | 4.84
|  | Sqm | 5 | 2 | 1.4 |  | 0.11 | 1.54
20mm thk. Agra Polish finish for Seat Cladding
| Seat(1000x1000) Top Lvl. +0.65m | Sqm | 24 | 4 | 0.89 |  | 0.1 | 8.54
|  | Sqm | 24 | 4 | 0.99 |  | 0.335 | 31.84
Cladding of Planter at Gym Podium
| 20mm thk. Polish Agra at Long Planter near Pargola. | Sqm | 1 | 1 | 29.035 |  | 0.5 | 14.52
|  | Sqm | 1 | 3 | 3 |  | 0.5 | 4.5
|  | Sqm | 1 | 4 | 3 |  | 0.5 | 6
|  | Sqm | 1 | 1 | 4.035 |  | 0.5 | 2.02
Cladding for Planter (5000x2000)
| side face | Sqm | 5 | 2 | 2.633 |  | 0.65 | 17.11
| front face | Sqm | 5 | 1 | 2 |  | 0.65 | 6.5
| Cladding for Planter (2685x2300) | Sqm | 1 | 2 | 2.685 |  | 0.5 | 2.69
|  | Sqm | 1 | 2 | 2.3 |  | 0.5 | 2.3
| Cladding for Planter (2685x2200) | Sqm | 1 | 2 | 2.685 |  | 0.5 | 2.69
|  | Sqm | 1 | 2 | 2.2 |  | 0.5 | 2.2
| Cladding for Planter (2685x2600) | Sqm | 1 | 2 | 2.685 |  | 0.5 | 2.69
|  | Sqm | 1 | 2 | 2.6 |  | 0.5 | 2.6
| Cladding for Planter (2632x2000) | Sqm | 5 | 2 | 2.632 |  | 0.5 | 13.16
|  | Sqm | 5 | 2 | 2 |  | 0.5 | 10
Cladding for Cheess Table (1500x1500)
| base cladding on Brick work | Sqm | 10 | 4 | 0.9 |  | 0.6 | 21.6
| Cladding strip on table side | Sqm | 10 | 4 | 1.5 |  | 0.16 | 9.6
Cladding for Cheess Table Seat (500x500)
| Cladding for seat | Sqm | 40 | 4 | 0.5 |  | 0.335 | 26.8
|  | Sqm | 40 | 4 | 0.405 |  | 0.1 | 6.48
| inner Cladding Strip of Planter at Gym Podium | Sqm | 1 | 1 | 28.435 |  | 0.11 | 3.13
|  | Sqm | 1 | 2 | 2.4 |  | 0.11 | 0.53
|  | Sqm | 1 | 1 | 2.7 |  | 0.11 | 0.3
|  | Sqm | 1 | 4 | 3 |  | 0.11 | 1.32
| Cladding for Planter (2685x2300) | Sqm | 1 | 2 | 2.083 |  | 0.11 | 0.46
|  | Sqm | 1 | 2 | 1.7 |  | 0.11 | 0.37
| Cladding for Planter (2685x2200) | Sqm | 1 | 2 | 2.083 |  | 0.11 | 0.46
|  | Sqm | 1 | 2 | 1.6 |  | 0.11 | 0.35
| Cladding for Planter (2685x2600) | Sqm | 1 | 2 | 2.083 |  | 0.11 | 0.46
|  | Sqm | 1 | 2 | 2 |  | 0.11 | 0.44
| Cladding for Planter (2632x2000) | Sqm | 5 | 2 | 2.032 |  | 0.11 | 2.24
|  | Sqm | 5 | 2 | 1.4 |  | 0.11 | 1.54
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 523.44
| Podium Stair Case at Canteen Riser | Sqm | 1 | 3 | 5.9 |  | 0.15 | 2.66
Qty. Rewise due to calculation correction
| Planter near Stiar case (long planter) canteen | Sqm | -1 | 1 | 22.08 |  | 0.5 | -11.04
|  | Sqm | -1 | 2 | 2.7 |  | 0.5 | -2.7
| front face | Sqm | -1 | 2 | 8 |  | 0.5 | -8
| cladding for Planter (5000x2000) attached to long planter | Sqm | -3 | 2 | 5 |  | 0.65 | -19.5
|  | Sqm | -3 | 1 | 2 |  | 0.65 | -3.9
| Planter seprate (5000x2000) at canteen Podium | Sqm | -2 | 2 | 5 |  | 0.65 | -13
|  | Sqm | -2 | 2 | 2 |  | 0.65 | -5.2
| Planter near pargola (long planter) Canteen | Sqm | -4 | 2 | 3 |  | 0.5 | -12
| cladding for Planter (5000x2000) | Sqm | -5 | 2 | 2 |  | 0.65 | -13
|  | Sqm | -2 | 1 | 5 |  | 0.65 | -6.5
|  | Sqm | -8 | 1 | 2 |  | 0.65 | -10.4
inner side clading strip of Planter
| long Planter near Staircase at canteen Podium. (22000x2700) | Sqm | -1 | 2 | 21.4 |  | 0.11 | -4.71
|  | Sqm | -1 | 2 | 2.24 |  | 0.11 | -0.49
| Planter inner side (5000x2000) | Sqm | -5 | 2 | 4.4 |  | 0.11 | -4.84
|  | Sqm | -5 | 2 | 1.4 |  | 0.11 | -1.54
| long Planter near pargola at canteen Podium. (22000x2700) | Sqm | -4 | 2 | 3 |  | 0.11 | -2.64
|  | Sqm | -4 | 2 | 2.4 |  | 0.11 | -2.11
| Planter inner side (5000x2000) | Sqm | -5 | 2 | 4.4 |  | 0.11 | -4.84
|  | Sqm | -5 | 2 | 1.4 |  | 0.11 | -1.54
20mm thk. Agra Polish finish for Seat Cladding
| Seat(1000x1000) Top Lvl. +0.65m | Sqm | -24 | 4 | 0.89 |  | 0.1 | -8.54
|  | Sqm | -24 | 4 | 0.99 |  | 0.335 | -31.84
Cladding of Planter at Gym Podium
| 20mm thk. Polish Agra at Long Planter near Pargola. | Sqm | -1 | 1 | 29.035 |  | 0.5 | -14.52
|  | Sqm | -1 | 3 | 3 |  | 0.5 | -4.5
|  | Sqm | -1 | 4 | 3 |  | 0.5 | -6
|  | Sqm | -1 | 1 | 4.035 |  | 0.5 | -2.02
Cladding for Planter (5000x2000)
| side face | Sqm | -5 | 2 | 2.633 |  | 0.65 | -17.11
| front face | Sqm | -5 | 1 | 2 |  | 0.65 | -6.5
| Cladding for Planter (2685x2300) | Sqm | -1 | 2 | 2.685 |  | 0.5 | -2.69
|  | Sqm | -1 | 2 | 2.3 |  | 0.5 | -2.3
| Cladding for Planter (2685x2200) | Sqm | -1 | 2 | 2.685 |  | 0.5 | -2.69
|  | Sqm | -1 | 2 | 2.2 |  | 0.5 | -2.2
| Cladding for Planter (2685x2600) | Sqm | -1 | 2 | 2.685 |  | 0.5 | -2.69
|  | Sqm | -1 | 2 | 2.6 |  | 0.5 | -2.6
| Cladding for Planter (2632x2000) | Sqm | -5 | 2 | 2.632 |  | 0.5 | -13.16
|  | Sqm | -5 | 2 | 2 |  | 0.5 | -10
| inner Cladding Strip of Planter at Gym Podium | Sqm | -1 | 1 | 28.435 |  | 0.11 | -3.13
|  | Sqm | -1 | 2 | 2.4 |  | 0.11 | -0.53
|  | Sqm | -1 | 1 | 2.7 |  | 0.11 | -0.3
|  | Sqm | -1 | 4 | 3 |  | 0.11 | -1.32
| Cladding for Planter (2685x2300) | Sqm | -1 | 2 | 2.083 |  | 0.11 | -0.46
|  | Sqm | -1 | 2 | 1.7 |  | 0.11 | -0.37
| Cladding for Planter (2685x2200) | Sqm | -1 | 2 | 2.083 |  | 0.11 | -0.46
|  | Sqm | -1 | 2 | 1.6 |  | 0.11 | -0.35
| Cladding for Planter (2685x2600) | Sqm | -1 | 2 | 2.083 |  | 0.11 | -0.46
|  | Sqm | -1 | 2 | 2 |  | 0.11 | -0.44
| Cladding for Planter (2632x2000) | Sqm | -5 | 2 | 2.032 |  | 0.11 | -2.24
|  | Sqm | -5 | 2 | 1.4 |  | 0.11 | -1.54
| Planter near Stiar case (long planter) canteen | Sqm | 1 | 1 | 22.08 |  | 0.5 | 11.04
|  | Sqm | 1 | 2 | 2.74 |  | 0.5 | 2.74
| front face | Sqm | 1 | 2 | 8 |  | 0.5 | 8
| cladding for Planter (5000x2000) attached to long planter | Sqm | 3 | 2 | 5.08 |  | 0.65 | 19.81
|  | Sqm | 3 | 1 | 2.08 |  | 0.65 | 4.06
| Planter seprate (5000x2000) at canteen Podium | Sqm | 2 | 2 | 5.08 |  | 0.65 | 13.21
|  | Sqm | 2 | 2 | 2.08 |  | 0.65 | 5.41
| Planter near pargola (long planter) Canteen | Sqm | 4 | 2 | 3 |  | 0.5 | 12
| cladding for Planter (5000x2000) | Sqm | 5 | 2 | 2.08 |  | 0.65 | 13.52
|  | Sqm | 2 | 1 | 5.08 |  | 0.65 | 6.6
|  | Sqm | 8 | 1 | 2 |  | 0.65 | 10.4
inner side clading strip of Planter
| long Planter near Staircase at canteen Podium. (22000x2700) | Sqm | 1 | 2 | 21.54 |  | 0.11 | 4.74
|  | Sqm | 1 | 2 | 2.24 |  | 0.11 | 0.49
| Planter inner side (5000x2000) | Sqm | 5 | 2 | 4.54 |  | 0.11 | 4.99
|  | Sqm | 5 | 2 | 1.54 |  | 0.11 | 1.69
| long Planter near pargola at canteen Podium. (22000x2700) | Sqm | 4 | 2 | 3 |  | 0.11 | 2.64
|  | Sqm | 4 | 2 | 2.4 |  | 0.11 | 2.11
| Planter inner side (5000x2000) | Sqm | 5 | 2 | 4.54 |  | 0.11 | 4.99
|  | Sqm | 5 | 2 | 1.54 |  | 0.11 | 1.69
a.2 | 20mm thk. Agra Polish finish for Seat Cladding
| Seat(1000x1000) Top Lvl. +0.65m | Sqm | 24 | 4 | 0.89 |  | 0.1 | 8.54
|  | Sqm | 24 | 4 | 1 |  | 0.335 | 32.16
b | Cladding of Planter at Gym Podium
| 20mm thk. Polish Agra at Long Planter near Pargola. | Sqm | 1 | 1 | 29.115 |  | 0.5 | 14.56
|  | Sqm | 1 | 3 | 3.08 |  | 0.5 | 4.62
|  | Sqm | 1 | 4 | 3 |  | 0.5 | 6
|  | Sqm | 1 | 1 | 4.115 |  | 0.5 | 2.06
Cladding for Planter (5000x2000)
| side face | Sqm | 5 | 2 | 3.013 |  | 0.65 | 19.58
| front face | Sqm | 5 | 1 | 2.08 |  | 0.65 | 6.76
| Cladding for Planter (2685x2300) | Sqm | 1 | 2 | 2.765 |  | 0.5 | 2.77
|  | Sqm | 1 | 2 | 2.38 |  | 0.5 | 2.38
| Cladding for Planter (2685x2200) | Sqm | 1 | 2 | 2.765 |  | 0.5 | 2.77
|  | Sqm | 1 | 2 | 2.28 |  | 0.5 | 2.28
| Cladding for Planter (2685x2600) | Sqm | 1 | 2 | 2.765 |  | 0.5 | 2.77
|  | Sqm | 1 | 2 | 2.68 |  | 0.5 | 2.68
| Cladding for Planter (2632x2000) | Sqm | 5 | 2 | 2.712 |  | 0.5 | 13.56
|  | Sqm | 5 | 2 | 2.08 |  | 0.5 | 10.4
Cladding for Cheess Table (1500x1500)
| base cladding on Brick work | Sqm | 10 | 4 | 0.9 |  | 0.6 | 21.6
| Cladding strip on table side | Sqm | 10 | 4 | 1.5 |  | 0.15 | 9
Cladding for Cheess Table Seat (500x500)
| Cladding for seat | Sqm | 40 | 4 | 0.5 |  | 0.335 | 26.8
|  | Sqm | 40 | 4 | 0.405 |  | 0.1 | 6.48
| inner Cladding Strip of Planter at Gym Podium | Sqm | 1 | 1 | 28.575 |  | 0.11 | 3.14
|  | Sqm | 1 | 2 | 2.54 |  | 0.11 | 0.56
|  | Sqm | 1 | 1 | 2.77 |  | 0.11 | 0.3
|  | Sqm | 1 | 4 | 3 |  | 0.11 | 1.32
| Cladding for Planter (2685x2300) | Sqm | 1 | 2 | 2.225 |  | 0.11 | 0.49
|  | Sqm | 1 | 2 | 1.84 |  | 0.11 | 0.4
| Cladding for Planter (2685x2200) | Sqm | 1 | 2 | 2.225 |  | 0.11 | 0.49
|  | Sqm | 1 | 2 | 1.74 |  | 0.11 | 0.38
| Cladding for Planter (2685x2600) | Sqm | 1 | 2 | 2.225 |  | 0.11 | 0.49
|  | Sqm | 1 | 2 | 2.14 |  | 0.11 | 0.47
| Cladding for Planter (2632x2000) | Sqm | 5 | 2 | 2.172 |  | 0.11 | 2.39
|  | Sqm | 5 | 2 | 1.54 |  | 0.11 | 1.69
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 73.77 | 6th RA
597.21
1.3 | Providing & Fixing Machine Cut 40 mm thk. Finish Agra Red stone machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 40 mm thk. Machine cut Finish Agra Red Sand Stone (Base rate Rs 550/Sqm) (Flooring & Seat Coping)
Agra Red Sandstone Polished Finish M3 at Floor 40mm thk.
Agra Red Sandstone Polished Finish M3 at Floor 40mm thk.
| at Canteen Podium on Floor | Sqm | 1 | 4 | 24.1 | 0.3 |  | 28.92
|  | Sqm | 1 | 2 | 47.845 | 0.3 |  | 28.71
| at Gym Podium on Floor | Sqm | 0 | 1 | 2.759 | 0.3
|  | Sqm | 0 | 3 | 0.657 | 0.3
|  | Sqm | 0 | 1 | 2.154 | 0.3
|  | Sqm | 0 | 1 | 4.71 | 0.3
|  | Sqm | 5 | 1 | 15.26 | 0.3 |  | 22.89
| DEDUCT CHESS TABLE | Sqm | 10 | -1 | 1.53 | 0.3 |  | -4.59
Agra Red Sandstone Polished Finish M3 at Planter Coping Lvl. 40mm thk.
Coping at Planter & Seats at Canteen Podium
| Planter near stair case (long Planter) | Sqm | 1 | 1 | 22 | 0.33 |  | 7.26
|  | Sqm | 1 | 2 | 2.4 | 0.33 |  | 1.58
|  | Sqm | 1 | 2 | 8 | 0.33 |  | 5.28
| Planter (5000x2000)(attached with long planter) | Sqm | 5 | 2 | 5 | 0.33 |  | 16.5
|  | Sqm | 5 | 2 | 2 | 0.33 |  | 6.6
| long Planter near pargola top coping | Sqm | 4 | 2 | 3 | 0.33 |  | 7.92
| Planter (5000x2000)(attached with long planter) | Sqm | 5 | 2 | 5 | 0.33 |  | 16.5
|  | Sqm | 5 | 2 | 2 | 0.33 |  | 6.6
| Seprate Seat top (1000x1000) | Sqm | 24 | 1 | 1 | 1 |  | 24
Coping at Planter & Seats at Gym Podium
| coping top at long Planter | Sqm | 1 | 1 | 29.035 | 0.33 |  | 9.58
|  | Sqm | 1 | 2 | 2.4 | 0.33 |  | 1.58
|  | Sqm | 1 | 1 | 3 | 0.33 |  | 0.99
|  | Sqm | 1 | 4 | 3 | 0.33 |  | 3.96
|  | Sqm | 1 | 1 | 4.035 | 0.33 |  | 1.33
| Planter (5000x2000)(attached with long planter) | Sqm | 5 | 2 | 5 | 0.33 |  | 16.5
|  | Sqm | 5 | 2 | 1.4 | 0.33 |  | 4.62
| Planter (2685x2300) | Sqm | 1 | 2 | 2.685 | 0.33 |  | 1.77
|  | Sqm | 1 | 2 | 1.7 | 0.33 |  | 1.12
| Planter (2685x2200) | Sqm | 1 | 2 | 2.685 | 0.33 |  | 1.77
|  | Sqm | 1 | 2 | 1.6 | 0.33 |  | 1.06
| Planter (2685x2600) | Sqm | 1 | 2 | 2.685 | 0.33 |  | 1.77
|  | Sqm | 1 | 2 | 2 | 0.33 |  | 1.32
| Planter (2632x2000) | Sqm | 5 | 2 | 2.632 | 0.33 |  | 8.69
|  | Sqm | 5 | 2 | 1.4 | 0.33 |  | 4.62
| Chess Table Top (1500x1500) | Sqm | 10 | 1 | 1.5 | 1.5 |  | 22.5
| Chess table seat (500x500) | Sqm | 10 | 4 | 0.5 | 0.5 |  | 10
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 261.35
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
261.35
AGRA RED SANDSTONE- SERRATED FINISH (PAVING)
1.4 | Providing & Fixing Serrated Finish Agra Red stone (Base Rate Rs 750/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 20mm thk Machine Cut Finish Agra-Red Sand Stone (Base rate Rs 550/Sqm) (Planter Wall Cladding & seat Cladding)
|  | Sqm | 1 | 5 | 7.4 | 2 |  | 74
|  | Sqm | 1 | 2 | 4.7 | 2 |  | 18.8
|  | Sqm | 1 | 1 | 47.845 | 2 |  | 95.69
| Serrated Stone at Canteen Podium M4 | Sqm | 1 | 1 | 47.845 | 2 |  | 95.69
Serrated Stone at Gym Podium M4
| 0 | Sqm | 1 | 5 | 10.005 | 2 |  | 100.05
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 384.23
| 0 | Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
384.23
NATURAL FINISH KANDLA GREY SANDSTONE (LARGE PAVED AREA, SEATINGS)
2.1 | Providing & Fixing 40mm natural Finish Kandla Grey Sand Stone (Base Rate Rs 900/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls. 40mm thk. Natural Finish Kadappa for Paving
| Kandla Stone P/Fixing between BH-01 & BH-07 |  |  |  | Area
| Area-1, Kandla Stone 40mm between BH-01 & BH-07 & BH-04 | Sqm | 1 | 1 | 1384.1512 |  |  | 1384.15 |  | Area
| deduct Col. (1200x375) | Sqm | -1 | 3 | 1.2 | 0.375 |  | -1.35
| deduct Round Col. For Podium | Sqm | -1 | 13 | 0.28274 |  |  | -3.68 |  | Area
| deduct Green Planter (near BH-01 east corner) | Sqm | -1 | 1 | 20.8286 |  |  | -20.83 |  | Area
| deduct Green Planter east face of BH-04 | Sqm | -1 | 1 | 51.5194 |  |  | -51.52 |  | Area
|  | Sqm | -1 | 1 | 49.0177 |  |  | -49.02 |  | Area
| Area-2, Area east side of BH-01 (Kandla Grey Stone) | Sqm | 1 | 1 | 293.837 |  |  | 293.84 |  | Area
| deduct Green Planter | Sqm | -1 | 1 | 28.71 |  |  | -28.71 |  | Area
|  | Sqm | -1 | 1 | 23.2452 |  |  | -23.25 |  | Area
| Area-3, area east Canteen (under Podium stair case) | Sqm | 1 | 1 | 36.715 | 8.48 |  | 311.34
| deduct Col. (1200x375) | Sqm | -1 | 10 | 1.2 | 0.375 |  | -4.5
| Area-4, area between BH-01 & waterbody | Sqm | 1 | 1 | 48.075 | 6 |  | 288.45
| Area-5, area between Canteen & BH-02 | Sqm | 1 | 1 | 36.715 | 8.165 |  | 299.78 |  |  | 288.5991
| Area-6, area at junction of road BH-02 & waterdody planter east side | Sqm | 1 | 1 | 91.4752 |  |  | 91.48 |  | Area
| Area-7, between BH-02 & waterdody (south face of BH-02) | Sqm | 1 | 1 | 281.5771 |  |  | 281.58 |  | Area
| deduct green Area long planter | Sqm | -1 | 6 | 3.215 | 0.6 |  | -11.57
|  | Sqm | -1 | 1 | 3.52 | 0.6 |  | -2.11
|  | Sqm | -1 | 1 | 4.74 | 0.6 |  | -2.84
|  | Sqm | -1 | 1 | 6.265 | 0.6 |  | -3.76
|  | Sqm | -1 | 1 | 7.79 | 0.6 |  | -4.67
|  | Sqm | -1 | 1 | 9.315 | 0.6 |  | -5.59
| Area-8, surrounding of waterbody | Sqm | 1 | 1 | 26.42 | 27.98 |  | 739.23
| deduct waterbody area | Sqm | -1 | 1 | 346.36 |  |  | -346.36 |  | Area
| deduct seat | Sqm | -1 | 8 | 2.836 | 0.286 |  | -6.49
| deduct green planter | Sqm | -1 | 2 | 2.005 | 0.615 |  | -2.47
| Area-9, area between BH-04 & Waterbody (under transfer slab) | Sqm | 1 | 1 | 463.3387 |  |  | 463.34 |  | Area
| deduct green planter of BH-04 | Sqm | -1 | 1 | 1.8 | 0.955 |  | -1.72
|  | Sqm | -1 | 1 | 5.85 | 1.8 |  | -10.53
|  | Sqm | -1 | 1 | 5.025 | 1.8 |  | -9.05
| deduct ramp portion | Sqm | -1 | 1 | 3 | 3.77 |  | -11.31
|  | Sqm | -1 | 1 | 6 | 2 |  | -12
| deduct R.C.C. Wall/Col. | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
| deduct R.C.C. Planter | Sqm | -1 | 8 | 4.5 | 1 |  | -36
| deduct M2 Leather finish Cuuddapah | Sqm | -1 | 5 | 11.3 | 0.8 |  | -45.2
| deduct seat | Sqm | -1 | 7 | 2.836 | 0.286 |  | -5.68
| Area-10, area south side of BH-04 (back side) | Sqm | 1 | 1 | 233.8909 |  |  | 233.89 |  | Area
| Area-11, area West side of BH-04 & road south side of Basket ball ground | Sqm | 1 | 1 | 822.07 |  |  | 822.07 |  | Area
| deduct green planter area between BH-04 & BH-05 | Sqm | -1 | 1 | 66.3654 |  |  | -66.37 |  | Area
| deduct planter of basket ball ground | Sqm | -1 | 1 | 6.14 | 0.61 |  | -3.75
|  | Sqm | -1 | 1 | 4.105 | 0.61 |  | -2.5
12 | Area-12, area between Planter & basket ball ground | Sqm | 1 | 1 | 49.23 |  |  | 49.23 |  | Area
| deduct seat | Sqm | -1 | 2 | 2.836 | 0.286 |  | -1.62
| Area-13, area north side of Gym (J/8-9') | Sqm | 1 | 1 | 20 | 4.505 |  | 90.1
| deduct Col. (1200x375) | Sqm | -1 | 2 | 1.2 | 0.375 |  | -0.9
| Area-14, area between BH03 & Gym (8/H) | Sqm | 0 | 1 | 216.6046 |  |  |  |  | Area
| Area-15, area between basket ball green planter & Reception BH-04 green planter | Sqm | 1 | 1 | 323.7174 |  |  | 323.72 |  | Area
| deduct Green Planter south side of Green Planter | Sqm | -1 | 1 | 40.6096 |  |  | -40.61 |  | Area
| dedut Planter of basket ball ground | Sqm | -1 | 1 | 7.13 | 0.61 |  | -4.35
|  | Sqm | -1 | 1 | 6.3 | 0.615 |  | -3.87
|  | Sqm | -1 | 1 | 4.895 | 0.615 |  | -3.01
|  | Sqm | -1 | 1 | 3.495 | 0.615 |  | -2.15
| Area-16, area north side of reception & at Road juction near waterbody | Sqm | 1 | 1 | 166.1684 |  |  | 166.17 |  | Area
| deduct Green Planternorth side of reception | Sqm | -1 | 1 | 9.36 | 0.6 |  | -5.62 |  | Area
|  | Sqm | -1 | 1 | 8.14 | 0.6 |  | -4.88
|  | Sqm | -1 | 1 | 6.615 | 0.6 |  | -3.97
|  | Sqm | -1 | 1 | 4.785 | 0.6 |  | -2.87
|  | Sqm | -1 | 1 | 3.26 | 0.6 |  | -1.96
| green planter of Toilet | Sqm | -1 | 1 | 6.03 | 0.6 |  | -3.62
| Area-17, area between BH-03 & Reception & Toilet at road junction (east side of BH-03) | Sqm | 1 | 1 | 215.4023 |  |  | 215.4 |  | Area
| deduct Green Planter of Toilet | Sqm | -1 | 2 | 6.64 | 0.6 |  | -7.97
|  | Sqm | -1 | 1 | 5.725 | 0.6 |  | -3.44
Area-18, Kandla Grey Stone at entrance Step or ramp in Boy's Hostel
BH-01 entrance Step & Ramp
| Tread | Sqm | 1 | 3 | 5.42 | 1.42 |  | 23.09
| Riser | Sqm | 1 | 3 | 5.42 |  | 0.15 | 2.44
| Kandla stone in side ramp | Sqm | 1 | 1 | 16.0089 |  |  | 16.01 |  | Area
BH-02 entrance Step & Ramp
| Tread | Sqm | 1 | 3 | 5.42 | 1.42 |  | 23.09
| Riser | Sqm | 1 | 3 | 5.42 |  | 0.15 | 2.44
| Kandla stone in side ramp | Sqm | 1 | 1 | 16.0089 |  |  | 16.01 |  | Area
BH-03 entrance Step & Ramp
| Tread | Sqm | 1 | 3 | 5.42 | 1.42 |  | 23.09
| Riser | Sqm | 1 | 3 | 5.42 |  | 0.15 | 2.44
| Kandla stone in side ramp | Sqm | 1 | 1 | 16.0089 |  |  | 16.01 |  | Area
BH-04 entrance Step & Ramp
| Tread | Sqm | 1 | 3 | 5.42 | 1.42 |  | 23.09
| Riser | Sqm | 1 | 3 | 5.42 |  | 0.15 | 2.44
| Kandla stone in side ramp | Sqm | 1 | 1 | 16.0089 |  |  | 16.01 |  | Area
| Area-1, under BH-01 Transfer Slab | Sqm | 1 | 1 | 641.8989 |  |  | 641.9 |  | Area
| deduct R.C.C Planter under transefer slab | Sqm | -1 | 9 | 4.5 | 1 |  | -40.5
| deduct Green Planter | Sqm | -1 | 1 | 5.025 | 1.2 |  | -6.03
|  | Sqm | -1 | 1 | 5.845 | 1.2 |  | -7.01
| DEDUCT SHEAR WALL | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
| Area-2, north side of Canteen (outer side) | Sqm | 1 | 1 | 31.5 | 2.215 |  | 69.77
| DEDUCT COL. | Sqm | -1 | 4 | 1.2 | 0.375 |  | -1.8
| Area-3, north side of BH-02 (outer side) | Sqm | 1 | 1 | 294.0689 |  |  | 294.07 |  | Area
| DEDUCT PLANTER | Sqm | -1 | 1 | 61.387 |  |  | -61.39
| COL. | Sqm | -1 | 3 | 1.2 | 0.375 |  | -1.35
| ROUND COL. | Sqm | -1 | 4 | 0.283 |  |  | -1.13
| Area-4, kandla stone at Green Planter between BH-01 & Waterbody | Sqm | 1 | 1 | 348.7221 |  |  | 348.72 |  | Area
| deduct Green Planter | Sqm | -1 | 1 | 45.3694 |  |  | -45.37 |  | Area
|  | Sqm | -1 | 1 | 36.9316 |  |  | -36.93 |  | Area
| ROUND COL. | Sqm | -1 | 5 | 0.283 |  |  | -1.42
| GREEN PLANTER | Sqm | -1 | 1 | 128.263 |  |  | -128.26
| Area-5, area between Gym Toilet & BH-02 long planter | Sqm | 1 | 1 | 119.2318 |  |  | 119.23 |  | Area
| Area-6, area under Transfer Slab of Bh-02 between Gym | Sqm | 1 | 1 | 583.16 |  |  | 583.16 |  | Area
| deduct Green Planter | Sqm | -1 | 1 | 2.255 | 1.2 |  | -2.71
|  | Sqm | -1 | 1 | 5.85 | 1.2 |  | -7.02
|  | Sqm | -1 | 1 | 5.025 | 1.2 |  | -6.03 |  |  | 288.5991
|  | Sqm | -1 | 1 | 2.4 | 1.2 |  | -2.88
| deduct R.C.C Planter under transefer slab | Sqm | -1 | 8 | 4.5 | 1 |  | -36
| DEDUCT SHEAR WALL | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
| SINGLE SEAT | Sqm | -1 | 6 | 3 | 0.45 |  | -8.1
| Area-7, area east side of BH-03 & at road junction | Sqm | 1 | 1 | 208.5709 |  |  | 208.57 |  | Area
| Area-8, area between north side of BH-03 & south side of Gym | Sqm | 1 | 1 | 381.484 |  |  | 381.48 |  | Area
| Area-9, area between west side of Gym & north side of BH-03 | Sqm | 1 | 1 | 327.5105 |  |  | 327.51 |  | Area
| deduct Green Planter | Sqm | -1 | 1 | 84.391 |  |  | -84.39 |  | Area
| DEDUCT ROUND COL. | Sqm | -1 | 3 | 0.283 |  |  | -0.85
| COL. | Sqm | -1 | 5 | 1.2 | 0.375 |  | -2.25
| Area-10, area under Transfer Slab of BH-03 between basket ball ground | Sqm | 1 | 1 | 495.09 |  |  | 495.09 |  | Area
| deduct Green Planter | Sqm | -1 | 1 | 5.85 | 1.2 |  | -7.02
|  | Sqm | -1 | 1 | 5.025 | 1.2 |  | -6.03
| deduction for R.C.C. Wall | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
| deduct R.C.C Planter under transefer slab | Sqm | -1 | 8 | 4.5 | 1 |  | -36
| Area-11, Kandla Stone back side of Basket Ball Ground | Sqm | 1 | 1 | 15.12 | 1.2 |  | 18.14
Area-12, Kandla Stone on Entrace Ramp of BH-01, BH-02, BH-03, BH-04
|  | Sqm | 4 | 1 | 6 | 2 |  | 48
|  | Sqm | 4 | 1 | 11.12 |  |  | 44.48
| Stair trade | Sqm | 4 | 2 | 3 | 0.34 |  | 8.16
| Riser | Sqm | 4 | 3 | 3 | 0.15 |  | 5.4
| side cladding | Sqm | 4 | 2 | 6 |  | 0.25 | 12
|  | Sqm | 4 | 1 | 3.23 |  | 0.5 | 6.46
|  | Sqm | 4 | 1 | 0.6 |  | 0.5 | 1.2
|  | Sqm | 4 | 1 | 1.07 |  | 0.5 | 2.14
Kandla Sandstone Natural Finish 40mm thk. On Seat Top
Seprate Seat under BH-01 Transfer Slan
| Top face | Sqm | 6 | 1 | 3 | 0.45 |  | 8.1
Seprate Seat under BH-04 Transfer Slan
| Top face | Sqm | 7 | 1 | 3 | 0.45 |  | 9.45
Seprate Seat under BH-02 Transfer Slan
| Top face | Sqm | 6 | 1 | 3 | 0.45 |  | 8.1
Seprate Seat under BH-03 Transfer Slan
| Top face | Sqm | 4 | 1 | 3 | 0.45 |  | 5.4
Seat at Green Planter East side of BH-01
| Top face | Sqm | 4 | 1 | 3 | 0.45 |  | 5.4
Seat at Green Planter between BH-04 & BH-07
| Top face | Sqm | 8 | 1 | 3 | 0.45 |  | 10.8
Seat at Green Planter between BH-04 & BH-05
| Top face | Sqm | 4 | 1 | 3 | 0.45 |  | 5.4
Seat between waterbody & Reception
| Top face | Sqm | 8 | 1 | 3 | 0.45 |  | 10.8
Seat at Green Planter between BH-01 & Waterbody
| Top face | Sqm | 11 | 1 | 3 | 0.45 |  | 14.85
| DEDUCT MAIN HOLE QUANTITY | Sqm | -1 | 1 | 127.29 |  |  | -127.29
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 8299.48
Sqm
1 | Kanda Stone under Transfer Slab Parallel to green Planter or Wall of BH-01 | Sqm | 1 | 1 | 3.4975 |  |  | 3.5 |  | Area
| Kanda Stone Parallel to long green Planter or Wall of BH-01 towards face of waterbody | Sqm | 1 | 1 | 29.25 | 0.6 |  | 17.55
| Kanda Stone Parallel to long green Planter or Wall of BH-02 towards face of waterbody (south face waterbody) | Sqm | 1 | 1 | 29.85 | 0.6 |  | 17.91
| Kanda Stone Parallel to long green Planter or Wall of BH-04 towards face of BH-07 (west face) | Sqm | 1 | 1 | 30.13 | 0.3 |  | 9.04
|  | Sqm | 1 | 1 | 6.1 | 0.28 |  | 1.71
| Kandla Stone under Transer Slan BH-04 near Green Planter | Sqm | 1 | 1 | 15 | 0.6 |  | 9
|  | Sqm | 1 | 1 | 3.4974 |  |  | 3.5
| BH-04 green Planter East side (face basket ball ground) | Sqm | 1 | 1 | 8.7796 |  |  | 8.78
| BH-02 transfer slab near ramp | Sqm | 1 | 1 | 3.4977 |  |  | 3.5
| BH-03 transfer slab near ramp | Sqm | 1 | 1 | 3.4974 |  |  | 3.5
|  | Sqm | 1 | 1 | 9 |  |  | 9
| Kandl Stone side of BH-05 west face(towards BH-04) | Sqm | 1 | 1 | 8.0468 |  |  | 8.05
2 | Kandla Stone 40mm thk. For Seat
2.1 | Seat at Green Planter of Basket Ball Ground
| Top face | Sqm | 5 | 1 | 3 | 0.5 |  | 7.5
2.2 | Seat between waterbody & BH-02 long Planter
| Top face | Sqm | 11 | 1 | 3 | 0.5 |  | 16.5
2.3 | Seat at Green Planter BH-02 North face
| Top face | Sqm | 4 | 1 | 3 | 0.5 |  | 6
2.4 | Seat at Green Planter of Gym East side frontof BH-03
| Top face | Sqm | 8 | 1 | 3 | 0.5 |  | 12
Seat at Green Planter between BH-01 & Waterbody
| Top face | Sqm | 1 | 1 | 3 | 0.5 |  | 1.5
3 | Kandla Stone P/Fixing Rework after stone demolished by other agencies as per direction of Engineer in Charge (JMR attached)
3.1 | between BH-02 & BH-04 Canteen area (1.092x0.292) | Sqm | 1 | 215 | 1.092 | 0.292 |  | 68.56
3.2 | infront of Canteen | Sqm | 1 | 15 | 1.092 | 0.292 |  | 4.78
3.3 | BH-02 near Ramp | Sqm | 1 | 30 | 1.092 | 0.292 |  | 9.57
3.4 | BH-03 | Sqm | 1 | 15 | 1.092 | 0.292 |  | 4.78
3.5 | BH-01 | Sqm | 1 | 8 | 1.092 | 0.292 |  | 2.55
Kandla Sandstone Natural Finish 20mm thk. On Seat
a | Seprate Seat under BH-01 Transfer Slan
| Side Cladding | Sqm | 6 | 2 | 3 |  | 0.335 | 12.06
|  | Sqm | 6 | 2 | 2.91 |  | 0.1 | 3.49
|  | Sqm | 6 | 2 | 0.5 |  | 0.335 | 2.01
|  | Sqm | 6 | 2 | 0.41 |  | 0.1 | 0.49
b | Seprate Seat under BH-04 Transfer Slan
| Side Cladding | Sqm | 7 | 2 | 3 |  | 0.335 | 14.07
|  | Sqm | 7 | 2 | 2.91 |  | 0.1 | 4.07
|  | Sqm | 7 | 2 | 0.5 |  | 0.335 | 2.35
|  | Sqm | 7 | 2 | 0.41 |  | 0.1 | 0.57
c | Seprate Seat under BH-02 Transfer Slan
| Side Cladding | Sqm | 6 | 2 | 3 |  | 0.335 | 12.06
|  | Sqm | 6 | 2 | 2.91 |  | 0.1 | 3.49
|  | Sqm | 6 | 2 | 0.5 |  | 0.335 | 2.01
|  | Sqm | 6 | 2 | 0.41 |  | 0.1 | 0.49
d | Seprate Seat under BH-03 Transfer Slan
| Side Cladding | Sqm | 4 | 2 | 3 |  | 0.335 | 8.04
|  | Sqm | 4 | 2 | 2.91 |  | 0.1 | 2.33
|  | Sqm | 4 | 2 | 0.5 |  | 0.335 | 1.34
|  | Sqm | 4 | 2 | 0.41 |  | 0.1 | 0.33
e | Seprate Seat near basket ball ground
| Side Cladding | Sqm | 2 | 2 | 3 |  | 0.335 | 4.02
|  | Sqm | 2 | 2 | 2.91 |  | 0.1 | 1.16
|  | Sqm | 2 | 2 | 0.5 |  | 0.335 | 0.67
|  | Sqm | 2 | 2 | 0.41 |  | 0.1 | 0.16
f | Seprate Seat near Waterbody
| Side Cladding | Sqm | 8 | 2 | 3 |  | 0.335 | 16.08
|  | Sqm | 8 | 2 | 2.91 |  | 0.1 | 4.66
|  | Sqm | 8 | 2 | 0.5 |  | 0.335 | 2.68
|  | Sqm | 8 | 2 | 0.41 |  | 0.1 | 0.66
g | Seat at Green Planter East side of BH-01
| Side Cladding | Sqm | 4 | 2 | 3 |  | 0.335 | 8.04
|  | Sqm | 4 | 2 | 2.91 |  | 0.1 | 2.33
|  | Sqm | 4 | 2 | 0.5 |  | 0.335 | 1.34
|  | Sqm | 4 | 2 | 0.41 |  | 0.1 | 0.33
h | Seat at Green Planter between BH-04 & BH-07
| Side Cladding | Sqm | 8 | 2 | 3 |  | 0.335 | 16.08
|  | Sqm | 8 | 2 | 2.91 |  | 0.1 | 4.66
|  | Sqm | 8 | 2 | 0.5 |  | 0.335 | 2.68
|  | Sqm | 8 | 2 | 0.41 |  | 0.1 | 0.66
i | Seat at Green Planter between BH-04 & BH-05
| Side Cladding | Sqm | 4 | 2 | 3 |  | 0.335 | 8.04
|  | Sqm | 4 | 2 | 2.91 |  | 0.1 | 2.33
|  | Sqm | 4 | 2 | 0.5 |  | 0.335 | 1.34
|  | Sqm | 4 | 2 | 0.41 |  | 0.1 | 0.33
j | Seat at Green Planter of basket ball ground
| Side Cladding | Sqm | 3 | 2 | 3 |  | 0.335 | 6.03
|  | Sqm | 3 | 2 | 2.91 |  | 0.1 | 1.75
|  | Sqm | 3 | 2 | 0.5 |  | 0.335 | 1.01
|  | Sqm | 3 | 2 | 0.41 |  | 0.1 | 0.25
k | Seat at Green Planter south sid eof BH-02 (long planter) between BH-02 & Waterbody
| Side Cladding | Sqm | 11 | 2 | 3 |  | 0.335 | 22.11
|  | Sqm | 11 | 2 | 2.91 |  | 0.1 | 6.4
|  | Sqm | 11 | 2 | 0.5 |  | 0.335 | 3.69
|  | Sqm | 11 | 2 | 0.41 |  | 0.1 | 0.9
l | Seat at Green Planter north side of BH-02
| Side Cladding | Sqm | 4 | 2 | 3 |  | 0.335 | 8.04
|  | Sqm | 4 | 2 | 2.91 |  | 0.1 | 2.33
|  | Sqm | 4 | 2 | 0.5 |  | 0.335 | 1.34
|  | Sqm | 4 | 2 | 0.41 |  | 0.1 | 0.33
m | Seat at Green Planter between BH-01 & waterbody
| Side Cladding | Sqm | 12 | 2 | 3 |  | 0.335 | 24.12
|  | Sqm | 12 | 2 | 2.91 |  | 0.1 | 6.98
|  | Sqm | 12 | 2 | 0.5 |  | 0.335 | 4.02
|  | Sqm | 12 | 2 | 0.41 |  | 0.1 | 0.98
n | Seat at Green Planter west side of Gym
| Side Cladding | Sqm | 8 | 2 | 3 |  | 0.335 | 16.08
|  | Sqm | 8 | 2 | 2.91 |  | 0.1 | 4.66
|  | Sqm | 8 | 2 | 0.5 |  | 0.335 | 2.68
|  | Sqm | 8 | 2 | 0.41 |  | 0.1 | 0.66
Revise Qty. due to calculation Correction
| Area-4, kandla stone at Green Planter between BH-01 & Waterbody | Sqm | 1 | 0 | 348.7221 |  |  | 0
| deduct Green Planter | Sqm | -1 | 0 | 45.3694 |  |  | 0
|  | Sqm | -1 | 0 | 36.9316 |  |  | 0
| ROUND COL. | Sqm | 0 | -5 | 0.283
| GREEN PLANTER | Sqm | 1 | 1 | 128.263 |  |  | 128.26
| deduct Green Planter | Sqm | -1 |  | 45.3694 |  |  | -45.37
Kandla Sandstone Natural Finish 40mm thk. On Seat Top
Seprate Seat under BH-01 Transfer Slan
| Top face | Sqm | 6 | -1 | 3 | 0.45 |  | -8.1
Seprate Seat under BH-04 Transfer Slan
| Top face | Sqm | 7 | -1 | 3 | 0.45 |  | -9.45
Seprate Seat under BH-02 Transfer Slan
| Top face | Sqm | 6 | -1 | 3 | 0.45 |  | -8.1
Seprate Seat under BH-03 Transfer Slan
| Top face | Sqm | 4 | -1 | 3 | 0.45 |  | -5.4
Seat at Green Planter East side of BH-01
| Top face | Sqm | 4 | -1 | 3 | 0.45 |  | -5.4
Seat at Green Planter between BH-04 & BH-07
| Top face | Sqm | 8 | -1 | 3 | 0.45 |  | -10.8
Seat at Green Planter between BH-04 & BH-05
| Top face | Sqm | 4 | -1 | 3 | 0.45 |  | -5.4
Seat between waterbody & Reception
| Top face | Sqm | 8 | -1 | 3 | 0.45 |  | -10.8
Seat at Green Planter between BH-01 & Waterbody
| Top face | Sqm | 11 | -1 | 3 | 0.45 |  | -14.85
Kandla Sandstone Natural Finish 40mm thk. On Seat Top
Seprate Seat under BH-01 Transfer Slan
| Top face | Sqm | 6 | 1 | 3 | 0.5 |  | 9
Seprate Seat under BH-04 Transfer Slan
| Top face | Sqm | 7 | 1 | 3 | 0.5 |  | 10.5
Seprate Seat under BH-02 Transfer Slan
| Top face | Sqm | 6 | 1 | 3 | 0.5 |  | 9
Seprate Seat under BH-03 Transfer Slan
| Top face | Sqm | 4 | 1 | 3 | 0.5 |  | 6
Seat at Green Planter East side of BH-01
| Top face | Sqm | 4 | 1 | 3 | 0.5 |  | 6
Seat at Green Planter between BH-04 & BH-07
| Top face | Sqm | 8 | 1 | 3 | 0.5 |  | 12
Seat at Green Planter between BH-04 & BH-05
| Top face | Sqm | 4 | 1 | 3 | 0.5 |  | 6
Seat between waterbody & Reception
| Top face | Sqm | 8 | 1 | 3 | 0.5 |  | 12
Seat at Green Planter between BH-01 & Waterbody
| Top face | Sqm | 11 | 1 | 3 | 0.5 |  | 16.5
Sqm
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 582.18 | 6th RA
8881.66
2.2 | Providing & Fixing 40mm Leather Finish Kadappa Stone (Base Rate Rs 2000/Sqm) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels.
Leather Finish Kadappa Stone under BH-01 Transfer Slab
|  | Sqm | 1 | 2 | 8.3 | 0.8 |  | 13.28
|  | Sqm | 1 | 3 | 11.3 | 0.8 |  | 27.12
Leather Finish Kadappa Stone under BH-04 Transfer Slab
|  | Sqm | 1 | 2 | 8.3 | 0.8 |  | 13.28
|  | Sqm | 1 | 3 | 11.3 | 0.8 |  | 27.12
Leather Finish Kadappa Stone under BH-02 Transfer Slab
|  | Sqm | 1 | 2 | 8.3 | 0.8 |  | 13.28
|  | Sqm | 1 | 3 | 11.3 | 0.8 |  | 27.12
Leather Finish Kadappa Stone under BH-03 Transfer Slab
|  | Sqm | 1 | 2 | 8.3 | 0.8 |  | 13.28
|  | Sqm | 1 | 3 | 11.3 | 0.8 |  | 27.12
| UP TO PREVIOUS BILL | Sqm. | [6 empty] | 161.6
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
161.6
2.3 | Providing & Fixing 40mm Polished Kadappa Stone prepolished, machine cut of required size, ne cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels.40mm thk. Polished finish Kadappa Stone (Base rate Rs 1750/Sqm) (Seater Coping)
| 40mm thk. Kadappa Polish at Waterbody Coping (top seat Lvl. +0.5m) inner Dia. =20.12m, Outer dia.=21.2m) (Avrg. Dia.=20.66m) | Sqm | 1 | 1 | 63.209 | 0.58 |  | 36.66
| UP TO PREVIOUS BILL | Sqm. | [6 empty] | 36.66
Qty. Rewise due to calculation correction
| 40mm thk. Kadappa Polish at Waterbody Coping (top seat Lvl. +0.5m) inner Dia. =20.12m, Outer dia.=21.2m) (Avrg. Dia.=20.66m) | Sqm | -1 | 1 | 63.209 | 0.58 |  | -36.66
| actual Qty. | Sqm | 1 | 1 | 64.8724 | 0.58 |  | 37.63
| THIS BILL TOTAL → | Sqm | [6 empty] | 0.97 | 6th RA
37.63
2.3 | Providing & Fixing 20mm Polished Finish Kadappa Stone prepolished, machine cut of required size, ne cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all levels.
| 20mm thk. Kadappa Polish in Waterbody Dia. =20.12m | Sqm | 1 | 1 | 317.7793 |  |  | 317.78
| inner side cladding waterbody | Sqm | 1 | 1 | 63.1768 |  | 0.71 | 44.86
| outer cladding (D=20.12+0.5*2+0.04*2=21.2m) | Sqm | 1 | 1 | 66.568 |  | 0.41 | 27.29
| UP TO PREVIOUS BILL | Sqm. | [6 empty] | 389.93
Sqm
| 20mm thk. Kadappa Polish in waterboy Podium Coumn Cladding (dia.1.2m) | Sqm | 2 | 1 | 3.768 |  | 0.7 | 5.28
| top coping | Sqm | 2 | 1 | 1.1304 |  |  | 2.26 |  | Area
| deduct Col. | Sqm | -1 | 2 | 0.2826 |  |  | -0.57 |  | Area
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 6.97 | 6th RA
396.9
2.5 | Providing & Fixing in Position 40mm thk stone cover of size 600mm x 600mm as per design for catch basin fixed on Precast concrete with M.S. angle.
1 | 740x740 (inner size) | Sqm | 97 | 1 | 0.89 | 0.89 |  | 76.83
2 | 610x610 | Sqm | 27 | 1 | 0.76 | 0.76 |  | 15.6
3 | 500x460 | Sqm | 21 | 1 | 0.65 | 0.6 |  | 8.19
4 | 900x800 | Sqm | 6 | 1 | 1.05 | 0.95 |  | 5.99
5 | 315x315 | Sqm | 34 | 1 | 0.465 | 0.465 |  | 7.35
6 | 800x900 | Sqm | 3 | 1 | 0.95 | 1.05 |  | 2.99
7 | 880x870 | Sqm | 1 | 1 | 1.03 | 1.02 |  | 1.05
8 | 800x800 | Sqm | 1 | 1 | 0.95 | 0.95 |  | 0.9
9 | 400x500 | Sqm | 5 | 1 | 0.55 | 0.65 |  | 1.79
10 | 430x470 | Sqm | 7 | 1 | 0.58 | 0.62 |  | 2.52
11 | 430x430 | Sqm | 4 | 1 | 0.58 | 0.58 |  | 1.35
12 | 570x570 | Sqm | 1 | 1 | 0.72 | 0.72 |  | 0.52
13 | 900x900 | Sqm | 2 | 1 | 1.05 | 1.05 |  | 2.21
| UP TO PREVIOUS BILL | Sqm. | [6 empty] | 127.29
Sqm
1 | 900x800 | Sqm | 5 | 1 | 1.05 | 0.95 |  | 4.99
2 | 600x600 | Sqm | 2 | 1 | 0.75 | 0.75 |  | 1.13
3 | 950x950 | Sqm | 5 | 1 | 1.1 | 1.1 |  | 6.05
4 | 1100x1100 | Sqm | 1 | 1 | 1.25 | 1.25 |  | 1.56
5 | 750x750 | Sqm | 2 | 1 | 0.9 | 0.9 |  | 1.62
6 | 550x550 | Sqm | 3 | 1 | 0.7 | 0.7 |  | 1.47
7 | 1000x1000 | Sqm | 1 | 1 | 1.15 | 1.15 |  | 1.32
8 | 870x880 | Sqm | 1 | 1 | 1.02 | 1.03 |  | 1.05
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 19.19 | 6th RA
146.48
2.5 | 12mm cement plaster in cement mortar 1:4 on wall etc. with all scaffolding
| Plater work in Waterbody Sump (900x900) | Sqm | 5 | 4 | 0.9 |  | 0.85 | 15.3
| Filterpit (2000x2000x1800) | Sqm | 1 | 4 | 2 |  | 0.8 | 6.4
Plaster work at end of Planter in Green Area
| Planter east side of BH-01 | Sqm | 1 | 1 | 39.733 |  | 0.15 | 5.96
|  | Sqm | 1 | 1 | 51.813 |  | 0.15 | 7.77
|  | Sqm | 1 | 1 | 47.55 |  | 0.15 | 7.13
| Planter between BH-04 & BH-07 | Sqm | 1 | 1 | 90.64 |  | 0.15 | 13.6
|  | Sqm | 1 | 1 | 96.915 |  | 0.15 | 14.54
| Planter beteen BH-01 & Waterbody | Sqm | 1 | 1 | 93.018 |  | 0.15 | 13.95
|  | Sqm | 1 | 1 | 77.105 |  | 0.15 | 11.57
|  | Sqm | 1 | 1 | 80.889 |  | 0.15 | 12.13
| Planter between BH-04 & BH-05 | Sqm | 1 | 1 | 112.946 |  | 0.15 | 16.94
| Planter back side of Reception | Sqm | 1 | 1 | 85.967 |  | 0.15 | 12.9
| Planter front side of Reception | Sqm | 1 | 2 | 9.36 |  | 0.15 | 2.81
|  | Sqm | 1 | 2 | 8.14 |  | 0.15 | 2.44
|  | Sqm | 1 | 2 | 6.615 |  | 0.15 | 1.98
|  | Sqm | 1 | 2 | 4.785 |  | 0.15 | 1.44
|  | Sqm | 1 | 2 | 3.26 |  | 0.15 | 0.98
|  | Sqm | 5 | 2 | 0.6 |  | 0.15 | 0.9
| Planter front of Gym Toilet | Sqm | 1 | 2 | 6.03 |  | 0.15 | 1.81
|  | Sqm | 2 | 2 | 6.64 |  | 0.15 | 3.98
|  | Sqm | 1 | 2 | 5.725 |  | 0.15 | 1.72
|  | Sqm | 1 | 2 | 3.59 |  | 0.15 | 1.08
| PLANTER EDGE PLASTER NOT PAYBLE | Sqm | -1 |  | 135.63 |  |  | -135.63
| UP TO PREVIOUS BILL | Sqm. | [6 empty] | 21.7
Sqm
Plaster work at end of Planter in Green Area
| Planter east side of BH-01 | Sqm | 1 | 1 | 39.733 |  | 0.15 | 5.96
|  | Sqm | 1 | 1 | 51.813 |  | 0.15 | 7.77
|  | Sqm | 1 | 1 | 47.55 |  | 0.15 | 7.13
| Planter between BH-04 & BH-07 | Sqm | 1 | 1 | 90.64 |  | 0.15 | 13.6
|  | Sqm | 1 | 1 | 96.915 |  | 0.15 | 14.54
| Planter beteen BH-01 & Waterbody | Sqm | 1 | 1 | 93.018 |  | 0.15 | 13.95
|  | Sqm | 1 | 1 | 77.105 |  | 0.15 | 11.57
|  | Sqm | 1 | 1 | 80.889 |  | 0.15 | 12.13
| Planter between BH-04 & BH-05 | Sqm | 1 | 1 | 112.946 |  | 0.15 | 16.94
| Planter back side of Reception | Sqm | 1 | 1 | 85.967 |  | 0.15 | 12.9
| Planter front side of Reception | Sqm | 1 | 2 | 9.36 |  | 0.15 | 2.81
|  | Sqm | 1 | 2 | 8.14 |  | 0.15 | 2.44
|  | Sqm | 1 | 2 | 6.615 |  | 0.15 | 1.98
|  | Sqm | 1 | 2 | 4.785 |  | 0.15 | 1.44
|  | Sqm | 1 | 2 | 3.26 |  | 0.15 | 0.98
|  | Sqm | 5 | 2 | 0.6 |  | 0.15 | 0.9
| Planter front of Gym Toilet | Sqm | 1 | 2 | 6.03 |  | 0.15 | 1.81
|  | Sqm | 2 | 2 | 6.64 |  | 0.15 | 3.98
|  | Sqm | 1 | 2 | 5.725 |  | 0.15 | 1.72
|  | Sqm | 1 | 2 | 3.59 |  | 0.15 | 1.08
|  | Sqm | -1 | 1 | 135.63 |  |  | -135.63 |  | NEED TO DISCUSS
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
21.7
NON-SCHEDULED ITEMS
NS-01 | Excavation in all types of soil (Poclanable)for footings of columns, Retaining walls, Core walls, catch pits, Lift pits trenches for drains, etc., by mechanical means upto 2 m depth (Using JCB,Poclane etc.,)including levelling, dressing the edges, with all leads and lifts including back filling in layers of 150mm with watering and compaction. Rate to include disposing the excess earth and spreading in layers to the required
| Planter BH-01 NORTH SIDE (EXECAVATION) | Cum | 1 |  | 11.91 | 0.61 | 0.823 | 5.98
| G 32-37/1-5 vertical | Cum | 2 |  | 9.3 | 0.61 | 0.823 | 9.34 |  | Avrege Depth 0.830
|  | Cum | 1 |  | 10.54 | 0.61 | 0.823 | 5.29
|  | Cum | 2 |  | 6.9 | 0.61 | 0.823 | 6.93
|  | Cum | 1 |  | 6.6 | 0.61 | 0.823 | 3.31
|  | Cum | 1 |  | 7.21 | 0.61 | 0.823 | 3.62
|  | Cum | 1 |  | 5.04 | 0.61 | 0.823 | 2.53
|  | Cum | 1 |  | 7.65 | 0.61 | 0.823 | 3.84
| G 32-37/1-5 horizontal | Cum | 5 |  | 0.615 | 0.61 | 0.823 | 1.54
|  | Cum | 1 |  | 3.36 | 0.61 | 0.823 | 1.69
|  | Cum | 4 |  | 0.91 | 0.61 | 0.823 | 1.83
|  | Cum | 3 |  | 2.145 | 0.61 | 0.823 | 3.23
| BH01-NORTH SIDE | Cum | 1 |  | 6.75 | 0.61 | 0.823 | 3.39
| Bet G 31-28 /1-5 vertical | Cum | 1 |  | 4.75 | 0.61 | 0.823 | 2.38
|  | Cum | 2 |  | 2.33 | 0.61 | 0.823 | 2.34
|  | Cum | 2 |  | 3.55 | 0.61 | 0.823 | 3.56
|  | Cum | 1 |  | 2.04 | 0.61 | 0.823 | 1.02
|  | Cum | 1 |  | 4.65 | 0.61 | 0.823 | 2.33
| Bet. G 31-28/1-5 horizontal | Cum | 5 |  | 0.615 | 0.61 | 0.823 | 1.54
|  | Cum | 3 |  | 2.155 | 0.61 | 0.823 | 3.25
|  | Cum | 3 |  | 0.91 | 0.61 | 0.823 | 1.37
| BH-02 EAST SIDE BET G 20-28/1-6 VERTICAL | Cum | 1 |  | 10.375 | 0.61 | 0.823 | 5.21
|  | Cum | 2 |  | 7.625 | 0.61 | 0.823 | 7.66
|  | Cum | 1 |  | 8.235 | 0.61 | 0.823 | 4.13
|  | Cum | 1 |  | 4.25 | 0.61 | 0.823 | 2.13
|  | Cum | 1 |  | 4.86 | 0.61 | 0.823 | 2.44
|  | Cum | 2 |  | 4.575 | 0.61 | 0.823 | 4.59
|  | Cum | 1 |  | 3.935 | 0.61 | 0.823 | 1.98
|  | Cum | 1 |  | 4.545 | 0.61 | 0.823 | 2.28
|  | Cum | 1 |  | 3.02 | 0.61 | 0.823 | 1.52
|  | Cum | 1 |  | 3.01 | 0.61 | 0.823 | 1.51
|  | Cum | 2 |  | 1.485 | 0.61 | 0.823 | 1.49
|  | Cum | 1 |  | 3.33 | 0.61 | 0.823 | 1.67
| BH-02 EAST SIDE BET G 20-28/1-6 Horizontal | Cum | 5 |  | 0.6 | 0.61 | 0.823 | 1.51
|  | Cum | 6 |  | 0.78 | 0.61 | 0.823 | 2.35
|  | Cum | 1 |  | 3.205 | 0.61 | 0.823 | 1.61
|  | Cum | 4 |  | 1.99 | 0.61 | 0.823 | 4
|  | Cum | 1 |  | 2.6 | 0.61 | 0.823 | 1.31
|  | Cum | 1 |  | 3.2 | 0.61 | 0.823 | 1.61
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 10.02 | 0.61 | 0.823 | 5.03
| BET.G 17-21/20-25 | Cum | 1 |  | 8.22 | 0.61 | 0.823 | 4.13
|  | Cum | 1 |  | 9.22 | 0.61 | 0.823 | 4.63
|  | Cum | 1 |  | 8.61 | 0.61 | 0.823 | 4.32
|  | Cum | 2 |  | 8.22 | 0.61 | 0.823 | 8.25
|  | Cum | 1 |  | 5.72 | 0.61 | 0.823 | 2.87
|  | Cum | 2 |  | 5.11 | 0.61 | 0.823 | 5.13
|  | Cum | 1 |  | 8.72 | 0.61 | 0.823 | 4.38
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Cum | 8 |  | 0.615 | 0.61 | 0.823 | 2.47
| BET.G 17-21/20-25 | Cum | 2 |  | 1.225 | 0.61 | 0.823 | 1.23
|  | Cum | 2 |  | 2.13 | 0.61 | 0.823 | 2.14
|  | Cum | 4 |  | 0.91 | 0.61 | 0.823 | 1.83
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 9.22 | 0.61 | 0.823 | 4.63
| BET.G 17-21/25-29 | Cum | 1 |  | 6.81 | 0.61 | 0.823 | 3.42
|  | Cum | 2 |  | 7.42 | 0.61 | 0.823 | 7.45
|  | Cum | 2 |  | 8.42 | 0.61 | 0.823 | 8.45
|  | Cum | 2 |  | 9.22 | 0.61 | 0.823 | 9.26
| PLANTER BET -01 AND WATER BODY Horizontal | Cum | 6 |  | 0.615 | 0.61 | 0.823 | 1.85
| BET.G 17-21/25-29 | Cum | 2 |  | 2.135 | 0.61 | 0.823 | 2.14
|  | Cum | 4 |  | 0.91 | 0.61 | 0.823 | 1.83
| PLANTER BET -01 AND WATER BODY VERTICAL | Cum | 1 |  | 8 | 0.61 | 0.823 | 4.02
| BET.G 17-21/29-35 | Cum | 1 |  | 5.61 | 0.61 | 0.823 | 2.82
|  | Cum | 1 |  | 4.61 | 0.61 | 0.823 | 2.31
|  | Cum | 2 |  | 5.22 | 0.61 | 0.823 | 5.24
|  | Cum | 3 |  | 3.61 | 0.61 | 0.823 | 5.44
|  | Cum | 1 |  | 5.61 | 0.61 | 0.823 | 2.82
|  | Cum | 1 |  | 4.42 | 0.61 | 0.823 | 2.22
|  | Cum | 1 |  | 6.02 | 0.61 | 0.823 | 3.02
| PLANTER BET -01 AND WATER BODY Horizontal | Cum | 5 |  | 0.615 | 0.61 | 0.823 | 1.54
| BET.G 17-21/29-35 | Cum | 3 |  | 3.36 | 0.61 | 0.823 | 5.06
|  | Cum | 6 |  | 0.91 | 0.61 | 0.823 | 2.74
|  | Cum | 1 |  | 2.135 | 0.61 | 0.823 | 1.07
| PLANTER BET -04 AND BH-05 VERTICAL | Cum | 1 |  | 11.9 | 0.61 | 0.823 | 5.97
| BET.G 32-36/39-47 | Cum | 1 |  | 7.79 | 0.61 | 0.823 | 3.91
|  | Cum | 2 |  | 6.59 | 0.61 | 0.823 | 6.62
|  | Cum | 2 |  | 5.69 | 0.61 | 0.823 | 5.71
|  | Cum | 2 |  | 4.79 | 0.61 | 0.823 | 4.81
|  | Cum | 2 |  | 2.99 | 0.61 | 0.823 | 3
|  | Cum | 2 |  | 5.09 | 0.61 | 0.823 | 5.11
|  | Cum | 2 |  | 2.99 | 0.61 | 0.823 | 3
|  | Cum | 1 |  | 2.09 | 0.61 | 0.823 | 1.05
|  | Cum | 1 |  | 4.7 | 0.61 | 0.823 | 2.36
| PLANTER BET -04 AND BH-05 VERTICAL | Cum | 3 |  | 0.615 | 0.61 | 0.823 | 0.93
| BET.G 32-36/39-47 | Cum | 1 |  | 2.135 | 0.61 | 0.823 | 1.07
|  | Cum | 7 |  | 0.91 | 0.61 | 0.823 | 3.2
|  | Cum | 6 |  | 3.36 | 0.61 | 0.823 | 10.12
| PLANTER NEAR ZYM Vertical | Cum | 1 |  | 8.62 | 0.61 | 0.823 | 4.33
| BET.G 2-11/48-52 | Cum | 1 |  | 6.01 | 0.61 | 0.823 | 3.02
|  | Cum | 2 |  | 6.61 | 0.61 | 0.823 | 6.64
|  | Cum | 2 |  | 5.41 | 0.61 | 0.823 | 5.43
|  | Cum | 2 |  | 7.22 | 0.61 | 0.823 | 7.25
|  | Cum | 2 |  | 4.81 | 0.61 | 0.823 | 4.83
|  | Cum | 2 |  | 5.41 | 0.61 | 0.823 | 5.43
|  | Cum | 2 |  | 4.81 | 0.61 | 0.823 | 4.83
|  | Cum | 1 |  | 7.22 | 0.61 | 0.823 | 3.62
|  | Cum | 2 |  | 6.61 | 0.61 | 0.823 | 6.64
|  | Cum | 1 |  | 9.22 | 0.61 | 0.823 | 4.63
| PLANTER NEAR ZYM Horizontal | Cum | 6 |  | 0.615 | 0.61 | 0.823 | 1.85
| BET.G 2-11/48-52 | Cum | 6 |  | 0.91 | 0.61 | 0.823 | 2.74
|  | Cum | 3 |  | 3.36 | 0.61 | 0.823 | 5.06
|  | Cum | 2 |  | 2.135 | 0.61 | 0.823 | 2.14
|  | Cum | 2 |  | 1.83 | 0.61 | 0.15 | 0.33
|  | Cum | 3 |  | 0.605 | 0.61 | 0.823 | 0.91
| PLANTER BET. BH-04 AND BH-07 Vertical | Cum | 1 |  | 10.88 | 0.61 | 0.823 | 5.46
| BET.G 13-18/48-52 | Cum | 1 |  | 6.27 | 0.61 | 0.823 | 3.15
|  | Cum | 2 |  | 8.77 | 0.61 | 0.823 | 8.81
|  | Cum | 2 |  | 6.77 | 0.61 | 0.823 | 6.8
|  | Cum | 1 |  | 8.77 | 0.61 | 0.823 | 4.4
|  | Cum | 1 |  | 11.38 | 0.61 | 0.823 | 5.71
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 2 |  | 0.615 | 0.61 | 0.823 | 0.62
| BET.G 13-18/48-52 | Cum | 3 |  | 3.36 | 0.61 | 0.823 | 5.06
|  | Cum | 3 |  | 0.91 | 0.61 | 0.823 | 1.37
| PLANTER BET. BH-04 AND BH-07 Horizontal | Cum | 7 |  | 0.615 | 0.61 | 0.823 | 2.16
| BET.G 13-18/48-42 | Cum | 2 |  | 2.13 | 0.61 | 0.823 | 2.14
|  | Cum | 6 |  | 0.91 | 0.61 | 0.823 | 2.74
|  | Cum | 1 |  | 0.3 | 0.61 | 0.823 | 0.15
|  | Cum | 1 |  | 3.36 | 0.61 | 0.823 | 1.69
| PLANTER BET. BH-04 AND BH-07 VERTICAL | Cum | 1 |  | 10.58 | 0.61 | 0.823 | 5.31
| BET.G 13-18/48-42 | Cum | 1 |  | 6.58 | 0.61 | 0.823 | 3.3
|  | Cum | 1 |  | 6.77 | 0.61 | 0.823 | 3.4
|  | Cum | 1 |  | 7.38 | 0.61 | 0.823 | 3.7
|  | Cum | 2 |  | 4.97 | 0.61 | 0.823 | 4.99
|  | Cum | 2 |  | 5.28 | 0.61 | 0.823 | 5.3
|  | Cum | 1 |  | 4.67 | 0.61 | 0.823 | 2.34
|  | Cum | 1 |  | 5.28 | 0.61 | 0.823 | 2.65
|  | Cum | 1 |  | 2.81 | 0.61 | 0.823 | 1.41
|  | Cum | 1 |  | 5.42 | 0.61 | 0.823 | 2.72
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL HORIZONTAL | Cum |  |  |  |  | 0.823
| BET.G 35-41/42-48 | Cum | 1 |  | 19.52 | 0.61 | 0.823 | 9.8
|  | Cum | 1 |  | 2.09 | 0.61 | 0.823 | 1.05
|  | Cum | 6 |  | 1.835 | 0.61 | 0.823 | 5.53
|  | Cum | 4 |  | 1.215 | 0.61 | 0.823 | 2.44
|  | Cum | 1 |  | 0.91 | 0.61 | 0.823 | 0.46
|  | Cum | 1 |  | 1.145 | 0.61 | 0.823 | 0.57
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL VERTICAL | Cum |  |  |  |  | 0.823
| BET.G 35-41/42-48 | Cum | 2 |  | 2 | 0.61 | 0.823 | 2.01
|  | Cum | 2 |  | 3 | 0.61 | 0.823 | 3.01
|  | Cum | 2 |  | 4.645 | 0.61 | 0.823 | 4.66
|  | Cum | 2 |  | 6.12 | 0.61 | 0.823 | 6.14
|  | Cum | 2 |  | 6.95 | 0.61 | 0.823 | 6.98
|  | Cum | 2 |  | 6.38 | 0.61 | 0.823 | 6.41
|  | Cum | 2 |  | 5.345 | 0.61 | 0.823 | 5.37
| BASKET BALL LONG WALL | Cum | 2 |  | 28.37 | 0.61 | 0.823 | 28.49
| BASKET WALL SHORT WALL | Cum | 2 |  | 14.19 | 0.61 | 0.823 | 14.25
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 34.935 | 0.61 | 0.83 | 17.69
| FIRE TENDER TOE WALL WITH BH-05 | Cum | 1 |  | 15 | 0.61 | 0.83 | 7.59
| FIRE TENDER TOE WALL WITH BH-01 | Cum | 1 |  | 31.4 | 0.61 | 0.83 | 15.9
| FIRE TENDER TOE WALL WITH BH-07 | Cum | 1 |  | 42.55 | 0.61 | 0.15 | 3.89
| TOE WALL BH-04 FOR GREEN | Cum | 2 |  | 31.44 | 0.61 | 0.83 | 31.84
| BH-04 RCC PLANTER | Cum | 6 |  | 5 | 1.25 | 0.83 | 31.13
|  | Cum | 2 |  | 5 | 1.5 | 0.83 | 12.45
| BH-03 RCC PLANTER | Cum | 6 |  | 5 | 1.25 | 0.83 | 31.13
|  | Cum | 2 |  | 5 | 1.5 | 0.83 | 12.45
Earth Excavation for Planter (2-6/28'-31')
| (28'/2-3) | Cum | 1 | 1 | 4.65 | 0.61 | 0.823 | 2.33 |  | 2.4348
0
|  | Cum | 1 | 1 | 2.04 | 0.61 | 0.823 | 1.02 |  | 1.0241
| (29'/2-3) | Cum | 0 | 1 | 2.61 | 0.61 | 0.823 |  |  | 1.3103
|  | Cum | 1 | 1 | 2.04 | 0.61 | 0.823 | 1.02 |  | 1.0241
|  | Cum | 1 | 1 | 2.34 | 0.61 | 0.823 | 1.17 |  | 1.1748
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.823 | 0.61 |  | 0.60746
0
| (30'/2-3) | Cum | 1 | 2 | 2.34 | 0.61 | 0.823 | 2.35 |  | 2.3495
0
| (31'/2-3) | Cum | 1 | 1 | 1.81 | 0.61 | 0.823 | 0.91 |  | 0.90867
|  | Cum | 1 | 1 | 2.94 | 0.61 | 0.823 | 1.48 |  | 1.476
|  | Cum | 1 | 1 | 6.75 | 0.61 | 0.823 | 3.39 |  | 3.3887
0
| (2-4/28'-31') | Cum | 1 | 1 | 0.61 | 0.61 | 0.823 | 0.31 |  | 0.30624
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
0
|  | Cum | 0 | 1 | 2.13 | 0.61 | 0.823 |  |  | 1.0693
0
| (29'/2-4) | Cum | 1 | 2 | 0.615 | 0.61 | 0.823 | 0.62 |  | 0.6175
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
|  | Cum | 1 | 1 | 1.535 | 0.61 | 0.823 | 0.77 |  | 0.77062
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
0
|  | Cum | 1 | 1 | 2.12 | 0.61 | 0.823 | 1.06 |  | 1.0643
0
| (31'/2-4) | Cum | 1 | 2 | 0.615 | 0.61 | 0.823 | 0.62 |  | 0.6175
0
Excavation for Planter (2-6/31'-37')
| (32'/2-5) | Cum | 1 | 1 | 7.65 | 0.61 | 0.823 | 3.84 |  | 3.8405
0
|  | Cum | 1 | 1 | 5.04 | 0.61 | 0.823 | 2.53 |  | 2.5302
| Excavation for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
| (33'/2-5) | Cum | 1 | 1 | 5.04 | 0.61 | 0.823 | 2.53 |  | 2.5302
|  | Cum | 1 | 1 | 2.17 | 0.61 | 0.823 | 1.09 |  | 1.0894
|  | Cum | 1 | 1 | 6 | 0.61 | 0.823 | 3.01 |  | 3.0122
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.823 | 0.61 |  | 0.60746
|  | Cum | 1 | 1 | 6.9 | 0.61 | 0.823 | 3.46 |  | 3.464
| Excavation for Sheet | Cum | 1 | 1 | 3 | 0.22 | 0.823 | 0.54 |  | 0.54318
|  | Cum | 1 | 1 | 6.9 | 0.61 | 0.823 | 3.46 |  | 3.464
| Excavation for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
0
| (35'/2-5) | Cum | 1 | 1 | 6.9 | 0.61 | 0.823 | 3.46 |  | 3.7652
|  | Cum | 1 | 1 | 2.41 | 0.61 | 0.823 | 1.21 |  | 1.2099
|  | Cum | 1 | 2 | 9.3 | 0.61 | 0.823 | 9.34 |  | 9.3378
| (37'/2-5) | Cum | 1 | 1 | 11.91 | 0.61 | 0.823 | 5.98 |  | 5.9792
| Excavation for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
0
| (2-5/32'-37') | Cum | 1 | 1 | 0.615 | 0.61 | 0.823 | 0.31 |  | 0.30875
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
|  | Cum | 1 | 2 | 0.615 | 0.61 | 0.823 | 0.62 |  | 0.6175
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
0
|  | Cum | 1 | 1 | 0.295 | 0.61 | 0.823 | 0.15 |  | 0.1481
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
|  | Cum | 1 | 1 | 0.615 | 0.61 | 0.823 | 0.31 |  | 0.30875
|  | Cum | 1 | 1 | 3.36 | 0.61 | 0.823 | 1.69 |  | 1.6868
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
|  | Cum | 1 | 1 | 0.615 | 0.61 | 0.823 | 0.31 |  | 0.30875
Excavation for Planter (17-21/20-25)
| (20'/17-21) | Cum | 1 | 1 | 10.02 | 0.61 | 0.823 | 5.03 |  | 5.0303
0
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.823 | 2.41 |  | 2.4148
0
|  | Cum | 1 | 1 | 3.41 | 0.61 | 0.823 | 1.71 |  | 1.7119
| (21'/17-21) | Cum | 1 | 1 | 2.41 | 0.61 | 0.823 | 1.21 |  | 1.2099
0
|  | Cum | 1 | 1 | 6.81 | 0.61 | 0.823 | 3.42 |  | 3.4188
| Excavation for Sheet | Cum | 1 | 1 | 3 | 0.22 | 0.823 | 0.54 |  | 0.54318
0
|  | Cum | 1 | 1 | 8.46 | 0.46 | 0.823 | 3.2 |  | 3.2028
| Excavation for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
0
|  | Cum | 1 | 1 | 1.61 | 0.61 | 0.823 | 0.81 |  | 0.80827
|  | Cum | 1 | 1 | 6.61 | 0.61 | 0.823 | 3.32 |  | 3.3184
|  | Cum | 1 | 1 | 3.41 | 0.61 | 0.823 | 1.71 |  | 1.7119
0
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.823 | 2.41 |  | 2.4148
| Excavation Work for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
|  | Cum | 1 | 1 | 2.41 | 0.61 | 0.823 | 1.21 |  | 1.2099
|  | Cum | 1 | 1 | 3.31 | 0.61 | 0.823 | 1.66 |  | 1.6617
|  | Cum | 1 | 1 | 5.11 | 0.61 | 0.823 | 2.57 |  | 2.5654
| Excavation Work for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
|  | Cum | 1 | 1 | 1.2 | 0.61 | 0.823 | 0.6 |  | 0.60244
| (24'/17-21) | Cum | 1 | 1 | 8.72 | 0.61 | 0.823 | 4.38 |  | 4.3777
0
| (17/20'-24') | Cum | 1 | 8 | 0.615 | 0.61 | 0.823 | 2.47 |  | 2.47
|  | Cum | 1 | 2 | 1.215 | 0.61 | 0.823 | 1.22 |  | 1.2199
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
|  | Cum | 1 | 2 | 0.91 | 0.61 | 0.823 | 0.91 |  | 0.91369
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
Excavation for Planter (17-21/25'-29')
| (20'/17-21) | Cum | 1 | 1 | 9.22 | 0.61 | 0.823 | 4.63 |  | 4.6287
|  | Cum | 1 | 1 | 6.81 | 0.61 | 0.823 | 3.42 |  | 3.4188
0
|  | Cum | 1 | 1 | 5.01 | 0.61 | 0.823 | 2.52 |  | 2.5152
0
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.823 | 0.91 |  | 0.90867
0
|  | Cum | 1 | 1 | 3.81 | 0.61 | 0.823 | 1.91 |  | 1.9127
| Excavation Work for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
0
|  | Cum | 1 | 1 | 3.61 | 0.61 | 0.823 | 1.81 |  | 1.8123
| Excavation for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
0
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.823 | 2.41 |  | 2.4148
0
|  | Cum | 1 | 1 | 3.61 | 0.61 | 0.823 | 1.81 |  | 1.8123
0
|  | Cum | 1 | 1 | 4.81 | 0.61 | 0.823 | 2.41 |  | 2.4148
0
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.823 | 0.91 |  | 0.90867
0
|  | Cum | 1 | 1 | 6.61 | 0.61 | 0.823 | 3.32 |  | 3.3184
0
|  | Cum | 1 | 1 | 8.61 | 0.61 | 0.823 | 4.32 |  | 4.3225
0
|  | Cum | 1 | 1 | 11.02 | 0.61 | 0.823 | 5.53 |  | 5.5324
| (17-21/25'-29') | Cum | 1 | 6 | 0.615 | 0.61 | 0.823 | 1.85 |  | 1.8525
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
0
|  | Cum | 1 | 2 | 0.91 | 0.61 | 0.823 | 0.91 |  | 0.91369
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
Excavation for Planter (17-21/29'-35')
| (29'/17-21) | Cum | 1 | 1 | 8 | 0.61 | 0.823 | 4.02 |  | 4.0162
|  | Cum | 1 | 1 | 5.61 | 0.61 | 0.823 | 2.82 |  | 2.8164
0
|  | Cum | 1 | 1 | 4.61 | 0.61 | 0.823 | 2.31 |  | 2.3144
| Excavation for Sheet | Cum | 1 | 1 | 3.3 | 0.22 | 0.823 | 0.6 |  | 0.5975
0
|  | Cum | 1 | 1 | 1.61 | 0.61 | 0.823 | 0.81 |  | 0.80827
0
|  | Cum | 1 | 6 | 3.61 | 0.61 | 0.823 | 10.87 |  | 10.874
0
|  | Cum | 1 | 1 | 5.61 | 0.61 | 0.823 | 2.82 |  | 2.8164
| Excavation for Sheet | Cum | 1 | 3 | 3.3 | 0.22 | 0.823 | 1.79 |  | 1.7925
0
|  | Cum | 1 | 1 | 4.61 | 0.61 | 0.823 | 2.31 |  | 2.3144
| (35'/17-20) | Cum | 1 | 1 | 6.02 | 0.61 | 0.823 | 3.02 |  | 3.0222
| (17-20/29'-35') | Cum | 1 | 3 | 3.36 | 0.61 | 0.823 | 5.06 |  | 5.0605
0
|  | Cum | 1 | 3 | 0.91 | 0.61 | 0.823 | 1.37 |  | 1.3705
0
|  | Cum | 1 | 1 | 0.91 | 0.61 | 0.823 | 0.46 |  | 0.45685
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
0
|  | Cum | 1 | 2 | 0.91 | 0.61 | 0.823 | 0.91 |  | 0.91369
0
|  | Cum | 1 | 5 | 0.615 | 0.61 | 0.823 | 1.54 |  | 1.5437
| Excavation for Sheet | Cum | 1 | 4 | 3.3 | 0.22 | 0.823 | 2.39 |  | 2.39
0
Excavation for Planter (20-28/2'-5')
| Excavation (2'/20-28) | Cum | 1 | 1 | 3.82 | 0.61 | 0.823 | 1.92 |  | 1.9178
|  | Cum | 1 | 3 | 1.625 | 0.61 | 0.823 | 2.45 |  | 2.7411
0
|  | Cum | 1 | 1 | 4.42 | 0.61 | 0.823 | 2.22 |  | 2.219
0
|  | Cum | 1 | 1 | 3.21 | 0.61 | 0.823 | 1.61 |  | 1.6115
0
|  | Cum | 1 | 4 | 0.78 | 0.61 | 0.823 | 1.57 |  | 4.0162
0
Excavation (3'/20-28)
| Excavation (6'/20-21) | Cum | 1 | 1 | 4.425 | 0.61 | 0.823 | 2.22 |  | 2.2215
|  | Cum | 1 | 2 | 1.495 | 0.61 | 0.823 | 1.5 |  | 1.8274
0
| Excavation (4'/22-23) | Cum | 1 | 3 | 3.21 | 0.61 | 0.823 | 4.83 |  | 4.8345
0
|  | Cum | 1 | 2 | 0.78 | 0.61 | 0.823 | 0.78 |  | 2.0081
0
|  | Cum | 1 | 1 | 2.61 | 0.61 | 0.823 | 1.31 |  | 1.3103
0
Excavation (20/2'-5')
| Excavation (20/2'-5') | Cum | 1 | 1 | 9.155 | 0.61 | 0.823 | 4.6 |  | 4.5961
|  | Cum | 1 | 2 | 6.405 | 0.61 | 0.823 | 6.43 |  | 6.431
| Excavation for Sheat | Cum | 1 | 4 | 3.3 | 0.22 | 0.823 | 2.39 |  | 2.39
0
|  | Cum | 1 | 1 | 4.88 | 0.61 | 0.823 | 2.45 |  | 2.4499
0
|  | Cum | 1 | 1 | 0.78 | 0.61 | 0.823 | 0.39 |  | 0.45936
0
| (23/2'-5') | Cum | 1 | 1 | 1.83 | 0.61 | 0.823 | 0.92 |  | 0.91871
0
|  | Cum | 1 | 1 | 0.6 | 0.61 | 0.823 | 0.3 |  | 0.30624
0
|  | Cum | 0 | 1 | 3.365 | 0.61 | 0.823 |  |  | 1.6893
0
|  | Cum | 1 | 2 | 3.355 | 0.61 | 0.823 | 3.37 |  | 3.3686
0
|  | Cum | 1 | 1 | 3.05 | 0.61 | 0.823 | 1.53 |  | 1.5362
0
|  | Cum | 1 | 1 | 0.305 | 0.61 | 0.823 | 0.15 |  | 0.30624
0
|  | Cum | 1 | 1 | 0.915 | 0.61 | 0.823 | 0.46 |  | 0.45936
0
|  | Cum | 1 | 1 | 2.11 | 0.61 | 0.823 | 1.06 |  | 1.0593
0
Excavation Side of BH-01 (15/23'-35')
0
| east face (15/23'-35') | Cum | 1 | 2 | 30.47 | 0.61 | 0.823 | 30.59 |  | 30.5937
0
|  | Cum | 1 | 2 | 0.6 | 0.61 | 0.823 | 0.6 |  | 0.60244
0
| north face (23'/9-10) | Cum | 1 | 2 | 6.245 | 0.61 | 0.823 | 6.27 |  | 6.2704
0
|  | Cum | 1 | 2 | 1.195 | 0.61 | 0.823 | 1.2 |  | 1.1999
0
| north face (23'/11-13) | Cum | 1 | 2 | 7.07 | 0.61 | 0.823 | 7.1 |  | 7.0987
0
|  | Cum | 1 | 2 | 1.195 | 0.61 | 0.823 | 1.2 |  | 1.1999
Excavation for Planter (20-28/2'-5')
| Excavation (42'/13-16) | Cum | 1 | 1 | 5.42 | 0.61 | 0.823 | 2.72 |  | 2.721
|  | Cum | 1 | 1 | 2.81 | 0.61 | 0.823 | 1.41 |  | 1.4107
|  | Cum | 1 | 1 | 4.01 | 0.61 | 0.823 | 2.01 |  | 2.0131
|  | Cum | 1 | 1 | 1.27 | 0.61 | 0.823 | 0.64 |  | 0.63758
0
|  | Cum | 1 | 2 | 4.67 | 0.61 | 0.823 | 4.69 |  | 4.689
|  | Cum | 1 | 1 | 0.99 | 0.61 | 0.823 | 0.5 |  | 0.49701
|  | Cum | 1 | 1 | 4.29 | 0.61 | 0.823 | 2.15 |  | 2.1537
| (45'/14-17) | Cum | 1 | 1 | 1.89 | 0.61 | 0.823 | 0.95 |  | 0.94884
0
|  | Cum | 1 | 1 | 3.69 | 0.61 | 0.823 | 1.85 |  | 1.8525
0
|  | Cum | 1 | 1 | 4.89 | 0.61 | 0.823 | 2.45 |  | 2.4549
| (46'/14-17) | Cum | 1 | 1 | 6.17 | 0.61 | 0.823 | 3.1 |  | 3.0975
0
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.823 | 0.61 |  | 0.60746
0
|  | Cum | 1 | 2 | 6.77 | 0.61 | 0.823 | 6.8 |  | 6.7975
0
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.823 | 0.91 |  | 0.90867
0
|  | Cum | 1 | 1 | 10.58 | 0.61 | 0.823 | 5.31 |  | 5.3115
| Excavation for Sheet | Cum | 1 | 5 | 3.3 | 0.22 | 0.823 | 2.99 |  | 2.9875
(15/42'-47')
|  | Cum | 1 | 7 | 0.615 | 0.61 | 0.823 | 2.16 |  | 2.1612
0
|  | Cum | 1 | 1 | 1.535 | 0.61 | 0.823 | 0.77 |  | 1.0718
0
|  | Cum | 1 | 1 | 0.3 | 0.61 | 0.823 | 0.15 |  | 0.15061
0
|  | Cum | 1 | 5 | 0.91 | 0.61 | 0.823 | 2.28 |  | 2.2842
0
|  | Cum | 1 | 1 | 3.36 | 0.61 | 0.823 | 1.69 |  | 1.6868
0
|  | Cum | 1 | 2 | 2.135 | 0.61 | 0.823 | 2.14 |  | 2.7561
0
0
Excavation for Planter (20-28/2'-5')
| Excavation (48'/13-16) | Cum | 1 | 1 | 11.38 | 0.61 | 0.823 | 5.71 |  | 5.7131
|  | Cum | 1 | 1 | 8.77 | 0.61 | 0.823 | 4.4 |  | 4.4028
| (49'/13-16) | Cum | 1 | 2 | 6.77 | 0.61 | 0.823 | 6.8 |  | 6.7975
| (50'/14-18) | Cum | 1 | 2 | 9.17 | 0.61 | 0.823 | 9.21 |  | 9.2072
|  | Cum | 1 | 1 | 8.27 | 0.61 | 0.823 | 4.15 |  | 4.1518
| (52'/14-18) | Cum | 1 | 1 | 10.88 | 0.61 | 0.823 | 5.46 |  | 5.4621
| P.C.C. P/L for Sheet | Cum | 1 | 3 | 3.3 | 0.22 | 0.823 | 1.79 |  | 1.7925
| (15/48'-53') | Cum | 1 | 2 | 0.615 | 0.61 | 0.823 | 0.62 |  | 0.6175
| (17/48'-49') | Cum | 1 | 3 | 0.88 | 0.61 | 0.823 | 1.33 |  | 1.3254
|  | Cum | 1 | 3 | 3.36 | 0.61 | 0.823 | 5.06 |  | 5.0605
0
Excavation outer side of BH-04 (Drg. No. TU/LA-P-206.3)
| Excavation Work west side (20/37'-50') | Cum | 1 | 1 | 33.92 | 0.61 | 0.823 | 17.03 |  | 17.0289
|  | Cum | 1 | 1 | 30.13 | 0.61 | 0.823 | 15.13 |  | 15.1262
0
| Excavation south side (49'/19-23) (longitudinal axies) | Cum | 1 | 1 | 1.525 | 0.61 | 0.823 | 0.77 |  | 0.7656
|  | Cum | 1 | 1 | 1.075 | 0.61 | 0.823 | 0.54 |  | 0.53968
|  | Cum | 1 | 1 | 2.6 | 0.61 | 0.823 | 1.31 |  | 1.3053
|  | Cum | 1 | 1 | 1.1 | 0.61 | 0.823 | 0.55 |  | 0.55223
|  | Cum | 1 | 1 | 3.94 | 0.61 | 0.823 | 1.98 |  | 1.978
| Excavation south side (49'/19-23) (transverse axies) | Cum | 1 | 1 | 1.39 | 0.61 | 0.823 | 0.7 |  | 0.69782
0
|  | Cum | 1 | 1 | 2 | 0.61 | 0.823 | 1 |  | 1.0041
0
|  | Cum | 1 | 1 | -0.22 | 0.61 | 0.823 | -0.11 |  | -0.11045
0
|  | Cum | 1 | 1 | 1 | 0.61 | 0.823 | 0.5 |  | 0.50203
0
|  | Cum | 1 | 1 | 1.36 | 0.61 | 0.823 | 0.68 |  | 0.68276
0
|  | Cum | 1 | 1 | 5.56 | 0.61 | 0.823 | 2.79 |  | 2.7913
| Excavation north side (36'/19-21) (longitudianal axies) | Cum | 0 | 1 | 3.02 | 0.61 | 0.823 |  |  | 1.5161
| Excavation north side (36'/19-21) (transverse axies) | Cum | 0 | 1 | 4.495 | 0.61 | 0.823 |  |  | 2.2566
0
| (transverse axies) | Cum | 0 | 1 | 1.685 | 0.61 | 0.823 |  |  | 0.84592
0
Excavation outer side of BH-04 (Drg. No. TU/LA-P-206.4)
| Excavation east side (32/37'-49') | Cum | 1 | 2 | 33.04 | 0.61 | 0.823 | 33.17 |  | 33.1741
|  | Cum | 1 | 2 | 1.36 | 0.61 | 0.823 | 1.37 |  | 1.5764
0
0
Excavation for Planter (39'-55'/32-36) (Drg. No. TU/LA-P-206.4)
| Excavation for Planter (39'-47'/32-36) | [8 empty] | 0
| longitudianal axies (40'/34-35) | Cum | 1 | 1 | 4.7 | 0.61 | 0.823 | 2.36 |  | 4.7191
0
|  | Cum | 1 | 1 | 2.09 | 0.61 | 0.823 | 1.05 |  | 1.0492
0
|  | Cum | 1 | 4 | 2.99 | 0.61 | 0.823 | 6 |  | 6.0043
0
|  | Cum | 1 | 2 | 5.09 | 0.61 | 0.823 | 5.11 |  | 5.1107
0
|  | Cum | 1 | 2 | 4.79 | 0.61 | 0.823 | 4.81 |  | 4.8094
0
|  | Cum | 1 | 2 | 5.69 | 0.61 | 0.823 | 5.71 |  | 5.7131
0
|  | Cum | 1 | 2 | 6.59 | 0.61 | 0.823 | 6.62 |  | 6.6168
0
|  | Cum | 1 | 1 | 7.79 | 0.61 | 0.823 | 3.91 |  | 3.9108
0
|  | Cum | 1 | 1 | 2.11 | 0.61 | 0.823 | 1.06 |  | 1.0593
0
| (47'/32-36) | Cum | 1 | 1 | 11.38 | 0.61 | 0.823 | 5.71 |  | 5.9742
| Excavation for Sheat | Cum | 1 | 4 | 3.3 | 0.22 | 0.823 | 2.39 |  | 2.39
0
| Transvere axies (34/40'-47') | Cum | 1 | 3 | 0.615 | 0.61 | 0.823 | 0.93 |  | 0.92625
0
|  | Cum | 1 | 6 | 3.36 | 0.61 | 0.823 | 10.12 |  | 10.1209
0
|  | Cum | 1 | 7 | 0.91 | 0.61 | 0.823 | 3.2 |  | 3.1979
0
|  | Cum | 1 | 1 | 2.135 | 0.61 | 0.823 | 1.07 |  | 1.0718
0
Excavation for Planter (30-39/37-40) near M4 (revised Drg. No. TU/LA-P-206.5 (front of Basket Ball)
aa | Excavation (west side wall) | Cum | 1 | 1 | 19.75 | 0.61 | 0.823 | 9.92 |  | 9.9151
| extra for Sheet | Cum | 1 | 3 | 3.3 | 0.22 | 0.823 | 1.79 |  | 1.7925
0
| north & south side wall | Cum | 2 | 1 | 2 | 0.61 | 0.823 | 2.01 |  | 2.0081
|  | Cum | 1 | 3 | 2.435 | 0.61 | 0.823 | 3.67 |  | 3.6673
|  | Cum | 1 | 1 | 2.44 | 0.61 | 0.823 | 1.22 |  | 1.225
|  | Cum | 1 | 1 | 2.13 | 0.61 | 0.823 | 1.07 |  | 1.0693
|  | Cum | 1 | 1 | 2.09 | 0.61 | 0.823 | 1.05 |  | 1.0492
|  | Cum | 1 | 2 | 5.345 | 0.61 | 0.823 | 5.37 |  | 5.3667
|  | Cum | 1 | 2 | 6.38 | 0.61 | 0.823 | 6.41 |  | 6.4059
|  | Cum | 1 | 2 | 6.95 | 0.61 | 0.823 | 6.98 |  | 6.9782
|  | Cum | 1 | 2 | 6.12 | 0.61 | 0.823 | 6.14 |  | 6.1448
|  | Cum | 1 | 2 | 4.645 | 0.61 | 0.823 | 4.66 |  | 4.6639
|  | Cum | 1 | 2 | 3 | 0.61 | 0.823 | 3.01 |  | 3.0122
|  | Cum | 1 | 4 | 0.615 | 0.61 | 0.823 | 1.23 |  | 1.235
|  | Cum | 1 | 2 | 0.61 | 0.61 | 0.823 | 0.61 |  | 0.61248
Excavation for Planter near BH-03 (drg. No. TU/LA-P-206.1) (48-52/2'-11')
Excavation for Stepped Foundation (west side wall) (2'/48-52)
| Longitudianal axies (2'/48-52) | Cum | 1 | 1 | 8.62 | 0.61 | 0.823 | 4.33 |  | 4.3275
|  | Cum | 1 | 1 | 6.01 | 0.61 | 0.823 | 3.02 |  | 3.0172
|  | Cum | 1 | 2 | 6.61 | 0.61 | 0.823 | 6.64 |  | 6.6368
|  | Cum | 1 | 3 | 5.41 | 0.61 | 0.823 | 8.15 |  | 8.1479
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.823 | 0.91 |  | 0.90867
|  | Cum | 1 | 1 | 6.01 | 0.61 | 0.823 | 3.02 |  | 3.0172
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.823 | 0.61 |  | 0.60746
|  | Cum | 1 | 5 | 4.81 | 0.61 | 0.823 | 12.07 |  | 14.4886
|  | Cum | 1 | 1 | 1.21 | 0.61 | 0.823 | 0.61 |  | 0.60746
|  | Cum | 1 | 1 | 5.41 | 0.61 | 0.823 | 2.72 |  | 2.716
|  | Cum | 1 | 1 | 1.81 | 0.61 | 0.823 | 0.91 |  | 0.90867
| (10'/49-50) | Cum | 1 | 2 | 6.61 | 0.61 | 0.823 | 6.64 |  | 6.6368
|  | Cum | 1 | 1 | 9.22 | 0.61 | 0.823 | 4.63 |  | 4.6287
| extra for Sheet | Cum | 1 | 8 | 3.3 | 0.22 | 0.823 | 4.78 |  | 4.78
Transverse axies (49/2'-11')
|  | Cum | 1 | 6 | 0.615 | 0.61 | 0.823 | 1.85 |  | 1.8525
|  | Cum | 1 | 4 | 0.91 | 0.61 | 0.823 | 1.83 |  | 1.8274
|  | Cum | 1 | 2 | 3.36 | 0.61 | 0.823 | 3.37 |  | 3.3736
|  | Cum | 1 | 3 | 0.605 | 0.61 | 0.823 | 0.91 |  | 0.91118
|  | Cum | 1 | 2 | 1.83 | 0.61 | 0.823 | 1.84 |  | 1.8374
|  | Cum | 1 | 2 | 2.135 | 0.61 | 0.823 | 2.14 |  | 2.1437
|  | Cum | 1 | 1 | 3.055 | 0.61 | 0.823 | 1.53 |  | 1.5337
|  | Cum | 1 | 1 | 3.165 | 0.61 | 0.823 | 1.59 |  | 1.5889
|  | Cum | 1 | 1 | 0.715 | 0.61 | 0.823 | 0.36 |  | 0.35895
Excavation for BH-05 outer side (drg. No. TU/LA-P-206.8)
| P.C.C. P/L for FIRE TENDER TOES Wall (north side wall) | Cum | 1 | 1 | 34.935 | 0.61 | 0.823 | 17.54 |  | 17.5384
| P.C.C. P/L for FIRE TENDER TOES Wall (west side wall) | Cum | 1 | 1 | 15 | 0.61 | 0.823 | 7.53 |  | 7.5305
0
| Excavation for Basket Ball Ground Toe Wall | [5 empty] | 0.823 |  |  | 0.823
| Basket Ball Long Ball | Cum | 1 | 2 | 28.76 | 0.61 | 0.823 | 28.88 |  | 28.8768
0
| BASKET WALL SHORT WALL | Cum | 1 | 2 | 14.19 | 0.61 | 0.823 | 14.25 |  | 14.7998
0
| SEAT | Cum | 1 | 2 | 3.3 | 0.22 | 0.823 | 1.19 |  | 1.195
0
0
Excavation for Basket Ball Ground Toe Wall
0
| FIRE TENDER TOE WALL WITH BH-01 |  | 1 | 1 | 31.4 | 0.61 | 0.823 | 15.76 |  | 15.7637
0
| FIRE TENDER TOE WALL WITH BH-07 |  | 1 | 1 | 42.55 | 0.61 | 0.823 | 21.36 |  | 21.3614
0
Excavation for Road Toe Wall BH-01
0
| Excavation for Road Toe Wall BH-01 east side towards water body | Cum | 1 | 2 | 30.54 | 0.61 | 0.823 | 30.66 |  | 30.664
0
|  | Cum | 1 | 2 | 0.67 | 0.61 | 0.823 | 0.67 |  | 0.67272
Excavation for Road Toe Wall BH-01 North side towards GYM
|  | Cum | 1 | 2 | 6.315 | 0.61 | 0.823 | 6.34 |  | 6.3406
|  | Cum | 1 | 2 | 1.265 | 0.61 | 0.823 | 1.27 |  | 1.2701
|  | Cum | 1 | 2 | 7.14 | 0.61 | 0.823 | 7.17 |  | 7.169
|  | Cum | 1 | 2 | 1.265 | 0.61 | 0.823 | 1.27 |  | 1.2701
Excavation for Road Toe Wall back side of Basket Ball (east side)
0
|  |  | 1 | 4 | 7.625 | 0.61 | 0.823 | 15.31 |  | 15.3119
Excavation for Road Toe wall outer parapheri BG-02 to Gym North side
0
|  | Cum | 1 | 8 | 7.625 | 0.61 | 0.823 | 30.62 |  | 30.6238
|  | Cum | 1 | 1 | 9.35 | 0.61 | 0.823 | 4.69 |  | 4.9952
Excavation for Planter between BH-03 & Basket Ball Ground
| Base Footning (4500x1000) | Cum | 1 | 8 | 5 | 1.5 | 0.823 | 49.38 |  | 49.38
0
Excavation for Planter between BH-04 & Base of Waterbody M3
| Base Footning (4500x1000) | Cum | 1 | 8 | 5 | 1.5 | 0.823 | 49.38 |  | 49.38
| Less Previous RA Quantity | Cum | -1 | 1 | 716.21 |  |  | -716.21 |  | 0
| Earth Excavation for Planter near Reception or west side of Waterbody (drg. No. TU/LA-P-206.1) (30'-35'/32-36) | Cum
| Earth Excavation for Planter | Cum
| Longitudianal axies (30'/32-36) | Cum | 1 | 1 | 11.97 | 0.61 | 0.823 | 6.01
|  | Cum | 1 | 1 | 2.01 | 0.61 | 0.823 | 1.01
|  | Cum | 1 | 1 | 7.965 | 0.61 | 0.823 | 4
| Longitudianal axies (31'/32-35) | Cum | 1 | 1 | 7.965 | 0.61 | 0.823 | 4
|  | Cum | 1 | 1 | 2.01 | 0.61 | 0.823 | 1.01
|  | Cum | 1 | 1 | 6.565 | 0.61 | 0.823 | 3.3
| Longitudianal axies (32'/32-35) | Cum | 1 | 1 | 6.565 | 0.61 | 0.823 | 3.3
|  | Cum | 1 | 1 | 2.14 | 0.61 | 0.823 | 1.07
|  | Cum | 1 | 1 | 5.035 | 0.61 | 0.823 | 2.53
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 5.035 | 0.61 | 0.823 | 2.53
|  | Cum | 1 | 1 | 2.14 | 0.61 | 0.823 | 1.07
|  | Cum | 1 | 1 | 3.5 | 0.61 | 0.823 | 1.76
| Longitudianal axies (33'/32-35) | Cum | 1 | 1 | 3.5 | 0.61 | 0.823 | 1.76
|  | Cum | 1 | 1 | 5.5 | 0.61 | 0.823 | 2.76
| Transvere axies (34/30'-35') | Cum | 1 | 6 | 0.615 | 0.61 | 0.823 | 1.85
|  | Cum | 1 | 3 | 2.135 | 0.61 | 0.823 | 3.22
|  | Cum | 1 | 1 | 1.83 | 0.61 | 0.823 | 0.92
|  | Cum | 1 | 3 | 0.91 | 0.61 | 0.823 | 1.37
|  | Cum | 1 | 1 | 0.605 | 0.61 | 0.823 | 0.3
| Earth Excavation for Planter South sid of BH-02 (drg. No. TU/LA-P-206.1 & 206.2) ( (15'-19'/20-32) | Cum
| Earth Excavation for Planter | Cum
| Longitudianal axies (15'/20-32) | Cum | 1 | 1 | 29.85 | 0.61 | 0.823 | 14.99
|  | Cum | 1 | 1 | 1.08 | 0.61 | 0.823 | 0.54
|  | Cum | 1 | 6 | 0.78 | 0.61 | 0.823 | 2.35
|  | Cum | 1 | 1 | 1.03 | 0.61 | 0.823 | 0.52
|  | Cum | 1 | 1 | 0.53 | 0.61 | 0.823 | 0.27
|  | Cum | 1 | 12 | 0.6 | 0.61 | 0.823 | 3.61
| Transvere axies (32/15'-19') | Cum | 1 | 1 | 11.535 | 0.61 | 0.823 | 5.79
| (32/15'-19') | Cum | 1 | 1 | 9.925 | 0.61 | 0.823 | 4.98
| (31/15'-19') | Cum | 1 | 2 | 8.4 | 0.61 | 0.823 | 8.43
| (30/15'-18') | Cum | 1 | 2 | 6.875 | 0.61 | 0.823 | 6.9
| (29/15'-17') | Cum | 0 | 2 | 6.875 | 0.61 | 0.823
|  | Cum | 1 | 2 | 5.35 | 0.61 | 0.823 | 5.37
|  | Cum | 1 | 2 | 4.13 | 0.61 | 0.823 | 4.15
|  | Cum | 6 | 2 | 3.825 | 0.61 | 0.823 | 23.04
|  | Cum | 1 | 1 | 3.825 | 0.61 | 0.823 | 1.92
|  | Cum | 1 | 1 | 5.435 | 0.61 | 0.823 | 2.73
| Earth Excavation for Sheat | Cum | 1 | 11 | 3 | 0.115 | 0.823 | 3.12
| Earth Excavation for Planter South sid of BH-02 & BH-03 (drg. No. TU/LA-P-206.1) ( (19'-21'/35-40) | Cum
| Earth Excavation or Planter | Cum
| Longitudianal axies (40/19'-20') | Cum | 1 | 2 | 4.2 | 0.61 | 0.823 | 4.22
|  | Cum | 1 | 2 | 6.335 | 0.61 | 0.823 | 6.36
|  | Cum | 1 | 2 | 7.25 | 0.61 | 0.823 | 7.28
|  | Cum | 1 | 2 | 6.64 | 0.61 | 0.823 | 6.67
|  | Cum | 1 | 5 | 0.6 | 0.61 | 0.823 | 1.51
| Earth Excavation for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
| Earth Excavation for Road Toe Wall (1/F-J) | Cum | 1 | 1 | 4.635 | 0.61 | 0.823 | 2.33
|  | Cum | 1 | 8 | 7.625 | 0.61 | 0.823 | 30.62
|  | Cum | 1 | 1 | 10.14 | 0.61 | 0.823 | 5.09
| Earth Excavation for Road Toe Wall (J/1-9) | Cum | 1 | 1 | 14.06 | 0.61 | 0.823 | 7.06
|  | Cum | 1 | 5 | 7.625 | 0.61 | 0.823 | 19.14
|  | Cum | 1 | 1 | 0.265 | 0.61 | 0.823 | 0.13
| Earth Excavation for Road Toe Wall (9/H-J) | Cum | 1 | 1 | 7.53 | 0.61 | 0.823 | 3.78
|  | Cum | 1 | 2 | 7.625 | 0.61 | 0.823 | 7.66
| Earth Excavation for Planter between BH-01 & Canteen | Cum
Cum
| Base Footning (4500x1000) | Cum | 1 | 9 | 5 | 1.5 | 0.823 | 55.55
| Earth Excavation for Planter between BH-02 & GYM | Cum
| Base Footning (4500x1000) | Cum | 1 | 8 | 5 | 1.5 | 0.823 | 49.38
| Earth Excavation for Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For P.C.C. =20.12+0.2*2+0.6*2+0.2*2=22.120m) | Cum |  |  | area
|  | Cum | 1 | 1 | 384.0961 |  | 0.823 | 316.11
Excavation under WBM area-
| Stone Agg. 90 to 45mm in Basket Ball Ground | [8 empty] | Depth as per level sheet attached
|  | Cum | 0 | 1 | 27.54 | 14.74 | 0.823 |  |  | D=(0.809+0.661+1.078+0.797+0.782+0.808)/6
0
| Stone Agg. 90 to 45mm in Road |  | 0
| Road between BH-05 & B3 Basket Ground | Cum | 0 | 1 | 29.2 | 6 | 0.823
|  | Cum | 0 | 1 | 8.32 | 6.78 | 0.823
| Road between BH-05 & BH-04 | Cum | 0 | 1 | 23.235 | 6 | 0.823
| Road between BH-05 & BH-04 | Cum | 0 | 1 | 2.275 | 6 | 0.823
| Road between BH-05 & BH-04 | Cum | 0 | 1 | 32.39 | 6 | 0.823
| Road between BH-05 & BH-04 | Cum | 0 | 1 | 5.295 | 6 | 0.823
0
| Road between BH-01 & Waterboy (east side) | Cum | 0 | 1 | 31.463 | 6 | 0.823
| Road between BH-01 & BH-07 (south side) | Cum | 0 | 1 | 33.193 | 6 | 0.823
|  | Cum | 0 | 1 | 29.854 | 6 | 0.823
|  | Cum | 0 | 1 | 33.667 | 6 | 0.823
|  | Cum | 0 | 1 | 12.3 | 6 | 0.823
0
| Stone Agg. 90 to 45mm in Planter Area |  | 0
| Planter Front of Basket Ground (west side) | Cum | 0 | 1 | 6.38 | 1.975 | 0.823
|  | Cum | 0 | 2 | 6.95 | 1.975 | 0.823
|  | Cum | 0 | 1 | 6.12 | 1.67 | 0.823
|  | Cum | 0 | 1 | 4.645 | 1.975 | 0.823
0
|  | Cum | 0 | 1 | 6.885 | 1.27 | 0.823
|  | Cum | 0 | 1 | 2.385 | 2.26 | 0.823
| space between basket ground & planter | Cum | 0 | 1 | 20.17 | 2.125 | 0.823
0
| planter front of Bh-05 (west side) | Cum | 0 | 1 | 12.58 | 1.19 | 0.823
|  | Cum | 0 | 1 | 7.09 | 0.9 | 0.823
|  | Cum | 0 | 1 | 1.6 | 5.98 | 0.823
|  | Cum | 0 | 1 | 1.6 | 4.18 | 0.823
|  | Cum | 0 | 2 | 1.6 | 2.38 | 0.823
|  | Cum | 0 | 1 | 1.145 | 0.9 | 0.823
0
|  | Cum | 0 | 1 | 2.745 | 1.5 | 0.823
|  | Cum | 0 | 1 | 1.6 | 6.675 | 0.823
|  | Cum | 0 | 1 | 3.07 | 1.065 | 0.823
|  | Cum | 0 | 1 | 1.6 | 3.9 | 0.823
|  | Cum | 0 | 1 | 2.77 | 0.96 | 0.823
|  | Cum | 0 | 1 | 1.6 | 4.09 | 0.823
|  | Cum | 0 | 1 | 3.25 | 1.095 | 0.823
|  | Cum | 0 | 1 | 8.61 | 4.615 | 0.823
0
| Stone agg. In planter front between Bh-07 & BH-04 | Cum | 0 | 1 | 1.6 | 8.56 | 0.823
|  | Cum | 0 | 1 | 1.6 | 6.85 | 0.823
|  | Cum | 0 | 1 | 1.6 | 7.45 | 0.823
|  | Cum | 0 | 1 | 0.99 | 8.85 | 0.823
|  | Cum | 0 | 1 | 1.6 | 4.89 | 0.823
|  | Cum | 0 | 1 | 1.6 | 5.33 | 0.823
|  | Cum | 0 | 1 | 1.6 | 1.45 | 0.823
|  | Cum | 0 | 1 | 1.6 | 3.83 | 0.823
|  | Cum | 0 | 1 | 1.415 | 2.425 | 0.823
|  | Cum | 0 | 1 | 0.755 | 1.965 | 0.823
|  | Cum | 0 | 1 | 5.465 | 4.2 | 0.823
0
| Stone agg. In planter east side of BH-1 or front of Water Body | Cum | 0 | 1 | 1.6 | 4 | 0.823
|  | Cum | 0 | 1 | 1.6 | 1 | 0.823
|  | Cum | 0 | 1 | 5.49 | 0.965 | 0.823
|  | Cum | 0 | 1 | 7.09 | 1 | 0.823
|  | Cum | 0 | 1 | 1.6 | 3 | 0.823
|  | Cum | 0 | 1 | 4.345 | 1 | 0.823
|  | Cum | 0 | 1 | 1.6 | 4 | 0.823
|  | Cum | 0 | 2 | 1.6 | 3 | 0.823
0
|  | Cum | 0 | 1 | 20.145 | 2.235 | 0.823
|  | Cum | 0 | 1 | 1.845 | 4.07 | 0.823
0
|  | Cum | 0 | 1 | 0.685 | 4.13 | 0.823
|  | Cum | 0 | 1 | 3.43 | 1.2 | 0.823
|  | Cum | 0 | 1 | 1.6 | 3 | 0.823
|  | Cum | 0 | 1 | 3.735 | 1.2 | 0.823
|  | Cum | 0 | 1 | 3.43 | 4.235 | 0.823
|  | Cum | 0 | 1 | 1.6 | 1.8 | 0.823
|  | Cum | 0 | 1 | 1.6 | 4.2 | 0.823
|  | Cum | 0 | 1 | 1.6 | 5 | 0.823
|  | Cum | 0 | 1 | 2.135 | 3.235 | 0.823
|  | Cum | 0 | 1 | 3.735 | 3.2 | 0.823
|  | Cum | 0 | 1 | 12.12 | 1.5 | 0.823
|  | Cum | 0 | 1 | 0.99 | 4.13 | 0.823
|  | Cum | 0 | 1 | 1.6 | 4.5 | 0.823
|  | Cum | 0 | 1 | 1.46 | 2.7 | 0.823
|  | Cum | 0 | 1 | 1.6 | 6 | 0.823
0
|  | Cum | 0 | 1 | 20.97 | 2 | 0.823
|  | Cum | 0 | 1 | 1.905 | 6.235 | 0.823
|  | Cum | 0 | 1 | 1.145 | 2 | 0.823
0
|  | Cum | 0 | 1 | 4.345 | 1.2 | 0.823
|  | Cum | 0 | 1 | 1.6 | 1.8 | 0.823
|  | Cum | 0 | 1 | 4.65 | 1 | 0.823
|  | Cum | 0 | 1 | 1.905 | 1.8 | 0.823
| Stone Agg. 90 to 45mm in Ramp Area Front side of Gym (West side) |  | 0
|  | Cum | 0 | 1 | 24.135 | 6.2 | 0.823
| This bill measurement- Item no 6 |  | 0
| WBM P/L for Road Work | Cum | 0
| Area-1, Road between Waterbody & BH-02 (remaining portion) | Cum | 0 | 1 | 45.5268 |  | 0.125 |  |  | area
| Area-2, Road between Canteen & BH-02 | Cum | 0 | 1 | 235.971 |  | 0.125 |  |  | area
| Area-3, Road south side of BH-04 | Cum | 0 | 1 | 229.3859 |  | 0.125 |  |  | area
| Area-4, Road between BH-03 & Gym | Cum | 0 | 1 | 161.3012 |  | 0.125 |  |  | area
This bill measurement- Excavation
Earth Excavation for Planter near Waterbody & Reception (22'-26'/32-36) Ref. Drg. No. TU/LA-P-206.1
Earth Excavation for Planter
| Longitudianal axies (32/22'-26') | Cum | 1 | 1 | 10.57 | 0.61 | 0.823 | 5.31
|  | Cum | 1 | 1 | 10.155 | 0.61 | 0.823 | 5.1
| (33/22'-26') | Cum | 1 | 2 | 8.935 | 0.61 | 0.823 | 8.97
| (34/22'-26') | Cum | 1 | 2 | 7.41 | 0.61 | 0.823 | 7.44
| (35/22'-26') | Cum | 1 | 2 | 5.58 | 0.61 | 0.823 | 5.6
| (36/22'-26') | Cum | 1 | 1 | 4.055 | 0.61 | 0.823 | 2.04
|  | Cum | 1 | 1 | 4.85 | 0.61 | 0.823 | 2.43
| Transverse Axies | Cum | 1 | 5 | 0.6 | 0.61 | 0.823 | 1.51
Earth Excavation for Ramp B/W for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205
|  | Cum | 1 | 2 | 6 | 0.645 | 0.823 | 6.37
|  | Cum | 1 | 1 | 2.925 | 0.645 | 0.823 | 1.55
|  | Cum | 1 | 1 | 1.08 | 0.645 | 0.823 | 0.57
|  | Cum | 1 | 1 | 2 | 0.645 | 0.823 | 1.06
| Earth Excavation for Brick Steps | Cum | 1 | 1 | 3 | 1.2 | 0.823 | 2.96
| Earth Excavation. for brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.645 | 0.823 | 0.32
Earth Excavation for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205
|  | Cum | 1 | 2 | 6 | 0.645 | 0.823 | 6.37
|  | Cum | 1 | 1 | 2.925 | 0.645 | 0.823 | 1.55
|  | Cum | 1 | 1 | 1.08 | 0.645 | 0.823 | 0.57
|  | Cum | 1 | 1 | 2 | 0.645 | 0.823 | 1.06
| Earth Excavation for Brick Steps | Cum | 1 | 1 | 3 | 1.2 | 0.823 | 2.96
| Earth Excavation for brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.645 | 0.823 | 0.32
Earth Excavation for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205
|  | Cum | 1 | 2 | 6 | 0.645 | 0.823 | 6.37
|  | Cum | 1 | 1 | 2.925 | 0.645 | 0.823 | 1.55
|  | Cum | 1 | 1 | 1.08 | 0.645 | 0.823 | 0.57
|  | Cum | 1 | 1 | 2 | 0.645 | 0.823 | 1.06
| Earth Excavation for Brick Steps | Cum | 1 | 1 | 3 | 1.2 | 0.823 | 2.96
| Earth Excavation for brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.645 | 0.823 | 0.32
Earth Excavation for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205
|  | Cum | 1 | 2 | 6 | 0.645 | 0.823 | 6.37
|  | Cum | 1 | 1 | 2.925 | 0.645 | 0.823 | 1.55
|  | Cum | 1 | 1 | 1.08 | 0.645 | 0.823 | 0.57
|  | Cum | 1 | 1 | 2 | 0.645 | 0.823 | 1.06
| Earth Excavation for Brick Steps | Cum | 1 | 1 | 3 | 1.2 | 0.823 | 2.96
| Earth Excavation for brick wall side of step continue | Cum | 1 | 1 | 0.6 | 0.645 | 0.823 | 0.32
P.C.C. P/L for Brick Work for Road Toe Wall (9/H-J)
|  | Cum | 1 | 1 | 7.625 | 0.76 | 0.823 | 4.77
|  | Cum | 1 | 1 | 1.1 | 0.76 | 0.823 | 0.69
Earth Excavation for Brick Work for Road Toe Wall (9/F-H) basket ball ground & BH-03
|  | Cum | 1 | 1 | 7.625 | 0.76 | 0.823 | 4.77
|  | Cum | 1 | 1 | 7.125 | 0.76 | 0.823 | 4.46
Earth Excavation for Brick work for Seprate Seat
P.C.C. P/L for P.C.C. P/L for Brick work seat under transfer slab of BH-04 towards Waterbody
| TOS lvl. +0.5m | Cum | 1 | 7 | 3.526 | 0.76 | 0.823 | 15.44
Earth Excavation for Brick work seat between Waterbody & Reception
| TOS lvl. +0.5m | Cum | 1 | 8 | 3.526 | 0.76 | 0.823 | 17.64
Earth Excavation for Brick work seat under transfer slab of BH-01 towards Canteen
| TOS lvl. +0.5m | Cum | 1 | 6 | 3.526 | 0.76 | 0.823 | 13.23
Earth Excavation for Fire Tender Wall (parallel to road)
| Fire Tender Wall towards BH-07 | Cum | 1 | 1 | 24.945 | 0.76 | 0.823 | 15.6
|  | Cum | 1 | 1 | 13.605 | 0.76 | 0.823 | 8.51
|  | Cum | 1 | 1 | 4.343 | 0.76 | 0.823 | 2.72
|  | Cum | 1 | 1 | 4.748 | 0.76 | 0.823 | 2.97
|  | Cum | 1 | 1 | 0.374 | 0.76 | 0.823 | 0.23
| Earth Excavation for green Planter wall BH-07 (west side) | Cum | 1 | 1 | 1.359 | 0.76 | 0.823 | 0.85
|  | Cum | 1 | 1 | 26.229 | 0.76 | 0.823 | 16.41
| Fire Tender Wall towards BH-01 | Cum | 1 | 1 | 10.508 | 0.76 | 0.823 | 6.57
|  | Cum | 1 | 1 | 1.639 | 0.76 | 0.823 | 1.03
|  | Cum | 1 | 1 | 2.059 | 0.76 | 0.823 | 1.29
|  | Cum | 1 | 1 | 2.938 | 0.76 | 0.823 | 1.84
|  | Cum | 1 | 1 | 7.795 | 0.76 | 0.823 | 4.88
|  | Cum | 1 | 1 | 2.063 | 0.76 | 0.823 | 1.29
|  | Cum | 1 | 1 | 1.079 | 0.76 | 0.823 | 0.67
|  | Cum | 1 | 1 | 3.273 | 0.76 | 0.823 | 2.05
|  | Cum | 1 | 1 | 5.084 | 0.76 | 0.823 | 3.18
| Fire Tender Wall Brick Work between BH-04 & BH-07 near green Planter (triangle type) | Cum | 0 | 1 | 1.398 | 0.76 | 0.823
|  | Cum | 0 | 1 | 6.182 | 0.76 | 0.823
|  | Cum | 0 | 1 | 0.23 | 0.76 | 0.823
|  | Cum | 0 | 1 | 8.695 | 0.76 | 0.823
|  | CUM | 1 | 1 | 16.409 | 0.76 | 0.823 | 10.26
| Earth Excavation for fire tender in green planter between BH-04 & BH-07 | Cum | 0 | 1 | 0.898 | 0.76 | 0.823
|  | Cum | 0 | 1 | 1.497 | 0.76 | 0.823
|  | Cum | 0 | 1 | 1.602 | 0.76 | 0.823
|  | Cum | 0 | 1 | 1.012 | 0.76 | 0.823
|  | Cum | 0 | 1 | 4.172 | 0.76 | 0.823
|  | Cum | 0 | 1 | 10.42 | 0.76 | 0.823
|  | Cum | 0 | 1 | 0.217 | 0.76 | 0.823
|  | Cum | 0 | 1 | 4.011 | 0.76 | 0.823
|  | CUM | 1 | 1 | 23.472 | 0.76 | 0.823 | 14.68
| Fire Tender Wall Brick Work connect to BH-04 to green Planter between BH-01 & waterbody | Cum | 1 | 1 | 15.694 | 0.76 | 0.823 | 9.82
|  | Cum | 1 | 1 | 0.225 | 0.76 | 0.823 | 0.14
| Earth Excavation for Fire Tender in Green planter between BH-01 & Waterbody | Cum | 1 | 1 | 1.497 | 0.76 | 0.823 | 0.94
|  | Cum | 1 | 1 | 1.6 | 0.76 | 0.823 | 1
|  | Cum | 1 | 1 | 3.43 | 0.76 | 0.823 | 2.15
|  | Cum | 1 | 1 | 1.497 | 0.76 | 0.823 | 0.94
|  | Cum | 1 | 1 | 3.735 | 0.76 | 0.823 | 2.34
|  | Cum | 1 | 1 | 4.345 | 0.76 | 0.823 | 2.72
| Fire Tender Wall Brick Work BH-01 west corner to Canteen parallel to road betwee canteen & BH-02 | Cum | 1 | 1 | 2.386 | 0.76 | 0.823 | 1.49
|  | Cum | 1 | 1 | 20.003 | 0.76 | 0.823 | 12.51
| parallel to canteen | Cum | 1 | 1 | 33.031 | 0.76 | 0.823 | 20.66
| parallel to BH-02 towards canteen (east face) | Cum | 1 | 1 | 31.771 | 0.76 | 0.823 | 19.87
|  | Cum | 1 | 1 | 4.375 | 0.76 | 0.823 | 2.74
|  | Cum | 1 | 1 | 0.17 | 0.76 | 0.823 | 0.11
Fire Tender Wall Brick Work for Road between BH-02 & Waterbody
| wall towards BH-02 (BH-02 to Gym toilet) | Cum | 1 | 1 | 18.473 | 0.76 | 0.823 | 11.55
|  | Cum | 1 | 1 | 9.868 | 0.76 | 0.823 | 6.17
|  | Cum | 1 | 1 | 7.05 | 0.76 | 0.823 | 4.41
fire tender wall towards waterbody planter to arround waterbody to Reception
|  | CUM | 1 | 1 | 36.696 | 0.76 | 0.823 | 22.95
|  | Cum | 0 | 1 | 0.337 | 0.76 | 0.823
|  | Cum | 0 | 1 | 3.183 | 0.76 | 0.823
|  | Cum | 0 | 1 | 33.632 | 0.76 | 0.823
| in planter | Cum | 1 | 1 | 8.053 | 0.76 | 0.823 | 5.04
| fire tender wall west side of reception | Cum | 1 | 1 | 14.555 | 0.76 | 0.823 | 9.1
Fire Tender Wall Brick Work for Road South side of BH-04 (back side)
|  | Cum | 1 | 1 | 14.343 | 0.76 | 0.823 | 8.97
Fire Tender Wall Brick Work for Road BH-04 (near watebody to basket ball ground planter) to BH-03
|  | Cum | 1 | 1 | 60.78 | 0.76 | 0.823 | 38.02
| basket ball ground planter to BH-03 corner(front of Gym) | Cum | 1 | 1 | 35.253 | 0.76 | 0.823 | 22.05
Deduct Previous Bill Qty. for Revise
Earth Excavation for Fire Tender Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 |  | -1 | 1 | 31.4 | 0.61 | 0.823 | -15.76
| FIRE TENDER TOE WALL WITH BH-07 |  | -1 | 1 | 42.55 | 0.61 | 0.823 | -21.36
| Earth Excavation for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
Earth Excavation for Road Toe Wall (1/E-J)
| Previous bill qty. release 2nos panal | Cum | 1 | 2 | 7.625 | 0.76 | 0.823 | 9.54
Earth Excavation Qty. Revise due to correction
Earth Excavation for Road Toe Wall back side of Basket Ball (east side)
|  |  | 1 | 3 | 7.625 | 0.76 | 0.823 | 14.31
Excavation for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | 1 | 8 | 7.625 | 0.76 | 0.823 | 38.15
|  | Cum | 1 | 1 | 9.35 | 0.76 | 0.823 | 5.85
| Earth Excavation for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
| P.C.C. P/L for Road Toe Wall (1/E-J) | Cum | 1 | 1 | 4.635 | 0.76 | 0.823 | 2.9
|  | Cum | 1 | 8 | 7.625 | 0.76 | 0.823 | 38.15
|  | Cum | 1 | 1 | 10.14 | 0.76 | 0.823 | 6.34
| Earth Excavation for Road Toe Wall (J/1-9) | Cum | 1 | 1 | 8.097 | 0.76 | 0.823 | 5.06
|  | Cum | 1 | 5 | 7.625 | 0.76 | 0.823 | 23.85
|  | Cum | 1 | 1 | 0.265 | 0.76 | 0.823 | 0.17
| Earth Excavation for Road Toe Wall (9/H-J) | Cum | 1 | 1 | 7.38 | 0.76 | 0.823 | 4.62
|  | Cum | 1 | 2 | 7.625 | 0.76 | 0.823 | 9.54
Previous Bill Qty. deduct for revision
Earth Excavation for Road Toe Wall back side of Basket Ball (east side)
|  |  | -1 | 3 | 7.625 | 0.61 | 0.823 | -11.48
Excavation for Road Toe wall outer parapheri BG-02 to Gym North side
|  | Cum | -1 | 8 | 7.625 | 0.61 | 0.823 | -30.62
|  | Cum | -1 | 1 | 9.35 | 0.61 | 0.823 | -4.69
| Earth Excavation for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | Cum
| Earth Excavation for Road Toe Wall (1/E-J) | Cum | -1 | 1 | 4.635 | 0.61 | 0.823 | -2.33
|  | Cum | -1 | 8 | 7.625 | 0.61 | 0.823 | -30.62
|  | Cum | -1 | 1 | 10.14 | 0.61 | 0.823 | -5.09
| Earth Excavation for Road Toe Wall (J/1-9) | Cum | -1 | 1 | 14.06 | 0.61 | 0.823 | -7.06
|  | Cum | -1 | 5 | 7.625 | 0.61 | 0.823 | -19.14
|  | Cum | -1 | 1 | 0.265 | 0.61 | 0.823 | -0.13
| Earth Excavation for Road Toe Wall (9/H-J) | Cum | -1 | 1 | 7.53 | 0.61 | 0.823 | -3.78
|  | Cum | -1 | 2 | 7.625 | 0.61 | 0.823 | -7.66
Earth Excavation for Sump in Waterbody
| EXCAVATION P.C.C. or Stone Soling in Waterbody for Sump (900x900x850) | Cum | 1 | 5 | 1.9 | 1.9 | 0.85 | 15.34
| EXCAVATION P.C.C. or Stone Soling in Waterbody for Filter Pit (2000x2000x1800) | Cum | 1 | 1 | 2.83 | 2.83 | 2.1 | 16.82
1 | Earth Excavation for Brick Work for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22)
1.1 | longitudianal axies | Cum | 1 | 2 | 7.07 | 0.76 | 0.15 | 1.61
1.2 | longitudianal axies | Cum | 1 | 2 | 6.245 | 0.76 | 0.15 | 1.42
2 | Earth Excavation for Brick Work for Green Planter South side of BH-03 towards Basket Ball Ground (Drg. No. TU/LA-P-206.1) (26'-27'/46-51)
2.1 | longitudianal axies | Cum | 1 | 2 | 7.07 | 0.76 | 0.15 | 1.61
2.2 | longitudianal axies | Cum | 1 | 2 | 6.245 | 0.76 | 0.15 | 1.42
3 | Earth Excavation for Brick Work for Green Planter West side of BH-02 under transfer slab (Drg. No. TU/LA-P-206.1) (7'-14'/32-33)
3.1 | longitudianal axies | Cum | 1 | 2 | 7.07 | 0.76 | 0.15 | 1.61
3.2 | longitudianal axies | Cum | 1 | 2 | 6.245 | 0.76 | 0.15 | 1.42
3.3 | longitudianal axies | Cum | 1 | 2 | 3.845 | 0.76 | 0.15 | 0.88
3.4 | longitudianal axies | Cum | 1 | 2 | 3.62 | 0.76 | 0.15 | 0.83
Excavation under WBM area-
| Stone Agg. 90 to 45mm in Basket Ball Ground | [8 empty] | Depth as per level sheet attached
|  | Cum | 1 | 1 | 27.54 | 14.74 | 0.823 | 334.09 |  | D=(0.809+0.661+1.078+0.797+0.782+0.808)/6
0
| Stone Agg. 90 to 45mm in Road |  | 0
| Road between BH-05 & B3 Basket Ground | Cum | 1 | 1 | 29.2 | 6 | 0.823 | 144.19
|  | Cum | 1 | 1 | 8.32 | 6.78 | 0.823 | 46.43
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 23.235 | 6 | 0.823 | 114.73
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 2.275 | 6 | 0.823 | 11.23
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 32.39 | 6 | 0.823 | 159.94
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 5.295 | 6 | 0.823 | 26.15
0
| Road between BH-01 & Waterboy (east side) | Cum | 1 | 1 | 31.463 | 6 | 0.823 | 155.36
| Road between BH-01 & BH-07 (south side) | Cum | 1 | 1 | 33.193 | 6 | 0.823 | 163.91
|  | Cum | 1 | 1 | 29.854 | 6 | 0.823 | 147.42
|  | Cum | 1 | 1 | 33.667 | 6 | 0.823 | 166.25
|  | Cum | 1 | 1 | 12.3 | 6 | 0.823 | 60.74
0
| Stone Agg. 90 to 45mm in Planter Area |  | 0
| Planter Front of Basket Ground (west side) | Cum | 1 | 1 | 6.38 | 1.975 | 0.823 | 10.37
|  | Cum | 1 | 2 | 6.95 | 1.975 | 0.823 | 22.59
|  | Cum | 1 | 1 | 6.12 | 1.67 | 0.823 | 8.41
|  | Cum | 1 | 1 | 4.645 | 1.975 | 0.823 | 7.55
0
|  | Cum | 1 | 1 | 6.885 | 1.27 | 0.823 | 7.2
|  | Cum | 1 | 1 | 2.385 | 2.26 | 0.823 | 4.44
| space between basket ground & planter | Cum | 1 | 1 | 20.17 | 2.125 | 0.823 | 35.27
0
| planter front of Bh-05 (west side) | Cum | 1 | 1 | 12.58 | 1.19 | 0.823 | 12.32
|  | Cum | 1 | 1 | 7.09 | 0.9 | 0.823 | 5.25
|  | Cum | 1 | 1 | 1.6 | 5.98 | 0.823 | 7.87
|  | Cum | 1 | 1 | 1.6 | 4.18 | 0.823 | 5.5
|  | Cum | 1 | 2 | 1.6 | 2.38 | 0.823 | 6.27
|  | Cum | 1 | 1 | 1.145 | 0.9 | 0.823 | 0.85
0
|  | Cum | 1 | 1 | 2.745 | 1.5 | 0.823 | 3.39
|  | Cum | 1 | 1 | 1.6 | 6.675 | 0.823 | 8.79
|  | Cum | 1 | 1 | 3.07 | 1.065 | 0.823 | 2.69
|  | Cum | 1 | 1 | 1.6 | 3.9 | 0.823 | 5.14
|  | Cum | 1 | 1 | 2.77 | 0.96 | 0.823 | 2.19
|  | Cum | 1 | 1 | 1.6 | 4.09 | 0.823 | 5.39
|  | Cum | 1 | 1 | 3.25 | 1.095 | 0.823 | 2.93
|  | Cum | 1 | 1 | 8.61 | 4.615 | 0.823 | 32.7
0
| Stone agg. In planter front between Bh-07 & BH-04 | Cum | 1 | 1 | 1.6 | 8.56 | 0.823 | 11.27
|  | Cum | 1 | 1 | 1.6 | 6.85 | 0.823 | 9.02
|  | Cum | 1 | 1 | 1.6 | 7.45 | 0.823 | 9.81
|  | Cum | 1 | 1 | 0.99 | 8.85 | 0.823 | 7.21
|  | Cum | 1 | 1 | 1.6 | 4.89 | 0.823 | 6.44
|  | Cum | 1 | 1 | 1.6 | 5.33 | 0.823 | 7.02
|  | Cum | 1 | 1 | 1.6 | 1.45 | 0.823 | 1.91
|  | Cum | 1 | 1 | 1.6 | 3.83 | 0.823 | 5.04
|  | Cum | 1 | 1 | 1.415 | 2.425 | 0.823 | 2.82
|  | Cum | 1 | 1 | 0.755 | 1.965 | 0.823 | 1.22
|  | Cum | 1 | 1 | 5.465 | 4.2 | 0.823 | 18.89
0
| Stone agg. In planter east side of BH-1 or front of Water Body | Cum | 1 | 1 | 1.6 | 4 | 0.823 | 5.27
|  | Cum | 1 | 1 | 1.6 | 1 | 0.823 | 1.32
|  | Cum | 1 | 1 | 5.49 | 0.965 | 0.823 | 4.36
|  | Cum | 1 | 1 | 7.09 | 1 | 0.823 | 5.84
|  | Cum | 1 | 1 | 1.6 | 3 | 0.823 | 3.95
|  | Cum | 1 | 1 | 4.345 | 1 | 0.823 | 3.58
|  | Cum | 1 | 1 | 1.6 | 4 | 0.823 | 5.27
|  | Cum | 1 | 2 | 1.6 | 3 | 0.823 | 7.9
0
|  | Cum | 1 | 1 | 20.145 | 2.235 | 0.823 | 37.05
|  | Cum | 1 | 1 | 1.845 | 4.07 | 0.823 | 6.18
0
|  | Cum | 1 | 1 | 0.685 | 4.13 | 0.823 | 2.33
|  | Cum | 1 | 1 | 3.43 | 1.2 | 0.823 | 3.39
|  | Cum | 1 | 1 | 1.6 | 3 | 0.823 | 3.95
|  | Cum | 1 | 1 | 3.735 | 1.2 | 0.823 | 3.69
|  | Cum | 1 | 1 | 3.43 | 4.235 | 0.823 | 11.95
|  | Cum | 1 | 1 | 1.6 | 1.8 | 0.823 | 2.37
|  | Cum | 1 | 1 | 1.6 | 4.2 | 0.823 | 5.53
|  | Cum | 1 | 1 | 1.6 | 5 | 0.823 | 6.58
|  | Cum | 1 | 1 | 2.135 | 3.235 | 0.823 | 5.68
|  | Cum | 1 | 1 | 3.735 | 3.2 | 0.823 | 9.84
|  | Cum | 1 | 1 | 12.12 | 1.5 | 0.823 | 14.96
|  | Cum | 1 | 1 | 0.99 | 4.13 | 0.823 | 3.37
|  | Cum | 1 | 1 | 1.6 | 4.5 | 0.823 | 5.93
|  | Cum | 1 | 1 | 1.46 | 2.7 | 0.823 | 3.24
|  | Cum | 1 | 1 | 1.6 | 6 | 0.823 | 7.9
0
|  | Cum | 1 | 1 | 20.97 | 2 | 0.823 | 34.52
|  | Cum | 1 | 1 | 1.905 | 6.235 | 0.823 | 9.78
|  | Cum | 0 | 1 | 1.145 | 2 | 0.823
0
|  | Cum | 1 | 1 | 4.345 | 1.2 | 0.823 | 4.29
|  | Cum | 1 | 1 | 1.6 | 1.8 | 0.823 | 2.37
|  | Cum | 1 | 1 | 4.65 | 1 | 0.823 | 3.83
|  | Cum | 1 | 1 | 1.905 | 1.8 | 0.823 | 2.82
| Stone Agg. 90 to 45mm in Ramp Area Front side of Gym (West side) |  | 0
|  | Cum | 1 | 1 | 24.135 | 6.2 | 0.823 | 123.15
| This bill measurement- Item no 6 |  | 0
| WBM P/L for Road Work | Cum
| Area-1, Road between Waterbody & BH-02 (remaining portion) | Cum | 1 | 1 | 45.5268 |  | 0.125 | 5.69 |  | area
| Area-2, Road between Canteen & BH-02 | Cum | 1 | 1 | 235.971 |  | 0.125 | 29.5 |  | area
| Area-3, Road south side of BH-04 | Cum | 1 | 1 | 229.3859 |  | 0.125 | 28.67 |  | area
| Area-4, Road between BH-03 & Gym | Cum | 1 | 1 | 161.3012 |  | 0.125 | 20.16 |  | area
| LESS THIS BILL QUANTITY | Cum | -1 |  | 2244.41 |  |  | -2244.41
| UP TO PREVIOUS BILL | Cum | [6 empty] | 2106.33
| Eacavation for Light Pole Foundation near Basket Ball Ground (900x900) | Cum | 2 | 1 | 1.1 | 1.1 | 1.2 | 2.9
| Excavation for Basket Ball Ground Pole Foundation (1500x1500) | Cum | 2 | 1 | 1.7 | 1.7 | 1.975 | 11.42
Cum
| THIS BILL TOTAL → | Cum | [6 empty] | 14.32
2120.65
NS-02 | Supplying and Filling in plinth, under floor with fine Approved ghagar or local available sand including ramming, watering, consolidating and dressing complete as per specification and as directed by the Project Manager.
| UP TO PREVIOUS BILL | Cum | [6 empty] | 0
Mesurement same as WBM-
Stone Agg. 90 to 45mm in Basket Ball Ground
|  | Cum | 1 | 0 | 27.54 | 14.74 | 0.3 | 0
| Stone Agg. 90 to 45mm in Road |  | 0
| Road between BH-05 & B3 Basket Ground | Cum | 1 | 0 | 29.2 | 6 | 0.3 | 0
|  | Cum | 1 | 0 | 8.32 | 6.78 | 0.3 | 0
| Road between BH-05 & BH-04 | Cum | 1 | 0 | 23.235 | 6 | 0.3 | 0
| Road between BH-05 & BH-04 | Cum | 1 | 0 | 2.275 | 6 | 0.3 | 0
| Road between BH-05 & BH-04 | Cum | 1 | 0 | 32.39 | 6 | 0.3 | 0
| Road between BH-05 & BH-04 | Cum | 1 | 0 | 5.295 | 6 | 0.3 | 0
0
| Road between BH-01 & Waterboy (east side) | Cum | 1 | 0 | 31.463 | 6 | 0.3 | 0
| Road between BH-01 & BH-07 (south side) | Cum | 1 | 0 | 33.193 | 6 | 0.3 | 0
|  | Cum | 1 | 0 | 29.854 | 6 | 0.3 | 0
|  | Cum | 1 | 0 | 33.667 | 6 | 0.3 | 0
|  | Cum | 1 | 0 | 12.3 | 6 | 0.3 | 0
0
0
|  | Cum | 1 | 1 | 14.5 | 4.7 | 0.4
ASPER CERTIFIED BY COLLIERS (SOFTCOPY & JMR ATTACHED)
| ROAD-1 | CUM | 1 | 1 | 19.476 | 6 | 0.3 | 35.06
| ROAD-2 | CUM | 1 | 1 | 50.243 | 6 | 0.3 | 90.44
| ROAD-3 | CUM | 1 | 1 | 67.397 | 6 | 0.3 | 121.31
| ROAD-4 | CUM | 1 | 1 | 149.302 | 6 | 0.3 | 268.74
| AREA-1 | CUM | 1 | 1 | 33.761 | 1 | 0.3 | 10.13
| AREA-2 | CUM | 1 | 1 | 45.214 | 1 | 0.3 | 13.56
| AREA-3 | CUM | 1 | 1 | 45.514 | 1 | 0.3 | 13.65
| AREA-4 | CUM | 1 | 1 | 11.751 | 1 | 0.3 | 3.53
| Near BH-01 West Side & BH-04 North Side Area | CUM | 1 | 1 | 14.5 | 4.7 | 0.4 | 27.26
|  | CUM | 1 | 1 | 44 | 13 | 0.4 | 228.8
| THIS BILL TOTAL → | Cum | [6 empty] | 812.48 | 6th RA
812.48
NS-03 | Preparation and consolidation of sub grade with power road roller of 8 to 12 tonne capacity, dressing to camber and consolidating with road roller including making good the undulations etc.
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
| Sub Grade Preparation for Road & Floor | Sqm
| Sub Grade Prepration for Basket Ball Ground | Sqm
|  | Sqm | 1 | 1 | 27.54 | 14.19 |  | 390.79
| Sub Grade Prepration for Planter Area | Sqm
| Planter Front of Basket Ground (west side) | Sqm | 1 | 1 | 6.38 | 1.605 |  | 10.24
|  | Sqm | 1 | 2 | 6.64 | 1.605 |  | 21.31
|  | Sqm | 1 | 1 | 5.095 | 1.6 |  | 8.15
|  | Sqm | 1 | 1 | 3.52 | 1.605 |  | 5.65
Sqm
|  | Sqm | 1 | 1 | 6.885 | 1.27 |  | 8.74
|  | Sqm | 1 | 1 | 2.385 | 2.26 |  | 5.39
| space between basket ground & planter | Sqm | 1 | 1 | 18.79 | 2.125 |  | 39.93
Sqm
| planter front of Bh-05 (west side) | Sqm | 1 | 1 | 12.58 | 1.19 |  | 14.97
|  | Sqm | 1 | 1 | 7.09 | 0.9 |  | 6.38
|  | Sqm | 1 | 1 | 1.6 | 5.98 |  | 9.57
|  | Sqm | 1 | 1 | 1.6 | 4.18 |  | 6.69
|  | Sqm | 1 | 2 | 1.6 | 2.38 |  | 7.62
|  | Sqm | 1 | 1 | 1.145 | 0.46 |  | 0.53
Sqm
|  | Sqm | 1 | 1 | 2.745 | 1.195 |  | 3.28
|  | Sqm | 1 | 1 | 1.6 | 6.424 |  | 10.28
|  | Sqm | 0.5 | 1 | 3.07 | 1.065 |  | 1.63
|  | Sqm | 1 | 1 | 1.6 | 3.62 |  | 5.79
|  | Sqm | 0.5 | 1 | 2.77 | 0.96 |  | 1.33
|  | Sqm | 1 | 1 | 1.6 | 3.815 |  | 6.1
|  | Sqm | 0.5 | 1 | 3.25 | 0.58 |  | 0.94
|  | Sqm | 0 | 1 | 8.61 | 4.615
Sqm
| Sub Grade Prepration for planter front between Bh-07 & BH-04 | Sqm | 1 | 1 | 1.6 | 8.11 |  | 12.98
|  | Sqm | 1 | 1 | 1.6 | 6.39 |  | 10.22
|  | Sqm | 1 | 1 | 1.6 | 6.92 |  | 11.07
|  | Sqm | 1 | 1 | 0.99 | 8.85 |  | 8.76
|  | Sqm | 1 | 1 | 1.6 | 4.89 |  | 7.82
|  | Sqm | 0 | 1 | 1.6 | 5.33
|  | Sqm | 0 | 1 | 1.6 | 1.45
|  | Sqm | 1 | 1 | 1.6 | 3.83 |  | 6.13
|  | Sqm | 1 | 1 | 1.415 | 2.425 |  | 3.43
|  | Sqm | 1 | 1 | 0.685 | 1.965 |  | 1.35
|  | Sqm | 0.5 | 1 | 5.465 | 4.2 |  | 11.48
Sqm
| Sub Grade Prepration for planter east side of BH-1 or front of Water Body | Sqm | 1 | 1 | 1.6 | 4 |  | 6.4
|  | Sqm | 1 | 1 | 1.6 | 1 |  | 1.6
|  | Sqm | 1 | 1 | 5.49 | 0.965 |  | 5.3
|  | Sqm | 1 | 1 | 7.09 | 1 |  | 7.09
|  | Sqm | 1 | 1 | 1.6 | 3 |  | 4.8
|  | Sqm | 1 | 1 | 4.345 | 1 |  | 4.35
|  | Sqm | 0 | 1 | 1.6 | 4
|  | Sqm | 1 | 2 | 1.6 | 3 |  | 9.6
Sqm
|  | Sqm | 1 | 1 | 20.145 | 2.235 |  | 45.02
|  | Sqm | 1 | 1 | 1.845 | 4.07 |  | 7.51
Sqm
|  | Sqm | 1 | 1 | 0.685 | 4.13 |  | 2.83
|  | Sqm | 1 | 1 | 3.43 | 1.2 |  | 4.12
|  | Sqm | 1 | 1 | 1.6 | 3 |  | 4.8
|  | Sqm | 1 | 1 | 3.735 | 1.2 |  | 4.48
|  | Sqm | 1 | 1 | 3.43 | 4.2 |  | 14.41
|  | Sqm | 1 | 1 | 1.6 | 1.8 |  | 2.88
|  | Sqm | 1 | 1 | 1.6 | 4.2 |  | 6.72
|  | Sqm | 1 | 1 | 1.6 | 5 |  | 8
|  | Sqm | 0 | 1 | 2.135 | 3.235
|  | Sqm | 1 | 1 | 3.735 | 3.2 |  | 11.95
|  | Sqm | 1 | 1 | 12.12 | 1.5 |  | 18.18
|  | Sqm | 1 | 1 | 0.99 | 4.13 |  | 4.09
|  | Sqm | 1 | 1 | 1.6 | 4.5 |  | 7.2
|  | Sqm | 1 | 1 | 1.46 | 2.7 |  | 3.94
|  | Sqm | 1 | 1 | 1.6 | 6 |  | 9.6
Sqm
|  | Sqm | 1 | 1 | 20.97 | 2 |  | 41.94
|  | Sqm | 1 | 1 | 1.905 | 6.235 |  | 11.88
|  | Sqm | 1 | 1 | 0.706 | 2 |  | 1.41
Sqm
|  | Sqm | 1 | 1 | 4.345 | 1.2 |  | 5.21
|  | Sqm | 1 | 1 | 1.6 | 1.8 |  | 2.88
|  | Sqm | 1 | 1 | 4.65 | 1 |  | 4.65
|  | Sqm | 1 | 1 | 1.905 | 1.8 |  | 3.43
| Sub Grade Prepration for Ramp Area Front side of Gym (West side) | Sqm
|  | Sqm | 1 | 1 | 24.135 | 6.2 |  | 149.64
| Sub Grade Prepration for for Waterbody as per drg. No.(inner dia. 20.12m), dia. For P.C.C. =20.12+0.2*2+0.6*2+0.2*2=22.120m) | Sqm |  |  | area
|  | Sqm | 1 | 1 | 384.0961 |  |  | 384.1
Sqm
| Sub Grade Prepration for Road Area | Sqm
| Area-1, Road between BH-01 & BH-07 | Sqm | 1 | 1 | 514.7 |  |  | 514.7
| Area-2, Road between BH-04 & west corner of BH-01 | Sqm | 1 | 1 | 169.79 |  |  | 169.79
| deduct area not done | Sqm | -1 | 1 | 6.545 | 6 |  | -39.27
| Area-3, Road between BH-01 west side & waterbody | Sqm | 1 | 1 | 580.43 |  |  | 580.43
| Area-4, Road between BH-04 west side | Sqm | 1 | 1 | 628.19 |  |  | 628.19
| Area-5, Road between BH-05 north side & Basket Ball Ground | Sqm | 1 | 1 | 303.47 |  |  | 303.47
| Area-6, Road front BH-05 east side | Sqm | 1 | 1 | 165.9 |  |  | 165.9
|  | Sqm |  |  | L | B
| Sub Grade Prepration for Ramp Area (1/H-J) | Sqm | 1 | 1 | 36.715 | 8.48 |  | 311.34
| Sub Grade Prepration for between BH-01 & Canteen | Sqm | 1 | 1 | 18.1 | 33.615 |  | 608.43
|  | Sqm |  |  | area
| add area near road junction near canteen east corner | Sqm | 1 | 1 | 40.53 |  |  | 40.53
| deduct R.C.C. Existng Col. | Sqm | -1 | 5 | 4.64 |  |  | -23.2
| deduct R.C.C. Planter Area | Sqm | -1 | 6 | 4.49 |  |  | -26.94
|  | Sqm | -1 | 3 | 4.5 |  |  | -13.5
| deduct sheat area | Sqm | -1 | 6 | 1.349 |  |  | -8.09
| Green Planter | Sqm | -1 | 2 | 1.47 | 5.555 |  | -16.33
Sqm
| Sub Grade Prepration for between BH-01 west side | Sqm | 1 | 1 | 364.85 |  |  | 364.85
| deduct existing Plnater | Sqm | -1 | 1 | 34.05 |  |  | -34.05
|  | Sqm | -1 | 1 | 70.8 |  |  | -70.8
|  | Sqm |  |  | area
| Sub Grade Prepration between BH-02 & GYM | Sqm | 1 | 1 | 478.103 |  |  | 478.1
| deduction for seat | Sqm | -1 | 6 | 1.35 |  |  | -8.1
|  | Sqm |  |  | L | B
| deduction for Green Planter | Sqm | -1 | 1 | 2.625 | 1.2 |  | -3.15
|  | Sqm | -1 | 1 | 5.85 | 1.2 |  | -7.02
|  | Sqm | -1 | 1 | 5.025 | 1.2 |  | -6.03
|  | Sqm | -1 | 1 | 2.4 | 1.2 |  | -2.88
Subgrade Prepratition for Boy's Hostel
2 | Subgrade for Ramp for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 1 | 1 | 6 | 1.54 |  | 9.24
|  | Sqm | 1 | 1 | 3.225 | 3 |  | 9.68
2.1 | Subgrade for Entry Area Steps of BH-01
| Steps for Entry | Sqm | 1 | 1 | 5.42 | 4.26 |  | 23.09
area
| Subgrade for side ramp of entrance | Sqm | 1 | 1 | 16 |  |  | 16
3 | Subgrade for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 1 | 1 | 6 | 1.54 |  | 9.24
|  | Sqm | 1 | 1 | 3.225 | 3 |  | 9.68
3.1 | Subgrade for Entry Area Steps of BH-02
| Steps for Entry | Sqm | 1 | 1 | 5.42 | 4.26 |  | 23.09
area
| Subgrade for side ramp of entrance | Sqm | 1 | 1 | 16 |  |  | 16
4 | Subgrade for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 1 | 1 | 6 | 1.54 |  | 9.24
|  | Sqm | 1 | 1 | 3.225 | 3 |  | 9.68
4.1 | Subgrade for Entry Area Steps of BH-03
| Steps for Entry | Sqm | 1 | 1 | 5.42 | 4.26 |  | 23.09
area
| Subgrade for side ramp of entrance | Sqm | 1 | 1 | 16 |  |  | 16
5 | Subgrade for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 1 | 1 | 6 | 1.54 |  | 9.24
|  | Sqm | 1 | 1 | 3.225 | 3 |  | 9.68
5.1 | Subgrade for Entry Area Steps of BH-04
| Steps for Entry | Sqm | 1 | 1 | 5.42 | 4.26 |  | 23.09
area
| Subgrade for side ramp of entrance | Sqm | 1 | 1 | 16 |  |  | 16
9 | Subgrade for Floor (area side of Road line) Laying of Kandla Stone |  |  |  | Area
| Area-1, area between BH-01 & BH-07 south side of Road | Sqm | 1 | 1 | 300.0786 |  |  | 300.08
| Area-2, BH-01 south side main entrance | Sqm | 1 | 1 | 160.0868 |  |  | 160.09
| deduct Green Planter Area | Sqm | -1 | 1 | 19.47 |  |  | -19.47
| Area-3, BH-01 south side main entrance | Sqm | 1 | 1 | 45.5218 |  |  | 45.52
| Area-4, BH-01 south side main entrance | Sqm | 1 | 1 | 241.8989 |  |  | 241.9
| deduct Green Planter Area | Sqm | -1 | 1 | 50.7604 |  |  | -50.76
| deduct Green Planter Area | Sqm | -1 | 1 | 43.292 |  |  | -43.29
| Area-5, BH-04 south side main entrance | Sqm | 1 | 1 | 61.0155 |  |  | 61.02
| deduct Green Planter Area | Sqm | -1 | 1 | 12.2755 |  |  | -12.28
| Area-6, Area between BH-04 & BH-02 , waterbody surrounding area | Sqm | 1 | 1 | 628.5243 |  |  | 628.52
| deduct Waterbody Area | Sqm | -1 | 1 | 341.7578 |  |  | -341.76
| deduct seat | Sqm | -1 | 8 | 2.836 | 0.286 |  | -6.49
| Area-7, Area under BH-04 transfer Slab towards waterbody | Sqm | 1 | 1 | 615.412 |  |  | 615.41
| deduct Green Planter area | Sqm | -1 | 1 | 3.155 | 1.799 |  | -5.68
|  | Sqm | -1 | 1 | 5.85 | 1.799 |  | -10.52
|  | Sqm | -1 | 1 | 5.025 | 1.799 |  | -9.04
| deduct for Entrance Ramp | Sqm | -1 | 1 | 3.823 | 3 |  | -11.47
| deduct for Entrance Ramp | Sqm | -1 | 1 | 6 | 2 |  | -12
| deduct R.C.C. Wall/Col. | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
|  | Sqm | -1 | 8 | 4.5 | 1 |  | -36
| deduct seat | Sqm | -1 | 7 | 2.836 | 0.286 |  | -5.68
area
| deduct Green Planter south side of Reception | Sqm | -1 | 1 | 40.6167 |  |  | -40.62
| Area-8, west side of reception (front of Basket ball ground & BH-03) | Sqm | 1 | 1 | 23.3075 |  |  | 23.31
| Area-9, north side of reception | Sqm | 1 | 1 | 68.8563 |  |  | 68.86
| deduct Green Planter area | Sqm | -1 | 1 | 9.36 | 0.6 |  | -5.62
|  | Sqm | -1 | 1 | 8.14 | 0.6 |  | -4.88
|  | Sqm | -1 | 1 | 6.616 | 0.6 |  | -3.97
|  | Sqm | -1 | 1 | 4.785 | 0.6 |  | -2.87
|  | Sqm | -1 | 1 | 3.26 | 0.6 |  | -1.96
| Area-10, area between BH-01 & Canteen, or under transfer slab | Sqm | 1 | 1 | 608.4315 |  |  | 608.43
| deduct green planter of BH-01 north face | Sqm | -1 | 1 | 5.025 | 1.194 |  | -6
|  | Sqm | -1 | 1 | 5.85 | 1.197 |  | -7
| deduct R.C.C. Planter area under transfer dalb BH-01 | Sqm | -1 | 9 | 4.5 | 1 |  | -40.5
| deduct R.C.C. shear wall | Sqm | -1 | 5 | 5 | 0.8 |  | -20
| deduct seat | Sqm | -1 | 6 | 2.836 | 0.286 |  | -4.87
|  | Sqm | -1 | 3 | 1.2 | 0.375 |  | -1.35
| deduct for Entrance Ramp | Sqm | -1 | 1 | 3.823 | 3 |  | -11.47
| deduct for Entrance Ramp | Sqm | -1 | 1 | 6 | 2 |  | -12
area
| Area-11, at junction of Road near canteen & BH-01 towards waterbody | Sqm | 1 | 1 | 77.1675 |  |  | 77.17
| Area-12, area east side of BH-01 | Sqm | 1 | 1 | 294.171 |  |  | 294.17
| deduct Green planter of BH-01 east face | Sqm | -1 | 1 | 28.785 |  |  | -28.78
|  | Sqm | -1 | 1 | 23.2452 |  |  | -23.25
| Area-13, area south side of BH-02 (long Planter) | Sqm | 1 | 3 | 2.987 | 1.55 |  | 13.89
|  | Sqm | 1 | 1 | 2.987 | 2 |  | 5.97
|  | Sqm | 1 | 1 | 2.987 | 1.3 |  | 3.88
|  | Sqm | 1 | 1 | 2.987 | 1.8 |  | 5.38
|  | Sqm | 1 | 1 | 5.1077 |  |  | 5.11
|  | Sqm | 1 | 1 | 7.194 |  |  | 7.19
|  | Sqm | 1 | 1 | 10.7681 |  |  | 10.77
|  | Sqm | 1 | 1 | 10.941 |  |  | 10.94
|  | Sqm | 1 | 1 | 17.5006 |  |  | 17.5
| Area-14, area south side of Toilet near Gym | Sqm | 1 | 1 | 67.2189 |  |  | 67.22
| deduct Green Planter area | Sqm | -1 | 2 | 6.639 | 0.6 |  | -7.97
|  | Sqm | -1 | 1 | 5.725 | 0.6 |  | -3.44
|  | Sqm | -1 | 1 | 3.589 | 0.6 |  | -2.15
| Area-15, area between BH-02 long Planter & Toilet of Gym | Sqm | 1 | 1 | 135.0703 |  |  | 135.07
| Area-16, area between BH-02 & GYM Transfer Slab | Sqm | 1 | 1 | 500.2299 |  |  | 500.23
| deduct Green Planter | Sqm | -1 | 1 | 0.999 | 1.2 |  | -1.2
|  | Sqm | -1 | 1 | 5.85 | 1.2 |  | -7.02
|  | Sqm | -1 | 1 | 5.024 | 1.2 |  | -6.03
|  | Sqm | -1 | 1 | 2.399 | 1.2 |  | -2.88
| deduct for Entrance Ramp | Sqm | -1 | 1 | 3.823 | 3 |  | -11.47
| deduct for Entrance Ramp | Sqm | -1 | 1 | 6 | 2 |  | -12
| deduct R.C.C. wall Col. | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
| deduct R.C.C. Planter area under transfer slab BH-02 | Sqm | -1 | 8 | 4.5 | 1 |  | -36
| deduct seat | Sqm | -1 | 6 | 2.836 | 0.286 |  | -4.87
| Area-17, Area north side of BH-02 | Sqm | 1 | 1 | 293.7889 |  |  | 293.79
| deduct green planter area | Sqm | -1 | 1 | 61.3885 |  |  | -61.39
| Area-18, Area north side of Canteen (J/1'-4') | Sqm | 1 | 1 | 31.5 | 1.985 |  | 62.53
| deduct Col. | Sqm | -1 | 4 | 1.2 | 0.375 |  | -1.8
| Area-19, Area north side gallary of BH-02 corner to Gym corner (J/5-9') | Sqm | 1 | 1 | 37.9 | 4.505 |  | 170.74
| deduct Col. | Sqm | -1 | 5 | 1.2 | 0.375 |  | -2.25
| Area-20, Area west side of canteen or north side of B H-03 | Sqm | 1 | 1 | 24.6285 | 13.365 |  | 329.16
| deduct Col. | Sqm | -1 | 5 | 1.2 | 0.375 |  | -2.25
| deduct Green Planter | Sqm | -1 | 1 | 82.6623 |  |  | -82.66
| Area-21, Area south side of Gym (8/H) | Sqm | 1 | 1 | 93.578 |  |  | 93.58
| Area-22, Area between Basket Ball Ground & BH-03, under Transfer slab | Sqm | 1 | 1 | 508.5971 |  |  | 508.6
| add area near road junction | Sqm | 1 | 1 | 47.9965 |  |  | 48
| deduct Green Planter | Sqm | -1 | 1 | 5.025 | 1.2 |  | -6.03
|  | Sqm | -1 | 1 | 5.85 | 1.2 |  | -7.02
| deduct for Entrance Ramp | Sqm | -1 | 1 | 3.823 | 3 |  | -11.47
| deduct for Entrance Ramp | Sqm | -1 | 1 | 6 | 2 |  | -12
| deduct R.C.C. wall Col. | Sqm | -1 | 5 | 5.8 | 0.8 |  | -23.2
| deduct R.C.C. Planter area under transfer slab BH-02 | Sqm | -1 | 8 | 4.5 | 1 |  | -36
| deduct seat | Sqm | -1 | 4 | 2.836 | 0.286 |  | -3.24
| deduct Col. | Sqm | -1 | 2 | 1.2 | 0.375 |  | -0.9
| Area-23, Area east side of BH-03 parallel to road | Sqm | 1 | 1 | 103.5326 |  |  | 103.53
| Area-24, Area east side of BH-02 parallel to road (Road between BH-02 & Canteen) | Sqm | 1 | 1 | 60.3692 |  |  | 60.37
| Area-24, towards canteen east of road (Road between BH-02 & Canteen) | Sqm | 1 | 1 | 17.9818 |  |  | 17.98
| Area-25, area between road of Basket ball ground & BH-05 | Sqm | 1 | 1 | 82.809 |  |  | 82.81
Subgrade for Road Work
| Area-1, Road between Waterbody & BH-02 (remaining portion) | Sqm | 1 | 1 | 43.026 |  |  | 43.03
| Area-2, Road between Canteen & BH-02 | Sqm | 1 | 1 | 235.971 |  |  | 235.97
| Area-3, Road south side of BH-04 | Sqm | 1 | 1 | 229.3859 |  |  | 229.39
| Area-4, Road between BH-03 & Gym | Sqm | 1 | 1 | 161.3012 |  |  | 161.3
Revise Qty. due to correction in 3rd R.A.Bill
| Area-2, Road between BH-04 & west corner of BH-01 | Sqm | 0 | 1 | 169.79
| add area for correction | Sqm | 1 | 1 | 6.545 | 6 |  | 39.27
| deduct area not done (revise measurement) | Sqm | -1 | 1 | 4.798 | 6 |  | -28.79
1 | Sub Grade preparation at west side of Basket ball ground (34'-39'/51-52)
|  | Sqm | 1 | 1 | 14.677 | 0.97 |  | 14.24
| deduct R.C.C. Col. | Sqm | -1 | 2 | 1.2 | 0.375 |  | -0.9
2 | Sub Grade preparation north side of BH-01, between BH-01 Entrance Door & Green Planter towards canteen
|  | Sqm | 1 | 1 | 15 | 0.6 |  | 9
3 | Sub Grade preparation north side of BH-04, between BH-04 Entrance Door & Green Planter towards waterbody
|  | Sqm | 1 | 1 | 15 | 0.6 |  | 9
| THIS BILL TOTAL → | Sqm | [6 empty] | 10795.98 | 6th RA
10795.98
NS-04 | Footing, raft, stitching slab, pedestals,pile caps, etc.,
| Planter BH-01 NORTH SIDE (SHUTT) | Sqm | 2 |  | 11.15 |  | 0.2 | 4.46 |  | 4A
| G 32-37/1-5 vertical | Sqm | 4 |  | 8.92 |  | 0.2 | 7.14 |  | 4A
|  | Sqm | 2 |  | 9.78 |  | 0.2 | 3.91 |  | 4A
|  | Sqm | 2 |  | 6.52 |  | 0.2 | 2.61 |  | 4A
|  | Sqm | 2 |  | 6.22 |  | 0.2 | 2.49 |  | 4A
|  | Sqm | 2 |  | 6.45 |  | 0.2 | 2.58 |  | 4A
|  | Sqm | 2 |  | 4.66 |  | 0.2 | 1.86 |  | 4A
|  | Sqm | 2 |  | 6.89 |  | 0.2 | 2.76 |  | 4A
| G32-37/1-5 HORIZONTAL | Sqm | 10 |  | 0.615 |  | 0.2 | 1.23 |  | 4A
|  | Sqm | 2 |  | 3.82 |  | 0.2 | 1.53 |  | 4A
|  | Sqm | 8 |  | 1.67 |  | 0.2 | 2.67 |  | 4A
|  | Sqm | 6 |  | 2.515 |  | 0.2 | 3.02 |  | 4A
| BH01-NORTH SIDE | Sqm | 2 |  | 5.99 |  | 0.2 | 2.4 |  | 4A
| Bet G 31-28 /1-5 vertical | Sqm | 2 |  | 3.99 |  | 0.2 | 1.6 |  | 4A
|  | Sqm | 4 |  | 2.19 |  | 0.2 | 1.75 |  | 4A
|  | Sqm | 4 |  | 2.79 |  | 0.2 | 2.23 |  | 4A
|  | Sqm | 2 |  | 1.66 |  | 0.2 | 0.66 |  | 4A
|  | Sqm | 2 |  | 3.89 |  | 0.2 | 1.56 |  | 4A
| Bet. G 31-28/1-5 horizontal | Sqm | 10 |  | 0.615 |  | 0.2 | 1.23 |  | 4A
|  | Sqm | 6 |  | 2.515 |  | 0.2 | 3.02 |  | 4A
|  | Sqm | 6 |  | 1.67 |  | 0.2 | 2 |  | 4A
| BH-02 EAST SIDE BET G 20-28/1-6 VERTICAL | Sqm | 2 |  | 9.615 |  | 0.2 | 3.85 |  | 4A
|  | Sqm | 4 |  | 7.245 |  | 0.2 | 5.8 |  | 4A
|  | Sqm | 2 |  | 7.475 |  | 0.2 | 2.99 |  | 4A
|  | Sqm | 2 |  | 3.87 |  | 0.2 | 1.55 |  | 4A
|  | Sqm | 2 |  | 4.1 |  | 0.2 | 1.64 |  | 4A
|  | Sqm | 4 |  | 4.195 |  | 0.2 | 3.36 |  | 4A
|  | Sqm | 2 |  | 3.555 |  | 0.2 | 1.42 |  | 4A
|  | Sqm | 2 |  | 3.785 |  | 0.2 | 1.51 |  | 4A
|  | Sqm | 2 |  | 2.64 |  | 0.2 | 1.06 |  | 4A
|  | Sqm | 2 |  | 2.87 |  | 0.2 | 1.15 |  | 4A
|  | Sqm | 4 |  | 2.26 |  | 0.2 | 1.81 |  | 4A
|  | Sqm | 2 |  | 2.57 |  | 0.2 | 1.03 |  | 4A
| BH-02 EAST SIDE BET G 20-28/1-6 Horizontal | Sqm | 10 |  | 0.6 |  | 0.2 | 1.2 |  | 4A
|  | Sqm | 12 |  | 1.54 |  | 0.2 | 3.7 |  | 4A
|  | Sqm | 2 |  | 3.205 |  | 0.2 | 1.28 |  | 4A
|  | Sqm | 8 |  | 2.37 |  | 0.2 | 3.79 |  | 4A
|  | Sqm | 2 |  | 2.6 |  | 0.2 | 1.04 |  | 4A
|  | Sqm | 2 |  | 3.2 |  | 0.2 | 1.28 |  | 4A
| PLANTER BET -01 AND WATER BODY VERTICAL | Sqm | 2 |  | 9.26 |  | 0.2 | 3.7 |  | 4A
| BET.G 17-21/20-25 | Sqm | 2 |  | 7.46 |  | 0.2 | 2.98 |  | 4A
|  | Sqm | 2 |  | 8.46 |  | 0.2 | 3.38 |  | 4A
|  | Sqm | 2 |  | 8.23 |  | 0.2 | 3.29 |  | 4A
|  | Sqm | 4 |  | 7.46 |  | 0.2 | 5.97 |  | 4A
|  | Sqm | 2 |  | 4.96 |  | 0.2 | 1.98 |  | 4A
|  | Sqm | 4 |  | 4.73 |  | 0.2 | 3.78 |  | 4A
|  | Sqm | 2 |  | 7.96 |  | 0.2 | 3.18 |  | 4A
| PLANTER BET -01 AND WATER BODY HORIZONTAL | Sqm | 16 |  | 0.615 |  | 0.2 | 1.97 |  | 4A
| BET.G 17-21/20-25 | Sqm | 4 |  | 1.975 |  | 0.2 | 1.58 |  | 4A
|  | Sqm | 4 |  | 2.515 |  | 0.2 | 2.01 |  | 4A
|  | Sqm | 8 |  | 1.67 |  | 0.2 | 2.67 |  | 4A
| PLANTER BET -01 AND WATER BODY VERTICAL | Sqm | 2 |  | 8.46 |  | 0.2 | 3.38 |  | 4A
| BET.G 17-21/25-29 | Sqm | 2 |  | 6.43 |  | 0.2 | 2.57 |  | 4A
|  | Sqm | 4 |  | 6.66 |  | 0.2 | 5.33 |  | 4A
|  | Sqm | 4 |  | 7.66 |  | 0.2 | 6.13 |  | 4A
|  | Sqm | 2 |  | 8.23 |  | 0.2 | 3.29 |  | 4A
|  | Sqm | 2 |  | 10.26 |  | 0.2 | 4.1 |  | 4A
| PLANTER BET -01 AND WATER BODY Horizontal | Sqm | 12 |  | 0.615 |  | 0.2 | 1.48 |  | 4A
| BET.G 17-21/25-29 | Sqm | 4 |  | 2.515 |  | 0.2 | 2.01 |  | 4A
|  | Sqm | 8 |  | 1.67 |  | 0.2 | 2.67 |  | 4A
| PLANTER BET -01 AND WATER BODY VERTICAL | Sqm | 2 |  | 7.24 |  | 0.2 | 2.9 |  | 4A
| BET.G 17-21/29-35 | Sqm | 2 |  | 5.23 |  | 0.2 | 2.09 |  | 4A
|  | Sqm | 4 |  | 4.23 |  | 0.2 | 3.38 |  | 4A
|  | Sqm | 6 |  | 4.46 |  | 0.2 | 5.35 |  | 4A
|  | Sqm | 6 |  | 3.23 |  | 0.2 | 3.88 |  | 4A
|  | Sqm | 2 |  | 5.23 |  | 0.2 | 2.09 |  | 4A
|  | Sqm | 0 |  | 3.66 |  | 0.2 |  |  | 4A
|  | Sqm | 2 |  | 5.26 |  | 0.2 | 2.1 |  | 4A
| PLANTER BET -01 AND WATER BODY Horizontal | Sqm | 10 |  | 0.615 |  | 0.2 | 1.23 |  | 4A
| BET.G 17-21/29-35 | Sqm | 6 |  | 3.36 |  | 0.2 | 4.03 |  | 4A
|  | Sqm | 12 |  | 0.91 |  | 0.2 | 2.18 |  | 4A
|  | Sqm | 2 |  | 2.135 |  | 0.2 | 0.85 |  | 4A
| PLANTER BET -04 AND BH-05 VERTICAL | Sqm | 2 |  | 11.14 |  | 0.2 | 4.46 |  | 4A
| BET.G 32-36/39-47 | Sqm | 2 |  | 8.91 |  | 0.2 | 3.56 |  | 4A
|  | Sqm | 4 |  | 6.21 |  | 0.2 | 4.97 |  | 4A
|  | Sqm | 4 |  | 5.31 |  | 0.2 | 4.25 |  | 4A
|  | Sqm | 4 |  | 4.41 |  | 0.2 | 3.53 |  | 4A
|  | Sqm | 4 |  | 2.61 |  | 0.2 | 2.09 |  | 4A
|  | Sqm | 4 |  | 4.71 |  | 0.2 | 3.77 |  | 4A
|  | Sqm | 4 |  | 2.61 |  | 0.2 | 2.09 |  | 4A
|  | Sqm | 2 |  | 1.71 |  | 0.2 | 0.68 |  | 4A
|  | Sqm | 2 |  | 3.94 |  | 0.2 | 1.58 |  | 4A
| PLANTER BET -04 AND BH-05 VERTICAL | Sqm | 6 |  | 0.615 |  | 0.2 | 0.74 |  | 4A
| BET.G 32-36/39-47 | Sqm | 2 |  | 2.975 |  | 0.2 | 1.19 |  | 4A
|  | Sqm | 14 |  | 1.67 |  | 0.2 | 4.68 |  | 4A
|  | Sqm | 12 |  | 3.36 |  | 0.2 | 8.06 |  | 4A
| PLANTER NEAR ZYM Vertical | Sqm | 2 |  | 7.86 |  | 0.2 | 3.14 |  | 4A
| BET.G 2-11/48-52 | Sqm | 2 |  | 5.63 |  | 0.2 | 2.25 |  | 4A
|  | Sqm | 4 |  | 6.23 |  | 0.2 | 4.98 |  | 4A
|  | Sqm | 4 |  | 5.03 |  | 0.2 | 4.02 |  | 4A
|  | Sqm | 4 |  | 6.46 |  | 0.2 | 5.17 |  | 4A
|  | Sqm | 4 |  | 4.43 |  | 0.2 | 3.54 |  | 4A
|  | Sqm | 4 |  | 5.03 |  | 0.2 | 4.02 |  | 4A
|  | Sqm | 4 |  | 4.43 |  | 0.2 | 3.54 |  | 4A
|  | Sqm | 2 |  | 6.46 |  | 0.2 | 2.58 |  | 4A
|  | Sqm | 4 |  | 6.23 |  | 0.2 | 4.98 |  | 4A
|  | Sqm | 2 |  | 8.46 |  | 0.2 | 3.38 |  | 4A
| PLANTER NEAR ZYM Horizontal | Sqm | 12 |  | 0.615 |  | 0.2 | 1.48 |  | 4A
| BET.G 2-11/48-52 | Sqm | 8 |  | 1.67 |  | 0.2 | 2.67 |  | 4A
|  | Sqm | 2 |  | 1.475 |  | 0.2 | 0.59 |  | 4A
|  | Sqm | 6 |  | 3.36 |  | 0.2 | 4.03 |  | 4A
|  | Sqm | 8 |  | 2.515 |  | 0.2 | 4.02 |  | 4A
|  | Sqm | 6 |  | 1.365 |  | 0.2 | 1.64 |  | 4A
| PLANTER BET. BH-04 AND BH-07 Vertical | Sqm | 2 |  | 10.12 |  | 0.2 | 4.05 |  | 4A
| BET.G 13-18/48-52 | Sqm | 2 |  | 5.89 |  | 0.2 | 2.36 |  | 4A
|  | Sqm | 4 |  | 8.39 |  | 0.2 | 6.71 |  | 4A
|  | Sqm | 4 |  | 6.39 |  | 0.2 | 5.11 |  | 4A
|  | Sqm | 2 |  | 8.39 |  | 0.2 | 3.36 |  | 4A
|  | Sqm | 2 |  | 10.62 |  | 0.2 | 4.25 |  | 4A
| PLANTER BET. BH-04 AND BH-07 Horizontal | Sqm | 4 |  | 0.615 |  | 0.2 | 0.49 |  | 4A
| BET.G 13-18/48-52 | Sqm | 6 |  | 3.36 |  | 0.2 | 4.03 |  | 4A
|  | Sqm | 6 |  | 1.67 |  | 0.2 | 2 |  | 4A
| PLANTER BET. BH-04 AND BH-07 Horizontal | Sqm | 14 |  | 0.615 |  | 0.2 | 1.72 |  | 4A
| BET.G 13-18/48-42 | Sqm | 4 |  | 2.515 |  | 0.2 | 2.01 |  | 4A
|  | Sqm | 10 |  | 1.67 |  | 0.2 | 3.34 |  | 4A
|  | Sqm | 2 |  | 1.06 |  | 0.2 | 0.42 |  | 4A
|  | Sqm | 2 |  | 3.36 |  | 0.2 | 1.34 |  | 4A
| PLANTER BET. BH-04 AND BH-07 VERTICAL | Sqm | 2 |  | 9.82 |  | 0.2 | 3.93 |  | 4A
| BET.G 13-18/48-42 | Sqm | 2 |  | 7.82 |  | 0.2 | 3.13 |  | 4A
|  | Sqm | 2 |  | 6.39 |  | 0.2 | 2.56 |  | 4A
|  | Sqm | 2 |  | 6.62 |  | 0.2 | 2.65 |  | 4A
|  | Sqm | 2 |  | 4.29 |  | 0.2 | 1.72 |  | 4A
|  | Sqm | 4 |  | 4.52 |  | 0.2 | 3.62 |  | 4A
|  | Sqm | 2 |  | 4.29 |  | 0.2 | 1.72 |  | 4A
|  | Sqm | 2 |  | 4.52 |  | 0.2 | 1.81 |  | 4A
|  | Sqm | 2 |  | 2.43 |  | 0.2 | 0.97 |  | 4A
|  | Sqm | 2 |  | 4.66 |  | 0.2 | 1.86 |  | 4A
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL HORIZONTAL | [8 empty] | 4A
| BET.G 35-41/42-48 | Sqm | 2 |  | 18.78 |  | 0.2 | 7.51 |  | 4A
|  | Sqm | 2 |  | 1.48 |  | 0.2 | 0.59 |  | 4A
|  | Sqm | 12 |  | 1.075 |  | 0.2 | 2.58 |  | 4A
|  | Sqm | 6 |  | 1.98 |  | 0.2 | 2.38 |  | 4A
|  | Sqm | 4 |  | 1.67 |  | 0.2 | 1.34 |  | 4A
|  | Sqm | 2 |  | 1.3 |  | 0.2 | 0.52 |  | 4A
| PLANTER NEAR BH-03 AND INFRONT OF BASKET BALL VERTICAL | [8 empty] | 4A
| BET.G 35-41/42-48 | Sqm | 4 |  | 2 |  | 0.2 | 1.6 |  | 4A
|  | Sqm | 4 |  | 3 |  | 0.2 | 2.4 |  | 4A
|  | Sqm | 4 |  | 4.645 |  | 0.2 | 3.72 |  | 4A
|  | Sqm | 4 |  | 6.12 |  | 0.2 | 4.9 |  | 4A
|  | Sqm | 4 |  | 6.95 |  | 0.2 | 5.56 |  | 4A
|  | Sqm | 4 |  | 6.38 |  | 0.2 | 5.1 |  | 4A
|  | Sqm | 4 |  | 5.345 |  | 0.2 | 4.28 |  | 4A
| SEAT | Sqm | -6 |  | 3 |  | 0.2 | -3.6 |  | 4B
| SEAT | Sqm | 6 |  | 3 |  | 0.31 | 5.58 |  | 4B
| SEAT | Sqm | -82 |  | 3 |  | 0.2 | -49.2 |  | 4B
| SEAT | Sqm | 82 |  | 3 |  | 0.365 | 89.79 |  | 4B
| FIRE TENDER TOE WALL WITH BH-05 | Sqm | 2 |  | 34.935 |  | 0.2 | 13.97 |  | 4A
| FIRE TENDER TOE WALL WITH BH-05 | Sqm | 2 |  | 15 |  | 0.2 | 6 |  | 4A
| FIRE TENDER TOE WALL WITH BH-01 | Sqm | 2 |  | 31.4 |  | 0.2 | 12.56 |  | 4A
| FIRE TENDER TOE WALL WITH BH-07 | Sqm | 2 |  | 42.55 |  | 0.2 | 17.02 |  | 4A
| TOE WALL BH-04 FOR GREEN | Sqm | 4 |  | 31.44 |  | 0.2 | 25.15 |  | 4A
| BH-04 RCC PLANTER | Sqm | 12 |  | 4.8 |  | 0.3 | 17.28 |  | 4A
|  | Sqm | 12 |  | 1.15 |  | 0.3 | 4.14 |  | 4A
|  | Sqm | 4 |  | 4.8 |  | 0.3 | 5.76 |  | 4A
|  | Sqm | 4 |  | 1.3 |  | 0.3 | 1.56 |  | 4A
| BH-03 RCC PLANTER | Sqm | 12 |  | 4.8 |  | 0.3 | 17.28 |  | 4A
|  | Sqm | 12 |  | 1.15 |  | 0.3 | 4.14 |  | 4A
|  | Sqm | 4 |  | 4.8 |  | 0.3 | 5.76 |  | 4A
|  | Sqm | 4 |  | 1.3 |  | 0.3 | 1.56 |  | 4A
| Form Work C/S for Tie Beam on Brick Work | [8 empty] | 4A
4A
| Form Work C/S for Planter (2-6/28'-31') | [8 empty] | 4A
4A
| (28'/2-3) (tie Beam=230x200) | Sqm | 1 | 2 | 3.545 |  | 0.2 | 1.42 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.43 |  | 0.2 | 0.57 |  | 4A
4A
| (29'/2-3) | Sqm | 0 | 2 | 2 |  | 0.2 |  |  | 4A
4A
|  | Sqm | 1 | 2 | 1.43 |  | 0.2 | 0.57 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.73 |  | 0.2 | 0.69 |  | 4A
4A
|  | Sqm | 1 | 2 | 0.6 |  | 0.2 | 0.24 |  | 4A
4A
| (30'/2-3) | Sqm | 2 | 2 | 1.73 |  | 0.2 | 1.38 |  | 4A
4A
| (31'/2-3) | Sqm | 1 | 2 | 1.2 |  | 0.2 | 0.48 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.33 |  | 0.2 | 0.93 |  | 4A
4A
|  | Sqm | 1 | 2 | 5.53 |  | 0.2 | 2.21 |  | 4A
4A
| (2-4/28'-31') | Sqm | 1 | 2 | 0.61 |  | 0.2 | 0.24 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.74 |  | 0.2 | 1.1 |  | 4A
4A
| (29'/2-4) | Sqm | 2 | 2 | 0.615 |  | 0.2 | 0.49 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.145 |  | 0.2 | 0.86 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.73 |  | 0.2 | 1.09 |  | 4A
4A
| (31'/2-4) | Sqm | 1 | 2 | 0.615 |  | 0.2 | 0.25 |  | 4A
4A
| Form Work C/S for Planter (2-6/31'-37') | [8 empty] | 4A
4A
| (32'/2-5) | Sqm | 1 | 2 | 6.43 |  | 0.2 | 2.57 |  | 4A
4A
|  | Sqm | 1 | 2 | 4.43 |  | 0.2 | 1.77 |  | 4A
| Form Work C/Sfor Beam Sheat (385x275) | Sqm | 1 | 2 | 3.3 |  | 0.275 | 1.82 |  | 4A
4A
| (33'/2-5) | Sqm | 1 | 2 | 4.43 |  | 0.2 | 1.77 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.56 |  | 0.2 | 0.62 |  | 4A
4A
|  | Sqm | 1 | 2 | 5.39 |  | 0.2 | 2.16 |  | 4A
4A
|  | Sqm | 1 | 2 | 0.6 |  | 0.2 | 0.24 |  | 4A
4A
|  | Sqm | 1 | 2 | 6.29 |  | 0.2 | 2.52 |  | 4A
| Form Work C/S for Sheat | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4A
4A
|  | Sqm | 1 | 2 | 6.29 |  | 0.2 | 2.52 |  | 4A
| Form Work C/S for Sheat | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4A
4A
| (35'/2-5) | Sqm | 1 | 2 | 6.89 |  | 0.2 | 2.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.8 |  | 0.2 | 0.72 |  | 4A
4A
|  | Sqm | 1 | 2 | 8.69 |  | 0.2 | 3.48 |  | 4A
4A
| (37'/2-5) | Sqm | 1 | 2 | 10.69 |  | 0.2 | 4.28 |  | 4A
| Form Work C/S for Sheat | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4A
4A
| (2-5/32'-37') | Sqm | 1 | 2 | 0.615 |  | 0.2 | 0.25 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 2 | 2 | 0.615 |  | 0.2 | 0.49 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.515 |  | 0.2 | 0.61 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 0.615 |  | 0.2 | 0.25 |  | 4A
4A
|  | Sqm | 1 | 2 | 3.36 |  | 0.2 | 1.34 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 0.615 |  | 0.2 | 0.25 |  | 4A
4A
| Form Work C/S for Planter (17-21/20-25) | Sqm | 0 | 2 | [5 empty] | 4A
4A
| (20'/17-21) | Sqm | 1 | 2 | 8.8 |  | 0.2 | 3.52 |  | 4A
4A
|  | Sqm | 1 | 2 | 4.2 |  | 0.2 | 1.68 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.8 |  | 0.2 | 1.12 |  | 4A
4A
| (21'/17-21) | Sqm | 1 | 2 | 1.8 |  | 0.2 | 0.72 |  | 4A
4A
|  | Sqm | 1 | 2 | 6.2 |  | 0.2 | 2.48 |  | 4A
| Form Work C/S for Sheet | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
|  | Sqm | 1 | 2 | 8 |  | 0.2 | 3.2 |  | 4A
| Form Work C/S for Sheet | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
4B
|  | Sqm | 1 | 2 | 1 |  | 0.2 | 0.4 |  | 4B
4B
|  | Sqm | 1 | 2 | 6 |  | 0.2 | 2.4 |  | 4B
4B
|  | Sqm | 1 | 2 | 2.8 |  | 0.2 | 1.12 |  | 4B
4B
|  | Sqm | 1 | 2 | 4.2 |  | 0.2 | 1.68 |  | 4B
| Form Work C/S Work for Sheet | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
4B
|  | Sqm | 1 | 2 | 1.8 |  | 0.2 | 0.72 |  | 4B
4B
|  | Sqm | 1 | 2 | 2.7 |  | 0.2 | 1.08 |  | 4B
4B
|  | Sqm | 1 | 2 | 4.5 |  | 0.2 | 1.8 |  | 4B
| Form Work C/S Work for Sheet | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
4B
|  | Sqm | 1 | 2 | 1.2 |  | 0.2 | 0.48 |  | 4B
| (24'/17-21) | Sqm | 1 | 2 | 7.5 |  | 0.2 | 3 |  | 4A
4A
| (17/20'-24') | Sqm | 8 | 2 | 0.615 |  | 0.2 | 1.97 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.205 |  | 0.2 | 0.88 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.9 |  | 0.2 | 1.52 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
| Form Work C/S for Planter (17-21/25'-29') | [8 empty] | 4A
4A
| (20'/17-21) | Sqm | 1 | 2 | 8 |  | 0.2 | 3.2 |  | 4A
4A
|  | Sqm | 1 | 2 | 6.2 |  | 0.2 | 2.48 |  | 4A
4A
|  | Sqm | 1 | 2 | 4.4 |  | 0.2 | 1.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.2 |  | 0.2 | 0.48 |  | 4A
4A
|  | Sqm | 1 | 2 | 3.2 |  | 0.2 | 1.28 |  | 4A
| Form Work C/S for Sheat | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
4B
|  | Sqm | 1 | 2 | 3 |  | 0.2 | 1.2 |  | 4B
| Form Work C/S for Sheat | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
|  | Sqm | 1 | 2 | 4.2 |  | 0.2 | 1.68 |  | 4A
4A
|  | Sqm | 1 | 2 | 3 |  | 0.2 | 1.2 |  | 4A
4A
|  | Sqm | 1 | 2 | 4.2 |  | 0.2 | 1.68 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.2 |  | 0.2 | 0.48 |  | 4A
4A
|  | Sqm | 1 | 2 | 6 |  | 0.2 | 2.4 |  | 4A
4A
|  | Sqm | 1 | 2 | 8 |  | 0.2 | 3.2 |  | 4A
4A
|  | Sqm | 1 | 2 | 9.8 |  | 0.2 | 3.92 |  | 4A
4A
| (17-21/25'-29') | Sqm | 6 | 2 | 0.615 |  | 0.2 | 1.48 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
| Form Work C/S for Planter (17-21/29'-35') | [8 empty] | 4A
4A
| (29'/17-21) | Sqm | 1 | 2 | 6.78 |  | 0.2 | 2.71 |  | 4A
4A
|  | Sqm | 1 | 2 | 5 |  | 0.2 | 2 |  | 4A
4A
|  | Sqm | 1 | 2 | 4 |  | 0.2 | 1.6 |  | 4A
| Form Work C/S for Sheat | Sqm | 1 | 2 | 3 |  | 0.275 | 1.65 |  | 4B
|  | Sqm | 1 | 2 | 1 |  | 0.2 | 0.4 |  | 4A
4A
|  | Sqm | 6 | 2 | 3 |  | 0.2 | 7.2 |  | 4A
4A
|  | Sqm | 1 | 2 | 5 |  | 0.2 | 2 |  | 4A
| Form Work C/S for Sheat | Sqm | 3 | 2 | 3 |  | 0.275 | 4.95 |  | 4B
|  | Sqm | 1 | 2 | 4 |  | 0.2 | 1.6 |  | 4A
4A
| (35'/17-20) | Sqm | 1 | 2 | 4.8 |  | 0.2 | 1.92 |  | 4A
4A
| (17-20/29'-35') | Sqm | 3 | 2 | 3.36 |  | 0.2 | 4.03 |  | 4A
4A
|  | Sqm | 3 | 2 | 1.9 |  | 0.2 | 2.28 |  | 4A
4A
|  | Sqm | 1 | 2 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.9 |  | 0.2 | 1.52 |  | 4A
4A
|  | Sqm | 5 | 2 | 0.615 |  | 0.2 | 1.23 |  | 4A
| Form Work C/S for Sheet | Sqm | 4 | 2 | 3 |  | 0.275 | 6.6 |  | 4B
Form Work C/S for Planter (20-28/2'-5')
| Form Work C/S (2'/20-28) | Sqm | 1 | 2 | 2.6 |  | 0.2 | 1.04 |  | 4A
4A
|  | Sqm | 3 | 2 | 0.6 |  | 0.2 | 0.72 |  | 4A
4A
|  | Sqm | 1 | 2 | 3.2 |  | 0.2 | 1.28 |  | 4A
4A
|  | Sqm | 1 | 2 | 2.6 |  | 0.2 | 1.04 |  | 4A
4A
|  | Sqm | 4 | 2 | 1.77 |  | 0.2 | 2.83 |  | 4A
4A
| Form Work C/S (3'/20-28) | [8 empty] | 4A
| Form Work C/S (6'/20-21) | Sqm | 1 | 2 | 3.205 |  | 0.2 | 1.28 |  | 4A
4A
|  | Sqm | 2 | 2 | 0.6 |  | 0.2 | 0.48 |  | 4A
4A
| R.C.C. P/L (4'/22-23) | Sqm | 3 | 2 | 2.6 |  | 0.2 | 3.12 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.77 |  | 0.2 | 1.42 |  | 4A
4A
|  | Sqm | 2 | 1 | 2 |  | 0.2 | 0.8 |  | 4A
4A
| Form Work C/S (20/2'-5') | [8 empty] | 4A
| Form Work C/S (20/2'-5') | Sqm | 2 | 1 | 9.155 |  | 0.2 | 3.66 |  | 4A
4A
|  | Sqm | 2 | 2 | 7.015 |  | 0.2 | 5.61 |  | 4A
| Form Work C/S for Sheet | Sqm | 4 | 2 | 3 |  | 0.275 | 6.6 |  | 4B
|  | Sqm | 2 | 1 | 5.49 |  | 0.2 | 2.2 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.525 |  | 0.2 | 0.61 |  | 4A
4A
| (23/2'-5') | Sqm | 2 | 1 | 2.44 |  | 0.2 | 0.98 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.22 |  | 0.2 | 0.49 |  | 4A
4A
|  | Sqm | 0 | 1 | 3.975 |  | 0.2 |  |  | 4A
4A
|  | Sqm | 2 | 2 | 3.965 |  | 0.2 | 3.17 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.325 |  | 0.2 | 1.33 |  | 4A
4A
|  | Sqm | 1 | 2 | 0.915 |  | 0.2 | 0.37 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.525 |  | 0.2 | 0.61 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.11 |  | 0.2 | 0.84 |  | 4A
4A
| Form Work C/S Side of BH-01 (15/23'-35') | [8 empty] | 4A
4A
| east face (15/23'-35') | Sqm | 2 | 2 | 29.25 |  | 0.2 | 23.4 |  | 4A
4A
|  | Sqm | 2 | 2 | 0.6 |  | 0.2 | 0.48 |  | 4A
4A
| north face (23'/9-10) | Sqm | 2 | 2 | 5.025 |  | 0.2 | 4.02 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.195 |  | 0.2 | 0.96 |  | 4A
4A
| north face (23'/11-13) | Sqm | 2 | 2 | 5.85 |  | 0.2 | 4.68 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.195 |  | 0.2 | 0.96 |  | 4A
4A
| Form Work C/S for Planter (20-28/2'-5') | [8 empty] | 4A
4A
| Form Work C/S (42'/13-16) | Sqm | 2 | 1 | 4.2 |  | 0.2 | 1.68 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.2 |  | 0.2 | 0.88 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.4 |  | 0.2 | 1.36 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.66 |  | 0.2 | 0.26 |  | 4A
4A
|  | Sqm | 2 | 2 | 4.06 |  | 0.2 | 3.25 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.38 |  | 0.2 | 0.15 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.68 |  | 0.2 | 1.47 |  | 4A
4A
| (45'/14-17) | Sqm | 2 | 1 | 1.28 |  | 0.2 | 0.51 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.08 |  | 0.2 | 1.23 |  | 4A
4A
|  | Sqm | 2 | 1 | 4.28 |  | 0.2 | 1.71 |  | 4A
4A
| (46'/14-17) | Sqm | 2 | 1 | 5.56 |  | 0.2 | 2.22 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.6 |  | 0.2 | 0.24 |  | 4A
4A
|  | Sqm | 2 | 2 | 6.16 |  | 0.2 | 4.93 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.2 |  | 0.2 | 0.48 |  | 4A
4A
|  | Sqm | 2 | 1 | 9.36 |  | 0.2 | 3.74 |  | 4A
| Form Work C/S for Sheat | Sqm | 2 | 5 | 3 |  | 0.275 | 8.25 |  | 4B
(15/42'-47')
|  | Sqm | 2 | 7 | 0.615 |  | 0.2 | 1.72 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.135 |  | 0.2 | 0.85 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.29 |  | 0.2 | 0.52 |  | 4A
4A
|  | Sqm | 2 | 5 | 1.9 |  | 0.2 | 3.8 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.36 |  | 0.2 | 1.34 |  | 4A
4A
|  | Sqm | 2 | 2 | 2.745 |  | 0.2 | 2.2 |  | 4A
4A
4A
| Form Work C/S for Planter (20-28/2'-5') | [8 empty] | 4A
4A
| Form Work C/S (48'/13-16) | Sqm | 2 | 1 | 10.16 |  | 0.2 | 4.06 |  | 4A
4A
|  | Sqm | 2 | 1 | 8.16 |  | 0.2 | 3.26 |  | 4A
4A
| (49'/13-16) | Sqm | 2 | 2 | 6.16 |  | 0.2 | 4.93 |  | 4A
4A
| (50'/14-18) | Sqm | 2 | 2 | 8.56 |  | 0.2 | 6.85 |  | 4A
4A
|  | Sqm | 2 | 1 | 7.66 |  | 0.2 | 3.06 |  | 4A
4A
| (52'/14-18) | Sqm | 2 | 1 | 9.66 |  | 0.2 | 3.86 |  | 4A
| Form Work C/S for Sheet | Sqm | 2 | 3 | 3 |  | 0.275 | 4.95 |  | 4B
| (15/48'-53') | Sqm | 2 | 2 | 0.615 |  | 0.2 | 0.49 |  | 4A
4A
| (17/48'-49') | Sqm | 2 | 3 | 1.9 |  | 0.2 | 2.28 |  | 4A
4A
|  | Sqm | 2 | 3 | 3.36 |  | 0.2 | 4.03 |  | 4A
4A
| Form Work C/S outer side of BH-04 (Drg. No. TU/LA-P-206.3) | [8 empty] | 4A
4A
| Form Work C/S Work west side (20/37'-50') | Sqm | 2 | 1 | 32.7 |  | 0.2 | 13.08 |  | 4A
4A
|  | Sqm | 2 | 1 | 29.865 |  | 0.2 | 11.95 |  | 4A
4A
| Form Work C/S south side (49'/19-23) (longitudinal axies) | Sqm | 2 | 1 | 0.915 |  | 0.2 | 0.37 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.465 |  | 0.2 | 0.19 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.97 |  | 0.2 | 0.79 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.49 |  | 0.2 | 0.2 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.72 |  | 0.2 | 1.09 |  | 4A
4A
| Form Work C/S south side (49'/19-23) (transverse axies) | Sqm | 2 | 1 | 2 |  | 0.2 | 0.8 |  | 4A
4A
|  | Sqm | 2 | 1 | 2 |  | 0.2 | 0.8 |  | 4A
4A
|  | Sqm | 2 | 1 | 1 |  | 0.2 | 0.4 |  | 4A
4A
|  | Sqm | 2 | 1 | 1 |  | 0.2 | 0.4 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.97 |  | 0.2 | 0.79 |  | 4A
4A
|  | Sqm | 2 | 1 | 6.17 |  | 0.2 | 2.47 |  | 4A
4A
| Form Work C/S north side (36'/19-21) (longitudianal axies) | Sqm | 2 | 1 | 1.8 |  | 0.2 | 0.72 |  | 4A
4A
| Form Work C/S north side (36'/19-21) (transverse axies) | Sqm | 2 | 1 | 4.495 |  | 0.2 | 1.8 |  | 4A
4A
| (transverse axies) | Sqm | 2 | 1 | 2.295 |  | 0.2 | 0.92 |  | 4A
4A
| Form Work C/S outer side of BH-04 (Drg. No. TU/LA-P-206.4) | [8 empty] | 4A
4A
| Form Work C/S east side (32/37'-49') | Sqm | 2 | 2 | 31.82 |  | 0.2 | 25.46 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.57 |  | 0.2 | 1.26 |  | 4A
4A
4A
| Form Work C/S for Planter (39'-55'/32-36) (Drg. No. TU/LA-P-206.4) | [8 empty] | 4A
4A
| Form Work C/S for Planter (39'-47'/32-36) | [8 empty] | 4A
| longitudianal axies (40'/34-35) | Sqm | 1 | 2 | 3.48 |  | 0.2 | 1.39 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.48 |  | 0.2 | 0.59 |  | 4A
4A
|  | Sqm | 2 | 4 | 2.38 |  | 0.2 | 3.81 |  | 4A
4A
|  | Sqm | 2 | 2 | 4.48 |  | 0.2 | 3.58 |  | 4A
4A
|  | Sqm | 2 | 2 | 4.18 |  | 0.2 | 3.34 |  | 4A
4A
|  | Sqm | 2 | 2 | 5.08 |  | 0.2 | 4.06 |  | 4A
4A
|  | Sqm | 2 | 2 | 5.98 |  | 0.2 | 4.78 |  | 4A
4A
|  | Sqm | 2 | 1 | 7.18 |  | 0.2 | 2.87 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.5 |  | 0.2 | 0.6 |  | 4A
4A
| (47'/32-36) | Sqm | 2 | 1 | 10.16 |  | 0.2 | 4.06 |  | 4A
| Form Work C/S for Sheet | Sqm | 2 | 4 | 3 |  | 0.275 | 6.6 |  | 4B
| Transvere axies (34/40'-47') | Sqm | 2 | 3 | 0.615 |  | 0.2 | 0.74 |  | 4A
4A
|  | Sqm | 2 | 6 | 3.36 |  | 0.2 | 8.06 |  | 4A
4A
|  | Sqm | 2 | 7 | 1.9 |  | 0.2 | 5.32 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
| Form Work C/S for Planter (48'-55'/32-36) | [8 empty] | 4A
| longitudianal axies (48'/34-35) | Sqm | 2 | 2 | 4.98 |  | 0.2 | 3.98 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.98 |  | 0.2 | 1.19 |  | 4A
4A
|  | Sqm | 2 | 6 | 3 |  | 0.2 | 7.2 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.9 |  | 0.2 | 0.76 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.8 |  | 0.2 | 1.52 |  | 4A
4A
|  | Sqm | 2 | 1 | 5.7 |  | 0.2 | 2.28 |  | 4A
4A
|  | Sqm | 2 | 2 | 3.3 |  | 0.2 | 2.64 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.3 |  | 0.2 | 0.52 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.3 |  | 0.2 | 1.32 |  | 4A
| Form Work C/S for Sheat | Sqm | 2 | 5 | 3.3 |  | 0.15 | 4.95 |  | 4B
| Form Work C/S for Sheat | Sqm | 2 | 4 | 3.3 |  | 0.15 | 3.96 |  | 4B
| Transverse axies (34/48'-55') | Sqm | 2 | 3 | 0.615 |  | 0.2 | 0.74 |  | 4A
4A
|  | Sqm | 2 | 6 | 1.9 |  | 0.2 | 4.56 |  | 4A
4A
|  | Sqm | 2 | 5 | 3.36 |  | 0.2 | 6.72 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.745 |  | 0.2 | 1.1 |  | 4A
4A
4A
| Form Work C/S for Planter (30-39/37-40) near M4 (revised Drg. No. TU/LA-P-206.5 (front of Basket Ball) | [8 empty] | 4A
| R.C.C. P/L (west side wall) | Sqm | 2 | 1 | 18.53 |  | 0.2 | 7.41 |  | 4A
| extra for Sheet | Sqm | 2 | 3 | 3 |  | 0.275 | 4.95 |  | 4B
| north & south side wall | Sqm | 2 | 2 | 2 |  | 0.2 | 1.6 |  | 4A
4A
|  | Sqm | 2 | 3 | 2.435 |  | 0.2 | 2.92 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.44 |  | 0.2 | 0.98 |  | 4A
4A
|  | Sqm | 2 | 1 | 2.13 |  | 0.2 | 0.85 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.48 |  | 0.2 | 0.59 |  | 4A
4A
|  | Sqm | 2 | 2 | 5.345 |  | 0.2 | 4.28 |  | 4A
4A
|  | Sqm | 2 | 2 | 6.38 |  | 0.2 | 5.1 |  | 4A
4A
|  | Sqm | 2 | 2 | 6.95 |  | 0.2 | 5.56 |  | 4A
4A
|  | Sqm | 2 | 2 | 6.12 |  | 0.2 | 4.9 |  | 4A
4A
|  | Sqm | 2 | 2 | 4.645 |  | 0.2 | 3.72 |  | 4A
4A
|  | Sqm | 2 | 2 | 3 |  | 0.2 | 2.4 |  | 4A
4A
|  | Sqm | 2 | 4 | 0.615 |  | 0.2 | 0.98 |  | 4A
4A
|  | Sqm | 2 | 2 | 0.61 |  | 0.2 | 0.49 |  | 4A
4A
| Form Work C/S for Planter near BH-03 (drg. No. TU/LA-P-206.1) (48-52/2'-11') | [8 empty] | 4A
| Form Work C/S for Stepped Foundation (west side wall) (2'/48-52) | [8 empty] | 4A
| Longitudianal axies (2'/48-52) | Sqm | 2 | 1 | 7.4 |  | 0.2 | 2.96 |  | 4A
4A
|  | Sqm | 2 | 1 | 5.4 |  | 0.2 | 2.16 |  | 4A
4A
|  | Sqm | 2 | 2 | 6 |  | 0.2 | 4.8 |  | 4A
4A
|  | Sqm | 2 | 3 | 4.8 |  | 0.2 | 5.76 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.2 |  | 0.2 | 0.48 |  | 4A
4A
|  | Sqm | 2 | 1 | 5.4 |  | 0.2 | 2.16 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.6 |  | 0.2 | 0.24 |  | 4A
4A
|  | Sqm | 2 | 5 | 4.2 |  | 0.2 | 8.4 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.6 |  | 0.2 | 0.24 |  | 4A
4A
|  | Sqm | 2 | 1 | 4.8 |  | 0.2 | 1.92 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.2 |  | 0.2 | 0.48 |  | 4A
4A
| (10'/49-50) | Sqm | 2 | 2 | 6 |  | 0.2 | 4.8 |  | 4A
4A
|  | Sqm | 2 | 1 | 8 |  | 0.2 | 3.2 |  | 4A
| extra for Sheet | Sqm | 2 | 8 | 3.3 |  | 0.15 | 7.92 |  | 4B
Transverse axies (49/2'-11')
|  | Sqm | 2 | 6 | 0.615 |  | 0.2 | 1.48 |  | 4A
4A
|  | Sqm | 2 | 4 | 1.9 |  | 0.2 | 3.04 |  | 4A
4A
|  | Sqm | 2 | 2 | 3.36 |  | 0.2 | 2.69 |  | 4A
4A
|  | Sqm | 2 | 3 | 1.595 |  | 0.2 | 1.91 |  | 4A
4A
|  | Sqm | 2 | 2 | 2.44 |  | 0.2 | 1.95 |  | 4A
4A
|  | Sqm | 2 | 2 | 2.745 |  | 0.2 | 2.2 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.055 |  | 0.2 | 1.22 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.165 |  | 0.2 | 1.27 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.705 |  | 0.2 | 0.68 |  | 4A
4A
4A
| Less Previous RA Quantity | Sqm | -1 |  | 573.77 |  |  | -573.77 |  | 4A
| QUANTITY SHIFTED FROM ITEM NO E.I 03 | [8 empty] | 4A
| Form Work C/S for BH-05 outer side (drg. No. TU/LA-P-206.8) | [8 empty] | 4A
| R.C.C. P/L for FIRE TENDER TOES Wall (north side wall) | Sqm | 2 | 1 | 34.935 |  | 0.2 | 13.97 |  | 4A
4A
| Form Work C/S FIRE TENDER TOES Wall (west side wall) | Sqm | 2 | 1 | 15 |  | 0.2 | 6 |  | 4A
4A
| Form Work C/S for Basket Ball Ground Toe Wall | [8 empty] | 4A
| Basket Ball Long Ball | Sqm | 2 | 2 | 27.54 |  | 0.2 | 22.03 |  | 4A
4A
| BASKET WALL SHORT WALL | Sqm | 2 | 2 | 14.65 |  | 0.2 | 11.72 |  | 4A
| SEAT | Sqm | 2 | 2 | 3.3 |  | 0.2 | 2.64 |  | 4B
Form Work C/S for Basket Ball Ground Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 | Sqm | 2 | 1 | 31.4 |  | 0.2 | 12.56 |  | 4A
4A
| FIRE TENDER TOE WALL WITH BH-07 | Sqm | 2 | 1 | 42.55 |  | 0.2 | 17.02 |  | 4A
4A
| Form Work C/S for Road Toe Wall at Planter between BH-07 & BH-04 | [8 empty] | 4A
|  | Sqm | 2 | 1 | 15.158 |  | 0.2 | 6.06 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.525 |  | 0.2 | 0.21 |  | 4A
4A
|  | Sqm | 2 | 1 | 33.295 |  | 0.2 | 13.32 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.495 |  | 0.2 | 0.6 |  | 4A
4A
|  | Sqm | 2 | 1 | 1.56 |  | 0.2 | 0.62 |  | 4A
4A
|  | Sqm | 2 | 1 | 0.99 |  | 0.2 | 0.4 |  | 4A
4A
|  | Sqm | 2 | 1 | 3.83 |  | 0.2 | 1.53 |  | 4A
4A
| Form Work C/S for Road Toe Wall BH-04 to Planter front of BH-01 | [8 empty] | 4A
4A
|  | Sqm | 2 | 1 | 0.39 |  | 0.2 | 0.16 |  | 4A
4A
|  | Sqm | 2 | 1 | 15.46 |  | 0.2 | 6.18 |  | 4A
| Form Work C/S for Road Toe Wall BH-01 | [8 empty] | 4A
4A
| for Road Toe Wall BH-01 east side towards water body | Sqm | 2 | 2 | 29.32 |  | 0.2 | 23.46 |  | 4A
4A
|  | Sqm | 2 | 2 | 0.67 |  | 0.2 | 0.54 |  | 4A
| for Road Toe Wall BH-01 North side towards GYM | [8 empty] | 4A
4A
|  | Sqm | 2 | 2 | 5.095 |  | 0.2 | 4.08 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.265 |  | 0.2 | 1.01 |  | 4A
4A
|  | Sqm | 2 | 2 | 5.92 |  | 0.2 | 4.74 |  | 4A
4A
|  | Sqm | 2 | 2 | 1.265 |  | 0.2 | 1.01 |  | 4A
4A
4A
| Form Work C/S for Road Toe Wall back side of Basket Ball (east side) | [8 empty] | 4A
4A
|  | Sqm | 2 | 3 | 7.625 |  | 0.2 | 9.15 |  | 4A
4A
| Excavation for Road Toe wall outer parapheri BG-02 to Gym North side | [8 empty] | 4A
4A
|  | Sqm | 2 | 8 | 7.625 |  | 0.2 | 24.4 |  | 4A
4A
|  | Sqm | 2 | 1 | 9.35 |  | 0.2 | 3.74 |  | 4A
4A
4A
| Form Work C/S for Planter between BH-03 & Basket Ball Ground | [8 empty] | 4A
4A
| Base Footning (4500x1000) | Sqm | 1 | 10 | 4.8 |  | 0.3 | 14.4 |  | 4A
|  | Sqm | 2 | 8 | 1.3 |  | 0.3 | 6.24 |  | 4A
4A
| Form Work C/S for Planter between BH-04 & Base of Waterbody M3 | [8 empty] | 4A
4A
| Base Footning (4500x1000) | Sqm | 1 | 10 | 4.8 |  | 0.3 | 14.4 |  | 4A
|  | Sqm | 2 | 8 | 1.3 |  | 0.3 | 6.24 |  | 4A
| Form Work C/S for Planter near Reception or west side of Waterbody (drg. No. TU/LA-P-206.1) (30'-35'/32-36) | [8 empty] | 4A
| Form Work C/S for Planter Tie Beam (230x200) | [8 empty] | 4A
| Longitudianal axies (30'/32-36) | [8 empty] | 4A
|  | Sqm | 2 | 1 | 10.75 |  | 0.2 | 4.3 |  | 4A
|  | Sqm | 2 | 1 | 1.4 |  | 0.2 | 0.56 |  | 4A
|  | Sqm | 2 | 1 | 7.35 |  | 0.2 | 2.94 |  | 4A
| Longitudianal axies (31'/32-35) | Sqm | 2 | 1 | 7.35 |  | 0.2 | 2.94 |  | 4A
|  | Sqm | 2 | 1 | 1.4 |  | 0.2 | 0.56 |  | 4A
|  | Sqm | 2 | 1 | 5.95 |  | 0.2 | 2.38 |  | 4A
| Longitudianal axies (32'/32-35) | Sqm | 2 | 1 | 5.95 |  | 0.2 | 2.38 |  | 4A
|  | Sqm | 2 | 1 | 1.53 |  | 0.2 | 0.61 |  | 4A
|  | Sqm | 2 | 1 | 4.42 |  | 0.2 | 1.77 |  | 4A
| Longitudianal axies (33'/32-35) | Sqm | 2 | 1 | 4.42 |  | 0.2 | 1.77 |  | 4A
|  | Sqm | 2 | 1 | 1.53 |  | 0.2 | 0.61 |  | 4A
|  | Sqm | 2 | 1 | 2.89 |  | 0.2 | 1.16 |  | 4A
| Longitudianal axies (33'/32-35) | Sqm | 2 | 1 | 2.89 |  | 0.2 | 1.16 |  | 4A
|  | Sqm | 2 | 1 | 4.89 |  | 0.2 | 1.96 |  | 4A
| Transvere axies (34/30'-35') | Sqm | 2 | 6 | 0.615 |  | 0.2 | 1.48 |  | 4A
|  | Sqm | 2 | 3 | 2.745 |  | 0.2 | 3.29 |  | 4A
|  | Sqm | 2 | 1 | 2.44 |  | 0.2 | 0.98 |  | 4A
|  | Sqm | 2 | 3 | 2.13 |  | 0.2 | 2.56 |  | 4A
|  | Sqm | 2 | 1 | 1.825 |  | 0.2 | 0.73 |  | 4A
| Form Work C/S for Planter South sid of BH-02 (drg. No. TU/LA-P-206.1 & 206.2) ( (15'-19'/20-32) | [8 empty] | 4A
| Form Work C/S for Planter | [8 empty] | 4A
| Longitudianal axies (15'/20-32) | Sqm | 2 | 1 | 29.85 |  | 0.2 | 11.94 |  | 4A
|  | Sqm | 2 | 1 | 2.07 |  | 0.2 | 0.83 |  | 4A
|  | Sqm | 2 | 7 | 2 |  | 0.2 | 5.6 |  | 4A
|  | Sqm | 2 | 1 | 2.02 |  | 0.2 | 0.81 |  | 4A
|  | Sqm | 2 | 1 | 1.52 |  | 0.2 | 0.61 |  | 4A
|  | Sqm | 2 | 11 | 0.6 |  | 0.2 | 2.64 |  | 4A
| Transvere axies (32/15'-19') | Sqm | 2 | 1 | 10.315 |  | 0.2 | 4.13 |  | 4A
| (32/15'-19') | Sqm | 2 | 1 | 9.245 |  | 0.2 | 3.7 |  | 4A
| (31/15'-19') | Sqm | 2 | 2 | 7.79 |  | 0.2 | 6.23 |  | 4A
| (30/15'-18') | Sqm | 2 | 2 | 6.265 |  | 0.2 | 5.01 |  | 4A
| (29/15'-17') | Sqm | 0 | 2 | 6.265 |  | 0.2 |  |  | 4A
|  | Sqm | 2 | 2 | 4.74 |  | 0.2 | 3.79 |  | 4A
|  | Sqm | 2 | 2 | 3.52 |  | 0.2 | 2.82 |  | 4A
|  | Sqm | 6 | 2 | 3.215 |  | 0.2 | 7.72 |  | 4A
|  | Sqm | 2 | 1 | 3.215 |  | 0.2 | 1.29 |  | 4A
|  | Sqm | 2 | 1 | 4.215 |  | 0.2 | 1.69 |  | 4A
| Form Work C/S Beam for Sheat | Sqm | 2 | 11 | 3 |  | 0.275 | 18.15 |  | 4A
| Form Work C/S for Planter South sid of BH-02 & BH-03 (drg. No. TU/LA-P-206.1) ( (19'-21'/35-40) | [8 empty] | 4A
| Form Work C/S for Planter | [8 empty] | 4A
| Longitudianal axies (40/19'-20') | Sqm | 2 | 2 | 3.59 |  | 0.2 | 2.87 |  | 4A
|  | Sqm | 2 | 2 | 5.725 |  | 0.2 | 4.58 |  | 4A
|  | Sqm | 2 | 2 | 6.64 |  | 0.2 | 5.31 |  | 4A
|  | Sqm | 2 | 2 | 6.03 |  | 0.2 | 4.82 |  | 4A
|  | Sqm | 2 | 5 | 0.6 |  | 0.2 | 1.2 |  | 4A
| Form Work C/S for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) | [8 empty] | 4A
| Form Work C/S for Road Toe Wall (1/F-J) | Sqm | 2 | 1 | 4.635 |  | 0.2 | 1.85 |  | 4A
|  | Sqm | 2 | 8 | 7.625 |  | 0.2 | 24.4 |  | 4A
|  | Sqm | 2 | 1 | 10.14 |  | 0.2 | 4.06 |  | 4A
| Form Work C/S for Road Toe Wall (J/1-9) | Sqm | 2 | 1 | 14.06 |  | 0.2 | 5.62 |  | 4A
|  | Sqm | 2 | 5 | 7.625 |  | 0.2 | 15.25 |  | 4A
|  | Sqm | 2 | 1 | 0.265 |  | 0.2 | 0.11 |  | 4A
| Form Work C/S for Road Toe Wall (9/H-J) | Sqm | 2 | 1 | 7.76 |  | 0.2 | 3.1 |  | 4A
|  | Sqm | 2 | 2 | 7.625 |  | 0.2 | 6.1 |  | 4A
Form Work C/S for Planter between BH-03 & Basket Ball Ground
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 10 | 4.5 |  | 1.025 | 46.13 |  | 4B
| outer face | Sqm | 2 | 8 | 1 |  | 0.8 | 12.8 |  | 4B
| inner face wall | Sqm | 2 | 5 | 4.1 |  | 1.025 | 42.03 |  | 4B
|  | Sqm | 2 | 8 | 0.6 |  | 0.8 | 7.68 |  | 4B
Form Work C/S for Planter between BH-04 & Base of Waterbody M3
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 10 | 4.5 |  | 1.025 | 46.13 |  | 4B
| outer face | Sqm | 2 | 8 | 1 |  | 0.8 | 12.8 |  | 4B
| inner face wall | Sqm | 2 | 8 | 4.1 |  | 1.025 | 67.24 |  | 4B
|  | Sqm | 2 | 8 | 0.6 |  | 0.8 | 7.68 |  | 4B
Form Work C/S for Planter between BH-01 & Canteen
| Base Footning (4500x1000) | Sqm | 1 | 12 | 4.8 |  | 0.3 | 17.28 |  | 4A
|  | Sqm | 2 | 9 | 1.3 |  | 0.3 | 7.02 |  | 4A
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 12 | 4.5 |  | 1.025 | 55.35 |  | 4B
| outer face | Sqm | 2 | 9 | 1 |  | 0.8 | 14.4 |  | 4B
| inner face wall | Sqm | 2 | 9 | 4.1 |  | 1.025 | 75.65 |  | 4B
|  | Sqm | 2 | 9 | 0.6 |  | 0.8 | 8.64 |  | 4B
Form Work C/S for Planter between BH-04 & Base of Waterbody M3
| Base Footning (4500x1000) | Sqm | 1 | 10 | 4.8 |  | 0.3 | 14.4 |  | 4A
|  | Sqm | 2 | 8 | 1.3 |  | 0.3 | 6.24 |  | 4A
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 10 | 4.5 |  | 1.025 | 46.13 |  | 4B
| outer face | Sqm | 2 | 8 | 1 |  | 0.8 | 12.8 |  | 4B
| inner face wall | Sqm | 2 | 8 | 4.1 |  | 1.025 | 67.24 |  | 4B
|  | Sqm | 2 | 8 | 0.6 |  | 0.8 | 7.68 |  | 4B
| Form Work C/S for Waterbody as per drg. No.(inner dia. 20.12m), dia. For R.C.C. =20.12+0.2*2+0.6*2=21.720m) |  |  |  | area
| base raft dia. 21.72m | Sqm | 1 | 1 | 68.2008 |  | 0.2 | 13.64 |  | 4A
| add for hold area (dia. 18.32m) | Sqm | 1 | 1 | 57.5248 |  | 0.2 | 11.5 |  | 4A
| Form Work for wall 200mm thk. (outer face) | Sqm | 1 | 1 | 64.4328 |  | 0.545 | 35.12 |  | 4B
| inner face of wall | Sqm | 1 | 1 | 63.1768 |  | 0.545 | 34.43 |  | 4B
| Form Work C/S for wall top beam (390x150) (outer) | Sqm | 1 | 1 | 64.4328 |  | 0.15 | 9.66 |  | 4A
| inner shutt. Beam | Sqm | 1 | 1 | 63.1768 |  | 0.34 | 21.48 |  | 4A
QUANTITY SHIFTED FROM ITEM NO E.I 03
Form Work C/S for Planter Tie Beam (230x200)
| Longitudianal axies (32/22'-26') | Sqm | 2 | 1 | 9.43 |  | 0.2 | 3.77 |  | 4A
|  | Sqm | 2 | 1 | 9.395 |  | 0.2 | 3.76 |  | 4A
| (33/22'-26') | Sqm | 2 | 2 | 8.175 |  | 0.2 | 6.54 |  | 4A
| (34/22'-26') | Sqm | 2 | 2 | 6.65 |  | 0.2 | 5.32 |  | 4A
| (35/22'-26') | Sqm | 2 | 2 | 4.82 |  | 0.2 | 3.86 |  | 4A
| (36/22'-26') | Sqm | 2 | 1 | 3.295 |  | 0.2 | 1.32 |  | 4A
|  | Sqm | 2 | 1 | 3.33 |  | 0.2 | 1.33 |  | 4A
| Transverse Axies | Sqm | 2 | 5 | 0.6 |  | 0.2 | 1.2 |  | 4A
Form Work C/S for Ramp for Entrance in BH-01 Ref. to drg. No. TU-LA-D-205 (on top surface
|  | Sqm | 2 | 1 | 6 |  | 0.1 | 1.2 |  | 4A
|  | Sqm | 2 | 1 | 2.925 |  | 0.1 | 0.59 |  | 4A
Form Work C/S for Ramp for Entrance in BH-02 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 2 | 1 | 6 |  | 0.1 | 1.2 |  | 4A
|  | Sqm | 2 | 1 | 2.925 |  | 0.1 | 0.59 |  | 4A
4A
R.C.C. P/L for Ramp for Entrance in BH-03 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 2 | 1 | 6 |  | 0.1 | 1.2 |  | 4A
|  | Sqm | 2 | 1 | 2.925 |  | 0.1 | 0.59 |  | 4A
4A
Form Work C/S for Ramp for Entrance in BH-04 Ref. to drg. No. TU-LA-D-205
|  | Sqm | 2 | 1 | 6 |  | 0.1 | 1.2 |  | 4A
|  | Sqm | 2 | 1 | 2.925 |  | 0.1 | 0.59 |  | 4A
4A
Form Work C/S for Road Toe Wall (9/H-J)
|  | Sqm | 2 | 1 | 7.625 |  | 0.2 | 3.05 |  | 4A
|  | Sqm | 2 | 1 | 1.1 |  | 0.2 | 0.44 |  | 4A
| Form Work C/S for Road Toe Wall (9/F-H) basket ball ground & BH-03 | [8 empty] | 4A
|  | Sqm | 2 | 1 | 7.625 |  | 0.2 | 3.05 |  | 4A
|  | Sqm | 2 | 1 | 7.125 |  | 0.2 | 2.85 |  | 4A
Form Work C/S for Fire Tender Wall (parallel to road) (Tie Beam 230x200)
| Fire Tender Wall towards BH-07 (Tie Beam 230x200) | Sqm | 2 | 1 | 24.945 |  | 0.2 | 9.98 |  | 4A
|  | Sqm | 2 | 1 | 13.605 |  | 0.2 | 5.44 |  | 4A
|  | Sqm | 2 | 1 | 4.343 |  | 0.2 | 1.74 |  | 4A
|  | Sqm | 2 | 1 | 4.748 |  | 0.2 | 1.9 |  | 4A
|  | Sqm | 2 | 1 | 0.374 |  | 0.2 | 0.15 |  | 4A
| Form Work C/Sfor green Planter wall BH-07 (west side) | Sqm | 2 | 1 | 1.359 |  | 0.2 | 0.54 |  | 4A
|  | Sqm | 2 | 1 | 26.229 |  | 0.2 | 10.49 |  | 4A
| Fire Tender Wall towards BH-01 | Sqm | 2 | 1 | 10.508 |  | 0.2 | 4.2 |  | 4A
|  | Sqm | 2 | 1 | 1.639 |  | 0.2 | 0.66 |  | 4A
|  | Sqm | 2 | 1 | 2.059 |  | 0.2 | 0.82 |  | 4A
|  | Sqm | 2 | 1 | 2.938 |  | 0.2 | 1.18 |  | 4A
|  | Sqm | 2 | 1 | 7.795 |  | 0.2 | 3.12 |  | 4A
|  | Sqm | 2 | 1 | 2.063 |  | 0.2 | 0.83 |  | 4A
|  | Sqm | 2 | 1 | 1.079 |  | 0.2 | 0.43 |  | 4A
|  | Sqm | 2 | 1 | 3.273 |  | 0.2 | 1.31 |  | 4A
|  | Sqm | 2 | 1 | 5.084 |  | 0.2 | 2.03 |  | 4A
| Fire Tender Wall Form Work C/S between BH-04 & BH-07 near green Planter (triangle type) | Sqm | 0 | 1 | 1.398 |  | 0.2
|  | Sqm | 0 | 1 | 6.182 |  | 0.2
|  | Sqm | 0 | 1 | 0.23 |  | 0.2
|  | Sqm | 0 | 1 | 8.695 |  | 0.2
|  | Sqm | 2 | 1 | 10.409 |  | 0.2 | 4.16 |  | 4A
| Form Work C/Sfor fire tender in green planter between BH-04 & BH-07 | Sqm | 0 | 1 | 0.898 |  | 0.2
|  | Sqm | 0 | 1 | 1.497 |  | 0.2
|  | Sqm | 0 | 1 | 1.602 |  | 0.2
|  | Sqm | 0 | 1 | 1.012 |  | 0.2
|  | Sqm | 0 | 1 | 4.172 |  | 0.2
|  | Sqm | 0 | 1 | 10.42 |  | 0.2
|  | Sqm | 0 | 1 | 0.217 |  | 0.2
|  | Sqm | 0 | 1 | 4.011 |  | 0.2
|  | Sqm | 2 | 1 | 23.472 |  | 0.2 | 9.39 |  | 4A
| Fire Tender Wall Brick Work connect to BH-04 to green Planter between BH-01 & waterbody Form Work C/S | Sqm | 2 | 1 | 15.694 |  | 0.2 | 6.28 |  | 4A
|  | Sqm | 2 | 1 | 0.225 |  | 0.2 | 0.09 |  | 4A
| Form Work C/S for Fire Tender in Green planter between BH-01 & Waterbody | Sqm | 2 | 1 | 1.497 |  | 0.2 | 0.6 |  | 4A
|  | Sqm | 2 | 1 | 1.6 |  | 0.2 | 0.64 |  | 4A
|  | Sqm | 2 | 1 | 3.43 |  | 0.2 | 1.37 |  | 4A
|  | Sqm | 2 | 1 | 1.497 |  | 0.2 | 0.6 |  | 4A
|  | Sqm | 2 | 1 | 3.735 |  | 0.2 | 1.49 |  | 4A
|  | Sqm | 2 | 1 | 4.345 |  | 0.2 | 1.74 |  | 4A
| Form Work C/S for Fire Tender Wall Brick Work BH-01 west corner to Canteen parallel to road betwee canteen & BH-02 | Sqm | 2 | 1 | 2.386 |  | 0.2 | 0.95 |  | 4A
|  | Sqm | 2 | 1 | 20.003 |  | 0.2 | 8 |  | 4A
| parallel to canteen | Sqm | 2 | 1 | 33.331 |  | 0.2 | 13.33 |  | 4A
| parallel to BH-02 towards canteen (east face) | Sqm | 2 | 1 | 31.771 |  | 0.2 | 12.71 |  | 4A
|  | Sqm | 2 | 1 | 4.373 |  | 0.2 | 1.75 |  | 4A
|  | Sqm | 2 | 1 | 0.17 |  | 0.2 | 0.07 |  | 4A
Form Work C/S Fire Tender Wall Brick Work for Road between BH-02 & Waterbody
| wall towards BH-02 (BH-02 to Gym toilet) | Sqm | 2 | 1 | 18.743 |  | 0.2 | 7.5 |  | 4A
|  | Sqm | 2 | 1 | 9.868 |  | 0.2 | 3.95 |  | 4A
|  | Sqm | 2 | 1 | 7.05 |  | 0.2 | 2.82 |  | 4A
Form Work C/S for fire tender wall towards waterbody planter to arround waterbody to Reception
|  | SQM | 2 | 1 | 36.696 |  | 0.2 | 14.68 |  | 4A
|  | Sqm | 0 | 1 | 0.337 |  | 0.2
|  | Sqm | 0 | 1 | 3.183 |  | 0.2
|  | Sqm | 0 | 1 | 33.632 |  | 0.2
| in planter | Sqm | 2 | 1 | 8.053 |  | 0.2 | 3.22 |  | 4A
| fire tender wall west side of reception | Sqm | 2 | 1 | 14.555 |  | 0.2 | 5.82 |  | 4A
Form Work C/S for Fire Tender Wall Brick Work for Road South side of BH-04 (back side)
|  | Sqm | 2 | 1 | 14.343 |  | 0.2 | 5.74 |  | 4A
Form Work C/S for Fire Tender Wall Brick Work for Road BH-04 (near watebody to basket ball ground planter) to BH-03
|  | Sqm | 2 | 1 | 60.78 |  | 0.2 | 24.31 |  | 4A
| basket ball ground planter to BH-03 corner(front of Gym) | Sqm | 2 | 1 | 35.253 |  | 0.2 | 14.1 |  | 4A
Deduct Previous Bill Qty. for Revise
Form Work C/S for Fire Tender Toe Wall
| FIRE TENDER TOE WALL WITH BH-01 (South side) | Sqm | -1 | 2 | 31.4 |  | 0.2 | -12.56 |  | 4A
| FIRE TENDER TOE WALL WITH BH-07 | Sqm | -1 | 2 | 42.55 |  | 0.2 | -17.02 |  | 4A
Form Work C/S for Sump in Waterbody
| for Waterbody for Sump (900x900x850) | Sqm | 5 | 4 | 0.9 |  | 0.85 | 15.3 |  | 4A
| Demolishing of P.C.C. or Stone Soling in Waterbody for Filter Pit (2000x2000x1800) | Sqm | 1 | 4 | 2 |  | 1.8 | 14.4 |  | 4A
| QUANTITY SHIFTED FROM E.I.03 | Sqm
1 | Form Work C/S for Tie Beam (230x200) for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22) (230x200)
1.1 | longitudianal axies | Sqm | 2 | 2 | 5.85 |  | 0.2 | 4.68 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.8 |  | 0.2 | 1.44 |  | 4B
1.2 | longitudianal axies | Sqm | 2 | 2 | 5.025 |  | 0.2 | 4.02 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.8 |  | 0.2 | 1.44 |  | 4B
2 | Form Work C/S Tie Beam (230x200) for Green Planter South side of BH-03 towards Basket Ball Ground (Drg. No. TU/LA-P-206.1) (26'-27'/46-51) | [8 empty] | 4B
2.1 | longitudianal axies | Sqm | 2 | 2 | 5.85 |  | 0.2 | 4.68 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.2 |  | 0.2 | 0.96 |  | 4B
2.2 | longitudianal axies | Sqm | 2 | 2 | 5.025 |  | 0.2 | 4.02 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.2 |  | 0.2 | 0.96 |  | 4B
3 | Form Work C/S Tie Beam (230x200) for Green Planter West side of BH-02 under transfer slab (Drg. No. TU/LA-P-206.1) (7'-14'/32-33) | [8 empty] | 4B
3.1 | longitudianal axies | Sqm | 2 | 2 | 5.85 |  | 0.2 | 4.68 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.2 |  | 0.2 | 0.96 |  | 4B
3.2 | longitudianal axies | Sqm | 2 | 2 | 5.025 |  | 0.2 | 4.02 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.2 |  | 0.2 | 0.96 |  | 4B
3.3 | longitudianal axies | Sqm | 2 | 2 | 2.625 |  | 0.2 | 2.1 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.2 |  | 0.2 | 0.96 |  | 4B
3.4 | longitudianal axies | Sqm | 2 | 2 | 2.4 |  | 0.2 | 1.92 |  | 4B
| Transverse axies | Sqm | 2 | 2 | 1.2 |  | 0.2 | 0.96 |  | 4B
4B
4 | Form Work C/S at Podium Lvl. For Chess Table (GYM Podium) | [8 empty] | 4B
| Chess Tabel (1500x1500) | Sqm | 10 | 1 | 1.44 | 1.44 |  | 20.74 |  | 4B
| deduct brick portion | Sqm | -1 | 10 | 0.84 | 0.84 |  | -7.06 |  | 4B
| R.C.C. band under seat (outer side) | Sqm | 10 | 4 | 0.84 |  | 0.23 | 7.73 |  | 4B
|  | Sqm | 10 | 4 | 0.38 |  | 0.23 | 3.5 |  | 4B
| side portion | Sqm | 10 | 4 |  |  | 0.1 | 4 |  | 4B
4B
5 | Form Work C/S Beam (385x275) for Seprate Seat | [8 empty] | 4B
5.1 | Form Work C/S Beam (385x275) for seprate seat under transfer slab of BH-03 towards Basket Ball Ground | [8 empty] | 4B
| TOS lvl. +0.5m | Sqm | 4 | 2 | 2.835 |  | 0.275 | 6.24 |  | 4B
| bottom face | Sqm | 4 | 1 | 2.835 | 0.155 |  | 1.76 |  | 4B
| side face | Sqm | 4 | 2 | 0.385 |  | 0.275 | 0.85 |  | 4B
5.2 | Form Work C/S Beam (385x275) for seprate seat near Basket Ball Ground | [8 empty] | 4B
| TOS lvl. +0.5m | CUM | 2 | 2 | 2.835 | 0.385 | 0.275 | 1.2 |  | 4B
| bottom face | Sqm | 2 | 1 | 2.835 | 0.155 |  | 0.88 |  | 4B
| side face | Sqm | 2 | 2 | 0.385 |  | 0.275 | 0.42 |  | 4B
5.3 | R.C.C. Beam (385x275) for seprate seat under transfer slab of BH-02 towards Gym | [8 empty] | 4B
| TOS lvl. +0.5m | CUM | 6 | 2 | 2.835 | 0.385 | 0.275 | 3.6 |  | 4B
| bottom face | Sqm | 6 | 1 | 2.835 | 0.155 |  | 2.64 |  | 4B
| side face | Sqm | 6 | 2 | 0.385 |  | 0.275 | 1.27 |  | 4B
5.4 | Form Work C/S Beam (385x275) for seprate seat under transfer slab of BH-04 towards Waterbody | [8 empty] | 4B
| TOS lvl. +0.5m | CUM | 7 | 2 | 2.835 | 0.385 | 0.275 | 4.2 |  | 4B
| bottom face | Sqm | 7 | 1 | 2.835 | 0.155 |  | 3.08 |  | 4B
| side face | Sqm | 7 | 2 | 0.385 |  | 0.275 | 1.48 |  | 4B
5.5 | Form Work C/S Beam (385x275) for seprate seat under transfer slab of BH-01 towards Canteen | [8 empty] | 4B
| TOS lvl. +0.5m | CUM | 6 | 2 | 2.835 | 0.385 | 0.275 | 3.6 |  | 4B
| bottom face | Sqm | 6 | 1 | 2.835 | 0.155 |  | 2.64 |  | 4B
| side face | Sqm | 6 | 2 | 0.385 |  | 0.275 | 1.27 |  | 4B
5.6 | Form Work C/S Beam (385x275) for seprate seat at waterbody | [8 empty] | 4B
| TOS lvl. +0.5m | CUM | 8 | 2 | 2.835 | 0.385 | 0.275 | 4.8 |  | 4B
| bottom face | Sqm | 8 | 1 | 2.835 | 0.155 |  | 3.52 |  | 4B |  | 12
| side face | Sqm | 8 | 2 | 0.385 |  | 0.275 | 1.69 |  | 4B
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 2062.67 | 0
| Form Work C/S for Light Pole Foundation near Basket Ball Ground (900x900) | Sqm | 2 | 4 | 0.9 |  | 0.25 | 1.8 |  | 4A
| Pedestal (250x250) | Sqm | 2 | 4 | 0.25 |  | 1.2 | 2.4 |  | 4B
| Form Work C/S for Basket Ball Ground Pole Foundation (1500x1500) | Sqm | 2 | 4 | 1.5 |  | 0.35 | 4.2 |  | 4A
| Pedestal (500x500) | Sqm | 2 | 4 | 0.5 |  | 1.975 | 7.9 |  | 4B
Below measurement shifted from Item No. E.I. 15
Form Work C/S for Planter between BH-01 & Canteen
| Base Footning (4500x1000) | Sqm | 1 | 12 | 4.8 |  | 0.3 | 17.28 |  | 4A
|  | Sqm | 2 | 9 | 1.3 |  | 0.3 | 7.02 |  | 4A
Form Work C/S for Planter between BH-04 & Base of Waterbody M3
| Base Footning (4500x1000) | Sqm | 1 | 10 | 4.8 |  | 0.3 | 14.4 |  | 4A
|  | Sqm | 2 | 8 | 1.3 |  | 0.3 | 6.24 |  | 4A
| Reclaim | Sqm |  |  | #REF!
BH4
| RCC Planter Besides ST-03 | Sqm | 3 | 2 | 1.5 |  | 0.873 | 7.86 |  | 4B
|  | Sqm | 3 | 2 | 3 |  | 0.873 | 15.71 |  | 4B
|  | Sqm | 3 | 2 | 1 |  | 0.723 | 4.34 |  | 4B
| RCC Planter Besides ST-03 | Sqm | 6 | 1 | 1.5 |  | 0.873 | 7.86 |  | 4B
|  | Sqm | 6 | 1 | 3 |  | 0.873 | 15.71 |  | 4B
|  | Sqm | 6 | 2 | 1 |  | 0.723 | 8.68 |  | 4B
BH3
| RCC Planter Besides ST-03 | Sqm | 2 | 2 | 1.5 |  | 0.873 | 5.24 |  | 4B
|  | Sqm | 2 | 2 | 3 |  | 0.873 | 10.48 |  | 4B
|  | Sqm | 2 | 2 | 1 |  | 0.723 | 2.89 |  | 4B
| RCC Planter Besides ST-03 | Sqm | 6 | 1 | 1.5 |  | 0.873 | 7.86 |  | 4B
|  | Sqm | 6 | 1 | 3 |  | 0.873 | 15.71 |  | 4B
|  | Sqm | 6 | 2 | 1 |  | 0.723 | 8.68 |  | 4B
Measurement shifted from EI-03 Form Faced Shuttering
Form Work C/S for Planter between BH-03 & Basket Ball Ground
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 10 | 4.5 |  | 1.025 | 46.13 |  | 4B
| outer face | Sqm | 2 | 8 | 1 |  | 0.8 | 12.8 |  | 4B
Form Work C/S for Planter between BH-04 & Base of Waterbody M3
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 10 | 4.5 |  | 1.025 | 46.13 |  | 4B
| outer face | Sqm | 2 | 8 | 1 |  | 0.8 | 12.8 |  | 4B
Form Work C/S for Planter between BH-01 & Canteen
| Base Footning (4500x1000) | Sqm | 0 | 12 | 4.8 |  | 0.3
|  | Sqm | 0 | 9 | 1.3 |  | 0.3
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 12 | 4.5 |  | 1.025 | 55.35 |  | 4B
| outer face | Sqm | 2 | 9 | 1 |  | 0.8 | 14.4 |  | 4B
Form Work C/S for Planter between BH-04 & Base of Waterbody M3
| Base Footning (4500x1000) | Sqm | 0 | 10 | 4.8 |  | 0.3 |  |  | 4B
|  | Sqm | 0 | 8 | 1.3 |  | 0.3 |  |  | 4B
Form Work C/S for Wall of R.C.C. PLanter (4500x1000)
| outer face wall | Sqm | 1 | 10 | 4.5 |  | 1.025 | 46.13 |  | 4B
| outer face | Sqm | 2 | 8 | 1 |  | 0.8 | 12.8 |  | 4B
| THIS BILL TOTAL → | Sqm | [6 empty] | 418.8 | 6th RA
2481.47
NS-04a | RAFT OF PLANTER WALLS TIE BEAM ON BRICK WALLS etc. ALL WORK FOR HARDSCAPE WORK | Sqm | 1 | [5 empty] | 1273.5 |  | 1398.49
NS-04b | FOR SIDE & BOTTOM OF SEATING SLAB EDGE,WALL OF PLANTERS ETC. | Sqm | 1 | [5 empty] | 1207.97
NS-4c | Extra over item no. E.I. 02 for Round, Circular shuttering
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
| Form Work C/S for Waterbody as per drg. No.(inner dia. 20.12m), dia. For R.C.C. =20.12+0.2*2+0.6*2=21.720m) | Sqm |  |  | area
| Base raft dia. 21.72m | Sqm | 1 | 1 | 68.2008 |  | 0.2 | 13.64
| add for hold area (dia. 18.32m) | Sqm | 1 | 1 | 57.5248 |  | 0.2 | 11.5
| Form Work for wall 200mm thk. (outer face) | Sqm | 1 | 1 | 64.4328 |  | 0.545 | 35.12
| inner face of wall | Sqm | 1 | 1 | 63.1768 |  | 0.545 | 34.43
| Form Work C/S for wall top beam (390x150) (outer) | Sqm | 1 | 1 | 64.4328 |  | 0.15 | 9.66
| inner shutt. Beam | Sqm | 1 | 1 | 63.1768 |  | 0.34 | 21.48
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
NS-05 | Providing and constructing half brick masonry using selected quality burnt clay FPS brick of class designation 75 in super structure laid in cement mortar 1:4 (1 cement : 4 coarse sand) mix, joints finished, flush / raked to 6mm depth as directed by Owner including providing and placing one no. 16 gauge 25 mm wide MS flat hoop reinforcement at every fourth course and anchoring the same by screwing with R.C.C members, scaffolding, curing, complete as per specification and drawing or as directed by Owner.
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
1 | Brick Work P/L for Filter Pit of Waterbody (2000x2000x1800) | Sqm | 1 | 2 | 2.4 |  | 2 | 9.6
|  | Sqm | 1 | 2 | 2.63 |  | 2 | 10.52
2 | Brick work for sump (900x900x850) | Sqm | 5 | 2 | 1.3 |  | 0.85 | 11.05
|  | Sqm | 5 | 2 | 1.53 |  | 0.85 | 13.01
Brick Work for Light Pole Foundation near Basket Ball Ground (900x900)
| Pedestal (250x250) | Sqm | 2 | 2 | 0.25 |  | 1.2 | 1.2
|  | Sqm | 2 | 2 | 0.48 |  | 1.2 | 2.3
Brick Work P/L for Basket Ball Ground Pole Foundation (1500x1500)
| Pedestal (500x500) | Sqm | 2 | 2 | 0.5 |  | 1.975 | 3.95
|  | Sqm | 2 | 2 | 0.73 |  | 1.975 | 5.77
| THIS BILL TOTAL → | Sqm | [6 empty] | 57.4 | 6th RA
57.4
NS-06 | Demolishing of P.C.C. & Stone Soling as per direction of Engineer in Charge
| UP TO PREVIOUS BILL | Cum | [6 empty] | 0
| Demolishing of P.C.C. or Stone Soling in Waterbody for Sump (900x900x850) | Cum | 1 | 5 | 1.9 | 1.9 | 0.25 | 4.51
| Demolishing of P.C.C. or Stone Soling in Waterbody for Filter Pit (2000x2000x1800) | Cum | 1 | 1 | 3 | 3 | 0.225 | 2.03
| P.C.C. desmentlling for Basket Ball Ground Pole Foundation (1500x1500) | Cum | 2 | 1 | 1.7 | 1.7 | 0.1 | 0.58
| P.C.C. desmentling for Basket ball Pole | Cum | 2 | 1 | 2.3 | 2.3 | 0.1 | 1.06
Agra Red Sandstone desmentling for Drain making at Canteen Podium as per direction of Engineer in Charge
b | Agra Natural Sandstone P/L at Canteen Podium for Making of Drain after fixing of Stone (Rework) as per direction of Engineer in Charge
| Drain Stone parallel to BH-02 at Canteen Face | Cum | 1 | 1 | 12.538 | 0.3 | 0.11 | 0.41
| Drain Stone parallel to Pargola at canteen | Cum | 1 | 1 | 4.16 | 0.3 | 0.11 | 0.14
|  | Cum | 1 | 1 | 15.844 | 0.3 | 0.11 | 0.52
| Drain Stone north side of canteen pargola parallel to outer railing | Cum | 1 | 1 | 31.93 | 0.3 | 0.11 | 1.05
| Drain parallel to long planter near stair case at canteen (east face) | Cum | 1 | 1 | 24.785 | 0.3 | 0.11 | 0.82
| south face of planter, Drain | Cum | 1 | 1 | 8 | 0.3 | 0.11 | 0.26
| JMR REQUIRED | Cum | -1 |  | 11.38 |  |  | -11.38
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
NS-07 | MS Tray Square, 6mm thk.
| UP TO PREVIOUS BILL | Kg | [6 empty] | 0
0
1 | 740x740 (inner size) | Each | 97
2 | 610x610 | Each | 27
3 | 900x800 | Each | 14
4 | 315x315 | Each | 34
5 | 880x870 | Each | 2
6 | 800x800 | Each | 1
7 | 900x900 | Each | 2
8 | 600x600 | Each | 2
9 | 950x950 | Each | 5
10 | 1100x1100 | Each | 1
11 | 750x750 | Each | 2
12 | 550x550 | Each | 3
13 | 1000x1000 | Each | 1
1 | (740x740 =inner size) (890x890 = MS Tray) |  |  |  | L | B | wt. | 0
| MS Flat 65x6mm (890x890) | Kg | 97 | 4 | 0.884 |  | 3.06 | 1049.56
| MS Plate 6mm thk. | Kg | 97 | 1 | 0.89 | 0.89 | 47.1 | 3618.87
| corner chamfer flat | Kg | 97 | 2 | 0.075 | 0.075 | 47.1 | 51.4
| side packing | Kg | 97 | 4 | 0.1 |  | 3.06 | 118.73
2 | (610x610 =inner size) (760x760 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm (760x760) | Kg | 27 | 4 | 0.754 |  | 3.06 | 249.18
| MS Plate 6mm thk. | Kg | 27 | 1 | 0.76 | 0.76 | 47.1 | 734.53
| corner chamfer flat | Kg | 27 | 2 | 0.075 | 0.075 | 47.1 | 14.31
| side packing | Kg | 27 | 4 | 0.1 |  | 3.06 | 33.05
3 | (900x800 =inner size) (1050x950 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 14 | 2 | 1.044 |  | 3.06 | 89.45
|  | Kg | 14 | 2 | 0.944 |  | 3.06 | 80.88
| MS Plate 6mm thk. | Kg | 14 | 1 | 1.05 | 0.95 | 47.1 | 657.75
| corner chamfer flat | Kg | 14 | 2 | 0.075 | 0.075 | 47.1 | 7.42
| side packing | Kg | 14 | 4 | 0.1 |  | 3.06 | 17.14
4 | (315x315 =inner size) (465x465 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 34 | 4 | 0.459 |  | 3.06 | 191.02
| MS Plate 6mm thk. | Kg | 34 | 1 | 0.465 | 0.465 | 47.1 | 346.26
| corner chamfer flat | Kg | 34 | 2 | 0.075 | 0.075 | 47.1 | 18.02
| side packing | Kg | 34 | 4 | 0.1 |  | 3.06 | 41.62
5 | (880x870 =inner size) (1050x950 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 2 | 2 | 1.024 |  | 3.06 | 12.53
|  | Kg | 2 | 2 | 1.02 |  | 3.06 | 12.48
| MS Plate 6mm thk. | Kg | 2 | 1 | 1.03 | 1.02 | 47.1 | 98.97
| corner chamfer flat | Kg | 2 | 2 | 0.075 | 0.075 | 47.1 | 1.06
| side packing | Kg | 2 | 4 | 0.1 |  | 3.06 | 2.45
6 | (800x800 =inner size) (950x950 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 1 | 4 | 0.944 |  | 3.06 | 11.55
| MS Plate 6mm thk. | Kg | 1 | 1 | 0.95 | 0.95 | 47.1 | 42.51
| corner chamfer flat | Kg | 1 | 2 | 0.075 | 0.075 | 47.1 | 0.53
| side packing | Kg | 1 | 4 | 0.1 |  | 3.06 | 1.22
7 | (900x900 =inner size) (1050x1050 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 2 | 4 | 1.044 |  | 3.06 | 25.56
| MS Plate 6mm thk. | Kg | 2 | 1 | 1.05 | 1.05 | 47.1 | 103.86
| corner chamfer flat | Kg | 2 | 2 | 0.075 | 0.075 | 47.1 | 1.06
| side packing | Kg | 2 | 4 | 0.1 |  | 3.06 | 2.45
8 | (600x600 =inner size) (750x750 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 2 | 4 | 0.744 |  | 3.06 | 18.21
| MS Plate 6mm thk. | Kg | 2 | 1 | 0.75 | 0.75 | 47.1 | 52.99
| corner chamfer flat | Kg | 2 | 2 | 0.075 | 0.075 | 47.1 | 1.06
| side packing | Kg | 2 | 4 | 0.1 |  | 3.06 | 2.45
9 | (950x950 =inner size) (1100x1100 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 5 | 4 | 1.094 |  | 3.06 | 66.95
| MS Plate 6mm thk. | Kg | 5 | 1 | 1.1 | 1.1 | 47.1 | 284.96
| corner chamfer flat | Kg | 5 | 2 | 0.075 | 0.075 | 47.1 | 2.65
| side packing | Kg | 5 | 4 | 0.1 |  | 3.06 | 6.12
10 | (1100x1100 =inner size) (1250x1250 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 1 | 4 | 1.244 |  | 3.06 | 15.23
| MS Plate 6mm thk. | Kg | 1 | 1 | 1.25 | 1.25 | 47.1 | 73.59
| corner chamfer flat | Kg | 1 | 2 | 0.075 | 0.075 | 47.1 | 0.53
| side packing | Kg | 1 | 4 | 0.1 |  | 3.06 | 1.22
11 | (750x750 =inner size) (900x900 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 2 | 4 | 0.894 |  | 3.06 | 21.89
| MS Plate 6mm thk. | Kg | 2 | 1 | 0.9 | 0.9 | 47.1 | 76.3
| corner chamfer flat | Kg | 2 | 2 | 0.075 | 0.075 | 47.1 | 1.06
| side packing | Kg | 2 | 4 | 0.1 |  | 3.06 | 2.45
12 | (550x550 =inner size) (700x700 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 3 | 4 | 0.694 |  | 3.06 | 25.48
| MS Plate 6mm thk. | Kg | 3 | 1 | 0.7 | 0.7 | 47.1 | 69.24
| corner chamfer flat | Kg | 3 | 2 | 0.075 | 0.075 | 47.1 | 1.59
| side packing | Kg | 3 | 4 | 0.1 |  | 3.06 | 3.67
13 | (1000x1000 =inner size) (1000x1000 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 1 | 4 | 1.144 |  | 3.06 | 14
| MS Plate 6mm thk. | Kg | 1 | 1 | 1.15 | 1.15 | 47.1 | 62.29
| corner chamfer flat | Kg | 1 | 2 | 0.075 | 0.075 | 47.1 | 0.53
| side packing | Kg | 1 | 4 | 0.1 |  | 3.06 | 1.22
14 | (1000x1000 =inner size) (1000x1000 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 0 | 4 | 1.15 |  | 3.06 |  |  | Repeated
| MS Plate 6mm thk. | Kg | 0 | 1 | 1.15 | 1.15 | 47.1 |  |  | Repeated
| corner chamfer flat | Kg | 0 | 2 | 0.075 | 0.075 | 47.1 |  |  | Repeated
| side packing | Kg | 0 | 4 | 0.1 |  | 3.06 |  |  | Repeated
MS Tray Square 6mm thk. (with slot)
| UP TO PREVIOUS BILL | Kg | [6 empty] | 0
0
1 | 500x460 (inner size of Manhole) | Each | 21
2 | 500x400 | Each | 5
3 | 470x430 | Each | 7
4 | 430x430 | Each | 4
5 | 570x570 | Each | 1
1 | (500x460 =inner size) (650x610 = MS Tray) |  |  |  | L |  | wt. | 0
| MS Flat 65x6mm | Kg | 21 | 2 | 0.644 |  | 3.06 | 82.77
|  | Kg | 21 | 2 | 0.604 |  | 3.06 | 77.63
| partition flat patti 65x6 | Kg | 21 | 2 | 0.638 |  | 3.06 | 82
| MS Plate 6mm thk. | Kg | 21 | 1 | 0.65 | 0.61 | 47.1 | 392.18
| corner chamfer flat | Kg | 21 | 2 | 0.075 | 0.075 | 47.1 | 11.13
| side packing | Kg | 21 | 4 | 0.1 |  | 3.06 | 25.7
2 | (500x400 =inner size) (650x550 = MS Tray) |  |  |  | L |  | wt.
| MS Flat 65x6mm | Kg | 5 | 2 | 0.644 |  | 3.06 | 19.71
|  | Kg | 5 | 2 | 0.55 |  | 3.06 | 16.83
| partition flat patti 65x6 | Kg | 5 | 2 | 0.638 |  | 3.06 | 19.52
| MS Plate 6mm thk. | Kg | 5 | 1 | 0.65 | 0.55 | 47.1 | 84.19
| corner chamfer flat | Kg | 5 | 2 | 0.075 | 0.075 | 47.1 | 2.65
| side packing | Kg | 5 | 4 | 0.1 |  | 3.06 | 6.12
3 | (470x430 =inner size) (620x580 = MS Tray) |  |  |  | L |  | wt.
| MS Flat 65x6mm | Kg | 7 | 2 | 0.614 |  | 3.06 | 26.3
|  | Kg | 7 | 2 | 0.58 |  | 3.06 | 24.85
| partition flat patti 65x6 | Kg | 7 | 2 | 0.638 |  | 3.06 | 27.33
| MS Plate 6mm thk. | Kg | 7 | 1 | 0.62 | 0.58 | 47.1 | 118.56
| corner chamfer flat | Kg | 7 | 2 | 0.075 | 0.075 | 47.1 | 3.71
| side packing | Kg | 7 | 4 | 0.1 |  | 3.06 | 8.57
4 | (430x430 =inner size) (580x580 = MS Tray) |  |  |  | L |  | wt.
| MS Flat 65x6mm | Kg | 4 | 2 | 0.574 |  | 3.06 | 14.05
|  | Kg | 4 | 2 | 0.58 |  | 3.06 | 14.2
| partition flat patti 65x6 | Kg | 4 | 2 | 0.568 |  | 3.06 | 13.9
| MS Plate 6mm thk. | Kg | 4 | 1 | 0.58 | 0.58 | 47.1 | 63.38
| corner chamfer flat | Kg | 4 | 2 | 0.075 | 0.075 | 47.1 | 2.12
| side packing | Kg | 4 | 4 | 0.1 |  | 3.06 | 4.9
5 | (570x570 =inner size) (720x720 = MS Tray) |  |  |  | L |  | wt.
| MS Flat 65x6mm | Kg | 1 | 2 | 0.714 |  | 3.06 | 4.37
|  | Kg | 1 | 2 | 0.72 |  | 3.06 | 4.41
| partition flat patti 65x6 | Kg | 1 | 2 | 0.708 |  | 3.06 | 4.33
| MS Plate 6mm thk. | Kg | 1 | 1 | 0.72 | 0.72 | 47.1 | 24.42
| corner chamfer flat | Kg | 1 | 2 | 0.075 | 0.075 | 47.1 | 0.53
| side packing | Kg | 1 | 4 | 0.1 |  | 3.06 | 1.22
| THIS BILL TOTAL → | Kg | [6 empty] | 9622.68 | 6th RA
9622.68
0
NS-08 | Providing & Fixing 230mm long upvc 75mm OD pipe for sleeve in planters including cutting hole in wall, making good with rich cement sand mortar etc. all complete as directed by engineer in charge.
| UP TO PREVIOUS BILL | Each | [6 empty] | 0
|  | Each | [5 empty] | 0
1 | Providing & Fixing of Sleeve in Planter at Podium | [6 empty] | 0
| Planter at Canteen Podium | [6 empty] | 0
| Long Planter near Stair Case | Each | 1 | 4 |  |  |  | 4
| in Planter (5000x2000) | Each | 1 | 5 |  |  |  | 5
| Long Planter near Pargola | Each | 1 | 4 |  |  |  | 4
| in Planter (5000x2000) | Each | 1 | 5 |  |  |  | 5
Planter at Gym Podium
| Planter towards BH-02 | Each | 1 | 5 |  |  |  | 5
| Long Planter near Pargola | Each | 1 | 5 |  |  |  | 5
| in Planter (5000x2000) | Each | 1 | 4 |  |  |  | 4
2 | Providing & Fixing of Sleeve in R.C.C. Planter at G.Floor
| Proving & Fixing of Sleeve in R.C.C. Planter Under BH-01 Transfer Slab | Each | 9 | 2 |  |  |  | 18
| Proving & Fixing of Sleeve in R.C.C. Planter Under BH-02 Transfer Slab | Each | 8 | 2 |  |  |  | 16
| Proving & Fixing of Sleeve in R.C.C. Planter Under BH-03 Transfer Slab | Each | 8 | 2 |  |  |  | 16
| Proving & Fixing of Sleeve in R.C.C. Planter Under BH-04 Transfer Slab | Each | 8 | 2 |  |  |  | 16
|  | Each | [5 empty] | 0
|  | Each | [5 empty] | 0
| THIS BILL TOTAL → | Each | [6 empty] | 98 | 6th RA
98
NS-09 | Cutting of Holes in Kandla Stone for Cunduit work in Floor
| UP TO PREVIOUS BILL | Each | [6 empty] | 0
|  | Each | [5 empty] | 0
a | Making & Cutting of Holes in Floor for Cunduit work | [6 empty] | 0
| south side of BH-01 ( 2 nos. hole at One location) | Each | 2 | 21 |  |  |  | 42
|  | Each | 2 | 21 |  |  |  | 42
| west side of BH-01 towards wterbody | Each | 2 | 21 |  |  |  | 42
|  | Each | 2 | 12 |  |  |  | 24
| alround of waterboy | Each | 2 | 43 |  |  |  | 86
| hole cutting at road between BH-02 & Waterbody | Each | 2 | 27 |  |  |  | 54
|  | Each | 2 | 24 |  |  |  | 48
| Making Hole in Red Stone Cladding of Podium Staircase | Each | 4 | 11 |  |  |  | 44
b | Making & Cutting of Holes in Floor for Light Fixing in Floor
| south side of BH-01 | Each | 1 | 21 |  |  |  | 21
|  | Each | 1 | 21 |  |  |  | 21
| west side of BH-01 towards wterbody | Each | 1 | 21 |  |  |  | 21
|  | Each | 1 | 12 |  |  |  | 12
| alround of waterboy | Each | 1 | 43 |  |  |  | 43
| hole cutting at road between BH-02 & Waterbody | Each | 1 | 27 |  |  |  | 27
|  | Each | 1 | 24 |  |  |  | 24
| Making Hole in Red Stone Cladding of Podium Staircase | Each | 2 | 11 |  |  |  | 22
Hole Cutting at Podium Lvl.
c | Making & Cutting of Holes in Floor for Conduit work
c.1 | Canteen Podium
| at Canteen Podium in Floor for Conduit on floor parallel to BH-01 | Each | 1 | 16 |  |  |  | 16
| at Canteen Podium in Floor for Conduit on floor parallel to BH-02 | Each | 1 | 5 |  |  |  | 5
| Hole cutting around long planter near stair case for Conduit | Each | 1 | 32 |  |  |  | 32
| Hole cutting around long planter near pargola for Conduit | Each | 1 | 24 |  |  |  | 24
Hole Cutting for Conduit in Planter Wall Cladding
| Long Planter near Stair case at Canteen podium | Each | 0 | 10
| Long Planter near Pargola at Canteen podium | Each | 1 | 8 |  |  |  | 8
c.2 | Gym Podium
| Hole cutting at Gym Podium for Conduit | Each | 1 | 38 |  |  |  | 38
| Hole cutting at Gym Podium for Conduit parallel to BH-03 | Each | 1 | 13 |  |  |  | 13
| Hole Cutting for Conduit in Planter Wall Cladding | Each | 0 | 15
| Cutting of Stone for Pole Fixing at Canteen Podium | Each | 0 | 4
| Cutting of Stone for Pole Fixing at Gym Podium | Each | 1 | 8 |  |  |  | 8
|  | Each | [5 empty] | 0
|  | Each | [5 empty] | 0
|  | Each | [5 empty] | 0
| THIS BILL TOTAL → | Each | [6 empty] | 717 | 6th RA
717
NS-10 | Extra over item no. 3.0 for Round, Circular Brick Work with bricks of class designation 75 in foundation, plinth & superstructure in: cement mortar 1:6 (1cement : 6 coarse sand).
| UP TO PREVIOUS BILL | Cum | [6 empty] | 0
Brick Work for Waterbody
| Brick Work outer side of Waterbody (dia.=20.12+0.2*2+0.23*2 =20.98) | Cum | 1 | 1 | 64.998 | 0.23 | 0.545 | 8.15
|  |  | -1 |  | 8.15 |  |  | -8.15
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
0
NS-13 | Champhering of Edges
| UP TO PREVIOUS BILL | Rmt | [6 empty] | 0
0
1 | Champhering at Coping at side cladding in staircase 5x5mm | [6 empty] | 0
| Coping at side cladding in staircase R.H.S. | [6 empty] | 0
| 1st, 2nd & 3rd Flight | Rmt | 1 | 3 | 3.822 |  |  | 11.47
| 4th Flight | Rmt | 1 | 1 | 3.471 |  |  | 3.47
| 1st, 2nd, 3rd Landing | Rmt | 1 | 3 | 2.794 |  |  | 8.38
Coping at side cladding in staircase L.H.S.
| 1st, 2nd & 3rd Flight | Rmt | 1 | 3 | 3.822 |  |  | 11.47
| 4th Flight | Rmt | 1 | 1 | 3.471 |  |  | 3.47
| 1st, 2nd, 3rd Landing | Rmt | 1 | 3 | 2.794 |  |  | 8.38
| front face for packing | Rmt | 1 | 2 | 0.3 |  |  | 0.6
|  | Rmt | 1 | 2 | 0.9 |  |  | 1.8
| champering for trad | Rmt | 1 | 47 | 5.9 |  |  | 277.3
2 | Champhering for Kandla Sandstone Natural Finish 20mm thk. for Seprate Seat (3000x500)
a | Seprate Seat under BH-01 Transfer Slab
| Side Cladding (horizontal edge champher) | Rmt | 6 | 2 | 3 |  |  | 36
|  | Rmt | 6 | 2 | 0.5 |  |  | 6
| vertical edge | Rmt | 6 | 4 |  |  | 0.335 | 8.04
b | Seprate Seat under BH-04 Transfer Slan
| Side Cladding | Rmt | 7 | 2 | 3 |  |  | 42
|  | Rmt | 7 | 2 | 0.5 |  |  | 7
| vertical edge | Rmt | 7 | 4 |  |  | 0.335 | 9.38
c | Seprate Seat under BH-02 Transfer Slan
| Side Cladding | Rmt | 6 | 2 | 3 |  |  | 36
|  | Rmt | 6 | 2 | 0.5 |  |  | 6
| vertical edge | Rmt | 6 | 4 |  |  | 0.335 | 8.04
d | Seprate Seat under BH-03 Transfer Slan
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
| vertical edge | Rmt | 4 | 4 |  |  | 0.335 | 5.36
e | Seprate Seat near basket ball ground
| Side Cladding | Rmt | 2 | 2 | 3 |  |  | 12
|  | Rmt | 2 | 2 | 0.5 |  |  | 2
| vertical edge | Rmt | 2 | 4 |  |  | 0.335 | 2.68
f | Seprate Seat near Waterbody
| Side Cladding | Rmt | 8 | 2 | 3 |  |  | 48
|  | Rmt | 8 | 2 | 0.5 |  |  | 8
| vertical edge | Rmt | 8 | 4 |  |  | 0.335 | 10.72
g | Seat at Green Planter East side of BH-01
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
| vertical edge | Rmt | 4 | 4 |  |  | 0.335 | 5.36
h | Seat at Green Planter between BH-04 & BH-07
| Side Cladding | Rmt | 8 | 2 | 3 |  |  | 48
|  | Rmt | 8 | 2 | 0.5 |  |  | 8
| vertical edge | Rmt | 8 | 4 |  |  | 0.335 | 10.72
i | Seat at Green Planter between BH-04 & BH-05
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
| vertical edge | Rmt | 4 | 4 |  |  | 0.335 | 5.36
j | Seat at Green Planter of basket ball ground
| Side Cladding | Rmt | 3 | 2 | 3 |  |  | 18
|  | Rmt | 3 | 2 | 0.5 |  |  | 3
| vertical edge | Rmt | 3 | 4 |  |  | 0.335 | 4.02
k | Seat at Green Planter south sid eof BH-02 (long planter) between BH-02 & Waterbody
| Side Cladding | Rmt | 11 | 2 | 3 |  |  | 66
|  | Rmt | 11 | 2 | 0.5 |  |  | 11
| vertical edge | Rmt | 11 | 4 |  |  | 0.335 | 14.74
l | Seat at Green Planter north side of BH-02
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
| vertical edge | Rmt | 4 | 4 |  |  | 0.335 | 5.36
m | Seat at Green Planter between BH-01 & waterbody
| Side Cladding | Rmt | 12 | 2 | 3 |  |  | 72
|  | Rmt | 12 | 2 | 0.5 |  |  | 12
| vertical edge | Rmt | 12 | 4 |  |  | 0.335 | 16.08
n | Seat at Green Planter west side of Gym
| Side Cladding | Rmt | 8 | 2 | 3 |  |  | 48
|  | Rmt | 8 | 2 | 0.5 |  |  | 8
| vertical edge | Rmt | 8 | 4 |  |  | 0.335 | 10.72
3 | Champhering for Waterbody Coping
| Waterbody Champhering inner side (Dia.-20.12) | Rmt | 1 | 1 | 63.1768 |  |  | 63.18
| Waterbody Champhering outer side (Dia.-21.26) | Rmt | 1 | 1 | 66.7564 |  |  | 66.76
| inner podium pasage Col. Dia.=1.2m | Rmt | 1 | 2 | 3.768 |  |  | 7.54
4 | Making of Champhering of Agra Red Sandstone Polished Finish M3 at Planter Coping Lvl. 40mm thk.
4.1 | Champhering of Coping at Planter & Seats at Canteen Podium
| Planter near stair case (long Planter) (outer side Champhering) | Rmt | 1 | 2 | 22.08 |  |  | 44.16
|  | Rmt | 1 | 2 | 2.74 |  |  | 5.48
| inner side champhering | Rmt | 1 | 2 | 21.42 |  |  | 42.84
|  | Rmt | 1 | 2 | 2.41 |  |  | 4.82
| Planter (5000x2000)(attached with long planter) (outer side) | Rmt | 5 | 2 | 5.04 |  |  | 50.4
|  | Rmt | 5 | 2 | 2.08 |  |  | 20.8
| inne side | Rmt | 5 | 2 | 4.38 |  |  | 43.8
|  | Rmt | 5 | 2 | 1.42 |  |  | 14.2
| long Planter near pargola top coping (outer + inner) | Rmt | 4 | 4 | 3 |  |  | 48
| Planter (5000x2000)(attached with long planter) (outer) | Rmt | 5 | 2 | 5.04 |  |  | 50.4
|  | Rmt | 5 | 2 | 2.08 |  |  | 20.8
| (inner) | Rmt | 5 | 2 | 4.38 |  |  | 43.8
|  | Rmt | 5 | 2 | 1.42 |  |  | 14.2
| Seprate Seat top (1000x1000) | Rmt | 24 | 4 | 1 |  |  | 96
b.2 | Champhering Coping at Planter & Seats at Gym Podium
| coping top at long Planter (outer) | Rmt | 1 | 2 | 29.115 |  |  | 58.23
|  | Rmt | 1 | 2 | 3.08 |  |  | 6.16
| Inner side | Rmt | 1 | 2 | 28.455 |  |  | 56.91
|  | Rmt | 1 | 2 | 2.42 |  |  | 4.84
| Planter merged in long Planter (5000x2000) (outer) | Rmt | 5 | 2 | 5.08 |  |  | 50.8
|  | Rmt | 5 | 1 | 2.08 |  |  | 10.4
| Inner side | Rmt | 5 | 2 | 4.42 |  |  | 44.2
|  | Rmt | 5 | 1 | 1.42 |  |  | 7.1
| Planter (2685x2300) (outer side) | Rmt | 3 | 2 | 2.765 |  |  | 16.59
|  | Rmt | 3 | 2 | 2.38 |  |  | 14.28
| inner | Rmt | 3 | 2 | 2.105 |  |  | 12.63
|  | Rmt | 3 | 2 | 1.72 |  |  | 10.32
| Planter (2632x2000) | Rmt | 5 | 2 | 2.712 |  |  | 27.12
|  | Rmt | 5 | 2 | 2.08 |  |  | 20.8
|  | Rmt | 5 | 2 | 2.052 |  |  | 20.52
|  | Rmt | 5 | 2 | 1.42 |  |  | 14.2
| Chess Table Top (1500x1500) | Rmt | 10 | 4 | 1.5 |  |  | 60
| Chess table seat (500x500) | Rmt | 40 | 4 | 0.5 |  |  | 80
|  |  | -1 |  | 2204.2 |  |  | -2204.2
0
| THIS BILL TOTAL → | Rmt | [6 empty] | 0 | 6th RA
0
NS-14 | Making of Groove in Stone Cladding for Architectural Appreance as per direction of Engineer in Charge
| UP TO PREVIOUS BILL | Cum | [6 empty] | 0
0
1 | Making of Groove at cladding in staircase Podium near canteen | [6 empty] | 0
| Coping at side cladding in staircase R.H.S. | [6 empty] | 0
| 1st, 2nd & 3rd Flight | Rmt | 1 | 3 | 3.822 |  |  | 11.47
| 4th Flight | Rmt | 1 | 1 | 3.471 |  |  | 3.47
| 1st, 2nd, 3rd Landing | Rmt | 1 | 3 | 2.794 |  |  | 8.38
Coping at side cladding in staircase L.H.S.
| 1st, 2nd & 3rd Flight | Rmt | 1 | 3 | 3.822 |  |  | 11.47
| 4th Flight | Rmt | 1 | 1 | 3.471 |  |  | 3.47
| 1st, 2nd, 3rd Landing | Rmt | 1 | 3 | 2.794 |  |  | 8.38
| front face for packing | Rmt | 1 | 2 | 0.3 |  |  | 0.6
|  | Rmt | 1 | 2 | 0.9 |  |  | 1.8
| Making of Groove in Riser of Stair case | Rmt | 1 | 47 | 5.9 |  |  | 277.3
2 | Making of Groove for Kandla Sandstone Natural Finish 20mm thk.Cladding for Seprate Seat (3000x500)
a | Seprate Seat under BH-01 Transfer Slab
| Side Cladding | Rmt | 6 | 2 | 3 |  |  | 36
|  | Rmt | 6 | 2 | 0.5 |  |  | 6
b | Seprate Seat under BH-04 Transfer Slab
| Side Cladding | Rmt | 7 | 2 | 3 |  |  | 42
|  | Rmt | 7 | 2 | 0.5 |  |  | 7
c | Seprate Seat under BH-02 Transfer Slab
| Side Cladding | Rmt | 6 | 2 | 3 |  |  | 36
|  | Rmt | 6 | 2 | 0.5 |  |  | 6
d | Seprate Seat under BH-03 Transfer Slab
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
e | Seprate Seat near basket ball ground
| Side Cladding | Rmt | 2 | 2 | 3 |  |  | 12
|  | Rmt | 2 | 2 | 0.5 |  |  | 2
f | Seprate Seat near Waterbody
| Side Cladding | Rmt | 8 | 2 | 3 |  |  | 48
|  | Rmt | 8 | 2 | 0.5 |  |  | 8
g | Seat at Green Planter East side of BH-01
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
h | Seat at Green Planter between BH-04 & BH-07
| Side Cladding | Rmt | 8 | 2 | 3 |  |  | 48
|  | Rmt | 8 | 2 | 0.5 |  |  | 8
i | Seat at Green Planter between BH-04 & BH-05
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
j | Seat at Green Planter of basket ball ground
| Side Cladding | Rmt | 3 | 2 | 3 |  |  | 18
|  | Rmt | 3 | 2 | 0.5 |  |  | 3
k | Seat at Green Planter south sid eof BH-02 (long planter) between BH-02 & Waterbody
| Side Cladding | Rmt | 11 | 2 | 3 |  |  | 66
|  | Rmt | 11 | 2 | 0.5 |  |  | 11
l | Seat at Green Planter north side of BH-02
| Side Cladding | Rmt | 4 | 2 | 3 |  |  | 24
|  | Rmt | 4 | 2 | 0.5 |  |  | 4
m | Seat at Green Planter between BH-01 & waterbody
| Side Cladding | Rmt | 12 | 2 | 3 |  |  | 72
|  | Rmt | 12 | 2 | 0.5 |  |  | 12
n | Seat at Green Planter west side of Gym
| Side Cladding | Rmt | 8 | 2 | 3 |  |  | 48
|  | Rmt | 8 | 2 | 0.5 |  |  | 8
3 | Making of Groove for Waterbody Coping
| Groove Making in Waterbody inner side (Dia.-20.12) | Rmt | 1 | 1 | 63.1768 |  |  | 63.18
| Groove Making in Waterbody Champhering outer side (Dia.-21.26) | Rmt | 1 | 1 | 66.7564 |  |  | 66.76
4 | Making of Groove of Agra Red Sandstone Polished Finish M3 at Planter Coping Lvl. 40mm thk.
4.1 | Making of Groove at Planter & Seats at Canteen Podium
| Planter near stair case (long Planter) (Horizontal Groove) | Rmt | 1 | 2 | 22.08 |  |  | 44.16
|  | Rmt | 2 | 2 | 2.74 |  |  | 10.96
|  | Rmt | 2 | 2 | 8 |  |  | 32
| Planter (5000x2000)(attached with long planter) | Rmt | 3 | 4 | 5.04 |  |  | 60.48
|  | Rmt | 3 | 4 | 2.08 |  |  | 24.96
| Planter (5000x2000) | Rmt | 2 | 4 | 5.04 |  |  | 40.32
|  | Rmt | 2 | 4 | 2.08 |  |  | 16.64
| long Planter near pargola top coping | Rmt | 4 | 2 | 3 |  |  | 24
| Planter (5000x2000)(attached with long planter) | Rmt | 5 | 4 | 5.04 |  |  | 100.8
|  | Rmt | 5 | 4 | 2.08 |  |  | 41.6
| Seprate Seat top (1000x1000) | Rmt | 24 | 4 | 1 |  |  | 96
Vertical Groove in Planter near Stair case Canteen
| Long Planter | Rmt | 1 | 2 | 0.5 |  |  | 1
| (5000x2000) | Rmt | 3 | 2 | 0.65 |  |  | 3.9
| (5000x2000) | Rmt | 2 | 4 | 0.65 |  |  | 5.2
Vertical Groove in Planter near Pargola Canteen
| Long Planter (5000x2000) | Rmt | 1 | 12 | 0.65 |  |  | 7.8
| Vertical Groove for Seprate Seat (1000x1000) | Rmt | 8 | 4 | 0.45 |  |  | 14.4
Vertical Groove
Planter near stair case (long Planter) (Horizontal Groove)
| Vertical Groove | Rmt | 1 | 73.6 |  |  | 0.5 | 36.8
|  | Rmt | 2 | 9.1333 |  |  | 0.5 | 9.13
|  | Rmt | 2 | 26.6667 |  |  | 0.5 | 26.67
Planter (5000x2000)(attached with long planter)
|  | Rmt | 3 | 33.6 |  |  | 0.65 | 65.52
|  | Rmt | 3 | 13.8667 |  |  | 0.65 | 27.04
Planter (5000x2000)
|  | Rmt | 2 | 33.6 |  |  | 0.65 | 43.68
|  | Rmt | 2 | 13.8667 |  |  | 0.65 | 18.03
long Planter near pargola top coping
| Vertical Groove (length =3.0m) | Rmt | 4 | 20 |  |  | 0.5 | 40
| Planter (5000x2000)(attached with long planter) | Rmt | 2 | 16.6667 |  |  | 0.65 | 21.67
|  | Rmt | 8 | 6.6667 |  |  | 0.65 | 34.67
| Seprate Seat top (1000x1000) | Rmt | 24 | 4 | 1 |  |  | 96
b.2 | Coping at Planter & Seats at Gym Podium
Horizontal Groove
| coping top at long Planter | Rmt | 1 | 2 | 29.115 |  |  | 58.23
|  | Rmt | 1 | 4 | 3.08 |  |  | 12.32
|  | Rmt | 1 | 2 | 3.04 |  |  | 6.08
|  | Rmt | 1 | 8 | 3 |  |  | 24
|  | Rmt | 1 | 2 | 4.075 |  |  | 8.15
| Planter (5000x2000)(attached with long planter) | Rmt | 5 | 4 | 5.08 |  |  | 101.6
|  | Rmt | 5 | 4 | 2.08 |  |  | 41.6
| Planter (2685x2300) | Rmt | 1 | 4 | 2.765 |  |  | 11.06
|  | Rmt | 1 | 4 | 2.38 |  |  | 9.52
| Planter (2685x2200) | Rmt | 1 | 4 | 2.765 |  |  | 11.06
|  | Rmt | 1 | 4 | 2.28 |  |  | 9.12
| Planter (2685x2600) | Rmt | 1 | 4 | 2.765 |  |  | 11.06
|  | Rmt | 1 | 4 | 2.68 |  |  | 10.72
| Planter (2632x2000) | Rmt | 5 | 4 | 2.712 |  |  | 54.24
|  | Rmt | 5 | 4 | 2.08 |  |  | 41.6
| Chess Table Top (1500x1500) (horizontal groove) | Rmt | 10 | 4 | 1.5 |  |  | 60
| Chess table seat (500x500) | Rmt | 10 | 16 | 0.5 |  |  | 80
Vertical Groove
| coping top at long Planter (L=29.12m) | Rmt | 1 | 97.0667 |  |  |  | 97.07
| (L=3.08m) | Rmt | 1 | 10.2667 |  |  |  | 10.27
| (L=3.04m) | Rmt | 1 | 10.1333 |  |  |  | 10.13
| (L=3) | Rmt | 4 | 10 |  |  |  | 40
| (L=4.08) | Rmt | 1 | 13.6 |  |  |  | 13.6
| Planter (5000x2000)(attached with long planter) (L=5.08) | Rmt | 2 | 16.9333 | 5.08 |  |  | 172.04
| (L=2.08) | Rmt | 8 | 6.6667 | 2.08 |  |  | 110.93
| Planter (2685x2300) (L=2.77) | Rmt | 2 | 9.2333 | 2.765 |  |  | 51.06
| (L=2.38) | Rmt | 2 | 7.9333 | 2.38 |  |  | 37.76
| Planter (2685x2200) (L=2.77) | Rmt | 2 | 9.2333 | 2.765 |  |  | 51.06
| (L=2.28) | Rmt | 2 | 7.6 | 2.28 |  |  | 34.66
| Planter (2685x2600) (L=2.77) | Rmt | 2 | 9.2333 | 2.765 |  |  | 51.06
| (L=2.68) | Rmt | 2 | 8.9333 | 2.68 |  |  | 47.88
| Planter (2632x2000) (L=2.71) | Rmt | 5 | 9.0333 | 2.712 |  |  | 122.49
| (L=2.08) | Rmt | 5 | 6.9333 | 2.08 |  |  | 72.11
| Chess Table Top (1500x1500) (horizontal groove) | Rmt | 10 | 4 | 1.5 |  |  | 60
| Chess table seat (500x500) | Rmt | 40 | 4 | 0.5 |  |  | 80
Verical Groove in Cladding at corner
| Long Planter | Rmt | 1 | 4 | 0.5 |  |  | 2
| Planter (5000x2000) | Rmt | 5 | 2 | 0.65 |  |  | 6.5
| planter | Rmt | 8 | 4 | 0.5 |  |  | 16
| Chess Table verticall groove | Rmt | 10 | 4 | 0.95 |  |  | 38
| Chess seat | Rmt | 40 | 4 | 0.45 |  |  | 72
|  |  | -1 |  | 3755.69 |  |  | -3755.69
0
| THIS BILL TOTAL → | Rmt | [6 empty] | 0 | 6th RA
0
0
NS-16 | Extra for Wastage & Cutting Stone in Particular Shape in 40mm natural Finish Kandla Grey Sand Stone
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
| Total Cumm. Qty. of Scheduled Item No. 2.1 | Sqm | 1 |  | 8881.66 |  |  | 8881.66
0
| THIS BILL TOTAL → | Sqm | [6 empty] | 8881.66 | 6th RA
8881.66
NS-17 | Extra over on item No. 2.3 for Extra wastage due to Special shape in paving of Kadappa Stone.
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
| 20mm thk. Kadappa Polish in Waterbody Dia. =20.12m | Sqm | 1 | 1 | 317.7793 |  |  | 317.78 |  | Area
| inner side cladding waterbody | Sqm | 1 | 1 | 63.1768 |  | 0.71 | 44.86
| outer cladding (D=20.12+0.5*2+0.04*2=21.2m) | Sqm | 1 | 1 | 66.568 |  | 0.41 | 27.29
0
| THIS BILL TOTAL → | Sqm | [6 empty] | 389.93 | 6th RA
389.93
E.I. 33 | Backfilling with selected, suitable excavated from outside or adjacent plots in plinths, back of retaining walls, foundations, under floors and trenches and spreading the remaining soil for specified location as directed by the Project Manager and shall be done in layers, not exceeding 20cm in depth and consolidating each deposited layer by mechanical means, ramming and watering till 95% compaction is achieved or as per specifications including re-excavation, transportation, loading, unloading, carriage to dumping spot and all incidentals at all depth, levels, leads and lifts complete. (Net consolidated area fill volume will be computed from the initial and final levels.)
| UP TO PREVIOUS BILL | Cum | [6 empty] | 0
Mesurement same as Excavation-
Stone Agg. 90 to 45mm in Basket Ball Ground
|  | Cum | 1 | 1 | 27.54 | 14.74 | 0.2 | 81.19
0
| Stone Agg. 90 to 45mm in Road |  | 0
| Road between BH-05 & B3 Basket Ground | Cum | 1 | 1 | 29.2 | 6 | 0.2 | 35.04
|  | Cum | 1 | 1 | 8.32 | 6.78 | 0.2 | 11.28
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 23.235 | 6 | 0.2 | 27.88
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 2.275 | 6 | 0.2 | 2.73
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 32.39 | 6 | 0.2 | 38.87
| Road between BH-05 & BH-04 | Cum | 1 | 1 | 5.295 | 6 | 0.2 | 6.35
|  |  | 0 |  |  |  | 0.2
| Road between BH-01 & Waterboy (east side) | Cum | 1 | 1 | 31.463 | 6 | 0.2 | 37.76
| Road between BH-01 & BH-07 (south side) | Cum | 1 | 1 | 33.193 | 6 | 0.2 | 39.83
|  | Cum | 1 | 1 | 29.854 | 6 | 0.2 | 35.82
|  | Cum | 1 | 1 | 33.667 | 6 | 0.2 | 40.4
|  | Cum | 1 | 1 | 12.3 | 6 | 0.2 | 14.76
0
| Stone Agg. 90 to 45mm in Planter Area |  | 0
| Planter Front of Basket Ground (west side) | Cum | 1 | 1 | 6.38 | 1.975 | 0.2 | 2.52
|  | Cum | 1 | 2 | 6.95 | 1.975 | 0.2 | 5.49
|  | Cum | 1 | 1 | 6.12 | 1.67 | 0.2 | 2.04
|  | Cum | 1 | 1 | 4.645 | 1.975 | 0.2 | 1.83
0
|  | Cum | 1 | 1 | 6.885 | 1.27 | 0.2 | 1.75
|  | Cum | 1 | 1 | 2.385 | 2.26 | 0.2 | 1.08
| space between basket ground & planter | Cum | 1 | 1 | 20.17 | 2.125 | 0.2 | 8.57
0
| planter front of Bh-05 (west side) | Cum | 1 | 1 | 12.58 | 1.19 | 0.2 | 2.99
|  | Cum | 1 | 1 | 7.09 | 0.9 | 0.2 | 1.28
|  | Cum | 1 | 1 | 1.6 | 5.98 | 0.2 | 1.91
|  | Cum | 1 | 1 | 1.6 | 4.18 | 0.2 | 1.34
|  | Cum | 1 | 2 | 1.6 | 2.38 | 0.2 | 1.52
|  | Cum | 1 | 1 | 1.145 | 0.9 | 0.2 | 0.21
0
|  | Cum | 1 | 1 | 2.745 | 1.5 | 0.2 | 0.82
|  | Cum | 1 | 1 | 1.6 | 6.675 | 0.2 | 2.14
|  | Cum | 1 | 1 | 3.07 | 1.065 | 0.2 | 0.65
|  | Cum | 1 | 1 | 1.6 | 3.9 | 0.2 | 1.25
|  | Cum | 1 | 1 | 2.77 | 0.96 | 0.2 | 0.53
|  | Cum | 1 | 1 | 1.6 | 4.09 | 0.2 | 1.31
|  | Cum | 1 | 1 | 3.25 | 1.095 | 0.2 | 0.71
|  | Cum | 1 | 1 | 8.61 | 4.615 | 0.2 | 7.95
0
| Stone agg. In planter front between Bh-07 & BH-04 | Cum | 1 | 1 | 1.6 | 8.56 | 0.2 | 2.74
|  | Cum | 1 | 1 | 1.6 | 6.85 | 0.2 | 2.19
|  | Cum | 1 | 1 | 1.6 | 7.45 | 0.2 | 2.38
|  | Cum | 1 | 1 | 0.99 | 8.85 | 0.2 | 1.75
|  | Cum | 1 | 1 | 1.6 | 4.89 | 0.2 | 1.56
|  | Cum | 1 | 1 | 1.6 | 5.33 | 0.2 | 1.71
|  | Cum | 1 | 1 | 1.6 | 1.45 | 0.2 | 0.46
|  | Cum | 1 | 1 | 1.6 | 3.83 | 0.2 | 1.23
|  | Cum | 1 | 1 | 1.415 | 2.425 | 0.2 | 0.69
|  | Cum | 1 | 1 | 0.755 | 1.965 | 0.2 | 0.3
|  | Cum | 1 | 1 | 5.465 | 4.2 | 0.2 | 4.59
0
| Stone agg. In planter east side of BH-1 or front of Water Body | Cum | 1 | 1 | 1.6 | 4 | 0.2 | 1.28
|  | Cum | 1 | 1 | 1.6 | 1 | 0.2 | 0.32
|  | Cum | 1 | 1 | 5.49 | 0.965 | 0.2 | 1.06
|  | Cum | 1 | 1 | 7.09 | 1 | 0.2 | 1.42
|  | Cum | 1 | 1 | 1.6 | 3 | 0.2 | 0.96
|  | Cum | 1 | 1 | 4.345 | 1 | 0.2 | 0.87
|  | Cum | 1 | 1 | 1.6 | 4 | 0.2 | 1.28
|  | Cum | 1 | 2 | 1.6 | 3 | 0.2 | 1.92
0
|  | Cum | 1 | 1 | 20.145 | 2.235 | 0.2 | 9
|  | Cum | 1 | 1 | 1.845 | 4.07 | 0.2 | 1.5
0
|  | Cum | 1 | 1 | 0.685 | 4.13 | 0.2 | 0.57
|  | Cum | 1 | 1 | 3.43 | 1.2 | 0.2 | 0.82
|  | Cum | 1 | 1 | 1.6 | 3 | 0.2 | 0.96
|  | Cum | 1 | 1 | 3.735 | 1.2 | 0.2 | 0.9
|  | Cum | 1 | 1 | 3.43 | 4.235 | 0.2 | 2.91
|  | Cum | 1 | 1 | 1.6 | 1.8 | 0.2 | 0.58
|  | Cum | 1 | 1 | 1.6 | 4.2 | 0.2 | 1.34
|  | Cum | 1 | 1 | 1.6 | 5 | 0.2 | 1.6
|  | Cum | 1 | 1 | 2.135 | 3.235 | 0.2 | 1.38
|  | Cum | 1 | 1 | 3.735 | 3.2 | 0.2 | 2.39
|  | Cum | 1 | 1 | 12.12 | 1.5 | 0.2 | 3.64
|  | Cum | 1 | 1 | 0.99 | 4.13 | 0.2 | 0.82
|  | Cum | 1 | 1 | 1.6 | 4.5 | 0.2 | 1.44
|  | Cum | 1 | 1 | 1.46 | 2.7 | 0.2 | 0.79
|  | Cum | 1 | 1 | 1.6 | 6 | 0.2 | 1.92
0
|  | Cum | 1 | 1 | 20.97 | 2 | 0.2 | 8.39
|  | Cum | 1 | 1 | 1.905 | 6.235 | 0.2 | 2.38
|  | Cum | 1 | 1 | 1.145 | 2 | 0.2 | 0.46
0
|  | Cum | 1 | 1 | 4.345 | 1.2 | 0.2 | 1.04
|  | Cum | 1 | 1 | 1.6 | 1.8 | 0.2 | 0.58
|  | Cum | 1 | 1 | 4.65 | 1 | 0.2 | 0.93
|  | Cum | 1 | 1 | 1.905 | 1.8 | 0.2 | 0.69
| Stone Agg. 90 to 45mm in Ramp Area Front side of Gym (West side) |  | 0
|  | Cum | 1 | 1 | 24.135 | 6.2 | 0.2 | 29.93
|  |  | -1 |  | 525.47 |  |  | -525.47 |  | NOT PAYABLE
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
0

## ROAD SAND FILLING
QUANTITY OF SAND FILLING IN ROAD OF BOYS HOSTAL(AS PLOTED)
DESCRIPTION | UNITS | LENGTH | WIDTH | HIGHT | QUANTITY
ROAD-1 | CUM | 19.476 | 6 | 0.3 | 35.0568
ROAD-2 | CUM | 50.243 | 6 | 0.3 | 90.4374
ROAD-3 | CUM | 67.397 | 6 | 0.3 | 121.3146
ROAD-4 | CUM | 149.302 | 6 | 0.3 | 268.7436
AREA-1 | CUM | 33.761 | 1 | 0.3 | 10.1283
AREA-2 | CUM | 45.214 | 1 | 0.3 | 13.5642
AREA-3 | CUM | 45.514 | 1 | 0.3 | 13.6542
AREA-4 | CUM | 11.751 | 1 | 0.3 | 3.5253
TOTAL QUANTITY |  |  |  |  | 556.4244

## MB GIRLS HOSTEL
Gannon Dunkerley & Co. Ltd.
Construction of Learning Block, Thapar University Patiala
MEASUREMENT SHEET (RA-06)
Name of Structure- "GIRLS HOSTEL-HARDSCAPING"
Item No. | Item | Unit | No. | Side/ Nos | L | B | H/D | Qty | Total Qty | Remarks
2 | Providing and laying in position ready mixed M-25 grade concrete for reinforced concrete works ,using cement content as per approved design mix manufactured in fully automatic batching plant and transported to site of work in transit mixers for all leads having continious agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete worksincluding pumping of R.M.C. from transit mixer to site of laying excluding the finishing and reinforcement including cost of admixture in recommende proportionas per IS:9103 to accelerate/retard setting of concrete , improve workability without imparing strength and durabilityas per direction of the chief enginner-in charge(min OPC contentto be considered in this item is 300kg/cum or as per design mix)
R.C.C. P/L M25 for Tie Beam on Brick Work
| R.C.C. P/L for Waterbody | Cum
| R.C.C. P/L for Base footing of Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For R.C.C. =7+0.2*2+0.6*2=8.60m) | Cum |  |  | area
| base raft dia. 8.6m | Cum | 1 | 1 | 58.0586 |  | 0.2 | 11.61
| deduction for hold area (dia. 5.2m) | Cum | -1 | 1 | 21.2264 |  | 0.2 | -4.25
| R.C.C. wall 200mm thk. | Cum | 1 | 1 | 22.68 | 0.23 | 0.545 | 2.84
| R.C.C. wall top beam (390x150) | Cum | 1 | 1 | 23.216 | 0.39 | 0.15 | 1.36
Cum
| R.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (18/F), Dia. 3.7m | Cum | 1 | 1 | 11.618 | 0.23 | 0.2 | 0.53
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.23 | 0.2 | 0.39
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 8.478 | 0.23 | 0.2 | 0.39
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.23 | 0.2 | 0.43
| at Grid (8/C-D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| at Grid (5-6/D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| at Grid (4-5/E), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| at Grid (3-4/F), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| R.C.C. P/L for Half Curved Seat (drg. No. 5128-16-101) | Cum
| Curved Seat seat at grid (20/F) | Cum | 1 | 1 | 8.215 | 0.23 | 0.2 | 0.38
|  | Cum | 1 | 1 | 8.2535 | 0.21 | 0.1 | 0.17
| Curved Seat seat at grid (12/F) | Cum | 1 | 1 | 2.343 | 0.23 | 0.2 | 0.11
|  | Cum | 1 | 1 | 1.98 | 0.21 | 0.1 | 0.04
| Curved Seat seat at grid (11/F-G) | Cum | 1 | 1 | 5.143 | 0.23 | 0.2 | 0.24
|  | Cum | 1 | 1 | 4.695 | 0.21 | 0.1 | 0.1
R.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101)
| at Grid (8/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (5-6/D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (4-5/E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (3-4/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
R.C.C. P/L for Half Curved Seat (tie beam & seating platform (drg. No. 5128-16-101)
| Curved Seat at grid (10/C-D) | Cum | 1 | 1 | 4.531 | 0.23 | 0.2 | 0.21
|  | Cum | 1 | 1 | 4.002 | 0.21 | 0.1 | 0.08
| Curved Seat seat at grid (9/C-D) | Cum | 1 | 1 | 5.284 | 0.23 | 0.2 | 0.24
|  | Cum | 1 | 1 | 4.807 | 0.21 | 0.1 | 0.1
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.143 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 1 | 2.853 | 0.21 | 0.1 | 0.06
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.121 | 0.23 | 0.2 | 0.14
|  | Cum | 1 | 1 | 2.833 | 0.21 | 0.1 | 0.06
R.C.C. Qty. Revise for calculation correction
| R.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m, (Brick Work Dia. =3+0.115+0.115=3.23m) | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (18/F), Dia. 3.7m (Brick Work Dia. =3.7+0.115+0.115=3.93m) | Cum | 1 | 1 | 12.3402 | 0.23 | 0.2 | 0.57
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.23 | 0.2 | 0.39
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 9.2002 | 0.23 | 0.2 | 0.42
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.23 | 0.2 | 0.47
| deduct qty. of revised measurement(RA-3rd) for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (20/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (18/F), Dia. 3.7m | Cum | -1 | 1 | 11.618 | 0.23 | 0.2 | -0.53
| at Grid (16-17/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (18/C), Dia. 3.0m (half) | Cum | -1 | 1 | 8.566 | 0.23 | 0.2 | -0.39
| at Grid (15/C-D), Dia. 2.7m | Cum | -1 | 1 | 8.478 | 0.23 | 0.2 | -0.39
| at Grid (15/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (14-15/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (13/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (12-13/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (10-11/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (10-11/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (9/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
| at Grid (9/E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.23 | 0.2 | -0.43
R.C.C. P/L for Waterbody
| R.C.C. P/L for Base footing of Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For R.C.C. =7+0.2*2+0.6*2=8.60m) |  |  |  | area
| base raft dia. 8.6m | Cum | 0 | 1 | 58.0586 |  | 0.2
| release for hold area (dia. 5.2m) | Cum | 1 | 1 | 21.2264 |  | 0.2 | 4.25 |  | area
| R.C.C. for Sump in waterbody (750x750x850) inner size | Cum | 2 | 2 | 0.75 | 0.2 | 0.85 | 0.51
|  | Cum | 2 | 2 | 1.15 | 0.2 | 0.85 | 0.78
R.C.C. for Filter Pit in waterbody (1000x1000x1000) inner size
| R.C.C. for Wall | Cum | 1 | 2 | 1 | 0.2 | 1 | 0.4
|  | Cum | 1 | 2 | 1.4 | 0.2 | 1 | 0.56
| Base footing of pit | Cum | 1 | 1 | 1.4 | 1.4 | 0.2 | 0.39
0
| UP TO PREVIOUS BILL | Cum | [6 empty] | 28.95
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
28.95
2 | Reinforcement for R.C.C. works including straightening, cutting , bending, placing in position and binding all complete. Cold twisted bars.
| Reinforcement Steel | MT | 1 |  | 2.12 |  |  | 2.12 |  | RA-3
| As per attached BBS | MT | 1 |  | 1.1937 |  |  | 1.19
| UP TO PREVIOUS BILL | MT | [6 empty] | 3.31
| As per attached BBS | MT
| THIS BILL TOTAL → | MT | [6 empty] | 0
3.31
3 | Providing and laying in position cement concrete of specified grade, 1:4:8 (1 Cement: 4 coarse sand: 8 graded stone aggregate 40mm nominal size)
P.C.C. P/L (1:4:8)
Cum
| P.C.C. P/L for Raised Area | Cum | 1 | 1 | 67.038 | 0.61 | 0.15 | 6.13
| Brick work for steps | Cum | 1 | 1 | 1.453 | 0.7 | 0.1 | 0.1
|  | Cum | 1 | 1 | 1.304 | 0.7 | 0.1 | 0.09
|  | Cum | 1 | 1 | 1.2 | 0.7 | 0.1 | 0.08
|  | Cum | 1 | 1 | 1.252 | 0.7 | 0.1 | 0.09
|  | Cum |  |  | area
| P.C.C. for Raised Area Top Lvl. +0.36m | Cum | 1 | 1 | 152.084 |  | 0.075 | 11.41
Cum
| P.C.C. P/L for Rectangle Seat | Cum | 24 | 1 | 1.96 | 0.645 | 0.15 | 4.55
|  | Cum |  |  | area
| P.C.C. P/L for Circular Seat (dia. 1.0m), dia.1.16m p.c.c. | Cum | 7 | 1 | 1.0563 |  | 0.15 | 1.11
| P.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (18/F), Dia. 3.7m | Cum | 1 | 1 | 11.618 | 0.61 | 0.15 | 1.06
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.61 | 0.15 | 0.78
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 8.478 | 0.61 | 0.15 | 0.78
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
Cum
| at Grid (8/C-D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
| at Grid (5-6/D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
| at Grid (4-5/E), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
| at Grid (3-4/F), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
Cum
| P.C.C. P/L for Half Curved Seat (drg. No. 5128-16-101) | Cum
| Curved Seat seat at grid (20/F) | Cum | 1 | 1 | 8.215 | 0.61 | 0.15 | 0.75
| Curved Seat seat at grid (12/F) | Cum | 1 | 1 | 2.343 | 0.61 | 0.15 | 0.21
| Curved Seat seat at grid (11/F-G) | Cum | 1 | 1 | 5.143 | 0.61 | 0.15 | 0.47
| P.C.C. P/L for Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For P.C.C. =7+0.2*2+0.6*2+0.2*2=9.0m) | Cum |  |  | area
|  | Cum | 1 | 1 | 63.585 |  | 0.1 | 6.36
1 | P.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101)
Cum
| at Grid (8/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (5-6/D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (4-5/E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (3-4/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
Cum
Qty. Revise due to canculation correction (R.A.3rd)
| P.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (18/F), Dia. 3.7m | Cum | 1 | 1 | 11.618 | 0.61 | 0.15 | 1.06
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.61 | 0.15 | 0.78
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 8.478 | 0.61 | 0.15 | 0.78
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.15 | 0.86
Cum
| P.C.C. P/L for Half Curved Seat (drg. No. 5128-16-101) | Cum
| Curved Seat seat at grid (20/F) | Cum | 1 | 1 | 8.215 | 0.76 | 0.15 | 0.94
| Curved Seat seat at grid (12/F) | Cum | 1 | 1 | 2.343 | 0.76 | 0.15 | 0.27
| Curved Seat seat at grid (11/F-G) | Cum | 1 | 1 | 5.143 | 0.76 | 0.15 | 0.59
deduction qty. for revision (clamed in R.A.3rd)
| P.C.C. P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (20/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (18/F), Dia. 3.7m | Cum | -1 | 1 | 11.618 | 0.61 | 0.15 | -1.06
| at Grid (16-17/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (18/C), Dia. 3.0m (half) | Cum | -1 | 1 | 8.566 | 0.61 | 0.15 | -0.78
| at Grid (15/C-D), Dia. 2.7m | Cum | -1 | 1 | 8.478 | 0.61 | 0.15 | -0.78
| at Grid (15/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (14-15/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (13/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (12-13/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (10-11/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (10-11/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (9/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
| at Grid (9/E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.15 | -0.86
P.C.C. P/L for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (20/F) | Cum | -1 | 1 | 8.215 | 0.61 | 0.15 | -0.75
| Curved Seat seat at grid (12/F) | Cum | -1 | 1 | 2.343 | 0.61 | 0.15 | -0.21
| Curved Seat seat at grid (11/F-G) | Cum | -1 | 1 | 5.143 | 0.61 | 0.15 | -0.47
2 | P.C.C. P/L for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (10/C-D) | Cum | 1 | 1 | 4.531 | 0.76 | 0.15 | 0.52
| Curved Seat seat at grid (9/C-D) | Cum | 1 | 1 | 5.284 | 0.76 | 0.15 | 0.6
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.143 | 0.76 | 0.15 | 0.36
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.121 | 0.76 | 0.15 | 0.36
3 | P.C.C. P/L for Sunken Area
P.C.C. P/L for Brick work of Sunken Area
| P.C.C. for Brick Work for Sunken Area | Cum | 1 | 1 | 28.25 | 1.039 | 0.1 | 2.94
| P.C.C. for Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 1.345 | 1.039 | 0.1 | 0.14
| P.C.C. P/L for Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 4.39 | 1.039 | 0.1 | 0.46
| P.C.C. in Floor area of sunken portion | Cum | 1 | 1 | 46.524 |  | 0.1 | 4.65 |  | Area
4 | P.C.C. P/L in Girl's hostel Floor for Stone Fixing
| Total Area of Floor | Cum | 1 | 1 | 1577.556 |  | 0.075 | 118.32 |  | Area
deduct Green Area
| dia. 3.0m | Cum | -1 | 15 | 7.065 |  | 0.075 | -7.95 |  | Area
| dia. 3.7m | Cum | -1 | 1 | 10.7467 |  | 0.075 | -0.81 |  | Area
| dia. 2.7m | Cum | -1 | 1 | 5.7227 |  | 0.075 | -0.43 |  | Area
| dia. 3.0m half | Cum | -1 | 1 | 5.0168 |  | 0.075 | -0.38 |  | Area
| deduct Raise Area | Cum | -1 | 1 | 152.0847 |  | 0.075 | -11.41 |  | Area
| deduct Waterbody | Cum | -1 | 1 | 50.2655 |  | 0.075 | -3.77 |  | Area
| deduct sunken area | Cum | -1 | 1 | 66.9707 |  | 0.075 | -5.02 |  | Area
| deduct R.C.C. wall | Cum | -1 | 6 | 4.175 | 0.45 | 0.075 | -0.85
| deduct Rec. Seat | Cum | -1 | 24 | 1.845 | 0.345 | 0.075 | -1.15
| deduct round seat dia. 0.83m | Cum | -1 | 7 | 0.581 |  | 0.075 | -0.31 |  | Area
5 | P.C.C. P/L for Sump or Filter pit for Waterbody
| Sump (750x750x850), base | Cum | 1 | 1 | 1.38 | 1.33 | 0.1 | 0.18
| Filter pit (1000x1000x1000) base | Cum | 1 | 1 | 1.515 | 1.63 | 0.1 | 0.25
| P.C.C. P/L at Waterbody for covering of PVC pipe of waterbody (dia.=7.0m) | Cum | 1 | 1 | 38.465 |  | 0.2 | 7.69
| UP TO PREVIOUS BILL | Cum | [6 empty] | 151.63
Cum
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
151.63
4 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation, plinth, superstructure above plinth level up to floor V level in all shapes & sizes with cement mortar 1:4 (1 cement : 4 course sand)
| Brick Work for Waterbody | Cum
| Brick Work outer side of Waterbody | Cum | 1 | 1 | 23.97 | 0.23 | 0.545 | 3
Cum
| Brick Work P/L for Raised Area | Cum | 1 | 1 | 67.038 | 0.46 | 0.3 | 9.25
|  | Cum | 1 | 1 | 67.038 | 0.345 | 0.3 | 6.94
|  | Cum | 1 | 1 | 67.038 | 0.23 | 0.14 | 2.16
| Brick work for steps | Cum | 1 | 1 | 1.399 | 0.6 | 0.44 | 0.37
|  | Cum | 1 | 1 | 1.711 | 0.3 | 0.15 | 0.08
Cum
|  | Cum | 1 | 1 | 1.319 | 0.6 | 0.44 | 0.35
|  | Cum | 1 | 1 | 1.594 | 0.3 | 0.15 | 0.07
Cum
|  | Cum | 1 | 1 | 1.246 | 0.6 | 0.44 | 0.33
|  | Cum | 1 | 1 | 1.2 | 0.3 | 0.15 | 0.05
Cum
|  | Cum | 1 | 1 | 1.25 | 0.6 | 0.44 | 0.33
|  | Cum | 1 | 1 | 1.311 | 0.3 | 0.15 | 0.06
|  | Cum | [9 empty] | 2
| Brick Work P/L for Rectangle Seat | Cum | 24 | 1 | 1.96 | 0.345 | 0.56 | 9.09 |  |  |  | 0.445
|  | Cum | 24 | 1 | 1.96 | 0.46 | 0.29 | 6.28 |  |  |  | 3.1416
|  | Cum | [9 empty] | 2.796 | 0.62211
| Brick Work P/L for Circular Seat (dia. 1.0m) | Cum | 7 | 1 | 2.231 | 0.23 | 0.75 | 2.69
Cum
| Brick Work P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (18/F), Dia. 3.7m | Cum | 1 | 1 | 11.618 | 0.46 | 0.3 | 1.6
|  | Cum | 1 | 1 | 11.618 | 0.345 | 0.3 | 1.2
|  | Cum | 1 | 1 | 11.618 | 0.23 | 0.19 | 0.51
Cum
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.46 | 0.3 | 1.18
|  | Cum | 1 | 1 | 8.566 | 0.345 | 0.3 | 0.89
|  | Cum | 1 | 1 | 8.566 | 0.23 | 0.19 | 0.37
Cum
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 8.478 | 0.46 | 0.3 | 1.17
|  | Cum | 1 | 1 | 8.478 | 0.345 | 0.3 | 0.88
|  | Cum | 1 | 1 | 8.478 | 0.23 | 0.19 | 0.37
Cum
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.46 | 0.3 | 1.3
|  | Cum | 1 | 1 | 9.42 | 0.345 | 0.3 | 0.97
|  | Cum | 1 | 1 | 9.42 | 0.23 | 0.19 | 0.41
Cum
| at Grid (8/C-D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| at Grid (5-6/D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| at Grid (4-5/E), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| at Grid (3-4/F), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.46 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.345 | 0.3
|  | Cum | 0 | 1 | 9.42 | 0.23 | 0.19
Cum
| Brick Work P/L for Half Curved Seat (drg. No. 5128-16-101) | Cum
| Curved Seat seat at grid (20/F) | Cum | 1 | 1 | 8.215 | 0.46 | 0.3 | 1.13
|  | Cum | 1 | 1 | 8.215 | 0.345 | 0.3 | 0.85
|  | Cum | 1 | 1 | 8.215 | 0.23 | 0.59 | 1.11
Cum
| Curved Seat seat at grid (12/F) | Cum | 1 | 1 | 1.243 | 0.46 | 0.3 | 0.17
|  | Cum | 1 | 1 | 1.243 | 0.345 | 0.3 | 0.13
|  | Cum | 1 | 1 | 1.243 | 0.23 | 0.59 | 0.17
Cum
| Curved Seat seat at grid (11/F-G) | Cum | 1 | 1 | 5.143 | 0.46 | 0.3 | 0.71
|  | Cum | 1 | 1 | 5.143 | 0.345 | 0.3 | 0.53
|  | Cum | 1 | 1 | 5.143 | 0.23 | 0.59 | 0.7
1 | Brick Work P/L for Green Portion (Circular) (drg. No. 5128-16-101)
| at Grid (8/C-D), Dia. 3.0m (for Brick work 3.230m) | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (5-6/D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (4-5/E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (3-4/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
2 | Brick Work P/L for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (10/C-D) | Cum | 1 | 1 | 4.531 | 0.46 | 0.3 | 0.63
|  | Cum | 1 | 1 | 4.531 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.531 | 0.23 | 0.59 | 0.61
| Curved Seat seat at grid (9/C-D) | Cum | 1 | 1 | 5.284 | 0.46 | 0.3 | 0.73
|  | Cum | 1 | 1 | 5.284 | 0.345 | 0.3 | 0.55
|  | Cum | 1 | 1 | 5.284 | 0.23 | 0.59 | 0.72
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.143 | 0.46 | 0.3 | 0.43
|  | Cum | 1 | 1 | 3.143 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.143 | 0.23 | 0.59 | 0.43
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.121 | 0.46 | 0.3 | 0.43
|  | Cum | 1 | 1 | 3.121 | 0.345 | 0.3 | 0.32
|  | Cum | 1 | 1 | 3.121 | 0.23 | 0.59 | 0.42
3 | Brick Work P/L for Sunken Area
| Brick Work P/L for Sunken Area | Cum | 1 | 1 | 28.335 | 0.839 | 0.6 | 14.26
| Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 1.353 | 0.305 | 0.4 | 0.17
|  | Cum | 1 | 1 | 1.353 | 0.304 | 0.55 | 0.23
|  | Cum | 1 | 1 | 1.353 | 0.23 | 0.05 | 0.02
| Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 4.459 | 0.305 | 0.4 | 0.54
|  | Cum | 1 | 1 | 4.459 | 0.304 | 0.55 | 0.75
|  | Cum | 1 | 1 | 4.459 | 0.23 | 0.05 | 0.05
Brick Work Qty. Revise for calculation correction
| Brick Work P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m, (Brick Work Dia. =3+0.115+0.115=3.23m) | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (18/F), Dia. 3.7m (Brick Work Dia. =3.7+0.115+0.115=3.93m) | Cum | 1 | 1 | 12.3402 | 0.46 | 0.3 | 1.7
|  | Cum | 1 | 1 | 12.3402 | 0.345 | 0.3 | 1.28
|  | Cum | 1 | 1 | 12.3402 | 0.23 | 0.19 | 0.54
Cum
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.46 | 0.3 | 1.18
|  | Cum | 1 | 1 | 8.566 | 0.345 | 0.3 | 0.89
|  | Cum | 1 | 1 | 8.566 | 0.23 | 0.19 | 0.37
Cum
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 9.2002 | 0.46 | 0.3 | 1.27
|  | Cum | 1 | 1 | 9.2002 | 0.345 | 0.3 | 0.95
|  | Cum | 1 | 1 | 9.2002 | 0.23 | 0.19 | 0.4
Cum
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
| deduct qty. of revised measurement(RA-3rd) for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (20/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (18/F), Dia. 3.7m | Cum | -1 | 1 | 11.618 | 0.46 | 0.3 | -1.6
|  | Cum | -1 | 1 | 11.618 | 0.345 | 0.3 | -1.2
|  | Cum | -1 | 1 | 11.618 | 0.23 | 0.19 | -0.51
Cum
| at Grid (16-17/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (18/C), Dia. 3.0m (half) | Cum | -1 | 1 | 8.566 | 0.46 | 0.3 | -1.18
|  | Cum | -1 | 1 | 8.566 | 0.345 | 0.3 | -0.89
|  | Cum | -1 | 1 | 8.566 | 0.23 | 0.19 | -0.37
Cum
| at Grid (15/C-D), Dia. 2.7m | Cum | -1 | 1 | 8.478 | 0.46 | 0.3 | -1.17
|  | Cum | -1 | 1 | 8.478 | 0.345 | 0.3 | -0.88
|  | Cum | -1 | 1 | 8.478 | 0.23 | 0.19 | -0.37
Cum
| at Grid (15/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (14-15/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (13/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (12-13/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (10-11/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (10-11/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (9/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
Cum
| at Grid (9/E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.46 | 0.3 | -1.3
|  | Cum | -1 | 1 | 9.42 | 0.345 | 0.3 | -0.97
|  | Cum | -1 | 1 | 9.42 | 0.23 | 0.19 | -0.41
4 | Brick work P/L for Sump or Filter pit for Waterbody as per direction of Engineer in Charge (outer face for wall).
| Sump (750x750x850), | Cum | 1 | 2 | 1.15 | 0.23 | 0.85 | 0.45
|  | Cum | 1 | 2 | 1.61 | 0.23 | 0.85 | 0.63
| Filter pit (1000x1000x1000) base | Cum | 1 | 2 | 1.4 | 0.23 | 0.85 | 0.55
|  | Cum | 1 | 2 | 1.86 | 0.23 | 0.85 | 0.73
| UP TO PREVIOUS BILL | Cum | [6 empty] | 122.93
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
122.93
5 | Providing & Laying gunited sprayed concrete (40mm thk, minimum) in Waterbody areas. Consisting of mix 1:4 (1 cement : 4 coarse sand) over Chicken Wire Mesh of approved weight per sq.m. using appropriate: a) Cleaning the surface where gunited concrete is to be applied. b) Applying sprayed concrete. d) Finishing the surface with trowel to achieve smooth finish.
Gunited Sprayed waterproofing for Waterbody
| for Waterbody as per drg. No.(Inner dia. 7.0m), dia. |  |  |  | area
| base raft dia. 7.0m | Sqm | 1 | 1 | 38.465 |  |  | 38.47 |  | Area
for Sump in Waterbody
| Sump inner size(750x750x850) | Sqm | 2 | 2 | 0.75 |  | 0.85 | 2.55
|  | Sqm | 2 | 2 | 1.3 |  | 0.85 | 4.42
| for Vertical Wall (dia.=20.12m) | Sqm | 1 | 1 | 21.9911 |  | 0.8 | 17.59
| Filter Pit (1000x1000x1000) | Sqm | 1 | 1 | 1 | 1 |  | 1
|  | Sqm | 1 | 4 | 1 |  | 1 | 4
a | Gunited Sprayed waterproofing for Waterbody
| for Waterbody as per drg. No.(Inner dia. 7.0m), dia. |  |  |  | area
| base raft dia. 7.0m | Sqm | 1 | 1 | 38.465 |  |  | 38.47
for Sump in Waterbody
| Sump inner size(750x750x850) | Sqm | 2 | 2 | 0.75 |  | 0.85 | 2.55
|  | Sqm | 2 | 2 | 1.15 |  | 0.85 | 3.91
| for Vertical Wall (dia.=7.0m) | Sqm | 1 | 1 | 21.98 |  | 0.8 | 17.58
| Filter Pit (1000x1000x1000) | Sqm | 1 | 1 | 1 | 1 |  | 1
|  | Sqm | 1 | 4 | 1 |  | 1 | 4
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 135.54
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
135.54
1.1 | Providing & Fixing 40mm Natural Finish Red Agra Sandstone (Base Rate : 550) machine cut of required size, approved shade, colour & Texture laid over 20mm thick base cement mortar 1:4 (1cement : 4 coarse sand), Joints treated with white cement, mixed with matching pigment, epoxy touch ups etc. complete at all levels.
| Agra Red Sandstone in Floor G.Hostel | Sqm | 1 | 1 | 44.839 | 24.3 |  | 1089.59
deduct White marble qty.
| White Marble in circle (2-3/C-D) (dia. 4.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (4-5/C-D) (dia. 4.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (3-4/D) (dia. 2.4m) | Sqm | -1 | 1 | 4.5239 |  |  | -4.52 |  | Area
| White Marble in circle (6/C) (r = 2.15m) half | Sqm | -1 | 1 | 10.511 |  |  | -10.51 |  | Area
| White Marble in circle (6/C-D) (r = 1.0m) | Sqm | -1 | 1 | 3.1416 |  |  | -3.14 |  | Area
| White Marble in circle (2-3/D-E) (r = 2.70m) | Sqm | -1 | 1 | 22.9022 |  |  | -22.9 |  | Area
| White Marble in circle (4/D-E) (r = 1.10m) | Sqm | -1 | 1 | 3.8013 |  |  | -3.8 |  | Area
| White Marble in circle (3-4/E) (r = 0.750m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77 |  | Area
| White Marble in circle (5-6/D-E) (r = 0.750m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77 |  | Area
| White Marble in circle (2-3/E-F) (r = 1.9m) | Sqm | -1 | 1 | 11.3411 |  |  | -11.34 |  | Area
| White Marble in circle (1/E-F) (r = 1.2m) | Sqm | -1 | 1 | 4.5239 |  |  | -4.52 |  | Area
| White Marble in circle (1/E-F) (r = 1.6m) | Sqm | -1 | 1 | 8.0425 |  |  | -8.04 |  | Area
| White Marble in circle (1'/E-F) (r = 1.3m) | Sqm | -1 | 1 | 5.3093 |  |  | -5.31 |  | Area
| White Marble in circle (1'/F-G) (r = 1.5m) | Sqm | -1 | 1 | 7.0686 |  |  | -7.07 |  | Area
| White Marble in circle (2/F-G) (r = 1.35m) | Sqm | -1 | 1 | 5.7256 |  |  | -5.73 |  | Area
| White Marble in circle (5-6/D-E) (r = 2.5m) | Sqm | -1 | 1 | 19.635 |  |  | -19.63 |  | Area
| White Marble in circle (4-5/E) (r = 2.85m) | Sqm | -1 | 1 | 25.5176 |  |  | -25.52 |  | Area
| White Marble in circle (3/F) (r = 2.75m) | Sqm | -1 | 1 | 23.7583 |  |  | -23.76 |  | Area
| White Marble in circle (5/F-G) (r = 0.85m) | Sqm | -1 | 1 | 2.2698 |  |  | -2.27 |  | Area
| White Marble in circle (5/F-G) (r = 0.5m) | Sqm | -1 | 1 | 0.7854 |  |  | -0.79 |  | Area
| White Marble in circle (8/C) (r = 1.5m) half | Sqm | -1 | 1 | 4.1203 |  |  | -4.12 |  | Area
| White Marble in circle (8/C-D) (r = 2.4m) | Sqm | -1 | 1 | 18.0956 |  |  | -18.1 |  | Area
| White Marble in circle (7/D-E) (r = 0.9m) | Sqm | -1 | 1 | 2.5447 |  |  | -2.54 |  | Area
| White Marble in circle (8/D-E) (r = 1.45m) | Sqm | -1 | 1 | 6.6052 |  |  | -6.61 |  | Area
| White Marble in circle (6-7-8/E) (r = 2.3m) | Sqm | -1 | 1 | 16.619 |  |  | -16.62 |  | Area
| White Marble in circle (8-9/C-D) (r = 0.75m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77 |  | Area
| White Marble in circle (9/C) (r = 0.75m) half | Sqm | -1 | 1 | 1.3031 |  |  | -1.3 |  | Area
| White Marble in circle (9/C-D) (r = 2.55m) | Sqm | -1 | 1 | 20.4282 |  |  | -20.43 |  | Area
| White Marble in circle (8-9/D) (r = 2.55m) | Sqm | -1 | 1 | 20.4282 |  |  | -20.43 |  | Area
| White Marble in circle (8-9/D) (r = 1.2m) | Sqm | -1 | 1 | 4.5239 |  |  | -4.52 |  | Area
| White Marble in circle (9/D-E) (r = 1.2m) | Sqm | -1 | 1 | 4.5239 |  |  | -4.52 |  | Area
| White Marble in circle (10/D) (r = 2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (9/E) (r = 2.4m) | Sqm | -1 | 1 | 18.0956 |  |  | -18.1 |  | Area
| White Marble in circle (9/E-F) (r = 1.5m) | Sqm | -1 | 1 | 7.0686 |  |  | -7.07 |  | Area
| White Marble in circle (10/C) (r = 2.0m) half | Sqm | -1 | 1 | 5.3739 |  |  | -5.37 |  | Area
| White Marble in circle (10/C-D) (r = 2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (10/E) (r = 3.0m) | Sqm | -1 | 1 | 28.2743 |  |  | -28.27 |  | Area
| White Marble in circle (10/F) (r = 3.0m) | Sqm | -1 | 1 | 21.2372 |  |  | -21.24 |  | Area
| White Marble in circle (11/C) (r = 2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (12/D) (r = 2.10m) | Sqm | -1 | 1 | 13.8544 |  |  | -13.85 |  | Area
| White Marble in circle (11/F) (r = 2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (11/F-G) (r = 2.70m) | Sqm | -1 | 1 | 22.9022 |  |  | -22.9 |  | Area
| White Marble in circle (12/F) (r = 1.6m) | Sqm | -1 | 1 | 8.0425 |  |  | -8.04 |  | Area
| White Marble in circle (12/F-G) (r = 0.6m) | Sqm | -1 | 1 | 1.131 |  |  | -1.13 |  | Area
| White Marble in circle (10-11/G) (r = 1.250m) half | Sqm | -1 | 1 | 3.6248 |  |  | -3.62 |  | Area
| White Marble in circle (12-13/C-D) (r =2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (14/C-D) (r =1.25m) | Sqm | -1 | 1 | 4.9087 |  |  | -4.91 |  | Area
| White Marble in circle (14/D) (r =2.7m) | Sqm | -1 | 1 | 22.9022 |  |  | -22.9 |  | Area
| White Marble in circle (14/D-E) (r =0.75m) | Sqm | -1 | 2 | 1.7671 |  |  | -3.53 |  | Area
| White Marble in circle (14/F) (r =3.0m) | Sqm | -1 | 1 | 28.2743 |  |  | -28.27 |  | Area
| White Marble in circle (14/F-G) (r =2.25m) | Sqm | -1 | 1 | 15.9043 |  |  | -15.9 |  | Area
| White Marble in circle (14-15/C) (r =1.15m) half | Sqm | -1 | 1 | 3.954 |  |  | -3.95 |  | Area
| White Marble in circle (15-16/C) (r =1.5m) half | Sqm | -1 | 1 | 2.5354 |  |  | -2.54 |  | Area
| White Marble in circle (16-17/C-D) (r =1.0m) | Sqm | -1 | 1 | 3.1416 |  |  | -3.14 |  | Area
| White Marble in circle (15-16/D) (r =2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57 |  | Area
| White Marble in circle (15-16/E) (r =2.50m) | Sqm | -1 | 1 | 19.635 |  |  | -19.63 |  | Area
| White Marble in circle (15-16/E) (r =1.30m) | Sqm | -1 | 1 | 5.3093 |  |  | -5.31 |  | Area
| White Marble in circle (16/F) (r =2.40m) | Sqm | -1 | 1 | 18.0956 |  |  | -18.1 |  | Area
| White Marble in circle (15/F) (r =0.75m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77 |  | Area
| White Marble in circle (16/F-G) (r =1.25m) | Sqm | -1 | 1 | 4.9087 |  |  | -4.91 |  | Area
| White Marble in circle (15-16/G) (r =2.5m)half | Sqm | -1 | 1 | 8.7442 |  |  | -8.74 |  | Area
| deduct sunken Area | Sqm | -1 | 1 | 66.9707 |  |  | -66.97
| deduct Waterbody Area | Sqm | -1 | 1 | 50.2655 |  |  | -50.27
| deduct green Planter Area Dia. 3.0m (11/D-E), (13/F-G), (15-16/C-D) | Sqm | -1 | 3 | 7.065 |  |  | -21.2
| deduct R.C.C. Wall | Sqm | -1 | 6 | 4.175 | 0.45 |  | -11.27
| Agra Red Sandstone in Floor G.Hostel (17-25/C-G) | Sqm | 1 | 1 | 20.08 | 24.3 |  | 487.94
| Agra Red Sandstone in Floor G.Hostel (13-16/A-C) entrance | Sqm | 1 | 1 | 84.261 |  |  | 84.26
deduct White marble cobbles at circle in floor
| White Marble in circle (18-19/C) (r= 2.50m) half | Sqm | -1 | 1 | 12.3495 |  |  | -12.35
| White Marble in circle (20/C) (r=1.750m) half | Sqm | -1 | 1 | 5.079 |  |  | -5.08
| White Marble in circle (18-19/G) (r=2.750m) half | Sqm | -1 | 1 | 12.3965 |  |  | -12.4
| White Marble in circle (20/G) (r=2.230m) half | Sqm | -1 | 1 | 13.5729 |  |  | -13.57
| White Marble in circle (21-22/F-G) (r=1.50m) half | Sqm | -1 | 1 | 7.0686 |  |  | -7.07
| White Marble in circle (21/F-G) (r=0.750m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77
| White Marble in circle (22-23/F) (r=2.250m) | Sqm | -1 | 1 | 15.9043 |  |  | -15.9
| White Marble in circle (24/F-G) (r=1.850m) | Sqm | -1 | 1 | 10.7521 |  |  | -10.75
| White Marble in circle (24-25/F-G) (r=1.30m) | Sqm | -1 | 1 | 5.3093 |  |  | -5.31
| White Marble in circle (20/F) (r=3.0m) | Sqm | -1 | 1 | 28.2743 |  |  | -28.27
| White Marble in circle (24'/E-F) (r=1.80m) | Sqm | -1 | 1 | 10.7521 |  |  | -10.75
| White Marble in circle (24'-25/E-F) (r=1.30m) | Sqm | -1 | 1 | 5.3093 |  |  | -5.31
| White Marble in circle (24'/D-E) (r=2.0m) | Sqm | -1 | 1 | 12.5664 |  |  | -12.57
| White Marble in circle (24'/C-D) (r=2.0m) | Sqm | -1 | 1 | 15.9043 |  |  | -15.9
| White Marble in circle (14/C) (r=1.150m) | Sqm | -1 | 1 | 4.1548 |  |  | -4.15
| White Marble in circle (15-16/C) (r=1.475m) | Sqm | -1 | 1 | 6.684 |  |  | -6.68
| White Marble in circle (14-15/B-C) (r=0.750m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77
| White Marble in circle (15-16/B') (r=1.50m) | Sqm | -1 | 1 | 6.8241 |  |  | -6.82
| White Marble in circle (14/B-B') (r=2.10m) | Sqm | -1 | 1 | 13.8544 |  |  | -13.85
| White Marble in circle (15/B) (r=1.0m) | Sqm | -1 | 1 | 3.1416 |  |  | -3.14
| White Marble in circle (14-15/A-B) (r=0.75m) | Sqm | -1 | 1 | 1.7671 |  |  | -1.77
| White Marble in circle (14/A'-B) (r=1.0m) | Sqm | -1 | 1 | 3.1416 |  |  | -3.14
| White Marble in circle (14-15/A'-B) (r=1.150m) | Sqm | -1 | 1 | 4.1548 |  |  | -4.15
DEDUCT
| SEAT | Sqm | -1 | 12 | 1.8 | 0.5 |  | -10.8
| CIRCULAR PART | Sqm | -1 | 1 | 9.425 |  |  | -9.43
|  | Sqm | -1 | 1 | 17.349 |  |  | -17.35
|  | Sqm | -1 | 1 | 10.752 |  |  | -10.75
| SHEAR WALL | Sqm | -1 | 3 | 4.175 | 0.45 |  | -5.64
| DEDUCT RISED PART(AREA) | Sqm | -1 | 1 | 152.0847 |  |  | -152.08
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 466.46
Sqm
Revise due to claculation Correction
| SEAT | Sqm | 1 | 12 | 1.8 | 0.5 |  | 10.8
| CIRCULAR PART | Sqm | 1 | 0 | 9.425 |  |  | 0
|  | Sqm | 1 | 0 | 17.349 |  |  | 0
|  | Sqm | 1 | 0 | 10.752 |  |  | 0
| SEAT | Sqm | -1 | 12 | 1.71 | 0.41 |  | -8.41
| THIS BILL TOTAL → | Sqm | [6 empty] | 2.39 | 6th RA
468.85
1.2 | Providing & Fixing 40/20mm 100mm x 10mm Polished Finish White Marble Cobbles (Base Rate : 1500) Pre-polished, machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls.
| White Marble in circle (2-3/C-D) (dia. 4.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| deduct seat portion | Sqm | -1 | 1 | 0.6185 | 0.345 |  | -0.21
| White Marble in circle (4-5/C-D) (dia. 4.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| White Marble in circle (3-4/D) (dia. 2.4m) | Sqm | 1 | 1 | 4.5239 |  |  | 4.52 |  | Area
| White Marble in circle (6/C) (r = 2.15m) half | Sqm | 1 | 1 | 10.511 |  |  | 10.51 |  | Area
| White Marble in circle (6/C-D) (r = 1.0m) | Sqm | 1 | 1 | 3.1416 |  |  | 3.14 |  | Area
| White Marble in circle (2-3/D-E) (r = 2.70m) | Sqm | 1 | 1 | 22.9022 |  |  | 22.9 |  | Area
| deduct rec. seat | Sqm | -1 | 1 | 0.855 | 0.345 |  | -0.29
| White Marble in circle (4/D-E) (r = 1.10m) | Sqm | 1 | 1 | 3.8013 |  |  | 3.8 |  | Area
| White Marble in circle (3-4/E) (r = 0.750m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77 |  | Area
| White Marble in circle (5-6/D-E) (r = 0.750m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77 |  | Area
| White Marble in circle (2-3/E-F) (r = 1.9m) | Sqm | 1 | 1 | 11.3411 |  |  | 11.34 |  | Area
| deduct rec. seat | Sqm | -1 | 1 | 0.342 | 0.345 |  | -0.12
| White Marble in circle (1/E-F) (r = 1.2m) | Sqm | 1 | 1 | 4.5239 |  |  | 4.52 |  | Area
| deduct rec. seat | Sqm | -1 | 1 | 1.696 | 0.345 |  | -0.59
| White Marble in circle (1/E-F) (r = 1.6m) | Sqm | 1 | 1 | 8.0425 |  |  | 8.04 |  | Area
| deduct rec. seat | Sqm | -1 | 1 | 1.845 | 0.345 |  | -0.64
| White Marble in circle (1'/E-F) (r = 1.3m) | Sqm | 1 | 1 | 5.3093 |  |  | 5.31 |  | Area
| deduct rec. seat | Sqm | -1 | 1 | 1.6185 | 0.345 |  | -0.56
| White Marble in circle (1'/F-G) (r = 1.5m) | Sqm | 1 | 1 | 7.0686 |  |  | 7.07 |  | Area
| deduct rec. seat | Sqm | -1 | 1 | 1.324 | 0.345 |  | -0.46
| deduct rec. seat | Sqm | -1 | 1 | 1.102 | 0.345 |  | -0.38
| White Marble in circle (2/F-G) (r = 1.35m) | Sqm | 1 | 1 | 5.7256 |  |  | 5.73 |  | Area
| deduct round seat (dia. 0.83m) | Sqm | -1 | 1 | 0.54079 |  |  | -0.54 |  | Area
| White Marble in circle (5-6/D-E) (r = 2.5m) | Sqm | 1 | 1 | 19.635 |  |  | 19.63 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| deduct half curve seat | Sqm | -1 | 2 | 3.143 | 0.23 |  | -1.45
| White Marble in circle (4-5/E) (r = 2.85m) | Sqm | 1 | 1 | 25.5176 |  |  | 25.52 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (3/F) (r = 2.75m) | Sqm | 1 | 1 | 23.7583 |  |  | 23.76 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (5/F-G) (r = 0.85m) | Sqm | 1 | 1 | 2.2698 |  |  | 2.27 |  | Area
| White Marble in circle (5/F-G) (r = 0.5m) | Sqm | 1 | 1 | 0.7854 |  |  | 0.79 |  | Area
| White Marble in circle (8/C) (r = 1.5m) half | Sqm | 1 | 1 | 4.1203 |  |  | 4.12 |  | Area
| White Marble in circle (8/C-D) (r = 2.4m) | Sqm | 1 | 1 | 18.0956 |  |  | 18.1 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (7/D-E) (r = 0.9m) | Sqm | 1 | 1 | 2.5447 |  |  | 2.54 |  | Area
| White Marble in circle (8/D-E) (r = 1.45m) | Sqm | 1 | 1 | 6.6052 |  |  | 6.61 |  | Area
| White Marble in circle (6-7-8/E) (r = 2.3m) | Sqm | 1 | 1 | 16.619 |  |  | 16.62 |  | Area
| White Marble in circle (8-9/C-D) (r = 0.75m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77 |  | Area
| White Marble in circle (9/C) (r = 0.75m) half | Sqm | 1 | 1 | 1.3031 |  |  | 1.3 |  | Area
| White Marble in circle (9/C-D) (r = 2.55m) | Sqm | 1 | 1 | 20.4282 |  |  | 20.43 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| deduct half curve seat | Sqm | -1 | 1 | 5.25 | 0.23 |  | -1.21
| White Marble in circle (8-9/D) (r = 2.55m) | Sqm | 1 | 1 | 20.4282 |  |  | 20.43 |  | Area
| White Marble in circle (8-9/D) (r = 1.2m) | Sqm | 1 | 1 | 4.5239 |  |  | 4.52 |  | Area
| White Marble in circle (9/D-E) (r = 1.2m) | Sqm | 1 | 1 | 4.5239 |  |  | 4.52 |  | Area
| White Marble in circle (10/D) (r = 2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| White Marble in circle (9/E) (r = 2.4m) | Sqm | 1 | 1 | 18.0956 |  |  | 18.1 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (9/E-F) (r = 1.5m) | Sqm | 1 | 1 | 7.0686 |  |  | 7.07 |  | Area
| White Marble in circle (10/C) (r = 2.0m) half | Sqm | 1 | 1 | 5.3739 |  |  | 5.37 |  | Area
| White Marble in circle (10/C-D) (r = 2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| deduct half curve seat | Sqm | -1 | 1 | 4.459 | 0.23 |  | -1.03
| White Marble in circle (10/E) (r = 3.0m) | Sqm | 1 | 1 | 28.2743 |  |  | 28.27 |  | Area
| White Marble in circle (10/F) (r = 3.0m) | Sqm | 1 | 1 | 21.2372 |  |  | 21.24 |  | Area
| White Marble in circle (11/C) (r = 2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| White Marble in circle (12/D) (r = 2.10m) | Sqm | 1 | 1 | 13.8544 |  |  | 13.85 |  | Area
| White Marble in circle (11/F) (r = 2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (11/F-G) (r = 2.70m) | Sqm | 1 | 1 | 22.9022 |  |  | 22.9 |  | Area
| deduct half curve seat | Sqm | -1 | 1 | 5.204 | 0.23 |  | -1.2
| White Marble in circle (12/F) (r = 1.6m) | Sqm | 1 | 1 | 8.0425 |  |  | 8.04 |  | Area
| deduct half curve seat | Sqm | -1 | 1 | 2.393 | 0.23 |  | -0.55 |  | Area
| White Marble in circle (12/F-G) (r = 0.6m) | Sqm | 1 | 1 | 1.131 |  |  | 1.13 |  | Area
| White Marble in circle (10-11/G) (r = 1.250m) half | Sqm | 1 | 1 | 3.6248 |  |  | 3.62 |  | Area
| White Marble in circle (12-13/C-D) (r =2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (14/C-D) (r =1.25m) | Sqm | 1 | 1 | 4.9087 |  |  | 4.91 |  | Area
| White Marble in circle (14/D) (r =2.7m) | Sqm | 1 | 1 | 22.9022 |  |  | 22.9 |  | Area
| deduct round seat (dia. 0.83m) | Sqm | -1 | 3 | 0.54079 |  |  | -1.62 |  | Area
| White Marble in circle (14/D-E) (r =0.75m) | Sqm | 1 | 2 | 1.7671 |  |  | 3.53 |  | Area
| White Marble in circle (14/F) (r =3.0m) | Sqm | 1 | 1 | 28.2743 |  |  | 28.27 |  | Area
| deduct round seat (dia. 0.83m) | Sqm | -1 | 3 | 0.54079 |  |  | -1.62 |  | Area
| White Marble in circle (14/F-G) (r =2.25m) | Sqm | 1 | 1 | 15.9043 |  |  | 15.9 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (14-15/C) (r =1.15m) half | Sqm | 1 | 1 | 3.954 |  |  | 3.95 |  | Area
| White Marble in circle (15-16/C) (r =1.5m) half | Sqm | 1 | 1 | 2.5354 |  |  | 2.54 |  | Area
| White Marble in circle (16-17/C-D) (r =1.0m) | Sqm | 1 | 1 | 3.1416 |  |  | 3.14 |  | Area
| White Marble in circle (15-16/D) (r =2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57 |  | Area
| White Marble in circle (15-16/E) (r =2.50m) | Sqm | 1 | 1 | 19.635 |  |  | 19.63 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (15-16/E) (r =1.30m) | Sqm | 1 | 1 | 5.3093 |  |  | 5.31 |  | Area
| White Marble in circle (16/F) (r =2.40m) | Sqm | 1 | 1 | 18.0956 |  |  | 18.1 |  | Area
| deduct green Planter (dia. 3.0m) | Sqm | -1 | 1 | 7.065 |  |  | -7.07 |  | Area
| White Marble in circle (15/F) (r =0.75m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77 |  | Area
| White Marble in circle (16/F-G) (r =1.25m) | Sqm | 1 | 1 | 4.9087 |  |  | 4.91 |  | Area
| White Marble in circle (15-16/G) (r =2.5m)half | Sqm | 1 | 1 | 8.7442 |  |  | 8.74 |  | Area
| deduct 600mm dia. Circle stone qty. | Sqm | -1 | 1 | 17.25 |  |  | -17.25
a | White marble cobbles at circle in floor
| White Marble in circle (18-19/C) (r= 2.50m) half | Sqm | 1 | 1 | 12.3495 |  |  | 12.35
| White Marble in circle (20/C) (r=1.750m) half | Sqm | 1 | 1 | 5.079 |  |  | 5.08
| White Marble in circle (18-19/G) (r=2.750m) half | Sqm | 1 | 1 | 12.3965 |  |  | 12.4
| White Marble in circle (20/G) (r=2.230m) half | Sqm | 1 | 1 | 13.5729 |  |  | 13.57
| White Marble in circle (21-22/F-G) (r=1.50m) half | Sqm | 1 | 1 | 7.0686 |  |  | 7.07
| White Marble in circle (21/F-G) (r=0.750m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77
| White Marble in circle (22-23/F) (r=2.250m) | Sqm | 1 | 1 | 15.9043 |  |  | 15.9
| White Marble in circle (24/F-G) (r=1.850m) | Sqm | 1 | 1 | 10.7521 |  |  | 10.75
| White Marble in circle (24-25/F-G) (r=1.30m) | Sqm | 1 | 1 | 5.3093 |  |  | 5.31
| White Marble in circle (20/F) (r=3.0m) | Sqm | 1 | 1 | 28.2743 |  |  | 28.27
| White Marble in circle (24'/E-F) (r=1.80m) | Sqm | 1 | 1 | 10.7521 |  |  | 10.75
| White Marble in circle (24'-25/E-F) (r=1.30m) | Sqm | 1 | 1 | 5.3093 |  |  | 5.31
| White Marble in circle (24'/D-E) (r=2.0m) | Sqm | 1 | 1 | 12.5664 |  |  | 12.57
| White Marble in circle (24'/C-D) (r=2.0m) | Sqm | 1 | 1 | 15.9043 |  |  | 15.9
| White Marble in circle (14/C) (r=1.150m) | Sqm | 1 | 1 | 4.1548 |  |  | 4.15
| White Marble in circle (15-16/C) (r=1.475m) | Sqm | 1 | 1 | 6.684 |  |  | 6.68
| White Marble in circle (14-15/B-C) (r=0.750m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77
| White Marble in circle (15-16/B') (r=1.50m) | Sqm | 1 | 1 | 6.8241 |  |  | 6.82
| White Marble in circle (14/B-B') (r=2.10m) | Sqm | 1 | 1 | 13.8544 |  |  | 13.85
| White Marble in circle (15/B) (r=1.0m) | Sqm | 1 | 1 | 3.1416 |  |  | 3.14
| White Marble in circle (14-15/A-B) (r=0.75m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77
| White Marble in circle (14/A'-B) (r=1.0m) | Sqm | 1 | 1 | 3.1416 |  |  | 3.14
| White Marble in circle (14-15/A'-B) (r=1.150m) | Sqm | 1 | 1 | 4.1548 |  |  | 4.15
b | White Stone P/L on Sunken portion, top coping face as per direction of Engineer in Charge
| outer line area | Sqm | 1 | 1 | 67.1589 |  |  | 67.16
| deduct inner area | Sqm | -1 | 1 | 46.3412 |  |  | -46.34
| DEDUCT SEAT MERGE IN CIRCULAR PART | Sqm | -1 | 1 | 2.197 |  |  | -2.2
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 750.7
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
750.7
1.3 | Providing & Fixing 40/20mm Sawn Finish White Marble (Base Rate : 1200) machine cut of required Size, approved shade, colour & texture laid over 20 mm thk. Base cement mortar 1:4 (1cement : 4 coarse sand), joints treated with matching pigment, epoxy touch ups, etc. complete at all lvls.
| White Marble Sawn Finish on Raised Area | Sqm | 1 | 1 | 152.0847 |  |  | 152.08 |  | Area
| White Marble Sawn Finish on Sunken Area | Sqm | 1 | 1 | 46.5421 |  |  | 46.54 |  | Area
| White Marble in Circular Portion of Circle 600mm dia. | Sqm | 1 | 1 |  |  |  | 1
| White Marble in circle (2-3/C-D) (dia. 4.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (4-5/C-D) (dia. 4.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (3-4/D) (dia. 2.4m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (6/C) (r = 2.15m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (6/C-D) (r = 1.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (2-3/D-E) (r = 2.70m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (4/D-E) (r = 1.10m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (3-4/E) (r = 0.750m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (5-6/D-E) (r = 0.750m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (2-3/E-F) (r = 1.9m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (1/E-F) (r = 1.2m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (1/E-F) (r = 1.6m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (1'/E-F) (r = 1.3m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (1'/F-G) (r = 1.5m) | Sqm | 1 | 1 | 0.283 |  |  | 0.28 |  | Area
| White Marble in circle (2/F-G) (r = 1.35m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (5/F-G) (r = 0.85m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (5/F-G) (r = 0.5m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (8/C) (r = 1.5m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (7/D-E) (r = 0.9m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (8/D-E) (r = 1.45m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (6-7-8/E) (r = 2.3m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (8-9/C-D) (r = 0.75m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (9/C) (r = 0.75m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (8-9/D) (r = 2.55m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (8-9/D) (r = 1.2m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (9/D-E) (r = 1.2m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (10/D) (r = 2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (9/E-F) (r = 1.5m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (10/C) (r = 2.0m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (10/C-D) (r = 2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (10/E) (r = 3.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (10/F) (r = 3.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (11/C) (r = 2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (12/D) (r = 2.10m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (11/F-G) (r = 2.70m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (12/F) (r = 1.6m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (12/F-G) (r = 0.6m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (10-11/G) (r = 1.250m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (14/C-D) (r =1.25m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (14/D) (r =2.7m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (14/D-E) (r =0.75m) | Sqm | 1 | 2 | 1.766 |  |  | 3.53 |  | Area
| White Marble in circle (14/F) (r =3.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (14-15/C) (r =1.15m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (15-16/C) (r =1.5m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (16-17/C-D) (r =1.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (15-16/D) (r =2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (15-16/E) (r =1.30m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (15/F) (r =0.75m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (16/F-G) (r =1.25m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (15-16/G) (r =2.5m)half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | Area
| White Marble in circle (20/C) (r=1.750m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (18-19/G) (r=2.750m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (20/G) (r=2.230m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | 0.75
| White Marble in circle (21-22/F-G) (r=1.50m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | 0.75
| White Marble in circle (21/F-G) (r=0.750m) | Sqm | 1 | 1 | 0.283 |  |  | 0.28 |  | 3.1416
| White Marble in circle (22-23/F) (r=2.250m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28 |  | 1.7671
| White Marble in circle (24/F-G) (r=1.850m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24-25/F-G) (r=1.30m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'/E-F) (r=1.80m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'-25/E-F) (r=1.30m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'/D-E) (r=2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'/C-D) (r=2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/C) (r=1.150m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15-16/C) (r=1.475m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14-15/B-C) (r=0.750m) | Sqm | 1 | 1 | 0.283 |  |  | 0.28
| White Marble in circle (15-16/B') (r=1.50m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/B-B') (r=2.10m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15/B) (r=1.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14-15/A-B) (r=0.75m) | Sqm | 1 | 1 | 0.283 |  |  | 0.28
| White Marble in circle (14/A'-B) (r=1.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14-15/A'-B) (r=1.150m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
b | sunken Area Step white ,marble stone
| stair area, Tread | Sqm | 1 | 2 | 1.353 | 0.32 |  | 0.87
| riser | Sqm | 1 | 3 | 1.353 |  | 0.15 | 0.61
| stair area | Sqm | 1 | 2 | 4.459 | 0.32 |  | 2.85
| riser | Sqm | 1 | 3 | 4.459 |  | 0.15 | 2.01
c | White Marble for Rec. Seat (2000x500)
| Side Cladding | Sqm | 24 | 2 | 2 |  | 0.325 | 31.2
|  | Sqm | 24 | 2 | 1.91 |  | 0.1 | 9.17
|  | Sqm | 24 | 2 | 0.5 |  | 0.325 | 7.8
|  | Sqm | 24 | 2 | 0.41 |  | 0.1 | 1.97
| top coping (double stone) | Sqm | 24 | 2 | 0.32 | 0.5 |  | 7.68
d | White Marble for Round seat dia. 1.0m
| side cladding | Sqm | 7 | 1 | 3.14 |  | 0.335 | 7.36
|  | Sqm | 7 | 1 | 2.7946 |  | 0.1 | 1.96
| top coping (double stone as per detail/engineer in charge) | Sqm | 7 | 2 | 0.785 |  |  | 10.99
e | White Marble for curved seat
Curved Seat (20/F)
| outer cladding | Sqm | 1 | 1 | 9.425 |  | 0.41 | 3.86 |  | 265
| inner cladding | Sqm | 1 | 1 | 8.705 |  | 0.265 | 2.31
| front face | Sqm | 1 | 1 | 7.855 |  | 0.145 | 1.14
| top coping (double layer) | Sqm | 1 | 2 | 8.64 | 0.5 |  | 8.64
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (11/F-G)
| outer cladding | Sqm | 1 | 1 | 5.5 |  | 0.41 | 2.26
| inner cladding | Sqm | 1 | 1 | 5.03 |  | 0.265 | 1.33
| front face | Sqm | 1 | 1 | 4.48 |  | 0.145 | 0.65
| top coping (double layer) | Sqm | 1 | 2 | 4.99 | 0.5 |  | 4.99
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (12/F)
| outer cladding | Sqm | 1 | 1 | 2.63 |  | 0.41 | 1.08
| inner cladding | Sqm | 1 | 1 | 2.255 |  | 0.265 | 0.6
| front face | Sqm | 1 | 1 | 1.81 |  | 0.145 | 0.26
| top coping (double layer) | Sqm | 1 | 2 | 2.22 | 0.5 |  | 2.22
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (10/C-D)
| outer cladding | Sqm | 1 | 1 | 4.81 |  | 0.41 | 1.97
| inner cladding | Sqm | 1 | 1 | 4.255 |  | 0.265 | 1.13
| front face | Sqm | 1 | 1 | 3.605 |  | 0.145 | 0.52
| top coping (double layer) | Sqm | 1 | 2 | 4.205 | 0.5 |  | 4.21
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (9/C-D)
| outer cladding | Sqm | 1 | 1 | 5.535 |  | 0.41 | 2.27
| inner cladding | Sqm | 1 | 1 | 5.035 |  | 0.265 | 1.33
| front face | Sqm | 1 | 1 | 4.45 |  | 0.145 | 0.65
| top coping (double layer) | Sqm | 1 | 2 | 4.99 | 0.5 |  | 4.99
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (4-5/D)
| outer cladding | Sqm | 1 | 1 | 3.255 |  | 0.41 | 1.33
| inner cladding | Sqm | 1 | 1 | 2.99 |  | 0.265 | 0.79
| front face | Sqm | 1 | 1 | 2.635 |  | 0.145 | 0.38
| top coping (double layer) | Sqm | 1 | 2 | 2.965 | 0.5 |  | 2.97
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (4-5/D-E)
| outer cladding | Sqm | 1 | 1 | 3.27 |  | 0.41 | 1.34
| inner cladding | Sqm | 1 | 1 | 2.97 |  | 0.265 | 0.79
| front face | Sqm | 1 | 1 | 2.615 |  | 0.145 | 0.38
| top coping (double layer) | Sqm | 1 | 2 | 2.945 | 0.5 |  | 2.95
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
f | White Marble on Coping top of Waterbody (double layer stone) as per specification
| r=4.04m | Sqm | 1 | 2 | 50.264 |  |  | 100.53
| deduct inner area (r=3.5m) | Sqm | -1 | 2 | 38.4845 |  |  | -76.97
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 390.22
Sqm
| White Marble Cladding for Raised Portion | Sqm | 1 | 1 | 67.35 |  | 0.49 | 33
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 33 | 6th RA
423.22
WATERPROOFING
STONE FINISH CATCH BASIN COVER
1.6 | Providing & Fixing in Position 40mm thk stone cover of size 600mm x 600mm as per design for catch basin fixed on Precast concrete with M.S. angle.
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
Sqm
1 | 740x740 (inner size) | Sqm | 3 | 1 | 0.89 | 0.89 |  | 2.38
2 | 750x750 (waterbody) | Sqm | 2 | 1 | 0.9 | 0.9 |  | 1.62
3 | 1000x1000 (sump) | Sqm | 1 | 1 | 1.15 | 1.15 |  | 1.32
4 | 450x450 | Sqm | 15 | 1 | 0.6 | 0.6 |  | 5.4
| THIS BILL TOTAL → | Sqm | [6 empty] | 10.72 | 6th RA
10.72
NON-SCHEDULED ITEMS
NS-01 | Up to or all kinds of soil below existing excavated level as handed over to the contractor by the Project-in-charge.
| Earth Excavation for Raised Area | Cum | 1 | 1 | 67.038 | 0.61 | 0.732 | 29.93
| Brick work for steps | Cum | 1 | 1 | 1.453 | 0.7 | 0.072 | 0.07
|  | Cum | 1 | 1 | 1.304 | 0.7 | 0.072 | 0.07
|  | Cum | 1 | 1 | 1.26 | 0.7 | 0.072 | 0.06
|  | Cum | 1 | 1 | 1.252 | 0.7 | 0.072 | 0.06
area
| Earth Excavation for Rectangle Seat | Cum | 24 | 1 | 1.96 | 0.645 | 0.162 | 4.92
area
| Earth Excavation for Circular Seat (dia. 1.0m), dia.1.16m p.c.c. | Cum | 7 | 1 | 1.0563 |  | 0.182 | 1.35
Earth Excavation for Green Portion (Circular) brick work (drg. No. 5128-16-101)
| at Grid (22-23/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (18/F), Dia. 3.7m | Cum | 1 | 1 | 11.618 | 0.61 | 0.732 | 5.19
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.61 | 0.732 | 3.82
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 8.478 | 0.61 | 0.732 | 3.79
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 9.42 | 0.61 | 0.732 | 4.21
| at Grid (8/C-D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
| at Grid (5-6/D), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
| at Grid (4-5/E), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
| at Grid (3-4/F), Dia. 3.0m | Cum | 0 | 1 | 9.42 | 0.61 | 0.15
Earth Excavation for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (20/F) | Cum | 1 | 1 | 8.215 | 0.61 | 0.732 | 3.67
| Curved Seat seat at grid (12/F) | Cum | 1 | 1 | 2.343 | 0.61 | 0.732 | 1.05
| Curved Seat seat at grid (11/F-G) | Cum | 1 | 1 | 5.143 | 0.61 | 0.732 | 2.3
| Earth Excavation for Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For P.C.C. =7+0.2*2+0.6*2+0.2*2=9.0m) |  |  |  | area
|  | Cum | 1 | 1 | 63.585 |  | 0.372 | 23.65
Earth Eaxcavation for Green Portion (Circular) (drg. No. 5128-16-101)
|  | Cum |  |  | 4.22 | 2.11
| at Grid (8/C-D), Dia. 3.0m (dia.=3+0.46+0.46+0.15+0.15=4.22m) | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23 |  | Area
| at Grid (5-6/D), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (4-5/E), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (3-4/F), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
Cum
Qty. Revise due to canculation correction (R.A.3rd)
| Earth Excavation for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (18/F), Dia. 3.7m | Cum | 1 | 1 | 11.618 |  | 0.732 | 8.5 |  | 4920
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23 |  | 2460
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 21.9697 |  | 0.732 | 16.08
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 12.0626 |  | 0.732 | 8.83
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 13.9796 |  | 0.732 | 10.23
Cum
| Earth Excavation for Half Curved Seat (drg. No. 5128-16-101) | Cum
| Curved Seat seat at grid (20/F) | Cum | 1 | 1 | 8.215 | 0.76 | 0.732 | 4.57
| Curved Seat seat at grid (12/F) | Cum | 1 | 1 | 2.343 | 0.76 | 0.732 | 1.3
| Curved Seat seat at grid (11/F-G) | Cum | 1 | 1 | 5.143 | 0.76 | 0.732 | 2.86
deduction qty. for revision (clamed in R.A.3rd)
| Earth Excavation for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (20/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (18/F), Dia. 3.7m | Cum | -1 | 1 | 11.618 | 0.61 | 0.732 | -5.19
| at Grid (16-17/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (18/C), Dia. 3.0m (half) | Cum | -1 | 1 | 8.566 | 0.61 | 0.732 | -3.82
| at Grid (15/C-D), Dia. 2.7m | Cum | -1 | 1 | 8.478 | 0.61 | 0.732 | -3.79
| at Grid (15/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (14-15/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (13/F-G), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (12-13/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (10-11/D-E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (10-11/F), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (9/C-D), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
| at Grid (9/E), Dia. 3.0m | Cum | -1 | 1 | 9.42 | 0.61 | 0.732 | -4.21
Earth Excavation for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (20/F) | Cum | -1 | 1 | 8.215 | 0.61 | 0.732 | -3.67
| Curved Seat seat at grid (12/F) | Cum | -1 | 1 | 2.343 | 0.61 | 0.732 | -1.05
| Curved Seat seat at grid (11/F-G) | Cum | -1 | 1 | 5.143 | 0.61 | 0.732 | -2.3
Earth Excavation for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (10/C-D) | Cum | 1 | 1 | 4.531 | 0.76 | 0.732 | 2.52
| Curved Seat seat at grid (9/C-D) | Cum | 1 | 1 | 5.284 | 0.76 | 0.732 | 2.94
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.143 | 0.76 | 0.732 | 1.75
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.121 | 0.76 | 0.732 | 1.74 |  |  | 2
3.1416
| Earth Excavation for Sunken Area | [9 empty] | 1.73
| P.C.C. P/L for Brick work of Sunken Area | [9 empty] | 10.8699
| excavatio for sunken portion | Cum | 1 | 1 | 78.6682 |  | 0.75 | 59 |  | Area
| excavtion for Brick Work for Sunken Area | Cum | 1 | 1 | 28.335 | 0.66 | 0.1 | 1.87
| excavtion for Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 1.353 | 1.039 | 0.1 | 0.14
| excavtion for Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 4.459 | 1.039 | 0.1 | 0.46
Earth Excavation for Sump or Filter pit for Waterbody
| Sump (750x750x850), base | Cum | 1 | 1 | 1.58 | 1.58 | 0.85 | 2.12 |  |  |  | 1150
| Filter pit (1000x1000x1000) base | Cum | 1 | 1 | 1.83 | 1.83 | 1 | 3.35
| UP TO PREVIOUS BILL | Cum | [6 empty] | 331.59
Cum
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
331.59
NS-03 | Preparation and consolidation of sub grade with power road roller of 8 to 12 tonne capacity, dressing to camber up to 225mm by excavation or filling and consolidating with road roller including making good the undulations etc.
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
Sqm
subgrade for Raised Area
| for Raised Area Top Lvl. +0.36m | Sqm | 1 | 1 | 136.65 |  |  | 136.65
subgrade for Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For Stone Soling. =7+0.2*2+0.6*2+0.2*2=9.0m)
| subgrade for footing | Sqm | 1 | 1 | 63.585 |  |  | 63.59
3 | subgrade for Sunken Area
subgrade for Brick work of Sunken Area
| subgrade in Floor area of sunken portion | Sqm | 1 | 1 | 46.5421 |  |  | 46.54
4 | subgrade in Girl's hostel Floor
| Total Area of Floor | Sqm | 1 | 1 | 1577.556 |  |  | 1577.56
deduct Green Area
| dia. 3.0m | Sqm | -1 | 15 | 7.065 |  |  | -105.98
| dia. 3.7m | Sqm | -1 | 1 | 10.7467 |  |  | -10.75
| dia. 2.7m | Sqm | -1 | 1 | 5.7227 |  |  | -5.72
| dia. 3.0m half | Sqm | -1 | 1 | 5.0168 |  |  | -5.02
| deduct Raise Area | Sqm | -1 | 1 | 152.0847 |  |  | -152.08
| deduct Waterbody | Sqm | -1 | 1 | 50.2655 |  |  | -50.27
| deduct sunken area | Sqm | -1 | 1 | 66.9707 |  |  | -66.97
| deduct R.C.C. wall | Sqm | -1 | 6 | 4.175 | 0.45 |  | -11.27
| deduct Rec. Seat | Sqm | -1 | 24 | 1.845 | 0.345 |  | -15.28
| deduct round seat dia. 0.83m | Sqm | -1 | 7 | 0.54079 |  |  | -3.79
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 1397.21 | 6th RA
1397.21
NS-04 | Suspended floors, roofs, landings balconies, access platform, Lintels, beams, plinth beams, girders, bressumers, Stairs, cantilevers
Form Work C/S for Waterbody
| Form Work for Base footing of Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For R.C.C. =7+0.2*2+0.6*2=8.60m) |  |  |  | length
| base raft dia. 8.6m | Sqm | 1 | 1 | 27.004 |  | 0.2 | 5.4 |  | 4A
| add inner face shuttering for hold area (dia. 5.2m) | Sqm | 1 | 1 | 16.328 |  | 0.2 | 3.27 |  | 4A
| form work C/S for wall 200mm thk. (outer) | Sqm | 1 | 1 | 23.236 |  | 0.545 | 12.66 |  | 4A
| inner shutt. Wall | Sqm | 1 | 1 | 21.98 |  | 0.545 | 11.98 |  | 4A
| R.C.C. wall top beam (390x150) (outer) | Sqm | 1 | 1 | 23.236 |  | 0.15 | 3.49 |  | 4A
| inner shutt. Beam | Sqm | 1 | 1 | 21.98 |  | 0.34 | 7.47 |  | 4A
4A
| Form Work C/S for Green Portion (Circular) Tie Beam (230x200) (drg. No. 5128-16-101) | [8 empty] | 4A
| at Grid (22-23/C-D), Dia. 3.0m outer face | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (20/F), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (18/F), Dia. 3.7m | Sqm | 1 | 1 | 11.618 |  | 0.2 | 2.32 |  | 4A
| inner face (dia.=3.24) | Sqm | 1 | 1 | 10.1736 |  | 0.2 | 2.03 |  | 4A
| at Grid (16-17/F), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (18/C), Dia. 3.0m (half) | Sqm | 1 | 1 | 8.566 |  | 0.2 | 1.71 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (15/C-D), Dia. 2.7m | Sqm | 1 | 1 | 8.478 |  | 0.2 | 1.7 |  | 4A
| inner face (dia.=2.24) | Sqm | 1 | 1 | 7.0336 |  | 0.2 | 1.41 |  | 4A
| at Grid (15/D-E), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (14-15/F-G), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (13/F-G), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (12-13/C-D), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (10-11/D-E), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (10-11/F), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (9/C-D), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | 1 | 1 | 7.9756 |  | 0.2 | 1.6 |  | 4A
| at Grid (9/E), Dia. 3.0m | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| at Grid (8/C-D), Dia. 3.0m | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.19
|  | Sqm | 0
| at Grid (5-6/D), Dia. 3.0m | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.19
|  | Sqm | 0
| at Grid (4-5/E), Dia. 3.0m | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.19
|  | Sqm | 0
| at Grid (3-4/F), Dia. 3.0m | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.3
|  | Sqm | 0 | 1 | 9.42 |  | 0.19
| inner face (dia.=2.54) | Sqm | 0 | 1 | 7.9756 |  | 0.2
Form Work C/S for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (20/F) | Sqm | 1 | 2 | 8.514 |  | 0.2 | 3.41 |  | 4B
|  | Sqm | 0 | 1 | 7.854 |  | 0.2 |  |  | 4B
| bottom projection | Sqm | 1 | 1 | 8.184 | 0.21 |  | 1.72 |  | 4B
| Curved Seat seat at grid (12/F) | Sqm | 1 | 2 | 2.343 |  | 0.2 | 0.94 |  | 4B
|  | Sqm | 0 | 1 | 1.809 |  | 0.2 |  |  | 4B
| bottom projection | Sqm | 1 | 1 | 1.809 | 0.21 |  | 0.38 |  | 4B
| Curved Seat seat at grid (11/F-G) | Sqm | 1 | 2 | 5.43 |  | 0.2 | 2.17 |  | 4B
|  | Sqm | 0 | 1 | 4.481 |  | 0.2 |  |  | 4B
| bottom projection | Sqm | 1 | 1 | 4.481 | 0.21 |  | 0.94 |  | 4B
Form Work C/S for Green Portion (Circular) (drg. No. 5128-16-101)
| at Grid (8/C-D), Dia. 3.0m | Sqm | 1 | 1 | 10.8644 |  | 0.2 | 2.17 |  | 4A
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A | 1
| at Grid (5-6/D), Dia. 3.0m | Sqm | 1 | 1 | 10.1422 |  | 0.2 | 2.03 |  | 4A | 3.1416
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A | 3.23
| at Grid (4-5/E), Dia. 3.0m | Sqm | 1 | 1 | 10.1422 |  | 0.2 | 2.03 |  | 4A | 10.1473
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
| at Grid (3-4/F), Dia. 3.0m | Sqm | 1 | 1 | 10.1422 |  | 0.2 | 2.03 |  | 4A
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88 |  | 4A
Form Work C/S for Half Curved Seat (tie beam & seating platform (drg. No. 5128-16-101)
| Curved Seat at grid (10/C-D) | Sqm | 1 | 2 | 4.531 |  | 0.2 | 1.81 |  | 4B
| bottom | Sqm | 1 | 1 | 4.002 | 0.21 |  | 0.84 |  | 4B
4B
| Curved Seat seat at grid (9/C-D) | Sqm | 1 | 2 | 5.289 |  | 0.2 | 2.12 |  | 4B
| bottom | Sqm | 1 | 1 | 4.81 | 0.21 | 0.1 | 0.1 |  | 4B
4B
| Curved Seat seat at grid (5/C-D) | Sqm | 1 | 2 | 3.143 |  | 0.2 | 1.26 |  | 4B
| bottom | Sqm | 1 | 1 | 2.853 | 0.21 | 0.1 | 0.06 |  | 4B
4B
| Curved Seat seat at grid (5/C-D) | Sqm | 1 | 2 | 3.121 |  | 0.2 | 1.25 |  | 4B
| bottom | Sqm | 1 | 1 | 2.833 | 0.21 | 0.1 | 0.06 |  | 4B
Form Work C/S Qty. Revise for calculation correction
| Form Work C/S for Green Portion (Circular) (drg. No. 5128-16-101) | Sqm
| at Grid (22-23/C-D), Dia. 3.0m, (Brick Work Dia. =3+0.115+0.115=3.23m) | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (20/F), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (18/F), Dia. 3.7m (Brick Work Dia. =3.7+0.115+0.115=3.93m) | Sqm | 1 | 2 | 12.3402 |  | 0.2 | 4.94 |  | 4A
| at Grid (16-17/F), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (18/C), Dia. 3.0m (half) | Sqm | 1 | 2 | 8.566 |  | 0.2 | 3.43 |  | 4A
| at Grid (15/C-D), Dia. 2.7m | Sqm | 1 | 2 | 9.2002 |  | 0.2 | 3.68 |  | 4A
| at Grid (15/D-E), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (14-15/F-G), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (13/F-G), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (12-13/C-D), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (10-11/D-E), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (10-11/F), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (9/C-D), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
| at Grid (9/E), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06 |  | 4A
4A
Form Work C/S for Green Portion (Circular) Tie Beam (230x200) (drg. No. 5128-16-101)
| at Grid (22-23/C-D), Dia. 3.0m outer face | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (20/F), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (18/F), Dia. 3.7m | Sqm | -1 | 1 | 11.618 |  | 0.2 | -2.32 |  | 4A
| inner face (dia.=3.24) | Sqm | -1 | 1 | 10.1736 |  | 0.2 | -2.03 |  | 4A
| at Grid (16-17/F), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (18/C), Dia. 3.0m (half) | Sqm | -1 | 1 | 8.566 |  | 0.2 | -1.71 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (15/C-D), Dia. 2.7m | Sqm | -1 | 1 | 8.478 |  | 0.2 | -1.7 |  | 4A
| inner face (dia.=2.24) | Sqm | -1 | 1 | 7.0336 |  | 0.2 | -1.41 |  | 4A
| at Grid (15/D-E), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (14-15/F-G), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (13/F-G), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (12-13/C-D), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (10-11/D-E), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (10-11/F), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (9/C-D), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
| inner face (dia.=2.54) | Sqm | -1 | 1 | 7.9756 |  | 0.2 | -1.6 |  | 4A
| at Grid (9/E), Dia. 3.0m | Sqm | -1 | 1 | 9.42 |  | 0.2 | -1.88 |  | 4A
Form Work C/S for Waterbody
| Form Work C/S for Sump in waterbody (750x750x850) inner size | Sqm | 2 | 4 | 0.75 |  | 0.85 | 5.1 |  | 4A
Form Work C/S for Filter Pit in waterbody (1000x1000x1000) inner size
| R.C.C. for Wall | Sqm | 1 | 4 | 1 |  | 1 | 4 |  | 4A
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 142.92
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
142.92
NS-04a | RAFT OF PLANTER WALLS TIE BEAM ON BRICK WALLS etc. ALL WORK FOR HARDSCAPE WORK | Sqm | 1 | [5 empty] | 125.86
NS-04b | FOR SIDE & BOTTOM OF SEATING SLAB EDGE,WALL OF PLANTERS ETC. | Sqm | 1 | [5 empty] | 17.06
NS-07 | MS Tray Square, 6mm thk.
| UP TO PREVIOUS BILL | Kg | [6 empty] | 0
Kg
MS Tray Square 6mm thk. (without slot)
1 | (740x740=inner size) | Each | 3 | 1 | 0.884 | 0.89
2 | 750x750 (waterbody) | Each | 2 | 1 | 0.9 | 0.9
3 | 1000x1000 (sump) | Each | 1 | 1 | 1.15 | 1.15
4 | 450x450 | Each | 15 | 1 | 0.6 | 0.6
1 | (740x740 =inner size) (890x890 = MS Tray) |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 3 | 4 | 0.884 |  | 3.06 | 32.46
| MS Plate 6mm thk. | Kg | 3 | 1 | 0.89 | 0.89 | 47.1 | 111.92
| corner chamfer flat | Kg | 3 | 2 | 0.075 | 0.075 | 47.1 | 1.59
| side packing | Kg | 3 | 4 | 0.1 |  | 3.06 | 3.67
2 | (750x750 =inner size) (900x900 = MS Tray) Waterbody |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 2 | 4 | 0.894 |  | 3.06 | 21.89
| MS Plate 6mm thk. | Kg | 2 | 1 | 0.9 | 0.9 | 47.1 | 76.3
| corner chamfer flat | Kg | 2 | 2 | 0.075 | 0.075 | 47.1 | 1.06
| side packing | Kg | 2 | 4 | 0.1 |  | 3.06 | 2.45
3 | (1000x1000 =inner size) (1150x1150 = MS Tray) Waterbody Sump |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 1 | 4 | 1.144 |  | 3.06 | 14
| MS Plate 6mm thk. | Kg | 1 | 1 | 1.15 | 1.15 | 47.1 | 62.29
| corner chamfer flat | Kg | 1 | 2 | 0.075 | 0.075 | 47.1 | 0.53
| side packing | Kg | 1 | 4 | 0.1 |  | 3.06 | 1.22
4 | (450x450 =inner size) (600x650 = MS Tray) Waterbody Sump |  |  |  | L | B | wt.
| MS Flat 65x6mm | Kg | 1 | 4 | 0.594 |  | 3.06 | 7.27
| MS Plate 6mm thk. | Kg | 1 | 1 | 0.6 | 0.6 | 47.1 | 16.96
| corner chamfer flat | Kg | 1 | 2 | 0.075 | 0.075 | 47.1 | 0.53
| side packing | Kg | 1 | 4 | 0.1 |  | 3.06 | 1.22
MS Tray Square 6mm thk. (with slot)
| (inner size=600x600), (frame size=750x750) | Each | 2 |  |  |  |  | 0
1 | (600x600 =inner size) (750x750 = MS Tray) |  |  |  | L |  | wt.
| MS Flat 65x6mm | Kg | 2 | 2 | 0.75 |  | 3.06 | 9.18
|  | Kg | 2 | 2 | 0.75 |  | 3.06 | 9.18
| partition flat patti 65x6 | Kg | 2 | 2 | 0.738 |  | 3.06 | 9.03
| MS Plate 6mm thk. | Kg | 2 | 1 | 0.75 | 0.75 | 47.1 | 52.99
| corner chamfer flat | Kg | 2 | 2 | 0.075 | 0.075 | 47.1 | 1.06
| side packing | Kg | 2 | 4 | 0.1 |  | 3.06 | 2.45
| THIS BILL TOTAL → | Kg | [6 empty] | 439.25 | 4th RA
439.25
NS-09 | Making hole of different size & shape, by stone cutter machine in stone flooring/cladding for fixing electrical fixtures, passing conduits & wires and making good after fixing fixtures etc. all complete as directed by engineer in charge.
| UP TO PREVIOUS BILL | Each | [6 empty] | 0
Each
Hole Cutting for Conduit Work in Floor
| Cutting of Holes for light in Agra Red Stone & White Marble for Conduit Fixing (Cutting of 2 nos. hole at same location | Each | 2 | 91 |  |  |  | 182
| holecutting for conduit around sunken portion | Each | 2 | 13 |  |  |  | 26
| holecutting for conduit around sunken portion at stair step | Each | 2 | 18 |  |  |  | 36
| cutting hole around waterboy | Each | 2 | 13 |  |  |  | 26
| cutting hole in waterbody | Each | 2 | 6 |  |  |  | 12
| around Raised portion | Each | 2 | 30 |  |  |  | 60
| hole in Raised portion stair step | Each | 8 | 3 |  |  |  | 24
| Making holes in Sunken Portion (Manhole cover | Each | 2 | 9 |  |  |  | 18
Hole Cutting for Light Fixing in Floor
| Cutting of Holes for light in Agra Red Stone & White Marble for Conduit Fixing | Each | 1 | 91 |  |  |  | 91
| holecutting for conduit around sunken portion | Each | 1 | 13 |  |  |  | 13
| holecutting for conduit around sunken portion at stair step | Each | 1 | 18 |  |  |  | 18
| cutting hole around waterboy | Each | 1 | 13 |  |  |  | 13
| cutting hole in waterbody | Each | 1 | 6 |  |  |  | 6
| around Raised portion | Each | 1 | 30 |  |  |  | 30
| hole in Raised portion stair step | Each | 4 | 3 |  |  |  | 12
| Making holes in Sunken Portion (Manhole cover | Each | 1 | 9 |  |  |  | 9
Each
| THIS BILL TOTAL → | Each | [6 empty] | 576 | 4th RA
576
NS-10 | Extra over item no. 3.0 for Round, Circular Brick Work with bricks of class designation 75 in foundation, plinth & superstructure in: cement mortar 1:6 (1cement : 6 coarse sand).
| UP TO PREVIOUS BILL | Cum | [6 empty] | 0
Brick Work for Waterbody
| Brick Work outer side of Waterbody | CUM | 1 | 1 | 23.97 | 0.23 | 0.545 | 3
| Brick Work P/L for Raised Area | CUM | 1 | 1 | 67.038 | 0.46 | 0.3 | 9.25
|  | CUM | 1 | 1 | 67.038 | 0.345 | 0.3 | 6.94
|  | CUM | 1 | 1 | 67.038 | 0.23 | 0.14 | 2.16
| Brick work for steps | CUM | 1 | 1 | 1.399 | 0.6 | 0.44 | 0.37
|  | CUM | 1 | 1 | 1.711 | 0.3 | 0.15 | 0.08
|  | CUM | 1 | 1 | 1.319 | 0.6 | 0.44 | 0.35
|  | CUM | 1 | 1 | 1.594 | 0.3 | 0.15 | 0.07
|  | CUM | 1 | 1 | 1.246 | 0.6 | 0.44 | 0.33
|  | CUM | 1 | 1 | 1.2 | 0.3 | 0.15 | 0.05
|  | CUM | 1 | 1 | 1.25 | 0.6 | 0.44 | 0.33
|  | CUM | 1 | 1 | 1.311 | 0.3 | 0.15 | 0.06
| Brick Work P/L for Circular Seat (dia. 1.0m) | CUM | 7 | 1 | 2.231 | 0.23 | 0.75 | 2.69
Brick Work P/L for Green Portion (Circular) (drg. No. 5128-16-101)
| Brick Work P/L for Green Portion (Circular) (drg. No. 5128-16-101) | Cum
| at Grid (22-23/C-D), Dia. 3.0m, (Brick Work Dia. =3+0.115+0.115=3.23m) | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (20/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (18/F), Dia. 3.7m (Brick Work Dia. =3.7+0.115+0.115=3.93m) | Cum | 1 | 1 | 12.3402 | 0.46 | 0.3 | 1.7
|  | Cum | 1 | 1 | 12.3402 | 0.345 | 0.3 | 1.28
|  | Cum | 1 | 1 | 12.3402 | 0.23 | 0.19 | 0.54
Cum
| at Grid (16-17/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (18/C), Dia. 3.0m (half) | Cum | 1 | 1 | 8.566 | 0.46 | 0.3 | 1.18
|  | Cum | 1 | 1 | 8.566 | 0.345 | 0.3 | 0.89
|  | Cum | 1 | 1 | 8.566 | 0.23 | 0.19 | 0.37
Cum
| at Grid (15/C-D), Dia. 2.7m | Cum | 1 | 1 | 9.2002 | 0.46 | 0.3 | 1.27
|  | Cum | 1 | 1 | 9.2002 | 0.345 | 0.3 | 0.95
|  | Cum | 1 | 1 | 9.2002 | 0.23 | 0.19 | 0.4
Cum
| at Grid (15/D-E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (14-15/F-G), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (13/F-G), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (12-13/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (10-11/D-E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (10-11/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (9/C-D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (9/E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
| at Grid (8/C-D), Dia. 3.0m (for Brick work 3.230m) | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (5-6/D), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (4-5/E), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
Cum
| at Grid (3-4/F), Dia. 3.0m | Cum | 1 | 1 | 10.1422 | 0.46 | 0.3 | 1.4
|  | Cum | 1 | 1 | 10.1422 | 0.345 | 0.3 | 1.05
|  | Cum | 1 | 1 | 10.1422 | 0.23 | 0.19 | 0.44
2 | Brick Work P/L for Half Curved Seat (drg. No. 5128-16-101)
Brick Work P/L for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (20/F) | CUM | 1 | 1 | 8.215 | 0.46 | 0.3 | 1.13
|  | CUM | 1 | 1 | 8.215 | 0.345 | 0.3 | 0.85
|  | CUM | 1 | 1 | 8.215 | 0.23 | 0.59 | 1.11
| Curved Seat seat at grid (12/F) | CUM | 1 | 1 | 2.343 | 0.46 | 0.3 | 0.32
|  | CUM | 1 | 1 | 2.343 | 0.345 | 0.3 | 0.24
|  | CUM | 1 | 1 | 2.343 | 0.23 | 0.59 | 0.32
| Curved Seat seat at grid (11/F-G) | CUM | 1 | 1 | 5.143 | 0.46 | 0.3 | 0.71
|  | CUM | 1 | 1 | 5.143 | 0.345 | 0.3 | 0.53
|  | CUM | 1 | 1 | 5.143 | 0.23 | 0.59 | 0.7
| Curved Seat seat at grid (10/C-D) | Cum | 1 | 1 | 4.531 | 0.46 | 0.3 | 0.63
|  | Cum | 1 | 1 | 4.531 | 0.345 | 0.3 | 0.47
|  | Cum | 1 | 1 | 4.531 | 0.23 | 0.59 | 0.61
| Curved Seat seat at grid (9/C-D) | Cum | 1 | 1 | 5.289 | 0.46 | 0.3 | 0.73
|  | Cum | 1 | 1 | 5.289 | 0.345 | 0.3 | 0.55
|  | Cum | 1 | 1 | 5.289 | 0.23 | 0.59 | 0.72
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.143 | 0.46 | 0.3 | 0.43
|  | Cum | 1 | 1 | 3.143 | 0.345 | 0.3 | 0.33
|  | Cum | 1 | 1 | 3.143 | 0.23 | 0.59 | 0.43
| Curved Seat seat at grid (5/C-D) | Cum | 1 | 1 | 3.121 | 0.46 | 0.3 | 0.43
|  | Cum | 1 | 1 | 3.121 | 0.345 | 0.3 | 0.32
|  | Cum | 1 | 1 | 3.121 | 0.23 | 0.59 | 0.42
3 | Brick Work P/L for Sunken Area
| Brick Work P/L for Sunken Area | Cum | 1 | 1 | 28.335 | 0.839 | 0.6 | 14.26
| Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 1.353 | 0.305 | 0.4 | 0.17
|  | Cum | 1 | 1 | 1.353 | 0.304 | 0.55 | 0.23
|  | Cum | 1 | 1 | 1.353 | 0.23 | 0.05 | 0.02
| Brick work for Stair case step in Sunken Area | Cum | 1 | 1 | 4.459 | 0.305 | 0.4 | 0.54
|  | Cum | 1 | 1 | 4.459 | 0.304 | 0.55 | 0.75
|  | Cum | 1 | 1 | 4.459 | 0.23 | 0.05 | 0.05
| NOT PAYABLE |  | -1 |  | 105.61 |  |  | -105.61
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
0
E.I.07 | Extra for shuttering in circular work (20% of respective centering and shuttering items) Ref. from D.A.R. Item no. 5.9.14
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
Form Work C/S for Tie Beam on Brick Work
Form Work C/S for Waterbody
| Form Work for Base footing of Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For R.C.C. =7+0.2*2+0.6*2=8.60m) |  |  |  | length
| base raft dia. 8.6m | Sqm | 1 | 1 | 27.004 |  | 0.2 | 5.4
| add inner face shuttering for hold area (dia. 5.2m) | Sqm | 1 | 1 | 16.328 |  | 0.2 | 3.27
| form work C/S for wall 200mm thk. (outer) | Sqm | 1 | 1 | 23.236 |  | 0.545 | 12.66
| inner shutt. Wall | Sqm | 1 | 1 | 21.98 |  | 0.545 | 11.98
| R.C.C. wall top beam (390x150) (outer) | Sqm | 1 | 1 | 23.236 |  | 0.15 | 3.49
| inner shutt. Beam | Sqm | 1 | 1 | 21.98 |  | 0.34 | 7.47
1 | Form Work C/S for Green Portion (Circular) (drg. No. 5128-16-101)
| Form Work C/S for Green Portion (Circular) (drg. No. 5128-16-101) | Sqm
| at Grid (22-23/C-D), Dia. 3.0m, (Brick Work Dia. =3+0.115+0.115=3.23m) | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (20/F), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (18/F), Dia. 3.7m (Brick Work Dia. =3.7+0.115+0.115=3.93m) | Sqm | 1 | 2 | 12.3402 |  | 0.2 | 4.94
| at Grid (16-17/F), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (18/C), Dia. 3.0m (half) | Sqm | 1 | 2 | 8.566 |  | 0.2 | 3.43
| at Grid (15/C-D), Dia. 2.7m | Sqm | 1 | 2 | 9.2002 |  | 0.2 | 3.68
| at Grid (15/D-E), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (14-15/F-G), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (13/F-G), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (12-13/C-D), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (10-11/D-E), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (10-11/F), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (9/C-D), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (9/E), Dia. 3.0m | Sqm | 1 | 2 | 10.1422 |  | 0.2 | 4.06
| at Grid (8/C-D), Dia. 3.0m | Sqm | 1 | 1 | 10.8644 |  | 0.2 | 2.17
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88
| at Grid (5-6/D), Dia. 3.0m | Sqm | 1 | 1 | 10.1422 |  | 0.2 | 2.03
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88
| at Grid (4-5/E), Dia. 3.0m | Sqm | 1 | 1 | 10.1422 |  | 0.2 | 2.03
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88
| at Grid (3-4/F), Dia. 3.0m | Sqm | 1 | 1 | 10.1422 |  | 0.2 | 2.03
|  | Sqm | 1 | 1 | 9.42 |  | 0.2 | 1.88
2 | Form Work C/S for Half Curved Seat (tie beam & seating platform (drg. No. 5128-16-101)
Form Work C/S for Half Curved Seat (drg. No. 5128-16-101)
| Curved Seat seat at grid (20/F) | Sqm | 1 | 2 | 8.514 |  | 0.2 | 3.41
|  | Sqm | 0 | 1 | 7.854 |  | 0.2
| bottom projection | Sqm | 1 | 1 | 8.182 | 0.21 |  | 1.72
| Curved Seat seat at grid (12/F) | Sqm | 1 | 2 | 2.343 |  | 0.2 | 0.94
|  | Sqm | 0 | 1 | 1.809 |  | 0.2
| bottom projection | Sqm | 1 | 1 | 1.809 | 0.21 |  | 0.38
| Curved Seat seat at grid (11/F-G) | Sqm | 1 | 2 | 5.43 |  | 0.2 | 2.17
|  | Sqm | 0 | 1 | 4.481 |  | 0.2
| bottom projection | Sqm | 1 | 1 | 4.481 | 0.21 |  | 0.94
| Curved Seat at grid (10/C-D) | Sqm | 1 | 2 | 4.531 |  | 0.2 | 1.81
| bottom | Sqm | 1 | 1 | 4.002 | 0.21 |  | 0.84
| Curved Seat seat at grid (9/C-D) | Sqm | 1 | 2 | 5.289 |  | 0.2 | 2.12
| bottom | Sqm | 1 | 1 | 4.81 | 0.21 | 0.1 | 0.1
| Curved Seat seat at grid (5/C-D) | Sqm | 1 | 2 | 3.143 |  | 0.2 | 1.26
| bottom | Sqm | 1 | 1 | 2.853 | 0.21 | 0.1 | 0.06
| Curved Seat seat at grid (5/C-D) | Sqm | 1 | 2 | 3.121 |  | 0.2 | 1.25
| bottom | Sqm | 1 | 1 | 2.833 | 0.21 | 0.1 | 0.06
| NOT PAYABLE |  | -1 |  | 133.82 |  |  | -133.82
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
0
NS-12 | Extra for Material wastage for Circular cutting in white marble
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 4th RA
0
NS-15 | Lakha Red Stone in Waterbody
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
| in Floor (dia.=7.0m) | Sqm | 1 | 1 | 38.465 |  |  | 38.47
| inner cladding | Sqm | 1 | 1 | 21.98 |  | 0.666 | 14.64
| THIS BILL TOTAL → | Sqm | [6 empty] | 53.11 | 4th RA
53.11
NS-13 | Champhering at Edges
| UP TO PREVIOUS BILL | Rmt | [6 empty] | 0
Rmt
a | sunken Area, white marble stone Champhering 5x5mm
| Sunken area, step tread | Rmt | 1 | 2 | 1.455 |  |  | 2.91
| Sunken area, step tread | Rmt | 1 | 2 | 4.475 |  |  | 8.95
| sunken area inner champhering | Rmt | 1 | 1 | 33.5198 |  |  | 33.52
b | White Marble for Rec. Seat (2000x500)
| Side Cladding | Rmt | 24 | 2 | 2 |  |  | 96
|  | Rmt | 24 | 2 | 0.5 |  |  | 24
| vertical | Rmt | 24 | 2 | 0.365 |  |  | 17.52
c | White Marble for Round seat dia. 1.0m
| top coping (double stone as per detail/engineer in charge) | Rmt | 7 | 1 | 3.14 |  |  | 21.98
d | White Marble for curved seat
Curved Seat (20/F)
| outer side | Rmt | 1 | 1 | 9.425 |  |  | 9.43
| front face | Rmt | 1 | 1 | 7.855 |  |  | 7.86
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (11/F-G)
| outer side | Rmt | 1 | 1 | 5.5 |  |  | 5.5
| front face | Rmt | 1 | 1 | 4.48 |  |  | 4.48
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (12/F)
| outer face | Rmt | 1 | 1 | 2.63 |  |  | 2.63
| front face | Rmt | 1 | 1 | 1.81 |  |  | 1.81
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (10/C-D)
| outer cladding | Rmt | 1 | 1 | 4.81 |  |  | 4.81
| front face | Rmt | 1 | 1 | 3.605 |  |  | 3.61
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (9/C-D)
| outer cladding | Rmt | 1 | 1 | 5.535 |  |  | 5.54
| front face | Rmt | 1 | 1 | 4.45 |  |  | 4.45
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (4-5/D)
| outer cladding | Rmt | 1 | 1 | 3.255 |  |  | 3.26
| front face | Rmt | 1 | 1 | 2.635 |  |  | 2.64
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (4-5/D-E)
| outer cladding | Rmt | 1 | 1 | 3.27 |  |  | 3.27
| front face | Rmt | 1 | 1 | 2.615 |  |  | 2.62
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
e | White Marble on Coping top of Waterbody (double layer stone) as per specification
| r=4.05m | Rmt | 1 | 1 | 25.434 |  |  | 25.43
| inner side (r=3.5m) | Rmt | 1 | 1 | 21.98 |  |  | 21.98
f | champhering for Riased area | Rmt | 1 | 1 | 67.366 |  |  | 67.37
| step tread | Rmt | 1 | 2 | 1.37 |  |  | 2.74
|  | Rmt | 1 | 2 | 1.2 |  |  | 2.4
|  | Rmt | 1 | 2 | 1.355 |  |  | 2.71
|  | Rmt | 1 | 2 | 1.45 |  |  | 2.9
| NOT PAYABLE | Sqm | -1 |  | 411.92 |  |  | -411.92
Rmt
| THIS BILL TOTAL → | Rmt | [6 empty] | 0 | 6th RA
0
NS 23 | Extra for Material wastage for Circular Stone in White Marbles
| UP TO PREVIOUS BILL | Sqm | [6 empty] | 0
Sqm
a | White Marble in Circular Portion of Circle 600mm dia.
| White Marble in circle (2-3/C-D) (dia. 4.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (4-5/C-D) (dia. 4.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (3-4/D) (dia. 2.4m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (6/C) (r = 2.15m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (6/C-D) (r = 1.0m) | Sqm | 1 | 1 | 3.14 |  |  | 3.14
| White Marble in circle (2-3/D-E) (r = 2.70m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (4/D-E) (r = 1.10m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (3-4/E) (r = 0.750m) | Sqm | 1 | 1 | 1.7663 |  |  | 1.77
| White Marble in circle (5-6/D-E) (r = 0.750m) | Sqm | 1 | 1 | 1.7663 |  |  | 1.77
| White Marble in circle (2-3/E-F) (r = 1.9m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (1/E-F) (r = 1.2m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (1/E-F) (r = 1.6m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (1'/E-F) (r = 1.3m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (1'/F-G) (r = 1.5m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (2/F-G) (r = 1.35m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (5/F-G) (r = 0.85m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (5/F-G) (r = 0.5m) | Sqm | 1 | 1 | 0.785 |  |  | 0.79
| White Marble in circle (8/C) (r = 1.5m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (7/D-E) (r = 0.9m) | Sqm | 1 | 1 | 2.5434 |  |  | 2.54
| White Marble in circle (8/D-E) (r = 1.45m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (6-7-8/E) (r = 2.3m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (8-9/C-D) (r = 0.75m) | Sqm | 1 | 1 | 1.7663 |  |  | 1.77
| White Marble in circle (9/C) (r = 0.75m) half | Sqm | 1 | 1 | 1.7663 |  |  | 1.77
| White Marble in circle (8-9/D) (r = 2.55m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (8-9/D) (r = 1.2m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (9/D-E) (r = 1.2m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (10/D) (r = 2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (9/E-F) (r = 1.5m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (10/C) (r = 2.0m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (10/C-D) (r = 2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (10/E) (r = 3.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (10/F) (r = 3.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (11/C) (r = 2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (12/D) (r = 2.10m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (11/F-G) (r = 2.70m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (12/F) (r = 1.6m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (12/F-G) (r = 0.6m) | Sqm | 1 | 1 | 1.1304 |  |  | 1.13
| White Marble in circle (10-11/G) (r = 1.250m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/C-D) (r =1.25m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/D) (r =2.7m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/D-E) (r =0.75m) | Sqm | 1 | 2 | 1.7663 |  |  | 3.53
| White Marble in circle (14/F) (r =3.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14-15/C) (r =1.15m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15-16/C) (r =1.5m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (16-17/C-D) (r =1.0m) | Sqm | 1 | 1 | 3.14 |  |  | 3.14
| White Marble in circle (15-16/D) (r =2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15-16/E) (r =1.30m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15/F) (r =0.75m) | Sqm | 1 | 1 | 1.7663 |  |  | 1.77
| White Marble in circle (16/F-G) (r =1.25m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15-16/G) (r =2.5m)half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (20/C) (r=1.750m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (18-19/G) (r=2.750m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (20/G) (r=2.230m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (21-22/F-G) (r=1.50m) half | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (21/F-G) (r=0.750m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77
| White Marble in circle (22-23/F) (r=2.250m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24/F-G) (r=1.850m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24-25/F-G) (r=1.30m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'/E-F) (r=1.80m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'-25/E-F) (r=1.30m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'/D-E) (r=2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (24'/C-D) (r=2.0m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/C) (r=1.150m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15-16/C) (r=1.475m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14-15/B-C) (r=0.750m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77
| White Marble in circle (15-16/B') (r=1.50m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (14/B-B') (r=2.10m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
| White Marble in circle (15/B) (r=1.0m) | Sqm | 1 | 1 | 3.14 |  |  | 3.14
| White Marble in circle (14-15/A-B) (r=0.75m) | Sqm | 1 | 1 | 1.7671 |  |  | 1.77
| White Marble in circle (14/A'-B) (r=1.0m) | Sqm | 1 | 1 | 3.14 |  |  | 3.14
| White Marble in circle (14-15/A'-B) (r=1.150m) | Sqm | 1 | 1 | 0.2826 |  |  | 0.28
b | sunken Ara Step white ,marble stone
| stair area, Tread | Sqm | 1 | 2 | 1.455 | 0.32 |  | 0.93
| riser | Sqm | 1 | 3 | 1.455 |  | 0.15 | 0.65
| stair area | Sqm | 1 | 2 | 4.475 | 0.32 |  | 2.86
| riser | Sqm | 1 | 3 | 4.475 |  | 0.15 | 2.01
c | White Marble for Rec. Seat (2000x500)
| Side Cladding | Sqm | 24 | 2 | 2 |  | 0.325 | 31.2
|  | Sqm | 24 | 2 | 1.91 |  | 0.1 | 9.17
|  | Sqm | 24 | 2 | 0.5 |  | 0.325 | 7.8
|  | Sqm | 24 | 2 | 0.41 |  | 0.1 | 1.97
| top coping (double stone) | Sqm | 24 | 2 | 0.32 | 0.5 |  | 7.68
d | White Marble for Round seat dia. 1.0m
| side cladding | Sqm | 7 | 1 | 3.14 |  | 0.335 | 7.36
|  | Sqm | 7 | 1 | 2.7946 |  | 0.1 | 1.96
| top coping (double stone as per detail/engineer in charge) | Sqm | 7 | 2 | 0.785 |  |  | 10.99
e | White Marble for curved seat
Curved Seat (20/F)
| outer cladding | Sqm | 1 | 1 | 9.425 |  | 0.41 | 3.86
| inner cladding | Sqm | 1 | 1 | 8.705 |  | 0.3 | 2.61
| front face | Sqm | 1 | 1 | 7.855 |  | 0.145 | 1.14
| top coping (double layer) | Sqm | 1 | 2 | 8.64 | 0.5 |  | 8.64
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (11/F-G)
| outer cladding | Sqm | 1 | 1 | 5.5 |  | 0.41 | 2.26
| inner cladding | Sqm | 1 | 1 | 5.03 |  | 0.3 | 1.51
| front face | Sqm | 1 | 1 | 4.48 |  | 0.145 | 0.65
| top coping (double layer) | Sqm | 1 | 2 | 4.99 | 0.5 |  | 4.99
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (12/F)
| outer cladding | Sqm | 1 | 1 | 2.63 |  | 0.41 | 1.08
| inner cladding | Sqm | 1 | 1 | 2.255 |  | 0.3 | 0.68
| front face | Sqm | 1 | 1 | 1.81 |  | 0.145 | 0.26
| top coping (double layer) | Sqm | 1 | 2 | 2.22 | 0.5 |  | 2.22
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (10/C-D)
| outer cladding | Sqm | 1 | 1 | 4.81 |  | 0.41 | 1.97
| inner cladding | Sqm | 1 | 1 | 4.255 |  | 0.3 | 1.28
| front face | Sqm | 1 | 1 | 3.605 |  | 0.145 | 0.52
| top coping (double layer) | Sqm | 1 | 2 | 4.205 | 0.5 |  | 4.21
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (9/C-D)
| outer cladding | Sqm | 1 | 1 | 5.535 |  | 0.41 | 2.27
| inner cladding | Sqm | 1 | 1 | 5.035 |  | 0.3 | 1.51
| front face | Sqm | 1 | 1 | 4.45 |  | 0.145 | 0.65
| top coping (double layer) | Sqm | 1 | 2 | 4.99 | 0.5 |  | 4.99
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (4-5/D)
| outer cladding | Sqm | 1 | 1 | 3.255 |  | 0.41 | 1.33
| inner cladding | Sqm | 1 | 1 | 2.99 |  | 0.3 | 0.9
| front face | Sqm | 1 | 1 | 2.635 |  | 0.145 | 0.38
| top coping (double layer) | Sqm | 1 | 2 | 2.965 | 0.5 |  | 2.97
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
Curved Seat (4-5/D-E)
| outer cladding | Sqm | 1 | 1 | 3.27 |  | 0.41 | 1.34
| inner cladding | Sqm | 1 | 1 | 2.97 |  | 0.3 | 0.89
| front face | Sqm | 1 | 1 | 2.615 |  | 0.145 | 0.38
| top coping (double layer) | Sqm | 1 | 2 | 2.945 | 0.5 |  | 2.95
| side face | Sqm | 1 | 2 | 0.29 |  | 0.41 | 0.24
|  | Sqm | 1 | 2 | 0.21 |  | 0.145 | 0.06
f | White Marble on Coping top of Waterbody (double layer stone) as per specification
| r=4.05m | Sqm | 1 | 2 | 51.5038 |  |  | 103.01
| deduct inner area (r=3.5m) | Sqm | -1 | 2 | 38.4845 |  |  | -76.97
| NOT PAYABLE | Sqm | -1 |  | 221.27 |  |  | -221.27
Sqm
Sqm
| THIS BILL TOTAL → | Sqm | [6 empty] | 0 | 6th RA
0
NS-14 | Making of Groove in Stone Cladding for Architectural Appreance as per direction of Engineer in Charge
| UP TO PREVIOUS BILL | Rmt | [6 empty] | 0
a | sunken Area, white marble stone groove
| Sunken area, step tread | Rmt | 1 | 2 | 1.455 |  |  | 2.91
| Sunken area, step tread | Rmt | 1 | 2 | 4.475 |  |  | 8.95
| sunken area inner champhering | Rmt | 1 | 1 | 33.5198 |  |  | 33.52
b | White Marble for Rec. Seat (2000x500) groove
| Side Cladding | Rmt | 24 | 2 | 2 |  |  | 96
|  | Rmt | 24 | 2 | 0.5 |  |  | 24
| vertical | Rmt | 24 | 2 | 0.365 |  |  | 17.52
c | White Marble for Round seat dia. 1.0m
| top coping (double stone as per detail/engineer in charge) | Rmt | 7 | 1 | 3.14 |  |  | 21.98
d | White Marble for curved seat
Curved Seat (20/F)
| outer side | Rmt | 1 | 1 | 9.425 |  |  | 9.43
| front face | Rmt | 1 | 1 | 7.855 |  |  | 7.86
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (11/F-G)
| outer side | Rmt | 1 | 1 | 5.5 |  |  | 5.5
| front face | Rmt | 1 | 1 | 4.48 |  |  | 4.48
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (12/F)
| outer face | Rmt | 1 | 1 | 2.63 |  |  | 2.63
| front face | Rmt | 1 | 1 | 1.81 |  |  | 1.81
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (10/C-D)
| outer cladding | Rmt | 1 | 1 | 4.81 |  |  | 4.81
| front face | Rmt | 1 | 1 | 3.605 |  |  | 3.61
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (9/C-D)
| outer cladding | Rmt | 1 | 1 | 5.535 |  |  | 5.54
| front face | Rmt | 1 | 1 | 4.45 |  |  | 4.45
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (4-5/D)
| outer cladding | Rmt | 1 | 1 | 3.255 |  |  | 3.26
| front face | Rmt | 1 | 1 | 2.635 |  |  | 2.64
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
Curved Seat (4-5/D-E)
| outer cladding | Rmt | 1 | 1 | 3.27 |  |  | 3.27
| front face | Rmt | 1 | 1 | 2.615 |  |  | 2.62
| side face | Rmt | 1 | 2 | 0.5 |  |  | 1
| vertical | Rmt | 1 | 4 | 0.45 |  |  | 1.8
e | White Marble on Coping top of Waterbody (double layer stone) as per specification
| r=4.05m | Rmt | 1 | 1 | 25.434 |  |  | 25.43
| inner side (r=3.5m) | Rmt | 1 | 1 | 21.98 |  |  | 21.98
f | champhering for Riased area | Rmt | 1 | 1 | 67.366 |  |  | 67.37
| step tread | Rmt | 1 | 2 | 1.37 |  |  | 2.74
|  | Rmt | 1 | 2 | 1.2 |  |  | 2.4
|  | Rmt | 1 | 2 | 1.355 |  |  | 2.71
|  | Rmt | 1 | 2 | 1.45 |  |  | 2.9
| NOT PAYABLE | Sqm | -1 |  | 411.92 |  |  | -411.92
| THIS BILL TOTAL → | Rmt | [6 empty] | 0 | 6th RA
0
Item reference BOYS HOSTEL-LANDSCAPE DEVELOPMENT CIVIL WORKS
6 | Supplying and laying sub base course ( water bound macadam) 100 m thick (consolidated thickness) with stone aggregate of size 93 to 45 mm including stone screening,sorting and consolidation with 8 to 10 tonne power road roller etc. and binding material complete all as specified by structural consultant. (Quantity may vary as per structural drawings)
| Stone Agg. P/L for Raised Area |  |  |  | area
| P.C.C. for Raised Area Top Lvl. +0.36m | Cum | 1 | 1 | 136.65 |  | 0.15 | 20.5
| deduct Brick work area | Cum | 0 | 1 | 30.987 |  | 0.15
Cum
| Stone Soling P/L for Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For Stone Soling. =7+0.2*2+0.6*2+0.2*2=9.0m) | Cum |  |  | area
| Stone Soling for footing | Cum | 1 | 1 | 63.585 |  | 0.15 | 9.54
WBM P/L for Sunken Area
WBM P/L for Brick work of Sunken Area
| WBM P/L in Floor area of sunken portion | Cum | 1 | 1 | 46.525 |  | 0.15 | 6.98 |  | Area
WBM P/L in Girl's hostel Floor for Stone Fixing
| Total Area of Floor | Cum | 1 | 1 | 1577.556 |  | 0.15 | 236.63 |  | Area
deduct Green Area
| dia. 3.0m | Cum | -1 | 15 | 7.065 |  | 0.15 | -15.9 |  | Area
| dia. 3.7m | Cum | -1 | 1 | 10.7467 |  | 0.15 | -1.61 |  | Area
| dia. 2.7m | Cum | -1 | 1 | 5.7227 |  | 0.15 | -0.86 |  | Area
| dia. 3.0m half | Cum | -1 | 1 | 5.0168 |  | 0.15 | -0.75 |  | Area
| deduct Raise Area | Cum | -1 | 1 | 152.0847 |  | 0.15 | -22.81 |  | Area
| deduct Waterbody | Cum | -1 | 1 | 50.2655 |  | 0.15 | -7.54 |  | Area
| deduct sunken area | Cum | -1 | 1 | 66.9707 |  | 0.15 | -10.05 |  | Area
| deduct R.C.C. wall | Cum | -1 | 6 | 4.175 | 0.45 | 0.15 | -1.69
| deduct Rec. Seat | Cum | -1 | 24 | 1.845 | 0.345 | 0.15 | -2.29
| deduct round seat dia. 0.83m | Cum | -1 | 7 | 0.581 |  | 0.15 | -0.61 |  | Area
| UP TO PREVIOUS BILL | Cum | [6 empty] | 209.54
| THIS BILL TOTAL → | Cum | [6 empty] | 0 | 6th RA
209.54

## BBS-Boys Hostel
M/S. Gannon Dunkerley & Co. Ltd.
Project : Hardscaping work for Thapar University Patiala
Sub. :- Bar Bending Schedule | [17 empty] | Date : | 2017-09-08
R.A. - Pre Final | [10 empty] | Boy's Hostel
S. N. | Particulars/Description | Bar |  |  | Nos |  |  | Length of Bars (mm) |  |  |  |  | Cutting Length Of Bar in Mtr. | Total Length of Over Laps | Dia of Bars
|  | Dia. | Spacing | Shape | Block | Member | Bar per Member | A | B | C | D | E |  |  | 8 | 10 | 12 | 16 | 20 | 25 | 32
A.1 | Reinft. For Tie Beam on Planter | [11 empty] | - | - | - | - | - | - | -
1 | Reinft. for Planter (2-6/28'-31') Tie Beam (Near BH-01 west side)
1.a | Longitudianal Axies (tie Beam=230x200)
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 |  | 3610 |  | 100 | 3670 | 0 | - | 7.34 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 |  | 3610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 19.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 2 | 2 | 100 |  | 1610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 2 | 2 | 100 |  | 1610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 2 | 9.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 1 | 6.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 1 | 5.15 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 3 | 2 | 100 |  | 1910 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 3 | 2 | 100 |  | 1910 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 3 | 10.55 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 2510 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 2510 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 1 | 13.55 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 1 | 8.15 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 5940 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  | 1 | 1 | 2 | 100 |  | 5940 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  | 1 | 1 | 31.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
1.b | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2920 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2920 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 6.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 6.725 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2695 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2695 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 14.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2695 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2695 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 14.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
1.a | Reinft. for Planter (2-6/28'-31') Tie Beam (Near BH-01 west side) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 35 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1740 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1740 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 10 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 24.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5570 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5570 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 28.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 4.9 | 100 |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3815 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3815 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 20.075 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1980 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1980 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 10.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7070 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7070 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 36.35 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8870 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8870 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 45.35 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6215 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6215 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 32.075 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 11100 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 11100 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 56.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
1.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 5 | 2 | 100 |  | 1020 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 5 | 2 | 100 |  | 1020 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 5 | 6.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 4 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 4 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 4 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 20.45 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 4 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Reinft. For Tie Beam of between BH-01 & Waterbody north side of BH-04 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9210 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9210 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 47.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 22.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2980 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2980 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 15.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1980 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1980 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 10.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 6.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 19.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 5445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 5445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 28.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 31.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 9.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2880 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2880 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 15.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1945 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1945 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 9.725 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 7.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4680 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4680 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 24.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7910 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7910 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 40.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 4 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 8 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 8 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 8 | 6.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2350 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2350 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.75 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.575 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 2045 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 2045 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 11.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2.b | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.b.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8410 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8410 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 43.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 7.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 7.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 19.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 26.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 3.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 4.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 16.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 22.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 17.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 18.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 7.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 41.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 10210 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 10210 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 52.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
15 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 4 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2.b.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 6 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 6 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 6 | 6.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 4 | 2 | 100 |  | 2045 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 4 | 2 | 100 |  | 2045 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 4 | 11.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2.c | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.c.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7190 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7190 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 36.95 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 26.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 8.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 6.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 16.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 4 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 4 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 4 | 16.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 2445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 2445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 13.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 6.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 21.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 445 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 3.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5210 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5210 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 27.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 1 | 3 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 1 | 3 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 1 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2.c.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 5 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 5 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 5 | 6.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 6 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 6 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 6 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 19.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Reinft. For Tie Beam of Planter between BH-07 & BH-04 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4610 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 24.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 5.2 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 5.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1205 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1205 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 7.025 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1585 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1585 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 8.925 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4240 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4240 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 22.2 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 560 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 560 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 3.8 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1460 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1460 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 8.3 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4240 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4240 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 22.2 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3085 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3085 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 16.425 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3260 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3260 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 17.3 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 4.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6340 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6340 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 32.7 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
15 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3580 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3580 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 18.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
16 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1380 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 7.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
17 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 49.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
18 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 5 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 5 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 5 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 7 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 7 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 7 | 6.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.575 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1400 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1400 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 8 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 5 | 2 | 100 |  | 2080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 5 | 2 | 100 |  | 2080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 5 | 16 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 5 | 2 | 100 |  | 2080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 5 | 2 | 100 |  | 2080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 5 | 11.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3.b | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.b.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 10570 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 10570 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 53.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8340 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 8340 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 42.7 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3605 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 3605 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 19.025 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6340 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6340 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 32.7 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 6005 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 6005 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 31.025 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 40.2 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 10070 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 10070 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 51.35 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 3 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 3 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 3 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3.b.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 6.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 19.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Reinft. For Tie Beam of Planter North side of BH-02 & Gym | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 16.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 6 | 2 | 100 |  | 1880 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 6 | 2 | 100 |  | 1880 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 6 | 10.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 5 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 5 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 5 | 6.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3680 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3680 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 19.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 14.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 2780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 2780 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 14.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 3685 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 3685 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 19.425 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2620 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2620 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 14.1 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 4 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 4 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 4 | 6.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1705 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1705 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 9.525 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2620 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2620 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 14.1 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 650 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 650 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 4.25 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4145 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4145 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 21.725 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 6.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2620 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2620 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 14.1 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3840 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 20.2 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2705 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2705 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 14.525 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7195 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 7195 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 36.975 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4230 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4230 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 22.15 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9635 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9635 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 49.175 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 4 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Reinft. For Tie Beam of Planter between BH-04 & BH-05 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3890 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3890 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 20.45 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1660 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1660 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 9.3 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 4 | 2 | 100 |  | 2560 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 4 | 2 | 100 |  | 2560 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 4 | 13.8 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4660 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4660 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 24.3 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 1925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 10.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 4360 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 4360 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 22.8 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 2525 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 2525 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 13.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6160 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6160 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 31.8 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1680 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1680 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 9.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4625 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4625 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 24.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 11090 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 11090 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 56.45 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 4 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 4 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 6.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 6 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 6 | 2 | 100 |  | 3770 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 6 | 19.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 7 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 7 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 7 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2925 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 15.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Reinft. For Tie Beam of Planter between BH-04 & BH-05 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 970 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 970 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 5.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1345 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1345 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 7.725 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5935 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 5935 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 30.675 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1705 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1705 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 9.525 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.575 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2015 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2015 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.075 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2320 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2320 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.6 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2010 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2315 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.575 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1660 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1660 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 9.3 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 |  |  |  | 6 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 6 | 2 | 100 |  | 1025 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 6 | 6.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 3 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 3 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 3 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2505 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 2505 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 13.525 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 5525 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 5525 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 28.625 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 6560 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 6560 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 33.8 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 7130 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 7130 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 36.65 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 6300 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 6300 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 32.5 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 4825 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 4825 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 25.125 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 3180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 16.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Reinft. For Tie Beam of Planter East side of BH-01 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 29730 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 29730 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 2 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 149.65 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 6.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Reinft. For Tie Beam of Planter West side of BH-04 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.a | Planter Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.a.1 | Longitudianal Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 33180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 33180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 2 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 166.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 30045 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 30045 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 2 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 151.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2280 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2280 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 12.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1095 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 6.475 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 645 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 4.225 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2170 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2170 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.85 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 670 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 670 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 4.35 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3215 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3215 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 17.075 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8.a.2 | Transverse Axies (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4975 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 4975 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 25.875 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3140 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 3140 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 16.7 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6615 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 6615 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 34.075 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2180 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.9 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2410 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2410 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 13.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 |  |  |  | 0 | 2 | 100 |  | 880 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 0 | 2 | 100 |  | 880 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 0 | 5.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1410 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 1410 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 8.05 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2150 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 2150 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 11.75 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9 | Reinft. For Tie Beam for Basket Ball Ground alround on B/W | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.a | Toe Wall Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.a.1 | (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| alround the basket ground | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 14600 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 14600 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 2 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 74 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 27950 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 27950 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 4 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 140.75 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9.a.2 | Tie Beam east side of basket ground for Toe wall | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 3 | 2 | 100 |  | 7575 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 3 | 2 | 100 |  | 7575 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 3 | 38.875 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
9.b | Toe Wall Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.b.1 | (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (385x275) Sheat) Bottom Bar | 12 |  |  |  | 2 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Top Bar | 12 |  |  |  | 2 | 3 | 100 |  | 2950 |  | 100 | #REF! |  | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 |  |  |  | 2 | 15.75 |  |  | 1280 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10 | Reinft. For Tie Beam for Basket Ball Ground alround on B/W | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.a | Toe Wall Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.a.1 | (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| alround the basket ground | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 34885 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 34885 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 2 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 175.425 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 14950 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 14950 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 1 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 75.75 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Tie Beam for Toe Wall Back side of Basket Ball Ground (east side) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 4 | 2 | 100 |  | 7575 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 4 | 2 | 100 |  | 7575 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 4 | 38.875 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Reinft. For Tie Beam for Road Toe Wall BH-02 to GYM North side | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1.a | Toe Wall Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (tie Beam=230x200) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 8 | 2 | 100 |  | 7575 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 8 | 2 | 100 |  | 7575 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 8 | 38.875 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9900 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 9900 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 50.5 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
11 | Reinft. For Tie Beam for Fire Tender Toe Wall | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.a | Toe Wall Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FIRE TENDER TOE WALL WITH BH-01 (South side) | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 31350 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 31350 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 2 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 157.75 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| FIRE TENDER TOE WALL WITH BH-07 | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 1 | 2 | 100 |  | 42500 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 1 | 2 | 100 |  | 42500 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 3 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 1 | 213.5 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
12 | Reinft. For Tie Beam for Fire Tender Toe Wall | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.a | Toe Wall Tie Beam | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | for Road Toe Wall BH-01 east side towards water body | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 29730 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 29730 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 |  |  |  | 4 | 4 |  |  | 500 |  |  | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 149.65 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1080 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 6.4 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 12
b | or Road Toe Wall BH-01 North side towards GYM | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 5505 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 5505 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 28.525 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1675 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1675 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 9.375 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 6330 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 6330 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 32.65 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1675 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 |  |  |  | 2 | 2 | 100 |  | 1675 |  | 100 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 |  |  |  | 2 | 9.375 |  |  | 820 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13 | Reinft. For R.C.C. Planter North side of Basket Ball Ground | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.a | Reinft. For Footing (4800x1300) |  |  |  |  | 2 | [6 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 2 | 32.3333 | 200 |  | 1200 |  | 200 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 2 | 7 | 200 |  | 4700 |  | 200 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 2 | 32.3333 | 200 |  | 1200 |  | 200 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 2 | 7 | 200 |  | 4700 |  | 200 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 |  |  |  | 2 | 10 | 300 | 168 | 500 | 168 | 300 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
13.a.1 | Reinft. For Wall 200mm thk. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 |  |  |  | 8 | 32.3333 | 300 |  | 1400 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 |  |  |  | 8 | 6.25 | 400 |  | 4450 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 |  |  |  | 8 | 6.25 | 400 |  | 950 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 |  |  |  | 4 | 20 | 300 |  | 118 |  | 300 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
13.b | Reinft. For Footing (4800x1150) |  |  |  |  | 6 | [6 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 6 | 32.3333 | 150 |  | 1050 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 6 | 6.75 | 150 |  | 4700 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 6 | 32.3333 | 150 |  | 1050 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 6 | 6.75 | 150 |  | 4700 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 |  |  |  | 6 | 10 | 300 | 168 | 500 | 168 | 300 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
13.b.1 | Reinft. For Wall 200mm thk. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 |  |  |  | 24 | 32.3333 | 300 |  | 1400 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 |  |  |  | 24 | 6.25 | 400 |  | 4450 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 |  |  |  | 24 | 6.25 | 400 |  | 950 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 |  |  |  | 12 | 20 | 300 |  | 118 |  | 300 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
14 | Reinft. For R.C.C. Planter BH-01 & GYM | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14.a | Reinft. For Footing (4800x1300) |  |  |  |  | 2 | [6 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 2 | 32.3333 | 150 |  | 1200 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 2 | 7 | 150 |  | 4700 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 2 | 32.3333 | 150 |  | 1200 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 2 | 7 | 150 |  | 4700 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 |  |  |  | 2 | 10 | 300 | 168 | 500 | 168 | 300 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
14.a.1 | Reinft. For Wall 200mm thk. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 |  |  |  | 8 | 32.3333 | 300 |  | 1400 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 |  |  |  | 8 | 6.25 | 400 |  | 4450 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 |  |  |  | 8 | 6.25 | 400 |  | 950 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 |  |  |  | 4 | 20 | 300 |  | 118 |  | 300 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
14.b | Reinft. For Footing (4800x1150) |  |  |  |  | 6 | [6 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 6 | 32.3333 | 150 |  | 1050 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 6 | 6.75 | 150 |  | 4700 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 |  |  |  | 6 | 32.3333 | 150 |  | 1050 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 |  |  |  | 6 | 6.75 | 150 |  | 4700 |  | 150 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 |  |  |  | 6 | 10 | 300 | 168 | 500 | 168 | 300 | #REF! |  | 0 | #REF! | 0 | 0 | 0 | 0 | 0
14.b.1 | Reinft. For Wall 200mm thk. | [11 empty] | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 |  |  |  | 24 | 32.3333 | 300 |  | 1400 |  |  | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 |  |  |  | 24 | 6.25 | 400 |  | 4450 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 |  |  |  | 24 | 6.25 | 400 |  | 950 |  | 400 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 |  |  |  | 12 | 20 | 300 |  | 118 |  | 300 | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
| Total Length | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0
| wt./mtr.@ | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0.39506 | 0.61728 | 0.888 | 1.5802 | 2.47 | 3.85 | 6.31
| wt. of bars | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0
| Total Wt. | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | #REF! | KG
| Say | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | #REF! | MT
[13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Previous Bill Qty. R.A-2 | [11 empty] | 0 |  | 10.22 | MT | 0 | 0 | 0 | 0 | 0
RA-3rd B.B.S.
1 | Reinft. Detail for Basket Ball Ground (Flooring) (27540x14190)
Bottom Reinft.
| Bottom Main Bar @200C/C | 10 | 200 | U Shape | 1 | 1 | 138.7 | 100 | 14600 | 100 |  |  | 14760 | 490 | - | 2115.175 | - | - | - | - | -
| Bottom Dis. Bar @200C/C | 10 |  | U Shape | 1 | 1 | 71.95 | 100 | 27950 | 100 |  |  | 28110 | 980 | - | 2093.026 | - | - | - | - | -
| Top Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Top Main Bar @200C/C | 10 |  | U Shape | 1 | 1 | 138.7 | 100 | 14600 | 100 |  |  | 14760 | 490 | - | 2115.175 | - | - | - | - | -
| Top Dis. Bar @200C/C | 10 |  | U Shape | 1 | 1 | 71.95 | 100 | 27950 | 100 |  |  | 28110 | 980 | - | 2093.026 | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 1 | 378 | 300 | 55 | 500 | 55 | 300 | 1130 | 0 | - | 427.14 | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Total Length | [6 empty] | 0 | 0 | 0 | 0 | 0 | - |  | 0 | 8843.542 | 0 | 0 | 0 | 0 | 0
| wt./mtr.@ | [6 empty] | 0 | 0 | 0 | 0 | 0 | - |  | 0.39506 | 0.61728 | 0.88889 | 1.5802 | 2.4691 | 3.858 | 6.321
| wt. of bars | [6 empty] | 0 | 0 | 0 | 0 | 0 | - |  | 0 | 5458.9765 | 0 | 0 | 0 | 0 | 0
| Total Wt. | [6 empty] | 0 | 0 | 0 | 0 | 0 | - |  | 5458.9765 | KG
| Say | [6 empty] | 0 | 0 | 0 | 0 | 0 | - |  | 5.459 | MT
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
B | Reinft. Detail for Planter near Reception or west side of Waterbody (drg. No. TU/LA-P-206.1) (30'-35'/32-36) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
B.a | Planter Tie Beam |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
B.a.1 | Longitudianal Axies (tie Beam=230x200) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Longitudianal axies (30'/32-36) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 11160 | 100 |  |  | 11320 | 0 | - | 22.64 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 11160 | 100 |  |  | 11320 | 0 | - | 22.64 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 54.5 | 180 | 150 | 180 | 150 |  | 740 | 0 | 40.33 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1810 | 100 |  |  | 1970 | 0 | - | 3.94 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1810 | 100 |  |  | 1970 | 0 | - | 3.94 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 7.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 5.735 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7530 | 100 |  |  | 7690 | 0 | - | 15.38 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7530 | 100 |  |  | 7690 | 0 | - | 15.38 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 36.35 | 180 | 150 | 180 | 150 |  | 740 | 0 | 26.899 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar (31'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7530 | 100 |  |  | 7690 | 0 | - | 15.38 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7530 | 100 |  |  | 7690 | 0 | - | 15.38 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 36.35 | 180 | 150 | 180 | 150 |  | 740 | 0 | 26.899 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar (31'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1810 | 100 |  |  | 1970 | 0 | - | 3.94 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1810 | 100 |  |  | 1970 | 0 | - | 3.94 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 7.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 5.735 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
6 | Beam (230x200) Bottom Bar (31'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6130 | 100 |  |  | 6290 | 0 | - | 12.58 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6130 | 100 |  |  | 6290 | 0 | - | 12.58 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 29.35 | 180 | 150 | 180 | 150 |  | 740 | 0 | 21.719 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
7 | Beam (230x200) Bottom Bar (32'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6130 | 100 |  |  | 6290 | 0 | - | 12.58 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6130 | 100 |  |  | 6290 | 0 | - | 12.58 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 29.35 | 180 | 150 | 180 | 150 |  | 740 | 0 | 21.719 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
8 | Beam (230x200) Bottom Bar (32'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1940 | 100 |  |  | 2100 | 0 | - | 4.2 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1940 | 100 |  |  | 2100 | 0 | - | 4.2 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.4 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.216 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
9 | Beam (230x200) Bottom Bar (32'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4600 | 100 |  |  | 4760 | 0 | - | 9.52 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4600 | 100 |  |  | 4760 | 0 | - | 9.52 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 21.7 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.058 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
10 | Beam (230x200) Bottom Bar (33'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4600 | 100 |  |  | 4760 | 0 | - | 9.52 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4600 | 100 |  |  | 4760 | 0 | - | 9.52 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 21.7 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.058 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
11 | Beam (230x200) Bottom Bar (33'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1940 | 100 |  |  | 2100 | 0 | - | 4.2 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1940 | 100 |  |  | 2100 | 0 | - | 4.2 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.4 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.216 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
12 | Beam (230x200) Bottom Bar (33'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3070 | 100 |  |  | 3230 | 0 | - | 6.46 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3070 | 100 |  |  | 3230 | 0 | - | 6.46 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 14.05 | 180 | 150 | 180 | 150 |  | 740 | 0 | 10.397 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
13 | Beam (230x200) Bottom Bar (34'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3070 | 100 |  |  | 3230 | 0 | - | 6.46 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3070 | 100 |  |  | 3230 | 0 | - | 6.46 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 14.05 | 180 | 150 | 180 | 150 |  | 740 | 0 | 10.397 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
14 | Beam (230x200) Bottom Bar (34'/32-35) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 5300 | 100 |  |  | 5460 | 0 | - | 10.92 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 5300 | 100 |  |  | 5460 | 0 | - | 10.92 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 25.2 | 180 | 150 | 180 | 150 |  | 740 | 0 | 18.648 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Transvere axies (34/30'-35') |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
15 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 6 | 2 | 100 | 1025 | 100 |  |  | 1185 | 0 | - | 14.22 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 6 | 2 | 100 | 1025 | 100 |  |  | 1185 | 0 | - | 14.22 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 6 | 3.825 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.983 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
16 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 3 | 2 | 100 | 2925 | 100 |  |  | 3085 | 0 | - | 18.51 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 3 | 2 | 100 | 2925 | 100 |  |  | 3085 | 0 | - | 18.51 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 3 | 13.325 | 180 | 150 | 180 | 150 |  | 740 | 0 | 29.582 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
17 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2620 | 100 |  |  | 2780 | 0 | - | 5.56 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2620 | 100 |  |  | 2780 | 0 | - | 5.56 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 11.8 | 180 | 150 | 180 | 150 |  | 740 | 0 | 8.732 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
18 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 3 | 2 | 100 | 2080 | 100 |  |  | 2240 | 0 | - | 13.44 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 3 | 2 | 100 | 2080 | 100 |  |  | 2240 | 0 | - | 13.44 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 3 | 9.1 | 180 | 150 | 180 | 150 |  | 740 | 0 | 20.202 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
17 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1775 | 100 |  |  | 1935 | 0 | - | 3.87 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1775 | 100 |  |  | 1935 | 0 | - | 3.87 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 7.575 | 180 | 150 | 180 | 150 |  | 740 | 0 | 5.606 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
C | Reinft. for Planter South sid of BH-02 (drg. No. TU/LA-P-206.1 & 206.2) ( (15'-19'/20-32) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Longitudianal axies (15'/20-32) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 30260 | 100 |  |  | 30420 | 980 | - | 62.8 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 30260 | 100 |  |  | 30420 | 980 | - | 62.8 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 150 | 180 | 150 | 180 | 150 |  | 740 | 0 | 111 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2250 | 100 |  |  | 2410 | 0 | - | 4.82 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2250 | 100 |  |  | 2410 | 0 | - | 4.82 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 9.95 | 180 | 150 | 180 | 150 |  | 740 | 0 | 7.363 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 7 | 2 | 100 | 1950 | 100 |  |  | 2110 | 0 | - | 29.54 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 7 | 2 | 100 | 1950 | 100 |  |  | 2110 | 0 | - | 29.54 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 7 | 8.45 | 180 | 150 | 180 | 150 |  | 740 | 0 | 43.771 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2200 | 100 |  |  | 2360 | 0 | - | 4.72 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2200 | 100 |  |  | 2360 | 0 | - | 4.72 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 9.7 | 180 | 150 | 180 | 150 |  | 740 | 0 | 7.178 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1700 | 100 |  |  | 1860 | 0 | - | 3.72 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1700 | 100 |  |  | 1860 | 0 | - | 3.72 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 7.2 | 180 | 150 | 180 | 150 |  | 740 | 0 | 5.328 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 12 | 2 | 100 | 1010 | 100 |  |  | 1170 | 0 | - | 28.08 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 12 | 2 | 100 | 1010 | 100 |  |  | 1170 | 0 | - | 28.08 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 3.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 2.775 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Transvere axies (32/15'-19') |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 10725 | 100 |  |  | 10885 | 0 | - | 21.77 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 10725 | 100 |  |  | 10885 | 0 | - | 21.77 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 52.325 | 180 | 150 | 180 | 150 |  | 740 | 0 | 38.721 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
6 | Beam (230x200) Bottom Bar (32/15'-19') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9725 | 100 |  |  | 9885 | 0 | - | 19.77 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9725 | 100 |  |  | 9885 | 0 | - | 19.77 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 47.325 | 180 | 150 | 180 | 150 |  | 740 | 0 | 35.021 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
7 | Beam (230x200) Bottom Bar (31/15'-19') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7965 | 100 |  |  | 8125 | 0 | - | 16.25 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7965 | 100 |  |  | 8125 | 0 | - | 16.25 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 38.525 | 180 | 150 | 180 | 150 |  | 740 | 0 | 28.509 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
8 | Beam (230x200) Bottom Bar (30/15'-18') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6645 | 100 |  |  | 6805 | 0 | - | 13.61 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6645 | 100 |  |  | 6805 | 0 | - | 13.61 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 31.925 | 180 | 150 | 180 | 150 |  | 740 | 0 | 23.625 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
9 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6445 | 100 |  |  | 6605 | 0 | - | 13.21 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6445 | 100 |  |  | 6605 | 0 | - | 13.21 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 30.925 | 180 | 150 | 180 | 150 |  | 740 | 0 | 22.885 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
10 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4950 | 100 |  |  | 5110 | 0 | - | 10.22 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4950 | 100 |  |  | 5110 | 0 | - | 10.22 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 23.45 | 180 | 150 | 180 | 150 |  | 740 | 0 | 17.353 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
11 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3700 | 100 |  | 100 | 3860 | 0 | - | 7.72 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3700 | 100 |  | 100 | 3860 | 0 | - | 7.72 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 17.2 | 180 | 150 | 180 | 150 |  | 740 | 0 | 12.728 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
12 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 12 | 2 | 100 | 3395 | 100 |  |  | 3555 | 0 | - | 85.32 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 12 | 2 | 100 | 3395 | 100 |  |  | 3555 | 0 | - | 85.32 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 15.675 | 180 | 150 | 180 | 150 |  | 740 | 0 | 11.6 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
12 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3395 | 100 |  |  | 3555 | 0 | - | 7.11 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3395 | 100 |  |  | 3555 | 0 | - | 7.11 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 15.675 | 180 | 150 | 180 | 150 |  | 740 | 0 | 11.6 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
13 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4625 | 100 |  |  | 4785 | 0 | - | 9.57 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4625 | 100 |  |  | 4785 | 0 | - | 9.57 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 21.825 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.151 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
14 | Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 11 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 103.686 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 11 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 103.686 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 1 | 13.45 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 16.14 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
D | Reinft. for Planter South side of BH-02 & BH-03 (drg. No. TU/LA-P-206.1) ( (19'-21'/35-40) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Longitudianal axies (40/19'-20') (Beam 230x200) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 3770 | 100 |  |  | 3930 | 0 | - | 15.72 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 3770 | 100 |  |  | 3930 | 0 | - | 15.72 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 17.55 | 180 | 150 | 180 | 150 |  | 740 | 0 | 12.987 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 5905 | 100 |  |  | 6065 | 0 | - | 24.26 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 5905 | 100 |  |  | 6065 | 0 | - | 24.26 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 28.225 | 180 | 150 | 180 | 150 |  | 740 | 0 | 20.887 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6820 | 100 |  |  | 6980 | 0 | - | 27.92 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6820 | 100 |  |  | 6980 | 0 | - | 27.92 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 32.8 | 180 | 150 | 180 | 150 |  | 740 | 0 | 24.272 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6440 | 100 |  |  | 6600 | 0 | - | 26.4 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6440 | 100 |  |  | 6600 | 0 | - | 26.4 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 30.9 | 180 | 150 | 180 | 150 |  | 740 | 0 | 22.866 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar (29/15'-17') | 10 |  | U Shape | 1 | 5 | 2 | 100 | 1010 | 100 |  |  | 1170 | 0 | - | 11.7 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 5 | 2 | 100 | 1010 | 100 |  |  | 1170 | 0 | - | 11.7 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 3.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 2.775 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
E | Reinft. for Road Toe wall outer parapheri (Ref. Drg. No. TU/LA-P-203) (1/F-J), (J/1-9), (9/H-J) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Reinft. (Tie beam) for Road Toe Wall (1/F-J) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1 | Beam (230x200) Bottom Bar (1/F-J) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4585 | 100 |  |  | 4745 | 0 | - | 9.49 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4585 | 100 |  |  | 4745 | 0 | - | 9.49 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 21.625 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.003 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar (1/F-J) | 10 |  | U Shape | 1 | 10 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 154.7 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 10 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 154.7 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 36.575 | 180 | 150 | 180 | 150 |  | 740 | 0 | 27.066 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar (1/F-J) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9785 | 100 |  |  | 9945 | 0 | - | 19.89 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9785 | 100 |  |  | 9945 | 0 | - | 19.89 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 47.625 | 180 | 150 | 180 | 150 |  | 740 | 0 | 35.243 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Reinft. (Tie beam) for Road Toe Wall (1/F-J) | [11 empty] | - |  | - | - | - | - | - | - | -
1 | Beam (230x200) Bottom Bar (J/1-9) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 14160 | 100 |  |  | 14320 | 490 | - | 29.62 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 14160 | 100 |  |  | 14320 | 490 | - | 29.62 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 69.5 | 180 | 150 | 180 | 150 |  | 740 | 0 | 51.43 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar (J/1-9) | 10 |  | U Shape | 1 | 5 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 77.35 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 5 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 77.35 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 36.575 | 180 | 150 | 180 | 150 |  | 740 | 0 | 27.066 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar (J/1-9) | 10 |  | Straight | 1 | 1 | 2 |  | 150 |  |  |  | 150 | 0 | - | 0.3 | - | - | - | - | -
| Top Bar | 10 |  | Straight | 1 | 1 | 2 |  | 150 |  |  |  | 150 | 0 | - | 0.3 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 2 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.48 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Reinft. (Tie beam) for Road Toe Wall (9/H-J) |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1 | Beam (230x200) Bottom Bar (J/1-9) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 8090 | 100 |  |  | 8250 | 0 | - | 16.5 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 8090 | 100 |  |  | 8250 | 0 | - | 16.5 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 39.15 | 180 | 150 | 180 | 150 |  | 740 | 0 | 28.971 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar (J/1-9) | 10 |  | U Shape | 1 | 2 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 30.94 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 30.94 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 36.575 | 180 | 150 | 180 | 150 |  | 740 | 0 | 54.131 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
F | Reinft. For R.C.C. Planter between BH-01 & CanteenPlanter North side of Basket Ball Ground | [11 empty] | - |  | - | - | - | - | - | - | -
F.a | Reinft. For Footing (4800x1300) |  |  |  | 1 | 3 | [6 empty] | - |  | - | - | - | - | - | - | -
| Bottom Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 3 | 32.3333 | 150 | 1200 | 150 |  |  | 1468 | 0 | 142.396 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 3 | 7 | 150 | 4700 | 150 |  |  | 4968 | 0 | 104.328 | - | - | - | - | - | -
| Top Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 3 | 32.3333 | 150 | 1200 | 150 |  |  | 1468 | 0 | 142.396 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 3 | 7 | 150 | 4700 | 150 |  |  | 4968 | 0 | 104.328 | - | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 3 | 6 | 300 | 168 | 500 | 168 | 300 | 1356 | 0 | - | 24.408 | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
F.a.1 | Reinft. For Wall 200mm thk. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| V.Bar @150C/C | 8 |  | L Shape | 1 | 8 | 32.3333 | 250 | 1400 |  |  |  | 1634 | 0 | 422.661 | - | - | - | - | - | -
| H. Bar Binder @200C/C (outer) | 8 |  | U Shape | 1 | 8 | 6.25 | 400 | 4450 | 400 |  |  | 5218 | 0 | 260.9 | - | - | - | - | - | -
|  | 8 |  | U Shape | 1 | 8 | 6.25 | 400 | 950 | 400 |  |  | 1718 | 0 | 85.9 | - | - | - | - | - | -
| spacer | 8 |  | U Shape | 1 | 4 | 14 | 300 | 118 | 300 |  |  | 686 | 0 | 38.416 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
F.b | Reinft. For Footing (4800x1150) |  |  |  | 1 | 6 | [6 empty] | - |  | - | - | - | - | - | - | -
| Bottom Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 6 | 32.3333 | 150 | 1050 | 150 |  |  | 1318 | 0 | 255.692 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 6 | 6.75 | 150 | 4700 | 150 |  |  | 4968 | 0 | 201.204 | - | - | - | - | - | -
| Top Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 6 | 32.3333 | 150 | 1050 | 150 |  |  | 1318 | 0 | 255.692 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 6 | 6.75 | 150 | 4700 | 150 |  |  | 4968 | 0 | 201.204 | - | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 6 | 5 | 300 | 168 | 500 | 168 | 300 | 1356 | 0 | - | 40.68 | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
F.b.1 | Reinft. For Wall 200mm thk. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| V.Bar @150C/C | 8 |  | L Shape | 1 | 24 | 31 | 250 | 1400 |  |  |  | 1634 | 0 | 1215.696 | - | - | - | - | - | -
| H. Bar Binder @200C/C (outer) | 8 |  | U Shape | 1 | 24 | 6.25 | 400 | 4450 | 400 |  |  | 5218 | 0 | 782.7 | - | - | - | - | - | -
|  | 8 |  | U Shape | 1 | 24 | 6.25 | 400 | 950 | 400 |  |  | 1718 | 0 | 257.7 | - | - | - | - | - | -
| spacer | 8 |  | U Shape | 1 | 12 | 14 | 300 | 118 | 300 |  |  | 686 | 0 | 115.248 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
G | Reinft. For R.C.C. Planter between BH-02 & GYM | [11 empty] | - |  | - | - | - | - | - | - | -
G.a | Reinft. For Footing (4800x1300) |  |  |  |  | 2 | [6 empty] | - |  | - | - | - | - | - | - | -
| Bottom Reinft. | [11 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 2 | 32.3333 | 150 | 1200 | 150 |  |  | 1468 | 0 | 94.931 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 2 | 7 | 150 | 4700 | 150 |  |  | 4968 | 0 | 69.552 | - | - | - | - | - | -
| Top Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 2 | 32.3333 | 150 | 1200 | 150 |  |  | 1468 | 0 | 94.931 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 2 | 7 | 150 | 4700 | 150 |  |  | 4968 | 0 | 69.552 | - | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 2 | 6 | 300 | 168 | 500 | 168 | 300 | 1356 | 0 | - | 16.272 | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
G.a.1 | Reinft. For Wall 200mm thk. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| V.Bar @150C/C | 8 |  | L Shape | 1 | 8 | 32.3333 | 250 | 1400 |  |  |  | 1634 | 0 | 422.661 | - | - | - | - | - | -
| H. Bar Binder @200C/C (outer) | 8 |  | U Shape | 1 | 8 | 6.25 | 400 | 4450 | 400 |  |  | 5218 | 0 | 260.9 | - | - | - | - | - | -
|  | 8 |  | U Shape | 1 | 8 | 6.25 | 400 | 950 | 400 |  |  | 1718 | 0 | 85.9 | - | - | - | - | - | -
| spacer | 8 |  | U Shape | 1 | 4 | 14 | 300 | 118 | 300 |  |  | 686 | 0 | 38.416 | - | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
G.b | Reinft. For Footing (4800x1150) |  |  |  | 1 | 6 | [6 empty] | - |  | - | - | - | - | - | - | -
| Bottom Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 6 | 32.3333 | 150 | 1050 | 150 |  |  | 1318 | 0 | 255.692 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 6 | 6.75 | 150 | 4700 | 150 |  |  | 4968 | 0 | 201.204 | - | - | - | - | - | -
| Top Reinft. |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 8 |  | U Shape | 1 | 6 | 32.3333 | 150 | 1050 | 150 |  |  | 1318 | 0 | 255.692 | - | - | - | - | - | -
| Dis.Bar @200C/C | 8 |  | U Shape | 1 | 6 | 6.75 | 150 | 4700 | 150 |  |  | 4968 | 0 | 201.204 | - | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 6 | 6 | 300 | 168 | 500 | 168 | 300 | 1356 | 0 | - | 48.816 | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
G.b.1 | Reinft. For Wall 200mm thk. | [11 empty] | - |  | - | - | - | - | - | - | -
| V.Bar @150C/C | 8 |  | L Shape | 1 | 20 | 32.3333 | 250 | 1400 |  |  |  | 1634 | 0 | 1056.653 | - | - | - | - | - | -
| H. Bar Binder @200C/C (outer) | 8 |  | U Shape | 1 | 20 | 6.25 | 400 | 4450 | 400 |  |  | 5218 | 0 | 652.25 | - | - | - | - | - | -
|  | 8 |  | U Shape | 1 | 20 | 6.25 | 400 | 950 | 400 |  |  | 1718 | 0 | 214.75 | - | - | - | - | - | -
| spacer | 8 |  | U Shape | 1 | 12 | 14 | 300 | 118 | 300 |  |  | 686 | 0 | 115.248 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
H | Reinft. For Waterbody | [11 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Reinft. Detail for Base footing of Waterbody as per drg. No. 5128-6-103 (inner dia. 7.0m), dia. For R.C.C. =20.12+0.2*2+0.6*2=21.72m) | [11 empty] | - |  | - | - | - | - | - | - | -
H.1 | base raft dia. 21.72m | [11 empty] | - |  | - | - | - | - | - | - | -
| Bottom Bar | [11 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 10 |  | L Shape | 1 | 1 | 452 | 100 | 2550 |  |  |  | 2630 | 0 | - | 1188.76 | - | - | - | - | -
| Binder @200C/C | 10 |  | Straight | 1 | 1 | 9.5 |  | 68201 |  |  |  | 68201 | 2450 | - | 671.185 | - | - | - | - | -
| Top Bar |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C | 10 |  | L Shape | 1 | 1 | 452 | 100 | 2550 |  |  |  | 2630 | 0 | - | 1188.76 | - | - | - | - | -
| Binder @200C/C | 10 |  | Straight | 1 | 1 | 9.5 |  | 68201 | 68201 |  |  | 68201 | 2450 | - | 671.185 | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 1 | 202 | 300 | 60 | 500 | 60 | 300 | 1140 | 0 | - | 230.28 | - | - | - | - | -
[5 empty] | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1.2 | Reinft. For Vertical Wall of Waterbody |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
| Vertical Bar @150C/C | 10 |  | L Shape | 1 | 1 | 452 | 150 |  | 920 |  |  | 130 | 0 | - | 58.76 | - | - | - | - | -
| Vertical Bar @150C/C | 10 |  | L Shape | 1 | 1 | 452 | 150 |  | 1260 |  |  | 130 | 0 | - | 58.76 | - | - | - | - | -
| Binder @200C/C for vertical bar | 10 |  | Straight | 1 | 2 | 3.725 |  | 68201 |  |  |  | 68201 | 2450 | - | 526.35 | - | - | - | - | -
| top beam bottom bar | 10 |  | U Shape | 1 | 1 | 452 | 100 | 340 | 100 |  |  | 500 | 0 | - | 226 | - | - | - | - | -
| binder (in beam & in footing) | 8 |  | Straight | 1 | 2 | 4 |  | 68201 |  |  |  | 68201 | 1960 | 561.288 | - | - | - | - | - | -
| spacer | 10 |  | U Shape | 1 | 2 | 68 | 300 | 110 | 300 |  |  | 670 | 0 | - | 91.12 | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Total Length | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 10288.341 | 6994.016 | 207.372 | 0 | 0 | 0 | 0
| wt./mtr.@ | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0.39506 | 0.61728 | 0.88889 | 1.5802 | 2.4691 | 3.858 | 6.321
| wt. of bars | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 4064.5298 | 4317.2938 | 184.3307 | 0 | 0 | 0 | 0
| Total Wt. | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 8566.1543 | KG
| Say | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 8.5662 | MT
[13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| G.Total Steel Work | [13 empty] | 24.2451 | MT
| Till Previous Bill Quantity. | [13 empty] | 24.2451 | MT
R.A.4th Bill
1 | Reinft. for Tie beam for Planter near Waterbody & Reception (22'-26'/32-36) Ref. Drg. No. TU/LA-P-206.1
R.C.C. Work for Planter Tie Beam (230x200)
Longitudianal axies (32/22'-26')
1 | Longitudianal axies (32/22'-26') |  |  |  | 1 | [7 empty] | - |  | - | - | - | - | - | - | -
1.1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9840 | 100 |  |  | 10000 | 0 | - | 20 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9840 | 100 |  |  | 10000 | 0 | - | 20 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 49.05 | 180 | 150 | 180 | 150 |  | 740 | 0 | 36.297 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
1.2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9580 | 100 |  |  | 9740 | 0 | - | 19.48 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9580 | 100 |  |  | 9740 | 0 | - | 19.48 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 47.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 35.335 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar (33/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 8360 | 100 |  |  | 8520 | 0 | - | 34.08 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 8360 | 100 |  |  | 8520 | 0 | - | 34.08 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 41.65 | 180 | 150 | 180 | 150 |  | 740 | 0 | 61.642 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar (34/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6830 | 100 |  |  | 6990 | 0 | - | 27.96 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6830 | 100 |  |  | 6990 | 0 | - | 27.96 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 34 | 180 | 150 | 180 | 150 |  | 740 | 0 | 50.32 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar (35/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 5000 | 100 |  |  | 5160 | 0 | - | 20.64 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 5000 | 100 |  |  | 5160 | 0 | - | 20.64 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 24.85 | 180 | 150 | 180 | 150 |  | 740 | 0 | 36.778 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar (36/22'-26') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3480 | 100 |  |  | 3640 | 0 | - | 7.28 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3480 | 100 |  |  | 3640 | 0 | - | 7.28 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 17.25 | 180 | 150 | 180 | 150 |  | 740 | 0 | 12.765 | - | - | - | - | - | -
5.1 | Beam (230x200) Bottom Bar (36/22'-26') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3740 | 100 |  |  | 3900 | 0 | - | 7.8 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3740 | 100 |  |  | 3900 | 0 | - | 7.8 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 18.55 | 180 | 150 | 180 | 150 |  | 740 | 0 | 13.727 | - | - | - | - | - | -
Transverse Axies
6 | Beam (230x200) Bottom Bar (36/22'-26') | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1080 | 100 |  |  | 1240 | 0 | - | 2.48 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1080 | 100 |  |  | 1240 | 0 | - | 2.48 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 5.25 | 180 | 150 | 180 | 150 |  | 740 | 0 | 3.885 | - | - | - | - | - | -
B | Reinft. for Road Toe Wall (9/H-J)
1 | Beam (230x200) Bottom Bar (9/H-J) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 15.47 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 15.47 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 38.875 | 180 | 150 | 180 | 150 |  | 740 | 0 | 28.768 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar (9/H-J) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1050 | 100 |  |  | 1210 | 0 | - | 2.42 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1050 | 100 |  |  | 1210 | 0 | - | 2.42 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 6.25 | 180 | 150 | 180 | 150 |  | 740 | 0 | 4.625 | - | - | - | - | - | -
C | Reinft. for Road Toe Wall (9/F-H) basket ball ground & BH-03
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 15.47 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7575 | 100 |  |  | 7735 | 0 | - | 15.47 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 38.875 | 180 | 150 | 180 | 150 |  | 740 | 0 | 28.768 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7075 | 100 |  |  | 7235 | 0 | - | 14.47 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7075 | 100 |  |  | 7235 | 0 | - | 14.47 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 36.375 | 180 | 150 | 180 | 150 |  | 740 | 0 | 26.918 | - | - | - | - | - | -
D | Reinft. for Fire Tender Wall (parallel to road) (Tie Beam 230x200)
D.1 | Fire Tender Wall towards BH-07 (Tie Beam 230x200)
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 24895 | 100 |  |  | 25055 | 980 | - | 52.07 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 24895 | 100 |  |  | 25055 | 980 | - | 52.07 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 125.475 | 180 | 150 | 180 | 150 |  | 740 | 0 | 92.852 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 13724 | 100 |  |  | 13884 | 490 | - | 28.748 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 13724 | 100 |  |  | 13884 | 490 | - | 28.748 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 69.62 | 180 | 150 | 180 | 150 |  | 740 | 0 | 51.519 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4293 | 100 |  |  | 4453 | 0 | - | 8.906 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4293 | 100 |  |  | 4453 | 0 | - | 8.906 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 22.465 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.624 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4698 | 100 |  |  | 4858 | 0 | - | 9.716 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4698 | 100 |  |  | 4858 | 0 | - | 9.716 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 24.49 | 180 | 150 | 180 | 150 |  | 740 | 0 | 18.123 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 324 | 100 |  |  | 484 | 0 | - | 0.968 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 324 | 100 |  |  | 484 | 0 | - | 0.968 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 2.62 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.939 | - | - | - | - | - | -
D.2 | Reinft. for green Planter wall BH-07 (west side)
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1309 | 100 |  |  | 1469 | 0 | - | 2.938 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1309 | 100 |  |  | 1469 | 0 | - | 2.938 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 7.545 | 180 | 150 | 180 | 150 |  | 740 | 0 | 5.583 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 26179 | 100 |  |  | 26339 | 980 | - | 54.638 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 26179 | 100 |  |  | 26339 | 980 | - | 54.638 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 131.895 | 180 | 150 | 180 | 150 |  | 740 | 0 | 97.602 | - | - | - | - | - | -
D.3 | Fire Tender Wall towards BH-01
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 10458 | 100 |  |  | 10618 | 0 | - | 21.236 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 10458 | 100 |  |  | 10618 | 0 | - | 21.236 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 53.29 | 180 | 150 | 180 | 150 |  | 740 | 0 | 39.435 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1589 | 100 |  |  | 1749 | 0 | - | 3.498 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1589 | 100 |  |  | 1749 | 0 | - | 3.498 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.945 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.619 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2013 | 100 |  |  | 2173 | 0 | - | 4.346 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2013 | 100 |  |  | 2173 | 0 | - | 4.346 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 11.065 | 180 | 150 | 180 | 150 |  | 740 | 0 | 8.188 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2885 | 100 |  |  | 3045 | 0 | - | 6.09 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2885 | 100 |  |  | 3045 | 0 | - | 6.09 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 15.425 | 180 | 150 | 180 | 150 |  | 740 | 0 | 11.415 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7688 | 100 |  |  | 7848 | 0 | - | 15.696 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7688 | 100 |  |  | 7848 | 0 | - | 15.696 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 39.44 | 180 | 150 | 180 | 150 |  | 740 | 0 | 29.186 | - | - | - | - | - | -
6 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1997 | 100 |  |  | 2157 | 0 | - | 4.314 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1997 | 100 |  |  | 2157 | 0 | - | 4.314 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 10.985 | 180 | 150 | 180 | 150 |  | 740 | 0 | 8.129 | - | - | - | - | - | -
7 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1043 | 100 |  |  | 1203 | 0 | - | 2.406 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1043 | 100 |  |  | 1203 | 0 | - | 2.406 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 6.215 | 180 | 150 | 180 | 150 |  | 740 | 0 | 4.599 | - | - | - | - | - | -
8 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1043 | 100 |  |  | 1203 | 0 | - | 2.406 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1043 | 100 |  |  | 1203 | 0 | - | 2.406 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 6.215 | 180 | 150 | 180 | 150 |  | 740 | 0 | 4.599 | - | - | - | - | - | -
9 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3265 | 100 |  |  | 3425 | 0 | - | 6.85 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3265 | 100 |  |  | 3425 | 0 | - | 6.85 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 17.325 | 180 | 150 | 180 | 150 |  | 740 | 0 | 12.821 | - | - | - | - | - | -
10 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 5100 | 100 |  |  | 5260 | 0 | - | 10.52 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 5100 | 100 |  |  | 5260 | 0 | - | 10.52 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 26.5 | 180 | 150 | 180 | 150 |  | 740 | 0 | 19.61 | - | - | - | - | - | -
D.3.1 | Fire Tender Wall Brick Work between BH-04 & BH-07 near green Planter (triangle type)
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1348 | 100 |  |  | 1508 | 0 | - | 3.016 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1348 | 100 |  |  | 1508 | 0 | - | 3.016 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 7.74 | 180 | 150 | 180 | 150 |  | 740 | 0 | 5.728 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6132 | 100 |  |  | 6292 | 0 | - | 12.584 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 6132 | 100 |  |  | 6292 | 0 | - | 12.584 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 31.66 | 180 | 150 | 180 | 150 |  | 740 | 0 | 23.428 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 232 | 100 |  |  | 392 | 0 | - | 0.784 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 232 | 100 |  |  | 392 | 0 | - | 0.784 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 2.16 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.598 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 8645 | 100 |  |  | 8805 | 0 | - | 17.61 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 8645 | 100 |  |  | 8805 | 0 | - | 17.61 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 44.225 | 180 | 150 | 180 | 150 |  | 740 | 0 | 32.727 | - | - | - | - | - | -
D.4 | Reinft. work for fire tender in green planter between BH-04 & BH-07
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 848 | 100 |  |  | 1008 | 0 | - | 2.016 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 848 | 100 |  |  | 1008 | 0 | - | 2.016 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 5.24 | 180 | 150 | 180 | 150 |  | 740 | 0 | 3.878 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1447 | 100 |  |  | 1607 | 0 | - | 3.214 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1447 | 100 |  |  | 1607 | 0 | - | 3.214 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.235 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.094 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1602 | 100 |  |  | 1762 | 0 | - | 3.524 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1602 | 100 |  |  | 1762 | 0 | - | 3.524 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 9.01 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.667 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 962 | 100 |  |  | 1122 | 0 | - | 2.244 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 962 | 100 |  |  | 1122 | 0 | - | 2.244 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 5.81 | 180 | 150 | 180 | 150 |  | 740 | 0 | 4.299 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4122 | 100 |  |  | 4282 | 0 | - | 8.564 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4122 | 100 |  |  | 4282 | 0 | - | 8.564 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 21.61 | 180 | 150 | 180 | 150 |  | 740 | 0 | 15.991 | - | - | - | - | - | -
6 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 10370 | 100 |  |  | 10530 | 0 | - | 21.06 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 10370 | 100 |  |  | 10530 | 0 | - | 21.06 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 52.85 | 180 | 150 | 180 | 150 |  | 740 | 0 | 39.109 | - | - | - | - | - | -
7 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 167 | 100 |  |  | 327 | 0 | - | 0.654 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 167 | 100 |  |  | 327 | 0 | - | 0.654 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 1.835 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.358 | - | - | - | - | - | -
8 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3961 | 100 |  |  | 4121 | 0 | - | 8.242 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3961 | 100 |  |  | 4121 | 0 | - | 8.242 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 20.805 | 180 | 150 | 180 | 150 |  | 740 | 0 | 15.396 | - | - | - | - | - | -
D.5 | Fire Tender Wall Brick Work connect to BH-04 to green Planter between BH-01 & waterbody
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 15644 | 100 |  |  | 15804 | 490 | - | 32.588 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 15644 | 100 |  |  | 15804 | 490 | - | 32.588 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 79.22 | 180 | 150 | 180 | 150 |  | 740 | 0 | 58.623 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 175 | 100 |  |  | 335 | 0 | - | 0.67 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 175 | 100 |  |  | 335 | 0 | - | 0.67 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 1.875 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.388 | - | - | - | - | - | -
for Fire Tender in Green planter between BH-01 & Waterbody
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1447 | 100 |  |  | 1607 | 0 | - | 3.214 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1447 | 100 |  |  | 1607 | 0 | - | 3.214 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.235 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.094 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1550 | 100 |  |  | 1710 | 0 | - | 3.42 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1550 | 100 |  |  | 1710 | 0 | - | 3.42 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.475 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3380 | 100 |  |  | 3540 | 0 | - | 7.08 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3380 | 100 |  |  | 3540 | 0 | - | 7.08 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 17.9 | 180 | 150 | 180 | 150 |  | 740 | 0 | 13.246 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1447 | 100 |  |  | 1607 | 0 | - | 3.214 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 1447 | 100 |  |  | 1607 | 0 | - | 3.214 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 8.235 | 180 | 150 | 180 | 150 |  | 740 | 0 | 6.094 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3685 | 100 |  |  | 3845 | 0 | - | 7.69 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3685 | 100 |  |  | 3845 | 0 | - | 7.69 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 19.425 | 180 | 150 | 180 | 150 |  | 740 | 0 | 14.375 | - | - | - | - | - | -
6 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4295 | 100 |  |  | 4455 | 0 | - | 8.91 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4295 | 100 |  |  | 4455 | 0 | - | 8.91 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 22.475 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.632 | - | - | - | - | - | -
D.6 | Fire Tender Wall Brick Work BH-01 west corner to Canteen parallel to road betwee canteen & BH-02
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2336 | 100 |  |  | 2496 | 0 | - | 4.992 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 2336 | 100 |  |  | 2496 | 0 | - | 4.992 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 12.68 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.383 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 19953 | 100 |  |  | 20113 | 490 | - | 41.206 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 19953 | 100 |  |  | 20113 | 490 | - | 41.206 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 100.765 | 180 | 150 | 180 | 150 |  | 740 | 0 | 74.566 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar parallel to canteen | 10 |  | U Shape | 1 | 1 | 2 | 100 | 33511 | 100 |  |  | 33671 | 980 | - | 69.302 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 33511 | 100 |  |  | 33671 | 980 | - | 69.302 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 168.555 | 180 | 150 | 180 | 150 |  | 740 | 0 | 124.731 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar parallel to BH-02 towards canteen (east face) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 32481 | 100 |  |  | 32641 | 980 | - | 67.242 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 32481 | 100 |  |  | 32641 | 980 | - | 67.242 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 163.405 | 180 | 150 | 180 | 150 |  | 740 | 0 | 120.92 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4318 | 100 |  |  | 4478 | 0 | - | 8.956 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 4318 | 100 |  |  | 4478 | 0 | - | 8.956 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 22.59 | 180 | 150 | 180 | 150 |  | 740 | 0 | 16.717 | - | - | - | - | - | -
6 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 180 | 100 |  |  | 340 | 0 | - | 0.68 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 180 | 100 |  |  | 340 | 0 | - | 0.68 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 1.9 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.406 | - | - | - | - | - | -
D.7 | Fire Tender Wall Brick Work for Road between BH-02 & Waterbody
D.7.1 | wall towards BH-02 (BH-02 to Gym toilet)
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 19491 | 100 |  |  | 19651 | 490 | - | 40.282 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 19491 | 100 |  |  | 19651 | 490 | - | 40.282 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 98.455 | 180 | 150 | 180 | 150 |  | 740 | 0 | 72.857 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9818 | 100 |  |  | 9978 | 0 | - | 19.956 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9818 | 100 |  |  | 9978 | 0 | - | 19.956 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 50.09 | 180 | 150 | 180 | 150 |  | 740 | 0 | 37.067 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7455 | 100 |  |  | 7615 | 0 | - | 15.23 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 7455 | 100 |  |  | 7615 | 0 | - | 15.23 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 38.275 | 180 | 150 | 180 | 150 |  | 740 | 0 | 28.324 | - | - | - | - | - | -
D.7.2 | fire tender wall towards waterbody planter to arround waterbody to Reception
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 287 | 100 |  |  | 447 | 0 | - | 0.894 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 287 | 100 |  |  | 447 | 0 | - | 0.894 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 2.435 | 180 | 150 | 180 | 150 |  | 740 | 0 | 1.802 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3133 | 100 |  |  | 3293 | 0 | - | 6.586 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 3133 | 100 |  |  | 3293 | 0 | - | 6.586 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 16.665 | 180 | 150 | 180 | 150 |  | 740 | 0 | 12.332 | - | - | - | - | - | -
3 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 33582 | 100 |  |  | 33742 | 980 | - | 69.444 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 33582 | 100 |  |  | 33742 | 980 | - | 69.444 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 168.91 | 180 | 150 | 180 | 150 |  | 740 | 0 | 124.993 | - | - | - | - | - | -
4 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9013 | 100 |  |  | 9173 | 0 | - | 18.346 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 9013 | 100 |  |  | 9173 | 0 | - | 18.346 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 46.065 | 180 | 150 | 180 | 150 |  | 740 | 0 | 34.088 | - | - | - | - | - | -
5 | Beam (230x200) Bottom Bar fire tender wall west side of reception | 10 |  | U Shape | 1 | 1 | 2 | 100 | 14988 | 100 |  |  | 15148 | 490 | - | 31.276 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 14988 | 100 |  |  | 15148 | 490 | - | 31.276 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 75.94 | 180 | 150 | 180 | 150 |  | 740 | 0 | 56.196 | - | - | - | - | - | -
D.8 | Fire Tender Wall Brick Work for Road South side of BH-04 (back side)
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 14175 | 100 |  |  | 14335 | 490 | - | 29.65 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 14175 | 100 |  |  | 14335 | 490 | - | 29.65 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 71.875 | 180 | 150 | 180 | 150 |  | 740 | 0 | 53.188 | - | - | - | - | - | -
D.9 | Fire Tender Wall Brick Work for Road BH-04 (near watebody to basket ball ground planter) to BH-03
1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 60730 | 100 |  |  | 60890 | 2450 | - | 126.68 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 60730 | 100 |  |  | 60890 | 2450 | - | 126.68 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 304.65 | 180 | 150 | 180 | 150 |  | 740 | 0 | 225.441 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar basket ball ground planter to BH-03 corner(front of Gym) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 35203 | 100 |  |  | 35363 | 980 | - | 72.686 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 35203 | 100 |  |  | 35363 | 980 | - | 72.686 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 177.015 | 180 | 150 | 180 | 150 |  | 740 | 0 | 130.991 | - | - | - | - | - | -
Deduct Previous Bill Qty. for Revise
1 | Beam (230x200) Bottom Bar basket ball ground planter to BH-03 corner(front of Gym) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 31350 | 100 |  |  | 31510 | 980 | - | 64.98 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 31350 | 100 |  |  | 31510 | 980 | - | 64.98 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 157.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 116.735 | - | - | - | - | - | -
2 | Beam (230x200) Bottom Bar basket ball ground planter to BH-03 corner(front of Gym) | 10 |  | U Shape | 1 | 1 | 2 | 100 | 42500 | 100 |  |  | 42660 | 1470 | - | 88.26 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 1 | 2 | 100 | 42500 | 100 |  |  | 42660 | 1470 | - | 88.26 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 1 | 213.5 | 180 | 150 | 180 | 150 |  | 740 | 0 | 157.99 | - | - | - | - | - | -
E | Reinft. for Waterbody Raft (Hold Portion)
Reinft.for Waterbody as per drg. No.(Inner dia. 20.12m), dia. For P.C.C. =20.12+0.2*2+0.6*2=21.720m)
base raft dia. 21.72m
release hold area (dia. 18.32m)
| Main Bottom Bar @ 150 C/C | 10 |  | Straight | 1 | 1 | 123.1333 |  | 15166.2 |  |  |  | 15166.2 | 490 | - | 1927.8 | - | - | - | - | -
| Dis. Bottom Bar @ 150 C/C | 10 |  | Straight | 1 | 1 | 123.1333 |  | 15166.2 |  |  |  | 15166.2 | 490 | - | 1927.8 | - | - | - | - | -
| Main Top Bar @ 150 C/C | 10 |  | Straight | 1 | 1 | 123.1333 |  | 15166.2 |  |  |  | 15166.2 | 490 | - | 1927.8 | - | - | - | - | -
| Dis. Top Bar @ 150 C/C | 10 |  | Straight | 1 | 1 | 123.1333 |  | 15166.2 |  |  |  | 15166.2 | 490 | - | 1927.8 | - | - | - | - | -
| Chair | 10 |  | Chair | 1 | 1 | 324 | 300 | 168 | 500 | 168 | 300 | 1356 | 0 | - | 439.344 | - | - | - | - | -
Reinft. For Sump in waterbody for Sump in waterbody (900x900x850) inner size
Base Footing
| Main Bar Top & Bottom | 10 | 150 | U Shape | 5 | 2 | 9 | 100 | 1200 | 100 |  |  | 1360 | 0 | - | 122.4 | - | - | - | - | -
| Dis. Bar Top & Bottom | 10 | 150 | U Shape | 5 | 2 | 9 | 100 | 1200 | 100 |  |  | 1360 | 0 | - | 122.4 | - | - | - | - | -
| Vertical Bar (Wall) (inner side) | 10 | 150 | L Shape | 5 | 4 | 8.3333 | 100 | 1000 |  |  |  | 1080 | 0 | - | 180 | - | - | - | - | -
| Vertical Bar (Wall) (outer side) | 10 | 150 | L Shape | 5 | 4 | 6.3333 | 100 | 1000 |  |  |  | 1080 | 0 | - | 136.8 | - | - | - | - | -
| binder in wall (inner side) | 10 | 150 | L Shape | 5 | 4 | 6.6667 | 100 | 950 |  |  |  | 1030 | 0 | - | 137.333 | - | - | - | - | -
| binder in wall (outer side) | 10 | 150 | L Shape | 5 | 4 | 6.6667 | 100 | 1250 |  |  |  | 1330 | 0 | - | 177.333 | - | - | - | - | -
| Spacer | 10 |  | U Shape | 5 | 4 | 3 | 300 | 130 | 300 |  |  | 690 | 0 | - | 41.4 | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
Reinft. For Sump in waterbody for Filter Pit in waterbody (2000x2000x1800) inner size
Base Footing
| Main Bar Top & Bottom | 10 | 150 | U Shape | 1 | 2 | 16.3333 | 100 | 2300 | 100 |  |  | 2460 | 0 | - | 80.36 | - | - | - | - | -
| Dis. Bar Top & Bottom | 10 | 150 | U Shape | 1 | 2 | 16.3333 | 100 | 2300 | 100 |  |  | 2460 | 0 | - | 80.36 | - | - | - | - | -
| Vertical Bar (Wall) (inner side) | 10 | 150 | L Shape | 1 | 4 | 10.3333 | 100 | 1950 |  |  |  | 2030 | 0 | - | 83.907 | - | - | - | - | -
| Vertical Bar (Wall) (outer side) | 10 | 150 | L Shape | 1 | 4 | 8 | 100 | 1950 |  |  |  | 2030 | 0 | - | 64.96 | - | - | - | - | -
| binder in wall (inner side) | 10 | 150 | L Shape | 1 | 4 | 13 | 100 | 2050 |  |  |  | 2130 | 0 | - | 110.76 | - | - | - | - | -
| binder in wall (outer side) | 10 | 150 | L Shape | 1 | 4 | 13 | 100 | 2350 |  |  |  | 2430 | 0 | - | 126.36 | - | - | - | - | -
| Spacer | 10 |  | U Shape | 1 | 4 | 6 | 300 | 130 | 300 |  |  | 690 | 0 | - | 16.56 | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Total Length | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 2447.598 | 12331.161 | 0 | 0 | 0 | 0 | 0
| wt./mtr.@ | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0.39506 | 0.61728 | 0.88889 | 1.5802 | 2.4691 | 3.858 | 6.321
| wt. of bars | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 966.9523 | 7611.8278 | 0 | 0 | 0 | 0 | 0
| Total Wt. | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 8578.7801 | KG
| Say | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 8.5788 | MT
[13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| G.Total Reinft. Work (Previous + This Bill) | [13 empty] | 32.8239 | MT
R.A.5th Bill
1 | R.C.C. Tie Beam (230x200) for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22) (230x200)
R.C.C. Work for Planter Tie Beam (230x200)
1 | longitudianal axies
1.1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6260 | 100 |  |  | 6420 | 0 | - | 25.68 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6260 | 100 |  |  | 6420 | 0 | - | 25.68 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 32.3 | 180 | 150 | 180 | 150 |  | 740 | 0 | 47.804 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
1.2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1750 | 100 |  |  | 1910 | 0 | - | 7.64 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1750 | 100 |  |  | 1910 | 0 | - | 7.64 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 9.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 14.43 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
1.3 | Beam (230x200) Bottom Bar (33/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 4935 | 100 |  |  | 5095 | 0 | - | 20.38 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 4935 | 100 |  |  | 5095 | 0 | - | 20.38 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 25.675 | 180 | 150 | 180 | 150 |  | 740 | 0 | 37.999 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
1.4 | Beam (230x200) Bottom Bar (34/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1750 | 100 |  |  | 1910 | 0 | - | 7.64 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1750 | 100 |  |  | 1910 | 0 | - | 7.64 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 9.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 14.43 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
2 | R.C.C. Tie Beam (230x200) for Green Planter north side of BH-04 (under Transfer Slab) Drg. No. TU/LA-P-206.2 (36'-37'/26-22) (230x200) | [11 empty] | - |  | - | - | - | - | - | - | -
| R.C.C. Work for Planter Tie Beam (230x200) | [11 empty] | - |  | - | - | - | - | - | - | -
2 | longitudianal axies | [11 empty] | - |  | - | - | - | - | - | - | -
2.1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6260 | 100 |  |  | 6420 | 0 | - | 25.68 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6260 | 100 |  |  | 6420 | 0 | - | 25.68 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 32.3 | 180 | 150 | 180 | 150 |  | 740 | 0 | 47.804 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
2.2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 6.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.99 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
2.3 | Beam (230x200) Bottom Bar (33/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 4935 | 100 |  |  | 5095 | 0 | - | 20.38 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 4935 | 100 |  |  | 5095 | 0 | - | 20.38 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 25.675 | 180 | 150 | 180 | 150 |  | 740 | 0 | 37.999 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
2.4 | Beam (230x200) Bottom Bar (34/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 6.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.99 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3 | R.C.C. Tie Beam (230x200) for Green Planter West side of BH-02 under transfer slab (Drg. No. TU/LA-P-206.1) (7'-14'/32-33) | [11 empty] | - |  | - | - | - | - | - | - | -
| R.C.C. Work for Planter Tie Beam (230x200) | [11 empty] | - |  | - | - | - | - | - | - | -
3 | longitudianal axies | [11 empty] | - |  | - | - | - | - | - | - | -
3.1 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6260 | 100 |  |  | 6420 | 0 | - | 25.68 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 6260 | 100 |  |  | 6420 | 0 | - | 25.68 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 32.3 | 180 | 150 | 180 | 150 |  | 740 | 0 | 47.804 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.2 | Beam (230x200) Bottom Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 6.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.99 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.3 | Beam (230x200) Bottom Bar (33/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 4935 | 100 |  |  | 5095 | 0 | - | 20.38 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 4935 | 100 |  |  | 5095 | 0 | - | 20.38 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 25.675 | 180 | 150 | 180 | 150 |  | 740 | 0 | 37.999 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.4 | Beam (230x200) Bottom Bar (34/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 6.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.99 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.5 | Beam (230x200) Bottom Bar (33/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 3035 | 100 |  |  | 3195 | 0 | - | 12.78 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 3035 | 100 |  |  | 3195 | 0 | - | 12.78 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 16.175 | 180 | 150 | 180 | 150 |  | 740 | 0 | 23.939 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.6 | Beam (230x200) Bottom Bar (34/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 6.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.99 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.7 | Beam (230x200) Bottom Bar (33/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 2810 | 100 |  |  | 2970 | 0 | - | 11.88 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 2810 | 100 |  |  | 2970 | 0 | - | 11.88 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 15.05 | 180 | 150 | 180 | 150 |  | 740 | 0 | 22.274 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
3.6 | Beam (230x200) Bottom Bar (34/22'-26') | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Top Bar | 10 |  | U Shape | 1 | 2 | 2 | 100 | 1150 | 100 |  |  | 1310 | 0 | - | 5.24 | - | - | - | - | -
| Stirrups @200C/C (180x150) | 8 |  | Rectangle | 1 | 2 | 6.75 | 180 | 150 | 180 | 150 |  | 740 | 0 | 9.99 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
4 | Reinft. Detail for Chess Table (1440x1440) | [11 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @200C/C | 8 |  | U Shape | 10 | 1 | 7.95 | 50 | 1390 | 50 |  |  | 1458 | 0 | 115.911 | - | - | - | - | - | -
| Dis. Bar @200C/C | 8 |  | U Shape | 10 | 1 | 7.95 | 50 | 1390 | 50 |  |  | 1458 | 0 | 115.911 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5 | Reinft. For Seprate Beam (385x275) | [11 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5.1 | Form Work C/S Beam (385x275) for seprate seat under transfer slab of BH-03 towards Basket Ball Ground | [11 empty] | - |  | - | - | - | - | - | - | -
| Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 4 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 37.704 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 4 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 37.704 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 4 | 15.75 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 75.6 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5.2 | Reinft. for Beam (385x275) for seprate seat near Basket Ball Ground | [11 empty] | - |  | - | - | - | - | - | - | -
| Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 2 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 18.852 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 2 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 18.852 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 2 | 15.75 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 37.8 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5.3 | Reinft. for Beam (385x275) for seprate seat near Basket Ball Ground | [11 empty] | - |  | - | - | - | - | - | - | -
| Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 6 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 56.556 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 6 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 56.556 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 6 | 15.75 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 113.4 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5.4 | Form Work C/S Beam (385x275) for seprate seat under transfer slab of BH-04 towards Waterbody | [11 empty] | - |  | - | - | - | - | - | - | -
| Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 7 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 65.982 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 7 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 65.982 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 7 | 15.75 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 132.3 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5.5 | Reinft. Detail for Beam (385x275) for seprate seat under transfer slab of BH-01 towards Canteen | [11 empty] | - |  | - | - | - | - | - | - | -
| Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 6 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 56.556 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 6 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 56.556 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 6 | 15.75 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 113.4 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
5.6 | Reinft. Detail for Beam (385x275) for seprate seat at waterbody | [11 empty] | - |  | - | - | - | - | - | - | -
| Beam (385x275) Seat) Bottom Bar | 12 |  | U Shape | 1 | 8 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 75.408 | - | - | - | -
| Top Bar | 12 |  | U Shape | 1 | 8 | 3 | 120 | 2950 | 120 |  |  | 3142 | 0 | - | - | 75.408 | - | - | - | -
| Stirrups @200C/C (335x225) | 8 |  | Rectangle | 1 | 8 | 15.75 | 335 | 225 | 335 | 225 |  | 1200 | 0 | 151.2 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Total Length | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1247.944 | 419.12 | 622.116 | 0 | 0 | 0 | 0
| wt./mtr.@ | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | 6.31
| wt. of bars | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 492.9379 | 258.597 | 552.439 | 0 | 0 | 0 | 0
| Total Wt. | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1303.9739 | KG
| Say | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1.304 | MT
[13 empty] | - |  | - | - | - | - | - | - | -
| Previous Bill Qty. | [13 empty] | 33.79 | MT | 5th R.A.
[13 empty] | - |  | - | - | - | - | - | - | -
| R.A.6th | [11 empty] | - |  | - | - | - | - | - | - | -
| Reinft. For Light Pole Foundation near Baket Ball Ground | [11 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Footing for Light Pole (900x900) | [11 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @200C/C | 10 |  | U Shape | 1 | 2 | 5 | 150 | 800 | 150 |  |  | 1060 | 0 | - | 10.6 | - | - | - | - | -
| Dis. Bar @200C/C | 10 |  | U Shape | 1 | 2 | 5 | 150 | 800 | 150 |  |  | 1060 | 0 | - | 10.6 | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Pedestal Vertical Bar | 12 |  | L Shape | 1 | 2 | 4 | 150 | 1400 |  |  |  | 1526 | 0 | - | - | 12.208 | - | - | - | -
| Tie (170x170) | 8 |  | Rectangle | 1 | 2 | 8 | 170 | 170 | 170 | 170 |  | 760 | 0 | 12.16 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Reinft. For Foundation of Baket Ball Ground Pole | [11 empty] | - |  | - | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Footing for Light Pole (1500x1500) | [11 empty] | - |  | - | - | - | - | - | - | -
| Main Bar @150C/C (Top & Bottom) | 10 |  | U Shape | 1 | 2 | 8 | 250 | 1400 | 250 |  |  | 1860 | 0 | - | 29.76 | - | - | - | - | -
| Dis. Bar @150C/C (Top & Bottom) | 10 |  | U Shape | 1 | 2 | 8 | 250 | 1400 | 250 |  |  | 1860 | 0 | - | 29.76 | - | - | - | - | -
| side bar for support | 10 |  | L Shape | 1 | 2 | 2 |  | 5600 |  |  |  | 5580 | 0 | - | 22.32 | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Pedestal Vertical Bar | 12 |  | L Shape | 1 | 2 | 4 | 150 | 2225 |  |  |  | 2351 | 0 | - | - | 18.808 | - | - | - | -
| Tie (420x420) | 8 |  | Rectangle | 1 | 2 | 15.8333 | 420 | 420 | 420 | 420 |  | 1760 | 0 | 55.733 | - | - | - | - | - | -
| (148x148) | 8 |  | Rectangle | 1 | 2 | 8 | 148 | 420 | 148 | 420 |  | 1216 | 0 | 19.456 | - | - | - | - | - | -
[13 empty] | - |  | - | - | - | - | - | - | -
| Total Length | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 87.349 | 103.04 | 31.016 | 0 | 0 | 0 | 0
| wt./mtr.@ | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | 6.31
| wt. of bars | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 34.5029 | 63.5757 | 27.5422 | 0 | 0 | 0 | 0
| Total Wt. | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 125.6207 | KG
| Say | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0.12562 | MT
| G.Total Qty. | [11 empty] | - |  | 33.9156 | MT | - | - | - | - | -
Note on B775: SHOW RECORD

## BBS RA2 (hidden)
Gannon Dunkerley & Co. Ltd.
Project : Hardscaping work for Thapar University Patiala
Sub. :- Bar Bending Schedule | [14 empty] | Date : | 2017-04-16
S. N. | Particulars/Description | Dia Of Bar | No Of Member | No. of Bars/ Member | Length of Bars (mm) |  |  |  |  | Bend Ded. | Cutting Length Of Bar in Mtr. | Dia of Bars
[5 empty] | A | B | C | D | E |  |  | 8 | 10 | 12 | 16 | 20 | 25 | 32
A.1 | Reinft. For Tie Beam on Planter
1 | Reinft. for Planter (2-6/28'-31') Tie Beam (Near BH-01 west side) | [8 empty] | 0
1.a | Longitudianal Axies (tie Beam=230x200)
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3610 |  | 100 | 2 | 3.77 | 0 | 7.54 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3610 |  | 100 | 2 | 3.77 | 0 | 7.54 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 19.05 |  |  | 820 |  |  | 5 | 0.74 | 14.097 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1610 |  | 100 | 2 | 1.77 | 0 | 7.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1610 |  | 100 | 2 | 1.77 | 0 | 7.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 9.05 |  |  | 820 |  |  | 5 | 0.74 | 13.394 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 2.48 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 2.48 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 6.4 |  |  | 820 |  |  | 5 | 0.74 | 4.736 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 780 |  | 100 | 2 | 0.94 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 780 |  | 100 | 2 | 0.94 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 5.15 |  |  | 820 |  |  | 5 | 0.74 | 3.811 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 1910 |  | 100 | 2 | 2.07 | 0 | 12.42 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 1910 |  | 100 | 2 | 2.07 | 0 | 12.42 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 10.55 |  |  | 820 |  |  | 5 | 0.74 | 23.421 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2510 |  | 100 | 2 | 2.67 | 0 | 5.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2510 |  | 100 | 2 | 2.67 | 0 | 5.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 13.55 |  |  | 820 |  |  | 5 | 0.74 | 10.027 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 8.15 |  |  | 820 |  |  | 5 | 0.74 | 6.031 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 5940 |  | 100 | 2 | 6.1 | 0 | 12.2 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 5940 |  | 100 | 2 | 6.1 | 0 | 12.2 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 31.05 |  |  | 820 |  |  | 5 | 0.74 | 22.977 | 0 | 0 | 0 | 0 | 0 | 0
1.b | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2920 |  | 100 | 2 | 3.08 | 0 | 6.16 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2920 |  | 100 | 2 | 3.08 | 0 | 6.16 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 11.5625 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 7.53 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 7.53 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 6.475 |  |  | 820 |  |  | 5 | 0.74 | 14.3745 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 8.177 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 6.725 |  |  | 820 |  |  | 5 | 0.74 | 9.953 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2695 |  | 100 | 2 | 2.855 | 0 | 11.42 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2695 |  | 100 | 2 | 2.855 | 0 | 11.42 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 14.475 |  |  | 820 |  |  | 5 | 0.74 | 21.423 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2695 |  | 100 | 2 | 2.855 | 0 | 11.42 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2695 |  | 100 | 2 | 2.855 | 0 | 11.42 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 14.475 |  |  | 820 |  |  | 5 | 0.74 | 21.423 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 8.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 8.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 16.354 | 0 | 0 | 0 | 0 | 0 | 0
1.a | Reinft. for Planter (2-6/28'-31') Tie Beam (Near BH-01 west side) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6840 |  | 100 | 2 | 7 | 0 | 14 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6840 |  | 100 | 2 | 7 | 0 | 14 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 35 |  |  | 820 |  |  | 5 | 0.74 | 25.9 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1740 |  | 100 | 2 | 1.9 | 0 | 3.8 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1740 |  | 100 | 2 | 1.9 | 0 | 3.8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 10 |  |  | 820 |  |  | 5 | 0.74 | 7.4 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4610 |  | 100 | 2 | 4.77 | 0 | 9.54 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4610 |  | 100 | 2 | 4.77 | 0 | 9.54 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 24.05 |  |  | 820 |  |  | 5 | 0.74 | 17.797 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 5570 |  | 100 | 2 | 5.73 | 0 | 11.46 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 5570 |  | 100 | 2 | 5.73 | 0 | 11.46 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 28.85 |  |  | 820 |  |  | 5 | 0.74 | 21.349 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 780 |  | 100 | 2 | 0.94 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 780 |  | 100 | 2 | 0.94 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 4.9 | 100 |  | 820 |  |  | 5 | 0.84 | 4.116 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 3815 |  | 100 | 2 | 3.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 3815 |  | 100 | 2 | 3.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 20.075 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1980 |  | 100 | 2 | 2.14 | 0 | 4.28 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1980 |  | 100 | 2 | 2.14 | 0 | 4.28 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 10.9 |  |  | 820 |  |  | 5 | 0.74 | 8.066 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 7070 |  | 100 | 2 | 7.23 | 0 | 14.46 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 7070 |  | 100 | 2 | 7.23 | 0 | 14.46 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 36.35 |  |  | 820 |  |  | 5 | 0.74 | 26.899 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 8870 |  | 100 | 2 | 9.03 | 0 | 18.06 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 8870 |  | 100 | 2 | 9.03 | 0 | 18.06 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 45.35 |  |  | 820 |  |  | 5 | 0.74 | 33.559 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6215 |  | 100 | 2 | 6.375 | 0 | 12.75 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6215 |  | 100 | 2 | 6.375 | 0 | 12.75 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 32.075 |  |  | 820 |  |  | 5 | 0.74 | 23.7355 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 11100 |  | 100 | 2 | 11.26 | 0 | 22.52 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 11100 |  | 100 | 2 | 11.26 | 0 | 22.52 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 56.85 |  |  | 820 |  |  | 5 | 0.74 | 42.069 | 0 | 0 | 0 | 0 | 0 | 0
1.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 5 | 2 | 100 |  | 1020 |  | 100 | 2 | 1.18 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 5 | 2 | 100 |  | 1020 |  | 100 | 2 | 1.18 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 5 | 6.475 |  |  | 820 |  |  | 5 | 0.74 | 23.9575 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 4 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 17.36 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 4 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 17.36 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 4 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 32.708 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 18.51 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 18.51 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 34.6875 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 23.58 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 23.58 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 20.45 |  |  | 820 |  |  | 5 | 0.74 | 45.399 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (385x275) Sheat) Bottom Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Top Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 4 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 75.6 | 0 | 0 | 0 | 0 | 0 | 0
2 | Reinft. For Tie Beam of between BH-01 & Waterbody north side of BH-04 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 9210 |  | 100 | 2 | 9.37 | 0 | 18.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 9210 |  | 100 | 2 | 9.37 | 0 | 18.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 47.4 |  |  | 820 |  |  | 5 | 0.74 | 35.076 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4380 |  | 100 | 2 | 4.54 | 0 | 9.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4380 |  | 100 | 2 | 4.54 | 0 | 9.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 22.9 |  |  | 820 |  |  | 5 | 0.74 | 16.946 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2980 |  | 100 | 2 | 3.14 | 0 | 12.56 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2980 |  | 100 | 2 | 3.14 | 0 | 12.56 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 15.9 |  |  | 820 |  |  | 5 | 0.74 | 23.532 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1980 |  | 100 | 2 | 2.14 | 0 | 8.56 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1980 |  | 100 | 2 | 2.14 | 0 | 8.56 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 10.9 |  |  | 820 |  |  | 5 | 0.74 | 16.132 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 6.9 |  |  | 820 |  |  | 5 | 0.74 | 5.106 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 3645 |  | 100 | 2 | 3.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 3645 |  | 100 | 2 | 3.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 19.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 5445 |  | 100 | 2 | 5.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 5445 |  | 100 | 2 | 5.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 28.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6180 |  | 100 | 2 | 6.34 | 0 | 12.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6180 |  | 100 | 2 | 6.34 | 0 | 12.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 31.9 |  |  | 820 |  |  | 5 | 0.74 | 23.606 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 1645 |  | 100 | 2 | 1.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 1645 |  | 100 | 2 | 1.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 9.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2880 |  | 100 | 2 | 3.04 | 0 | 6.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2880 |  | 100 | 2 | 3.04 | 0 | 6.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 15.4 |  |  | 820 |  |  | 5 | 0.74 | 11.396 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 1945 |  | 100 | 2 | 2.105 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 1945 |  | 100 | 2 | 2.105 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 9.725 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 7.9 |  |  | 820 |  |  | 5 | 0.74 | 5.846 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4680 |  | 100 | 2 | 4.84 | 0 | 9.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4680 |  | 100 | 2 | 4.84 | 0 | 9.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 24.4 |  |  | 820 |  |  | 5 | 0.74 | 18.056 | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 7910 |  | 100 | 2 | 8.07 | 0 | 16.14 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 7910 |  | 100 | 2 | 8.07 | 0 | 16.14 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 40.9 |  |  | 820 |  |  | 5 | 0.74 | 30.266 | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (385x275) Sheat) Bottom Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Top Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 4 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 75.6 | 0 | 0 | 0 | 0 | 0 | 0
2.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 8 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 20.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 8 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 20.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 8 | 6.475 |  |  | 820 |  |  | 5 | 0.74 | 38.332 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2350 |  | 100 | 2 | 2.51 | 0 | 5.02 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2350 |  | 100 | 2 | 2.51 | 0 | 5.02 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.75 |  |  | 820 |  |  | 5 | 0.74 | 9.435 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.575 |  |  | 820 |  |  | 5 | 0.74 | 9.3055 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 12.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 12.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 23.125 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 2045 |  | 100 | 2 | 2.205 | 0 | 13.23 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 2045 |  | 100 | 2 | 2.205 | 0 | 13.23 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 11.225 |  |  | 820 |  |  | 5 | 0.74 | 24.9195 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 8.177 | 0 | 0 | 0 | 0 | 0 | 0
2.b | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.b.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 8410 |  | 100 | 2 | 8.57 | 0 | 17.14 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 8410 |  | 100 | 2 | 8.57 | 0 | 17.14 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 43.05 |  |  | 820 |  |  | 5 | 0.74 | 31.857 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 7.9 |  |  | 820 |  |  | 5 | 0.74 | 5.846 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 7.9 |  |  | 820 |  |  | 5 | 0.74 | 5.846 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 3645 |  | 100 | 2 | 3.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 3645 |  | 100 | 2 | 3.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 19.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 5180 |  | 100 | 2 | 5.34 | 0 | 10.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 5180 |  | 100 | 2 | 5.34 | 0 | 10.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 26.9 |  |  | 820 |  |  | 5 | 0.74 | 19.906 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 445 |  | 100 | 2 | 0.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 445 |  | 100 | 2 | 0.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 3.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 645 |  | 100 | 2 | 0.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 645 |  | 100 | 2 | 0.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 4.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 6.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 6.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 16.9 |  |  | 820 |  |  | 5 | 0.74 | 12.506 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4380 |  | 100 | 2 | 4.54 | 0 | 9.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4380 |  | 100 | 2 | 4.54 | 0 | 9.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 22.9 |  |  | 820 |  |  | 5 | 0.74 | 16.946 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3380 |  | 100 | 2 | 3.54 | 0 | 7.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3380 |  | 100 | 2 | 3.54 | 0 | 7.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 17.9 |  |  | 820 |  |  | 5 | 0.74 | 13.246 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 3445 |  | 100 | 2 | 3.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 3445 |  | 100 | 2 | 3.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 18.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 7.9 |  |  | 820 |  |  | 5 | 0.74 | 5.846 | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 8180 |  | 100 | 2 | 8.34 | 0 | 16.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 8180 |  | 100 | 2 | 8.34 | 0 | 16.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 41.9 |  |  | 820 |  |  | 5 | 0.74 | 31.006 | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 10210 |  | 100 | 2 | 10.37 | 0 | 20.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 10210 |  | 100 | 2 | 10.37 | 0 | 20.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 52.05 |  |  | 820 |  |  | 5 | 0.74 | 38.517 | 0 | 0 | 0 | 0 | 0 | 0
15 | Beam (385x275) Sheat) Bottom Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Top Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 4 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 75.6 | 0 | 0 | 0 | 0 | 0 | 0
2.b.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 6 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 14.22 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 6 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 14.22 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 6 | 6.125 |  |  | 820 |  |  | 5 | 0.74 | 27.195 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 4 | 2 | 100 |  | 2045 |  | 100 | 2 | 2.205 | 0 | 17.64 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 4 | 2 | 100 |  | 2045 |  | 100 | 2 | 2.205 | 0 | 17.64 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 4 | 11.225 |  |  | 820 |  |  | 5 | 0.74 | 33.226 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 12.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 12.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 23.125 | 0 | 0 | 0 | 0 | 0 | 0
2.c | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.c.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 7190 |  | 100 | 2 | 7.35 | 0 | 14.7 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 7190 |  | 100 | 2 | 7.35 | 0 | 14.7 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 36.95 |  |  | 820 |  |  | 5 | 0.74 | 27.343 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 5180 |  | 100 | 2 | 5.34 | 0 | 10.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 5180 |  | 100 | 2 | 5.34 | 0 | 10.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 26.9 |  |  | 820 |  |  | 5 | 0.74 | 19.906 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 1445 |  | 100 | 2 | 1.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 1445 |  | 100 | 2 | 1.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 8.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 6.9 |  |  | 820 |  |  | 5 | 0.74 | 5.106 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 6.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 6.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 16.9 |  |  | 820 |  |  | 5 | 0.74 | 12.506 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 4 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 26.72 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 4 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 26.72 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 4 | 16.9 |  |  | 820 |  |  | 5 | 0.74 | 50.024 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 2445 |  | 100 | 2 | 2.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 2445 |  | 100 | 2 | 2.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 13.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2180 |  | 100 | 2 | 2.34 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2180 |  | 100 | 2 | 2.34 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.9 |  |  | 820 |  |  | 5 | 0.74 | 8.806 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 6.9 |  |  | 820 |  |  | 5 | 0.74 | 5.106 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4180 |  | 100 | 2 | 4.34 | 0 | 8.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4180 |  | 100 | 2 | 4.34 | 0 | 8.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 21.9 |  |  | 820 |  |  | 5 | 0.74 | 16.206 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 445 |  | 100 | 2 | 0.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 445 |  | 100 | 2 | 0.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 3.225 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 5210 |  | 100 | 2 | 5.37 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 5210 |  | 100 | 2 | 5.37 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 27.05 |  |  | 820 |  |  | 5 | 0.74 | 20.017 | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (385x275) Sheat) Bottom Bar | 12 | 1 | 3 | 100 |  | 2925 |  | 100 | 2 | 3.077 | 0 | 0 | 9.231 | 0 | 0 | 0 | 0
| Top Bar | 12 | 1 | 3 | 100 |  | 2925 |  | 100 | 2 | 3.077 | 0 | 0 | 9.231 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 1 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 18.9 | 0 | 0 | 0 | 0 | 0 | 0
2.c.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 5 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 11.85 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 5 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 11.85 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 5 | 6.125 |  |  | 820 |  |  | 5 | 0.74 | 22.6625 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 6 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 26.04 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 6 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 26.04 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 6 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 49.062 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 6.17 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 6.17 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 11.5625 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 23.58 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 23.58 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 19.85 |  |  | 820 |  |  | 5 | 0.74 | 44.067 | 0 | 0 | 0 | 0 | 0 | 0
3 | Reinft. For Tie Beam of Planter between BH-07 & BH-04 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4610 |  | 100 | 2 | 4.77 | 0 | 9.54 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4610 |  | 100 | 2 | 4.77 | 0 | 9.54 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 24.05 |  |  | 820 |  |  | 5 | 0.74 | 17.797 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 840 |  | 100 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 840 |  | 100 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 5.2 |  |  | 820 |  |  | 5 | 0.74 | 3.848 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2380 |  | 100 | 2 | 2.54 | 0 | 5.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2380 |  | 100 | 2 | 2.54 | 0 | 5.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.9 |  |  | 820 |  |  | 5 | 0.74 | 9.546 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 925 |  | 100 | 2 | 1.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 925 |  | 100 | 2 | 1.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 5.625 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 1205 |  | 100 | 2 | 1.365 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 1205 |  | 100 | 2 | 1.365 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 7.025 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 1585 |  | 100 | 2 | 1.745 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 1585 |  | 100 | 2 | 1.745 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 8.925 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4240 |  | 100 | 2 | 4.4 | 0 | 8.8 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4240 |  | 100 | 2 | 4.4 | 0 | 8.8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 22.2 |  |  | 820 |  |  | 5 | 0.74 | 16.428 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 560 |  | 100 | 2 | 0.72 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 560 |  | 100 | 2 | 0.72 | 0 | 1.44 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 3.8 |  |  | 820 |  |  | 5 | 0.74 | 2.812 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1460 |  | 100 | 2 | 1.62 | 0 | 3.24 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1460 |  | 100 | 2 | 1.62 | 0 | 3.24 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 8.3 |  |  | 820 |  |  | 5 | 0.74 | 6.142 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4240 |  | 100 | 2 | 4.4 | 0 | 8.8 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4240 |  | 100 | 2 | 4.4 | 0 | 8.8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 22.2 |  |  | 820 |  |  | 5 | 0.74 | 16.428 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 3085 |  | 100 | 2 | 3.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 3085 |  | 100 | 2 | 3.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 16.425 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3260 |  | 100 | 2 | 3.42 | 0 | 6.84 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3260 |  | 100 | 2 | 3.42 | 0 | 6.84 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 17.3 |  |  | 820 |  |  | 5 | 0.74 | 12.802 | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 780 |  | 100 | 2 | 0.94 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 780 |  | 100 | 2 | 0.94 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 4.9 |  |  | 820 |  |  | 5 | 0.74 | 3.626 | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6340 |  | 100 | 2 | 6.5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6340 |  | 100 | 2 | 6.5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 32.7 |  |  | 820 |  |  | 5 | 0.74 | 24.198 | 0 | 0 | 0 | 0 | 0 | 0
15 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3580 |  | 100 | 2 | 3.74 | 0 | 7.48 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3580 |  | 100 | 2 | 3.74 | 0 | 7.48 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 18.9 |  |  | 820 |  |  | 5 | 0.74 | 13.986 | 0 | 0 | 0 | 0 | 0 | 0
16 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1380 |  | 100 | 2 | 1.54 | 0 | 3.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 7.9 |  |  | 820 |  |  | 5 | 0.74 | 5.846 | 0 | 0 | 0 | 0 | 0 | 0
17 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 9770 |  | 100 | 2 | 9.93 | 0 | 19.86 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 9770 |  | 100 | 2 | 9.93 | 0 | 19.86 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 49.85 |  |  | 820 |  |  | 5 | 0.74 | 36.889 | 0 | 0 | 0 | 0 | 0 | 0
18 | Beam (385x275) Sheat) Bottom Bar | 12 | 5 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 46.53 | 0 | 0 | 0 | 0
| Top Bar | 12 | 5 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 46.53 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 5 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 94.5 | 0 | 0 | 0 | 0 | 0 | 0
3.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 7 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 16.59 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 7 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 16.59 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 7 | 6.125 |  |  | 820 |  |  | 5 | 0.74 | 31.7275 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.575 |  |  | 820 |  |  | 5 | 0.74 | 9.3055 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1400 |  | 100 | 2 | 1.56 | 0 | 3.12 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1400 |  | 100 | 2 | 1.56 | 0 | 3.12 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 8 |  |  | 820 |  |  | 5 | 0.74 | 5.92 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 5 | 2 | 100 |  | 2080 |  | 100 | 2 | 2.24 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 5 | 2 | 100 |  | 2080 |  | 100 | 2 | 2.24 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 5 | 16 |  |  | 820 |  |  | 5 | 0.74 | 59.2 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 5 | 2 | 100 |  | 2080 |  | 100 | 2 | 2.24 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 5 | 2 | 100 |  | 2080 |  | 100 | 2 | 2.24 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 5 | 11.4 |  |  | 820 |  |  | 5 | 0.74 | 42.18 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 12.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 12.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 23.125 | 0 | 0 | 0 | 0 | 0 | 0
3.b | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.b.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 10570 |  | 100 | 2 | 10.73 | 0 | 21.46 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 10570 |  | 100 | 2 | 10.73 | 0 | 21.46 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 53.85 |  |  | 820 |  |  | 5 | 0.74 | 39.849 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 8340 |  | 100 | 2 | 8.5 | 0 | 17 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 8340 |  | 100 | 2 | 8.5 | 0 | 17 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 42.7 |  |  | 820 |  |  | 5 | 0.74 | 31.598 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 3605 |  | 100 | 2 | 3.765 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 3605 |  | 100 | 2 | 3.765 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 19.025 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6340 |  | 100 | 2 | 6.5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6340 |  | 100 | 2 | 6.5 | 0 | 13 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 32.7 |  |  | 820 |  |  | 5 | 0.74 | 24.198 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 6005 |  | 100 | 2 | 6.165 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 6005 |  | 100 | 2 | 6.165 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 31.025 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 7840 |  | 100 | 2 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 7840 |  | 100 | 2 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 40.2 |  |  | 820 |  |  | 5 | 0.74 | 29.748 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 10070 |  | 100 | 2 | 10.23 | 0 | 20.46 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 10070 |  | 100 | 2 | 10.23 | 0 | 20.46 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 51.35 |  |  | 820 |  |  | 5 | 0.74 | 37.999 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (385x275) Sheat) Bottom Bar | 12 | 3 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 27.918 | 0 | 0 | 0 | 0
| Top Bar | 12 | 3 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 27.918 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 3 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 56.7 | 0 | 0 | 0 | 0 | 0 | 0
3.b.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 6.125 |  |  | 820 |  |  | 5 | 0.74 | 9.065 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 8.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 8.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 16.354 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 15.72 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 15.72 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 19.85 |  |  | 820 |  |  | 5 | 0.74 | 29.378 | 0 | 0 | 0 | 0 | 0 | 0
4 | Reinft. For Tie Beam of Planter North side of BH-02 & Gym | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3080 |  | 100 | 2 | 3.24 | 0 | 6.48 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3080 |  | 100 | 2 | 3.24 | 0 | 6.48 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 16.4 |  |  | 820 |  |  | 5 | 0.74 | 12.136 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 6 | 2 | 100 |  | 1880 |  | 100 | 2 | 2.04 | 0 | 24.48 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 6 | 2 | 100 |  | 1880 |  | 100 | 2 | 2.04 | 0 | 24.48 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 6 | 10.4 |  |  | 820 |  |  | 5 | 0.74 | 46.176 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 5 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 12.4 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 5 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 12.4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 5 | 6.4 |  |  | 820 |  |  | 5 | 0.74 | 23.68 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3680 |  | 100 | 2 | 3.84 | 0 | 7.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3680 |  | 100 | 2 | 3.84 | 0 | 7.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 19.4 |  |  | 820 |  |  | 5 | 0.74 | 14.356 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2780 |  | 100 | 2 | 2.94 | 0 | 5.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2780 |  | 100 | 2 | 2.94 | 0 | 5.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 14.9 |  |  | 820 |  |  | 5 | 0.74 | 11.026 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2180 |  | 100 | 2 | 2.34 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2180 |  | 100 | 2 | 2.34 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.9 |  |  | 820 |  |  | 5 | 0.74 | 8.806 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 2780 |  | 100 | 2 | 2.94 | 0 | 17.64 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 2780 |  | 100 | 2 | 2.94 | 0 | 17.64 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 14.9 |  |  | 820 |  |  | 5 | 0.74 | 33.078 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 3685 |  | 100 | 2 | 3.845 | 0 | 23.07 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 3685 |  | 100 | 2 | 3.845 | 0 | 23.07 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 19.425 |  |  | 820 |  |  | 5 | 0.74 | 43.1235 | 0 | 0 | 0 | 0 | 0 | 0
4.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2620 |  | 100 | 2 | 2.78 | 0 | 5.56 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2620 |  | 100 | 2 | 2.78 | 0 | 5.56 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 14.1 |  |  | 820 |  |  | 5 | 0.74 | 10.434 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 4 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 10.04 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 4 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 10.04 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 4 | 6.475 |  |  | 820 |  |  | 5 | 0.74 | 19.166 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1705 |  | 100 | 2 | 1.865 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1705 |  | 100 | 2 | 1.865 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 9.525 |  |  | 820 |  |  | 5 | 0.74 | 7.0485 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2620 |  | 100 | 2 | 2.78 | 0 | 11.12 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2620 |  | 100 | 2 | 2.78 | 0 | 11.12 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 14.1 |  |  | 820 |  |  | 5 | 0.74 | 20.868 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 650 |  | 100 | 2 | 0.81 | 0 | 1.62 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 650 |  | 100 | 2 | 0.81 | 0 | 1.62 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 4.25 |  |  | 820 |  |  | 5 | 0.74 | 3.145 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4145 |  | 100 | 2 | 4.305 | 0 | 8.61 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4145 |  | 100 | 2 | 4.305 | 0 | 8.61 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 21.725 |  |  | 820 |  |  | 5 | 0.74 | 16.0765 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1180 |  | 100 | 2 | 1.34 | 0 | 2.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 6.9 |  |  | 820 |  |  | 5 | 0.74 | 5.106 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2620 |  | 100 | 2 | 2.78 | 0 | 5.56 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2620 |  | 100 | 2 | 2.78 | 0 | 5.56 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 14.1 |  |  | 820 |  |  | 5 | 0.74 | 10.434 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3840 |  | 100 | 2 | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3840 |  | 100 | 2 | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 20.2 |  |  | 820 |  |  | 5 | 0.74 | 14.948 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2705 |  | 100 | 2 | 2.865 | 0 | 5.73 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2705 |  | 100 | 2 | 2.865 | 0 | 5.73 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 14.525 |  |  | 820 |  |  | 5 | 0.74 | 10.7485 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 7195 |  | 100 | 2 | 7.355 | 0 | 14.71 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 7195 |  | 100 | 2 | 7.355 | 0 | 14.71 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 36.975 |  |  | 820 |  |  | 5 | 0.74 | 27.3615 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4230 |  | 100 | 2 | 4.39 | 0 | 8.78 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4230 |  | 100 | 2 | 4.39 | 0 | 8.78 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 22.15 |  |  | 820 |  |  | 5 | 0.74 | 16.391 | 0 | 0 | 0 | 0 | 0 | 0
13 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 9635 |  | 100 | 2 | 9.795 | 0 | 19.59 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 9635 |  | 100 | 2 | 9.795 | 0 | 19.59 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 49.175 |  |  | 820 |  |  | 5 | 0.74 | 36.3895 | 0 | 0 | 0 | 0 | 0 | 0
14 | Beam (385x275) Sheat) Bottom Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Top Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 4 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 75.6 | 0 | 0 | 0 | 0 | 0 | 0
5 | Reinft. For Tie Beam of Planter between BH-04 & BH-05 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3890 |  | 100 | 2 | 4.05 | 0 | 8.1 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3890 |  | 100 | 2 | 4.05 | 0 | 8.1 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 20.45 |  |  | 820 |  |  | 5 | 0.74 | 15.133 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1660 |  | 100 | 2 | 1.82 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1660 |  | 100 | 2 | 1.82 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 9.3 |  |  | 820 |  |  | 5 | 0.74 | 6.882 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 4 | 2 | 100 |  | 2560 |  | 100 | 2 | 2.72 | 0 | 21.76 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 4 | 2 | 100 |  | 2560 |  | 100 | 2 | 2.72 | 0 | 21.76 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 4 | 13.8 |  |  | 820 |  |  | 5 | 0.74 | 40.848 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4660 |  | 100 | 2 | 4.82 | 0 | 9.64 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4660 |  | 100 | 2 | 4.82 | 0 | 9.64 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 24.3 |  |  | 820 |  |  | 5 | 0.74 | 17.982 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 1925 |  | 100 | 2 | 2.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 1925 |  | 100 | 2 | 2.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 10.625 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 4360 |  | 100 | 2 | 4.52 | 0 | 18.08 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 4360 |  | 100 | 2 | 4.52 | 0 | 18.08 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 22.8 |  |  | 820 |  |  | 5 | 0.74 | 33.744 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 2525 |  | 100 | 2 | 2.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 2525 |  | 100 | 2 | 2.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 13.625 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6160 |  | 100 | 2 | 6.32 | 0 | 12.64 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6160 |  | 100 | 2 | 6.32 | 0 | 12.64 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 31.8 |  |  | 820 |  |  | 5 | 0.74 | 23.532 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1680 |  | 100 | 2 | 1.84 | 0 | 3.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1680 |  | 100 | 2 | 1.84 | 0 | 3.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 9.4 |  |  | 820 |  |  | 5 | 0.74 | 6.956 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4625 |  | 100 | 2 | 4.785 | 0 | 9.57 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4625 |  | 100 | 2 | 4.785 | 0 | 9.57 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 24.125 |  |  | 820 |  |  | 5 | 0.74 | 17.8525 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 11090 |  | 100 | 2 | 11.25 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 11090 |  | 100 | 2 | 11.25 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 56.45 |  |  | 820 |  |  | 5 | 0.74 | 41.773 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (385x275) Sheat) Bottom Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Top Bar | 12 | 4 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 37.224 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 4 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 75.6 | 0 | 0 | 0 | 0 | 0 | 0
5.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 4.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 6.125 |  |  | 820 |  |  | 5 | 0.74 | 9.065 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 6 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 47.16 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 6 | 2 | 100 |  | 3770 |  | 100 | 2 | 3.93 | 0 | 47.16 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 6 | 19.85 |  |  | 820 |  |  | 5 | 0.74 | 88.134 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 7 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 30.38 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 7 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 30.38 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 7 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 57.239 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 6.17 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2925 |  | 100 | 2 | 3.085 | 0 | 6.17 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 15.625 |  |  | 820 |  |  | 5 | 0.74 | 11.5625 | 0 | 0 | 0 | 0 | 0 | 0
6 | Reinft. For Tie Beam of Planter between BH-04 & BH-05 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 970 |  | 100 | 2 | 1.13 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 970 |  | 100 | 2 | 1.13 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 5.85 |  |  | 820 |  |  | 5 | 0.74 | 4.329 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1345 |  | 100 | 2 | 1.505 | 0 | 6.02 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1345 |  | 100 | 2 | 1.505 | 0 | 6.02 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 7.725 |  |  | 820 |  |  | 5 | 0.74 | 11.433 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 5935 |  | 100 | 2 | 6.095 | 0 | 12.19 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 5935 |  | 100 | 2 | 6.095 | 0 | 12.19 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 30.675 |  |  | 820 |  |  | 5 | 0.74 | 22.6995 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1705 |  | 100 | 2 | 1.865 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1705 |  | 100 | 2 | 1.865 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 9.525 |  |  | 820 |  |  | 5 | 0.74 | 7.0485 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.575 |  |  | 820 |  |  | 5 | 0.74 | 9.3055 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2015 |  | 100 | 2 | 2.175 | 0 | 4.35 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2015 |  | 100 | 2 | 2.175 | 0 | 4.35 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.075 |  |  | 820 |  |  | 5 | 0.74 | 8.1955 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2320 |  | 100 | 2 | 2.48 | 0 | 4.96 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2320 |  | 100 | 2 | 2.48 | 0 | 4.96 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.6 |  |  | 820 |  |  | 5 | 0.74 | 9.324 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2010 |  | 100 | 2 | 2.17 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.05 |  |  | 820 |  |  | 5 | 0.74 | 8.177 | 0 | 0 | 0 | 0 | 0 | 0
9 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2315 |  | 100 | 2 | 2.475 | 0 | 4.95 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.575 |  |  | 820 |  |  | 5 | 0.74 | 9.3055 | 0 | 0 | 0 | 0 | 0 | 0
10 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1660 |  | 100 | 2 | 1.82 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1660 |  | 100 | 2 | 1.82 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 9.3 |  |  | 820 |  |  | 5 | 0.74 | 6.882 | 0 | 0 | 0 | 0 | 0 | 0
11 | Beam (230x200) Bottom Bar | 10 | 6 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 14.22 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 6 | 2 | 100 |  | 1025 |  | 100 | 2 | 1.185 | 0 | 14.22 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 6 | 6.125 |  |  | 820 |  |  | 5 | 0.74 | 27.195 | 0 | 0 | 0 | 0 | 0 | 0
12 | Beam (385x275) Sheat) Bottom Bar | 12 | 3 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 27.918 | 0 | 0 | 0 | 0
| Top Bar | 12 | 3 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 27.918 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 3 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 56.7 | 0 | 0 | 0 | 0 | 0 | 0
6.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 2505 |  | 100 | 2 | 2.665 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 2505 |  | 100 | 2 | 2.665 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 13.525 |  |  | 820 |  |  | 5 | 0.74 | 20.017 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 5525 |  | 100 | 2 | 5.685 | 0 | 22.74 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 5525 |  | 100 | 2 | 5.685 | 0 | 22.74 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 28.625 |  |  | 820 |  |  | 5 | 0.74 | 42.365 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 6560 |  | 100 | 2 | 6.72 | 0 | 26.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 6560 |  | 100 | 2 | 6.72 | 0 | 26.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 33.8 |  |  | 820 |  |  | 5 | 0.74 | 50.024 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 7130 |  | 100 | 2 | 7.29 | 0 | 29.16 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 7130 |  | 100 | 2 | 7.29 | 0 | 29.16 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 36.65 |  |  | 820 |  |  | 5 | 0.74 | 54.242 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 6300 |  | 100 | 2 | 6.46 | 0 | 25.84 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 6300 |  | 100 | 2 | 6.46 | 0 | 25.84 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 32.5 |  |  | 820 |  |  | 5 | 0.74 | 48.1 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 4825 |  | 100 | 2 | 4.985 | 0 | 19.94 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 4825 |  | 100 | 2 | 4.985 | 0 | 19.94 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 25.125 |  |  | 820 |  |  | 5 | 0.74 | 37.185 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 13.36 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 3180 |  | 100 | 2 | 3.34 | 0 | 13.36 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 16.9 |  |  | 820 |  |  | 5 | 0.74 | 25.012 | 0 | 0 | 0 | 0 | 0 | 0
7 | Reinft. For Tie Beam of Planter East side of BH-01 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 29730 |  | 100 | 2 | 29.89 | 0 | 119.56 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 29730 |  | 100 | 2 | 29.89 | 0 | 119.56 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 2 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 149.65 |  |  | 820 |  |  | 5 | 0.74 | 221.482 | 0 | 0 | 0 | 0 | 0 | 0
7.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 4.96 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 4.96 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 6.4 |  |  | 820 |  |  | 5 | 0.74 | 9.472 | 0 | 0 | 0 | 0 | 0 | 0
8 | Reinft. For Tie Beam of Planter West side of BH-04 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.a | Planter Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.a.1 | Longitudianal Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 33180 |  | 100 | 2 | 33.34 | 0 | 66.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 33180 |  | 100 | 2 | 33.34 | 0 | 66.68 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 2 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 166.9 |  |  | 820 |  |  | 5 | 0.74 | 123.506 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 30045 |  | 100 | 2 | 30.205 | 0 | 60.41 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 30045 |  | 100 | 2 | 30.205 | 0 | 60.41 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 2 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 151.225 |  |  | 820 |  |  | 5 | 0.74 | 111.9065 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2280 |  | 100 | 2 | 2.44 | 0 | 4.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2280 |  | 100 | 2 | 2.44 | 0 | 4.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 12.4 |  |  | 820 |  |  | 5 | 0.74 | 9.176 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 2.51 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1095 |  | 100 | 2 | 1.255 | 0 | 2.51 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 6.475 |  |  | 820 |  |  | 5 | 0.74 | 4.7915 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 645 |  | 100 | 2 | 0.805 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 645 |  | 100 | 2 | 0.805 | 0 | 1.61 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 4.225 |  |  | 820 |  |  | 5 | 0.74 | 3.1265 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2170 |  | 100 | 2 | 2.33 | 0 | 4.66 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2170 |  | 100 | 2 | 2.33 | 0 | 4.66 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.85 |  |  | 820 |  |  | 5 | 0.74 | 8.769 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 670 |  | 100 | 2 | 0.83 | 0 | 1.66 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 670 |  | 100 | 2 | 0.83 | 0 | 1.66 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 4.35 |  |  | 820 |  |  | 5 | 0.74 | 3.219 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3215 |  | 100 | 2 | 3.375 | 0 | 6.75 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3215 |  | 100 | 2 | 3.375 | 0 | 6.75 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 17.075 |  |  | 820 |  |  | 5 | 0.74 | 12.6355 | 0 | 0 | 0 | 0 | 0 | 0
8.a.2 | Transverse Axies (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 4975 |  | 100 | 2 | 5.135 | 0 | 10.27 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 4975 |  | 100 | 2 | 5.135 | 0 | 10.27 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 25.875 |  |  | 820 |  |  | 5 | 0.74 | 19.1475 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 3140 |  | 100 | 2 | 3.3 | 0 | 6.6 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 3140 |  | 100 | 2 | 3.3 | 0 | 6.6 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 16.7 |  |  | 820 |  |  | 5 | 0.74 | 12.358 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 6615 |  | 100 | 2 | 6.775 | 0 | 13.55 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 6615 |  | 100 | 2 | 6.775 | 0 | 13.55 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 34.075 |  |  | 820 |  |  | 5 | 0.74 | 25.2155 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2180 |  | 100 | 2 | 2.34 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2180 |  | 100 | 2 | 2.34 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.9 |  |  | 820 |  |  | 5 | 0.74 | 8.806 | 0 | 0 | 0 | 0 | 0 | 0
5 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2410 |  | 100 | 2 | 2.57 | 0 | 5.14 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2410 |  | 100 | 2 | 2.57 | 0 | 5.14 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 13.05 |  |  | 820 |  |  | 5 | 0.74 | 9.657 | 0 | 0 | 0 | 0 | 0 | 0
6 | Beam (230x200) Bottom Bar | 10 | 0 | 2 | 100 |  | 880 |  | 100 | 2 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 0 | 2 | 100 |  | 880 |  | 100 | 2 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 0 | 5.4 |  |  | 820 |  |  | 5 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 1410 |  | 100 | 2 | 1.57 | 0 | 3.14 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 1410 |  | 100 | 2 | 1.57 | 0 | 3.14 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 8.05 |  |  | 820 |  |  | 5 | 0.74 | 5.957 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 2150 |  | 100 | 2 | 2.31 | 0 | 4.62 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 2150 |  | 100 | 2 | 2.31 | 0 | 4.62 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 11.75 |  |  | 820 |  |  | 5 | 0.74 | 8.695 | 0 | 0 | 0 | 0 | 0 | 0
9 | Reinft. For Tie Beam for Basket Ball Ground alround on B/W | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.a | Toe Wall Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.a.1 | (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| alround the basket ground | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 14600 |  | 100 | 2 | 14.76 | 0 | 59.04 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 14600 |  | 100 | 2 | 14.76 | 0 | 59.04 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 2 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 74 |  |  | 820 |  |  | 5 | 0.74 | 109.52 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 27950 |  | 100 | 2 | 28.11 | 0 | 112.44 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 27950 |  | 100 | 2 | 28.11 | 0 | 112.44 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 4 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 140.75 |  |  | 820 |  |  | 5 | 0.74 | 208.31 | 0 | 0 | 0 | 0 | 0 | 0
9.a.2 | Tie Beam east side of basket ground for Toe wall | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 3 | 2 | 100 |  | 7575 |  | 100 | 2 | 7.735 | 0 | 46.41 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 3 | 2 | 100 |  | 7575 |  | 100 | 2 | 7.735 | 0 | 46.41 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 3 | 38.875 |  |  | 820 |  |  | 5 | 0.74 | 86.3025 | 0 | 0 | 0 | 0 | 0 | 0
9.b | Toe Wall Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.b.1 | (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (385x275) Sheat) Bottom Bar | 12 | 2 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 18.612 | 0 | 0 | 0 | 0
| Top Bar | 12 | 2 | 3 | 100 |  | 2950 |  | 100 | 2 | 3.102 | 0 | 0 | 18.612 | 0 | 0 | 0 | 0
| Stirrups @200C/C (335x225) | 8 | 2 | 15.75 |  |  | 1280 |  |  | 5 | 1.2 | 37.8 | 0 | 0 | 0 | 0 | 0 | 0
10 | Reinft. For Tie Beam for Basket Ball Ground alround on B/W | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.a | Toe Wall Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.a.1 | (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| alround the basket ground | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 34885 |  | 100 | 2 | 35.045 | 0 | 70.09 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 34885 |  | 100 | 2 | 35.045 | 0 | 70.09 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 2 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 175.425 |  |  | 820 |  |  | 5 | 0.74 | 129.8145 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 14950 |  | 100 | 2 | 15.11 | 0 | 30.22 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 14950 |  | 100 | 2 | 15.11 | 0 | 30.22 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 1 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 75.75 |  |  | 820 |  |  | 5 | 0.74 | 56.055 | 0 | 0 | 0 | 0 | 0 | 0
| Tie Beam for Toe Wall Back side of Basket Ball Ground (east side) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 4 | 2 | 100 |  | 7575 |  | 100 | 2 | 7.735 | 0 | 61.88 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 4 | 2 | 100 |  | 7575 |  | 100 | 2 | 7.735 | 0 | 61.88 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 4 | 38.875 |  |  | 820 |  |  | 5 | 0.74 | 115.07 | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Reinft. For Tie Beam for Road Toe Wall BH-02 to GYM North side | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1.a | Toe Wall Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (tie Beam=230x200) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 8 | 2 | 100 |  | 7575 |  | 100 | 2 | 7.735 | 0 | 123.76 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 8 | 2 | 100 |  | 7575 |  | 100 | 2 | 7.735 | 0 | 123.76 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 8 | 38.875 |  |  | 820 |  |  | 5 | 0.74 | 230.14 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 9900 |  | 100 | 2 | 10.06 | 0 | 20.12 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 9900 |  | 100 | 2 | 10.06 | 0 | 20.12 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 50.5 |  |  | 820 |  |  | 5 | 0.74 | 37.37 | 0 | 0 | 0 | 0 | 0 | 0
11 | Reinft. For Tie Beam for Fire Tender Toe Wall | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.a | Toe Wall Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FIRE TENDER TOE WALL WITH BH-01 (South side) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 31350 |  | 100 | 2 | 31.51 | 0 | 63.02 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 31350 |  | 100 | 2 | 31.51 | 0 | 63.02 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 2 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 157.75 |  |  | 820 |  |  | 5 | 0.74 | 116.735 | 0 | 0 | 0 | 0 | 0 | 0
| FIRE TENDER TOE WALL WITH BH-07 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 1 | 2 | 100 |  | 42500 |  | 100 | 2 | 42.66 | 0 | 85.32 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 1 | 2 | 100 |  | 42500 |  | 100 | 2 | 42.66 | 0 | 85.32 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 3 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 6 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 1 | 213.5 |  |  | 820 |  |  | 5 | 0.74 | 157.99 | 0 | 0 | 0 | 0 | 0 | 0
12 | Reinft. For Tie Beam for Fire Tender Toe Wall | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.a | Toe Wall Tie Beam | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a | for Road Toe Wall BH-01 east side towards water body | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 29730 |  | 100 | 2 | 29.89 | 0 | 119.56 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 29730 |  | 100 | 2 | 29.89 | 0 | 119.56 | 0 | 0 | 0 | 0 | 0
| Lap @50D | 10 | 4 | 4 |  |  | 500 |  |  |  | 0.5 | 0 | 8 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 149.65 |  |  | 820 |  |  | 5 | 0.74 | 221.482 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 4.96 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1080 |  | 100 | 2 | 1.24 | 0 | 4.96 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 6.4 |  |  | 820 |  |  | 5 | 0.74 | 9.472 | 0 | 0 | 0 | 0 | 0 | 0 | 12
b | or Road Toe Wall BH-01 North side towards GYM | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 5505 |  | 100 | 2 | 5.665 | 0 | 22.66 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 5505 |  | 100 | 2 | 5.665 | 0 | 22.66 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 28.525 |  |  | 820 |  |  | 5 | 0.74 | 42.217 | 0 | 0 | 0 | 0 | 0 | 0
2 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1675 |  | 100 | 2 | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1675 |  | 100 | 2 | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 9.375 |  |  | 820 |  |  | 5 | 0.74 | 13.875 | 0 | 0 | 0 | 0 | 0 | 0
3 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 6330 |  | 100 | 2 | 6.49 | 0 | 25.96 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 6330 |  | 100 | 2 | 6.49 | 0 | 25.96 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 32.65 |  |  | 820 |  |  | 5 | 0.74 | 48.322 | 0 | 0 | 0 | 0 | 0 | 0
4 | Beam (230x200) Bottom Bar | 10 | 2 | 2 | 100 |  | 1675 |  | 100 | 2 | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0 | 0
| Top Bar | 10 | 2 | 2 | 100 |  | 1675 |  | 100 | 2 | 1.835 | 0 | 7.34 | 0 | 0 | 0 | 0 | 0
| Stirrups @200C/C (180x150) | 8 | 2 | 9.375 |  |  | 820 |  |  | 5 | 0.74 | 13.875 | 0 | 0 | 0 | 0 | 0 | 0
13 | Reinft. For R.C.C. Planter North side of Basket Ball Ground | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.a | Reinft. For Footing (4800x1300) |  | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 2 | 32.3333 | 200 |  | 1200 |  | 200 | 2 | 1.568 | 101.3973 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 2 | 7 | 200 |  | 4700 |  | 200 | 2 | 5.068 | 70.952 | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 2 | 32.3333 | 200 |  | 1200 |  | 200 | 2 | 1.568 | 101.3973 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 2 | 7 | 200 |  | 4700 |  | 200 | 2 | 5.068 | 70.952 | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 | 2 | 10 | 300 | 168 | 500 | 168 | 300 | 5 | 1.336 | 0 | 26.72 | 0 | 0 | 0 | 0 | 0
13.a.1 | Reinft. For Wall 200mm thk. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 | 8 | 32.3333 | 300 |  | 1400 |  |  | 1 | 1.684 | 435.5947 | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 | 8 | 6.25 | 400 |  | 4450 |  | 400 | 2 | 5.218 | 260.9 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 | 8 | 6.25 | 400 |  | 950 |  | 400 | 2 | 1.718 | 85.9 | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 | 4 | 20 | 300 |  | 118 |  | 300 | 2 | 0.686 | 54.88 | 0 | 0 | 0 | 0 | 0 | 0
13.b | Reinft. For Footing (4800x1150) |  | 6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 6 | 32.3333 | 150 |  | 1050 |  | 150 | 2 | 1.318 | 255.692 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 6 | 6.75 | 150 |  | 4700 |  | 150 | 2 | 4.968 | 201.204 | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 6 | 32.3333 | 150 |  | 1050 |  | 150 | 2 | 1.318 | 255.692 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 6 | 6.75 | 150 |  | 4700 |  | 150 | 2 | 4.968 | 201.204 | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 | 6 | 10 | 300 | 168 | 500 | 168 | 300 | 5 | 1.336 | 0 | 80.16 | 0 | 0 | 0 | 0 | 0
13.b.1 | Reinft. For Wall 200mm thk. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 | 24 | 32.3333 | 300 |  | 1400 |  |  | 1 | 1.684 | 1306.784 | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 | 24 | 6.25 | 400 |  | 4450 |  | 400 | 2 | 5.218 | 782.7 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 | 24 | 6.25 | 400 |  | 950 |  | 400 | 2 | 1.718 | 257.7 | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 | 12 | 20 | 300 |  | 118 |  | 300 | 2 | 0.686 | 164.64 | 0 | 0 | 0 | 0 | 0 | 0
14 | Reinft. For R.C.C. Planter BH-01 & GYM | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14.a | Reinft. For Footing (4800x1300) |  | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 2 | 32.3333 | 150 |  | 1200 |  | 150 | 2 | 1.468 | 94.9307 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 2 | 7 | 150 |  | 4700 |  | 150 | 2 | 4.968 | 69.552 | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 2 | 32.3333 | 150 |  | 1200 |  | 150 | 2 | 1.468 | 94.9307 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 2 | 7 | 150 |  | 4700 |  | 150 | 2 | 4.968 | 69.552 | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 | 2 | 10 | 300 | 168 | 500 | 168 | 300 | 5 | 1.336 | 0 | 26.72 | 0 | 0 | 0 | 0 | 0
14.a.1 | Reinft. For Wall 200mm thk. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 | 8 | 32.3333 | 300 |  | 1400 |  |  | 1 | 1.684 | 435.5947 | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 | 8 | 6.25 | 400 |  | 4450 |  | 400 | 2 | 5.218 | 260.9 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 | 8 | 6.25 | 400 |  | 950 |  | 400 | 2 | 1.718 | 85.9 | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 | 4 | 20 | 300 |  | 118 |  | 300 | 2 | 0.686 | 54.88 | 0 | 0 | 0 | 0 | 0 | 0
14.b | Reinft. For Footing (4800x1150) |  | 6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bottom Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 6 | 32.3333 | 150 |  | 1050 |  | 150 | 2 | 1.318 | 255.692 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 6 | 6.75 | 150 |  | 4700 |  | 150 | 2 | 4.968 | 201.204 | 0 | 0 | 0 | 0 | 0 | 0
| Top Reinft. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main Bar @150C/C | 8 | 6 | 32.3333 | 150 |  | 1050 |  | 150 | 2 | 1.318 | 255.692 | 0 | 0 | 0 | 0 | 0 | 0
| Dis.Bar @200C/C | 8 | 6 | 6.75 | 150 |  | 4700 |  | 150 | 2 | 4.968 | 201.204 | 0 | 0 | 0 | 0 | 0 | 0
| Chair | 10 | 6 | 10 | 300 | 168 | 500 | 168 | 300 | 5 | 1.336 | 0 | 80.16 | 0 | 0 | 0 | 0 | 0
14.b.1 | Reinft. For Wall 200mm thk. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V.Bar @150C/C | 8 | 24 | 32.3333 | 300 |  | 1400 |  |  | 1 | 1.684 | 1306.784 | 0 | 0 | 0 | 0 | 0 | 0
| H. Bar Binder @200C/C (outer) | 8 | 24 | 6.25 | 400 |  | 4450 |  | 400 | 2 | 5.218 | 782.7 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 | 24 | 6.25 | 400 |  | 950 |  | 400 | 2 | 1.718 | 257.7 | 0 | 0 | 0 | 0 | 0 | 0
| spacer | 8 | 12 | 20 | 300 |  | 118 |  | 300 | 2 | 0.686 | 164.64 | 0 | 0 | 0 | 0 | 0 | 0
| Total Length |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 15165 | 5940 | 633 | 0 | 0 | 0 | 0
| wt./mtr.@ |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0.39506 | 0.61728 | 0.888 | 1.5802 | 2.47 | 3.85 | 6.31
| wt. of bars |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 5991 | 3667 | 562 | 0 | 0 | 0 | 0
| Total Wt. |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 10220 | KG
| Say |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 10.22 | MT
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.413