## Invoice
ZAMIL AIR CONDITIONERS INDIA PVT. LTD
(Formerly known as ADVANTEC COILS PVT. LTD.)
SCO-20, 1st Floor, Kalgidhar Enclave,
Kalka Road, Baltana, Zirakpur,PUNJAB
PROFORMA INVOICE
M/s. THAPAR UNIVERSITY |  |  | RUNNING BILL : | RA-02
Bhadson Road, Thapar Technology Campus |  |  | Invoice No.: | T/PB/027/PI/02
Patiala (PUNJAB) 147004 |  |  | Date : | 28/03/2018
|  |  | Job No.: | T/PB/027
LOI REF. NO. : TU/CS/PSJ/17-18/150101/01 |  |  |  | DATED : 09-10-2017
PROJECT : MEP Plumbing Pumps & Plumbing Machinery For Boys Hostel And Learning Block at Thapar University
SR. NO. | DESCRIPTION | PREVIOUS AMOUNT | CURRENT AMOUNT | CUMULATIVE AMOUNT
1 | Whereas Due @100% Against Pro-Rata Supply And Installation Of Material At Site As Per Attached Annexure And MB Summary | 1367330.78 | 8114713.22 | 9482044
BANK INFORMATION :-
BENEFICIARY'S NAME :- Zamil Air Conditionders India Pvt. Ltd.
BANK NAME : AXIS BANK
CASH CREIDIT A/C. NO. : 912030024390832
IFSC CODE : UTIB0001609
BRANCH : Corporate Banking Branch New Delhi
| TOTAL DUE PAYMENT | 1367330.78 | 8114713.22 | 9482044
CIN No. : U74899DL1992PTC050416
PAN No. : AAACA0907F |  |  |  | For Zamil Air Conditioners India Pvt.Ltd
Service Tax No. : AAACA0907FSD008
TIN No. : 03112070603
Authorized Signatory
Regd. Office : 1ST Floor, H-9/B-1, Mohan Cooperative Industrial Estate, Mathura Road, New Delhi-110044

## Summary
PROJECT : THAPAR EXTENSION PATIALA
Project : SITC of plumbing pumps and plumbing machinery of Boys Hostel and Learning Block
| P.O. No. : TU/CS/PSJ/17-18/150101/01 | Date : 09-10-2017
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
GRAND SUMMARY
Sub Head | DESCRIPTION | UoM | SUPPLY AMOUNT |  |  | ITC AMOUNT |  |  | SITC AMOUNT
|  |  | PREVIOUS | THIS BILL | CUMULATIVE | PREVIOUS | THIS BILL | CUMULATIVE | PREVIOUS | THIS BILL | CUMULATIVE
A | Supply, Installing, Testing & Commissioning of Plumbing Machineary and Water Treatment Plant. | ₹ | 1167566 | 3506146.4 | 4673712.4 | 0 | 977113.8 | 977113.8 | 1167566 | 4483260.2 | 5650826.2
B | Supply, Installing, Testing & Commissioning Plumbing System for Boys Hostel | ₹ | 0 | 1773233.5 | 1773233.5 | 0 | 223777.55 | 223777.55 | 0 | 1997011.05 | 1997011.05
C | Variation Items | ₹ | 0 | 181788.6 | 181788.6 | 0 | 146728 | 146728 | 0 | 328516.6 | 328516.6
| GRAND TOTAL ( A+B) | ₹ | 1167566 | 5461168.5 | 6628734.5 | 0 | 1347619.35 | 1347619.35 | 1167566 | 6808787.85 | 7976353.85
[7 empty] | VAT@15.95% |  | 186226.777 |  | 186226.777
[7 empty] | ServiceTax@15% |  |  |  | 0
[7 empty] | LabourCess@1% |  | 13538 |  | 13538
[7 empty] | GST@18% |  |  | 1225581.813 | 1225581.813
[7 empty] | LabourCess@1% |  |  | 80343.6966 | 80343.6966
[7 empty] | Now Payble Amount |  | 1367330.777 | 8114713 | 9482044

## BH Pump Station
THAPAR UNIVERSITY PATIALA
M/s. Zamil Airconditioners India Private Limited
| Services : Supply, Installation, Testing and Commissioning of Plumbing Pumps | [12 empty] | 0
P.O. No. : TU/CS/PSJ/17-18/150101/01
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | SUPPLY RATE | ITC RATE | GST Rates |  | SUPPLY QUANTITY |  |  | SUPPLY AMOUNT |  |  | INSTALLATION QUANTITY |  |  | INSTALLATION AMOUNT
[6 empty] | Supply | ITC | PREV. | THIS BILL | CUM. | PREVIOUS | THIS BILL | CUMULATIVE | PREV. | THIS BILL | CUM. | PREVIOUS | THIS BILL | CUMULATIVE
A) | WATER SUPPLY AND DRAINAGE PUMPS : |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0
|  |  |  | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0
1 | Fixed Speed Hydropneumatic System For Domestic/Flushing OverHead Water Storage Tanks Fillings. |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
| Supply, Installation, Testing & Commissioning of Factory Assembled Compact self contained Hydropneumatic system comprising of following : |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
| Make: Grundfoss / DP or eq. |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
i) | Vertical, Non-self Priming, multistage, inline, centrifugal clear water pumps with cast iron pump housing, S.S 304 impeller and SS-316 shaft, C.I. Base & head, TEFC motor, "F" insulation class, IP55 enclosure class, 2900 RPM (with mechanical seal) Vendor to submit performance curves and technical catalogue of the proposed model for review and information. |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
ii) | MCC panel mounted in frame with auto cut in/cut off controls, manual ride over, sequential change over facilty with interconnecting cables, controllers complete in all respects. |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
iii) | Pressure vessel (200 litres or as of vendors design details) with food grade internal surface painted and food grade pre charged diaphgram with inlet and outlet, pressure switches for auto on/off control, butterfly / ball valve / NRV of suitable pressure rating, vibration isolator, GI "heavy class" suction & delivery header & interconnection piping, control panel with neccessary control cabling etc. complete in all respects. |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
1.1 | For Boys hostel blocks ( Centralized domestic transfer pump ) |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
■ | Capacity/Flow rate - 250 LPM of each pump |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
■ | Pumping Head - 60 Mtr |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
■ | Power Requirement (HP) - 6.0 HP each or as per manufacturer recommendation |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
■ | Location - (Proposed UG Plumbing Pump Room) |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
■ | 1 Set = 3 Nos. Pump (2 Working +1 standby) |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
a) | Supply | Set | 1 | 427778 | 0 | 427736 |  |  | 1 | 1 | 0 | 427736 | 427736 |  | 0 | 0 |  | 0 | 0
b) | Installation, testing & commissioning | Set | 1 | 0 | 29746 |  | 29174 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 |  | 29174 | 29174 | DONE
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
1.2 | For Boys hostel blocks ( Centralized flushing transfer pump ) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Capacity/Flow rate-250 LPM of each pump |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Pumping Head - 60 Mtr |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Power Requirement (HP) - 6.0 HP each or as per manufacturer recommendation |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Location - (Proposed UG Plumbing Pump Room) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | 1 Set = 2 Nos. Pump (1 Working +1 standby) | set | 1 | 303376 | 0 | 297551 |  |  | 1 | 1 | 0 | 297551 | 297551 |  | 0 | 0 |  | 0 | 0
| Installation, Testing & Commissioning | Set | 1 | 0 | 29746 |  | 29174 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 |  | 29174 | 29174 | DONE
1.3 | For Boys hostel blocks ( Irrigation pump) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Capacity/Flow Rate - 450 LPM of each pump |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Pumping Head - 50 Mtr |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Power Requirement (HP) - 7.5 HP each or as per manufacturer recommendation |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | Location - (Proposed UG Plumbing Pump Room) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
■ | 1 Set = 2 Nos. Pump (1 Working +1 standby) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | Supply | Set |  | 394695 | 0 | 387116 | 0 | 0 | 1 | 1 | 0 | 387116 | 387116 |  | 0 | 0 |  | 0 | 0
b) | Installation, testing & commissioning | Set | 1 | 0 | 29746 | 0 | 29174 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 |  | 29174 | 29174 | DONE
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
2 | Variable Speed Hydropneumatic System For Domestic Use ( at terrace for upper 2 floors over each tower ) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Supply, testing, installation, testing & commissioning of Compact self contained Hydropneumatic system comprising of following : |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
i) | Horizontal, multistage, centrifugal clear water pumps with SS-304 casing, S.S 304 impeller and SS-316 shaft, C.I. Base & head TEFC motor (with mechanical seal) Vendor to submit performance curves, dimension detail and technical catalogue of the proposed model for review and information. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
ii) | MCC panel with sequential control with mounted microprocessor PID controller and variable frequency drive (VFD) integrated in a single body or as separate components with pressure sensor transmitter (one dedicated to each pump) minimum two lined LCD display, diodes to indicate pump ready, pump running and fault and capable to communicate with other controllers following MODBUS-RTU or BACNET Class-2 protocol through RS485 port. System should be capable to compensate for frictional losses at lower flows. All alarms should be displayed in the controller. System should be equipped with dry running protection. (Quantity of VFD = 1 No.) complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
iii) | Pre-charged diaphragm pressure vessel with interchangeable membrane, charging connection, connected to outlet header with necessary flanges, gaskets, isolating valves, nuts/bolts etc. complete (size of pressure vessel shall be of suitable capacity or as per manufacturer calculation / recommendation). |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
iv) | Set of accessories such as pressure switches, pressure transducers,valve (butterfly / ball valve & NRV of PN 10 rating i.e. 10 kg / cm2 ) , vibration Isolator, GI "heavy class" suction & delivery header & interconnection piping, level controller, pressure gauge inter connecting power and control cabling etc. complete with Vibration eliminator of required quantities complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
2.1 | For each tower : |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
● | Capacity/Flow Rate - 300 LPM |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
● | Pumping Head - 25-30 Mtr |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
● | Power Requirement (HP) - 3.0 HP each or as per manufacturer recommendation |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
● | Location - Terrace |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
● | 1 Set = 2 Nos. Pump (1 Working +1 standby) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | Supply | Set | 4 | 292344 | 0 | 286731 |  |  | 6 | 6 | 0 | 1720386 | 1720386 |  | 0 | 0 |  | 0 | 0
b) | Installation, Testing & Commissioning | Set | 4 | 0 | 29746 |  | 29174 |  | 0 | 0 | 0 | 0 | 0 |  | 6 | 6 |  | 175044 | 175044 | DONE
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | Providing and fixing of submersible non-clog, open impeller sump pump with vortex impeller connected to TEFC submersible motor for 415 + 10% volts, 3 phase, 50 cycles A.C. power supply with mechanical seal, pump connector unit with rubber diaphragm and bend of the following specifications, MCC panel ( located on near wall) with auto sequential change over with both pumps shut at low level, one pump working at mid level and both pump working with an alarm hooter at high level, including interconnecting cables, piping works, valves, controls etc. all pre set as required complete in all respects. Cost shall included electrical control panel with starter. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
3.1 | Sump Pump Drainage ( Main Pump Room ) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | Discharge : 400 lpm |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
b) | Head : 10 metre |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
c) | HP : 3.0 HP each or as per manufacturer recommendation. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
d) | Casing : Aluminium alloy / C.I |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
e) | Impeller & Shaft: S.S. 410 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
f) | Solid Handling Capacity: 15 mm |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
g) | Length of water proof cable with each pump : 10 meter |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
h) | Length of GI lifting chain with each pump : 5 Meter. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
i) | G.I. heavy class header main of suitable diameter and length |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
j) | Level controller and starter control panel |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
k) | Quantity : 2 Nos. (1 Working +1 Standby) | Set | 1 | 170725 | 28556 | 167447 | 28007 |  | 1 | 1 | 0 | 167447 | 167447 |  | 1 | 1 |  | 28007 | 28007 | done
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | Providing and fixing motorized solenoid valve/rotary actuator (CI body, SS316 disc, EPDM boot seat, SS416 shaft, RPTEF bushing @ PN10 rating) for filling of overhead water tank complete with electrical water level control panel, including by-pass connection for the same dia with manually operated butterfly valve, float valve/ controller and all piping and accessories complete in all respects (Belimo/ Legris make or eq.). |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a. | 50 mm dia | Set | 4 | 41046 | 2380 | 40257 | 2334 |  | 4 | 4 | 0 | 161028 | 161028 |  | 4 | 4 |  | 9336 | 9336 | DONE
b. | 40 mm dia. | Set | 4 | 38595 | 1785 | 37853 | 1750 |  | 6 | 6 | 0 | 227118 | 227118 |  | 6 | 6 |  | 10500 | 10500 | DONE
c. | 32 nn dia | Set |  | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0
[13 empty] | 0 | [5 empty] | 0
5 | Puddle Flange for Water Tanks |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Providing and fixing M.S fabricated hot dipped galvanized coating puddle flange comprising of 600 mm dia long M.S class 'B' pipe (screwed end up to 50 mm & flange for more than 50 mm dia) with 6 mm thick M.S plates of required size including cutting holes in centre of plate, inserting pipe & making welded (Arc) joint complete. Same shall be installed with TEC welded joint in position with reinforcement bars of RCC tank wall/slab including making cutout in shuttering during concrete casting of tank of following diameter complete in all respects . (Location: underground tanks.) |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | 25 mm dia | Each | 6 | 1320 | 238 | 1294 | 233 | 6 | 0 | 6 | 7920 | 0 | 7920 |  | 6 | 6 |  | 1398 | 1398
b) | 50 mm dia | Each | 2 | 1949 | 357 | 1911 | 350 | 2 | 0 | 2 | 3898 | 0 | 3898 |  | 2 | 2 |  | 700 | 700
c) | 80 mm dia | Each | 4 | 2523 | 595 | 2474 | 583 | 1 | 0 | 1 | 2523 | 0 | 2523 |  | 1 | 1 |  | 583 | 583
d) | 100 mm dia | Each | 6 | 4241 | 714 | 4159 | 700 | 5 | 0 | 5 | 21205 | 0 | 21205 |  | 5 | 5 |  | 3500 | 3500
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
6 | WATER TANK COVER |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Providing and fixing 500 mm dia M.S. water tank cover with 40 mm seat and lockable arrangement complete in all respects including all fitting & accessories complete in all respects. | Each | 4 | 4291 | 595 | 4208 | 583 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
7 | G.I VENT PIPE |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Providing and fixing G.I. Vent Pipe class 'B' (medium duty) for R.C.C water storage tanks comprising of 600 mm long vertical pipe, return bend with mosquito grating & cast brass perforated coupling including all associated civil work complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | 150 mm dia | Each | 4 | 1840 | 595 | 1804 | 583 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
8 | M.S. STRUCTURAL WORK |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Providing and fixing M.S. structural work fabricated from standard sections, (MS rounds, angles, channels etc.) including cutting to size, drilling, welding, including cost of fasteners, clamps in RCC structural members as directed, including two or more coats of synthetic paint over one coat of primer after surface preparation including cutting and making good walls complete in all respects. (For pipe works in pump room ) | Kg | 300 | 93 | 24 | 91 | 23 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
9 | Providing and fixing of mosquito overflow grating /Jali of the following diameters including all fittings & accessories complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | 100 mm dia | Each | 4 | 737 | 119 | 722 | 116 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
10 | Providing and fixing forged brass auto air vent valve 10 PN rating including all fitting & accessories complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | 25 mm dia | Each | 4 | 4291 | 179 | 4208 | 175 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
11 | Providing and fixing cast iron butterfly valve (PN 16) complete with 2 nos. matching flanges, bolts, nuts, 3.0 mm thick compressed asbestos gasket complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a) | 50 mm dia | Each | 2 | 3071 | 357 | 3012 | 350 |  | 35 | 35 | 0 | 105420 | 105420 |  | 35 | 35 |  | 12250 | 12250 | done
b) | 80 mm dia | Each | 3 | 4064 | 536 | 3985 | 525 |  | 3 | 3 | 0 | 11955 | 11955 |  | 3 | 3 |  | 1575 | 1575 | done
c) | 100 mm dia | Each | 5 | 4974 | 714 | 4878 | 700 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
12 | EXTERNAL WATER SUPPLY ( BOYS HOSTEL) MAIN LINE FROM PUMP ROOM TO HOSTEL BLOCK BASE | [7 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
A | IRRIGATION SYSTEM | [7 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m or as required complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | Pipes, upto 150 mm dia | Mtr | 940 | 0 | 191 |  | 187 |  | 0 | 0 | 0 | 0 | 0 |  | 560.2 | 560.2 |  | 104757.4 | 104757.4
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 50 mm OD | Mtr | 120 | 259 | 119 | 254 | 116 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
b | 75 mm OD | Mtr | 750 | 466 | 179 | 457 | 175 | 570 | 0.2 | 570.2 | 265620 | 91.4 | 265711.4 |  | 570.2 | 570.2 |  | 99785 | 99785 | DONE
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
b | 20 mm dia. | Each | 7 | 478 | 96 | 468 | 94 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
c | 40 mm dia. | Each | 2 | 1808 | 143 | 1773 | 140 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | Providing, fixing and testing G.I. Pipe (medium class) including painting with two coats of synthetic enamel paint of approved shade.(for G.H. rising above the ground) ) complete in all respects. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 20 mm dia. | Mtr | 10 | 210 | 108 | 205 | 105 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
b | 25 mm dia. | Mtr | 70 | 255 | 119 | 250 | 116 |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged to HDPE tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 65 mm dia. | Each | 3 | 5824 | 447 | 5712 | 438 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” and connected to HDPE tail piece complete in all respects. (Optional of sluice valve) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 65 mm dia. | Each |  | 2097 | 447 | 2056 | 438 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1 | 4291 | 179 | 4208 | 175 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | Internal size 90 cm x 90cm x 100 cm | Each | 5 | 17622 | 5890 | 17283 | 5776 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
b | Internal size 300cm x 300cm x 600 cm | Each | 7 | 5125 | 1400 | 5026 | 1373 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for C.I. & uPVC specials including necessary excavation, shuttering and centring, curing complete. | Cum | 2 | 7356 | 1190 | 7214 | 1167 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| TOTAL IRRIGATION SYSTEM |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
B | FLUSHING SYSTEM |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m or as required complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | Pipes, upto 150 mm dia | Mtr | 1350 | 0 | 191 |  | 187 |  | 0 | 0 | 0 | 0 | 0 |  | 560.2 | 560.2 |  | 104757.4 | 104757.4
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 90 mm OD | Mtr | 750 | 643 | 179 | 630 | 175 | 570 | 0.2 | 570.2 | 366510 | 126 | 366636 |  | 570.2 | 570.2 |  | 99785 | 99785 | DONE
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 40 mm dia. | Each | 7 | 1808 | 119 | 1773 | 116 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | Providing, fixing and testing G.I. Pipe IS 1239 (medium class) with tap off connection from HDPE main pipe with adaptor/ connector etc. and including 4 mm thick Pypekote tape wrapping all around , bitumen paint and covered with 150 mm sand cover all around pipe etc. (for riser to each hostel block ) complete in all respects. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 40 mm dia. | Mtr | 600 | 493 | 143 | 483 | 140 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged to HDPE tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 75 mm dia. | Each | 3 | 6736 | 536 | 6606 | 525 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” and connected to HDPE tail piece complete in all respects. (Optional of sluice valve) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 75 mm dia. | Each |  | 2318 | 536 | 2273 | 525 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1 | 4291 | 238 | 4208 | 233 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | Internal size 90 cm x 90cm x 100 cm | Each | 10 | 17622 | 5890 | 17283 | 5776 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for pipes at junctions etc. including necessary excavation, shuttering and centring, curing complete in all respects. | Cum | 3 | 7356 | 1190 | 7214 | 1167 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
B | TOTAL FLUSHING SYSTEM |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
C | DOMESTIC SYSTEM |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | Pipes, upto 150 mm dia | Mtr | 1350 | 0 | 191 | 0 | 187 |  | 0 | 0 | 0 | 0 | 0 |  | 560.2 | 560.2 |  | 104757.4 | 104757.4
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 110 mm OD | Mtr | 750 | 877 | 238 | 860 | 233 | 570 | 0.2 | 570.2 | 499890 | 172 | 500062 |  | 570.2 | 570.2 |  | 132856.6 | 132856.6 | DONE
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | Providing, fixing and testing G.I. Pipe to IS 1239 (medium class) with tap off connection from HDPE main pipe with adaptor/ connector etc. and including 4 mm thick Pypekote tape wrapping all around , bitumen paint and covered with 150 mm sand cover all around pipe etc. (for riser to each hostel block ) complete in all respects. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 50 mm | Mtr | 600 | 544 | 191 | 533 | 187 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | Disinfecting water mains by flushing with water containing bleaching powder at 0.5gms per litre of water and cleaning the same with fresh water, operation to be repeated three times including getting the samples of water from the disinfected main te |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 110 mm OD | Mtr | 750 | 20 | 24 | 19 | 23 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
b | 50 mm dia. | Mtr | 600 | 14 | 24 | 13 | 23 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
8 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 50mm dia. | Each | 7 | 2682 | 191 | 2630 | 187 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged uPVC /HDPE /CI tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 80 mm dia. | Each | 3 | 6736 | 536 | 6606 | 525 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” complete (Optional of sluice valve) |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | 80 mm dia. | Each |  | 2318 | 536 | 2273 | 525 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1 | 4291 | 238 | 2893 | 233 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect. |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
a | Internal size 90 cm x 90cm x 100 cm | Each | 10 | 17622 | 5890 | 17283 | 5776 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for pipes at junctions etc. including necessary excavation, shuttering and centring, curing complete in all respects. | Cum | 3 | 7356 | 1190 | 7214 | 1167 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| TOTAL DOMESTIC SYSTEM |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| GRAND TOTAL | [9 empty] | 1167566 | 3506146.4 | 4673712.4 |  |  |  | 0 | 977113.8 | 977113.8

## Pumping Machinery
THAPAR UNIVERSITY PATIALA
M/s. Zamil Airconditioners India Private Limited
Services : Supply, Installation, Testing and Commissioning of Plumbing Machinery
P.O. No. : TU/CS/PSJ/17-18/150101/01
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | SUPPLY RATE | ITC RATE | GST Rates |  | SUPPLY QUANTITY |  |  | SUPPLY AMOUNT |  |  | INSTALLATION QUANTITY |  |  | INSTALLATION AMOUNT
[6 empty] | Supply | ITC | PREV. | THIS BILL | CUM. | PREVIOUS | THIS BILL | CUMULATIVE | PREV. | THIS BILL | CUM. | PREVIOUS | THIS BILL | CUMULATIVE
| IMPORTANT NOTES : | [7 empty] | 0
0
| a) The pump shall be capable of developing the required total head at rated capacity for continuous operation. The pumps shall operate satisfactorily at any point on the Head-Discharge (H-Q) characteristic curve over a range of 50% to 130% capacity. The total head capacity curve shall be continuously rising towards the shut off. The shut off head shall be at least 110% of the total head. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| b) All associated piping, valves & other appurtenances shall be paid seperately as per relevant items | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| c) The Tenderer must submit along with his offer, the make and the model of the pump unit proposed by him. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| d) Required power supply would be made available at individual control panels of packaged pumping systems in the pump room and solenoid valves at terrace level. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| e) Wherever mechanical seal has been asked for, it must be `factory fitted` at pump manufacturer`s works. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
1 | HYDROPNEUMATIC SYSTEMS | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
1.1 | Supply, installing, testing and commissioning of clear water Factory Fitted packaged hydropneumatic pumping system for general water supply as per following details: | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Type of Drive - Variable frequency drive for each pump | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| System Capacity | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Maximum System Discharge : 30 M3/hr. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| System Pressure : 6.0 kg/cm2 | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Pumps- 3 Nos (2W+1S) | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Flow of each Pump - 15 M3/hr. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| The packaged unit shall be complete with : | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
1.1 contd. | a) Pumps: Vertical monoblock booster pumpset with mechanical seal | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Material of Construction (M.O.C): Corrosion Resistant in general :Casing — C.I./ Stainless Steel -AISI 304 | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| : Impeller — Stainless Steel -AISI 304 | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| : Shaft — Stainless Steel - AISI 304 | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| : Pump Head — Cast Iron/ Stainless Steel - AISI 304 | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| : Base — Cast Iron | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| : Motor Stool — Cast Iron | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Motor: 2900 RPM; 3Ph 415V 50Hz | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Insulation Class - F | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Protection - IP54 Min. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| b) Pressure Tank: FRP vessel with replacable polyetheruethane (PEU) bladder certified for drinking water. Minimum 8 Bar pressure rating — 1 No. of 200 to 250 Lts. Capacity. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| c) Interconnecting Pipe work, Valves and Vibration Eliminators : Common suction & delivery headers in hot dipped galvanized steel pipes and fittings, Isolating valves, non return valves and vibration eliminators on suction & delivery side of pumps. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| d) Common fabricated base frame, duly painted. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| e) Power and control cabling between panel and pumps. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| f) Accessories like presure guages, pressure transducers etc. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| g) System Control Panel : The system control panel shall be factory built and tested and shall have the following minimum features: | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| i) Fully protected, powder coated metallic housing. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| ii) Complete switchgear, under/over voltage protection, single phase preventors etc. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| iii) VFDs for all the pumps | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| iv) Site programmable application optimised software | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| v) Integrated Modbus interface for BMS compatibility | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| vi) Large graphic display with as easy to use menu. | [7 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| Programmable Control System shall be PLC based, duly authentiated by the Pump Manufacturer. | Set | 1 | 689490 | 29746 | 676252 | 29174 |  | 1 | 1 | 0 | 676252 | 676252 |  | 1 | 1 |  | 29174 | 29174 | PENDING
1.1contd | Details of Equipment offered (To be filled in by the tenderer) | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Pumps | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Make: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Model: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| HP/KW: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| M.O.C : Casing —……………….. : Impeller — …………….. : Shaft — ………………. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Pressure Tank | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Make: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Model: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Capacity | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| M.O.C : Shell —……………….. : Bladder — …………….. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Valves | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Make: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Type: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Size: Suction side —………... Delivery side — ……... NRV — ………………. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Type of Programmable Logic Controller — ………………….. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| The pump Panel shall be also to convese with Building Management System | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Notes: 1) Switchgear and starter ratings are indicative. The Tenderer shall quote for the actual rating required as per the pump model proposed by him. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| 2) Provision for BMS connectivity. The panel should have sufficient no. of potential free contacts for connectivity with Building Management System for monitoring purposes | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| TOTAL for "Hydropnuematic Systems" carried over to SUMMARY | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
2 | SUMP DRAINAGE PUMPS | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
2.1 | Supply, installing, testing and commissioning drainage pumping system in the sump of Under ground Pump Room comprising of the following: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 2 Nos.Vertical fully floodable type submersible drainage pumps in close coupled design single stage, suitable for handling minimum 12 mm dia solids. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Duty | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Discharge of each pump : 300 LPM | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Working Head : 14 M | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Material of Construction (M.O.C): Corrosion Resistant in general | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| : Bearings — Anti friction, prelubricated ball bearings, packed with grease for life. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Motor: — Dry Motor with built in over load protection | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Protection - IP68. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Insulation Class - F | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| b) Electric control panel for automatic operation of pumps as per the water level in the sump.The pump operation shall be controlled with magnetic float type level controller.The Panel shall comprise of incoming switch/MCB, voltmeter & ammeter, On-Off-Trip lamps, starters with circuit breakers for each pump, single phase preventor for three phase motors only for each starter, rotating start sequence, both pumps to work simultaneously to meet peak flow There shall be an audio-visual alarm, if any pump fails to start. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| c) Power cabling and control cabling between magnetic float type controller panel and pump panels including cable tray as required . | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| d) Each pump should be skid base mounted of 9" height to avoid mud choking. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| e) Pump suspension systemwith Stainless Steel Sling wire with `U` clamp. | Set | 1 | 113286 | 24987 | 111110 | 24507 |  | 1 | 1 | 0 | 111110 | 111110 |  | 1 | 1 |  | 24507 | 24507 | DONE
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
2.1 contd. | Details of Pump offered (To be filled in by the tenderer) | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Make: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Model: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| HP/KW: | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| M.O.C : Casing —……………….. : Impeller — …………….. : Shaft — ………………. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| TOTAL for " Sump Pumps and Control Panel" carried over to SUMMARY | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4 | CABLING AND MAIN PANEL | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4.1 | Supplying and fixing of following types and sizes of 1.1 KV grade PVC insulated conductor armoured cable conforming to IS : 1554. | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 4C 4 sq.mm. Copper conductor | M | 50 | 252 | 48 | 247 | 47 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| c) 4C 16 sq.mm. `Al' conductor | M | 30 | 795 | 48 | 779 | 47 |  | 0 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4.2 | Supplying, laying & terminating of following types and size of 1.1 KV grade PVC isulated armoured control cables conforming to IS : 1554 Part-II |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 2C 1.5 sq.mm.Cu. Conductor | M | 100 | 84 | 24 | 82 | 23 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| b) 3C 1.5 sq.mm.Cu. Conductor | M | 100 | 105 | 36 | 102 | 35 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4.3 | Supplying and making end termination with brass double compression glands and copper/aluminium lugs for following size of PVC insulated and PVC sheathed/XLPE copper/aluminium conductor cable of 1.1 KV grade as required : |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 4C 4 sq.mm. Copper conductor | Set | 4 | 332 | 149 | 325 | 146 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| c) 4C 16 sq.mm. `Al' conductor | Set | 2 | 486 | 149 | 476 | 146 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4.4 | Providing and fixing following size G.I. strip / wire on surface or in recess for body earthing of motors as required. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 25x6 mm G.I. strip | M | 50 | 111 | 24 | 108 | 23 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| b) 8 SWG dia. | M | 100 | 15 | 12 | 14 | 11 |  | 124 | 124 | 0 | 1736 | 1736 |  | 124 | 124 |  | 1364 | 1364
[6 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4.5 | Supply, fabricating and installing following size of perforated M.S. powder coated (of approved shade) (0.65 micron) cable trays including horizontal and vertical bends, reducers, tees, cross members and other accessories as required and duly suspended from the ceiling with M.S. suspenders and including painting etc. as required : |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 100 mm. width x 40 mm. depth x 1.6 mm. thickness | M | 30 | 244 | 119 | 239 | 116 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
4.6 | Supply, installation, testing and commissioning of electric pump control panel metal clad cubicle type suitable for 440V AC three phase 50Hz supply system. The panel shall be completely compartmentalised and complete with Aluminium Bus Bars, designation labels as per requirement, continuous Aluminium earth bar 40mm x 6 mm, panel separators, protective screens, cable clamping support system, top/bottom cable gland plates for incoming and out going cable entries as per details given below: |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| MAIN PANEL WATER PUMPING SYSTEM |  |  |  |  | 0 |  |  | 1 | 1 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| INCOMER |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| 160 A 36KA FP MCCB with phase spreader and extended rotary handles - 1 No. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| BUSBARS |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| A set of 200 A 415V 50Hz TPN 3 Ph 4 wire aluminium busbars. C./D. 1 Amp/ mm2. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| INSTRUMENTS FOR INCOMER |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| A set of instrumentation with a set of Current transformer 100/5A with Ammeter 0-100A, Selector Switch, Voltmeter 0-500V with selector switch, a set of phase indicating lights with mcb fuses and energy meter (KWH). |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| OUTGOING FEEDERS |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| 16A DP 10KA MCB - 2 No. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| 25A DP 10KA MCB - 2 No. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| 25A FP 10KA MCB - 2 No. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| 100A TPN 25KA MCCB with phase spreader and extended rotary handle - 2 No. | Set | 1 | 57918 | 3570 | 56805 | 3501 |  | 1 | 1 | 0 | 56805 | 56805 |  | 1 | 1 |  | 3501 | 3501
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| TOTAL for "Cabling and Main Panel" carried over to SUMMARY |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5 | PIPE WORK AND VALVES |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.1 | Providing, fixing, jointing, testing and commissioning medium class (Class B) G.I. Pipe work conforming to IS:1239 (Part I)-1990 for pipes upto 150 mm dia.and MS pipe work conforming to IS:3589-1991 for pipes above 150 mm dia. with all fittings, flanges, specials & clamps effecting proper connections, including painting with two coats of epoxy paint of approved quality and shade over a coat of primer on exposed pipework, complete in all respects: (Pipe work restricted within the plant room for suction and delivery headers and delivery pipe of submersible pumps) |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 100 mm dia pipe | M | 30 | 1691 | 381 | 1658 | 373 |  | 113.05 | 113.05 | 0 | 187436.9 | 187436.9 |  | 113.05 | 113.05 |  | 42167.65 | 42167.65 | DONE
| b) 80 mm dia pipe | M | 5 | 1632 | 286 | 1600 | 280 |  | 255.4 | 255.4 | 0 | 408640 | 408640 |  | 255.4 | 255.4 |  | 71512 | 71512 | DONE
| c) 65 mm dia pipe | M | 20 | 1333 | 238 | 1307 | 233 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
| d) 50 mm dia pipe | M | 20 | 888 | 191 | 870 | 187 |  | 81.7 | 81.7 | 0 | 71079 | 71079 |  | 81.7 | 81.7 |  | 15277.9 | 15277.9 | DONE
| e) 40 mm dia pipe | M | 10 | 757 | 143 | 742 | 140 |  | 55.3 | 55.3 | 0 | 41032.6 | 41032.6 |  | 55.3 | 55.3 |  | 7742 | 7742 | DONE
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.2 | Providing and fixing butterfly valve of approved make including a set of MS flanges, required nos. of nut & bolts all complete and as per following specification: |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| MOC: |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Body - Cast Iron |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Shaft - Carbon Steel / Stainless Steel |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Body Liner - EPDM/ nitrile rubber |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Disc - Epoxy coated C.I./ D.I. |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 100 mm dia ( with lever) (PN 16) | No. | 6 | 4974 | 714 | 4878 | 700 |  | 13 | 13 | 0 | 63414 | 63414 |  | 13 | 13 |  | 9100 | 9100 | DONE
| b) 65 mm dia ( with lever) (PN 16) | No. | 3 | 3664 | 447 | 3593 | 438 |  | 14 | 14 | 0 | 50302 | 50302 |  | 14 | 14 |  | 6132 | 6132 | DONE
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
5.3 | Providing and fixing Dual plate (Wafer type) check valve (non return valve) of Class PN 16, having cast iron body, stainless steel disc ( AISI 316), trim and spring of approved make. including a set of MS flanges, required nos. of nut & bolts all complete. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0
| a) 100 mm dia | No. | 1 | 4124 | 714 | 4044 | 700 |  | 1 | 1 | 0 | 4044 | 4044 |  | 1 | 1 |  | 700 | 700 | DONE
| b) 50 mm dia | No. | 2 | 1780 | 357 | 1745 | 350 |  | 24 | 24 | 0 | 41880 | 41880 |  | 24 | 24 |  | 8400 | 8400 | DONE
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.4 | Providing and fixing of flanged C.I (Pot) strainer on suction ends submerged in water tanks, all complete. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 100 mm dia | No. | 4 | 10112 | 714 | 9917 | 700 |  | 6 | 6 | 0 | 59502 | 59502 |  | 6 | 6 |  | 4200 | 4200 | DONE
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.5 | Providing and fixing of flanged end Pot strainer in cast iron body with stainless steel perforated sheet screen basket, complete with drain plug. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 100 mm dia | Nos. | 4 | 10112 | 714 | 9917 | 700 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.6 | Providing, fixing, testing and commissioningof Full Bore Ball Valves of approved makes. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| MOC: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Body : Nickel plated brass |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Ball : Chrome plated brass |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Washers : PTFE |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Operating Handle : Aluminium Painted |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Pressure Rating : Minimum 20 Bar |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Temerature Withstanding : 900 C Min. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 50 mm dia | Nos. | 2 | 2993 | 238 | 2935 | 233 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| b) 40 mm dia | Nos. | 2 | 2034 | 179 | 1994 | 175 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| c) 32 mm dia | Nos. | 2 | 1433 | 143 | 1405 | 140 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.7 | Providing and fixing heavy duty resilient rubber neoprene lined single arch vibration eliminators suitable for raw water up to 70 deg.C temperature, pressure upto 15 Bar and vacuum rating upto 700 mm Hg. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| a) 100 mm dia | Nos. | 2 | 5149 | 714 | 5050 | 700 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.8 | Supplying, installation, setting, testing and commissioning of differential type pressure switches of size 100 mm dia for operation of pumps. | Nos. | 1 | 9194 | 179 | 9017 | 175 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.9 | Supplying, installation, setting, testing and commissioning of glycerin filled dial type pressure gauge with isolation cock, all complete | Nos. | 1 | 1963 | 179 | 1925 | 175 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.1 | Providing and fixing level indicator assembly for water tanks comprising 2 nos. 15 mm dia gunmetal level guage isolation cocks with screwed ends, heavy guage transparent polythelyne tube of upto 6.0 m length, 100 mm wide x 20 mm thick teak wood indicating board painted with level indications in cms and litres, as required. | Sets | 4 | 9807 | 952 | 9618 | 933 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
5.11 | Providing, fixing, testing and commissioning of Electro Magnetic Flow Transmeter with Communication Port, of approved makes. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Suitability: Fresh Water |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| MOC: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Body : Non-corrosive |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Lining : PTFE |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Flanges : Stainless Steel |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Electrode : Stainless Steel |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Coil Housing : Stainless Steel |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Pressure Rating : Minimum 10 Bar |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Temerature Withstanding : upto 850 C |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Display: LCD showing both flow rate and totalised flow |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| Communication Port: RS 485 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
G | a) 100 mm dia nominal bore | No. | 1 | 95847 | 1785 | 94006 | 1750 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| TOTAL for "Pipe work and Valves" carried over to SUMMARY | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0
| GRAND TOTAL | [9 empty] | 0 | 1773233.5 | 1773233.5 |  |  |  | 0 | 223777.55 | 223777.55

## Variation Items
c
M/s. Zamil Airconditioners India Private Limited
Services : Supply, Installation, Testing and Commissioning of Plumbing Machinery
P.O. No. : TU/CS/PSJ/17-18/150101/01
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | SUPPLY RATE | ITC RATE | GST Rates |  | SUPPLY QUANTITY |  |  | SUPPLY AMOUNT |  |  | INSTALLATION QUANTITY |  |  | INSTALLATION AMOUNT
[6 empty] | Supply | ITC | PREV. | THIS BILL | CUM. | PREVIOUS | THIS BILL | CUMULATIVE | PREV. | THIS BILL | CUM. | PREVIOUS | THIS BILL | CUMULATIVE
0
| Extra Items | [8 empty] | 0 | [8 empty] | 0
| Electrical | [8 empty] | 0 | [8 empty] | 0
1 | Providing and fixing following size G.I. strip / wire on surface or in recess for body earthing of motors as required. | [8 empty] | 0 | [8 empty] | 0
[10 empty] | 0 | [8 empty] | 0
| a) 32x6 mm G.I. strip | M |  |  |  | 113 | 48 |  | 46 | 46 |  | 5198 | 5198 |  | 46 | 46 |  | 2208 | 2208 | DONE
[9 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
2 | Supply, fabricating and installing following size of perforated M.S. powder coated (of approved shade) (0.65 micron) cable trays including horizontal and vertical bends, reducers, tees, cross members and other accessories as required and duly suspended from the ceiling with M.S. suspenders and including painting etc. as required : | [7 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
[9 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
| a) 300 mm. width x 50 mm. depth x 1.6 mm. thickness | M |  |  |  | 401 | 90 |  | 8.7 | 8.7 |  | 3488.7 | 3488.7 |  | 8.7 | 8.7 |  | 783 | 783 | DONE
[9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| b) 150 mm. width x 50 mm. depth x 1.6 mm. thickness | M |  |  |  | 248 | 84 |  | 60.7 | 60.7 |  | 15053.6 | 15053.6 |  | 60.7 | 60.7 |  | 5098.8 | 5098.8 | DONE
[9 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
3 | Supply and laying in cable including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and sheathed aluminium conductor armoured cable complete as required. The costs shall include providing a gap of 1D between all the cables being laid and properl clamping with cable clamps and ties. Prices shall include providing and fixing of Identification tags for all cables and route markers for cables in ground etc. as per specification and or as per direction of Project in-charge. | [7 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
[9 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
| a) 3 –1/2 core 300 Sq mm |  |  |  |  | 1237 | 84 |  | 39.3 | 39.3 |  | 48614.1 | 48614.1 |  | 39.3 | 39.3 |  | 3301.2 | 3301.2 | DONE
| b) 4 core 35 Sq mm |  |  |  |  | 191 | 48 |  | 110 | 110 |  | 21010 | 21010 |  | 110 | 110 |  | 5280 | 5280 | DONE
| c) 4 core 25 Sq mm |  |  |  |  | 151 | 42 |  | 17.7 | 17.7 |  | 2672.7 | 2672.7 |  | 17.7 | 17.7 |  | 743.4 | 743.4 | DONE
[9 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
4 | Cable end termination XLPE insulated 1100 Volt grade cables including the cost of crimping tinned copper heavy duty lugs, double compression glands, insulation tape etc. complete as required and as below. | [7 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
[9 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0
| a) 3 –1/2 core 300 Sq mm |  |  |  |  | 2946 | 540 |  | 2 | 2 |  | 5892 | 5892 |  | 2 | 2 |  | 1080 | 1080 | DONE
| b) 4 core 35 Sq mm |  |  |  |  | 505 | 276 |  | 2 | 2 |  | 1010 | 1010 |  | 2 | 2 |  | 552 | 552 | DONE
| c) 4 core 25 Sq mm |  |  |  |  | 427 | 240 |  | 2 | 2 |  | 854 | 854 |  | 2 | 2 |  | 480 | 480 | DONE
[9 empty] | 0 |  |  | 0 |  |  | #VALUE! | #VALUE!
| Plumbing | [7 empty] | 0 |  |  | 0 |  |  | #VALUE! | #VALUE!
[9 empty] | 0 |  |  | 0 |  |  | #VALUE! | #VALUE!
1 | Providing ,Fixing, testing and commissioning of vitreous china Wall/floor mounting type (European type) water closet with C.P.Bolts, nuts other fixing arrangement solid plastic seat with lid, C.P. brass hinges and rubber buffers, concealed dual flushing cistern ( 3-6 liters/flush) with flush pipe , clamp with adaptor, WC flexible connector, C.P. brass screws and washers complete, including cutting and making good the walls floors where required complete in all respects. | Nos |  |  |  |  | 1371 |  | 0 |  |  | 0 |  |  | #VALUE! | #VALUE! |  | #VALUE! | #VALUE!
[9 empty] | 0 |  |  | 0 |  |  | #VALUE! | #VALUE! |  |  | 0
2 | Providing ,Fixing, testing and commissioning of vitreous china wash basin Under Water Counter round/oval with waste coupling fitting,32mm CP cast brass bottle trap and pipe to wall with CP wall flange and rubber adopter for waste connection, CP deck mounted mixer with battery operated and built in sensor for auto cut in/cut off operation complete including cutting and making good the walls where required complete in all respects. | Nos |  |  |  |  | 915 |  | 0 |  |  | 0 |  |  | #VALUE! | #VALUE! |  | #VALUE! | #VALUE!
[9 empty] | 0 |  |  | 0 |  |  | #VALUE! | #VALUE! |  |  | 0
3 | Providing ,Fixing, testing and commissioning of 15 mm dia angle valve with flanges including 450 mm long copper connecting pipe with nuts complete. | Nos |  |  |  |  | 86 |  | 0 |  |  | 0 |  |  | #VALUE! | #VALUE! |  | #VALUE! | #VALUE!
[9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
4 | Providing, Fixing & testing of uPVC SWR (Type-B) pipes conforming to IS 13592 along with all required fittings like tees, bends, cowls, crosses with or without access doors jointed with approved solvent cement fixed to walls and ceilings including angle supports with clamps and structural support as per good practice /manufacturers recomandation and complete including core cut in R.C.C/brick work (slab/beam/wall) and making good the same whatever required. Soil, Waste and Vent pipe) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
a} | 110mm OD | RM |  |  |  | 272 | 142 |  | 142 | 142 |  | 38624 | 38624 |  | 142 | 142 |  | 20164 | 20164 | DONE.
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
5 | Providing, Fixing & testing of f uPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| 40 mm OD | RM |  |  |  | 45 | 45 |  | 22.9 | 22.9 |  | 1030.5 | 1030.5 |  | 22.9 | 22.9 |  | 1030.5 | 1030.5 | DONE
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
6 | Providing and laying cement concrete 1:2:4 mix (1 cement:2 coarse sand: 4 graded stone aggregate 20 mm nominal size) 75 mm in bed and alround uPVC soil & waste pipes including excavation, refilling where required complete in all respect as per standard design. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| Pipe 90 to 110 mm OD | RM |  |  |  |  | 614 |  | 0 |  |  | 0 | 0 |  | 93.5 | 93.5 |  | 57409 | 57409 | PENDING
| Pipe 40 to 63 mm OD | RM |  |  |  |  | 372 |  | 0 |  |  | 0 | 0 |  | 83 | 83 |  | 30876 | 30876 | PENDING
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
7 | Providing, Fixing & testing of uPVC P or S trap including jointing with solvent cement and making good the walls, floors etc., complete of nominal size. | Nos |  |  |  | 188 | 114 |  | 5 | 5 |  | 940 | 940 |  | 5 | 5 |  | 570 | 570 | DONE
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
8 | Providing, Fixing & testing of 125 mm dia, 1 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| a) 125mm dia over Floor Trap & floor Drain | Nos |  |  |  | 527 | 114 |  | 6 | 6 |  | 3162 | 3162 |  | 6 | 6 |  | 684 | 684 | DONE
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
9 | Providing, Fixing & testing of stainless steel ball valve working pressure of 10 Kg/cm2 with wheel & female screwed ends of approved quality to I complete in all respects. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| a) 25 mm dia | Nos |  |  |  | 959 | 222 |  | 10 | 10 |  | 9590 | 9590 |  | 10 | 10 |  | 2220 | 2220 | DONE
| b) 20 mm dia | Nos |  |  |  | 670 | 200 |  | 1 | 1 |  | 670 | 670 |  | 1 | 1 |  | 200 | 200 | DONE
| c) 15 mm dia | Nos |  |  |  | 426 | 176 |  | 12 | 12 |  | 5112 | 5112 |  | 12 | 12 |  | 2112 | 2112 | DONE
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
10 | Providing and fixing Dual plate (Wafer type) check valve (non return valve) of Class PN 16, having cast iron body, stainless steel disc ( AISI 316), trim and spring of approved make. including a set of MS flanges, required nos. of nut & bolts all complete. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| a) 65 mm dia | Nos |  |  |  | 5437 | 1181 |  | 2 | 2 |  | 10874 | 10874 |  | 2 | 2 |  | 2362 | 2362 | DONE
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
11 | Providing, Fixing & testing of CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493. With fabricated & subssequently epoxy painted clamps/ structural steel supports as required for directed at site including cutting chases and fitting the same with cement concrete /cement mortar as required. All termination points for installation of faucets shall have brass termination fittings. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| a) 25 mm nominal bore | RM |  |  |  | 201 | 91 |  | 25 | 25 |  | 5025 | 5025 |  | 25 | 25 |  | 2275 | 2275 | DONE
| b) 15 mm nominal bore | RM |  |  |  | 112 | 91 |  | 26.5 | 26.5 |  | 2968 | 2968 |  | 26.5 | 26.5 |  | 2411.5 | 2411.5 | DONE
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
12 | Variable Speed Hydropneumatic System For Domestic Use ( at terrace for upper 2 floors over each tower ) | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| Supply, testing, installation, testing & commissioning of Compact self contained Hydropneumatic system comprising of following : | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| Horizontal, multistage, centrifugal clear water pumps with SS-304 casing, S.S 304 impeller and SS-316 shaft, C.I. Base & head TEFC motor (with mechanical seal) Vendor to submit performance curves, dimension detail and technical catalogue of the proposed model for review and information. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| MCC panel with sequential control with mounted microprocessor PID controller and variable frequency drive (VFD) integrated in a single body or as separate components with pressure sensor transmitter (one dedicated to each pump) minimum two lined LCD display, diodes to indicate pump ready, pump running and fault and capable to communicate with other controllers following MODBUS-RTU or BACNET Class-2 protocol through RS485 port. System should be capable to compensate for frictional losses at lower flows. All alarms should be displayed in the controller. System should be equipped with dry running protection. (Quantity of VFD = 1 No.) complete in all respects. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| Pre-charged diaphragm pressure vessel with interchangeable membrane, charging connection, connected to outlet header with necessary flanges, gaskets, isolating valves, nuts/bolts etc. complete (size of pressure vessel shall be of suitable capacity or as per manufacturer calculation / recommendation). | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| Set of accessories such as pressure switches, pressure transducers,valve (butterfly / ball valve & NRV of PN 10 rating i.e. 10 kg / cm2 ) , vibration Isolator, GI "heavy class" suction & delivery header & interconnection piping, level controller, pressure gauge inter connecting power and control cabling etc. complete with Vibration eliminator of required quantities complete in all respects. | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
[9 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0
| For each tower : | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
| Capacity/Flow Rate - 300 LPM | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
| Pumping Head - 25-30 Mtr | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
| Power Requirement (HP) - 3.0 HP each or as per manufacturer recommendation | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
| Location - Terrace | [7 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0
| 1 Set = 2 Nos. Pump (1 Working +1 standby) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Supply | Set |  |  |  | 286731 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  | DONE
| Installation, Testing & Commissioning | Set |  |  |  |  | 29174 |  | 0 | [5 empty] | 0 |  |  | 0 | 0 | DONE
[9 empty] | 0 | [5 empty] | 0
| GRAND TOTAL | [9 empty] | 0 | 181788.6 | 181788.6 |  |  |  | 0 | 146728 | 146728

## Challan Detail
3
M/s. Zamil Airconditioners India Private Limited
P.O. No. : TU/CS/PSJ/17-18/150101/01
Services : Supply, Installation, Testing and Commissioning of Plumbing Pumps
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | Previous Invoice No. | INVOICE NO. | SUPPLY QUANTITY |  |  | Remarks
[6 empty] | PREV. | THIS BILL | CUM.
A) | WATER SUPPLY AND DRAINAGE PUMPS :
1 | Fixed Speed Hydropneumatic System For Domestic/Flushing OverHead Water Storage Tanks Fillings. | [5 empty] | 0
| Supply, Installation, Testing & Commissioning of Factory Assembled Compact self contained Hydropneumatic system comprising of following : | [5 empty] | 0
| Make: Grundfoss / DP or eq. | [5 empty] | 0
i) | Vertical, Non-self Priming, multistage, inline, centrifugal clear water pumps with cast iron pump housing, S.S 304 impeller and SS-316 shaft, C.I. Base & head, TEFC motor, "F" insulation class, IP55 enclosure class, 2900 RPM (with mechanical seal) Vendor to submit performance curves and technical catalogue of the proposed model for review and information. | [5 empty] | 0
ii) | MCC panel mounted in frame with auto cut in/cut off controls, manual ride over, sequential change over facilty with interconnecting cables, controllers complete in all respects. | [5 empty] | 0
iii) | Pressure vessel (200 litres or as of vendors design details) with food grade internal surface painted and food grade pre charged diaphgram with inlet and outlet, pressure switches for auto on/off control, butterfly / ball valve / NRV of suitable pressure rating, vibration isolator, GI "heavy class" suction & delivery header & interconnection piping, control panel with neccessary control cabling etc. complete in all respects. | [5 empty] | 0
1.1 | For Boys hostel blocks ( Centralized domestic transfer pump ) | [5 empty] | 0
■ | Capacity/Flow rate - 250 LPM of each pump | [5 empty] | 0
■ | Pumping Head - 60 Mtr | [5 empty] | 0
■ | Power Requirement (HP) - 6.0 HP each or as per manufacturer recommendation | [5 empty] | 0
■ | Location-(Proposed UG Plumbing Pump Room) | [5 empty] | 0
■ | 1 Set = 3 Nos. Pump (2 Working +1 standby) | [5 empty] | 0
a) | Supply | Set | 1 |  | GMGR/2017-18/109 |  | 1 | 1
b) | Installation, testing & commissioning | Set | 1 |  |  |  | 0
0
1.2 | For Boys hostel blocks ( Centralized flushing transfer pump ) | [5 empty] | 0
■ | Capacity/Flow rate-250 LPM of each pump | [5 empty] | 0
■ | Pumping Head - 60 Mtr | [5 empty] | 0
■ | Power Requirement (HP) - 6.0 HP each or as per manufacturer recommendation | [5 empty] | 0
■ | Location - (Proposed UG Plumbing Pump Room) | [5 empty] | 0
■ | 1 Set = 2 Nos. Pump (1 Working +1 standby) | set | 1 |  | GMGR/2017-18/120 |  | 1 | 1
| Installation, Testing & Commissioning | Set | 1 |  |  |  | 0
1.3 | For Boys hostel blocks ( Irrigation pump) | [5 empty] | 0
■ | Capacity/Flow Rate - 450 LPM of each pump | [5 empty] | 0
■ | Pumping Head - 50 Mtr | [5 empty] | 0
■ | Power Requirement (HP) - 7.5 HP each or as per manufacturer recommendation | [5 empty] | 0
■ | Location - (Proposed UG Plumbing Pump Room) | [5 empty] | 0
■ | 1 Set = 2 Nos. Pump (1 Working +1 standby) | [5 empty] | 0
a) | Supply | Set |  |  | GMGR/2017-18/120 | 0 | 1 | 1
b) | Installation, testing & commissioning | Set | 1 |  |  |  | 0
0
2 | Variable Speed Hydropneumatic System For Domestic Use ( at terrace for upper 2 floors over each tower ) | [5 empty] | 0
0
| Supply, testing, installation, testing & commissioning of Compact self contained Hydropneumatic system comprising of following : | [5 empty] | 0
i) | Horizontal, multistage, centrifugal clear water pumps with SS-304 casing, S.S 304 impeller and SS-316 shaft, C.I. Base & head TEFC motor (with mechanical seal) Vendor to submit performance curves, dimension detail and technical catalogue of the proposed model for review and information. | [5 empty] | 0
0
ii) | MCC panel with sequential control with mounted microprocessor PID controller and variable frequency drive (VFD) integrated in a single body or as separate components with pressure sensor transmitter (one dedicated to each pump) minimum two lined LCD display, diodes to indicate pump ready, pump running and fault and capable to communicate with other controllers following MODBUS-RTU or BACNET Class-2 protocol through RS485 port. System should be capable to compensate for frictional losses at lower flows. All alarms should be displayed in the controller. System should be equipped with dry running protection. (Quantity of VFD = 1 No.) complete in all respects. | [5 empty] | 0
0
iii) | Pre-charged diaphragm pressure vessel with interchangeable membrane, charging connection, connected to outlet header with necessary flanges, gaskets, isolating valves, nuts/bolts etc. complete (size of pressure vessel shall be of suitable capacity or as per manufacturer calculation / recommendation). | [5 empty] | 0
0
iv) | Set of accessories such as pressure switches, pressure transducers,valve (butterfly / ball valve & NRV of PN 10 rating i.e. 10 kg / cm2 ) , vibration Isolator, GI "heavy class" suction & delivery header & interconnection piping, level controller, pressure gauge inter connecting power and control cabling etc. complete with Vibration eliminator of required quantities complete in all respects. | [5 empty] | 0
0
2.1 | For each tower : | [5 empty] | 0
● | Capacity/Flow Rate - 300 LPM | [5 empty] | 0
● | Pumping Head - 25-30 Mtr | [5 empty] | 0
● | Power Requirement (HP) - 3.0 HP each or as per manufacturer recommendation | [5 empty] | 0
● | Location - Terrace | [5 empty] | 0
● | 1 Set = 2 Nos. Pump (1 Working +1 standby) | [5 empty] | 0
0
a) | Supply | Set | 4 |  | GMGR/2017-18/119, GMGR/2017-18/120 |  | 4 | 4
b) | Installation, Testing & Commissioning | Set | 4 |  |  |  | 0
0
0
3 | Providing and fixing of submersible non-clog, open impeller sump pump with vortex impeller connected to TEFC submersible motor for 415 + 10% volts, 3 phase, 50 cycles A.C. power supply with mechanical seal, pump connector unit with rubber diaphragm and bend of the following specifications, MCC panel ( located on near wall) with auto sequential change over with both pumps shut at low level, one pump working at mid level and both pump working with an alarm hooter at high level, including interconnecting cables, piping works, valves, controls etc. all pre set as required complete in all respects. Cost shall included electrical control panel with starter. | [5 empty] | 0
0
3.1 | Sump Pump Drainage ( Main Pump Room ) | [5 empty] | 0
a) | Discharge : 400 lpm | [5 empty] | 0
b) | Head : 10 metre | [5 empty] | 0
c) | HP : 3.0 HP each or as per manufacturer recommendation. | [5 empty] | 0
d) | Casing : Aluminium alloy / C.I | [5 empty] | 0
e) | Impeller & Shaft: S.S. 410 | [5 empty] | 0
f) | Solid Handling Capacity: 15 mm | [5 empty] | 0
g) | Length of water proof cable with each pump : 10 meter | [5 empty] | 0
h) | Length of GI lifting chain with each pump : 5 Meter. | [5 empty] | 0
i) | G.I. heavy class header main of suitable diameter and length | [5 empty] | 0
j) | Level controller and starter control panel | [5 empty] | 0
k) | Quantity : 2 Nos. (1 Working +1 Standby) | Set | 1 |  | GMGR/2017-18/108 |  | 1 | 1
0
4 | Providing and fixing motorized solenoid valve/rotary actuator (CI body, SS316 disc, EPDM boot seat, SS416 shaft, RPTEF bushing @ PN10 rating) for filling of overhead water tank complete with electrical water level control panel, including by-pass connection for the same dia with manually operated butterfly valve, float valve/ controller and all piping and accessories complete in all respects (Belimo/ Legris make or eq.). | [5 empty] | 0
a. | 50 mm dia | Set | 4 |  | 169 |  | 4 | 4
b. | 40 mm dia. | Set | 4 |  | 169 |  | 6 | 6
c. | 32 mm dia. | Set |  |  | 169 |  | 2 | 2
5 | Puddle Flange for Water Tanks | [5 empty] | 0
0
| Providing and fixing M.S fabricated hot dipped galvanized coating puddle flange comprising of 600 mm dia long M.S class 'B' pipe (screwed end up to 50 mm & flange for more than 50 mm dia) with 6 mm thick M.S plates of required size including cutting holes in centre of plate, inserting pipe & making welded (Arc) joint complete. Same shall be installed with TEC welded joint in position with reinforcement bars of RCC tank wall/slab including making cutout in shuttering during concrete casting of tank of following diameter complete in all respects . (Location: underground tanks.) | [5 empty] | 0
0
a) | 25 mm dia | Each | 6 | 353 | 430 | 6 | 0 | 6
b) | 50 mm dia | Each | 2 | 353 | 430 | 2 | 0 | 2
c) | 80 mm dia | Each | 4 | 353 | 430 | 1 | 0 | 1
d) | 100 mm dia | Each | 6 | 353 | 430 | 5 | 0 | 5
0
6 | WATER TANK COVER | [5 empty] | 0
0
| Providing and fixing 500 mm dia M.S. water tank cover with 40 mm seat and lockable arrangement complete in all respects including all fitting & accessories complete in all respects. | Each | 4 |  |  |  | 0
0
7 | G.I VENT PIPE | [5 empty] | 0
0
| Providing and fixing G.I. Vent Pipe class 'B' (medium duty) for R.C.C water storage tanks comprising of 600 mm long vertical pipe, return bend with mosquito grating & cast brass perforated coupling including all associated civil work complete in all respects. | [5 empty] | 0
0
a) | 150 mm dia | Each | 4 |  |  |  | 0
0
8 | M.S. STRUCTURAL WORK | [5 empty] | 0
0
| Providing and fixing M.S. structural work fabricated from standard sections, (MS rounds, angles, channels etc.) including cutting to size, drilling, welding, including cost of fasteners, clamps in RCC structural members as directed, including two or more coats of synthetic paint over one coat of primer after surface preparation including cutting and making good walls complete in all respects. (For pipe works in pump room ) | Kg | 300 |  |  |  | 0
0
9 | Providing and fixing of mosquito overflow grating /Jali of the following diameters including all fittings & accessories complete in all respects. | [5 empty] | 0
0
a) | 100 mm dia | Each | 4 |  |  |  | 0
0
10 | Providing and fixing forged brass auto air vent valve 10 PN rating including all fitting & accessories complete in all respects. | [5 empty] | 0
0
a) | 25 mm dia | Each | 4 |  |  |  | 0
0
11 | Providing and fixing cast iron double flanged butterfly valve (PN 16) complete with 2 nos. matching flanges, bolts, nuts, 3.0 mm thick compressed asbestos gasket complete in all respects. | [5 empty] | 0
0
a) | 50 mm dia | Each | 2 |  | 1108, 1114 |  | 35 | 35
b) | 80 mm dia | Each | 3 |  | 1394 |  | 3 | 3 | Why not in Collier Inspection report
c) | 100 mm dia | Each | 5 |  |  |  | 0
12 | EXTERNAL WATER SUPPLY ( BOYS HOSTEL) MAIN LINE FROM PUMP ROOM TO HOSTEL BLOCK BASE | [5 empty] | 0
0
A | IRRIGATION SYSTEM | [5 empty] | 0
0
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m or as required complete in all respects. | [5 empty] | 0
a | Pipes, upto 150 mm dia | Mtr | 940 |  |  |  | 0
0
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects. | [5 empty] | 0
a | 50 mm OD | Mtr | 120 |  |  |  | 0
b | 75 mm OD | Mtr | 750 |  | 12178 | 570 | 0.2 | 570.2
0
3 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect. | [5 empty] | 0
b | 20 mm dia. | Each | 7 |  |  |  | 0
c | 40 mm dia. | Each | 2 |  |  |  | 0
0
4 | Providing, fixing and testing G.I. Pipe (medium class) including painting with two coats of synthetic enamel paint of approved shade.(for G.H. rising above the ground) ) complete in all respects. | [5 empty] | 0
a | 20 mm dia. | Mtr | 10 |  |  |  | 0
b | 25 mm dia. | Mtr | 70 |  | 951 |  | 0 |  | Why not in Collier Inspection report
0
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged to HDPE tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect. | [5 empty] | 0
a | 65 mm dia. | Each | 3 |  |  |  | 0
0
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” and connected to HDPE tail piece complete in all respects. (Optional of sluice valve) | [5 empty] | 0
a | 65 mm dia. | Each |  |  |  |  | 0
0
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1 |  |  |  | 0
0
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect. | [5 empty] | 0
a | Internal size 90 cm x 90cm x 100 cm | Each | 5 |  |  |  | 0
b | Internal size 300cm x 300cm x 600 cm | Each | 7 |  |  |  | 0
0
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for C.I. & uPVC specials including necessary excavation, shuttering and centring, curing complete. | Cum | 2 |  |  |  | 0
0
| TOTAL IRRIGATION SYSTEM | [5 empty] | 0
0
B | FLUSHING SYSTEM | [5 empty] | 0
0
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m or as required complete in all respects. | [5 empty] | 0
a | Pipes, upto 150 mm dia | Mtr | 1350 |  |  |  | 0
0
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects. | [5 empty] | 0
a | 90 mm OD | Mtr | 750 |  | 12178 | 570 | 0.2 | 570.2
0
3 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect. | [5 empty] | 0
a | 40 mm dia. | Each | 7 |  |  |  | 0
0
4 | Providing, fixing and testing G.I. Pipe IS 1239 (medium class) with tap off connection from HDPE main pipe with adaptor/ connector etc. and including 4 mm thick Pypekote tape wrapping all around , bitumen paint and covered with 150 mm sand cover all around pipe etc. (for riser to each hostel block ) complete in all respects. | [5 empty] | 0
a | 40 mm dia. | Mtr | 600 |  |  |  | 0
0
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged to HDPE tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect. | [5 empty] | 0
a | 75 mm dia. | Each | 3 |  |  |  | 0
0
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” and connected to HDPE tail piece complete in all respects. (Optional of sluice valve) | [5 empty] | 0
a | 75 mm dia. | Each |  |  |  |  | 0
0
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1 |  |  |  | 0
0
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect. | [5 empty] | 0
a | Internal size 90 cm x 90cm x 100 cm | Each | 10 |  |  |  | 0
0
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for pipes at junctions etc. including necessary excavation, shuttering and centring, curing complete in all respects. | Cum | 3 |  |  |  | 0
0
B | TOTAL FLUSHING SYSTEM | [5 empty] | 0
0
C | DOMESTIC SYSTEM | [5 empty] | 0
0
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m. | [5 empty] | 0
a | Pipes, upto 150 mm dia | Mtr |  |  |  |  | 0
0
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects. | [5 empty] | 0
a | 110 mm OD | Mtr | 750 |  | 12178 | 570 | 0.2 | 570.2
0
0
0
| IMPORTANT NOTES : | [5 empty] | 0
| a) The pump shall be capable of developing the required total head at rated capacity for continuous operation. The pumps shall operate satisfactorily at any point on the Head-Discharge (H-Q) characteristic curve over a range of 50% to 130% capacity. The total head capacity curve shall be continuously rising towards the shut off. The shut off head shall be at least 110% of the total head. | [5 empty] | 0
| b) All associated piping, valves & other appurtenances shall be paid seperately as per relevant items | [5 empty] | 0
| c) The Tenderer must submit along with his offer, the make and the model of the pump unit proposed by him. | [5 empty] | 0
| d) Required power supply would be made available at individual control panels of packaged pumping systems in the pump room and solenoid valves at terrace level. | [5 empty] | 0
| e) Wherever mechanical seal has been asked for, it must be `factory fitted` at pump manufacturer`s works. | [5 empty] | 0
0
1 | HYDROPNEUMATIC SYSTEMS | [5 empty] | 0
0
1.1 | Supply, installing, testing and commissioning of clear water Factory Fitted packaged hydropneumatic pumping system for general water supply as per following details: | [5 empty] | 0
0
| Type of Drive - Variable frequency drive for each pump | [5 empty] | 0
0
| System Capacity | [5 empty] | 0
| Maximum System Discharge : 30 M3/hr. | [5 empty] | 0
| System Pressure : 6.0 kg/cm2 | [5 empty] | 0
| Pumps- 3 Nos (2W+1S) | [5 empty] | 0
| Flow of each Pump - 15 M3/hr. | [5 empty] | 0
0
| The packaged unit shall be complete with : | [5 empty] | 0
0
1.1 contd. | a) Pumps: Vertical monoblock booster pumpset with mechanical seal | [5 empty] | 0
0
| Material of Construction (M.O.C): Corrosion Resistant in general :Casing — C.I./ Stainless Steel -AISI 304 | [5 empty] | 0
| : Impeller — Stainless Steel -AISI 304 | [5 empty] | 0
| : Shaft — Stainless Steel - AISI 304 | [5 empty] | 0
| : Pump Head — Cast Iron/ Stainless Steel - AISI 304 | [5 empty] | 0
| : Base — Cast Iron | [5 empty] | 0
| : Motor Stool — Cast Iron | [5 empty] | 0
0
| Motor: 2900 RPM; 3Ph 415V 50Hz | [5 empty] | 0
| Insulation Class - F | [5 empty] | 0
| Protection - IP54 Min. | [5 empty] | 0
0
| c) Interconnecting Pipe work, Valves and Vibration Eliminators : Common suction & delivery headers in hot dipped galvanized steel pipes and fittings, Isolating valves, non return valves and vibration eliminators on suction & delivery side of pumps. | [5 empty] | 0
| d) Common fabricated base frame, duly painted. | [5 empty] | 0
| e) Power and control cabling between panel and pumps. | [5 empty] | 0
| f) Accessories like presure guages, pressure transducers etc. | [5 empty] | 0
0
| g) System Control Panel : The system control panel shall be factory built and tested and shall have the following minimum features: | [5 empty] | 0
| i) Fully protected, powder coated metallic housing. | [5 empty] | 0
| ii) Complete switchgear, under/over voltage protection, single phase preventors etc. | [5 empty] | 0
| iii) VFDs for all the pumps | [5 empty] | 0
| iv) Site programmable application optimised software | [5 empty] | 0
| v) Integrated Modbus interface for BMS compatibility | [5 empty] | 0
| vi) Large graphic display with as easy to use menu. | [5 empty] | 0
| Programmable Control System shall be PLC based, duly authentiated by the Pump Manufacturer. | Set | 1 |  | 108 |  | 1 | 1
1.1contd | Details of Equipment offered (To be filled in by the tenderer) | [5 empty] | 0
| Pumps | [5 empty] | 0
| Make: | [5 empty] | 0
| Model: | [5 empty] | 0
| HP/KW: | [5 empty] | 0
0
| M.O.C : Casing —……………….. : Impeller — …………….. : Shaft — ………………. | [5 empty] | 0
| Pressure Tank | [5 empty] | 0
| Make: | [5 empty] | 0
| Model: | [5 empty] | 0
| Capacity | [5 empty] | 0
0
| M.O.C : Shell —……………….. : Bladder — …………….. | [5 empty] | 0
0
| Valves | [5 empty] | 0
| Make: | [5 empty] | 0
| Type: | [5 empty] | 0
| Size: Suction side —………... Delivery side — ……... NRV — ………………. | [5 empty] | 0
| Type of Programmable Logic Controller — ………………….. | [5 empty] | 0
0
| The pump Panel shall be also to convese with Building Management System | [5 empty] | 0
0
| Notes: 1) Switchgear and starter ratings are indicative. The Tenderer shall quote for the actual rating required as per the pump model proposed by him. | [5 empty] | 0
| 2) Provision for BMS connectivity. The panel should have sufficient no. of potential free contacts for connectivity with Building Management System for monitoring purposes | [5 empty] | 0
0
0
0
2 | SUMP DRAINAGE PUMPS | [5 empty] | 0
0
2.1 | Supply, installing, testing and commissioning drainage pumping system in the sump of Under ground Pump Room comprising of the following: | [5 empty] | 0
| a) 2 Nos.Vertical fully floodable type submersible drainage pumps in close coupled design single stage, suitable for handling minimum 12 mm dia solids. | [5 empty] | 0
| Duty | [5 empty] | 0
| Discharge of each pump : 300 LPM | [5 empty] | 0
| Working Head : 14 M | [5 empty] | 0
| Material of Construction (M.O.C): Corrosion Resistant in general | [5 empty] | 0
| : Bearings — Anti friction, prelubricated ball bearings, packed with grease for life. | [5 empty] | 0
0
| Motor: — Dry Motor with built in over load protection | [5 empty] | 0
| Protection - IP68. | [5 empty] | 0
| Insulation Class - F | [5 empty] | 0
0
| b) Electric control panel for automatic operation of pumps as per the water level in the sump.The pump operation shall be controlled with magnetic float type level controller.The Panel shall comprise of incoming switch/MCB, voltmeter & ammeter, On-Off-Trip lamps, starters with circuit breakers for each pump, single phase preventor for three phase motors only for each starter, rotating start sequence, both pumps to work simultaneously to meet peak flow There shall be an audio-visual alarm, if any pump fails to start. | [5 empty] | 0
| c) Power cabling and control cabling between magnetic float type controller panel and pump panels including cable tray as required . | [5 empty] | 0
| d) Each pump should be skid base mounted of 9" height to avoid mud choking. | [5 empty] | 0
| e) Pump suspension systemwith Stainless Steel Sling wire with `U` clamp. | Set | 1 |  | GMGR/2018-19/27 |  | 1 | 1
0
2.1 contd. | Details of Pump offered (To be filled in by the tenderer) | [5 empty] | 0
| Make: | [5 empty] | 0
| Model: | [5 empty] | 0
| HP/KW: | [5 empty] | 0
| M.O.C : Casing —……………….. : Impeller — …………….. : Shaft — ………………. | [5 empty] | 0
0
0
0
0
4 | CABLING AND MAIN PANEL | [5 empty] | 0
0
4.1 | Supplying and fixing of following types and sizes of 1.1 KV grade PVC insulated conductor armoured cable conforming to IS : 1554. | [5 empty] | 0
| a) 4C 4 sq.mm. Copper conductor | M | 50 |  |  |  | 0
| c) 4C 16 sq.mm. Al' conductor | M | 30 |  |  |  | 0
0
4.2 | Supplying, laying & terminating of following types and size of 1.1 KV grade PVC isulated armoured control cables conforming to IS : 1554 Part-II | [5 empty] | 0
| a) 2C 1.5 sq.mm.Cu. Conductor | M | 100 |  |  |  | 0
| b) 3C 1.5 sq.mm.Cu. Conductor | M | 100 |  |  |  | 0
0
4.3 | Supplying and making end termination with brass double compression glands and copper/ aluminium lugs for following size of PVC insulated and PVC sheathed/XLPE copper/aluminium conductor cable of 1.1 KV grade as required : | [5 empty] | 0
| a) 4C 4 sq.mm. Copper conductor | Set | 4 |  |  |  | 0
| c) 4C 16 sq.mm. `Al' conductor | Set | 2 |  |  |  | 0
0
4.4 | Providing and fixing following size G.I. strip / wire on surface or in recess for body earthing of motors as required. | [5 empty] | 0
0
| a) 25x6 mm G.I. strip | M | 50 |  |  |  | 0
| b) 8 SWG dia. | M | 100 |  | 1756 |  | 124 | 124
0
4.5 | Supply, fabricating and installing following size of perforated M.S. powder coated (of approved shade) (0.65 micron) cable trays including horizontal and vertical bends, reducers, tees, cross members and other accessories as required and duly suspended from the ceiling with M.S. suspenders and including painting etc. as required : | [5 empty] | 0
0
| a) 100 mm. width x 40 mm. depth x 1.6 mm. thickness | M | 30 |  |  |  | 0
0
4.6 | Supply, installation, testing and commissioning of electric pump control panel metal clad cubicle type suitable for 440V AC three phase 50Hz supply system. The panel shall be completely compartmentalised and complete with Aluminium Bus Bars, designation labels as per requirement, continuous Aluminium earth bar 40mm x 6 mm, panel separators, protective screens, cable clamping support system, top/bottom cable gland plates for incoming and out going cable entries as per details given below: | [5 empty] | 0
0
| MAIN PANEL WATER PUMPING SYSTEM |  |  |  | 35 |  | 1 | 1
| INCOMER | [5 empty] | 0
| 160 A 36KA FP MCCB with phase spreader and extended rotary handles - 1 No. | [5 empty] | 0
| BUSBARS | [5 empty] | 0
| A set of 200 A 415V 50Hz TPN 3 Ph 4 wire aluminium busbars. C./D. 1 Amp/ mm2. | [5 empty] | 0
0
| INSTRUMENTS FOR INCOMER | [5 empty] | 0
0
| A set of instrumentation with a set of Current transformer 100/5A with Ammeter 0-100A, Selector Switch, Voltmeter 0-500V with selector switch, a set of phase indicating lights with mcb fuses and energy meter (KWH). | [5 empty] | 0
| OUTGOING FEEDERS | [5 empty] | 0
| 16A DP 10KA MCB - 2 No. | [5 empty] | 0
| 25A DP 10KA MCB - 2 No. | [5 empty] | 0
| 25A FP 10KA MCB - 2 No. | [5 empty] | 0
| 100A TPN 25KA MCCB with phase spreader and extended rotary handle - 2 No. | Set | 1 |  |  |  | 0
0
0
0
5 | PIPE WORK AND VALVES | [5 empty] | 0
0
5.1 | Providing, fixing, jointing, testing and commissioning medium class (Class B) G.I. Pipe work conforming to IS:1239 (Part I)-1990 for pipes upto 150 mm dia.and MS pipe work conforming to IS:3589-1991 for pipes above 150 mm dia. with all fittings, flanges, specials & clamps effecting proper connections, including painting with two coats of epoxy paint of approved quality and shade over a coat of primer on exposed pipework, complete in all respects: (Pipe work restricted within the plant room for suction and delivery headers and delivery pipe of submersible pumps) | [5 empty] | 0
0
| a) 100 mm dia pipe | M | 30 |  | 885 |  | 113.05 | 113.05 | Please recheck & CMR Report
| b) 80 mm dia pipe | M | 5 |  | 885 |  | 255.4 | 255.4 | Please recheck & CMR Report
| c) 65 mm dia pipe | M | 20 |  |  |  | 0 |  | No Challan Mentioned
| d) 50 mm dia pipe | M | 20 |  | 899, 951 |  | 81.7 | 81.7 | Why Not In Colliers Report
| e) 40 mm dia pipe | M | 10 |  | 899, 951 |  | 55.3 | 55.3 | Why Not In Colliers Report
0
5.2 | Providing and fixing butterfly valve of approved make including a set of MS flanges, required nos. of nut & bolts all complete and as per following specification: | [5 empty] | 0
| MOC: | [5 empty] | 0
| Body - Cast Iron | [5 empty] | 0
| Shaft - Carbon Steel / Stainless Steel | [5 empty] | 0
| Body Liner - EPDM/ nitrile rubber | [5 empty] | 0
| Disc - Epoxy coated C.I./ D.I. | [5 empty] | 0
0
| a) 100 mm dia ( with lever) (PN 16) | No. | 6 |  | 1394 |  | 13 | 13 | Why Not In Colliers Report
| b) 65 mm dia ( with lever) (PN 16) | No. | 3 |  | 1108,1114 |  | 14 | 14
0
5.3 | Providing and fixing Dual plate (Wafer type) check valve (non return valve) of Class PN 16, having cast iron body, stainless steel disc ( AISI 316), trim and spring of approved make. including a set of MS flanges, required nos. of nut & bolts all complete. | [5 empty] | 0
0
| a) 100 mm dia | No. | 1 |  | 1374 |  | 1 | 1
| b) 50 mm dia | No. | 2 |  | 1138 |  | 24 | 24
0
5.4 | Providing and fixing of flanged C.I (Pot) strainer on suction ends submerged in water tanks, all complete. | [5 empty] | 0
0
| a) 100 mm dia | No. | 4 |  | 71 |  | 6 | 6
Note on F284: R A Singh: GATEPASS NOT AVILABLE

## Challan detail-Variation Items
c
M/s. Zamil Airconditioners India Private Limited
Services : Supply, Installation, Testing and Commissioning of Plumbing Machinery
P.O. No. : TU/CS/PSJ/17-18/150101/01
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | SUPPLY RATE | ITC RATE | Previous Invoice No. | Invoice No. | SUPPLY QUANTITY
[8 empty] | PREV. | THIS BILL | CUM.
| Extra Items | [8 empty] | 0
| Electrical | [8 empty] | 0
1 | Providing and fixing following size G.I. strip / wire on surface or in recess for body earthing of motors as required. | [8 empty] | 0
0
| a) 32x6 mm G.I. strip | M |  |  |  |  | 1756 |  | 46 | 46
[9 empty] | 0 | 0
2 | Supply, fabricating and installing following size of perforated M.S. powder coated (of approved shade) (0.65 micron) cable trays including horizontal and vertical bends, reducers, tees, cross members and other accessories as required and duly suspended from the ceiling with M.S. suspenders and including painting etc. as required : | [7 empty] | 0 | 0
[9 empty] | 0 | 0
| a) 300 mm. width x 50 mm. depth x 1.6 mm. thickness | M |  |  |  |  | 76 |  | 8.7 | 8.7
[9 empty] | 0 | 0
| b) 150 mm. width x 50 mm. depth x 1.6 mm. thickness | M |  |  |  |  | 76 |  | 60.7 | 60.7
[9 empty] | 0 | 0
3 | Supply and laying in cable including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and sheathed aluminium conductor armoured cable complete as required. The costs shall include providing a gap of 1D between all the cables being laid and properl clamping with cable clamps and ties. Prices shall include providing and fixing of Identification tags for all cables and route markers for cables in ground etc. as per specification and or as per direction of Project in-charge. | [7 empty] | 0 | 0
[9 empty] | 0 | 0
| a) 3 –1/2 core 300 Sq mm | [5 empty] | 1140 |  | 39.3 | 39.3 | DONE
| b) 4 core 35 Sq mm | [5 empty] | 1231 |  | 110 | 110
| c) 4 core 25 Sq mm | [5 empty] | 1231 |  | 17.7 | 17.7
| d) 4 core 16 Sq mm | [5 empty] | 1231 |  | 127 | 127
| e) 4 core 10 Sq mm | [5 empty] | 1755 |  | 14.8 | 14.8 | Not In Collier Report
[9 empty] | 0 | 0
4 | Cable end termination XLPE insulated 1100 Volt grade cables including the cost of crimping tinned copper heavy duty lugs, double compression glands, insulation tape etc. complete as required and as below. | [7 empty] | 0 | 0
[9 empty] | 0 | 0
| a) 3 –1/2 core 300 Sq mm | [7 empty] | 2 | 2
| b) 4 core 35 Sq mm | [7 empty] | 2 | 2
| c) 4 core 25 Sq mm | [7 empty] | 2 | 2
| d) 4 core 16 Sq mm | [7 empty] | 8 | 8
| e) 4 core 10 Sq mm | [7 empty] | 2 | 2
Plumbing
1 | Providing ,Fixing, testing and commissioning of vitreous china Wall/floor mounting type (European type) water closet with C.P.Bolts, nuts other fixing arrangement solid plastic seat with lid, C.P. brass hinges and rubber buffers, concealed dual flushing cistern ( 3-6 liters/flush) with flush pipe , clamp with adaptor, WC flexible connector, C.P. brass screws and washers complete, including cutting and making good the walls floors where required complete in all respects. | Nos
2 | Providing ,Fixing, testing and commissioning of vitreous china wash basin Under Water Counter round/oval with waste coupling fitting,32mm CP cast brass bottle trap and pipe to wall with CP wall flange and rubber adopter for waste connection, CP deck mounted mixer with battery operated and built in sensor for auto cut in/cut off operation complete including cutting and making good the walls where required complete in all respects. | Nos
3 | Providing ,Fixing, testing and commissioning of 15 mm dia angle valve with flanges including 450 mm long copper connecting pipe with nuts complete. | Nos
4 | Providing, Fixing & testing of uPVC SWR (Type-B) pipes conforming to IS 13592 along with all required fittings like tees, bends, cowls, crosses with or without access doors jointed with approved solvent cement fixed to walls and ceilings including angle supports with clamps and structural support as per good practice /manufacturers recomandation and complete including core cut in R.C.C/brick work (slab/beam/wall) and making good the same whatever required. Soil, Waste and Vent pipe)
a} | 110mm OD | RM |  |  |  |  | VT1823 |  | 142 | 142
0
5 | Providing, Fixing & testing of f uPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia. | [7 empty] | #VALUE! | #VALUE!
| a) 50 mm OD | RM |  |  |  |  | VT1823 |  | 1.8 | 1.8
| b) 40 mm OD | RM |  |  |  |  | VT1823 |  | 22.9 | 22.9
[9 empty] | #VALUE! | #VALUE!
6 | Providing and laying cement concrete 1:2:4 mix (1 cement:2 coarse sand: 4 graded stone aggregate 20 mm nominal size) 75 mm in bed and alround uPVC soil & waste pipes including excavation, refilling where required complete in all respect as per standard design. | [7 empty] | #VALUE! | #VALUE!
| Pipe 90 to 110 mm OD | RM | [6 empty] | #VALUE! | #VALUE!
| Pipe 40 to 63 mm OD | RM | [6 empty] | 0
0
7 | Providing, Fixing & testing of uPVC P or S trap including jointing with solvent cement and making good the walls, floors etc., complete of nominal size. | Nos |  |  |  |  | VT0438 |  | 5 | 5
[9 empty] | #VALUE! | #VALUE!
8 | Providing, Fixing & testing of 125 mm dia, 1 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete. | [7 empty] | 0
| a) 125mm dia over Floor Trap & floor Drain | Nos |  |  |  |  | 1310 |  | 6 | 6
[9 empty] | #VALUE! | #VALUE!
9 | Providing, Fixing & testing of stainless steel ball valve working pressure of 10 Kg/cm2 with wheel & female screwed ends of approved quality to I complete in all respects. | [7 empty] | #VALUE! | #VALUE!
| a) 25 mm dia | Nos |  |  |  |  | 1225 |  | 10 | 10
| b) 20 mm dia | Nos |  |  |  |  | 1225 |  | 1 | 1
| c) 15 mm dia | Nos |  |  |  |  | 1225 |  | 12 | 12
[9 empty] | #VALUE! | #VALUE!
10 | Providing and fixing Dual plate (Wafer type) check valve (non return valve) of Class PN 16, having cast iron body, stainless steel disc ( AISI 316), trim and spring of approved make. including a set of MS flanges, required nos. of nut & bolts all complete. | [7 empty] | #VALUE! | #VALUE!
| a) 80 mm dia | Nos |  |  |  |  | 1138 |  | 2 | 2
| b) 65 mm dia | Nos |  |  |  |  | 1138 |  | 2 | 2
[9 empty] | #VALUE! | #VALUE!
11 | Providing, Fixing & testing of CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493. With fabricated & subssequently epoxy painted clamps/ structural steel supports as required for directed at site including cutting chases and fitting the same with cement concrete /cement mortar as required. All termination points for installation of faucets shall have brass termination fittings. | [8 empty] | 0
[9 empty] | #VALUE! | #VALUE!
| a) 25 mm nominal bore | [5 empty] | VT0128 |  | 25 | 25
| b) 15 mm nominal bore | [5 empty] | VT0128 |  | 26.5 | 26.5
[9 empty] | #VALUE! | #VALUE!
12 | Providing and fixing C.I. double flanged butterfly valve working pressure of 10 Kg/cm2 complete with bolts, nuts, washers 3 mm thick insertion neoprene gasket. | [7 empty] | #VALUE! | #VALUE!
| a) 65 mm nominal bore | [5 empty] | 1108 , 1394 |  | 14 | 14
[9 empty] | #VALUE! | #VALUE!
13 | Variable Speed Hydropneumatic System For Domestic Use ( at terrace for upper 2 floors over each tower ) | [7 empty] | #VALUE! | #VALUE!
[9 empty] | #VALUE! | #VALUE!
| Supply, testing, installation, testing & commissioning of Compact self contained Hydropneumatic system comprising of following : | [7 empty] | #VALUE! | #VALUE!
| Horizontal, multistage, centrifugal clear water pumps with SS-304 casing, S.S 304 impeller and SS-316 shaft, C.I. Base & head TEFC motor (with mechanical seal) Vendor to submit performance curves, dimension detail and technical catalogue of the proposed model for review and information. | [7 empty] | 0
0
| MCC panel with sequential control with mounted microprocessor PID controller and variable frequency drive (VFD) integrated in a single body or as separate components with pressure sensor transmitter (one dedicated to each pump) minimum two lined LCD display, diodes to indicate pump ready, pump running and fault and capable to communicate with other controllers following MODBUS-RTU or BACNET Class-2 protocol through RS485 port. System should be capable to compensate for frictional losses at lower flows. All alarms should be displayed in the controller. System should be equipped with dry running protection. (Quantity of VFD = 1 No.) complete in all respects. | [7 empty] | 0
0
| Pre-charged diaphragm pressure vessel with interchangeable membrane, charging connection, connected to outlet header with necessary flanges, gaskets, isolating valves, nuts/bolts etc. complete (size of pressure vessel shall be of suitable capacity or as per manufacturer calculation / recommendation). | [7 empty] | 0
0
| Set of accessories such as pressure switches, pressure transducers,valve (butterfly / ball valve & NRV of PN 10 rating i.e. 10 kg / cm2 ) , vibration Isolator, GI "heavy class" suction & delivery header & interconnection piping, level controller, pressure gauge inter connecting power and control cabling etc. complete with Vibration eliminator of required quantities complete in all respects. | [7 empty] | 0
0
| For each tower : | [7 empty] | 0
| Capacity/Flow Rate - 300 LPM | [7 empty] | 0
| Pumping Head - 25-30 Mtr | [7 empty] | 0
| Power Requirement (HP) - 3.0 HP each or as per manufacturer recommendation | [7 empty] | 0
| Location - Terrace | [7 empty] | 0
| 1 Set = 2 Nos. Pump (1 Working +1 standby) | [7 empty] | 0
0
| Supply | Set |  |  |  |  | 109 |  | 2 | 2
| Installation, Testing & Commissioning | Set

## Measurement
THAPAR UNIVERSITY PATIALA
M/s. Zamil Airconditioners India Private Limited
P.O. No. : TU/CS/PSJ/17-18/150101/01
Services : Supply, Installation, Testing and Commissioning of Plumbing Pumps & Plumbing Machinery for Boys Hostel and Learning Block
Bill No. : RA-02 (High Side Works) Boys Hostel Sub-station
MEASUREMENT SHEET
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | JMR NO | Quantity |  |  | Remarks
[5 empty] | PREV. | THIS BILL | CUM.
Supply, Installation, Testing and Commissioning of Plumbing Pumps
A) | WATER SUPPLY AND DRAINAGE PUMPS :
1 | Fixed Speed Hydropneumatic System For Domestic/ Flushing OverHead Water Storage Tanks Fillings.
Supply, Installation, Testing & Commissioning of Factory Assembled Compact self contained Hydropneumatic system comprising of following :
Make: Grundfoss / DP or eq.
i) | Vertical, Non-self Priming, multistage, inline, centrifugal clear water pumps with cast iron pump housing, S.S 304 impeller and SS-316 shaft, C.I. Base & head, TEFC motor, "F" insulation class, IP55 enclosure class, 2900 RPM (with mechanical seal) Vendor to submit performance curves and technical catalogue of the proposed model for review and information.
ii) | MCC panel mounted in frame with auto cut in/cut off controls, manual ride over, sequential change over facilty with interconnecting cables, controllers complete in all respects.
iii) | Pressure vessel (200 litres or as of vendors design details) with food grade internal surface painted and food grade pre charged diaphgram with inlet and outlet, pressure switches for auto on/off control, butterfly / ball valve / NRV of suitable pressure rating, vibration isolator, GI "heavy class" suction & delivery header & interconnection piping, control panel with neccessary control cabling etc. complete in all respects.
1.1 | For Boys hostel blocks ( Centralized domestic transfer pump )
■ | Capacity/Flow rate - 250 LPM of each pump
■ | Pumping Head - 60 Mtr
■ | Power Requirement (HP) - 6.0 HP each or as per manufacturer recommendation
■ | Location -(Proposed UG Plumbing Pump Room)
■ | 1 Set = 3 Nos. Pump (2 Working +1 standby)
a) | Supply | Set | 1 |  |  |  | 0
b) | Installation, testing & commissioning | Set | 1 | JMR NO 01 |  | 1 | 1
0
1.2 | For Boys hostel blocks (Centralized flushing transfer pump) |  |  |  |  | 0
■ | Capacity/Flow rate-250 LPM of each pump |  |  |  |  | 0
■ | Pumping Head - 60 Mtr |  |  |  |  | 0
■ | Power Requirement (HP) - 6.0 HP each or as per manufacturer recommendation |  |  |  |  | 0
■ | Location - (Proposed UG Plumbing Pump Room) |  |  |  |  | 0
■ | 1 Set = 2 Nos. Pump (1 Working +1 standby) | set | 1 |  |  | 0
| Installation, Testing & Commissioning | Set | 1 | JMR NO 01 |  | 1 | 1
1.3 | For Boys hostel blocks ( Irrigation pump) |  |  |  |  | 0
■ | Capacity/Flow Rate - 450 LPM of each pump |  |  |  |  | 0
■ | Pumping Head - 50 Mtr |  |  |  |  | 0
■ | Power Requirement (HP) - 7.5 HP each or as per manufacturer recommendation |  |  |  |  | 0
■ | Location - (Proposed UG Plumbing Pump Room) |  |  |  |  | 0
■ | 1 Set = 2 Nos. Pump (1 Working +1 standby) |  |  |  |  | 0
a) | Supply | Set |  |  |  | 0
b) | Installation, testing & commissioning | Set | 1 | JMR NO 02 |  | 1 | 1
2 | Variable Speed Hydropneumatic System For Domestic Use ( at terrace for upper 2 floors over each tower )
Supply, testing, installation, testing & commissioning of Compact self contained Hydropneumatic system comprising of following :
i) | Horizontal, multistage, centrifugal clear water pumps with SS-304 casing, S.S 304 impeller and SS-316 shaft, C.I. Base & head TEFC motor (with mechanical seal) Vendor to submit performance curves, dimension detail and technical catalogue of the proposed model for review and information.
ii) | MCC panel with sequential control with mounted microprocessor PID controller and variable frequency drive (VFD) integrated in a single body or as separate components with pressure sensor transmitter (one dedicated to each pump) minimum two lined LCD display, diodes to indicate pump ready, pump running and fault and capable to communicate with other controllers following MODBUS-RTU or BACNET Class-2 protocol through RS485 port. System should be capable to compensate for frictional losses at lower flows. All alarms should be displayed in the controller. System should be equipped with dry running protection. (Quantity of VFD = 1 No.) complete in all respects.
iii) | Pre-charged diaphragm pressure vessel with interchangeable membrane, charging connection, connected to outlet header with necessary flanges, gaskets, isolating valves, nuts/bolts etc. complete (size of pressure vessel shall be of suitable capacity or as per manufacturer calculation / recommendation).
iv) | Set of accessories such as pressure switches, pressure transducers,valve (butterfly / ball valve & NRV of PN 10 rating i.e. 10 kg / cm2 ) , vibration Isolator, GI "heavy class" suction & delivery header & interconnection piping, level controller, pressure gauge inter connecting power and control cabling etc. complete with Vibration eliminator of required quantities complete in all respects.
2.1 | For each tower :
● | Capacity/Flow Rate - 300 LPM
● | Pumping Head - 25-30 Mtr
● | Power Requirement (HP) - 3.0 HP each or as per manufacturer recommendation
● | Location - Terrace
● | 1 Set = 2 Nos. Pump (1 Working +1 standby)
a) | Supply | Set | 4
b) | Installation, Testing & Commissioning | Set | 4 | JMR NO 3,4,5,6 |  | 4 | 4
3 | Providing and fixing of submersible non-clog, open impeller sump pump with vortex impeller connected to TEFC submersible motor for 415 + 10% volts, 3 phase, 50 cycles A.C. power supply with mechanical seal, pump connector unit with rubber diaphragm and bend of the following specifications, MCC panel ( located on near wall) with auto sequential change over with both pumps shut at low level, one pump working at mid level and both pump working with an alarm hooter at high level, including interconnecting cables, piping works, valves, controls etc. all pre set as required complete in all respects. Cost shall included electrical control panel with starter.
3.1 | Sump Pump Drainage ( Main Pump Room )
a) | Discharge : 400 lpm
b) | Head : 10 metre
c) | HP : 3.0 HP each or as per manufacturer recommendation.
d) | Casing : Aluminium alloy / C.I
e) | Impeller & Shaft: S.S. 410
f) | Solid Handling Capacity: 15 mm
g) | Length of water proof cable with each pump : 10 meter
h) | Length of GI lifting chain with each pump : 5 Meter.
i) | G.I. heavy class header main of suitable diameter and length
j) | Level controller and starter control panel
k) | Quantity : 2 Nos. (1 Working +1 Standby) | Set | 1 | JMR NO 02 |  | 1 | 1
4 | Providing and fixing motorized solenoid valve/rotary actuator (CI body, SS316 disc, EPDM boot seat, SS416 shaft, RPTEF bushing @ PN10 rating) for filling of overhead water tank complete with electrical water level control panel, including by-pass connection for the same dia with manually operated butterfly valve, float valve/ controller and all piping and accessories complete in all respects (Belimo/ Legris make or eq.).
a. | 50 mm dia | Set | 4 | JMR NO 3,4,5,6 |  | 4 | 4
b. | 40 mm dia. | Set | 4 | JMR NO 3,4,5,6,7 |  | 6 | 6
c. | 32 mm dia. | Set | 2 | 3 |  | 2 | 2
5 | Puddle Flange for Water Tanks
Providing and fixing M.S fabricated hot dipped galvanized coating puddle flange comprising of 600 mm dia long M.S class 'B' pipe (screwed end up to 50 mm & flange for more than 50 mm dia) with 6 mm thick M.S plates of required size including cutting holes in centre of plate, inserting pipe & making welded (Arc) joint complete. Same shall be installed with TEC welded joint in position with reinforcement bars of RCC tank wall/slab including making cutout in shuttering during concrete casting of tank of following diameter complete in all respects . (Location: underground tanks.)
a) | 25 mm dia | Each | 6 | 1, 4 |  | 12 | 12
b) | 50 mm dia | Each | 2 | 1, 4 |  | 10 | 10
c) | 80 mm dia | Each | 4 | 4 |  | 1 | 1
d) | 100 mm dia | Each | 6 | 1, 4 |  | 23 | 23
6 | WATER TANK COVER
| Providing and fixing 500 mm dia M.S. water tank cover with 40 mm seat and lockable arrangement complete in all respects including all fitting & accessories complete in all respects. | Each | 4
7 | G.I VENT PIPE
Providing and fixing G.I. Vent Pipe class 'B' (medium duty) for R.C.C water storage tanks comprising of 600 mm long vertical pipe, return bend with mosquito grating & cast brass perforated coupling including all associated civil work complete in all respects.
a) | 150 mm dia | Each | 4
8 | M.S. STRUCTURAL WORK
| Providing and fixing M.S. structural work fabricated from standard sections, (MS rounds, angles, channels etc.) including cutting to size, drilling, welding, including cost of fasteners, clamps in RCC structural members as directed, including two or more coats of synthetic paint over one coat of primer after surface preparation including cutting and making good walls complete in all respects. (For pipe works in pump room ) | Kg | 300
9 | Providing and fixing of mosquito overflow grating /Jali of the following diameters including all fittings & accessories complete in all respects.
a) | 100 mm dia | Each | 4
10 | Providing and fixing forged brass auto air vent valve 10 PN rating including all fitting & accessories complete in all respects.
a) | 25 mm dia | Each | 4
11 | Providing and fixing cast iron double flanged butterfly valve (PN 16) complete with 2 nos. matching flanges, bolts, nuts, 3.0 mm thick compressed asbestos gasket complete in all respects.
a) | 50 mm dia | Each | 2 | JMR NO 1,2,3,4,5,6,7,8 |  | 35 | 35
b) | 80 mm dia | Each | 3 | JMR NO 01,02 |  | 3 | 3
c) | 100 mm dia | Each | 5
12 | EXTERNAL WATER SUPPLY ( BOYS HOSTEL) MAIN LINE FROM PUMP ROOM TO HOSTEL BLOCK BASE
A | IRRIGATION SYSTEM
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m or as required complete in all respects.
a | Pipes, upto 150 mm dia | Mtr | 940 | As per pipe measurement |  | 560.2 | 560.2
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects.
a | 50 mm OD | Mtr | 120
b | 75 mm OD | Mtr | 750 | JMR NO 8 |  | 570.2 | 570.2
3 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect.
b | 20 mm dia. | Each | 7
c | 40 mm dia. | Each | 2
4 | Providing, fixing and testing G.I. Pipe (medium class) including painting with two coats of synthetic enamel paint of approved shade.(for G.H. rising above the ground) ) complete in all respects.
a | 20 mm dia. | Mtr | 10
b | 25 mm dia. | Mtr | 70 | 1, 4, 7, 8, 9, 10 |  | 10 | 10
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged to HDPE tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect.
a | 65 mm dia. | Each | 3
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” and connected to HDPE tail piece complete in all respects. (Optional of sluice valve)
a | 65 mm dia. | Each
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect.
a | Internal size 90 cm x 90cm x 100 cm | Each | 5
b | Internal size 300cm x 300cm x 600 cm | Each | 7
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for C.I. & uPVC specials including necessary excavation, shuttering and centring, curing complete. | Cum | 2
B | FLUSHING SYSTEM
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m or as required complete in all respects.
a | Pipes, upto 150 mm dia | Mtr | 1350 | As per pipe measurement |  | 560.2 | 560.2
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects.
a | 90 mm OD | Mtr | 750 | JMR NO 8 |  | 570.2 | 570.2
3 | Providing , fixing, testing and commissioning brass ball valve full bore type with lever tested to 20 kg/cm2 and female screwed ends,of approved quality complete in all respect.
a | 40 mm dia. | Each | 7
4 | Providing, fixing and testing G.I. Pipe IS 1239 (medium class) with tap off connection from HDPE main pipe with adaptor/ connector etc. and including 4 mm thick Pypekote tape wrapping all around , bitumen paint and covered with 150 mm sand cover all around pipe etc. (for riser to each hostel block ) complete in all respects.
a | 40 mm dia. | Mtr | 600
5 | Providing , fixing, testing and commissioning C.I. double flanged sluice valves conforming to IS 780 of PN- 1.0 with flanged to HDPE tail piece, suitable for key bolts, nuts, washers, 3mm thick insertion rubber gasket with matching flanges etc., complete in all respect.
a | 75 mm dia. | Each | 3
6 | Providing , fixing, testing and commissioning C.I. butterfly valves PN-1.0 complete with bolts, nuts, 1.5 mm thick compressed asbestos gasket and flanges as per Table “E” and connected to HDPE tail piece complete in all respects. (Optional of sluice valve)
a | 75 mm dia. | Each
7 | Providing and fixing single acting Air Realese Valve 50 mm dia as per manufacturer specifications including testing and commissioning complete in all respect. | Each | 1
8 | Providing and constructing masonry valve chamber cms with 75 class designation brick work in cement mortar 1:4 , with C.I. surface box 100mm top diameter, 160mm bottom diameter and 180mm deep(inside) with chained lid and R.C.C. top slab 1:2:4, including necessary excavation , foundation concrete(1:5:10) 100mm th. and 150mm projection allround, inside plastering with cement mortar 1:3(1cement: 3 coarse sand) 12 mm th. finished with a floating coat of neat cement etc., complete in all respect.
a | Internal size 90 cm x 90cm x 100 cm | Each | 10
9 | Providing and fixing anchor blocks of concrete 1:2:4 mix (1 cement : 2 coarse nominal size) for pipes at junctions etc. including necessary excavation, shuttering and centring, curing complete in all respects. | Cum | 3
C | DOMESTIC SYSTEM
1 | Excavating trenches of required width for pipes, etc. including excavation for sockets and dressing of sides in hard/dense soil, ramming of bottom, depth upto 1.5 m including getting out the excavated soil and then returning the soil asrequired in layers by ramming, watering etc. and disposing of surplus excavated soil as directed within a lead of 200 m.
a | Pipes, upto 150 mm dia | Mtr | 1350 | As per pipe measurement |  | 560.2 | 560.2
2 | Providing , fixing and testing HDPE pipes conforming to (IS: 4985 - PE 80 ) PN 10 rated with all fittings e.g. couplings, plugs, tees, bends, reducers, and screwed adoptors, flanged tail pieces etc., welded joint as directed or manufacturer's recommendation including back filling with 150 mm sand all around complete in all respects.
a | 110 mm OD | Mtr | 750 | JMR NO 8 |  | 570.2 | 570.2
Supply, Installation, Testing and Commissioning of Plumbing Machinery
IMPORTANT NOTES :
a) The pump shall be capable of developing the required total head at rated capacity for continuous operation. The pumps shall operate satisfactorily at any point on the Head-Discharge (H-Q) characteristic curve over a range of 50% to 130% capacity. The total head capacity curve shall be continuously rising towards the shut off. The shut off head shall be at least 110% of the total head.
b) All associated piping, valves & other appurtenances shall be paid seperately as per relevant items
c) The Tenderer must submit along with his offer, the make and the model of the pump unit proposed by him.
d) Required power supply would be made available at individual control panels of packaged pumping systems in the pump room and solenoid valves at terrace level.
e) Wherever mechanical seal has been asked for, it must be `factory fitted` at pump manufacturer`s works.
1 | HYDROPNEUMATIC SYSTEMS
1.1 | Supply, installing, testing and commissioning of clear water Factory Fitted packaged hydropneumatic pumping system for general water supply as per following details:
Type of Drive - Variable frequency drive for each pump
System Capacity
Maximum System Discharge : 30 M3/hr.
System Pressure : 6.0 kg/cm2
Pumps- 3 Nos (2W+1S)
Flow of each Pump - 15 M3/hr.
The packaged unit shall be complete with :
1.1 contd. | a) Pumps: Vertical monoblock booster pumpset with mechanical seal
Material of Construction (M.O.C): Corrosion Resistant in general :Casing — C.I./ Stainless Steel -AISI 304
: Impeller — Stainless Steel -AISI 304
: Shaft — Stainless Steel - AISI 304
: Pump Head — Cast Iron/ Stainless Steel - AISI 304
: Base — Cast Iron
: Motor Stool — Cast Iron
Motor: 2900 RPM; 3Ph 415V 50Hz
Insulation Class - F
Protection - IP54 Min.
b) Pressure Tank: FRP vessel with replacable polyetheruethane (PEU) bladder certified for drinking water. Minimum 8 Bar pressure rating — 1 No. of 200 to 250 Lts. Capacity.
c) Interconnecting Pipe work, Valves and Vibration Eliminators : Common suction & delivery headers in hot dipped galvanized steel pipes and fittings, Isolating valves, non return valves and vibration eliminators on suction & delivery side of pumps.
d) Common fabricated base frame, duly painted.
e) Power and control cabling between panel and pumps.
f) Accessories like presure guages, pressure transducers etc.
g) System Control Panel : The system control panel shall be factory built and tested and shall have the following minimum features:
i) Fully protected, powder coated metallic housing.
ii) Complete switchgear, under/over voltage protection, single phase preventors etc.
iii) VFDs for all the pumps
iv) Site programmable application optimised software
v) Integrated Modbus interface for BMS compatibility
vi) Large graphic display with as easy to use menu.
| Programmable Control System shall be PLC based, duly authentiated by the Pump Manufacturer. | Set | 1 | JMR NO 01 |  | 1 | 1
1.1contd | Details of Equipment offered (To be filled in by the tenderer)
Pumps
Make:
Model:
HP/KW:
M.O.C : Casing —……………….. : Impeller — …………….. : Shaft — ……………….
Pressure Tank
Make:
Model:
Capacity
M.O.C : Shell —……………….. : Bladder — ……………..
Valves
Make:
Type:
Size: Suction side —………... Delivery side — ……... NRV — ……………….
Type of Programmable Logic Controller — …………………..
The pump Panel shall be also to convese with Building Management System
Notes: 1) Switchgear and starter ratings are indicative. The Tenderer shall quote for the actual rating required as per the pump model proposed by him.
2) Provision for BMS connectivity. The panel should have sufficient no. of potential free contacts for connectivity with Building Management System for monitoring purposes
2 | SUMP DRAINAGE PUMPS
2.1 | Supply, installing, testing and commissioning drainage pumping system in the sump of Under ground Pump Room comprising of the following:
a) 2 Nos.Vertical fully floodable type submersible drainage pumps in close coupled design single stage, suitable for handling minimum 12 mm dia solids.
Duty
Discharge of each pump : 300 LPM
Working Head : 14 M
Material of Construction (M.O.C): Corrosion Resistant in general
: Bearings — Anti friction, prelubricated ball bearings, packed with grease for life.
Motor: — Dry Motor with built in over load protection
Protection - IP68.
Insulation Class - F
b) Electric control panel for automatic operation of pumps as per the water level in the sump.The pump operation shall be controlled with magnetic float type level controller.The Panel shall comprise of incoming switch/MCB, voltmeter & ammeter, On-Off-Trip lamps, starters with circuit breakers for each pump, single phase preventor for three phase motors only for each starter, rotating start sequence, both pumps to work simultaneously to meet peak flow There shall be an audio-visual alarm, if any pump fails to start.
c) Power cabling and control cabling between magnetic float type controller panel and pump panels including cable tray as required .
d) Each pump should be skid base mounted of 9" height to avoid mud choking.
| e) Pump suspension systemwith Stainless Steel Sling wire with `U` clamp. | Set | 1 | 1 |  | 1 | 1
2.1 contd. | Details of Pump offered (To be filled in by the tenderer)
Make:
Model:
HP/KW:
M.O.C : Casing —……………….. : Impeller — …………….. : Shaft — ……………….
4 | CABLING AND MAIN PANEL
4.1 | Supplying and fixing of following types and sizes of 1.1 KV grade PVC insulated conductor armoured cable conforming to IS : 1554.
| a) 4C 4 sq.mm. Copper conductor | M | 50
| c) 4C 16 sq.mm. `Al' conductor | M | 30 |  |  | 141.8 | 141.8
4.2 | Supplying, laying & terminating of following types and size of 1.1 KV grade PVC isulated armoured control cables conforming to IS : 1554 Part-II
| a) 2C 1.5 sq.mm.Cu. Conductor | M | 100
| b) 3C 1.5 sq.mm.Cu. Conductor | M | 100
4.3 | Supplying and making end termination with brass double compression glands and copper/aluminium lugs for following size of PVC insulated and PVC sheathed/XLPE copper/aluminium conductor cable of 1.1 KV grade as required :
| a) 4C 4 sq.mm. Copper conductor | Set | 4
| c) 4C 16 sq.mm. `Al' conductor | Set | 2
4.4 | Providing and fixing following size G.I. strip / wire on surface or in recess for body earthing of motors as required.
| a) 25x6 mm G.I. strip | M | 50
| b) 8 SWG dia. | M | 100 | JMR NO 11 |  | 124 | 124
4.5 | Supply, fabricating and installing following size of perforated M.S. powder coated (of approved shade) (0.65 micron) cable trays including horizontal and vertical bends, reducers, tees, cross members and other accessories as required and duly suspended from the ceiling with M.S. suspenders and including painting etc. as required :
| a) 100 mm. width x 40 mm. depth x 1.6 mm. thickness | M | 30
4.6 | Supply, installation, testing and commissioning of electric pump control panel metal clad cubicle type suitable for 440V AC three phase 50Hz supply system. The panel shall be completely compartmentalised and complete with Aluminium Bus Bars, designation labels as per requirement, continuous Aluminium earth bar 40mm x 6 mm, panel separators, protective screens, cable clamping support system, top/bottom cable gland plates for incoming and out going cable entries as per details given below:
MAIN PANEL WATER PUMPING SYSTEM
INCOMER
160 A 36KA FP MCCB with phase spreader and extended rotary handles - 1 No.
BUSBARS
A set of 200 A 415V 50Hz TPN 3 Ph 4 wire aluminium busbars. C./D. 1 Amp/ mm2.
INSTRUMENTS FOR INCOMER
A set of instrumentation with a set of Current transformer 100/5A with Ammeter 0-100A, Selector Switch, Voltmeter 0-500V with selector switch, a set of phase indicating lights with mcb fuses and energy meter (KWH).
OUTGOING FEEDERS
16A DP 10KA MCB - 2 No.
25A DP 10KA MCB - 2 No.
25A FP 10KA MCB - 2 No.
| 100A TPN 25KA MCCB with phase spreader and extended rotary handle - 2 No. | Set | 1
5 | PIPE WORK AND VALVES
5.1 | Providing, fixing, jointing, testing and commissioning medium class (Class B) G.I. Pipe work conforming to IS:1239 (Part I)-1990 for pipes upto 150 mm dia.and MS pipe work conforming to IS:3589-1991 for pipes above 150 mm dia. with all fittings, flanges, specials & clamps effecting proper connections, including painting with two coats of epoxy paint of approved quality and shade over a coat of primer on exposed pipework, complete in all respects: (Pipe work restricted within the plant room for suction and delivery headers and delivery pipe of submersible pumps)
| a) 100 mm dia pipe | M | 30 | JMR NO 1,2 |  | 113.05 | 113.05
| b) 80 mm dia pipe | M | 5 | 1, 3, 4, 7, 8, 9, 10 |  | 255.4 | 255.4
| c) 65 mm dia pipe | M | 20 | 4 |  | 3.75 | 3.75
| d) 50 mm dia pipe | M | 20 | 1, 3, 4, 6, 7, 8, 9, 10 |  | 81.7 | 81.7
| e) 40 mm dia pipe | M | 10 | 2, 6, 7, 8, 9, 10 |  | 55.3 | 55.3
5.2 | Providing and fixing butterfly valve of approved make including a set of MS flanges, required nos. of nut & bolts all complete and as per following specification:
MOC:
Body - Cast Iron
Shaft - Carbon Steel / Stainless Steel
Body Liner - EPDM/ nitrile rubber
Disc - Epoxy coated C.I./ D.I.
| a) 100 mm dia ( with lever) (PN 16) | No. | 6 | 1, 4 |  | 13 | 13
| b) 65 mm dia ( with lever) (PN 16) | No. | 3 | 1, 3, 4, 7, 8, 9, 10 |  | 14 | 14
0
5.3 | Providing and fixing Dual plate (Wafer type) check valve (non return valve) of Class PN 16, having cast iron body, stainless steel disc ( AISI 316), trim and spring of approved make. including a set of MS flanges, required nos. of nut & bolts all complete. |  |  |  |  | 0
0
| a) 100 mm dia | No. | 1 | 1 |  | 3 | 3
| b) 50 mm dia | No. | 2 | 1, 3, 4, 7, 8, 9, 10 |  | 24 | 24
5.4 | Providing and fixing of flanged C.I (Pot) strainer on suction ends submerged in water tanks, all complete.
| a) 100 mm dia | No. | 4 | 1, 4 |  | 6 | 6

## Meas. detail-Variation Item
c
M/s. Zamil Airconditioners India Private Limited
Services : Supply, Installation, Testing and Commissioning of Plumbing Machinery
P.O. No. : TU/CS/PSJ/17-18/150101/01
Bill No. : RA-02 (High Side Work) Boys Hostel Sub-station
ITEM NO. | DESCRIPTION OF WORK | UNIT | BOQ Qty. | SUPPLY RATE | ITC RATE | Page No. | Quantity
[7 empty] | PREV. | THIS BILL | CUM.
| Extra Items | [7 empty] | 0
| Electrical | [7 empty] | 0
1 | Providing and fixing following size G.I. strip / wire on surface or in recess for body earthing of motors as required. | [7 empty] | 0
0
| a) 32x6 mm G.I. strip | M |  |  |  | 11 |  | 46 | 46
0
2 | Supply, fabricating and installing following size of perforated M.S. powder coated (of approved shade) (0.65 micron) cable trays including horizontal and vertical bends, reducers, tees, cross members and other accessories as required and duly suspended from the ceiling with M.S. suspenders and including painting etc. as required : | [7 empty] | 0
0
| a) 300 mm. width x 40 mm. depth x 1.6 mm. thickness | M |  |  |  | 11 |  | 8.7 | 8.7
0
| b) 150 mm. width x 40 mm. depth x 1.6 mm. thickness | M |  |  |  | 11 |  | 66.2 | 66.2
0
3 | Supply and laying in cable including testing and commissioning of the following 1100 volt grade armoured XLPE insulated and sheathed aluminium conductor armoured cable complete as required. The costs shall include providing a gap of 1D between all the cables being laid and properl clamping with cable clamps and ties. Prices shall include providing and fixing of Identification tags for all cables and route markers for cables in ground etc. as per specification and or as per direction of Project in-charge. | [7 empty] | 0
0
| a) 3 –1/2 core 300 Sq mm |  |  |  |  | 11 |  | 39.3 | 39.3
| b) 4 core 35 Sq mm |  |  |  |  | 11 |  | 110 | 110
| c) 4 core 25 Sq mm |  |  |  |  | 11 |  | 17.7 | 17.7
| d) 4 core 16 Sq mm |  |  |  |  | 11 |  | 127 | 127
| e) 4 core 10 Sq mm |  |  |  |  | 11 |  | 14.8 | 14.8
0
4 | Cable end termination XLPE insulated 1100 Volt grade cables including the cost of crimping tinned copper heavy duty lugs, double compression glands, insulation tape etc. complete as required and as below. | [7 empty] | 0
0
| a) 3 –1/2 core 300 Sq mm |  |  |  |  | 11 |  | 2 | 2
| b) 4 core 35 Sq mm |  |  |  |  | 11 |  | 2 | 2
| c) 4 core 25 Sq mm |  |  |  |  | 11 |  | 2 | 2
| d) 4 core 16 Sq mm |  |  |  |  | 11 |  | 8 | 8
| e) 4 core 10 Sq mm |  |  |  |  | 11 |  | 2 | 2
Plumbing
1 | Providing ,Fixing, testing and commissioning of vitreous china Wall/floor mounting type (European type) water closet with C.P.Bolts, nuts other fixing arrangement solid plastic seat with lid, C.P. brass hinges and rubber buffers, concealed dual flushing cistern ( 3-6 liters/flush) with flush pipe , clamp with adaptor, WC flexible connector, C.P. brass screws and washers complete, including cutting and making good the walls floors where required complete in all respects. | Nos
2 | Providing ,Fixing, testing and commissioning of vitreous china wash basin Under Water Counter round/oval with waste coupling fitting,32mm CP cast brass bottle trap and pipe to wall with CP wall flange and rubber adopter for waste connection, CP deck mounted mixer with battery operated and built in sensor for auto cut in/cut off operation complete including cutting and making good the walls where required complete in all respects. | Nos
3 | Providing ,Fixing, testing and commissioning of 15 mm dia angle valve with flanges including 450 mm long copper connecting pipe with nuts complete. | Nos
4 | Providing, Fixing & testing of uPVC SWR (Type-B) pipes conforming to IS 13592 along with all required fittings like tees, bends, cowls, crosses with or without access doors jointed with approved solvent cement fixed to walls and ceilings including angle supports with clamps and structural support as per good practice /manufacturers recomandation and complete including core cut in R.C.C/brick work (slab/beam/wall) and making good the same whatever required. Soil, Waste and Vent pipe)
a} | 110mm OD | RM |  |  |  | 2,3,5,7,8,9,10 |  | 142 | 142
0
5 | Providing, Fixing & testing of f uPVC pipes, conforming to IS 4985 class 3 (6 kg/cm2) including injection moulded fittings, jointing with solvent cement, cutting and making good the floors and walls and jointing to trap/waste pipe, complete of outer dia. | [6 empty] | 0
| a) 50 mm OD | RM |  |  |  | 2 |  | 1.8 | 1.8
| b) 40 mm OD | RM |  |  |  | 2,5,6 |  | 22.9 | 22.9
0
6 | Providing and laying cement concrete 1:2:4 mix (1 cement:2 coarse sand: 4 graded stone aggregate 20 mm nominal size) 75 mm in bed and alround uPVC soil & waste pipes including excavation, refilling where required complete in all respect as per standard design. | [6 empty] | 0
| Pipe 90 to 110 mm OD | RM | [5 empty] | 0
| Pipe 40 to 63 mm OD | RM | [5 empty] | 0
0
7 | Providing, Fixing & testing of uPVC P or S trap including jointing with solvent cement and making good the walls, floors etc., complete of nominal size. | Nos |  |  |  | 2,5 |  | 5 | 5
0
8 | Providing, Fixing & testing of 125 mm dia, 1 mm thick Stainless steel grating with frame for floor traps or drains of required pattern including cutting and making good the floors complete. | [6 empty] | 0
| a) 125mm dia over Floor Trap & floor Drain | Nos |  |  |  | 2,5 |  | 6 | 6
0
9 | Providing, Fixing & testing of stainless steel ball valve working pressure of 10 Kg/cm2 with wheel & female screwed ends of approved quality to I complete in all respects. | [6 empty] | 0
| a) 25 mm dia | Nos |  |  |  | 1,3,4,7,8,9,10 |  | 10 | 10
| b) 20 mm dia | Nos |  |  |  | 5 |  | 1 | 1
| c) 15 mm dia | Nos |  |  |  | 1,3,4,7,8,9,10 |  | 12 | 12
0
10 | Providing and fixing Dual plate (Wafer type) check valve (non return valve) of Class PN 16, having cast iron body, stainless steel disc ( AISI 316), trim and spring of approved make. including a set of MS flanges, required nos. of nut & bolts all complete. | [6 empty] | 0
| a) 65 mm dia | Nos |  |  |  | 4 |  | 2 | 2
0
11 | Providing, Fixing & testing of CPVC (Chlorinated Poly Vinyl Chloride) water supply pipes with pipe as per CTS SDR 11 (operating pressure - 7 Bar @ 82 Deg C and 28 Bar @ 23 Deg C)for pipes from 1/2 Inch to 2 Inch. Schedule 40 Pipe to be used from 2-1/2 Inch to 6 Inch. Pipes shall be joined using solvent welded CPVC fittings i.e. Tees, Elbows, Couplers, Unions, Reducers, brushings etc. including transition fittings (connection between CPVC & metal pipe/GI) i.e. Brass Adaptors (both Male & Female threaded) conforming to ASTM D-2846. ASTM F441 with only CPVC solvent cement conforming to ASTM F-493. With fabricated & subssequently epoxy painted clamps/ structural steel supports as required for directed at site including cutting chases and fitting the same with cement concrete /cement mortar as required. All termination points for installation of faucets shall have brass termination fittings. | [6 empty] | 0
0
| a) 25 mm nominal bore |  |  |  |  | 2 |  | 25 | 25
| b) 15 mm nominal bore |  |  |  |  | 5 |  | 26.5 | 26.5
0
12 | Providing and fixing C.I. double flanged butterfly valve working pressure of 10 Kg/cm2 complete with bolts, nuts, washers 3 mm thick insertion neoprene gasket. | [6 empty] | 0
| a) 65 mm nominal bore |  |  |  |  | 1,3,4,7,8,9,10 |  | 14 | 14
0
13 | Variable Speed Hydropneumatic System For Domestic Use ( at terrace for upper 2 floors over each tower ) | [6 empty] | 0
0
| Supply, testing, installation, testing & commissioning of Compact self contained Hydropneumatic system comprising of following : | [6 empty] | 0
| Horizontal, multistage, centrifugal clear water pumps with SS-304 casing, S.S 304 impeller and SS-316 shaft, C.I. Base & head TEFC motor (with mechanical seal) Vendor to submit performance curves, dimension detail and technical catalogue of the proposed model for review and information. | [6 empty] | 0
0
| MCC panel with sequential control with mounted microprocessor PID controller and variable frequency drive (VFD) integrated in a single body or as separate components with pressure sensor transmitter (one dedicated to each pump) minimum two lined LCD display, diodes to indicate pump ready, pump running and fault and capable to communicate with other controllers following MODBUS-RTU or BACNET Class-2 protocol through RS485 port. System should be capable to compensate for frictional losses at lower flows. All alarms should be displayed in the controller. System should be equipped with dry running protection. (Quantity of VFD = 1 No.) complete in all respects. | [6 empty] | 0
Pre-charged diaphragm pressure vessel with interchangeable membrane, charging connection, connected to outlet header with necessary flanges, gaskets, isolating valves, nuts/bolts etc. complete (size of pressure vessel shall be of suitable capacity or as per manufacturer calculation / recommendation).
Set of accessories such as pressure switches, pressure transducers,valve (butterfly / ball valve & NRV of PN 10 rating i.e. 10 kg / cm2 ) , vibration Isolator, GI "heavy class" suction & delivery header & interconnection piping, level controller, pressure gauge inter connecting power and control cabling etc. complete with Vibration eliminator of required quantities complete in all respects.
For each tower :
Capacity/Flow Rate - 300 LPM
Pumping Head - 25-30 Mtr
Power Requirement (HP) - 3.0 HP each or as per manufacturer recommendation
Location - Terrace
1 Set = 2 Nos. Pump (1 Working +1 standby)
| Supply | Set | [5 empty] | 2 | 2
| Installation, Testing & Commissioning | Set

## Variation electrical items
Measurement of Electrical items
GH PUMP ROOM
| 4c 16sqmm | 4c 25sqmm | 4c 35sqmm | 3.5c 300sqmm | g.i strip 32*6 | 8 swg wire | 150mm cable trey | 300mm cable trey | gland termination
Main Panel to Sub Panel |  |  |  | 39.3 |  |  |  |  | 2
Sub panel to Hydro phenumatic pump panel |  | 17.7 |  |  | 14 | 25.2 | 9.9 | 1.2 | 2
Sub panel to Bore well pump starter |  |  | 110 |  |  | 25.6 | 5.3 | 7.5 | 2
Sub panel to sump pump panel | 14.8 |  |  |  |  | 35 | 6
TOTAL | 14.8 | 17.7 | 110 | 39.3 | 14 | 85.8 | 21.2 | 8.7 | 6
BH PUMP ROOM |  |  |  |  | JMR NO 12 | JMR NO 11
| 4c 16sqmm | 4c 25sqmm | 4c 35sqmm | 3.5c 300sqmm | g.i strip 32*6 | 8 swg wire | 150mm cable trey | 300mm cable trey | gland termination
main panel to sub panel
sub panel to pump starter 1 | 35 |  |  |  | 14 | 5 | 9.5 |  | 2
sub panel to pump starter 2 | 31.5 |  |  |  |  | 9 | 12 |  | 2
sub panel to pump starter 3 | 31.5 |  |  |  | 18 | 10 | 8 |  | 2
sub panel to sump pump | 29 |  |  |  |  | 14.2 | 10 |  | 2
TOTAL | 127 | 0 | 0 | 0 | 32 | 38.2 | 39.5 | 0 | 8
| 141.8 | 17.7 | 110 | 39.3 | 46 | 124 | 60.7 | 8.7 | 14