## Sheet1
Excavation, Foundation & Plinth | 20%
Civil structure | 60%
Finishing | 20%
Overall | 100%
Absolute/ In terms of Weightage
|  | Mill House | Absolute | 90% | 40% | 0%
|  |  | In terms of Weightage | 18% | 24% | 0% | 42%
|  | Control Panel Room for Mill House (G+1) |  | 100% | 10% | 0%
|  | Cooling Tower for Mill Bearing |  | 100% | 0% | 0%

## Sheet3
Falling Film Evaporator | 2650000
Falling Film Evaporator | 2650000
Falling Film Evaporator | 2650000
Falling Film Evaporator | 3315000
Falling Film Evaporator | 3315000
Falling Film Evaporator | 3315000
Falling Film Evaporator | 2600000
Falling Film Evaporator | 2600000
Falling Film Evaporator | 2600000
Juice Clarifier | 3000000
Juice Clarifier | 3000000
Falling Film Evaporator | 3500000
Falling Film Evaporator | 3500000
Falling Film Evaporator | 3500000
Falling Film Evaporator | 3500000
Falling Film Evaporator | 2650000
Falling Film Evaporator | 2650000
Falling Film Evaporator | 3315000
Falling Film Evaporator | 3315000
Rotary Screen | 4000000
Foundation Bolts & Shim Plates | 1000000
Foundation Bolts for Syrup Plant and Carriers | 600000
Foundation Bolts for Syrup Plant and Carriers | 1500000
Foundation Bolts for Syrup Plant and Carriers | 300000
Condenser Bellows | 100000
51625000

## Sheet2
Excavation, Foundation & Plinth | 20%
Civil structure | 60%
Finishing | 20%
Overall | 100%
Particulars | Absolute/ In terms of Weightage |  |  | Overall Completion Percentage
| Foundation | Civil structure | Finishing |  |  | Overall Completion Percentage
Plant Buildings and its progress
Milling House Section
Mill House | 90% | 40% | 0% |  | 1
| 18% | 24% | 0% | 42% | 2 | 42%
Control Panel Room for Mill House (G+1) | 100% | 10% | 0% |  | 3 | 30%
| 20% | 6% | 0% | 26% | 4 | 26%
Cooling Tower for Mill Bearing | 100% | 0% | 0% |  | 5 | 20%
| 20% | 0% | 0% | 20% | 6 | 20%
Boiler Section |  |  |  |  | 7
Boiler & Bagasse Handling Section | 100% | 0% | 0% |  | 8 | 20%
| 20% | 0% | 0% | 20% | 9 | 20%
RCC Chimney | 0% | 0% | 0% |  | 10 | 0%
| 0% | 0% | 0% | 0% | 11 | 0%
Power House Section |  |  |  |  | 12
Power House | 100% | 20% | 0% |  | 13 | 40%
| 20% | 12% | 0% | 32% | 14 | 32%
Control Room for Power House | 100% | 40% | 0% |  | 15 | 50%
| 20% | 24% | 0% | 44% | 16 | 44%
Cooling Tower for Power House | 100% | 0% | 0% |  | 17 | 20%
| 20% | 0% | 0% | 20% | 18 | 20%
Raw Syrup Plant Section
Raw Syrup Plant | 100% | 100% | 50% |  |  | 90%
| 20% | 60% | 10% | 90% |  | 90%
MCC & DCS Control Room for Raw Syrup Plant (G+1) | 100% | 0% | 0% |  |  | 20%
| 20% | 0% | 0% | 20% |  | 20%
Cooling Tower for Raw Syrup Plant | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Other Sections
Evaporator Section | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Distillation & MSDH Section | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Cooling Tower for Distillation & MSDH Evaporator Section | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Fermentation Section | 100% | 10% | 0% |  |  | 35%
| 20% | 6% | 0% | 26% |  | 26%
MCC Room for Fermentation Section | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Cooling Tower for Fermentation Section | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Ethanol Storage Section (PESO) | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Condensate Polishing Unit for Distillery | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Excess Water Cooling Tower | 100% | 0% | 0% |  |  | 30%
| 20% | 0% | 0% | 20% |  | 20%
Raw Spent Wash Lagoon | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Water Treatment Plant | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Fire Fighting System | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Condensate Polishing Unit for Sugar (Milk of Lime Station) | 100% | 5% | 0% |  |  | 20%
| 20% | 3% | 0% | 23% |  | 23%
Effluent Treatment Plant | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Raw Water Tank | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Bagasse Yard | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Service Water Reservoir | 100% | 100% | 50% |  |  | 90%
| 20% | 60% | 10% | 90% |  | 90%
Lagoon for Sugar | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Switch Yard | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Weigh Bridge Room | 0% | 0% | 0% |  |  | 0%
| 0% | 0% | 0% | 0% |  | 0%
Average Completion |  |  |  | 15.26% |  | ~30%
Non-Plant Buildings and its progress
Security Rooms | 0% |  |  | 0% |  | 0%
Time Office | 0% |  |  | 0% |  | 0%
Excise Office | 0% |  |  | 0% |  | 0%
Office for CE, CC, LAB & Toilet | 0% |  |  | 0% |  | 0%
Workers Toilet | 0% |  |  | 0% |  | 0%
Landscape Development
Internal Roads |  |  |  | 0% |  | 0%

## Sheet4
Stages | Weightage
Excavation, Foundation & Plinth | 20%
Civil structure | 60%
Finishing | 20%
Overall | 100%