## Pie Chart
Particulars | Amount | Particular | Amount In Rs. In Cr.
Land Cost & site development | 3.80 Cr. | Land Cost & site development | 3.8
Technical Civil works | 6.66 Cr. | Technical Civil works | 6.66
Plant & Machinery | 55.29 Cr. | Plant & Machinery | 55.29
Computers and other assets | 1.42 Cr. | Computers and other assets | 1.42
Preoperative expenses (incl. IDC) | 3.69 Cr. | Preoperative expenses | 3.69
Contingency @ 2.7% | 1.62 Cr. | Contingency | 1.62
TOTAL | 72.48

## Civil Status
S No. | Discription | Proposed Area(Sq.mt.) | Status
1 | Puff Panel for Dairy Building Width 105m x Height 7.5m x 4 Nos. Panel | 3150 | Work yet not started
2 | Puff Panel for Dairy Building Length 115m x Height 7.5m x 8 Nos. Panel | 6600 | Work yet not started
3 | Puff Panel for Dairy Building Ceiling 115m Length x 105m Width | 12075 | Work yet not started
4 | Puff Panel for Hygiene Station 10m Length x 10m Width | 2000 | Work yet not started
5 | Flooring & Civil Work 80m Length x 105 Width | 8400 | Work yet not started
Total |  | 32225
S No. | Discription | Proposed Area(Sq.mt.) | Status
1 | Main Building | 15276.1 | Column work has been started
2 | Utilities | 1236 | Work yet not started
3 | Tiolet | 80 | Work yet not started
4 | Boiler | 480 | Work yet not started
5 | Security Block | 37.2 | Work yet not started
6 | Adminisrative block | 180 | Work yet not started
Total |  | 17289.3

## Civil work
Cost of the Civil Work
S NO. | Description | L | B | H | volume in cubic. ft. | No of column | total volume in cubic. ft. | Quantity | Unit | Type of structure | Rate per unit | Value assessed | Remark
1 | Footing | 4.5 | 3.5 | 5 | 78.75 | 203 | 15986.25 | 452.6759 | Cum | RCC | 8340.85 | 3775701.9202 | CPWD DSR 2023 vol-1, ref-4.1.2
2 | Column Type A | 2 | 2 | 6 | 24 | 148 | 3552 | 100.5805 | Cum | RCC | 8340.85 | 838926.779 | CPWD DSR 2023 vol-1, ref-4.1.2
3 | Column Type B | 2 | 1.5 | 6 | 18 | 55 | 990 | 28.0334 | Cum | RCC | 8340.85 | 233822.4975 | CPWD DSR 2023 vol-1, ref-4.1.2
4 | Boundary Wall | 800 |  | 2.1341 |  |  |  | 18377.3902 | sq. ft. | Precast | 100 | 1837739.0244 | Market rate
| Brick work | 686 |  | 0.8 |  |  |  | 686 | RMT | Brickwork | 4500 | 3087000 | Market rate
| Columns in Brickwork | 0.3 | 0.23 | 1.5 | 0.1035 | 382 | 39.537 | 39.537 | Cum | R.C.C | 8340.85 | 329772.1864 | CPWD DSR 2023 vol-1, ref-4.1.2
5 | Steel in Columns | [6 empty] | 44765 | KG | TMT Bars | 80 | 3581200 | Market rate
Total | [11 empty] | 13684162.4076
|  | 380.9524 | 381.9524
685.4

## TMT Calculation
Invoice No. | Invoice Date | Vendor Name | Amount |  | quantity | 30 | Rate per Kg weight | man power charge | Total | Add Gst | Final amount
G/2023-24/5422 | 2024-02-20 | Shri Rathi Steel Ltd | 1416788 | 1416788 | 24720 |  | 0.057313 | 10 | 10.0573 | 1.8103 | 11.8676
G/2023-24/6001 | 2024-03-17 | Shri Rathi Steel Ltd | 1157917 |  | 44765 |  | 0.025867 | 10 | 10.0259 | 1.8047 | 11.8305
| Quantity(ton) | Quantity(ton) |  |  | Quantity(KG) | Quantity
| 2.895 | 3.16
| 4.19 | 4.12
| 4.65 | 4.845
| 7.91 | 7.83
| 5.075 | 0.09
Total | 24.72 | 20.045 |  |  | 24720 |  | 20045
Total Quant. | 44.765 |  |  |  | 44765

## Land
Land
Sqmtr | acre
43161.8 | 10.6678
S no. | Village | Kathi No. | Khasra No. | Seller | Extent of land
1 | Siswal | 245/316 | 40 / /1 / 2 (6-13), 2 /2 (7-0), 3/2 (7-3), 8 (8-0), 9(8-0), 10 (7-8), 13 (8-0), 18/1 (2-6) | Bimla | 54 Kanal 10 Marla
2 | Siswal | 246/317 | 140 / /11 (7-8), 12 (8-0), 19 (8-0),20 (7-8) | Bimla | 30 Kanal 16 Marla
Total |  |  |  |  | 85 Kanal 6 Marla
[6 empty] | 32105000 | amount
[6 empty] | 2247350 | stamp
[6 empty] | 34352350 | Total

## P & M
[6 empty] | 40 | 64 | 38.4
Sl. No. | Invoice No. | Invoice Date | Vendor Name | Amount | Advances | Remarks | Calculation
1 | 18/23-24 | 2023-11-24 | Sahiba Fabrication | 71232000 | 21369600 | 30% Advance against PI No.18/23-24 70% after delivery | 21369600
2 | 18-1/23-24 | 2023-11-24 | Sahiba Fabrication |  |  |  |  | 12062400
3 | 18-2/23-24 | 2023-11-24 | Sahiba Fabrication
| HR/23-24/005 | 2023-11-24 | Sahiba Fabrication | 35840000 | 14336000 | 40% Advance | 14336000
5 | 5450050306 | 2024-01-16 | Multivac | 6136000 | 1560000 | 30% Advance against PI No. 5450050306 40% Before delivery, 20% after Delivery, 10% after installation | 1560000 | 1560000 |  | 1840800
6 | 187 | 2023-11-12 | Dima | 24456344 | 9782806 | 100% Advance has been made | 9782806
7 | FBE/CCBPE/2023-2024 | 2024-02-15 | Food & Biotech Engineer | 159300000 | 54000000 | 40% advance againt PI No. (FBE/CCBPE/2023-2024) 60% after Delivery | 54000000
5 | 2008960 | 2024-02-23 | FAM NV | 5292013 | 1587560 | 30% advance made | 1587560 | 1587603.9
8 | 10 | 2023-12-05 | Ashish Technical pvt ltd | 6496000 | 3897600 | 60 % Advance & 40% Before Dispatch | 3897600 | 3897600
9 | 531 | 2024-02-15 | Frick India ltd | 45430000 | 11550000 | 30% advance against PI No. (531) 70% after delivery | 11550000
10 | 131 | 2024-02-17 | Green-Tech India | 5723000 | 1940000 | 40% advance made | 1940000 | 1940000 | 4850000
11 | 325 | 2024-02-19 | Uttam Enviro tech engineers pvt. Ltd. | 6490000 | 2750000 | 40% Advance has been made | 2750000 | 2596000 |  | 5500000 | 2200000
12 | 230 | 2024-02-28 | Urjex Boiler pvt.ltd. | 14160000 | 4956000 | 40% advance made | 4956000 | 4956000 | 1200000
13 | 2402008 | 2024-02-29 | PPml ltd | 24000 | 24000 | 100% Advance has been made | 24000
14 | 101 | 2024-03-19 | Fillpack | 8260000 | 2800000 | 40% advance | 2800000
15 | bpm/2324/629 | 2024-03-22 | Balaji Packing machine | 1062000 | 531000 | 50% advance aginst PI No. (bpm/2324/629) 50% after Delivery | 531000
16 | PI_240308 | 2024-03-21 | NVS Industries | 6372000 | 1620000 | 30% advance PI No. (PI_240308) 70% after Delivery | 1620000
17 | PI/23-24/0082 | 2024-03-22 | Tech-N-Tech Engineers | 33405800 | 14155000 | 50% advance against PI No. (PI/23-24/0082) 50% after Delivery | 14155000
18 | 686 | 2023-12-30 | M/s mittal Machinery Store | 26267 | 26267 | 100% Advance has been made | 26267
19 | 685 | 2023-12-30 | M/s mittal Machinery Store | 49501 | 49501 | 100% Advance has been made | 49501
20 | 741 | 2023-12-21 | M/s mittal Machinery Store | 3280 | 3280 | 100% Advance has been made | 3280
21 | AIS/23-24/1162 | 2024-03-05 | Advance Iron & Steel Company | 439928 | 439928 | 100% Advance has been made | 439928
22 | AIS/23-24/1189 | 2024-03-14 | Advance Iron & Steel Company | 217002 | 217002 | 100% Advance has been made | 217002
23 | PSINV-23-04913 | 2024-03-05 | KL Steels Pvt Ltd | 1591703.35 | 1591703.35 | 100% Advance has been made | 1591703.35
25 | PSINV-23-04923 | 2024-03-06 | KL Steels Pvt Ltd | 1785933.53 | 1785933.53 | 100% Advance has been made | 1785933.53
27 | PSINV-23-05107 | 2024-03-18 | KL Steels Pvt Ltd | 1682789.39 | 1682789.39 | 100% Advance has been made | 1682789.39
28 | PSINV-23-05108 | 2024-03-18 | KL Steels Pvt Ltd | 203625.72 | 203625.72 | 100% Advance has been made | 203625.72
29 | G/2023-24/5422 | 2024-02-20 | Shri Rathi Steel Ltd | 1416788 | 1416788 | 100% Advance has been made | 1416788
30 | G/2023-24/6001 | 2024-03-17 | Shri Rathi Steel Ltd | 1157917 | 1157917 | 100% Advance has been made | 1157917
Total |  |  |  | 438253891.99 | 155434300.99 |  | 155434300.99
416
144063934.99
For Civil
31 | 2024-02-08 | Swaraj Precast | 118944 | 100% Advance has been made |  | 118944
32 | 2024-02-15 | Swaraj Precast | 196258 | 100% Advance has been made |  | 196258
33 | 2024-02-15 | Swaraj Precast | 196258 | 100% Advance has been made |  | 196258
36 | 2024-02-20 | Swaraj Precast | 255730 | 100% Advance has been made |  | 255730
35 | 2024-02-20 | Swaraj Precast | 190310 | 100% Advance has been made |  | 190310
30 | 30-02-2024 | Swaraj Precast | 148680 | 100% Advance has been made |  | 148680
40 | 2024-02-09 | Swaraj Precast | 118944 | 100% Advance has been made |  | 118944

## P & M (TEV)
Main Equipments
S. No: | Item |  | Quantity | Approved/ Not Approved by MoFPI | Status
A | Milk Procurement
1 | Bulk coolers, 2000 KL Cap |  | 40 | Not approved | Yet to arrive on site
2 | Computerized Milk Weighment & Testing |  | 40
B | Milk Reception
1 | Thermisor cap 25 KL/hr ho deg.C/ 15 Sec |  | 1 | Approved | Yet to arrive on site
2 | Weigh Bridge |  | 1
3 | Storage Silos 60 KL |  | 3
C | Milk Processing
1 | Milk Pasteuizer 25 KL/hr |  | 1 | Approved | Yet to arrive on site
2 | Bactofuge 25 KL/hr - Used for cheese |  | -
3 | Milk Separator 25 KL/hr |  | 1
4 | Cream Pasteuizer 3 KL/hr |  | 1
5 | Chilled Water |  | 1
6 | Storage Silos 60 KL (PMT) |  | 4
7 | Cream Silos 5 KL |  | 2
8 | Homogenizer |  | 1
D | Cheese Equipments
1 | Double 'O' Vats cap.15000/16000 |  | 3 | Approved | Yet to arrive on site
2 | Finishing Vats, cap 10 KL |  | 3
3 | Cooking and Stretching 2.0/2.5 HT.batch stream |  | 1
4 | Drum Moulder for 2.5 HT |  | 1
5 | Dry Salter Suitable |  | 1
6 | Water Doser Suitable |  | -
7 | Cooling Vat 1 set |  | 1
8 | Drying room at 2 deg. C |  | 1
9 | Dicer cap. 2.0 MT/hr |  | 1
10 | Sifter Suitable |  | 1
11 | Tumbler Suitable |  | 1
12 | Anticaking Agent Doser |  | 1
13 | Conveyor 1 set |  | 1
14 | FFS Machine 2 MT/hr |  | 1
15 | Multivac Double Decker |  | 1
16 | Set of conveyors with metal detector |  | 1
17 | Maturing room cold storage |  | 1
18 | Blast Freezer cold storage |  | 1
19 | Cold Store Deep Freezer |  | 1
20 | Presses for 20kg block cheddar |  | 1
21 | Cheese Hoop |  | 1
22 | Maturing Cold Storage Cheddar |  | 1
E | Whey Equipments
1 | AZO Filter |  | 1 | Approved | Yet to arrive on site
2 | Whey Pasteurizer 25 KL/hr |  | 1
3 | Whey Separator 25 KL/hr |  | 1
4 | Whey Calrifier 25 KL/hr |  | 1
5 | Nano Filteration 20 KL/hr |  | 1
6 | Nano Polisher 20 KL/hr |  | 1
7 | Suitable Evaporator |  | 1
8 | Crystallization |  | 1
9 | Silos 60 KL |  | 2
10 | Ultra Filterator 20 KL/hr for WPC 80 |  | -
F | Cheese Process
1 | Grater |  | 1 | Approved | Yet to arrive on site
2 | Processing Kettle 80 Ltr |  | 1
3 | Block Filling Ceka Pollatiner |  | 1
4 | Slice IWS |  | -
5 | Portion Machine (80-100 portion/min) |  | 1
6 | Filling Machine for Tubs |  | 1
7 | Filling Machine for Bottle |  | 1
8 | Cold Storage |  | 1
9 | Homogenizer 1000-1500 KL/hr |  | 1
10 | Pumps |  | 1
G | Ghee
1 | Cream Concentrator 1.5-2 KL/hr capacity |  | 1 | Approved | Yet to arrive on site
2 | Ghee Kettle Cap - 1 MT |  | 2
3 | Ghee Kalrifier 1 MT/hr |  | 1
4 | Ghee Filling Machine in Jars |  | 1
5 | Ghee Pouch Filling |  | 1
H | Paneer
1 | Silos 30 KL |  | 2 | Approved | Yet to arrive on site
2 | Milk Pumps (10 KL/ hr) |  | 1
3 | PHE cap 3000 ltr/hr 6 deg.C to 90 deg.C |  | 1
4 | Milk Storage Tank (3 KL) |  | 3
5 | Pumps with VFD (10 KL/ hr) |  | 1
6 | Alpma equipments |  | 1
7 | Moulds with lids |  | 40
8 | Roler conveyor |  | 1
9 | Presses |  | 1
10 | Water cooling |  | 1
11 | PHE for cold water (10 KL/ hr) |  | 1
12 | Milk Pumps |  | 1
13 | Whey Storage Silos (30 KL) |  | 3
14 | Acid Tank System (2 KL) |  | 2 |  | Yet to arrive on site
15 | SS Pipes & fittings |  | 1
16 | Multivac Thermo Forming Machine R225 |  | 1
17 | Howbart slicer |  | 2
18 | Electriclas |  | 1
19 | Thermisation |  | 1
20 | Cold Storage plus |  | 1
21 | Cold storage deep |  | 1
22 | Multivac small vacuum packaging |  | 1
23 | Misc |  | 1
I | Dahi
1 | PHE cap 3000 ltr/hr 6 deg.C to 90 deg.C |  | 1 | Approved | Yet to arrive on site
2 | Culture tank 5000 KL |  | 2
3 | Filing machine |  | 1
4 | Incubation room 1 set |  | 1
5 | Cold storage 1 set |  | 1
6 | Trolleys |  | 10
Laboratory Ware, Equipments & Instruments
S. No: | Equipment |  | Quantity | Approved / Not Approved by MoFPI | Remark
I | General Equipments
1 | Laboratory Glass Ware |  | Lot | Not Approved | Yet to arrive on site
2 | Laboratory Chemical Reagents |  | Lot
II | Laboratory Equipments
1 | Analytical Balance Top-loading automatic |  | 1 | Not Approved | Yet to arrive on site
2 | Analytical Balance Dhona type Manual |  | 2
3 | Moisture Oven-Air circulation Fan |  | 2
4 | Mufle Furnace 0 deg. To 96 deg.C |  | 1
5 | Soxhelt extraction set 6 packets |  | 1
6 | Refractor-meter |  | 2
7 | Moisture Balance Meter |  | 2
8 | pH Meter |  | 2
9 | Thickness guage tester (.001 LC) |  | 2
10 | T.L.C. Kit |  | 2
11 | Ultra Voilet Kit |  | 1
12 | Microscope |  | 2
III | Sophisticated Modern Equipments
1 | U.V. Visible Spectophotometer |  | 1 | Not Approved | Yet to arrive on site
2 | Gas Chromatograph |  | 1
3 | Flame Photometer |  | 1
4 | Bomb Calorimeter |  | 1
5 | Polarimeter |  | 1
6 | HPLC |  | 1
IV | Microbiology Testing Facilities
1 | Laminar Flow |  | 1 | Not Approved | Yet to arrive on site
2 | Colony Counter, Digital |  | 2
3 | BOD Incubator |  | 2
4 | Autoclave |  | 1
5 | Centrifuge |  | 1
7.3.2.3 Power Utilities
S. No: | Equipment |  | Quantity | Approved / Not Approved by MoFPI | Remark
A | 33 KV Sub-Station (Refer SLD)
1 | 2.0 MVA, 33 KV/ 433V Transformer |  | 2 No. | Not Approved | Yet to arrive on site
2 | 33 KV, Vacuum Circuit Breaker (VCB) |  | 1 No.
3 | 30 KV, Lightening Arrestor (LAS) |  | 2 Set
4 | 33 KV, TP Isolators |  | 2 Nos.
5 | RTCC Panel |  | 1 No.
6 | 110 V Battery with Charger |  | 1 No.
7 | PCCs, MCC, MDB,SDB |  | 1 Nos.
8 | 3200 A, TPN Bus Duct |  | 15 Mtrs.
9 | 1250 A, TPN Bus Duct |  | 3 Mtrs.
10 | 1000A, TPN Bus Duct |  | 10 Mtrs.
11 | 700 KVAR Capacitors with control panel |  | 2 Nos.
12 | Steel Structures |  | Lot
13 | Control cables |  | Lot
14 | Earthing System |  | Lot
15 | Misc.
B | D.G. Set for Emergency Power to PCC 2 NOS. 500 KVA + 1NO 125KVA DG Set with Control Panel |  | 2 Nos. | Approved
1 | 11 KV, XLPE Cables for a total load for 4000 KVA, entire localized load centers |  |  |  | Yet to arrive on site
2 | Internal Electrification
3 | External Electrification
7.3.2.4 Equipment to Generate and Distribute Process Steam
S. No: | Equipment |  | Quantity | Approved / Not Approved by MoFPI | Remark
A | Bio-Mass Boiler With Standard Components
| Bio-mass based boiler of capacity 12,000 Kg/hr |  |  | Not Approved | Yet to arrive on site
1 | of saturated steam @ 10.50 Bar including standard components like ID & FD |  | 1
Fan, motors and mounting /fittings etc.
2 | Air Pre-heater |  | 1
3 | Dust Collector |  | 1
4 | Packing @ 2%
5 | Supervision of Erection charges
B | Essential accessories, erection & commissioning and certification of Boiler
| Chimney complete with ladder, lightening |  |  | Not Approved | Yet to arrive on site
1 | arrestor including ducting to connect it with boiler |  | 1
and canvas duct for FD fan
2 | Complete feed water system including a tank of 30 kL, structure for staging and all valves, fittings etc. |  | 1
3 | Steam system including Pressure Reducing Station, main header with all standard fittings and mountings etc. |  | 2
4 | Miscellaneous items like support structure of ducts, boiler operation platform, foundation bolts, refractory lining etc. |  | LOT
5 | IBR approval |  | 1
6 | Packing and loading charges @ 5%
7 | Erection and commissioning charges
8 | Steam distribution piping from boiler house to use points |  | LOT
Milk Tankers
S. No: | Equipment | Capacity(KL) | Quantity | Approved / Not Approved by MoFPI | Remark
1 | Reefer Vans | 18 | 4 | Approved | Yet to arrive on site

## Contractor..Supplier
S. No | Name of Contractor/Supplier | Product
1 | Balak Ram Shori Lal | Cheese
2 | Bharat Shudh Ghee Supply Co. | Ghee
3 | Freeze Snacks N Desserts | Cheese
4 | G.R. Traders | Cheese
5 | G.S. Traders | Cheese
6 | Golden Oven | Cheese
7 | Grocer Store | Cheese
8 | Imperial International | Cheese
9 | Lucky Marketing | Cheese
10 | M.R. Trading Company | Cheese
11 | M.S. Traders | Cheese
12 | Maha Maya Agro Food Industries | Ghee
13 | Shyam Enterprises | Cheese
14 | The Perfect Choice | Cheese
15 | Zomato Hyperpure Pvt.Ltd. | Cheese

## PEB Building
PEB Building
S No. | Building name | Area | Level/Floors
1 | Dryer section | 20.4Mtr X 17.7Mtr | 0.0MLVL to 21.0MLVL / 5 floors
2 | Evaporator section | 20.4Mtr X 9.27Mtr | 0.0MLVL to 21.0MLVL / 3 floors
3 | Whey Process/Crystallization section | 20.4Mtr X 21.38Mtr | 0.0MLVL to 5.2MLVL / 1 floors
4 | Butter section | 8.98Mtr X 12.93 Mtr | 0.0MLVL to 5.2MLVL / 1 floors
5 | Ghee section | 8.98Mtr X 38.22Mtr | 0.0MLVL to 5.2MLVL / 1 floors
6 | Grater, Emulsifier, Stabilzer, Ingredient room | 13.5Mtr X 11.88Mtr | 0.0MLVL to 5.2MLVL / 1 floors
7 | Processing Kettle | 13.5Mtr X 9.99Mtr | 0.0MLVL to 5.2MLVL / 1 floors
8 | Process cheese Packing Room | 13.5Mtr X 16.55Mtr | 0.0MLVL to 5.2MLVL / 1 floors
9 | Process cheese Stacking Room | 13.5Mtr X 12.77Mtr | 0.0MLVL to 5.2MLVL / 1 floors
10 | Dahi production area | 13.3Mtr X 21.6Mtr | 0.0MLVL to 5.2MLVL / 1 floors
11 | Dahi filling & packing area | 13.3Mtr X 29.5Mtr | 0.0MLVL to 5.2MLVL / 1 floors
12 | Paneer production area | 19.7Mtr X 21.6Mtr | 0.0MLVL to 5.2MLVL / 1 floors
13 | Paneer cutting & packing area | 19.7Mtr X 29.5Mtr | 0.0MLVL to 5.2MLVL / 1 floors
14 | Mozzarella & Natural Cheese | 27.79Mtr X 51.88Mtr | 0.0MLVL to 5.2MLVL / 1 floors
15 | CIP section | 15.2Mtr X 12.3Mtr | 0.0MLVL to 5.2MLVL / 1 floors
16 | Milk process & storage section | 31Mtr X 12.3Mtr | 0.0MLVL to 5.2MLVL / 1 floors
17 | Secondary Packaging | 93.6Mtr X 18Mtr | 0.0MLVL to 3.0MLVL / 1 floors
18 | Packaging material store room | 96Mtr X 18Mtr | 3.0MLVL to 7.0MLVL / 1 floors
19 | Milk lab | 6.6Mtr X 4.5Mtr | 0.0MLVL to 5.2MLVL / 1 floors
20 | Purchase Office | 5.5Mtr X 2.7Mtr | 0.0MLVL to 5.2MLVL / 1 floors
21 | Cold rooms & Storage area | 108.65Mtr X 30.77Mtr | 0.0MLVL to 5.2MLVL / 1 floors
22 | MCC room | 10.2Mtr X 12.3Mtr | 0.0MLVL to 5.2MLVL / 1 floors
23 | Scada room | 4.8Mtr X 12.3Mtr | 0.0MLVL to 5.2MLVL / 1 floors
24 | ETP | 12.48Mtr X 47Mtr | 0.0MLVL to 6.0MLVL / 1 floors
25
26
27
28

## Administrative block
Adm and Other blocks
S No. | Building name | Area | Level/Floors
1 | Administrative block | 20 Mtr X 9 Mtr | Ground Floor
2 | Engg Stor & WorkShop | 11 Mtr x 13 Mtr | Ground Floor
3 | Canteen | 11.5 Mtr x 7.7 Mtr | Ground Floor
4 | DG Shed | 11.5 Mtr x 7.8 Mtr | Ground Floor
5 | Toilet | 8 Mtr x 13 Mtr | Ground Floor
6 | Boiler section | 18Mtr X 27Mtr | 0.0MLVL to 17.0MLVL / 1 floors
7 | Refrigeration Machine room | 11.54Mtr X 24Mtr | 0.0MLVL to 6.0MLVL / 1 floors
8 | RO & Air compressor section | 11.54Mtr X 8Mtr | 0.0MLVL to 6.0MLVL / 1 floors
9 | PCC & APFC Panel room | 11.54Mtr X 10Mtr | 0.0MLVL to 6.0MLVL / 1 floors

## GST Sheet
Plant & Machinery (Summary including GST)
S No. | Particulars | Basic Cost Rs. Lakhs (incl. GST)
1 | Plant & Machinery | 4627.96
2 | Laboratory Ware, Equipments & Instruments Cost Break-up | 59
3 | Power | 368.75
4 | Steam Requirement | 107.38
5 | RO Plant & Water Softening Plant | 59
6 | Air Compressor | 35.4
7 | ETP | 70.8
8 | CIP (Cleaning in Process) | 59
9 | Milk Tankers | 141.6
10 | Misc. Assets | 141.6
| Total | 5670.49