As per approved layout plan provided by the client, the building and the civil work have been done according to the layout plan which has been approved by the competent Authority “Gram Panchayat Kamalapur, Vijaynagara District Hosapete, Karnataka”.

As per the Taj Hampi master schedule program provided by company, only 3% of the total work has been completed. Below table shows the status of the resort as per the Taj Hampi master schedule program:

| Task Name | Start | Finish | Duration | % Complete | Rem. Dur. |
| --- | --- | --- | --- | --- | --- |
| Taj Hampi Master control program | Wed 3/1/23 | Wed 3/25/26 | 940.38 days | 3% | 916.67 days |
| Pre-Construction Activities | Thu 3/2/23 | Tue 3/18/25 | 627 days | 10% | 564.42 days |
| Appointments of Consultants | Thu 3/2/23 | Tue 2/27/24 | 304.5 days | 39% | 185.67 days |
| Design Development | Fri 8/18/23 | Tue 3/18/25 | 485 days | 9% | 442.92 days |
| Tender Drawings, BOQ & Specifications | Sat 9/30/23 | Sat 9/28/24 | 305 days | 9% | 278.21 days |
| Tendering process & Award | Fri 8/25/23 | Tue 3/18/25 | 479.13 days | 4% | 458.04 days |
| Project Execution Works | Wed 3/1/23 | Mon 1/12/26 | 879.88 days | 0% | 878.72 days |
| MEP Works | Wed 3/1/23 | Mon 12/22/25 | 861.88 days | 0% | 861.88 days |
| Closure/Handover | Mon 3/10/25 | Wed 3/25/26 | 319.5 days | 0% | 319.5 days |

Out of 40,954.18 Sq. Mt. land, company has planned to utilize 32,501.50 Sq. Mt. of land for the proposed resort purpose for which the plan is approved.

It's imperative to highlight that the remaining work is yet to commence.