## 6000 TCD Milling
6000 TCD MILLING PLANT
S. No. | NAME OF EQUIPMENT | QUANTITY | MACHINE ARRIVED AT SITE | MACHINE INSTALLATION | TESTING | PRODUCTION | AMOUNT PAID
(INR)
1 | Cane unloader | 5 nos. | No | No | No | No | -
2 | Cane Carrier | 1 no. | No | No | No | No | -
3 | Cane Chopper | 1 no. | No | No | No | No | -
4 | Cane leveler | 1 no. | No | No | No | No | -
5 | Swing hammer fibrizer | 1 no. | No | No | No | No | -
6 | Rake Elevator | 1 no. | No | No | No | No | -
7 | Fibrized Cane Belt Type Carrier | 1 no. | No | No | No | No | -
8 | Cane equalizer | 1 no. | No | No | No | No | -
9 | Magnetic Tramp Iron Separator | 1 no. | No | No | No | No | -
10 | Automatic Cane Feeding Devices | 1 no. | No | No | No | No | -
11 | Milling Plant | 4 nos. | No | No | No | No | -
12 | Hydraulic Pressure System | ---- | No | No | No | No | -
13 | Lubrication | ---- | No | No | No | No | -
14 | Juice Tray | 4 nos. | No | No | No | No | -
15 | Mill Gangway | ---- | No | No | No | No | -
16 | Donnelly chute | 4 nos. | No | No | No | No | -
17 | Toothed underfeed roller | 4 nos. | No | No | No | No | -
18 | Mill Drive | 4 nos. | No | No | No | No | -
19 | VFD | 4 nos. | No | No | No | No | -
20 | Gearbox | 4 nos. | No | No | No | No | -
21 | Coupling |  | No | No | No | No | -
22 | Rake Type Intermediate Carrier with Imbibition Equipment and Mixed Juice Pumps | 3 nos. | No | No | No | No | -
23 | Rotary Screen | 1 no. | Yes | No | No | No | 4000000
24 | Juice Pumps | ---- | No | No | No | No | -
| For 1st mill | 1 no. | No | No | No | No | -
| For 2nd mill | 1 no. | No | No | No | No | -
| For 3rd ,4th mill | 2 nos. | No | No | No | No | -
| Screened juice | 3 nos. | No | No | No | No | -
(2 W+1SB)
25 | Imb. Pumps | 02 nos. | No | No | No | No | -
(1W+1SB)
26 | Magnetic flow meter | 1 no. | No | No | No | No | -
27 | Auxiliary Cooling Tower for Mill bearing Cooling | 1 no. | No | No | No | No | -
28 | Mill House Crane and Gantry | 1 no. | No | No | No | No | -

## 3000 TCD Raw Syrup
3000 TCD RAW SYRUP PLANT
S. No. | NAME OF EQUIPMENT | QUANTITY | MACHINE ARRIVED AT SITE | MACHINE INSTALLATION | TESTING | PRODUCTION | AMOUNT PAID
(INR)
1. | Mass flow meter | 1 no. | No | No | No | No | -
for juice
2. | Juice Heaters | 2 nos. | No | No | No | No | -
3. | Juice Defecator | 1 no. | No | No | No | No | -
4. | Defecated Juice Pumps | 2 nos. | No | No | No | No | -
5. | Clarifier | 1 no. | Yes | No | No | No | 6000000
6. | Clear Juice Pumps | 2 nos. | No | No | No | No | -
7. | Rotary Vacuum | 1 no. | No | No | No | No | -
Filter
8. | MOL preparation | 1 no. | No | No | No | No | -
System
9. | Evaporator with 9 nos. FFE | 1 no. | Yes | In-progress | No | No | 51625000
10. | Syrup transfer to distillery | 1 no. | No | No | No | No | -
11. | Condensate | 1 no. | No | No | No | No | -
extraction system
12. | Steam consumption & Bleeding Scheme | 1 no. | No | No | No | No | -
13. | CIP | 1 no. | No | No | No | No | -
14. | Condensers | 2 nos. | No | No | No | No | -
15. | Injection water pumps | 2 nos. | No | No | No | No | -
16. | Cooling tower | 1 no. | No | No | No | No | -
17. | Excess condensate cooling tower | 1 no. | No | No | No | No | -
18. | Overhead tanks with water pumps | 2 nos. | No | No | No | No | -
19. | Air compressor | 2 nos. | No | No | No | No | -
20. | Structural Staging | ----- | No | No | No | No | -
21. | Pipelines | ----- | No | No | No | No | -
22. | Insulation and | ----- | No | No | No | No | -
Cladding
23. | Electricals | ----- | No | No | No | No | -
24. | Instrumentation | ----- | No | No | No | No | -

## 225 KLPD Ethanol
225 KLPD ETHANOL (DISTILLERY) PLANT
S. No. | NAME OF EQUIPMENT | QUANTITY | MACHINE ARRIVED AT SITE | MACHINE INSTALLATION | TESTING | PRODUCTION | AMOUNT PAID
(INR)
1. | Molasses Storage and Handling Section | 1 no. | No | No | No | No | -
2. | Syrup Storage and Handling Section | 1 no. | No | No | No | No | -
3. | Spent Wash Recycle Section | 1 no. | No | No | No | No | -
4. | Fermentation Section | 1 no. | No | No | No | No | -
5. | Distillation Section with Columns, Reboilers, Condensers & Coolers and Pumps | 1 no. | No | No | No | No | -
6. | Dehydration Section | 1 no. | No | No | No | No | -
7. | Product Receiving and Storage Section | 1 no. | No | No | No | No | -
8. | Evaporation Section: Integrated + SA (Future Provision for B Molasses) | 1 no. | No | No | No | No | -
9. | Condensate Polishing Unit | 1 no. | No | No | No | No | -
10. | Utilities | 1 no. | No | No | No | No | -

## CO-Gen
120 TPH BOILER & 21.8 MW CO-GENERATION PLANT
S. No. | NAME OF EQUIPMENT | QUANTITY | MACHINE ARRIVED AT SITE | MACHINE INSTALLATION | TESTING | PRODUCTION | AMOUNT PAID
(INR)
1. | Boiler (120 TPH, 87 Kg/Cm2) | 1 no. | No | No | No | No | -
| Turbo Generator | 1 no. | No | No | No | No | -
| Auxiliary Cooling Tower | 1 no. | No | No | No | No | -
| Ash Handling System | 1 no. | No | No | No | No | -
| EOT Crane | 1 no. | No | No | No | No | -
| Utilities | 1 no. | No | No | No | No | -
| Electrical Equipment | 1 no. | No | No | No | No | -
| Control & Instrumentation | 1 no. | No | No | No | No | -
2. | 21.8 Mw Turbo Generator Set (Steam Turbine) | 1 Set | No | No | No | No | -
| Gearbox | ---- | No | No | No | No | -
| Couplings | ---- | No | No | No | No | -
| Governing System | ---- | No | No | No | No | -
| Lubrication System | ---- | No | No | No | No | -
| Accessories | ---- | No | No | No | No | -
| Electrical | ---- | No | No | No | No | -
| Control & Instrumentation | ---- | No | No | No | No | -
| Turbine Control Panel | ---- | No | No | No | No | -
3. | Bagasse Elevator | 1 No. | No | No | No | No | -
4. | Main Bagasse Carrier | 1 No. | No | No | No | No | -
5. | Surplus Bagasse Belt Conveyor | 1 No. | No | No | No | No | -
6. | Return Bagasse Carrier | 1 No. | No | No | No | No | -
7. | Ro / Dm Water Plant | 1 No. | No | No | No | No | -
8. | Auxiliary Cooling Tower | 1 No. | No | No | No | No | -
9. | PRDS | 1 Set | No | No | No | No | -
10. | Air Compressor for Instrument | 2 Nos. | No | No | No | No | -
(1W+1SB)
11. | EOT Crane For TG | 1 No. | No | No | No | No | -
12. | DG Set | 1 No. | No | No | No | No | -
13. | DCS | ---- | No | No | No | No | -
14. | Plant Piping | ---- | No | No | No | No | -
15. | Effluent Treatment Plant | ---- | No | No | No | No | -
16. | Condensate Polishing Unit Follower by UF & RO System | ---- | No | No | No | No | -
17. | Air Conditioning System | ---- | No | No | No | No | -
18. | Fire Protection System | ---- | No | No | No | No | -
19. | Electrical Distribution System | ---- | No | No | No | No | -