## Sheet1
Particulars | Amount in Rs. Cr.
Building and civil work | 78.64
Furniture, Fixtures, Interior and finishing | 45.54
Plant & Machineries and utilities | 43
Provision for contingencies | 11.06
Interest during construction period | 13.76
TOTAL | 192

## Builidng Area
Floorwise Status of Building and civil work in Phase II
Block Name | Floor | Plint area in sq. mtr. | Plint area in sq. ft. | Type of structure | Height(Ft.) | Plinth area rate per sq. ft. | Value assessed | Status of Building and civil work
| Fifth Floor | 2068.787 | 22268.4233 | RCC framed structure | ~10 | 2200 | 48990531.1896 | As per the representative all the works are completed and beds have been laid and as information provided. Only AC and equipment installation is due.
| Sixth Floor | 3744.425 | 40304.9907 |  |  | 1400 | 56426986.98 | Structure work is Completed, outer brickwork is completed and putty work was observed to be in progress
| Seventh Floor | 3744.425 | 40304.9907 |  |  | 1400 | 56426986.98 | Structure work is Completed, outer brickwork is completed and putty work was observed to be in progress
| Eighth Floor | 3744.425 | 40304.9907 |  |  | 1250 | 50381238.375 | Structure work is Completed, outer brickwork is completed and few deshuttering work was observed to be in progress
| Ninth Floor | 3744.425 | 40304.9907 |  |  | 1250 | 50381238.375 | Structure work is Completed, outer brickwork is completed.
| Tenth Floor | 3744.425 | 40304.9907 |  |  | 1250 | 50381238.375 | Structure work is Completed, outer brickwork is completed.
| Terrace Floor | 597.533 | 6431.8452 |  |  | 950 | 6110252.9514 | Structure work is in progress
BLOCK 11 | Sixth Floor | 397.778 | 4281.6824 |  |  | 1400 | 5994355.3488 | Structure work is Completed, outer brickwork is completed, internal finishing work of server room is in progress
| Seventh Floor | 397.778 | 4281.6824 |  |  | 1350 | 5780271.2292 | Structure work is Completed, outer brickwork is completed, internal brickwork and few plumbing work was observed to be in progress
| Eighth Floor | 418.928 | 4509.341 |  |  | 1200 | 5411209.1904 | Structure work is Completed, outer brickwork is completed, internal brickwork and few deshuttering work was observed to be in progress
| Ninth Floor | 418.928 | 4509.341 |  |  | 1100 | 4960275.0912 | Structure work is Completed, outer brickwork is completed, internal brickwork was observed to be in progress
| Tenth Floor | 257.902 | 2776.0571 |  |  | 1100 | 3053662.8408 | Structure work is Completed, outer brickwork is completed, internal brickwork was observed to be in progress
| Terrace Floor | 98.957 | 1065.1731 |  |  | 950 | 1011914.4906 | Structure work is in progress
ESS | Ground Floor | 141.3043 | 1521 |  |  | 1400 | 2129400 | Strcuture completed. Major civil work completed. Finishing and interior work is due.
ESS | First Floor | 141.3043 | 1521 |  |  | 1400 | 2129400 | Strcuture completed. Major civil work completed. Finishing and interior work is due.
BLOCK 3C | Ground Floor | 1283.8707 | 13819.5837 |  | 15 | 1300 | 17965458.81 | Strcuture work is completed.
| First Floor | 1253.9657 | 13497.6863 |  | 12 | 1300 | 17546992.164 | Strcuture work is completed. | 990
| Second Floor | 1395.27 | 15018.6863 |  | 12 | 1300 | 19524292.164 | Strcuture work is completed.
| Third Floor | 1395.27 | 15018.6863 |  |  | 1300 | 19524292.164 | Strcuture work is completed.
| Fourth Floor | 1061.037 | 11421.0023 |  |  | 900 | 10278902.0412 | Slab casting work is in progress.
| Terrace Floor | 147.98 | 1592.8567 |  |  | 0 | 0 | Work not started yet.
BLOCK 3G | Ground Floor | 900 | 9687.6 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| First Floor | 650 | 6996.6 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Second Floor | 785 | 8449.74 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Third Floor | 785 | 8449.74 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Fourth Floor | 785 | 8449.74 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Fifth Floor | 785 | 8449.74 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Sixth Floor | 725 | 7803.9 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Terrace Floor | 65 | 699.66 |  |  | 0 | 0 | No construction work has been statred yet. Also no land demarcation has been done yet.
| Total | 35678.718 | 384045.7206 |  |  |  | 434408898.7602

## Status
Floorwise area of the Proposed building block in Phase II
FLOOR BLOCK | 10B&10C | BLOCK11 | BLOCK 3C+ESS | BLOCK-3G
Basement 2 | 0 | 0 | 0 | 0
Basement 1 | 0 | 0 | 0 | 0
Ground Floor | 0 | 0 | 1425.175 | 900
First Floor | 0 | 0 | 1395.27 | 650
Second Floor | 0 | 0 | 1395.27 | 785
Third Floor | 0 | 0 | 1395.27 | 785
Fourth Floor | 0 | 0 | 1061.037 | 785
Fifth Floor | 2068.787 | 0 | 0 | 785
Sixth Floor | 3744.425 | 397.778 | 0 | 725
Seventh Floor | 3744.425 | 397.778 | 0 | 0
Eighth Floor | 3744.425 | 418.928 | 0 | 0
Ninth Floor | 3744.425 | 418.928 | 0 | 0
Tenth Floor | 3744.425 | 257.902 | 0 | 0
Terrace Floor | 597.533 | 98.957 | 147.98 | 65
In Sq. mtr. | 21388.445 | 1990.271 | 6820.002 | 5480
In Sq. ft | 230225.222 | 21423.277 | 73410.5015 | 58986.72

## Plant and machinery
Vendor | Particular | Date | Amount