## Sheet1
Sr. No. | Projects City | Handover/Termination of Project | Date of Handover/Termination Notice | Writ Petition/Arbitration
1 | Kanpur | The assets of the processing plant have been handed over to ILFS. A copy of the said handed over letter is attached herewith. | 2012-05-11 | The ILFS (one of the lenders) proposed to take over the plant on the terms as mentioned in the Definative Agreements executed with it, and all other lenders gave their NOC including IDBI Bank for the said transaction. However due to change in the management of ILFS, they took step back and didn't make payment in terms of the executed agreement so company filed the Writ Petition and Court has issued notice to all the lenders including IDBI Bank. Copies of the IDBI NOC & Writ Petition & Last court order are attached herewith.
|  | The assets of the power plant have been handedover to ILFS. A copy of the said handed over letter is attached herewith. | 2014-01-15
2 | Muzaffar Nagar | Due to non-Payment of tipping fees by the Municipal Corporation, the company has decided to terminate the said project and on 24.12.2018, the company has handed over all the plant assets and Vehicles and other equipments to the Municipal Corporation. A copy of handed over letter dated 24-12-2018 is attached herewith for your reference. | 24-12.2018 | NA
3 | Indore | Due to non-payment of tipping fees by the Municipal Corporation, workers have decide not to work on the site therefore the Municipal Corporation has Terminated the said contract. A copy of termination letter is attached herewith for your reference. | 2017-09-14 | NA
4 | Patna | We have terminated this project as the Minicipal Corporation was not paying tipping Fees. A copy of Termination Letter is attached herewith. | 2011-07-21 | An Arbitration Award has been passed in the favour of the Company for an amount of INR 11,89,12,705 and out of that Municipal Corporation has deposited INR 3,81,32,908/- in the IDBI Bank account. A copy of Arbitration Award and payment proof is attached herewith for your reference.