## Working
S.NO. | PARTICULARS | ESTIMATED COST (Rs. In Cr.) | AMOUNT SHOWN BY THE COMPANY (UPTO 31.12.23) (As Per C.A. Certificate) | AMOUNT SHOWN BY THE COMPANY (UPTO 31.12.23) (As Per C.A. Certificate) | DIFFERENCE OF LAST CA CERTIFICATE AND CURRENT CA CERTIFICATE | LAST LIE REPORT APPROVED AMOUNT | AMOUNT APPROVED BY LIE (As on 31-01-2024) | TOTAL AMOUNT APPROVED (UPTO 31-01-2024) | REMARKS
1 | Land including land developments | 1.15 | 1.63 | 1.63 | 0 | 1.35 |  | ~1.35 | This includes cost of land with stamp duty (as per the value mentioned in the sale deed). For breakup of expenditure please refer to Table below.
2 | Building and other civil works. | 8.74 | 9.67 | 13.53 | 3.86 | 5.27 | ~9.21 | ~9.21 | The cost assessment for building and civil works is done in accordance with the benchmark or market cost, as per the percentage of work completed. Minor difference which is coming from CA Certificate is normal which comes from actual vs. estimated calculation. (As CA certificate was prepared in December and shows the expenditure incurred till 31.12.2023 and the survey was conducted 31.01.2024)
3 | Plant, Machinery and equipment. | 26.16 | 24.5 | 32.15 | 7.65 | -- | -- | -- | 1. In last quarter as per survey done on 17-10-2023 no machine was arrived but in this quarter survey done on 31-01-2024 significant machine installation work is done as shown in Part C (3). 2. Due to confidentiality company has not shared us list of P&M Invoices. On their request our team went to their office to check the Invoices/ Bills. Our team could verify the Invoices/ Bills of several parties as mentioned in the Table xx below amounting of Rs.20.46 crores. However this shall not be construed as cross verification of Bills since Bill wise verification of machines on site is not done. If Bank has access to the Invoices/ Bills then Bank may tally it with
4 | Pre-operative Expenses | 1.75 | 3.28 | 4.75 | 1.47 |  |  |  | Since breakup was not available therefore we were unable to verify its cost as of now and thus have not commented on this item.
5 | Interest During Construction | 2.4 | 0.61 | 1.46 | 0.85 |  |  |  | Can be referred directly from CA certificate as out of Engineering purview. Not in scope of LIE.
6 | Margin Money for Working Capital | 0.2 | 0 | 0.46 | 0.46 |  |  |  | Can be referred directly from CA certificate as out of Engineering purview. Not in scope of LIE.
|  | 40.4 | 39.69 | 53.98 | 14.29

## Project cost & expenditure
Land including land developments | 1.15 | 2.911% | 1.63 | 4.107%
Building | 8.74 | 22.13% | 9.67 | 24.36%
Plant Machinery (Imported & Domestic) | 26.16 | 66.23% | 24.5 | 61.73%
Preoperative Expenses | 1.75 | 4.43% | 3.28 | 8.264%
Interest During Construction | 1.5 | 3.797% | 0.61 | 1.537%
Margin Money for Working Capital | 0.2 | 0.5063% | 0 | 0%
| 39.5 |  | 39.69
Land including land developments | 1.35 | 4.514%
Building | 8.1 | 27.08%
Plant Machinery (Imported & Domestic) | 20.46 | 68.41%
29.91
61.7284

## Civil Work Cost
Building and other civil work
SR.NO | Particular | Type of Structure | L | B | Area/Qty (sq. mtr) | Unit | Area/Qty | Rate | Amount | Status
1 | Bagging Unit | G.I. Shed |  |  | 800 | Sq. Ft | 8611.12 | 1000 | 8611120 | The major civil shed works have been completed.
2 | Sun Drying Unit | Concrete Platform |  |  | 972 | Sq. Ft | 10462.5108 | 550 | 5754380.94 | Footing structure work, levelling and and P.C.C finish flooring is done. | 2821 |  | 144
3 | Biogas Upgradation Plant | G.I. Shed |  |  | 1296 | Sq. Ft | 13950.0144 | 1200 | 16740017.28 | All the Civil work is finished, only soil filling and flooring work is due |  |  | 324
4 | Master Control Room and Office Room | R.C.C. Structure |  |  | 1026 | Sq. Ft | 11043.7614 | 1400 | 15461265.96 | G+2 Structure work is complete except deshuttering of 2nd floor and brickwork is in progress. |  |  | 468
5 | Raw Water | R.C.C. Structure |  |  | 468 | Sq. Ft | 5037.5052 | 1000 | 5037505.2 | Construction Work Is Complete
6 | Hot Water Treatment Plant | G.I Shed |  |  | 468 | Sq. Ft | 5037.5052 | 1200 | 6045006.24 | Major work is completed, 20-30 % of GI shed roof covering is due.
7 | Mixer | R.C.C. Structure |  |  |  | Cum | 160 | 9500 | 1520000 | Structure work is complete
8 | Digester 1 | R.C.C. Structure |  |  |  | Cum | 850 | 10000 | 8500000 | Structure work is complete
9 | Digester 2 | R.C.C. Structure |  |  |  | Cum | 850 | 10000 | 8500000 | Structure work is complete, covering with green net is due
10 | Lagoon | R.C.C. Structure |  |  | 741 | Sq. Ft | 7976.0499 | 1100 | 8773654.89 | Structure/Construction work in progress
11 | Guard Room | R.C.C. Structure |  |  | 16.7226 | Sq. Ft | 180 | 1250 | 225000 | One guard room is completed and finishing work in the other guard room is in progress
12 | Meter Room | R.C.C. Structure |  |  | 16.7226 | Sq. Ft | 180 | 1100 | 198000 | Finishing work is in progress
13 | Boundary Wall | Pre Cast |  |  | 2010.72 | Sq. Ft | 21643.189 | 140 | 3030046.4611 | Completed
14 | Column for support of fire pipe | R.C.C. Structure |  |  |  |  | 33.1088 | 10357 | 342907.3237 | Completed
|  | Steel |  |  |  |  | 2599.0369 | 89 | 231314.2819
15 | Road | R.C.C. Road |  |  |  | Cum | 759 | 10357 | 7860963 | Work in progress
16 | Drain | Brick Work and plaster |  |  |  | R.M. | 550 | 3000 | 1650000 | Work in progress
17 | Pump House | R.C.C. Structure |  |  | 288 | Sq. Ft | 3100.0032 | 1200 | 3720003.84
18 | Extra Work (site development) | [7 empty] | 5311000 | Work in progress
Total | [8 empty] | 107512185.4167
| Land | [7 empty] | 13551400
121063585.4167
[8 empty] | land | 0 |  | Land | 13551400
[8 empty] | P.M |  |  | Building | 107512185.4167
[8 empty] | B&C |  |  | P&M | 204550000
[10 empty] | 29.905 |  | 325613585.4167

## Sheet1
Plant & Machinery | Rs. In Lacs
Name of the Vendor | Amount
Planet Biogas Germany | 1,246.61
Import Duties | 181.03
Advance to UP Transmission | 45.45
Biogas Compression from Kirloskar | 123.82
Biogas Upgradation Package | 789.57
HME Boilers | 41.44
Infinite Buildfoam | 22.45
Machine Electricals (Electro Control Systems) | 336.56
Avant Garde Expenses | 47.41
Upen Infra | 129.94
Ceasefire Industries | 81.50
Tharayil Engineering | 31.13
Shipping & Transport | 14.03
Chawla, Eagle, Growth India, Aaradhya Fluidways, Pratiman, Borg etc. | 71.07
Misc. payments, advance | 52.42
Total-P&M | 3,214.44
Building
Ananjay Enterprises | 5.28
Nuzra Tradeers (Boundary Wall Panels) | 1.65
Metering Work by AR Electro Enterprises | 13.14
Makin Developers | 1,084.85
Flowmore | 9.20
Tata Bluescope | 11.33
Steel Purchased | 0.45
Porta Cabin from Fabking | 8.62
Main Gate from Gandhi Automations Pvt Ltd | 5.39
Steeline Buildcon | 210.89
Sagar Borewells | 2.00
Total-Building | 1,352.80

## Sheet2
Particulars | Expenditure verified through bills (in Rs. In CR)
PlanET | 10.735
BGEI | 7.83
Electro Control Systems | 1.89
Total | 20.455
NOTE:
1. These amount were verified against bills produced at M/s. carbon Circle Pvt Ltd. Level 5, The Circle, Huda City Centre, gurugram PIN: 122002

## MAterial cost bifurcation
| Area | H | Qty | Rate | Amount
Excavation |  |  | 120.96 | 350 | 42336
Brickwork |  |  | 79.76 | 5746 | 458300.96
Soil Filling |  |  | 1166.4 | 400 | 466560
Plinth |  |  | 11.4 | 9793 | 111640.2
Retaining Wall | 86.4 | 0.15 | 12.96 | 9793 | 126917.28 | 1236.025
Steel |  |  | 9561.3 | 89.65 | 857170.545
GSB |  |  | 194.4 | 3000 | 583200
P.C.C |  |  | 145.8 | 6000 | 2646124.985
|  |  |  | Total | 5292249.97
|  |  |  | Cost Per Sq. ft | 505.8062

## Land
| 3.14 | 225 | 216.09 | 7 | 195.8418 | 9000 | 1762576.2
| 3.14 | 225 | 174.24 | 3 | 478.1592 | 9000 | 4303432.8
| 3.14 | 25 | 22.09 | 3.5 | 31.9809 | 9000 | 287828.1
| 4.14 | 25 | 17.64 | 3 | 91.4112 | 9000 | 822700.8
[5 empty] | 797.3931 | 9000 | 7176537.9
| Land | Cost
| 2.143 | 4532000 |  |  | S.NO | GATA NO | Area in (HECTARES) | Sale Price | Stamp Durty | TOTAl
| 0.18575 | 770700 |  |  | 1 | 391 | 1.0715 | 4238000 | 220300 | 4458300
| 0.18575 | 926100 |  |  | 2 | 161 | 0.18575 | 734000 | 36700 | 770700
| 0.225 | 2056000 |  |  | 3 | 161 | 0.18575 | 882000 | 44100 | 926100
Total | 2.7395 | 8284800 |  |  | 4 | 388 | 0.225 | 1958000 | 98000 | 2056000
[5 empty] | 5 | 391 | 1.0715 | 5086000 | 254300 | 5340300
| 4532000 |  |  |  | Total |  | 2.7395 | 12898000 | 653400 | 13551400

## Status
Anaerobic Digestor 1 | 100%
Anaerobic Digestor 2 | 100%
Mixer | 100%
Lagoon | 100%
Hot Water Treatment Plant | 95%
Biogas Upgradation plant | 95%
Raw Water Storage | 100%
Pump House | 80%
Raw Water Storage | 100%
Master Control Room and Office Room | 85%
Bagging unit | 95%
Sun drying area | 95%
Guard Room | 100%
Meter Room | 80%
Internal Road | 100%
Drainage | 80%

## Sheet5
|  | Particulars | Project Cost as Budgeted | Project Cost as Budgeted | Expenditure Incurred Till 31st December 2023 | Expenditure Incurred Till Date
|  |  | Project Cost as Budgeted | (As per CA Certificate) | (As per CA Certificate) | (LIE Assessment)
|  | Land including land developments | 1.15 | 1.15 | 1.63 | 1.35
|  | Building & Civil works | 8.74 | 8.74 | 9.67 | 5.44
|  | Plant Machinery | 26.16 | 26.16 | 24.5 | ---
|  | Preoperative Expenses | 1.75 | 1.75 | 3.28 | ---
|  | Interest During Construction | 1.5 | 2.4 | 0.61 | ---
|  | Margin Money for Working Capital | 0.2 | 0.2 | 0 | ---
|  | Total | 39.5 | 40.4 | 39.69 | 6.8
Particulars | Vendor | Expenditure verified through bills
Digester | PlanET | 10.735 |  |  | 15.47
BUP | BGEI | 7.83 |  |  | 9.29
Total estimated cost (as per C.A. Certificate) | 26.6 | 18.565 |  |  | 1.13
Cost incured till (31st December 2023) | 24.5 | #VALUE! |  |  | 0.12
Planet
BUP
Makin

## Sheet2 (2)
Name of the Package | Name of the Vendor – PO awarded | Total Contract Value (Rs. In Lacs) | Remarks | % allocation in Phase-1 | Phase-1 Amount | Bills/ Invoices Seen (Rs. In cr)
Digester vendor | PlanET (incl. Customs duty + CHA charges) | 1547.75 | --- | 100% | 1547.75 | 10.735 |  | #REF!
Biogas Upgradation Plant (BUP) Vendor | Biogas Engineering India Pvt Ltd. | 929.95 | (for ultimate capacity of 10 TPD) | 50% | 464.975 | 7.83 | 20.455
Product Gas Compressor Supplier | Kirloskar Pneumatic Company Limited | 113 | (for ultimate capacity of 10 TPD) | 50% | 56.5 | -- | #REF!
Portable Cabin Container Supplier | Fabking Solutions Pvt Ltd. | 5.47 | --- | 100% | 5.47 | --
Bay at 132 KV @ Richha S/s | UPPCl | 45.45 | (for ultimate capacity of 10 TPD) | 50% | 22.725 | --
Cladding Sheet/ Insulation Material | Tata Bluescope Steel Pvt Ltd. / Infinite Build Foam | 73.9 | --- | 100% | 73.9 | --
Air Compressor | Kirloskar Pneumatic Company Limited | 12.39 | --- | 100% | 12.39 | --
Pumps | Flowmore Ltd. | 9.2 | --- | 100% | 9.2 | --
Plant Electricals | Electro control Systems | 421.2 | (for ultimate capacity of 10 TPD) | 50% | 210.6 | 1.89
Fire Fighting System | Ceasefire Industries Pvt Ltd. | 123.34 | (for ultimate capacity of 10 TPD) | 50% | 61.67 | --
Hot Water Generator | HME Boilers Pvt Ltd. | 56.67 | (for ultimate capacity of 10 TPD) | 50% | 28.335 | --
Erection, Commissioning & Quality | Tharayil Engineering Pvt Ltd. | 60.31 | (for ultimate capacity of 10 TPD) | 50% | 30.155 | --
Electric Meter (Supply & Services) | ARC Electro Enterprises | 22.86 | (for ultimate capacity of 10 TPD) | 50% | 11.43 | --
Weigh Machine | Eagle Scale Manufacturing Works | 14.16 | (for ultimate capacity of 10 TPD) | 50% | 7.08 | --
Main Gate | Gandhi Automation Pvt Ltd. | 7.08 | (for ultimate capacity of 10 TPD) | 50% | 3.54 | --
Odorising, Metering & Pipeline | Yet to be awarded | --- | (for ultimate capacity of 10 TPD) | 50% | -- | --
Bagging Unit | Yet to be awarded | --- | (for ultimate capacity of 10 TPD) | 50% | -- | --
SCADA | Yet to be awarded | --- | (for ultimate capacity of 10 TPD) | 50% | -- | --
Lab | Yet to be awarded | --- | (for ultimate capacity of 10 TPD) | 50% | -- | --
TOTAL |  | 3442.73 |  |  | 2545.72 | 20.455

## Sheet2 (3)
Name of the Package | Name of the Vendor – PO awarded | Total Contract Value (Rs. In Lacs) | Remarks | % allocation in Phase-1 | Phase-1 Amount | Bills/ Invoices Seen (Rs. In cr)
Civil Works Contractor | Makin Developers Pvt Ltd. | 1221.06 | --- | 100% | 1221.06 | 10.15 | 12.19
PEB shed | Steeline Buildcon Pvt Ltd. | 204.41 | (for ultimate capacity of 10 TPD) | 50% | 102.205 | 2.04
TOTAL |  | 1425.47 |  |  | 1323.265 | 12.19

## Invoices
S.No | Particular | Date | Invoice No | Amount | Purchase Order
1 | Abhishek gangwar | 2023-12-04 | 23-24/01 | 34000 |  | 365922518.58 |  | 347872
|  | 2024-01-01 | 23-24/02 | 112750 |  | 256773414.23 |  | 2715370.8
| Total |  |  | 146750 |  | 231011393.08 |  | 5304876.4
| Ali JCB | 2024-01-02 | 101 | 73666 |  |  |  | 187128
|  | 2024-01-18 | 102 | 51500 |  |  |  | 1634261.32
|  | 2024-02-02 | 103 | 47331 |  |  |  | 969243
|  | 2024-03-01 | 104 | 52338 |  |  |  | 26524382
| Total |  |  | 224835 |  |  |  | 37683133.52 | 403605652.1
2 | Annu Transport | 2023-12-17 | 10 | 14986
|  | 2023-12-17 | 11 | 89376 |  |  | Date | Invoice No | Value in Euro | Value in INR
|  | 2023-12-21 | 12 | 121425 |  |  | 2023-03-08 | SAARP-019-10085 | 29514.9
|  | 2023-12-28 | 13 | 16505 |  |  | 2023-05-05 | SAINP-019-10180 |  | 347872
|  | 2024-01-02 | 14 | 665587 |  |  | 2023-03-08 | SAARP-019-10084 | 57661.7
|  |  | 16 | 56490 |  |  | 2023-04-26 | SAINP-019-10179 | 2034
|  |  | 17 | 255745 |  |  | 2023-05-05 | SAINP-019-10180 | 17763.71
|  |  | 18 | 96135 |  |  | 2023-04-06 | SAARP-019-10089 | 10535.25
|  | 2024-02-22 | 19 | 431150 |  |  | 2023-04-06 | SAARP-019-10088 | 288308.5
|  | 2024-03-01 | 20 | 78920 |  |  | 2023-04-06 | SAARP-019-10087 | 2107.05
|  | 2024-03-01 | 21 | 20832 |  |  | 2024-02-29 | SAINP-019-10204 | 11000
| Total |  |  | 1847151 |  |  | 2024-03-01 | SAINP-019-10204 | 1400
3 | AR Electro Enterprises | 2023-06-27 | AREE/23-24/21 | 560500 |  |  | 2024-01-31 | SAINP-019-10197 | 2946.36
|  | 2023-11-10 | AREE/23-24/54 | 383500 |  |  | 2024-04-16 | SAINP-019-10208 | 68868.1
|  | 2023-11-10 | AREE/23-24/55 | 383500 |  |  | 2023-09-15 | SAARP-019-10084 | 716900
|  | 2023-12-08 | AREE/23-24/60 | 383500 |  |  | 2023-12-04 | SAINP-019-10192 | 86175
| Total |  |  | 1711000 |  |  | 2023-09-30 | SAARP-019-10084 | 117900
4 | Beniwal Associates Pvt Ltd. | 2023-11-10 | 595 | 88500 |  |  | 2023-09-29 | SAARP-019-10100 | 258705.29
| Total |  |  | 88500 |  |  |  |  | 1671819.86 | 145448327.82
5 | Biogas Engineering (BGEI) | 2024-05-07 | BGI/FTY24-25/002 | 92747000
| Total |  |  | 92747000
6 | Everest Human Resource Consultants | 2024-02-08 | CB/BAR/23-24/01 | 56775.93
| Total |  |  | 56775.93
7 | Fabking | 2023-11-08 | CS/23-23/526 | 100000
|  | 2023-11-08 | FAB/23-24/601 | 113280
| Total |  |  | 213280
8 | Flowmore | 2023-11-21 | U2230210872 | 859488 |  |  | Material | 1153234 | 100331358 | 116594067.9
|  | 2023-11-21 | U2230210873 | 60704 |  |  | Installation | 196766 | 17118642 | 16262709.9
| Total |  |  | 920192 |  |  |  | 1350000 | 117450000 | 1340161.7 | 116594067.9
9 | Gungwar Construction | 2023-04-05 | 20 | 51200
|  | 2023-04-18 | 25 | 48000
|  | 2023-05-01 | 26 | 48000 | [5 empty] | 1427.64 | 142764000
| Total |  |  | 147200 | [6 empty] | =
10 | HME Boilers Pvt Ltd | 2023-11-08 | 31 | 2806000
| Total |  |  | 2806000
11 | Indian Crane Service | 2023-12-05 | 28 | 94400
| Total |  |  | 94400
12 | Kirloskar Pneumatic Co. Ltd. | 2023-11-08 | 34401000973 | 11311307
| Total |  |  | 11311307
13 | Makin Developer Pvt Ltd | 2023-05-12 | 1st RA Bill | 8214169.85
|  | 2023-06-02 | 2nd RA Bill | 8991333.87
|  | 2023-07-01 | 3rd RA Bill | 12048070.3
|  | 2023-08-01 | 4th RA Bill | 10840519.97
|  | 2023-09-01 | 5th RA Bill | 8060898.51
|  | 2023-10-02 | 6th RA Bill | 3405574.58
|  | 2023-11-01 | 7th RA Bill | 14335568.19
|  | 2023-04-07 | MA-02 | 4371451.6
|  | 2023-04-07 | MDPL/MA/01 | 5738603.14
|  | 2023-05-22 | MDPL/MA/02 | 3744454.47
|  | 2023-06-13 | MDPL/MA/03 | 3912045.95
|  | 2023-06-16 | MDPL/MA/04 | 3133450
|  | 2023-07-05 | MDPL/MA/05 | 3688605.07
|  | 2023-07-10 | MDPL/MA/06 | 2815754
|  | 2023-07-28 | MDPL/MA/07 | 2601322.92
|  | 2023-09-11 | MDPL/MA/08 | 523750.08
|  | 2023-10-14 | MDPL/MA/09 | 1487359.32
|  | 2023-10-18 | MDPL/MA/10 | 2219202.4
|  | 2023-11-11 | MDPL/MA/11 | 2809531.62
|  | 2023-04-28 | MDPL/MAT.ADV/01 | 5684299.54
|  | 2023-06-30 | RA MISC - 01 | 145220.71
|  | 2023-08-01 | RA MISC - 02 | 83781.18
|  | 2023-09-01 | RA MISC - 03 | 100298.04
|  | 2023-10-02 | RA MISC - 04 | 78062.78
|  | 2023-11-01 | RA MISC - 05 | 115776.26
| Total |  |  | 109149104.35
14 | Safetechno Services | 2023-06-01 | STS/23-24/056 | 108560
| Total |  |  | 108560
15 | Salman Earthmovers |  |  | 90000
|  | 2024-03-21 |  | 54000
45000
|  | 2024-01-02 |  | 48000
51000
|  | 2024-03-03 |  | 21000
| Total |  |  | 309000
| State Bank of India | 2023-07-31 | T0723051V1979 | 3823862.12
| Total |  |  | 3823862.12
| Schenker India Pvt Ltd | 2023-12-14 | 1550067656 | 310130.49
|  | 2023-12-14 | 1550067658 | 1180741.48
|  | 2023-12-15 | 1550067758 | 2589541.76
|  | 2023-11-06 | 1552523050 | 6903
| Total |  |  | 4087316.73
| Shril Nityanand Pad Ashram | 2024-01-16 | 22 | 106652
|  | 2024-02-02 | 53 | 198506
|  | 2024-02-17 | 72 | 140070
|  | 2024-03-01 | 118 | 127862
|  | 2024-03-17 | 120 | 123144
| Total |  |  | 696234
| Steeline Buildcon Pvt Ltd. | 2023-10-12 |  | 237150.5
|  | 2023-10-11 | SBPL/2023-24/111 | 2342135
|  | 2023-10-12 | SBPL/2023-24/112 | 2637831
|  | 2023-10-25 | SBPL/2023-24/114 | 375240
|  | 2023-10-25 | SBPL/2023-24/115 | 1565860
|  | 2023-11-05 | SBPL/2023-24/118 | 179360
|  | 2023-11-05 | 481384782179 | 2509860
|  | 2023-12-06 | SBPL/2023-24/120 | 1251390
|  | 2023-12-17 | SBPL/2023-24/122 | 1247071.2
| Total |  |  | 12345897.7 | 2.1
| Tata BlueSCope Steel | 2023-09-15 | CI2302102253 | 133384.2
| Total |  |  | 133384.2
| Tharayil Engineering Pvt Ltd | 2023-12-07 | 23-24/1372 | 512669.45
| Total |  |  | 512669.45
| Upen Infra Structure Pvt Ltd | 2023-12-04 | UISPL/23-24/01 | 5337364.2
| Total |  |  | 5337364.2
| YSR & Associates | 2023-05-02 | YSR/2023-24/017 | 19426
|  | 2023-05-02 | YSR/2023-24/018 | 19426
|  | 2023-05-15 | YSR/2023-24/031 | 132160
|  | 2023-05-15 | YSR/2023-24/032 | 10915
|  | 2023-10-09 | YSR/2023-24/220 | 67400
|  | 2023-11-14 | YSR/2023-24/393 | 5900
|  | 2023-11-14 | YSR/2023-24/394 | 5900
|  | 2024-02-08 | YSR/2023-24/557 | 71390
| Total |  |  | 332517
| Amit Kumar Pandey & Company | 2023-10-07 | AKPC/2023-24/100 | 47200
| Total |  |  | 47200
| Chetan K & Associates | 2023-07-04 | 065/2023-24 | 20000
| Total |  |  | 20000
| Gandhi Automation Pvt Ltd | 2024-03-20 | S/2324/03770 | 61360
| Total |  |  | 61360
| SKPMA Gaushala Trust |  |  | 158150
| Total |  |  | 158150
| planET Biogas Global Gmbh |  |  | 116594067.9