## COP
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
COST OF PROJECT |  | (Rs. In Lacs)
S.NO. | COST OF PROJECT | TOTAL
1 | LAND | 5
2 | BUILDING (COST OF CONSTRUCTION) | 2023.7
3 | FURNITURE & FIXTURES | 708
4 | PLANT AND MACHINERY | 379.96
| TOTAL FIXED ASSETS | 3116.66
5 | PRELIMINARY EXPENSES | 175.4958
| TOTAL COST OF PROJECT | 3292.1558
SOURCE OF FUNDS |  | (Rs. In Lacs)
S.NO. | MEANS OF FINANCE | TOTAL
1 | PARTNERS CAPITAL /QUASI CAPITAL | 1074.16
2 | TERM LOAN FROM BANK | 2218.004
| TOTAL SOURCE OF FUNDS | 3292.164
NOTE:
1 | LAND IS SITUATED AT KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN, HAVING TOTAL AREA OF 32800 SQUARE METERS.
2 | SPECIFICATION
a | NO. OF ROOMS / VILLAS | 18
b | BANQUET HALL | 1
c | SWIMMING POOL | 1
d | SPA | 1
3 | MANPOWER | 35

## TL Cal
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
TERM LOAN CALCULATION
(Rs. In Lacs)
S.NO. | PARTICULARS | AMOUNT | MARGIN % | OWN FUNDS | BANK LOAN
1 | BUILDING (COST OF CONSTRUCTION) | 1870.3 | 33.76% | 631.46 | 1238.84
2 | FURNITURE & FIXTURES | 708 | 10% | 70.8 | 637.2
3 | PLANT AND MACHINERY | 379.96 | 10% | 37.996 | 341.964
TOTAL |  | 2958.26 |  | 740.256 | 2218.004

## PROPOSED LAND DETAILS
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
LAND DETAILS
S.NO | LAND DETAILS & SITE DEVELOPMENT | AREA IN SQUARE METERS | TOTAL AMOUNT (RS. IN LAKHS)
(a) | LAND IS SITUATED AT KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN. | 32800 | 5
TOTAL |  | 32800 | 5

## PROPOSED CONSTRUCTION DETAILS
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
BUILDING (COST OF CONSTRUCTION)
S.NO | DESCRIPTION | Area in Sq. ft. | Construction Rate per Sq. ft. | AMOUNT (RS.)
1 | Foundation |  |  | 52500000
2 | One Room Villa (12) | 17140.59 | 2700 | 46279593
3 | Two Room Villa (3) | 5529.68 | 2700 | 14930136
4 | Reception Block | 3368.38 | 1900 | 6399922
5 | Spa and Gym | 2361.84 | 1310 | 3094010.4
6 | Restaurant & Bar Block | 5300.62 | 1650 | 8746023
7 | BOH | 6394.03 | 1650 | 10550149.5
8 | Staff Area |  |  | 6000000
9 | Landscaping |  |  | 10000000
10 | Archietect Fees |  |  | 8000000
11 | Brand Tie Up Cost |  |  | 5000000
Add : GST @ 18% |  |  |  | 30869970.102
TOTAL |  |  |  | 202369804.002
AMOUNT ( Rs. In Lakhs) |  |  |  | 2023.698

## PROPOSED FURNITURE
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
FURNITURE & FIXTURES
S.NO. | PARTICULARS | NO'S | RATE (RS. IN LACS) | AMOUNT (RS. IN LACS)
1 | ROOMS/VILLA'S FURNITURE | 18 | 26 | 468
2 | RESTAURANT FURNITURE | 1 | 41 | 41
3 | RECEPTION FURNITURE | 1 | 30 | 30
4 | BANQUET FURNITURE | 1 | 29 | 29
5 | OTHER AREA FURNITURE | 1 | 32 | 32
Add : GST @ 18% |  |  |  | 108
TOTAL |  |  |  | 708

## PROPOSED P&M
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
PLANT AND MACHINERY
S.NO. | PARTICULARS | NO'S | RATE | AMOUNT (RS. IN LACS)
1 | Air Conditions | 65 | 0.5 | 32.5
2 | DG Set | 3 | 12.5 | 37.5
3 | Transformer | 2 | 10.5 | 21
4 | CCTV | 1 | 21 | 21
5 | Television Sets | 40 | 0.45 | 18
6 | Sewerage Treatment Plant | 1 | 22.75 | 22.75
7 | WATER TREATMENT | 1 | 15.5 | 15.5
8 | WATER SOFTNER PLANT | 1 | 20.75 | 20.75
9 | FILTER PLANT | 1 | 12.5 | 12.5
10 | WATER HEATER | 36 | 0.2 | 7.2
11 | Refrigerator | 26 | 0.3 | 7.8
12 | KITCHEN EQUIPMENTS | 1 | 40.5 | 40.5
13 | COMPUTER SYSTEM | Lumpsum | 26.5 | 26.5
14 | EPABX SYSTEM, TELEPHONE SETS AND TELEPHONE LINES | 1 | 18.5 | 18.5
15 | Electrical Installation | Lumpsum | 20 | 20
Add : GST @ 18% |  |  |  | 57.96
TOTAL |  |  |  | 379.96

## PROJECT IMPLEMENTAION SCHEDULE
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
IMPLEMENTATION SCHEDULE OF PROPOSED UNIT
S.NO | ACTIVITIES | START DATE | END DATE
1 | LAND
2 | BUILDING | - | 31.03.2026
3 | PLANT AND MACHINERY
| ORDER PLACEMENT | - | 31.01.2026
| RECEIPT OF MACHINE | 01.04.2025 | 28.02.2026
| INSTALLATION | 01.04.2025 | 31.03.2026
| COMMISSIONING | 01.04.2025 | 31.03.2026
4 | FURNITURE/FIXTURE/MISC ASSTES
| ORDER PLACEMENT | - | 31.01.2026
| RECEIPT OF FURNITURE | 01.04.2025 | 28.02.2026
| INSTALLATION | 01.04.2025 | 31.03.2026

## MANPOWER PLANNING
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
MANPOWER DETAILS PER MONTH
S.NO | DESIGNATION | NO. | RATE | TOTAL
A. | Operations -Hotel
1 | Manager - Hotel | 1 | 100000 | 100000
2 | Receptionist | 2 | 35000 | 70000
3 | Housekeeping Staffs | 6 | 25000 | 150000
4 | Cleaner | 3 | 15000 | 45000
5 | Sweeper | 3 | 15000 | 45000
B. | Operations - Others
1 | Manager | 1 | 85000 | 85000
2 | Chef | 2 | 55000 | 110000
3 | Cooking Staff | 3 | 40000 | 120000
4 | Waiters | 4 | 20000 | 80000
5 | Cleaner | 2 | 15000 | 30000
6 | Swimming Pool and Spa | 3 | 30000 | 90000
C. | General
1 | GM | 1 | 125000 | 125000
2 | Office Boy | 1 | 25000 | 25000
3 | Accountant | 2 | 30000 | 60000
4 | Store Keeper | 1 | 30000 | 30000
TOTAL |  | 35 |  | 1165000

## PROJECTED PL & BS
Project Report of M/s VAYU SUITES
PROJECTED PROFITABILITY STATEMENT | [12 empty] | (Amount Rs. in Lacs)
| YEAR | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
REVENUE:
| Rooms/Villa Receipts | 0 | 0 | 0 | 1469.664 | 1587.2371 | 1714.2161 | 1851.3534 | 1999.4616 | 2159.4186 | 2332.1721 | 2518.7458 | 2720.2455
| Other Receipts | 0 | 0 | 0 | 209.2726 | 229.9765 | 252.7396 | 277.7673 | 305.2854 | 335.5424 | 368.8116 | 405.3934 | 445.6184
| Total Revenue | 0 | 0 | 0 | 1678.9366 | 1817.2136 | 1966.9557 | 2129.1206 | 2304.747 | 2494.961 | 2700.9836 | 2924.1392 | 3165.8639
EXPENSES:
| Food & Beverages Exp. | 0 | 0 | 0 | 92.2014 | 100.1152 | 108.7158 | 118.0636 | 128.2244 | 139.2695 | 151.277 | 164.3316 | 178.5259
| Salary Expenses | 0 | 0 | 0 | 139.8 | 153.78 | 169.158 | 186.0738 | 204.6812 | 225.1493 | 247.6642 | 272.4307 | 299.6737
| Financial Expenses | 0 | 0 | 0 | 191.6 | 180.8963 | 167.2409 | 150.9621 | 132.0602 | 108.5666 | 74.9032 | 33.3673 | 2.0278
| Adm. & Operational Exp. | 0 | 0 | 0 | 827.3768 | 910.1144 | 1001.1259 | 1101.2385 | 1211.3623 | 1332.4985 | 1465.7484 | 1612.3232 | 1773.5556
| Pre-Operative Expenses W/off | 0 | 0 | 0 | 34.31 | 34.31 | 34.31 | 34.31 | 34.32 | 0 | 0 | 0 | 0
| Total Expenses | 0 | 0 | 0 | 1285.2882 | 1379.2159 | 1480.5506 | 1590.6481 | 1710.6481 | 1805.4839 | 1939.5928 | 2082.4528 | 2253.783
| Less : Depreciation | 0 | 0 | 0 | 343.439 | 300.2717 | 264.3376 | 233.8387 | 207.573 | 184.7102 | 164.656 | 146.9685 | 131.3074
| Total Expenses including Depreciation | 0 | 0 | 0 | 1628.7272 | 1679.4875 | 1744.8881 | 1824.4868 | 1918.2211 | 1990.1941 | 2104.2488 | 2229.4213 | 2385.0904
| Operating Profit | 0 | 0 | 0 | 50.2094 | 137.7261 | 222.0675 | 304.6339 | 386.526 | 504.7669 | 596.7348 | 694.7179 | 780.7735
| Profit Before Tax | 0 | 0 | 0 | 50.2094 | 137.7261 | 222.0675 | 304.6339 | 386.526 | 504.7669 | 596.7348 | 694.7179 | 780.7735
| Provision For Tax | 0 | 0 | 0 | 15.0628 | 41.3178 | 66.6203 | 91.3902 | 115.9578 | 151.4301 | 179.0204 | 208.4154 | 234.2321
| Profit After Tax | 0 | 0 | 0 | 35.1466 | 96.4083 | 155.4473 | 213.2437 | 270.5682 | 353.3368 | 417.7144 | 486.3025 | 546.5415
| Net Retained Profit | 0 | 0 | 0 | 35.1466 | 96.4083 | 155.4473 | 213.2437 | 270.5682 | 353.3368 | 417.7144 | 486.3025 | 546.5415
Project Report of M/s VAYU SUITES
PROJECTED BALANCE SHEET | [12 empty] | (Amount Rs. in Lacs)
| YEAR | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
LIABILITIES
| Partner's Capital | 5 | 503.19 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16
| Reserves and Surplus | 0 | 0 | 0 | 35.1466 | 131.5549 | 287.0022 | 500.2459 | 770.814 | 1124.1508 | 1541.8652 | 2028.1677 | 2574.7092
| Term Loan From Bank | 0 | 920 | 2218 | 2138 | 1998 | 1828 | 1628 | 1398 | 1078 | 638 | 158 | 0
| Unsecured Loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Current Liabilities | 0 | 0 | 0 | 63.85 | 73.43 | 84.44 | 97.11 | 111.68 | 128.43 | 142.87 | 156.23 | 174.74
| Total Liabilities | 5 | 1423.19 | 3292.16 | 3311.1566 | 3277.1449 | 3273.6022 | 3299.5159 | 3354.654 | 3404.7408 | 3396.8952 | 3416.5577 | 3823.6092
| YEAR | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
ASSETS
| Fixed Assets | 5 | 1393 | 3116.66 | 2773.221 | 2472.9494 | 2208.6118 | 1974.7731 | 1767.2001 | 1582.4899 | 1417.8339 | 1270.8654 | 1139.558
| Loans and Deposits | 0 | 0 | 0 | 320 | 600 | 860 | 1100 | 1330 | 1500 | 1630 | 1700 | 2150
| Other Current Assets | 0 | 0.0025 | 0.0041667 | 60.0598 | 71.3597 | 93.7445 | 126.8669 | 171.5081 | 215.7751 | 226.3555 | 259.2165 | 315.6454
| Cash and Bank | 0 | 0 | 0 | 16.69 | 25.96 | 38.68 | 59.62 | 82.01 | 102.54 | 118.77 | 182.54 | 214.47
| Preoperative Expenses | 0 | 30.1875 | 175.4958 | 141.1858 | 106.8758 | 72.5658 | 38.2558 | 3.9358 | 3.9358 | 3.9358 | 3.9358 | 3.9358
| Total Assets | 5 | 1423.19 | 3292.16 | 3311.1566 | 3277.1449 | 3273.6022 | 3299.5159 | 3354.654 | 3404.7408 | 3396.8952 | 3416.5577 | 3823.6092
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Report of M/s VAYU SUITES
ROOMS/VILLA RECEIPTS
| Total No.of Rooms/Villa | 18
| Total No. of Days in Year | 365 Days
| Season Days | 219 Days
| Off Season Days | 146 Days
| Particulars | During Season | During Off Season
| No. of Rooms / Villa | 18 | 18
| Occupancy | 60% | 40%
| Total Rooms/Villa to be Occupied | 10.8 | 7.2
| Total No. of Days in Season | 212 | 153
| Tariff | 45000 | 30000
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
[5 empty] | 8% | 8% | 8% | 8% | 8% | 8% | 8% | 8%
Rooms/Villa Receipts -
| During Season | 0 | 0 | 103032000 | 111274560 | 120176524.8 | 129790646.784 | 140173898.5267 | 151387810.4089 | 163498835.2416 | 176578742.0609 | 190705041.4258
| During Off Season | 0 | 0 | 33048000 | 35691840 | 38547187.2 | 41630962.176 | 44961439.1501 | 48558354.2821 | 52443022.6247 | 56638464.4346 | 61169541.5894
| Total Rooms/ Villa Booking Receipts (A) | 0 | 0 | 136080000 | 146966400 | 158723712 | 171421608.96 | 185135337.6768 | 199946164.6909 | 215941857.8662 | 233217206.4955 | 251874583.0152
Rooms/ Villa Service Charges -
%tage of Gross Receipts | bar: 30000 2026-27 to 30000 2034-35
| Total Rooms/ Villa Service Charges Receipts (B) | 0 | 0 | 10886400 | 11757312 | 12697896.96 | 13713728.7168 | 14810827.0141 | 15995693.1753 | 17275348.6293 | 18657376.5196 | 20149966.6412
| Total Rooms/ Villa Receipts (A+B) | 0 | 0 | 146966400 | 158723712 | 171421608.96 | 185135337.6768 | 199946164.6909 | 215941857.8662 | 233217206.4955 | 251874583.0152 | 272024549.6564
Project Report of M/s VAYU SUITES
FOOD RECEIPTS
| Total No. of Days in Year | 45000 2024-25: 365 Days
| Season Days | 45000 2024-25: 219 Days
| Off Season Days | 45000 2024-25: 146 Days
| Service | 45000 2024-25: During Season; 30000 2025-26: During Off Season
Particulars
| Sitting Capacity | 45000 2024-25: 100; 30000 2025-26: 100
| Occupancy | 45000 2024-25: 15%; 30000 2025-26: 10%
| Total Seats to be Occupied | 45000 2024-25: 15; 30000 2025-26: 10
| Total No. of Days in Season | 45000 2024-25: 212; 30000 2025-26: 153
| Avg Selling Price per Plate | 45000 2024-25: 1000; 30000 2025-26: 850
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
[5 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
Services
| During Season | 0 | 0 | 3180000 | 3498000 | 3847800 | 4232580 | 4655838 | 5121421.8 | 5633563.98 | 6196920.378 | 6816612.4158
| During Off Season | 0 | 0 | 1300500 | 1430550 | 1573605 | 1730965.5 | 1904062.05 | 2094468.255 | 2303915.0805 | 2534306.5885 | 2787737.2474
| Total Food Receipts (A) | 0 | 0 | 4480500 | 4928550 | 5421405 | 5963545.5 | 6559900.05 | 7215890.055 | 7937479.0605 | 8731226.9666 | 9604349.6632
EVENT SERVICES
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| No. of Events in a Year | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Occupancy %tage | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
| No. of Days to be Occupied | 0 | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
| %tage Increase in rates | 0 | 0 | 0 | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
| Event Tariff Per Day | 0 | 0 | 500000 | 550000 | 605000 | 665500 | 732050 | 805255 | 885780.5 | 974358.55 | 1071794.405
| Total Receipts from Event | 0 | 0 | 16000000 | 17600000 | 19360000 | 21296000 | 23425600 | 25768160 | 28344976 | 31179473.6 | 34297420.96
Project Report of M/s VAYU SUITES
SERVICES FROM SPA
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Total No. of Days | 0 | 0 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | 365
| Total No. of Rooms/ Villa | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
| Avg. No. of Person to be stayed in Single Villa | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Total Person in a year | 0 | 0 | 26280 | 26280 | 26280 | 26280 | 26280 | 26280 | 26280 | 26280 | 26280
%tage of Person will use SPA Services | bar: 2024-25 to 2034-35
| Person will use SPA Services | 0 | 0 | 525.6 | 525.6 | 525.6 | 525.6 | 525.6 | 525.6 | 525.6 | 525.6 | 525.6
%tage increase in Price | bar: 2027-28 to 2034-35
| SPA Price per Person | 0 |  | 850 | 892.5 | 937.125 | 983.9813 | 1033.1803 | 1084.8393 | 1139.0813 | 1196.0354 | 1255.8371
| Receipts from SPA ('C) | 0 | 0 | 446760 | 469098 | 492552.9 | 517180.545 | 543039.5723 | 570191.5509 | 598701.1284 | 628636.1848 | 660067.9941
| TOTAL OTHER RECEIPTS (A+B+C) | 0 | 0 | 20927260 | 22997648 | 25273957.9 | 27776726.045 | 30528539.6223 | 33554241.6059 | 36881156.1889 | 40539336.7514 | 44561838.6173
Project Report of M/s VAYU SUITES
EXPENSES SUMMARY
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Food & Beverages Exp. | 0 | 0 | 9220140 | 10011517.2 | 10871581.176 | 11806364.5301 | 12822436.2385 | 13926949.9382 | 15127696.6139 | 16433162.0917 | 17852589.7827
| Salary Expenses | 0 |  | 13980000 | 15378000 | 16915800 | 18607380 | 20468118 | 22514929.8 | 24766422.78 | 27243065.058 | 29967371.5638
| Financial Expenses | 0 | 0 | 19160000 | 18089625 | 16724087.5 | 15096215 | 13206024 | 10856657.65 | 7490323.415 | 3336730.7565 | 202778.8322
| Adm. & Operational Exp. | 0 | 0 | 82737676 | 91011443.6 | 100112587.96 | 110123846.756 | 121136231.4316 | 133249854.5748 | 146574840.0322 | 161232324.0355 | 177355556.439
| Total Expenses | 0 | 0 | 125097816 | 134490585.8 | 144624056.636 | 155633806.2861 | 167632809.6701 | 180548391.9629 | 193959282.8411 | 208245281.9417 | 225378296.6176
FOOD AND BEVERAGES EXPENSES
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Receipts from Rooms/ Villa Services | 0 | 0 | 10886400 | 11757312 | 12697896.96 | 13713728.7168 | 14810827.0141 | 15995693.1753 | 17275348.6293 | 18657376.5196 | 20149966.6412
| Receipts from Food | 0 | 0 | 4480500 | 4928550 | 5421405 | 5963545.5 | 6559900.05 | 7215890.055 | 7937479.0605 | 8731226.9666 | 9604349.6632
| Total | 0 | 0 | 15366900 | 16685862 | 18119301.96 | 19677274.2168 | 21370727.0641 | 23211583.2303 | 25212827.6898 | 27388603.4862 | 29754316.3044
| %tage of Material Consumed |  |  | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60%
| Total Cost of Material Consumed | 0 | 0 | 9220140 | 10011517.2 | 10871581.176 | 11806364.5301 | 12822436.2385 | 13926949.9382 | 15127696.6139 | 16433162.0917 | 17852589.7827
Project Report of M/s VAYU SUITES
ADM. & OPERATIONAL EXPENSES
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| %tage Increase in Expenses |  |  |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
| Laundry and Toiletries Expenses | 0 | 0 | 50463142 | 55509456.2 | 61060401.82 | 67166442.002 | 73883086.2022 | 81271394.8224 | 89398534.3047 | 98338387.7351 | 108172226.5086
| Event Management Expenses | 0 | 0 | 5000000 | 5500000 | 6050000 | 6655000 | 7320500 | 8052550 | 8857805 | 9743585.5 | 10717944.05
| Electricity and Water Expenses | 0 | 0 | 9397454 | 10337199.4 | 11370919.34 | 12508011.274 | 13758812.4014 | 15134693.6415 | 16648163.0057 | 18312979.3063 | 20144277.2369
| Swimming Pool and Spa Maintenance Expenses | 0 | 0 | 1583102 | 1741412.2 | 1915553.42 | 2107108.762 | 2317819.6382 | 2549601.602 | 2804561.7622 | 3085017.9384 | 3393519.7323
| Repairs and Maintenance Expenses | 0 | 0 | 2060684 | 2266752.4 | 2493427.64 | 2742770.404 | 3017047.4444 | 3318752.1888 | 3650627.4077 | 4015690.1485 | 4417259.1633
| Telephone and Internet Expenses | 0 | 0 | 158124 | 173936.4 | 191330.04 | 210463.044 | 231509.3484 | 254660.2832 | 280126.3116 | 308138.9427 | 338952.837
| Travelling Expenses | 0 | 0 | 843610 | 927971 | 1020768.1 | 1122844.91 | 1235129.401 | 1358642.3411 | 1494506.5752 | 1643957.2327 | 1808352.956
| Advertisement Expenses | 0 | 0 | 2000000 | 2200000 | 2420000 | 2662000 | 2928200 | 3221020 | 3543122 | 3897434.2 | 4287177.62
| Printing Expenses | 0 | 0 | 131560 | 144716 | 159187.6 | 175106.36 | 192616.996 | 211878.6956 | 233066.5652 | 256373.2217 | 282010.5438
| Professional & Legal Fees | 0 | 0 | 100000 | 110000 | 121000 | 133100 | 146410 | 161051 | 177156.1 | 194871.71 | 214358.881
| Other Administrative Expenses | 0 | 0 | 11000000 | 12100000 | 13310000 | 14641000 | 16105100 | 17715610 | 19487171 | 21435888.1 | 23579476.91
| Total | 0 | 0 | 82737676 | 91011443.6 | 100112587.96 | 110123846.756 | 121136231.4316 | 133249854.5748 | 146574840.0322 | 161232324.0355 | 177355556.439
| Project Report of M/s VAYU SUITES | 2026-27: Budget
|  |  |  | Software Chrges | 400000 | AMC | AC , Accounting Charges, Commission Exp. Booking Agent 5%, Insurance 2.5 Lacs, Security Charges 1.20 Lacs, Curtalary and Linens, Other Misc 3 Lacs.
FINANCIAL EXPENSES
| Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
| Interest on Term Loan | 3018750 | 14530833.3333 | 19145000 | 18073125 | 16705937.5 | 15076250 | 13184062.5 | 10832500 | 7463750 | 3307500 | 170625
| Bank Charges | 0 | 0 | 5000 | 5500 | 6050 | 6655 | 7320.5 | 8052.55 | 8857.805 | 9743.5855 | 10717.9441
| Other Interest and Charges | 0 | 0 | 10000 | 11000 | 12100 | 13310 | 14641 | 16105.1 | 17715.61 | 19487.171 | 21435.8881
| (-) Charged to Pre-operative Expenses | 3018750 | 14530833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 19160000 | 18089625 | 16724087.5 | 15096215 | 13206024 | 10856657.65 | 7490323.415 | 3336730.7565 | 202778.8322

## Reason
S.No. | Heads | Reasoning
1 | Revenue from Room
- | Room Tariff | As per the Industry standards for such Hotels Room Revenue is Rs. 75k-80k per night. Comparitives Hotels in such range are Sujan Jawai, Amritara Jawai Resort. We have taken Tariff on conservative approach for season 45k and for non season 30k. |  | why room rent is high when we have not any competitive edge benefit, like (No hills, river, no view )
- | No. of Days | We have taken Seasons days from September to March (212 Days) and Non Season days from April to August (153 Days). |  | seasonal should be October to March
- | Occupancy % | Occupancy is mostly dependes on Weekends. We can assume that there will be 100% Occupancy for 156 days (52 weeks *3) and 20% occupancy on remaining days.
2 | Service Charges
- | As per Industry norms, 8% service charges have been charged from room guest which includes laundary, Room Dining and others (Double Beds, Room Decoration, Early Check in charges, Child Care Charges, Travel Desk Charges and Other Miscellaneous as per guest Demand).
3 | Revenue from Restaurant
- | Seating Capacity | Seating Capacity is for 100 persons.
- | Avg. selling price per plate | As per Industry standard norms for season Rs. 1000/- per person per plate and for non season Rs. 850/- per person per plate.
- | No. of Days | We have taken Seasons days from September to March (212 Days) and Non Season days from April to August (153 Days).
- | Occupancy % | Occupancy is mostly dependes on Weekends. As the Hotel is mostly used for stay purpose so occupancy of restaurant is normally 10%-15%.
4 | Revenue from Event
- | No. of Events in A Year | Normally 40 Events will be take place in a Year.
- | Occupancy | We have taken 80% occupancy which means that approx 32 Events will take place in a year.
- | Increase in rates | 5% increase every year, as per standards.
- | Tariff per Event | As per industry standards Rs. 500000/- will be charged which includes the Venue, Food, Arrangements, Lighting, Sound, etc.
5 | Revenue from SPA
- | Avg. Person per Rooms | 4 Persons per room.
- | Occupancy | We have taken 2% occupancy as per industry standards.
- | Increase in rates | 5% increase every year, as per standards.
- | Rates | As per industry standards Rs. 850/- will be charged.
5 | Food & Beverages Expenses
- | As per Industry norms, Cost has been estimated as 60% of the Revenue from Food.
6 | Administrative Expenses
- | Laundry and Toiletries Expenses | As per Industry norms we have considered 35%-40% of Room Revenue as Laundry and Toiletries Expenses with every year increase of 0.5% to 1% increase. |  | why is it so high expenses
- | Event Expenses | As per Industry norms we have considered 35% of Event Revenue as Event Expenses.
- | Electricity and Water Expenses | We have considered 50k-55k units consumption per month with every year increase of 10%. |  | reasoning for the 55k units
- | Swimming Pool and Spa Maintenance Expenses | This is as per industry standards.
- | Repairs and Maintenance Expenses | This is as per industry standards.
- | Telephone and Internet Expenses | This is as per industry standards, for all staff.
- | Travelling Expenses | This is as per industry standards.
- | Advertisement Expenses | This is as per industry standards.
- | Printing Expenses | This is as per industry standards.
- | Professional & Legal Fees | It includes Audit and Other Professional charges.
- | Other Administrative Expenses | It Includes:
| - | Software Charges - Rs. 325000/- per month. | 3900000
| - | Insurance Charges - Rs. 250000/- per month. | 3000000
| - | Security Charges - Rs. 100000/- per month. | 1200000
| - | Cutlury and Linen - Rs. 1100000/- per year. | 1100000
| - | Other Miscellaneous - Rs. 150000/- per month. | 1800000

## Depreciation
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
Calculation of Depreciation as per Income Tax | [12 empty] | (Rs. in Lakhs)
PARTICULARS | Rate | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Land |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Building | 10%
WDV (Beg.) |  | 0 | 0 | 1388 | 2023.7 | 1821.33 | 1639.197 | 1475.2773 | 1327.7496 | 1194.9746 | 1075.4772 | 967.9294 | 871.1365
Additions |  | 0 | 1388 | 635.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 1388 | 2023.7 | 2023.7 | 1821.33 | 1639.197 | 1475.2773 | 1327.7496 | 1194.9746 | 1075.4772 | 967.9294 | 871.1365
Current Dep. |  | 0 | 0 | 0 | 202.37 | 182.133 | 163.9197 | 147.5277 | 132.775 | 119.4975 | 107.5477 | 96.7929 | 87.1136
WDV (End of Year) |  | 0 | 1388 | 2023.7 | 1821.33 | 1639.197 | 1475.2773 | 1327.7496 | 1194.9746 | 1075.4772 | 967.9294 | 871.1365 | 784.0228
Plant & Machinery | 15%
WDV (Beg.) |  | 0 | 0 | 0 | 326.86 | 277.831 | 236.1564 | 200.7329 | 170.623 | 145.0295 | 123.2751 | 104.7838 | 89.0663
Additions |  | 0 | 0 | 326.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 326.86 | 326.86 | 277.831 | 236.1564 | 200.7329 | 170.623 | 145.0295 | 123.2751 | 104.7838 | 89.0663
Current Dep. |  | 0 | 0 | 0 | 49.029 | 41.6746 | 35.4235 | 30.1099 | 25.5934 | 21.7544 | 18.4913 | 15.7176 | 13.3599
WDV (End of Year) |  | 0 | 0 | 326.86 | 277.831 | 236.1564 | 200.7329 | 170.623 | 145.0295 | 123.2751 | 104.7838 | 89.0663 | 75.7063
Computers & Softwares | 40%
WDV (Beg.) |  | 0 | 0 | 0 | 53.1 | 31.86 | 19.116 | 11.4696 | 6.8818 | 4.1291 | 2.4774 | 1.4865 | 0.89188
Additions |  | 0 | 0 | 53.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 53.1 | 53.1 | 31.86 | 19.116 | 11.4696 | 6.8818 | 4.1291 | 2.4774 | 1.4865 | 0.89188
Current Dep. |  | 0 | 0 | 0 | 21.24 | 12.744 | 7.6464 | 4.5878 | 2.7527 | 1.6516 | 0.99097 | 0.59458 | 0.35675
WDV (End of Year) |  | 0 | 0 | 53.1 | 31.86 | 19.116 | 11.4696 | 6.8818 | 4.1291 | 2.4774 | 1.4865 | 0.89188 | 0.53513
Furniture & Fixture | 10%
WDV (Beg.) |  | 0 | 0 | 0 | 708 | 637.2 | 573.48 | 516.132 | 464.5188 | 418.0669 | 376.2602 | 338.6342 | 304.7708
Additions |  | 0 | 0 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 708 | 708 | 637.2 | 573.48 | 516.132 | 464.5188 | 418.0669 | 376.2602 | 338.6342 | 304.7708
Current Dep. |  | 0 | 0 | 0 | 70.8 | 63.72 | 57.348 | 51.6132 | 46.4519 | 41.8067 | 37.626 | 33.8634 | 30.4771
WDV (End of Year) |  | 0 | 0 | 708 | 637.2 | 573.48 | 516.132 | 464.5188 | 418.0669 | 376.2602 | 338.6342 | 304.7708 | 274.2937
Total Current Dep. |  | 0 | 0 | 0 | 343.439 | 300.2717 | 264.3376 | 233.8387 | 207.573 | 184.7102 | 164.656 | 146.9685 | 131.3074
(Rs. in Lakhs)
YEAR |  | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Gross Block |  | 5 | 5 | 1393 | 3116.66 | 2773.221 | 2472.9493 | 2208.6118 | 1974.7731 | 1767.2001 | 1582.4899 | 1417.8339 | 1270.8654
Addition |  | 0 | 1388 | 1723.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 5 | 1393 | 3116.66 | 3116.66 | 2773.221 | 2472.9493 | 2208.6118 | 1974.7731 | 1767.2001 | 1582.4899 | 1417.8339 | 1270.8654
Less: Dep |  | 0 | 0 | 0 | 343.439 | 300.2717 | 264.3376 | 233.8387 | 207.573 | 184.7102 | 164.656 | 146.9685 | 131.3074
Net Block |  | 5 | 1393 | 3116.66 | 2773.221 | 2472.9494 | 2208.6118 | 1974.7731 | 1767.2001 | 1582.4899 | 1417.8339 | 1270.8654 | 1139.558

## Repayment Schedule
M/s VAYU SUITES
NEW HOTEL PROJECT
REG. ADDRESS : -LOBBY LEVEL, INSIDE HOTEL VISHNUPRIYA, 9, GULAB BAGH ROAD, UDAIPUR, RAJASTHAN, 313001
UNIT ADDRESS : -KHASARA NO. 579/546, REVENUE VILLAGE-SENA, TEHSIL-BALI, DISTRICT-PALI, RAJASTHAN
REPAYMENT SCHEDULE |  | Interest @ | 8.75% |  |  | (Rs. in lacs)
Months | Opening | Received | Total | Repaid | Closing | Interest | Total
2024-25
2024-08-01 | 0 | 115 | 115 | 0 | 115 | 0.83854
2024-09-01 | 115 | 115 | 230 | 0 | 230 | 1.6771
2024-10-01 | 230 | 115 | 345 | 0 | 345 | 2.5156
2024-11-01 | 345 | 115 | 460 | 0 | 460 | 3.3542
2024-12-01 | 460 | 115 | 575 | 0 | 575 | 4.1927
2025-01-01 | 575 | 115 | 690 | 0 | 690 | 5.0312
2025-02-01 | 690 | 115 | 805 | 0 | 805 | 5.8698
2025-03-01 | 805 | 115 | 920 | 0 | 920 | 6.7083 | 30.1875
2025-26 | Opening | Received | Total | Repaid | Closing | Interest | Total
2025-04-01 | 920 | 115 | 1035 | 0 | 1035 | 7.5469
2025-05-01 | 1035 | 115 | 1150 | 0 | 1150 | 8.3854
2025-06-01 | 1150 | 115 | 1265 | 0 | 1265 | 9.224
2025-07-01 | 1265 | 115 | 1380 | 0 | 1380 | 10.0625
2025-08-01 | 1380 | 115 | 1495 | 0 | 1495 | 10.901
2025-09-01 | 1495 | 115 | 1610 | 0 | 1610 | 11.7396
2025-10-01 | 1610 | 115 | 1725 | 0 | 1725 | 12.5781
2025-11-01 | 1725 | 115 | 1840 | 0 | 1840 | 13.4167
2025-12-01 | 1840 | 115 | 1955 | 0 | 1955 | 14.2552
2026-01-01 | 1955 | 115 | 2070 | 0 | 2070 | 15.0938
2026-02-01 | 2070 | 115 | 2185 | 0 | 2185 | 15.9323
2026-03-01 | 2185 | 33 | 2218 | 0 | 2218 | 16.1729 | 145.3083
2026-27 | Opening | Received | Total | Repaid | Closing | Interest | Total
2026-04-01 | 2218 | 0 | 2218 | 0 | 2218 | 16.1729
2026-05-01 | 2218 | 0 | 2218 | 0 | 2218 | 16.1729
2026-06-01 | 2218 | 0 | 2218 | 0 | 2218 | 16.1729
2026-07-01 | 2218 | 0 | 2218 | 0 | 2218 | 16.1729
2026-08-01 | 2218 | 0 | 2218 | 10 | 2208 | 16.1
2026-09-01 | 2208 | 0 | 2208 | 10 | 2198 | 16.0271
2026-10-01 | 2198 | 0 | 2198 | 10 | 2188 | 15.9542
2026-11-01 | 2188 | 0 | 2188 | 10 | 2178 | 15.8812
2026-12-01 | 2178 | 0 | 2178 | 10 | 2168 | 15.8083
2027-01-01 | 2168 | 0 | 2168 | 10 | 2158 | 15.7354
2027-02-01 | 2158 | 0 | 2158 | 10 | 2148 | 15.6625
2027-03-01 | 2148 | 0 | 2148 | 10 | 2138 | 15.5896 | 191.45
2027-28 | Opening | Received | Total | Repaid | Closing | Interest | Total
2027-04-01 | 2138 | 0 | 2138 | 10 | 2128 | 15.5167
2027-05-01 | 2128 | 0 | 2128 | 10 | 2118 | 15.4437
2027-06-01 | 2118 | 0 | 2118 | 10 | 2108 | 15.3708
2027-07-01 | 2108 | 0 | 2108 | 10 | 2098 | 15.2979
2027-08-01 | 2098 | 0 | 2098 | 12.5 | 2085.5 | 15.2068
2027-09-01 | 2085.5 | 0 | 2085.5 | 12.5 | 2073 | 15.1156
2027-10-01 | 2073 | 0 | 2073 | 12.5 | 2060.5 | 15.0245
2027-11-01 | 2060.5 | 0 | 2060.5 | 12.5 | 2048 | 14.9333
2027-12-01 | 2048 | 0 | 2048 | 12.5 | 2035.5 | 14.8422
2028-01-01 | 2035.5 | 0 | 2035.5 | 12.5 | 2023 | 14.751
2028-02-01 | 2023 | 0 | 2023 | 12.5 | 2010.5 | 14.6599
2028-03-01 | 2010.5 | 0 | 2010.5 | 12.5 | 1998 | 14.5687 | 180.7313
2028-29 | Opening | Received | Total | Repaid | Closing | Interest | Total
2028-04-01 | 1998 | 0 | 1998 | 12.5 | 1985.5 | 14.4776
2028-05-01 | 1985.5 | 0 | 1985.5 | 12.5 | 1973 | 14.3865
2028-06-01 | 1973 | 0 | 1973 | 12.5 | 1960.5 | 14.2953
2028-07-01 | 1960.5 | 0 | 1960.5 | 12.5 | 1948 | 14.2042
2028-08-01 | 1948 | 0 | 1948 | 15 | 1933 | 14.0948
2028-09-01 | 1933 | 0 | 1933 | 15 | 1918 | 13.9854
2028-10-01 | 1918 | 0 | 1918 | 15 | 1903 | 13.876
2028-11-01 | 1903 | 0 | 1903 | 15 | 1888 | 13.7667
2028-12-01 | 1888 | 0 | 1888 | 15 | 1873 | 13.6573
2029-01-01 | 1873 | 0 | 1873 | 15 | 1858 | 13.5479
2029-02-01 | 1858 | 0 | 1858 | 15 | 1843 | 13.4385
2029-03-01 | 1843 | 0 | 1843 | 15 | 1828 | 13.3292 | 167.0594
2029-30 | Opening | Received | Total | Repaid | Closing | Interest | Total
2029-04-01 | 1828 | 0 | 1828 | 15 | 1813 | 13.2198
2029-05-01 | 1813 | 0 | 1813 | 15 | 1798 | 13.1104
2029-06-01 | 1798 | 0 | 1798 | 15 | 1783 | 13.001
2029-07-01 | 1783 | 0 | 1783 | 15 | 1768 | 12.8917
2029-08-01 | 1768 | 0 | 1768 | 17.5 | 1750.5 | 12.7641
2029-09-01 | 1750.5 | 0 | 1750.5 | 17.5 | 1733 | 12.6365
2029-10-01 | 1733 | 0 | 1733 | 17.5 | 1715.5 | 12.5089
2029-11-01 | 1715.5 | 0 | 1715.5 | 17.5 | 1698 | 12.3812
2029-12-01 | 1698 | 0 | 1698 | 17.5 | 1680.5 | 12.2536
2030-01-01 | 1680.5 | 0 | 1680.5 | 17.5 | 1663 | 12.126
2030-02-01 | 1663 | 0 | 1663 | 17.5 | 1645.5 | 11.9984
2030-03-01 | 1645.5 | 0 | 1645.5 | 17.5 | 1628 | 11.8708 | 150.7625
2030-31 | Opening | Received | Total | Repaid | Closing | Interest | Total
2030-04-01 | 1628 | 0 | 1628 | 17.5 | 1610.5 | 11.7432
2030-05-01 | 1610.5 | 0 | 1610.5 | 17.5 | 1593 | 11.6156
2030-06-01 | 1593 | 0 | 1593 | 17.5 | 1575.5 | 11.488
2030-07-01 | 1575.5 | 0 | 1575.5 | 17.5 | 1558 | 11.3604
2030-08-01 | 1558 | 0 | 1558 | 20 | 1538 | 11.2146
2030-09-01 | 1538 | 0 | 1538 | 20 | 1518 | 11.0687
2030-10-01 | 1518 | 0 | 1518 | 20 | 1498 | 10.9229
2030-11-01 | 1498 | 0 | 1498 | 20 | 1478 | 10.7771
2030-12-01 | 1478 | 0 | 1478 | 20 | 1458 | 10.6312
2031-01-01 | 1458 | 0 | 1458 | 20 | 1438 | 10.4854
2031-02-01 | 1438 | 0 | 1438 | 20 | 1418 | 10.3396
2031-03-01 | 1418 | 0 | 1418 | 20 | 1398 | 10.1937 | 131.8406
2031-32 | Opening | Received | Total | Repaid | Closing | Interest | Total
2031-04-01 | 1398 | 0 | 1398 | 20 | 1378 | 10.0479
2031-05-01 | 1378 | 0 | 1378 | 20 | 1358 | 9.9021
2031-06-01 | 1358 | 0 | 1358 | 20 | 1338 | 9.7562
2031-07-01 | 1338 | 0 | 1338 | 20 | 1318 | 9.6104
2031-08-01 | 1318 | 0 | 1318 | 30 | 1288 | 9.3917
2031-09-01 | 1288 | 0 | 1288 | 30 | 1258 | 9.1729
2031-10-01 | 1258 | 0 | 1258 | 30 | 1228 | 8.9542
2031-11-01 | 1228 | 0 | 1228 | 30 | 1198 | 8.7354
2031-12-01 | 1198 | 0 | 1198 | 30 | 1168 | 8.5167
2032-01-01 | 1168 | 0 | 1168 | 30 | 1138 | 8.2979
2032-02-01 | 1138 | 0 | 1138 | 30 | 1108 | 8.0792
2032-03-01 | 1108 | 0 | 1108 | 30 | 1078 | 7.8604 | 108.325
2032-33 | Opening | Received | Total | Repaid | Closing | Interest | Total
2032-04-01 | 1078 | 0 | 1078 | 30 | 1048 | 7.6417
2032-05-01 | 1048 | 0 | 1048 | 30 | 1018 | 7.4229
2032-06-01 | 1018 | 0 | 1018 | 30 | 988 | 7.2042
2032-07-01 | 988 | 0 | 988 | 30 | 958 | 6.9854
2032-08-01 | 958 | 0 | 958 | 40 | 918 | 6.6937
2032-09-01 | 918 | 0 | 918 | 40 | 878 | 6.4021
2032-10-01 | 878 | 0 | 878 | 40 | 838 | 6.1104
2032-11-01 | 838 | 0 | 838 | 40 | 798 | 5.8187
2032-12-01 | 798 | 0 | 798 | 40 | 758 | 5.5271
2033-01-01 | 758 | 0 | 758 | 40 | 718 | 5.2354
2033-02-01 | 718 | 0 | 718 | 40 | 678 | 4.9437
2033-03-01 | 678 | 0 | 678 | 40 | 638 | 4.6521 | 74.6375
2033-34 | Opening | Received | Total | Repaid | Closing | Interest | Total
2033-04-01 | 638 | 0 | 638 | 40 | 598 | 4.3604
2033-05-01 | 598 | 0 | 598 | 40 | 558 | 4.0687
2033-06-01 | 558 | 0 | 558 | 40 | 518 | 3.7771
2033-07-01 | 518 | 0 | 518 | 40 | 478 | 3.4854
2033-08-01 | 478 | 0 | 478 | 40 | 438 | 3.1937
2033-09-01 | 438 | 0 | 438 | 40 | 398 | 2.9021
2033-10-01 | 398 | 0 | 398 | 40 | 358 | 2.6104
2033-11-01 | 358 | 0 | 358 | 40 | 318 | 2.3188
2033-12-01 | 318 | 0 | 318 | 40 | 278 | 2.0271
2034-01-01 | 278 | 0 | 278 | 40 | 238 | 1.7354
2034-02-01 | 238 | 0 | 238 | 40 | 198 | 1.4437
2034-03-01 | 198 | 0 | 198 | 40 | 158 | 1.1521 | 33.075
2034-35 | Opening | Received | Total | Repaid | Closing | Interest | Total
2034-04-01 | 158 | 0 | 158 | 40 | 118 | 0.86042
2034-05-01 | 118 | 0 | 118 | 40 | 78 | 0.56875
2034-06-01 | 78 | 0 | 78 | 40 | 38 | 0.27708
2034-07-01 | 38 | 0 | 38 | 38 | 0 | 0 | 1.7063
Year | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Interest | 30.1875 | 145.3083 | 191.45 | 180.7313 | 167.0594 | 150.7625 | 131.8406 | 108.325 | 74.6375 | 33.075 | 1.7063
Principal | 920 | 1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repayment | 0 | 0 | 80 | 140 | 170 | 200 | 230 | 320 | 440 | 480 | 158
Outstanding | 920 | 2218 | 2138 | 1998 | 1828 | 1628 | 1398 | 1078 | 638 | 158 | 0
Current Maturity | 0 | 80 | 140 | 170 | 200 | 230 | 320 | 440 | 480 | 158 | 0
Long Term Maturity | 920 | 2138 | 1998 | 1828 | 1628 | 1398 | 1078 | 638 | 158 | 0 | 0
EMI | 30.1875 | 145.3083 | 271.45 | 320.7313 | 337.0594 | 350.7625 | 361.8406 | 428.325 | 514.6375 | 513.075 | 159.7063

## DSCR
Project Report of M/s VAYU SUITES
DSCR CALCULATIONS
Debt Equity Ratio | [10 empty] | (Rs. In Lakhs)
Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Debt Equity Ratio = a/b | 1.8283 | 2.0649 | 1.9273 | 1.6571 | 1.343 | 1.034 | 0.75773 | 0.49038 | 0.24388 | 0.05093 | 0
Term Loan | 920 | 2218 | 2138 | 1998 | 1828 | 1628 | 1398 | 1078 | 638 | 158 | 0
Total (a) | 920 | 2218 | 2138 | 1998 | 1828 | 1628 | 1398 | 1078 | 638 | 158 | 0
Capital + Internal Accruals | 503.19 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16 | 1074.16
Reserve & Surplus | 0 | 0 | 35.1466 | 131.5549 | 287.0022 | 500.2459 | 770.814 | 1124.1508 | 1541.8652 | 2028.1677 | 2574.7092
Total (b) | 503.19 | 1074.16 | 1109.3066 | 1205.7149 | 1361.1622 | 1574.4059 | 1844.974 | 2198.3108 | 2616.0252 | 3102.3277 | 3648.8692
Debt Service Coverage Ratio (DSCR) | (Rs. In Lakhs) 2034-35: (Rs. In Lakhs)
Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Net Operating Profit | 0 | 0 | 35.1466 | 96.4083 | 155.4473 | 213.2437 | 270.5682 | 353.3368 | 417.7144 | 486.3025 | 546.5415
Add: Interest Expenses | 0 | 0 | 191.45 | 180.7312 | 167.0594 | 150.7625 | 131.8406 | 108.325 | 74.6375 | 33.075 | 1.7063
Add: Depreciation | 0 | 0 | 343.439 | 300.2717 | 264.3376 | 233.8387 | 207.573 | 184.7102 | 164.656 | 146.9685 | 131.3074
Add: Preliminary Expenses W/off | 0 | 0 | 34.31 | 34.31 | 34.31 | 34.31 | 34.32 | 0 | 0 | 0 | 0
Total (A) | 0 | 0 | 535.7256 | 543.1012 | 552.5342 | 563.5349 | 575.6618 | 646.372 | 657.0079 | 666.346 | 679.5551
EMI | 0 | 0 | 271.45 | 320.7313 | 337.0594 | 350.7625 | 361.8406 | 428.325 | 514.6375 | 513.075 | 159.7063
Total (B) | 0 | 0 | 271.45 | 320.7313 | 337.0594 | 350.7625 | 361.8406 | 428.325 | 514.6375 | 513.075 | 159.7063
Debt Service Coverage Ratio (DSCR)A/B | 0 | 0 | 1.9736 | 1.6933 | 1.6393 | 1.6066 | 1.5909 | 1.5091 | 1.2766 | 1.2987 | 4.255
Average DSCR based on 2025-2035 | 2024-25: 1.6638
Current Ratio | (Rs. In Lakhs) 2034-35: (Rs. In Lakhs)
Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Current Ratio = a/b | 0 | 5.2083e-05 | 1.9463 | 2.8646 | 3.489 | 3.9329 | 3.6683 | 3.1988 | 3.171 | 6.8159 | 15.3377
Current Assets (a) | 0.0025 | 0.0041667 | 396.7498 | 697.3197 | 992.4245 | 1286.4869 | 1583.5181 | 1818.3151 | 1975.1255 | 2141.7565 | 2680.1154
Current Liabilities including Current Term Loan Installment (b) | 0 | 80 | 203.85 | 243.43 | 284.44 | 327.11 | 431.68 | 568.43 | 622.87 | 314.23 | 174.74
TOL/TNW | (Rs. In Lakhs) 2034-35: (Rs. In Lakhs)
Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
TOL/TNW= a/b | 1.945 | 2.4681 | 2.2744 | 1.8851 | 1.4841 | 1.123 | 0.82002 | 0.54978 | 0.29894 | 0.10142 | 0.047941
TOL (a) | 920 | 2218 | 2201.85 | 2071.43 | 1912.44 | 1725.11 | 1509.68 | 1206.43 | 780.87 | 314.23 | 174.74
TNW (b) | 473.0025 | 898.6642 | 968.1208 | 1098.839 | 1288.5963 | 1536.15 | 1841.0382 | 2194.375 | 2612.0894 | 3098.3919 | 3644.9333
Fixed Asset Coverage Ratio | (Rs. In Lakhs) 2034-35: (Rs. In Lakhs)
Particulars | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
Net Fixed Asset/Debt= a/b | 1.5141 | 1.4052 | 1.2971 | 1.2377 | 1.2082 | 1.213 | 1.2641 | 1.468 | 2.2223 | 8.0435 | -
Net Fixed Asset (a) | 1393 | 3116.66 | 2773.221 | 2472.9494 | 2208.6118 | 1974.7731 | 1767.2001 | 1582.4899 | 1417.8339 | 1270.8654 | 1139.558
Debt (b) | 920 | 2218 | 2138 | 1998 | 1828 | 1628 | 1398 | 1078 | 638 | 158 | 0