File No.: VIS (2024-25)-PL333-292-386		       	                          Dated: 10.01.2025

TECHNO-ECONOMIC VIABILITY

STUDY REPORT

OF

63.30 MW WIND-SOLAR HYBRID POWER PLANT

(36 MW DC Solar + 27.30 MW Wind)

SETUP BY

M/S SAI INFINIUM LIMITED

REPORT PREPARED FOR

M/S SAI INFINIUM LIMITED

3RD FLOOR, 2137, BANSAL HOUSE, NR. GOLDEN ARC, ATABHAI CHOWK, BHAVNAGAR, GUJARAT, INDIA, 364002

**Important - In case of any query/ issue or escalation you may please contact Incident Manager Valuers@rkassociates.org. We will appreciate your feedback in order to improve our services.

NOTE: As per IBA Guidelines please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct.

IMPORTANT NOTICE

COPYRIGHT FORMAT: This report is prepared on the copyright format of R. K. Associates Valuers & Techno Engineering Consultants (P) Ltd. (R. K. Associates) to serve our clients with the best possible information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R. K. Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format or report or any of its content/ information/ data by any organization or individual other than R.K Associates will be seen as an unlawful act and necessary legal action can be taken against the defaulters.

This report is intended for the sole use of the intended recipient/s and contains material that is STRICTLY CONFIDENTIAL AND PRIVATE.

DEFECT LIABILITY PERIOD: In case of any query/ issue or escalation you may please contact Incident Manager at valuers@rkassociates.org. Though adequate care has been taken while preparing this report as per its scope, but still we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it will be considered that the report is complete in all respect and has been accepted by the client up to their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

Part O: R. K. Associates Important Disclaimer and Remarks are integral part of this report and Feasibility assessment is subject to this section. Reader of the report is advised to read all the points mentioned in these sections carefully.

| TABLE OF CONTENTS |  |  |
| --- | --- | --- |
| SECTIONS | PARTICULARS | PAGE NO. |
| Part A | Report Summary | 4 |
| Part B | INTRODUCTION |  |
|  | - About the Report | 6 |
|  | - Executive summary | 6 |
|  | - Purpose of the Report | 11 |
|  | - Scope of the Report | 11 |
|  | - Methodology/ Model Adopted | 12 |
|  | - Data Information received from | 12 |
|  | - Documents/ Data Referred | 12 |
| Part C | Company Profile |  |
|  | - Company Overview | 13 |
|  | - Proposed Shareholding Pattern | 14 |
|  | - Promoters/Directors Profile | 15 |
| Part D | Proposed Unit’s Infrastructure Details |  |
|  | - Proposed Plant Location | 22 |
|  | - Google Map Location | 23 |
|  | - Schematic Layout Plan | 24 |
|  | - Land Details | 24 |
|  | - Site pictures | 27 |
|  | - Building & Civil Works | 29 |
|  | - Plant and Machinery/ Equipment details | 29 |
|  | - Utilities | 31 |
| Part E | Project Technical details |  |
|  | - Capacity of Proposed Hybrid Power Plant | 32 |
|  | - Project Implementation | 32 |
|  | - Commercial Agreement Details | 32 |
|  | - EPC Details | 36 |
|  | - Technical Specification of proposed Power Plant | 41 |
|  | - Technological Assessment | 52 |
|  | - Manpower | 52 |
| Part F | Industry Overview & Analysis | 53 |
| Part G | SWOT Analysis | 61 |
| Part H | Project Cost and Means of Finance | 64 |
| Part I | Project Implementation Schedule | 69 |
| Part J | Statutory Approvals ¦ Licences ¦ NOC | 71 |
| Part K | Company’s Financial Feasibility | 73 |
| Part L | Conclusion | 99 |
| Part M | Disclaimer ¦ Remarks | 101 |

| PART A | REPORT SUMMARY |
| --- | --- |

| S. No. | PARTICULAR | DESCRIPTION |
| --- | --- | --- |
|  | Name of the Company: | M/s Sai Infinium Limited |
|  | Registered Address: | 3rd Floor, 2137, Bansal House, NR. Golden ARC, Atabhai Chowk, Bhavnagar, Gujarat, India, 364002 |
|  | Project Name | 63.30 MW Wind - Solar Hybrid Power Plant ( Captive & Open Access) |
|  | Project Location: | Sardharka Village Wankaner Taluka Morbi District, State of Gujrat 363621 |
|  | Project Type: | 63.30 MW Wind-Solar Hybrid Power Plant ( Captive and Open Access) |
|  | Project Industry: | Renewable Energy |
|  | Product Type / Deliverables: | Power Generation |
|  | Report Prepared for Organization: | M/s. Sai Infinium Limited |
|  | TEV Consultant Firm: | M/s. R.K Associates Valuers & Techno Engineering Consultants (P) Ltd. |
|  | Report type: | Techno-Economic Viability Report |
|  | Purpose of the Report: | To assess Technical & Economic Viability for the purpose of seeking external financial assistance to setup captive Wind-Solar Hybrid Power Plant. |
|  | Scope of the Report: | To assess, evaluate & comment on Technical, Economical & Commercial Viability of the Project as per data information provided by the client, independent Industry research and data/ information available on public domain. |
|  | Date of Report: | 10th January 2025 |
|  | Documents referred for the Project: | - PROJECT INITIATION DOCUMENTS: - Detailed Project Report - Financial Projections of the Project - Project proposed Schedule - Statutory Approval Details - Layout and Master Plan - PROCUREMENT DOCUMENTS: - EPC Agreement - List of Plant & Machinery along with acquisition costs for the same - Details of Expected Supplier of Plant & Machinery - Process Flow Chart - Sanction/proposed map of the sites - Lease/Sale deeds of the Land - STATUTORY APPROVALS, LICENCES & NOCs - Certificate of Incorporation - MSME UDYAM Registration Certificate - GETCO, GERC, GEDA Approvals - NOC/Application for Ground water |
|  | Means of Finance: | Equity & Debt (D/E Ratio 3.00 TPC) |
|  | Key Financial Indicators: | Key Indicators; Value. Average DSCR; 2.68. Average EBITDA Margin; 87.54%. Avg. PAT Margin; 43.69%. NPV & IRR; INR 244 Cr. & 16.99%. Payback Period; 7.05 years. |

Note: Above financial indicators are based on the financial projections of the proposed project provided by the firm and assessment and analysis of the same done by us.

| PART B | INTRODUCTION |
| --- | --- |

- ABOUT THE REPORT:

This is a Techno-Economic Viability Study Report of the proposed 63.30 MW Hybrid power project [36 MW DC Solar + 27.30 MW Wind] at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621

- EXECUTIVE SUMMARY:

Gujarat Renewable Energy Policy- 2023: Government of India has pledged for transition to clean energy in power sector through nationwide targets with commitment towards Nationally Determined Contribution of 50% of cumulative electric power installed capacity from non-fossil fuel-based energy resources by the year 2030. Government of Gujarat is playing a pivotal role in this energy transition. State has successfully demonstrated its commitment towards clean energy with installed Renewable Capacity of 21.6 GW at present in which the addition of about 12 GW has taken place during last 5 years.

Taking cognizance of the generational shift occurring in electricity sector, the need for expediting efforts for de-carbonization and in an endeavour to embrace renewable energy more effusively, Government of Gujarat has notified a Renewable Energy Policy-2023 (Reference: Gujarat Renewable Energy Policy- 2023 G.R. No. REN/e-file/20/2023/0476/B1 Sachivalaya, Gandhinagar, Date: 04/10/2023)  for further encouraging setting up of renewable generation projects based on Wind, Solar and Wind-Solar Hybrid technologies.

Renewable Energy Projects that are installed and commissioned during the operative period will be eligible for the benefits and incentives outlined in this policy. Further, the projects commissioned after 19th June-2023 under Wind Solar Hybrid Policy-2018 and before the issuance of this Policy shall be eligible for the benefits under this Policy. These benefits will be applicable for a period of 25 years from the date of commissioning or the lifespan of the RE project, as defined by GERC/MoP/MNRE, whichever is earlier.

Wind-Solar Hybrid under the Policy: Solar and wind energy generations being complementary to each other, 'hybridization' of two technologies would help in minimizing the variability apart from optimally utilizing available infrastructure, including land and transmission systems.

Capacity of one resource (solar or wind) in the hybrid projects shall be as per the National Wind-solar Hybrid Policy notified by MNRE vide letter no. F. No. 238/78/2017-Wind dated 14th May 2018 for Wind Solar Hybrid Projects and its amendment from time to time. For the purpose of simplicity, wind-solar hybrid power generation plants are divided into two categories:

Type-A Projects: This category includes the conversion of existing or under construction standalone wind or solar power plants into hybrid projects. Wind or solar capacity under construction shall be considered based on the registration certificate issued by GEDA or evacuation permission granted by GETCO / STU to the solar or wind RE developers as the case may be, before the issuance of this policy. The installed wind or solar capacity shall be considered based capacity of power purchase agreement (PPA) or wheeling agreement.

Type-B Projects: This includes new wind-solar hybrid power generation Gujarat Renewable Energy Policy-2023 Page 9 of 28 projects that are not registered with GEDA or for which evacuation permission has not been granted by GETCO/ STU until the date of issuance of this policy. Further, in the absence of a common RPO and tariff, only AC integration will be allowed. The integration of wind and solar components of a wind-solar hybrid project shall be allowed at the plant end or at the pooling / sending station depending upon the feasibility issued by DISCOM / GETCO in accordance with the connectivity regulations of GERC / CERC, Safety regulations issued by CEA and all other applicable regulations / standards / code.

This executive summary outlines the development of a 63.30 MW Hybrid Power Project (36 MW DC Solar + 27.30 MW Wind) at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621. The project, initiated by M/s Sai Infinium Limited, aims to harness solar & Wind energy to meet the organization's growing electricity needs sustainably and to optimize the operation cost while taking the existing Rolling mill to full capacity.

As a parent company M/s Sai Infinium Limited has been venturing into shipping and ship-breaking industry since last 15 years. The company has forayed into integration with Bandhan TMX with the production capacity of 20,000 MT per month.

The company is having a modern integrated steel manufacturing unit at Bhavnagar – western India, which has the facility of manufacturing of finished steel long product from captive steel semis with adequate refining facility through LRF (Ladle refining furnace) to ensure flawless production of refined steel.

This highly sophisticated integrated steel plant facility comprising steel melting shop (SMS) equipped with electric furnace & ladle refining furnace, Continuous Billet Casting unit, Rolling mill with Block mill and German Technology (Thermex). Brief features of integrated plant are as follows:

- 25 Ton X 2 Electric furnace.

- 30 Ton X 1 Ladle refining furnace (for liquid steel refining).

- 3 stand: 6X11 M radius CCM (with copper mould tube).

- Standalone rolling mill equipped with block mill, only it’s kind of mill in western India after TATA.

- Well-equipped in-house laboratory.

Company manufacture TMX bars and structural steel under the brand name “Bandhan TMX” through hot charging rolling mill with latest Tempcore quenching technology under licensing of CRM, Belgium’s Tempcore cooling technology. Company produces their Captive raw material (Billet) from sponge iron by using this technology for manufacturing of TMX bars. Company manufactures as well as deal in the following items on regular basis:

- Thermo Mechanical Treated (TMX) Bars: Fe 500 D, Fe 550, Fe 550 D, Fe 615 – 8mm to 32 mm

- M.s Billet.

Currently, company is having a sanction load of 33700 KW, however this integrated manufacturing plant is running for 8 hours per day and it consumes ~60 lakhs units per month to operate at this scope and scale. Historical financial position of the company is shown in the below table as on from 31st March 2022 to 31st March 2024:

| Particular | As on 31st March 2022 (Lakhs) | As on 31st March 2023 (Lakhs) | As on 31st March 2024 (Lakhs) |
| --- | --- | --- | --- |
| Total Assets | 18,746.10 | 19,595.46 | 31,469.04 |
| Long term borrowings | 2257.94 | 4741.67 | 5225.10 |
| Short term borrowings | 9061.62 | 3493.09 | 3842.75 |
| Turnover | 14,940.98 | 51,010.50 | 45,479.86 |
| PAT | 233.17 | 83.58 | 944.08 |
| Cash flow at the end | 21.52 | 28.34 | 58.53 |

As per the internal assessment shown in the below table, after 24 hours of operation of plant, it would be requiring more than 1.8 Crores units a month. As per the latest electricity bill shared by client, currently applicable tariff is INR 5.85 per unit (subsidized rate as the plant operates only from 10 pm to 6 am) and as the company plans to operate the factory for 24 hours the charges will go up to INR 8.75 per unit. And therefore, the company has planned installation the hybrid wind - solar project to offset the electricity consumption while the plant operates for 3 shifts.

| Particular | Hours | Units per month | INR/Unit | Monthly Expense | Yearly Expense INR |
| --- | --- | --- | --- | --- | --- |
| Current Running Hours | 8 | 60,00,000 | 5.85 | 3,51,00,000 | 42,12,00,000 |
| Proposed Hours | 24 | 1,80,00,000 | 8.75 | 15,75,00,000 | 1,89,00,00,000 |
| Hybrid Installation | 24 | 1,11,84,575 (Captive) | 4.87 | 5,44,27,397 | 1,36,87,48,356 |
|  |  | 67,90,537 (Industrial) | 8.75 | 5,96,34,966 |  |
| Net-off (Savings) |  |  |  |  | 52,12,51,644 |

As assessed above, the company is expected to save up to INR 52.12 Crore by installing the proposed captive hybrid power plant. The primary objectives of the hybrid power plant is to reduce annual electricity cost by ~30%, decrease the carbon footprint by 30,000 tons per year, and ensure a reliable and renewable energy source for Sai Infinium Limited's operations.

This is a 63.30 MW Captive hybrid power plant (36 MW DC Solar + 27.30 MW Wind), so whatever we will generate here, Gujarat Energy Transmission Corporation Limited (GETCO), power transmission company in the state of Gujarat, India will provide same units credit to the company’s electricity bill unit to unit basis.

The plant will feature high-efficiency solar panels with a combined capacity of 36 MW DC Solar (~62062 nos. of Solar PV Module) 580Wp of BiN-08-580 type Solar module from Waaree Energies Limited and Suzlon S 120 – (2.1 X 13) 27.30 MW Wind turbine generator (WTG). It will utilize advanced photovoltaic (PV) technology and include a state-of-the-art monitoring system to optimize performance and maintenance.

Proposed Power plant will be implemented through appointment of EPC, for which company has signed an agreement with Gujrat based renewable solution provider “Opera Energy Private Limited” dated 7th January 2025 for design, develop, transfer and maintain the Wind-Solar hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer. According to which, minimum guarantee of estimated generated unit from the hybrid project would be 1469 lakhs (KWh/annum).

The plant is expected to reduce CO2 emissions by ~30,000 tons annually, contributing significantly to Sai Infinium Limited's sustainability goals. Additionally, the project will create ~100 local jobs during the construction phase and ~25 permanent positions for ongoing operations & maintenance. Thus, the proposed hybrid power plant represents a strategic investment in renewable energy, offering significant cost savings, environmental benefits, and alignment with Sai Infinium Limited's sustainability objectives.

As per the agreement, the M/s Opera Energy Private Limited (EPC) will operate the plant on behalf of the company. As per the lease agreement shared by client, EPC has also acquired ~126.45 Acre leasehold land at Village: Sardharka Taluka: Wankaner Morbi District, Gujrat 363621 for proposed 63.30 MW Hybrid power project and will be sub-lease to Sai Infinium Limited post financial closure. Grid Connectivity approval from Gujarat Energy Transmission Corporation Limited for 30 MW Wind Solar hybrid power plant at 66KV Gangiyavadar substation of GETCO has been taken by EPC dated 31st January 2024. As per data/information provided by the client, sub-lease agreement will signed between the parties according to the financial and payment related milestone decided mutually.

Schematic layout plan has been prepared and shared by the client, which can be change during implementation period as informed by the management. As per data/information provided to us, the EPC has obtained some Statutory Approvals/NOC’s such as Grid Connectivity Approval has been taken by EPC from GETCO. Ref: GETCO/R&C/STAGE2000127 Dated: 31/01/2024. EPC has applied for Provisional Registration of Renewable Energy Project under Gujarat Renewable Energy Policy- 2023 from Gujarat Energy Development Agency (GEDA) Ref: PR No.: GEDA/PR/WSH/23-24/02/824/13 Dated 3rd Feb 2024. (Refer the section Statutory Approval in the later part of the report).

During the site visit, we found that the proposed land is a vacant agricultural land which is not demarcated and work on the Project has not been started yet. As per informed by client, land development work will start post financial closure in March 2025. (Kindly refer the site pictures captured during the survey attached in the later section of the report).

As per the EPC agreement, the proposed captive hybrid power plant will be setting up with an initial investment of INR 467.91 Crore including EPC, IDC, Contingencies & Preliminary & Pre-operative expenses, which is proposed to be funded through a term loan of INR 350.93 Crore and promoter’s equity of INR 116.98 Crore. Plant is expected to be operational from 1st April, 2026 after having a 12 months implementation period from 1st March 2025 to 31st March 2026.

At present, the company is in discussion with Financial Institutions to fund the project through a term loan of INR 350.93 Crore. In this regard M/s Sai Infinium Limited has appointed R.K. associates to assess the Techno-Economic Viability of the proposed hybrid power plant. The company plans to achieve the financial closure by March, 2025 (expected).

- PURPOSE OF THE REPORT: To assess Project’s Technical and Financial Feasibility for Client’s requirement.

- SCOPE OF THE REPORT: To only assess, evaluate & comment on Technical & Financial Feasibility of the proposed Wind Solar Hybrid power plant being set up by M/s Sai Infinium Limited as per the data/information provided by the company.

NOTES:

- Project status is taken as per the Site inspection carried out by our survey team dated 15th Jan 2025.

- Scrutiny about the company, background check, and credibility, credit worthiness of the company or its promoters is out-of-scope of this report.

- Any verification of the documents/ information from originals/ source is out-of-scope of this report.

- This report is only an opinion in respect to Technical and Financial Feasibility of the project as per the future Projections provided by the firm and independent analysis done by us and doesn’t contains any recommendations including taking decision on the loan or any other financial exposure.

- This is not an audit activity of any kind. We have relied upon the data/ information shared by the company in good faith.

- Any review of the existing business of the promoters is out of scope of this report.

- Detailed cost estimation or detailed cost vetting is out of scope of the project.

- This is not a Detailed Project Report or a detailed design or architecture document. Land and property details mentioned in the report is only for illustration purpose as per the information provided to us by the client. The same doesn’t tantamount for taking any responsibility regarding its legality, ownership and conforming to statutory norms.

- METHODOLOGY/ MODEL ADOPTED:

- Data/ Information collection.

- Review of Data/ Information collected related to TEV study.

- Independent review & assessment of technology used and financial projections provided by the company.

- Projections of Revenue, P&L, Balance Sheet, Working Capital Schedule, Depreciation Schedule, Loan Schedule as per the inputs given by the company and assessed by us

- Calculation of key financial indicators and ratio analysis including DSCR, NPV & IRR and payback period of the project.

- Report compilation and Final conclusion.

- DATA/ INFORMATION RECEIVED FROM:

All the data/Information has been received from M/s Sai Infinium Limited and M/s Impetus Finsol LLP and the required details about them shown in the below table:

| Particulars | Details |
| --- | --- |
| Company | M/s Sai Infinium & M/s Impetus Finsol LLP |
| Contact Person | Mr. Nikhil Gupta |
| Email Address | impetus.finsol@gmail.com, bandhan@infiniumgroup.in |
| Contact No. | +91-9099050621 |

- DOCUMENTS / DATA REFFERED:

- Detailed Project Report and Promoters Profile

- Financial Projections of the proposed 63.30 MW Wind-Solar Hybrid Power Plant Project.

- EPC Agreement with Opera Energy Private Limited along with EPC profile.

- Technical Specification of WTG and Solar PV Modules

- PV Syst and WRA reports.

- Sardharka Key plan and Schematic Layout Plant

- Grid Connectivity approval from GETCO

- Certificates of Statutory approvals/NOC’s.

- Survey Report.

| PART C | COMPANY PROFILE |
| --- | --- |

- COMPANY OVERVIEW:

As per certificate of incorporation shared by the client, Company was originally incorporated with the name “Sai Inductomelt Pvt. Ltd” on 16th day of August 2004 under the Company’s Act 1956. According to the Certificate of Incorporation pursuant to change of name, the name of the company has been changed from Sai Inductomelt Private Limited to M/s Sai Bandhan Infinium Private Limited with effect from 23 May 2019 Pursuant to rule 29 of the Companies (Incorporation) Rules, 2014.

Further, as per the Certificate of Incorporation Consequent upon conversion to public company, the constitution of the company has changed from Private limited to Public Limited with effect from 15th October, 2024 and name of the company became M/s Sai Bandhan Infinium Limited”.

Furthermore, as per the certificate of Incorporation pursuant to change of name, the name of the company has been changed from Sai Bandhan Infinium Limited to Sai Infinium Limited with effect from the date of 22nd November 2024. Below table shows the incorporation details of the company:

| Incorporation Details of the Company |  |
| --- | --- |
| Particular | Description |
| Company Name | M/s Sai Infinium Limited |
| CIN | U35105GJ2004PLC044607 |
| Date of Incorporation | 16th August 2004 |
| Registration Number | 044607 |
| ROC Name | ROC Ahmedabad |
| Company Category | Company limited by shares |
| Company Subcategory | Non-government company |
| Class of Company | Public |
| Registered Address | 3rd Floor, 2137, Bansal House, NR. Golden Arc, Atabhai Chowk, Bhavnagar, Gujarat, India, 364002 |
| Authorized Capital | INR 61,01,00,000 |
| Paid up Capital | INR 58,53,40,000 |
| Date of last AGM | 30/09/2024 |
| Date of Balance Sheet | 31/03/2024 |
| Company Status | Active |

Source: Information extracted from MCA website & public domain

As per the amended Memorandum of Association (MoA) shared by the client, the company was incorporated to undertake and carry on the trader and business of shippers, breakers, ship repairers, shipping agents, broker, ship managers, tug owners, roading brokers, freight contractors, barge owners, lighter men, dredgers and forwarding agents, ship store merchants, ship husbands, stevedores, salvors, ship builders and ship repairers and to carry on business of breaking, cutting, dismantling of ship, steamers, trailers, steam launches, ocean going vessels, playing on water either by Company itself or through other arrangements whether on contract or job work basis.

To carry on the business of manufacturing of and dealing in larc slabs, billets, ingots, squares, sheets by electro metallurgical process by operating induction are furnace of any other process and to manufacture, buy sell, import, export and dear in bars, sections, foils frats, rods, pipes, tubes, angles, channels, strips, plates, sheets, rails, nails, pins, coils, circles, nuts bolts, fasteners wire ropes, ferrous and nonferrous metal of all kinds and to conduct and carry on business of roiling, re-roiling, casting, welding, extruding, stretching, reducing forging, pressing, drawing, machining, grinding, processing working or finishing in any manner of all kinds of metals and alloys.

The company is categorised as medium enterprise with Udyam Registration Number UDYAM-GJ-05-0004339 dated 8th Feb 2021. In this company, the promoters have proposed to set up the proposed captive 63.30 MW Wind-Solar Hybrid power project at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621.

- PROPOSED SHAREHOLDING PATTERN:

As per the data/information provided by the client, Shareholding of promoters dated 20th January 2025 is as follows:

| Name of the Shareholder | Amount (In Rs.) | % age of total equity | No. of Equity Shares @ Rs. 10 each |
| --- | --- | --- | --- |
| Nikhil Gupta | 55,600 | 0.01% | 5,560 |
| Ishu Shivnarayan Bansal | 43,17,89,600 | 73.77% | 4,31,78,960 |
| Devansh Infinium Pvt Ltd | 6,82,60,000 | 11.66% | 68,26,000 |
| Sandeep Kothari | 2,78,00,000 | 4.75% | 27,80,000 |
| Dimple Kothari | 1,11,20,000 | 1.90% | 11,12,000 |
| Urja Ships Private Limited | 1,11,20,000 | 1.90% | 11,12,000 |
| Breamer Subsea Pvt Ltd | 55,60,000 | 0.95% | 5,56,000 |
| Kapoorchand Bansal | 73,94,800 | 1.26% | 7,39,480 |
| Devang Ashokbhai Deliwala | 13,34,400 | 0.23% | 1,33,440 |
| Negadia Mehul Pravinbhai | 13,34,400 | 0.23% | 1,33,440 |
| Pravinkumar Patel | 20,01,600 | 0.34% | 2,00,160 |
| Radha Vipul Shah | 33,91,600 | 0.58% | 3,39,160 |
| Bharat Vadilal Mehta | 97,85,600 | 1.67% | 9,78,560 |
| Shah Rekha Haresh | 33,91,600 | 0.58% | 3,39,160 |
| Yogesh Pradyumanbhai Sarvaiya | 6,67,200 | 0.11% | 66,720 |
| Pitroda Hemangini Ramkrishna | 3,33,600 | 0.06% | 33,360 |
| Grand Total | 58,53,40,000 | 100% | 5,85,34,000 |

Source: Data/Information provided by the client.

- KEY PROMOTER’S/DIRECTORS PROFILE:

As per data/information provided by the client about the promoters & directors, below table illustrate the educational & professional experience of the promoters along with the Address, DIN and contact details for FY 2024-25 as on 20th Jan 2025:

| Name/ D.O.B | Designation/DIN | Address & Contact Details | Appointment Date | Qualifications/Experience |
| --- | --- | --- | --- | --- |
| Mr. Nikhil Gupta (25th March 1989) | Director DIN: 07981873 | 203, Shanti Jyot, Near Rupani Circle, Bhavnagar, Gujarat 364002 +91-9099050621 | 20/12/2018 | Mr. Nikhil Gupta, aged 35 years, is the joint Managing Director of the Company. He is the Head of Marketing & Administration in the business and holding an experience of over 10 years and has worked alongside leading entrepreneurs. |
| Mrs. Avani Ranka (Age: 21) | Director DIN: 10809483 | Add: Ward 17 62 Lohiya Marg, Shujalpur, Shujalpur Mandi shujalpur, Madhya Pradesh- 465333 +91-9479512003 (avanirankaa@gmail.com) | 16/10/2024 | B. Tech. Engineering, Part time job |
| Mrs. Astha Digant Mehta (Age: 34) | Director DIN: 10810751 | Add: Plot No. 8/B Takhteswat Plot Bhavnagar -364002 +91-9998068010 (astha.mehta29@gmail.com) | 16/10/2024 | Educational Background: Bachelor’s Degree in Commerce from the Bhavnagar University and a Master of Business Administration in Finance from Gujarat technological university at Ahmedabad Professional Experience: She has 8 years of experience in the Finance sector |
| Mr. Mehul Shashikant Vadodaria (Age: 63) | Director DIN: 10768714 | Add: Plot No. 2188/89/Bhakti Baug, Hill drive, Vadodaria Park, Bhavnagar, 364002, Gujarat ,India +91-9825205639 (chimanlalsmehta@yahoo.com) | 15/10/2024 | Educational Background: He has passed out Gujarat secondary education board Gandhinagar Professional Experience: He has 40 years of experience in the social and political and industrial sector. Previously, He was Ex- Mayar in Bhavnagar from Dec 2005 to June 2008 |
| Mr. Dineshkumar Ravishankar Dave (Age: 69) | Director DIN: 10776918 | Add: 401 Abhijyot Flat, Nr Bileshwar Mahadev, Sattelite, Jodhpur Char Rasta, Ahmedabad- 380015, Gujarat +91- 7600035067 (efilling4incometax6@gmail.com) | 15/10/2024 | Educational Background: He Hold a Bachelor Degree of Science from the Saurathtra University , P.P. Institute of Science, Bhavnagar Professional Experience: He has 40 years of experience in the banking sector. Previously, He was Associates With State Bank of India |
| Mr. Shivnarayan Vijaykumar Bansal 28th December, 1989 | Managing Director DIN: 02247531 | Plot No. 2137/A, “SHIVA”, Beside Golden Arc Complex, Atabhai Chowk, Bhavnagar, Gujarat – 364002 | 29/08/2024 | Mr. ShivNarayan Bansal, aged 35 years, is the appointed director from 29/08/2024. Educational Background: Mr. Shivnarayan Bansal has completed his graduation in Bachelor of Business from Latrobe University, Australia. Professional Experience: He is having over 10 years of experience in various fields such as finance and ship recycling and off shore Industrial and other business activities. He is examining and advising on Purchase of Old ships and finalizes the deals with the suppliers. He is also guiding on off shore activities and is arranging finance for the business of the company. He plays a major role in providing strategic guidance in the Company. He will be supervising the functional heads and responsible for the overall operation and growth of the Company. |
| Mr. Sandeep Kothari (November, 4 1979) | Director DIN: 08574383 | Wing B 603, Leela Shanti Height, Iscon Mega City, Water Tank Road, Sterling Hospital, Bhavnagar, Gujarat – 364002 | 08/08/2024 | Mr. Sandeep Kothari, aged 45 years, was Non-Executive Director of the Company. He holds the directorship in the Company since August 08, 2024. Educational Background: He holds a degree in Bachelor of Commerce from Barkatullah University Bhopal. He is also a fellow member of ICAI. Professional Experience: He has 8 years of experience in steel industry with overall experience of over 20 years. Presently, he is also a Director in Urja Ships Private Limited, Breamer Subsea Pvt Ltd, Tangible Recycling Pvt Ltd and is also a designated partner in Bansal Endeavours LLP and karta of Sandeep Kothari HUF |
| Mr. Munishkumar Amritlal Bansal D.O.B: 25th November, 1982 | Director DIN: 06364716 | Plot No. 313 to 319, Near Water Tank, Opp. Victoria Park, Iscon Megacity, Bhavnagar, Gujarat – 364002 | 29/08/2024 | Mr. MunishKumar Bansal, aged 42 years, bearing PAN no. AUSPB3624P has been appointed as Director of the Company. Professional Experience: He has working industrial experience of over 15 years and has worked alongside leading entrepreneurs. Mr. Munishkumar Bansal is the joint Managing Director of the Company and is taking care of Business development and plays an active role while taking strategic decisions of the business. |

Source: Data/Information provided by the client and data extracted from MCA

Below tables shows the information of the companies/LLPs with which each Director is associated with to give a basic background detail of the promoters as found on public domain in general/ tertiary category research.

(MR. NIKHIL GUPTA DIN: 07981873)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Fidelis International Private Limited (U36100GJ2015PTC084732) | Director | 01/11/2018 | 01/11/2018 |
| 2 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 20/12/2018 | 20/12/2018 |
| 3 | Sai Infinium Private Limited (U27320GJ2019PTC110732) | Director | - | 08/11/2019 |
| 4 | Oro International Private Limited (U74999GJ2015PTC083987) | Director | - | 29/04/2019 |

Source: Information extracted from MCA website & public domain

(MRS. AVANI RANKA DIN: 10809483)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 16/10/2024 | 24/10/2024 |
| 2 | Sai Infinium Limited (U35105GJ2004PLC044607) | Additional Director | - | 16/10/2024 |

Source: Information extracted from MCA website & public domain

(MRS. ASTHA DIGANT MEHTA DIN: 10810751)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 16/10/2024 | 24/10/2024 |
| 2 | Sai Infinium Limited (U35105GJ2004PLC044607) | Additional Director | - | 16/10/2024 |

Source: Information extracted from MCA website & public domain

(MR. MEHUL SHASHIKANT VADODARIA DIN: 10768714)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 15/10/2024 | 24/10/2024 |
| 2 | Sai Infinium Limited (U35105GJ2004PLC044607) | Additional Director | - | 15/10/2024 |

Source: Information extracted from MCA website & public domain

(MR. DINESHKUMAR RAVISHANKAR DAVE DIN: 10776918)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 15/10/2024 | 24/10/2024 |
| 2 | Sai Infinium Limited (U35105GJ2004PLC044607) | Additional Director | - | 15/10/2024 |

Source: Information extracted from MCA website & public domain

(MR. SHIVNARAYAN VIJAYKUMAR BANSAL DIN: 02247531)

| S. No | Company Name (CIN/FCRN/LLPIN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| List of Associated Companies |  |  |  |  |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Managing Director | 29/08/2024 | 24/10/2024 |
| 2 | Devansh Infinium Private Limited (U24109GJ2023PTC141598) | Director | 15/03/2024 | 15/03/2024 |
| 3 | Bansal Fintrade Private Limited (U65999GJ2009PTC107234) | Director | 03/12/2013 | 09/10/2019 |
| 4 | Devansh Multimetals Private Limited (U27100GJ2014PTC078735) | Director | 14/02/2014 | 14/02/2014 |
| 5 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | - | 29/08/2024 |
| 6 | Sai Infinium Private Limited (U27320GJ2019PTC110732) | Director | - | 07/08/2024 |
| 7 | Orbis Infinium Private Limited (U92190GJ2014PTC078907) | Director | - | 25/02/2014 |
| 8 | Bansal International Private Limited (U35110GJ2004PTC107230) | Director | - | 10/07/2008 |
| 9 | Saffron Refinery Private Limited (U36994GJ2020PTC118355) | Director | - | 21/11/2020 |
| 10 | Bansal Fintrade Private Limited (U65999GJ2009PTC107234) | Additional Director | - | 03/12/2013 |
| List of Associated LLPs |  |  |  |  |
| 1 | Leela Responsible Recycling LLP (AAO-7795) | Partner | - | 04/04/2019 |
| 2 | Saibaba Shiprecycling LLP (AAP-0879) | Partner | - | 26/04/2019 |
| 3 | Bansal Endeavours LLP (AAO-0999) | Partner | - | 22/01/2019 |
| 4 | Bansal Vesselbreakers LLP (AAO-2454) | Partner | - | 11/02/2019 |
| 5 | Bansal Vesselrecycling LLP (AAP-3707) | Partner | - | 21/05/2019 |

Source: Information extracted from MCA website & public domain

(MR. SANDEEP KOTHARI DIN: 08574383)

| S. No | Company Name (CIN/FCRN/LLPIN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| List of Associated Companies |  |  |  |  |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 08/08/2024 | 08/08/2024 |
| 2 | Tangible Recycling Private Limited (U51100GJ2015PTC082024) | Director | 08/12/2022 | 30/09/2023 |
| 3 | Urja Ships Private Limited (U35900MH2022PTC395911) | Director | 30/03/2023 | 02/09/2023 |
| 4 | Breamer Subsea Private Limited (U82990GJ2023PTC143633) | Director | 07/08/2023 | 07/08/2023 |
| 5 | Tangible Recycling Private Limited (U51100GJ2015PTC082024) | Additional Director | - | 08/12/2022 |
| 6 | Urja Ships Private Limited (U35900MH2022PTC395911) | Additional Director | - | 30/03/2023 |
| 7 | Arihant Ferroalloys Private Limited (U28999GJ2019PTC110088) | Director | - | 27/09/2019 |
| List of Associated LLPs |  |  |  |  |
| 1 | BANSAL ENDEAVOURS LLP (AAO-0999) | Designated Partner | - | 01/10/2023 |
| 2 | BANSAL ENDEAVOURS LLP (AAO-0999) | - | - | 15/10/2019 |

Source: Information extracted from MCA website & public domain

(MR. MUNISHKUMAR AMRITLAL BANSAL DIN: 06364716)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Sai Infinium Limited (U35105GJ2004PLC044607) | Director | 29/08/2024 | 29/08/2024 |
| 2 | Devansh Infinium Private Limited (U24109GJ2023PTC141598) | Director | 23/05/2024 | 23/05/2024 |
| 3 | Sai Infinium Private Limited (U27320GJ2019PTC110732) | Director | 16/06/2023 | 16/06/2023 |
| 4 | Shirdi Ship Breaking Private Limited (U37100GJ2012PTC071923) | Director | 12/09/2012 | 12/09/2012 |
| 5 | Honey Shipbreaking Private Limited (U35117GJ2003PTC041848) | Director | 01/09/2016 | 01/09/2016 |
| 6 | Pratyaksh Ship Breaking Private Limited (U74999GJ2017PTC100260) | Director | 05/04/2021 | 05/04/2021 |
| 7 | Shanti Ship Breakers Private Limited (U35117GJ2002PTC041019) | Director | - | 10/09/2018 |

Source: Information extracted from MCA website & public domain

| PART D | PROPOSED INFRASTRUCTURE DETAILS |
| --- | --- |

- PROPOSED PLANT LOCATION:

The proposed Wind Solar Hybrid Power plant will be set up by M/s Sai Infinium Limited through EPC at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621, which is spread over an area of 126.45 Acre leasehold land as per the data/information provided to us by the company.

During the site visit, we found that the proposed land is a vacant agricultural land which is not demarcated and work on the Project has not been started yet. As per informed by client, land development work will start soon. (Kindly refer the site pictures captured during the survey attached in the later section of the report).

Table: 1 is showing the details of the adjoining properties of the land for proposed hybrid power plant and Table: 2 is showing the Connectivity Details of the Proposed Location:

| Table: 1 Adjoining Property Details |  |
| --- | --- |
| Location | Details |
| East | Agricultural land |
| West | Agricultural land |
| North | Jali to Derala link road |
| South | Agricultural land |

| Table: 2 Connectivity Details of the Proposed Location |  |
| --- | --- |
| Connectivity | Details |
| Road | ~10 mt.wide Jali to Derala road |
| Rail | Wankaner, Junction - ~10 km away |
| Airport | Rajkot International Airport, - ~50 km away |

- LOCATION MAP:

- GOOGLE MAP LOCATION:

The hybrid power plant is proposed to be commissioned at  at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621 with GPS coordinates 22°38'54.9" North and 71°01'46.3" East  as per the Google map attached below:

- GOOGLE MAP LAYOUT:

Demarcation of the land with approximate measurement on the Google map is attached in the below picture:

- SCHEMATIC LAYOUT PLAN:

As per the data/information provided by the client/Company, Schematic layout plan layout plan is attached below for reference:

Note: As informed by the client, the schematic layout plan is subject to change as per the actual implementation plan.

- LAND DETAILS:

As per the EPC agreement, M/s Opera Energy Private Limited has acquired ~126.45 Acre leasehold land at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621 for 63.30 MW Hybrid power project and will be sub-lease to Sai Infinium Limited. Grid Connectivity approval from GETCO for 30 MW Wind Solar hybrid power plant at 66KV Gangiyavadar substation of GETCO has been taken by Opera dated 13th Jan 2024. According to the commercial offer given by EPC, procuring the required Private land on lease for Wind & private land for Solar on Lease basis as below:

| Procuring of Land |  |
| --- | --- |
| Type of Land | Private |
| For Wind | On lease basis (With Mortgageable lease rights). Note: Per WTG 1 acre with NA & balance 1.5 acre without NA with agreement of easmentary rights |
| For Solar | On Lease basis with NA. With considering 2.5 acre per MW DC |

In private free hold land, the registered lease deed shall be executed in favour of the customer before the commissioning of the project. Lease shall be 3.0 lacs per WTG per year with 7% escalation on every 3rd year basis start from 2nd year on wards and for solar 50k/ Acre/ Year with 7% escalation on every 3rd year basis start from 2nd year onwards. Balance all other documents like 7/12 extracts, NA Permissions, etc. shall be obtained after the commissioning of the project as per the government procedures and guidelines.

As per data/information provided by the client, sub-lease agreement will signed between the parties according to the financial and payment related milestone decided mutually. Below table shows the detail of procured leasehold land to set up the proposed Wind Solar Hybrid Power Plant:

| Village: Sardharka Taluka: Wankaner Morbi District |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S. No. | Survey No | Farmer Name | Area(Hectare) | Area(Acre) | Lease Status |
| 1 | 531 P1 | Zala Navubha Punjabhai | 1.3152 | 3.25 | Done |
| 2 | 497 | Zala Balubha Bahadursinh | 3.3488 | 8.28 | Done |
| 3 | 523 | Zala Jitubha Narubha | 2.9947 | 7.40 | Done |
| 4 | 524p1 | Zala Narubha Jashubha | 1.7099 | 4.23 | Done |
| 5 | 524p2 | Zala Digvijaysinh Dashrathsinh | 1.2947 | 3.20 | Done |
| 6 | 488p1 | Najarudin Abuji Badi | 1.0826 | 2.68 | Done |
| 8 | 489 P2 | Mahboobbhai Doshmamad Badi | 0.9713 | 2.40 | Done |
| 9 | 532 | Rukmudeen Ibrahimbhai Mamadbhai Badi | 2.1752 | 5.38 | Done |
| 10 | 489p1 | Alibhai Doshmamad Badi | 0.951 | 2.35 | Done |
| 12 | 515 | Zala Vanrajsinh Jorubha | 0.9814 | 2.43 | Done |
| 13 | 496 P1 | Mamadbhai Hasanbhai Parasara | 1.1027 | 2.72 | Done |
| 14 | 531 P2 | Zala Pravinsinh Punjaji | 1.3152 | 3.25 | Done |
| 15 | 520 P1 | Mahamadbhai Hasanbhai Parasara | 1.2647 | 3.13 | Done |
| 16 | 520 P2 | Najamudin Hasanbhai Parasara | 1.2646 | 3.12 | Done |
| 17 | 496 P2 | Najamudin Hasanbhai Parasara | 1.0927 | 2.70 | Done |
| 20 | 526 | Ravatbhai Kalabhai Makwana | 2.1549 | 5.32 | Done |
| 21 | 521 | Dhirubhai Kalabhai Makwana | 3.2375 | 8.00 | Done |
| 22 | 514 | Jyotiben Chandulal Kapasi | 0.9611 | 2.37 | Done |
| 23 | 494 | Nurmamad Valibhai Parasara | 1.7503 | 4.33 | Done |
| 24 | 492 P1 | Nisarahmad Sajibhai Parasara | 1.0319 | 2.55 | Done |
| 25 | 495 | Abdul Valibhai Parasara | 1.0725 | 2.65 | Done |
| 27 | 530p2 | Bhupatsinh Kalubhai Jadeja | 1.3051 | 3.22 | Done |
| 28 | 530p1 | Bhupatsinh Kalubhai Jadeja | 1.3051 | 3.22 | Done |
| 29 | 518 | Abbasbhai Amanjibhai Parasara | 1.6795 | 4.15 | Done |
| 30 | 519 | Abbasbhai Amanjibhai Parasara | 2.4585 | 6.08 | Done |
| 31 | 516 | Hardevsinh Udesinh Zala | 1.0117 | 2.50 | Done |
| 32 | 512 | Velubha Takhubha Zala | 2.1853 | 5.40 | Done |
| 33 | 511 | Jitendrasinh Udesinh Zala | 2.5495 | 6.30 | Done |
| 34 | 491 | Ajitsinh Khumansinh Zala | 2.6709 | 6.60 | Done |
| 35 | 498 | Husenbhai Ahmedbhai Parasara | 1.902 | 4.70 | Done |
| 36 | 492p2 | Parvejahmad Rasulbhai Parasara | 1.032 | 2.55 | Done |
|  | Total |  | 51.17 | 126.45 |  |

During the site visit dated 15th January 2025, we found that the proposed land is a vacant agricultural land which is not demarcated and work on the Project has not been started yet. As per informed by client, land development work will start soon. (Kindly refer the site pictures captured during the survey attached in the later section of the report).

EPC/Company needs to obtain Change of land use (CLU) as it seems an agricultural land. Any kind of sale/lease deed is not shared with us by the client due to confidentiality and Sub-lease is subject to payment milestones as per informed by client. We recommend the financial institution to suggest the client to submit the lease/sub-lease deed along with the current status of land use before disbursement.

- SITE PICTURES:

Site pictures were captured during the site visit on 8th May 2024, for reference few of the pictures are attached below:

- BUILDING & CIVIL WORKS:

The proposed wind solar hybrid power plant will not be having major building and civil works. Only land development and foundation work will be there as per the requirement of WTG and PV modules. Out of total EPC cost of INR 438.81 Cr., ~5% i.e. INR 21.94 Cr. will be the cost of Civil work, which seems to be reasonable after considering the infrastructure of the plant. However we are relied upon the data/information and EPC agreement of Opera Energy Private Limited shared with us by the client in this regard.

- PLANT & MACHINERY/ EQUIPMENTS DETAILS:

| Wind Power Plant |  |
| --- | --- |
| Turbine Make | Suzlon |
| Model | S120-2.1MW |
| Hub Height | 140 Mt. |
| Rotor Diameter | 120 Mt. |
| Tower Height | 138.20 Mt. |
| Tower Type | Tabular Steel Tower/Hybrid Concrete Tower |
| Foundation Level | Site Specific (0.5 mtr) |

Source: Data/information provided by the client.

| Solar Power Plant |  |
| --- | --- |
| Solar Module capacity | 580Wp |
| type | BiN-08-580 |
| Make | Waaree Energies Ltd. (ALMM Approved) |
| Panels Required | ~62062 Units (2387 Strings x 26 In series) |
| Number of Inverter | 89 Units |
| Invertor Make | Sungrow |

Source: Data/information provided by the client.

As per data/information provided by client, below are the cost bifurcation of 36 MW solar DC and 27.30 MW Wind power plant:

| Cost Bifurcation of 36 MW (DC) Solar Power Project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Particular | Cost/MW | Total MW (DC) | Total Amount | GST | Total Amount |
| Supply of Solar panel and Construction of Solar Park with supply of PV panel Tier-1 Top Con, Inverter, all required, Inverter duty transformer, Aux. transformer, LTDB, MMS, HT cable, LT cable, DC cable, Earthing cable, HDPE pipe, cable accessories, Earthing strip, Metering. Balance of Plant (Land, Permits, Approvals, Land Fencing, Approach Road, Internal Line, Commissioning) (Auto Tracker) | 32000000 | 36 | 1152000000 | 13.80% |  |
| Total Amount for 36 MW Solar (DC) | 32000000 | 36 | 1152000000 | 158976000 | 1310976000 |

Source: Data/information provided by the client.

| Cost Bifurcation of 27.3 MW Wind Power Project (2.1 MW * 13 Nos. WTGs) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Particular | Basic | GST@12% | Total |
| Supply | WOEG | 144286161 | 17314339 | 161600500 |
|  | Stub | 1697320 | 203678 | 1900998 |
|  | Stub Hardware | 101929 | 12231 | 114160 |
|  | Packaged SS | 3914590 | 469751 | 4384341 |
| Total |  | 150000000 | 18000000 | 168000000 |
| BOP (Balance of Plant) Cost |  |  |  |  |
| Description | Particular | Basic | GST@18% | Total |
| Balance of Plant (BOP) | Road Development | 5084746 | 915254 | 6000000 |
|  | Civil work for Foundation | 12711864 | 2288136 | 15000000 |
|  | USS Material | 10084746 | 1815254 | 11900000 |
|  | 33 KV Line Material | 12661017 | 2278983 | 14940000 |
|  | Erection | 8135593 | 1464407 | 9600000 |
|  | Commissioning | 4237288 | 762712 | 5000000 |
|  | Storage, Security & Insurance | 5084746 | 915254 | 6000000 |
| Total |  | 58000000 | 10440000 | 68440000 |
| Grand Total |  | 208000000 | 28704000 | 236440000 |
| Total amount for 13 WTGs Nos. 27.3 MW |  | 2704000000 | 373152000 | 3077152000 |

Source: Data/information provided by the client.

As per EPC agreement, the estimated cost the plant will be ~INR 416.87 Crore including the procurement and installation of plant & machinery. We have relied upon the data/information provided to us by the client for the estimated cost of the Plant & Machinery as per EPC agreement. It is to be noted here that the detailed cost vetting is out of scope of this TEV report.

- UTILITIES: Details of Water, Electricity and other utilities are describes as below:

- WATER:

As per the data/information provided by the client, there are two canals nearby the site and drinking water can also be arranged through local municipality supply.

- ELECTRICITY:

Not required as it is a power generating hybrid power plant itself.

| PART E | PROJECT TECHNICAL DETAILS |
| --- | --- |

- CAPACITY OF THE PROPOSED WIND SOLAR HYBRID POWER PLANT:

This is a 63.30 MW Captive hybrid power plant (36 MW DC Solar + 27.30 MW Wind), so whatever we will generate here, Gujarat Energy Transmission Corporation Limited (GETCO), power transmission company in the state of Gujarat, India will provide same units credit to the company’s electricity bill unit to unit basis as illustrated in the below table:

| Capacity of the proposed Power plant |  |
| --- | --- |
| Particular | Capacity |
| Solar Power Plant | 36 MW (~62062 nos. of Solar Panel) 580Wp of BiN-08-580 from Waaree Energies Limited |
| Wind Power Plant | 27.30 MW Suzlon S 120 – (2.1 X 13) |

Source: Data/information provided by the client.

- PROJECT IMPLEMENTATION:

M/s Sai Infinium Limited has executed an EPC/Techno-Commercial contract with Opera Energy Private Limited for Captive hybrid power plant for 27.30 MW WTG with 36,96% PLF & 36 MW DC Solar 18.55% PLF.

Opera Energy Private Limited, is a prominent Gujarat based solar and hybrid power generating company has been appointed an EPC through entering into a legal agreement dated 7th January 2025 who will be the solution provider for the proposed 63.30 MW hybrid project to implement on turnkey basis within 12 months of zero date for design, develop, transfer and maintain the solar and wind hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer.

- COMMERCIAL AGREEMENT DETAILS:

Techno-Commercial Contract is signed on 7th January 2025 by both the parties for design, develop, transfer and maintain the solar and wind hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer. As per Scope of supply, estimated generated unit from the hybrid project would be 1469 lakhs kWh per year as shown in the below table:

| Estimated Generation: |  |
| --- | --- |
| Wind: | Approx. 68 Lac/ WTG/ Year |
| Solar: | Approx. 16.25 Lac/ MW DC |
| Estimated Hybrid Generation: | Approx. 53.8 Lac KWh/ MW/ Year |
|  | Wind: 13 nos of WTG x 68 Lacs KWh = 884 Lacs KWh/Year Solar: 36 MW DC x 16.25 Lac KWh = 585 Lacs KWh/Year Total Hybrid Generation: 1469 Lacs KWh/ Year |

Source: EPC Agreement shared by client.

COMMERCIAL DETAILS OF AGREEMENT

Commercial details of EPC agreement is shown in the below table:

| Commercial Details of EPC Agreement |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Division | Particular | UOM | Amount per Unit | GST (%) | Total Amount |
| 1 | Wind | Supply of 27.3 MW (2.1 Suzlon, 140 mtr), including logistic for WTG supply from Ex works to wind farm storage yard and Supply of Package, Substation. Special lifting tools, Stub, Template and required accessories, hardware, Supervision & Service, PSS, included | WTG | 150000000 | (12%) 1,80,00,000 | 16,80,00,000 |
| 2 |  | Balance of Plant (Land, Foundation, Approach Road, Sub Station Installation, WTG Erection and Commissioning) | WTG | 58000000 | 18% 1,04,40,000 | 6,84,40,000 |
| Amount per WTG |  |  |  | 208000000 | 13.80% 28704000 | 236704000 |
| A | Total Amount for 12 WTG Nos for 25.20 MW |  |  | 2704000000 | 373152000 | 3077152000 |
| 1 | Solar | Supply of Solar Panel and construction of solar park with supply of PV panel Tier -1 Top Con, Inverter, all required, Inverter duty Transformer, Aux, transformer, LTDB, MMS, HT Cable, LT cable, DC cable, earthing cable, HDPE pipe, cable accessories, Earthing strip, Metering. Balance of Plant (Land, Permits, Approvals, Land, Fencing, Approach Road, Internal Line, Commissioning) | MW | 32000000 | (13.80%) 4416000 | 36416000 |
| B | Total amount for 36 MW Solar DC |  |  | 1152000000 | 158976000 | 1310976000 |
| C | Total Hybrid Project Amount |  |  | 3856000000 | 532128000 | 4388128000 |

Source: EPC agreement provided by the client.

OPERATION AND MAINTENANCE SERVICES

Opera Energy Private Limited (EPC) is agreed to operate and maintain the WTG/ Solar Plant for the first 2 years of operation from the date of commissioning, free of cost to the Buyer. This shall also include the provision of necessary spares and consumables.

Opera shall facilitate for necessary arrangements for a Complete Operation, Maintenance and Security Contract with the facility provider from the start of the 3rd year of operation from the date of commissioning to the end of the 25th year at the anticipated rates as mentioned. From the beginning of the 3rd year from the date of commissioning to the end of the 10th year O&M Expenses as per the below table.

| O&M Expenses |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Items | Unit | WTG/ Plant | Common Infra | Total Price Per MW | Project Size (MW) | Net Price (Lac) |  | Escalation rate per year |
| Wind | Rs/ MW/ Year | 9.52 | 1.5 | 11.02 | 27.3 | 300.8 |  | 5% |
| Solar DC | Rs/ MW/ Year | 3.5 | 0 | 3.5 | 36 | 126 |  | 5% |
| Total |  |  |  |  |  |  | 83.15 |  |

EVACUATION ARRANGEMENT AND GRID AVAILABILITY

Opera shall arrange for adequate evacuation facilities for the project. The timely completion of the permanent power evacuation arrangement depends on various permissions from Government / Nodal Agency / DISCOM and also the Right of Way (ROW) by the local villagers. Accordingly, in case of any delay in the completion of the permanent power evacuation arrangement, EPC shall arrange for a temporary power evacuation for the commissioning of the project, subject to feasibility with the relevant agency.

Any change or levy of new charges, levies, duties or access shall be borne by Buyer at actual, as levied by any Government Authority from time to time. The buyer shall also agree to enter into an agreement with the concerned service provider for such O&M as per their draft and terms & conditions therein.

STATUTORY FEES AND CHARGES

The following are some of the prevailing Open Access Charges & losses payable by the Buyer:

| S. No. | Description | Unit | Amount in Rs | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Transmission Charges | Rs. /MW/day | 4400 | Charges will vary every. year as per GERC order |
| 2 | SLDC & Operating Charges | Rs. /Day | 614 | Approx. |
| 3 | Forecasting & Scheduling | Rs./MW/month | 1,500 | Needs to be done by QCA |
| 4 | GEDA Certification | Rs. /MW/Year | 12,000 | Charges will vary every- year as per GERC order |
| 5 | GETCO Feeder Bay Maintenance Charges | Rs. /MW/Year | 60,000 | Approx. |
| 6 | Deviation penalty | Rs. /Year | 75000 | Deviation penalty 2p to 4p |
| 7 | Transmission Losses | % | 3.84% | As per the GERC order for TL losses |
| 8 | Windfarm Internal Losses | % | 2.5% |  |
| 9 | Wheeling Losses | % | 8.5 % | 8.5 % for 11kV as per the Tariff Order |
| 10 | Insurance | Rs/Year | 0.10% of WDV Net Block Y-o-Y Basis |  |

Source: EPC agreement shared by the client.

The following are some of the indicatory Statutory Fee’s payable by the Buyer:

| One-Time Charges / Registration Fees / Transfer Fees |  |  |  |  |
| --- | --- | --- | --- | --- |
| S. No | Description | Unit | Amount in Rs. | Remarks |
| 1 | GEDA application Form & processing Fee | Rs. | 4,00,000 |  |
| 2 | Transfer Permission Fees | Rs. | 75,000 | For Transfer Permit |
| 3 | Getco Registration Fess | Rs. | 1,00,000 | For BPTA agreement |
| 4 | Other statutory fees | Rs. | 4,00,000 |  |

Source: As per the EPC agreement shared  by the client.

- EPC DETAILS:

As per data/information shared by client and information available in public domain, appointed EPC “M/s Opera Energy Pvt Ltd” is a Gujrat based OHSAS 18001 and ISO 9001:2015 certified end-to-end solution provider in conventional wind and Large-scale PV Solar projects.

Opera Energy was incorporated in the year 2012, having its corporate office at A-603 & 604, World Trade Tower, SG Highway, Makarba, Ahmedabad, Gujarat – 380051 and as per MCA registered office is at 207 - Kuber Avanue, Panch Bunglow Raod, Near Gurudwara Cross Road, Jamnagar, Jamnagar, Gujarat, India, 361001 at present. As per data/information available on MCA, incorporation details of EPC are shown in the below table:

| Particular | Description |
| --- | --- |
| Name | M/s Opera Energy Private Limited |
| CIN | U40109GJ2012PTC071508 |
| Reg. Address | 207 - Kuber Avanue, Panch Bunglow Raod, Near Gurudwara Cross Road, Jamnagar, Jamnagar, Gujarat, India, 361001 |
| Website | https://operaenergy.in/ |
| ROC | ROC Ahmedabad |
| Date of Incorporation | 13/08/2012 |
| Company Category | Company limited by shares |
| Company Sub Category | Non-government company |
| Class of Company | Private |
| Authorised Share Capital | INR 1,00,00,000 |
| Paid-up Share Capital | INR 1,00,000 |
| Date of Balance Sheet | 31/03/2024 |
| Date of last AGM | 30/09/2024 |

Source: Ministry of Corporate Affair

Opera has end-to-end solution provider in conventional wind and Large-scale PV Solar projects.  Evolved to become a leading Dynamic growth across verticals has also led Opera to have a strong footprint in the renewable energy sector. Having grown exponentially over the years in this sector, Opera has emerged as a top Developer in RE sector.

Opera is expanding its scope of activities and identifying the renewable energy sector as a growing and sustain-able industry to pursue. According to the customer’s energy requirements Opera offer solutions that are better for the clients to reduce their energy costs, become power independent and cut down their carbon emissions.

Their customized RE solutions to help businesses lower their carbon footprint and meet sustainability targets. Businesses can choose solar / wind to meet their sustainability goals. They also offer Operation and Maintenance Services (O&M) through a separate O&M agreement to the customers. This provides them with a long-term annuity stream of revenue.

SERVICES OF OPERA UNDER WIND AND SOLAR:

| Name | Designation/Description |
| --- | --- |
| Stage-1 Site Development | - Site Identification, Supply of Wind Masts, Wind Resource Study, SRA (Solar Resource Study), Energy Yield Prediction, Govt. Orders, Load Flow Study, Micro Sitting, Evacuation Permits, Land, Soil & Logistic Survey, Project Financials, Acquisition of Site Specific NOCs VIZ. Govt. Mining, Forestry, CRZ, MOD, etc. |
| Stage-2 Land & ROW | - Acquisition of Land for WTG and Sub station - Acquisition of ROW for WTG Locations - Execution of PPA - Acquisition of site-specific NOCs. |
| Stage-3 Infrastructures | - Soil Testing - Plant design - Road Construction - Infra clearance - Infra Development - Plot Development - Crane pad, hardstand - Foundations - Road |
| Stage-4 WTG & PV Module E&C | - Supply of Heavy Vehicles - Supply of WTG Components to WTG Locations - Erection of WTG - PV Module supply & Erection - Supply of other PV components to Site - Supply & Erection of Inverters and other Electrical Equipment's - Commissioning of Solar Plant. |
| Stage-5 Poer & Grid | - Supply & Erection of Electrical Equipment's - Construction of substation - External Lines & Distribution Network - Unit switch yards - Transmission Lines - SCADA |
| Stage-6 O&M | - O&M WTG and Wind farm - O&M of BoP Components - Scheduled Maintenance - Unscheduled Maintenance - O&M of Substation |

Sources: As per data/information available in public domain.

KEY TEAM OF EPC:

| Name | Designation/Description |
| --- | --- |
| Amit Kambariya Managing Director & CEO | - The founder of Opera Energy, has a decade-plus of entre- epineuria experience in the renewable energy sector. Holds Bachelor's in Computer Application and PGDCA from Saurashtra University. |
| Manimaran Krishnan Director: BD & Operations | - Has 16+ years of experience in the field of Business Development, Strategic Business Planning and Asset Management in the renewable energy sector. Had previously worked for Vestas India, Mytrah Energy and Sembcorp Energy. Holds MBA in Project Management from Alagappa University. |
| Vipul Jambucha Director: Projects & Cranes | - Has 26+ Years’ Experience in Mechanical Engineering and Project Management field. Had previously worked at Agrocel, Suzlon, Vestas, and EDF Renewables. Worked at India and Overseas. Holds Project Management Professional (PMP), MBA Project and Mechanical Engineering Degree |
| Jayesh Sanjava Associate Director | - Has 10+ years of experience in the field of operations & projects in the renewable energy sector. Had previously worked for Enercon India, Mytrah Energy, GE Renewable Energy Holds a Master degree in Master of Law from Saurashtra University. |
| Dilip Vasra Head Corporate Finance | - Has extensive experience in the field of risk management, setting up financial systems and controls, Merger & Acquisition, EPC contracting and raising Public/Private equity and large project funding Holds a bachelor’s degree in commerce from Saurashtra University. |
| Raja Rajeswari Legal Advisor | - Has over 25 years of legal expertise and has been an attorney since 1997. She advises businesses on legal risk minimization, regulatory framework, and statutory compliance. She has extensive experience in litigation across India, including in the Supreme Court, the APTEL, the Electricity Regulatory Commission, and other high courts and power regulatory forums. |

Source: Data/Information provided by the client.

KEY PROJECT DETAILS OF OPERA:

| Sr. No. | Year | Project Location | Type | Capacity (MW) |
| --- | --- | --- | --- | --- |
| 1 | 2014 - 2018 | GJ - Dwarka | Wind | 300 |
| 2 | 2015 - 2016 | GJ - Bhatel | Wind | 78.6 |
| 3 | 2018 - 2020 | GJ - Jodiya | Wind | 100 |
| 4 | 2018 - 2019 | GJ - Amreli | Wind | 35.7 |
| 5 | 2018 - 2020 | GJ - Jamjodhpur | Wind | 197.5 |
| 6 | 2019 - 2020 | GJ - Mandavi | Wind | 17.6 |
| 7 | 2019 - 2022 | GJ - Lakhpat | Wind | 300 |
| 8 | 2020 - 2021 | GJ - Khambhaliya | Sub station |  |
| 9 | 2021 - 2022 | GJ - Gondal | Wind | 48.6 |
| 10 | 2021 - 2022 | GJ - Rajkot | Solar | 100 |
| 11 | 2021 - 2022 | GJ - Khambhaliya | Wind | 115 |
| 12 | 2021 - 2022 | GJ - Jamnagar | Hybrid | 60 |
| 13 | 2021 - 2022 | GJ - Mahuva | hybrid | 151.2 |
| 14 | 2021 - 2022 | MH - Kallam | Solar | 300 |
| 15 | 2022 - 2023 | GJ - Jamnagar | hybrid | 520 |
| 16 | 2022 - 2023 | GJ - Jamnagar | Wind | 37.8 |
| 17 | 2022 – 2023 | GJ - Jamnagar | Wind | 24.3 |
| 18 | 2022 – 2023 | GJ - Amreli | Wind | 140 |

Source: Data/Information provided by the client.

| Asset Under Management (Operation & Maintenance) |  |  |  |  |
| --- | --- | --- | --- | --- |
| S. No | Financial Year | Customer Name | Solar / Wind | Capacity In Mw |
| 1 | 2020-21 | Envision Wind Power Service India Pvt Ltd (Owner Sprng Energy) | Wind | 197.5 |
| 2 | 2021-22 | Cleanmax Max Vent Power Pvt Ltd | Wind | 35.1 |
| 3 | 2021-22 | Tata Power Renewable Energy Ltd | Solar | 154 |
| Total |  |  |  | 386.6 |

Source: Data/Information provided by the client.

| EPC PROJECT ON GOING |  |  |  |
| --- | --- | --- | --- |
| S. No | Financial Year | Solar / Wind | Capacity in MW |
| 1 | 2024-25 | Solar + Wind | 250 |
| 2 | 2021-22 | Solar + Wind | 140 |
| 3 | 2022-23 | Wind | 25 |
| 4 | 2022-23 | Wind | 25 |
| 5 | 2022-23 | Solar + Wind | 70 |
| 6 | 2024-25 | Solar + Wind | 36 |
| Total |  |  | 546 |

Source: Data/Information provided by the client

As per the audited annual reports provided by the client, below table shows the profitability and financial health of EPC:

| Financial Position of EPC (INR Thousand) |  |  |  |
| --- | --- | --- | --- |
| S. No | Particular | FY 2022-23 | FY 2023-24 |
| 1 | Turnover | 1628308.979 | 3275989.250 |
| 2 | PAT | 47708.530 | 105568.64 |
| 3 | Cash | 6680.17 | 22028.37 |
| 4 | Total Non-Current Asset | 101391.255 | 180194.306 |
| 5 | Current Assets | 479302.53 | 1037916.002 |
| 6 | Long Term Borrowing | 3370.54 | 443042.52 |

Source: Data/Information provided by the client

- PROPOSED PLANT & MACHINERY/EQUIPMENT DETAILS:

| Wind Power Plant |  |
| --- | --- |
| Basic date |  |
| Turbine Make | Suzlon |
| Model | S120-2.1MW |
| Hub Heigh | 140 Mt. |
| Rotor Diameter | 120 mtr |
| Tower Height | 138.20 mtr |
| Tower Type | Tabular Steel Tower/Hybrid Concrete Tower |
| Foundation Level | Site Specific (0.5 mtr) |
| Operating Data |  |
| Rotor Speed Range | 8.1 to 13.11 rpm |
| Rate Wind Speed | 9.5 m/s (without turbulence intensity according to IEC 61400) |
| Cut in wind Speed | 3.0 m/s |
| Cut out wind Speed | 18.0 m/s |
| Tower Data |  |
| Hub Height | 90/105 mtr |
| Material | Welded steel plate according to EN10025/Concrete |
| Internals | Ladder-guided climber, cabling lights |
| Generator |  |
| Type | Slip ring asynchronous generator |
| Rated frequency | 50 Hz |
| Power factor with consumption | 0.94 cap. To 0.94 ind. |
| Rotor data |  |
| Rotor cone angle | 3.5 degree |
| Rotor speed at rated power | 10.7 rpm |
| Main shaft tilt angle | 5 degree |
| Blades |  |
| Quantity | 3 |
| length | 59.0 m |
| material | Glass fibre-reinforced epoxy |
| Type of aerodynamic | Pitch/full blade |
| Transformers |  |
| Type | Oil filled transformer |
| Winding connection | Delta/star |
| Vector group | Dyn5/Dyn11 (grid-dependent) |
| Rated apparent power | 2500 kVA |

Source: Data/information provided by the client.

| Solar Power Plant |  |
| --- | --- |
| Produced Energy | 59496 MWh/year |
| Specific production | 1653 kWh/kWp/year |
| Performance Ratio (PR) | 82.78% |
| Solar Module capacity | 580Wp |
| type | BiN-08-580 |
| Make | Waaree Energies Ltd. |
| Panels Required | ~62062 Units (2387 Strings x 26 In series) |
| Number of Inverter | 89 Units |
| Invertor Make | Sungrow |
| Max. PV input voltage | 1500 V |
| Total Power | 26700 kWAc |
| Max. efficiency | >30 Degree Celsius |

Source: Data/information provided by the client.

- TECHNICAL SPECIFICATIONS OF THE PROPOSED POWER PLANT:

As per the data/information provided by the client, below table shows the technical specification of the proposed Power plant:

WTG ((13 x 2.1) 27.30 MW):

BASIC DATA:

OPERATING DATA:

TOWER DATA: (TABULAR STEEL TOWER AND HYBRID CONCRETE TOWER):

NACELLE DATA:

ROTOR DATA:

TRANSFORMER DATA:

SITE CONDITIONS AS PER WRA SUMMARYREPORT OF EPC FOR WIND:

| Site Description |  |
| --- | --- |
| Project Location | Wankaner, Gujarat |
| Land Type | Private Land |
| No. of Available Locations | 13 |
| Terrain Type | Plain Terrain |
| Soil Type | Murrum & Hard Rock |
| Elevation Range (m) | 85 to 125 m AMSL |

| Wind Climatic Parameters |  |
| --- | --- |
| Particulars | Details |
| No Of WMS | 1 |
| Wind Mast | Chitrakhada |
| Wind Mast Height | 100 M |
| Measurement Period | Nov 2020 – Oct 2021 |
| Elevation | 119 M |
| Project Average WS At 140 M | 6.60 M/S |
| WPD At 140 M | 266 W/M2 |
| Temperature At 10 M | 27.1 Degree Celsius |
| Pressure At 10 M | 977 Mbar |
| Air Density | 1.15 Kg/M3 |
| Wind Shear | 0.329 |
| Turbulence Intensity At 15 M/S | 0.08 |

LONG TERM WIND AT SITE @ 140 METRE:

PROJECT: 36 MWP DC SOLAR

PVSYST V7.2.8 VC0, SIMULATION DATE: 10/01/25

- TECHNOLOGICAL ASSESSMENT:

Thus as per the above technical assessment, it seems to be reasonable to comment that the proposed wind solar hybrid power plant is technically viable as the company is implementing the plant through EPC and both Tiear-1 solar PV modules & WTG are standard make of Waree Energies Limited and Suzlon S 120 (2.1 X 13) MW respectively.

The plant will feature high-efficiency solar panels with a combined capacity of 36 MW DC Solar (~62062 nos. of Solar Panel) 580Wp of BiN-08-580 type Solar module from ALLLM approved Waaree Energies Limited, Suzlon S 120 – (2.1 X 13) 27.30 MW Wind turbine generator (WTG) and 89 Nos. Sungrow make SG320HX-20 300 kWAC 1500 Vdc Inverter System, which is a high yield, Grid-Friendly and Safety proven system. It will utilize advanced photovoltaic (PV) technology and include a state-of-the-art monitoring system to optimize performance and maintenance.

Further, EPC has guaranteed for generation of 1469 lakhs kWh yearly bases on the WRA and PVSyst reports. Thus, It seems reasonable to comment that the plant will be running smoothly. Technology & specification of the plant are matching with the need to run the power plant to achieve the economies of scale.

- MANPOWER:

As per the EPC agreement, Opera will be responsible to operate the plant on behalf of Sai Infinium Limited and there would be no additional manpower required to operate since the cost of manpower is already adjusted in O & M expenses.

| PART F | INDUSTRY OVERVIEW |
| --- | --- |

- INTRODUCTION:

India's energy demand is expected to increase more than that of any other country in the coming decades due to its sheer size and enormous potential for growth and development. Therefore, most of this new energy demand must be met by low-carbon, renewable sources. India's announcement India that it intends to achieve net zero carbon emissions by 2070 and to meet 50% of its electricity needs from renewable sources by 2030 marks a historic point in the global effort to combat climate change.

India was ranked fourth in wind power capacity and solar power capacity, and fourth in renewable energy installed capacity, as of 2023. Installed renewable power generation capacity has increased at a fast pace over the past few years, posting a CAGR of 15.4% between FY16 and FY23. India has 125.15 GW of renewable energy capacity in FY23. India is the market with the fastest growth in renewable electricity, and by 2026, new capacity additions are expected to double.

With the increased support of the Government and improved economics, the sector has become attractive from an investor’s perspective. As India looks to meet its energy demand on its own, which is expected to reach 15,820 TWh by 2040, renewable energy is set to play an important role.

- MARKET SIZE:

- As of July 2024, Renewable energy sources, including biomass, waste to power and waste to energy, have a combined installed capacity of 150.27 GW.

- As of July 2024, 44% of the total power installed capacity is from non-fossil-based sources, which fulfils the target of 40% by the end of 2022.

- India's installed renewable energy capacity is expected to increase to about 170 GW by March 2025 from the level of 135 GW as of December 2023, according to research agency ICRA.

- The country is targeting about 450 Gigawatt (GW) of installed renewable energy capacity by 2030 – about 280 GW (over 60%) is expected from solar.

- The non-hydro renewable energy capacity addition stood at 4.2 GW for the first three months of FY23 against 2.6 GW for the first three months of FY22. According to research by the Council on Energy, Environment and Water's Centre for Energy Finance (CEEW-CEF), India's total installed power generation capacity reached 416 GW in FY23, of which 125 GW (30%) came from renewable energy (RE) and 47 GW (11%) comes from hydro.

- The electricity generation target (Including RE) for the year 2023-24 has been fixed as 1750 Billion Units (BU). i.e. growth of around 7.2% over the actual generation of 1624.158 BU for the previous year (2022-23). The generation during 2022-23 was 1624.158 BU as compared to 1491.859 BU generated during 2021-22, representing a growth of about 8.87%.

- The installed solar energy capacity has increased by 26 times in the last 9 years and stands at 73.32 GW as of December 2023. In 2023, India has added 7.5 GW of solar power capacity.

- During January 2024, the capacity addition from solar energy stood at 9008.47 MW.

- Solar power accounted for 16.9% of the total installed power capacity and 40.1% of the total installed renewable capacity at the end of December 2023. Solar power's share increased by 0.3% from the last quarter, when it accounted for 39.5% of the total renewable capacity.

- India has hydroelectric power projects with a total capacity of 15 GW under construction, which will increase the country's total hydro capacity from 42 GW to 67 GW by 2031-32, supported by IMD's prediction of higher rainfall and the government's proactive stance towards accelerated hydropower development.

- India has generated 75.57 BU of solar power in the first eleven months of FY24.

- Power generation from renewable energy sources (not including hydro) stood at 22.41 billion units (BU) in January 2024, down from 25.79 BU in January 2023.

- India added a record 18.48 GW of renewable energy capacity in 2023-24, a 21% increase over the previous year.

- Power generation from renewable energy sources (not including hydro) stood at 22.27 billion units (BU) in June 2024, up from 21.86 BU in June 2024.

- Power generation from renewable energy sources stood at 62.09 billion units (BU) between April-June 2024, up from 57.94 BU in the same period in the previous year.

- With a potential capacity of 363 GW and with policies focused on the renewable energy sector, Northern India is expected to become the hub for renewable energy in India.

- INVESTMENT:

According to the data released by the Department for Promotion of Industry and Internal Trade (DPIIT), the non-conventional energy space in India has become highly attractive for investors and received an FDI inflow of US$ 15.36 billion between April 2000-September 2023. More than Rs. 5.2 lakh crore (US$ 70 billion) has been invested in India’s renewable energy sector since 2014. Some major investments and developments in the Indian renewable energy sector are as follows:

- India is set to significantly boost its renewable energy investments, with a projected increase of 83% to approximately US$ 16.5 billion in 2024, as part of its strategy to transition to cleaner energy sources and reduce carbon emissions.

- India is set to invest over US$ 360 billion in renewable energy and infrastructure by 2030, with US$ 190 billion to US$ 215 billion needed to achieve 500 GW of renewable capacity. An additional US$ 150 billion to US$ 170 billion will be required for electricity transmission and storage.

- Brookfield Asset Management plans to boost its investments in India’s renewable energy sector to over US$ 10 billion in the next three to four years, also exploring electric vehicles and green hydrogen.

- India's renewable energy sector set to attract over $250 billion in investments, with solar PV projects expecting $15.5 billion and battery manufacturing $2.7 billion.

- The non-conventional energy space in India has become highly attractive for investors and received an FDI inflow of US$ 17.88 billion between April 2000-March 2024.

- According to Moody's, India will require US$ 190 billion-US$ 215 billion of investment over the next seven years to achieve the target of 500 GW of renewable energy capacity by 2030, and another US$ 150 billion-US$ 170 billion for electricity transmission, distribution, and energy storage.

- Radiance Renewables, an Indian renewable energy developer, and the UK's Private Infrastructure Development Group have formed a joint venture called Radiance InfraCo Renewables to develop greenfield solar and wind-solar hybrid projects for commercial and industrial clients in India, leveraging their expertise to support the country's transition towards its net-zero emissions target by 2070.

- Maruti Suzuki India will invest Rs. 450 crore (US$ 54 million) over the next three years in renewable energy projects, including a biogas plant at Manesar and expanding solar capacity. The pilot biogas plant aims to produce 1 lakh cubic meters of biogas in FY 2024-25, offsetting 190 tonnes of CO2 annually. Solar capacity will grow from 43.2 MWp to 78.2 MWp by FY 2025-26, supporting Suzuki's 'Environment Vision 2050.

- NTPC Green Energy Ltd. will invest Rs. 80,000 crore (US$ 9.59 billion) in Maharashtra for green hydrogen, ammonia, and methanol projects, including 2 GW pumped storage and up to 5 GW renewable energy projects, as part of a plan to build 60 GW renewable capacity by 2032.

- On December 4, 2023, Andhra Pradesh announced Rs 6600 crore (US$ 794 million) clean energy and infrastructure expansion plans, including a 750 MW solar project, 100 MW solar plant, substation enhancements, collaborations with HPCL, Avera AI Mobility's electric vehicle expansion, and SECI contract for solar energy.

- On January 4, 2024, Torrent Power signed four initial pacts with the Gujarat government to invest Rs 47,350 crore (US$ 5.70 billion) in renewable energy, green hydrogen, and electricity distribution. These investments are aimed at contributing to the state's development and creating employment opportunities.

- On January 8, 2024, Tata Power announced an Rs 70,000 crore (US$ 8.42 billion) investment to develop 10 GW of solar and wind power capacity in Tamil Nadu over the next 5-7 years. This aligns with its goal of achieving 70% clean energy production by 2030.

- In November 2023, AmpIn Energy Transition announced an investment of Rs. 3,100 crore (US$ 372.6 million) to establish renewable energy projects exceeding 600 MW and an integrated manufacturing facility for solar cells and modules across the Eastern region. The funding will be focused in West Bengal, Bihar, Odisha, Jharkhand, Chhattisgarh, and the Northeastern States.

- Around US$ 2.8 trillion will be invested in energy in 2023 globally. More than US$ 1.7 trillion is going to clean energy, including renewable power, nuclear, grids, storage, low-emission fuels, efficiency improvements and end-use renewables and electrification.

- US$ 2.4 billion National Hydrogen Mission for production of 5 MMT by 2030 and US$ 36 million additional in budget.

- 59 solar parks with an aggregate capacity 40 GW have been approved in India. Solar Parks in Pavagada (2 GW), Kurnool (1 GW) and Bhadla-II (648 MW) are included in the top 5 operational solar parks of 7 GW capacity in the country.

- The world’s largest renewable energy park of 30 GW capacity solar-wind hybrid project is under installation in Gujarat.

- India offers a great opportunity for investments in the RE sector; $196.98 Bn worth of projects are underway in India.

- Wind Energy has an offshore target of 30 GW by 2030 with 3 potential sites identified.

- GOVERNMENT INITIATIVES:

- In the Interim Budget for 2024-2025, The Government of India doubled funding for the National Green Hydrogen Mission, allocating Rs. 600 crores (US$ 72 million). Additionally, Rs. 17,490 crores (US$ 2.10 billion) were allocated for the Green Hydrogen Mission and the Strategic Interventions for Green Hydrogen Transition (SIGHT) Programme, highlighting a commitment to sustainable energy transition.

- In the Interim Budget for 2024-2025, the fiscal allocation for solar power grid infrastructure development surged to Rs. 8,500 Crore (US$ 1.02 billion), a significant rise from the previous year's Rs. 4,970 Crore (US$ 0.60 billion).

- As of January 2, 2024, the Government of India is implementing the Production Linked Incentive (PLI) Scheme for the National Programme on High Efficiency Solar PV Modules, aimed at achieving gigawatt-scale manufacturing capacity. Under Tranche-II, with a budget allocation of Rs 19,500 crore (US$ 2.35 billion), Letters of Award were issued in April 2023 for the establishment of 39,600 MW of fully or partially integrated solar PV module manufacturing units.

- The Ministry of New and Renewable Energy (MNRE) has proposed the establishment of a 13,000 MW renewable energy (RE) capacity along with a 12,000 MWh Battery Energy Storage System (BESS) in Ladakh. On October 18, 2023, the Cabinet Committee on Economic Affairs approved the construction of an Inter-State Transmission System (ISTS) to facilitate the power evacuation and grid integration of these RE projects in Ladakh.

- Proposed solar cities and parks: The Solar Park Scheme launched in December 2014 with a capacity of 20,000 MW was expanded to 40,000 MW by March 2017. As of November 30, 2023, 50 solar parks have been approved, totaling around 37,490 MW capacity across 12 states. Of these, 10,401 MW has been commissioned, including 284 MW in 2023.

- On February 13, 2024, Prime Minister Mr. Narendra Modi launched PM Surya Ghar Muft Bijli Yojana, offering free rooftop solar electricity to 1 crore households, backed by subsidies and concessional loans.

- On December 12, 2023, the Union Minister for New & Renewable Energy and Power reported the installation of 140 MW solar power plants and 2.73 lakh standalone solar pumps under PM-KUSUM, aimed at farmer welfare and environmental sustainability.

- In Budget 2023-24, Green Growth was identified as one of the nodes in the SAPTARISHI (7 priorities).

- In Budget 2023-24, pumped storage projects received a push with a detailed framework to be formulated.

- Union Budget 2023-24 envisions to create sustainable cities of tomorrow. To translate this, states and cities will be encouraged to undertake urban planning reforms and actions to transform our cities into 'sustainable cities of tomorrow.’

- The Indian government's commitment to reaching net-zero emissions by 2070 and increasing its renewable energy target to 500 GW by 2030 at the COP26 summit has provided great support to the industry and spurred unprecedented growth.

- In Budget 2023-24, Rs. 8,300 crore central sector support for ISTS infrastructure for 13 GW renewable energy from Ladakh was announced.

- On November 19, Prime Minister Mr. Narendra Modi dedicated the 600 MW Kameng Hydro Power Station in Arunachal Pradesh to the country. The project, which covers more than 80 kilometres and costs about Rs. 8,200 crore, is located in Arunachal Pradesh's West Kameng District.

- CONCLUSION:

India has set a target to reduce the carbon intensity of the nation’s economy by less than 45% by the end of the decade, achieve 50% cumulative electric power installed by 2030 from renewables, and achieve net-zero carbon emissions by 2070. Low-carbon technologies could create a market worth up to $80 billion in India by 2030.

India‘s target is to produce five million tonnes of green hydrogen by 2030. The Green Hydrogen target is set at India’s electrolyser manufacturing capacity is projected to reach 8 GW per year by 2025. The cumulative value of the green hydrogen market in India could reach $8 Bn by 2030 and India will require at least 50 gigawatts (GW) of electrolysers or more to ramp up hydrogen production.

India’s ambitious renewable energy goals are transforming its power sector. The rising population and widespread electrification in rural homes are fuelling the demand for energy to power homes, businesses and communities. Clean energy will reduce pollution levels as villages become self-sustainable with their use of clean energy. In 2022, India's renewable energy sector is expected to boom with a likely investment of US$ 15 billion this year, as the government focuses on electric vehicles, green hydrogen, and the manufacturing of solar equipment.

It is expected that by 2040, around 49% of the total electricity will be generated by renewable energy as more efficient batteries will be used to store electricity, which will further cut the solar energy cost by 66% as compared to the current cost. The use of renewables in place of coal will save India Rs. 54,000 crore (US$ 8.43 billion) annually. Around 15,000 MW of wind-solar hybrid capacity is expected to be added between 2020-25.

As per the Central Electricity Authority (CEA) estimates, by 2029-30, the share of renewable energy generation would increase from 18% to 44%, while that of thermal is expected to reduce from 78% to 52%. The CEA also estimates India’s power requirement to grow to reach 817 GW by 2030.

| PART G | SWOT ANALYSIS |
| --- | --- |

| SWOT ANALYSIS |  |
| --- | --- |
| STRENGTHS | - Cost Saving on Energies: As per the assessment, Company will save ~52.12 Crore annually by setting up this captive hybrid power plant. The Proposed Hybrid Solar – Wind Power Plant will reduce its electricity bill significantly by producing its own power instead of purchasing from the grid. With high local electricity tariffs, this could result in significant cost savings. - Sustainability and Environmental Benefits: The plant will help Sai Infinium Limited meet its sustainability goals and reduce its carbon footprint, appealing to environmentally conscious investors and customers. The primary objectives of the hybrid power plant is to reduce annual electricity cost by ~30%, decrease the carbon footprint by 30,000 tons per year, and ensure a reliable and renewable energy source for Sai Infinium Limited's operations. - Energy Independence: By generating its own electricity, Sai Infinium Limited reduces its exposure to energy price volatility and potential supply disruptions. - Government Incentives: Sai Infinium Limited benefits from local and national subsidies and tax credits for renewable energy projects, improving the financial feasibility of the plant. - Scalability: As Sai Infinium Limited’s energy needs grow, it can expand the solar array or add more panels to increase capacity, providing flexibility for future growth. - Technological Advancements: The plant will feature high-efficiency solar panels with a combined capacity of 36 MW DC Solar (~62062 nos. of Solar PV Module) 580Wp of BiN-08-580 type Solar module from Waaree Energies Limited and Suzlon S 120 – (2.1 X 13) 27.30 MW Wind turbine generator (WTG). It will utilize advanced photovoltaic (PV) technology and include a state-of-the-art monitoring system to optimize performance and maintenance, which improves energy efficiency and lowers the cost per megawatt-hour of electricity. - EPC Agreement: The proposed power plant will be implemented through appointed well known EPC M/s Opera Energy Private Limited, for which Techno-Commercial Contract is signed on 7th Jan 2025 by both the parties for design, develop, transfer and maintain the solar and wind hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer. Thus management of Sai Infinium is free to focus on operate the existing business efficiently. |
| WEAKNESSES | - High Initial Capital Investment: INR 467.91 Crore required for the initial setup of 63.30 MW Hybrid [36 MW DC Solar + 27.30 MW Wind] power plant might strain Sai Infinium Limited’s capital, affecting short-term financial stability. - Space Requirements: The proposed plant requires 126.45 acres of land i.e. 2 Acre per MW approx., which might be challenging to secure in densely populated areas or where land prices are high. - Intermittency: The plant’s output will vary with weather conditions and time of day, requiring Sai Infinium Limited to invest in energy storage solutions or backup power sources. - Maintenance Costs: Regular maintenance and potential repairs for the plant could incur additional costs, impacting the overall budget and operational efficiency. - Long Payback Period: With an estimated payback period of 7-8 years, Sai Infinium Limited might face challenges in demonstrating short-term returns to stakeholders. |
| OPPORTUNITIES | - Growing Demand for Renewable Energy: As more businesses and governments commit to renewable energy, Sai Infinium Limited could benefit from increased demand for its surplus power under open access arrangements. - Technological Innovations: Advancements in battery storage technology could enable Sai Infinium Limited to store excess energy and provide a more consistent power supply, enhancing profitability. - Regulatory Support: New regulations mandating a percentage of renewable energy in the grid mix could provide additional revenue opportunities through power sales. - Open Access Benefits: Sai Infinium Limited can sell excess electricity to other businesses or utilities through open access policies, diversifying its revenue streams. - Corporate Social Responsibility (CSR): Investing in solar energy can enhance Sai Infinium Limited’s brand image, attracting customers and partners who value sustainability. - Expansion Potential: As Sai Infinium Limited is an existing and old group, Company can diversified its business in future by entering into large scale Renewable projects. |
| THREATS | - Regulatory Risks: Changes in government policies or reductions in subsidies could impact the financial viability of the solar project, affecting Sai Infinium Limited’s profitability. - Market Competition: Increased competition from other renewable energy sources or cheaper conventional energy options might affect the market share and pricing power of Sai Infinium Limited. - Technological Risks: Rapid changes in solar technology or issues with the reliability of the installed equipment could pose risks to the project’s performance and financial returns. - Economic Fluctuations: Economic downturns could affect investment availability and delay project implementation or expansion plans. |

| PART H | PROJECT COST AND MEANS OF FINANCE |
| --- | --- |

As per data/information shared by the client, the proposed Wind Solar Hybrid power project is proposed to be commissioned by making an investment of INR 467.91 Crore as shown in the below table along with Means of finance:

| Total Project Cost |  |  |  |
| --- | --- | --- | --- |
| Particular (INR Crore) | 36.00 MW | 27.30 MW | Solar + Wind |
|  | Solar Plant | Wind Plant | Hybrid |
| Land Development Cost | 0.00 | 0.00 | 0.00 |
| Building & Civil Works | 6.555 | 15.386 | 21.94 |
| Plant & Machinery | 124.543 | 292.329 | 416.87 |
| Interest During Construction (IDC) |  |  | 22.52 |
| Preoperative Expenses ~ 1.0% of Hard Cost |  |  | 4.39 |
| Contingencies at ~ 0.5% of Hard Cost |  |  | 2.19 |
| Sub Total | 131.10 | 307.72 | 467.91 |

Source: As per the EPC Agreement and other data/Information provided by the company.

| Means of Finance |  |  |  |
| --- | --- | --- | --- |
| S. No. | Particular |  | Amount (INR Crore) |
|  | Equity | 25% | 116.98 |
|  | Term Loan from Bank | 75% | 350.93 |
|  | Total |  | 467.91 |

Source: Data/Information provided by the company.

Notes:

- It is to be noted that the detailed vetting of the project cost is out of scope of this TEV report and we have relied upon the data/information provided by the client regarding Total Project cost in good faith, however as a TEV consultant we have cross verified the cost of the major components of TPC independently wherever required for the purpose of TEV only.

- Proposed Hybrid Power plant will be implemented through appointment of EPC, for which company has signed an agreement with Opera Energy Pvt Ltd. dated 7th Jan 2025 for design, develop, transfer and maintain the solar and wind hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer. As per the commercial details of EPC agreement below table shows the Cost of the project:

| Commercial Details of EPC Agreement |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Division | Particular | UOM | Amount per Unit | GST (%) | Total Amount |
| 1 | Wind | Supply of 27.3 MW (2.1 Suzlon, 140 mtr), including logistic for WTG supply from Ex works to wind farm storage yard and Supply of Package, Substation. Special lifting tools, Stub, Template and required accessories, hardware, Supervision & Service, PSS, included | WTG | 150000000 | (12%) 1,80,00,000 | 16,80,00,000 |
| 2 |  | Balance of Plant (Land, Foundation, Approach Road, Sub Station Installation, WTG Erection and Commissioning) | WTG | 58000000 | 18% 1,04,40,000 | 6,84,40,000 |
| Amount per WTG |  |  |  | 208000000 | 13.80% 28704000 | 236704000 |
| A | Total Amount for 12 WTG Nos for 25.20 MW |  |  | 2704000000 | 373152000 | 3077152000 |
| 1 | Solar | Supply of Solar Panel and construction of solar park with supply of PV panel Tier -1 Top Con, Inverter, all required, Inverter duty Transformer, Aux, transformer, LTDB, MMS, HT Cable, LT cable, DC cable, earthing cable, HDPE pipe, cable accessories, Earthing strip, Metering. Balance of Plant (Land, Permits, Approvals, Land, Fencing, Approach Road, Internal Line, Commissioning) | MW | 32000000 | (13.80%) 4416000 | 36416000 |
| B | Total amount for 36 MW Solar DC |  |  | 1152000000 | 158976000 | 1310976000 |
| C | Total Hybrid Project Amount |  |  | 3856000000 | 532128000 | 4388128000 |

- As per the data/information provided by the client, Cost Bifurcation of Solar and Wind Power Plants as offered by EPC consultant are shown below:

| Cost Bifurcation of 36 MW (DC) Solar Power Project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Particular | Cost/MW | Total MW (DC) | Total Amount | GST | Total Amount |
| Supply of Solar panel and Construction of Solar Park with supply of PV panel Tier-1 Top Con, Inverter, all required, Inverter duty transformer, Aux. transformer, LTDB, MMS, HT cable, LT cable, DC cable, Earthing cable, HDPE pipe, cable accessories, Earthing strip, Metering. Balance of Plant (Land, Permits, Approvals, Land Fencing, Approach Road, Internal Line, Commissioning) (Auto Tracker) | 32000000 | 36 | 1152000000 | 13.80% |  |
| Total Amount for 36 MW Solar (DC) | 32000000 | 36 | 1152000000 | 158976000 | 1310976000 |

Source: Data/Information provided by the client.

| Cost Bifurcation of 27.3 MW Wind Power Project (2.1 MW * 13 Nos. WTGs) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Particular | Basic | GST@12% | Total |
| Supply | WOEG | 144286161 | 17314339 | 161600500 |
|  | Stub | 1697320 | 203678 | 1900998 |
|  | Stub Hardware | 101929 | 12231 | 114160 |
|  | Packaged SS | 3914590 | 469751 | 4384341 |
| Total |  | 150000000 | 18000000 | 168000000 |
| BOP (Balance of Plant) Cost |  |  |  |  |
| Description | Particular | Basic | GST@18% | Total |
| Balance of Plant (BOP) | Road Development | 5084746 | 915254 | 6000000 |
|  | Civil work for Foundation | 12711864 | 2288136 | 15000000 |
|  | USS Material | 10084746 | 1815254 | 11900000 |
|  | 33 KV Line Material | 12661017 | 2278983 | 14940000 |
|  | Erection | 8135593 | 1464407 | 9600000 |
|  | Commissioning | 4237288 | 762712 | 5000000 |
|  | Storage, Security & Insurance | 5084746 | 915254 | 6000000 |
| Total |  | 58000000 | 10440000 | 68440000 |
| Grand Total |  | 208000000 | 28704000 | 236440000 |
| Total amount for 13 WTGs Nos. 27.3 MW |  | 2704000000 | 373152000 | 3077152000 |

Source: Data/Information provided by the client.

- As per data/information provided by the client, Out of total EPC cost of INR 438.81 Crore, ~5% i.e. 21.94 Crore is the estimated cost of building & civil works and ~95% i.e. 416.87 Crore is the cost of plant and machinery for hybrid power plant.

- As per the data/information provided by the client, applicable Interest during Construction (IDC) is 11%. Thus the company is required to pay INR 22.52 Crore as IDC from March 2025 to 31st March 2026 (12 months) as per the proposed Loan repayment schedule.

- Preliminary & Pre-Operative Expenses has been considered based on the estimate of company’s resources involvement as INR 4.39 Crore, which is 1% of hard cost of the project. However, Company did not provide us any invoices/bills against these tentative costs considered. We recommend that the bank/financial institutions advice the company to submit actual cost based on the final quotations/invoices/bills. This will help validate the assertion of different costs considered by the client.

- Contingency cost of INR 2.19 Crore has been considered based on general assumption and professional experience (~0.5 of Hard Cost of the Project).

- The project is proposed to be funded through a term loan of INR 350.93 crores and promoter’s Equity of INR 116.98 crores.

- Thus, ~INR 7.39 Crore per MW is the expected CAPEX for the proposed 63.30 MW Wind Solar Hybrid power plant as shown in the below table:

| Particular | Capex (INR Cr.) | MW | Per MW Cost |
| --- | --- | --- | --- |
| Solar | 131.09 | 36.00 | INR 3.64 Cr. |
| Wind | 307.71 | 27.30 | INR 11.27 Cr. |

Per MW cost of Solar and Wind power plants are in the line with market trends. The cost of a 1 MW solar power plant in India is typically between ₹4 and ₹5 crores. The cost depends on several factors, including: Solar panels, Land, Balance of system (BOS) components, Installation challenges, Batteries. For reference Amplus Solar (https://amplussolar.com/blogs/1mw-solar-power-plant) and Waree (https://waaree.com/blog/5-mw-solar-power-energy-plant-in-india-profit-cost-land-requirement/) are known name in this field.

Similarly, According to a report by the Ministry of New and Renewable Energy in India, the capital cost of wind power projects in India ranges from INR 5.5 crore per MW to INR 6.5 crore per MW (approximately USD 750,000 to USD 880,000 per MW) for onshore wind projects, and from INR 8.5 crore per MW to INR 12 crore per MW (approximately USD 1.2 million to USD 1.6 million per MW) for offshore wind project. (https://www.linkedin.com/pulse/india-wind-energy-potential-quesrow#:~:text=According%20to%20a%20report%20by,INR%2012%20crore%20per%20MW%20).

Further, as informed by client, the proposed hybrid model in use incorporates a range of advanced technological improvements and structural enhancements. Specifically, it utilizes a combination of hybrid tubular and lattice tower structures, designed with a higher hub height and an expanded blade swept area and turbines with DFIG technology.

These features allow for a significantly increased energy capture and improved efficiency. These structural enhancements, coupled with state-of-the-art production technology, contribute to both the higher upfront costs and the enhanced production capacity achieved with this model. This approach represents an investment in the latest technology, aligning with industry trends focused on achieving higher output per unit and reducing lifetime costs through greater efficiency, whereas the Rs. 5-7cr for on shore projects were proposed for the older technology turbines with less hub height and small swept area as per design.

| PART I | PROJECT IMPLEMENTETION SCHEDULE |
| --- | --- |

The proposed hybrid power plant is expected to achieve its C.O.D till 1st April 2026, as per the proposed implementation schedule shown in the table below:

| S. No. | Particulars | Activity | Expected completion date | Status |
| --- | --- | --- | --- | --- |
|  | Land | Land Procurement | FY 2024 | Completed |
|  |  | Land Development | 31st March 2025 | Scheduled |
|  | Sanction of Rupee Term Loan | Sanction of Rupee Term Loan | 1st March 2025 | Scheduled |
|  | Building & Civil Works | Appointment of Architect | 7th Jan 2025 | Completed |
|  |  | Building/Layout Plan Preparation | 31st March 2025 | Scheduled |
|  |  | Building Plan Sanction | 31st March 2025 | Scheduled |
|  |  | Appointment of Civil contractor/ developer | 7th Jan 2025 | Completed |
|  |  | Building & Civil Works completion | September 2025 | Scheduled |
|  | Plant & Machinery | Finalization of P&M suppliers | 7th Jan 2025 | Completed |
|  |  | Orders to P&M suppliers | 31st March 2025 | Scheduled |
|  |  | Arrival of P&M | September 2025 | Scheduled |
|  |  | Installation of P&M | December 2025 | Scheduled |
|  |  | Utility Installation | Jan 2026 | Scheduled |
|  | Statutory Approvals, registrations & NOCs | From the respective authorities | Feb 2026 | Pending except the approval obtained as per “Section L” |
|  | Finishing & Trail Run | Informed by client | March, 2026 | Scheduled |
|  | Commercial Operation Date | Informed by client | 1st April 2026 | Scheduled |

Notes:

- Proposed Hybrid Power plant will be implemented through appointment of EPC, for which company has signed an agreement with Opera Energy Ltd. dated 7th Jan 2025 for design, develop, transfer and maintain the solar and wind hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer. Thus there is no need to appoint architect, civil contractor/developer separately and procurement of the Plant & Machinery will also be handled by EPC only.

- Schedule has been made as per feasibility to achieve different milestones.

- Achievement of Milestone will depend on sanction of term loan as per proposed timeline.

- For current status of statutory approvals, kindly refer the “Section L” of this report.

- It is to be noted here that hybrid power plant will be implemented through EPC and thus

- As per this timeline, the expected C.O.D will be 1st April 2026.

| PART J | STATUTORY APPROVALS ¦ LICENCES ¦ NOC |
| --- | --- |

As shown in the below table along with current status, following major approvals are required, However the list is not exhaustive and State/District Authorities may be approached for further clearances required (if any):

| S. No. | REQUIRED APPROVALS | DATE REFERENCE NO. | STATUS (Approved/ Applied For/ Pending) |
| --- | --- | --- | --- |
|  | Provisional Registration of Renewable Energy Project under Gujarat Renewable Energy Policy- 2023 Gujarat Energy Development Agency (GEDA) | PR No.: GEDA/PR/WSH/23-24/02/824/13 Dated: 3rd February 2024 | Applied |
|  | Land conversion to Industrial/Non agriculture Sub Divisional Magistrate, Bharuch, Gujrat. | - | Pending |
|  | Grid Connectivity Approval Gujrat Energy Transmission Corporation Limited (GETCO) | GETCO/R&C/STAGE2000127 Dated: 13/01/2024 | Approved |
|  | Electricity Regulatory Compliance Gujarat Electricity Regulatory Commission (GERC) | - | Pending |
|  | Building and civil works Plan Sanction Approval Concerned local development authority | - | Pending |
|  | Pre-establishment fire NOC Fire and Emergency Services, Government Of Gujrat | - | Apply in due course |
|  | Fire NOC (on completion) Fire and Emergency Services, Government Of Gujrat | - | Will be Applied post C.O.D |

Observation Note:

- As per EPC agreement, Opera Energy Private Limited has taken Grid Connectivity approval from GETCO for 30 MW Wind Solar hybrid power plant at 66KVGangiyavadar substation of GETCO, Ref: GETCO/R&C/STAGE2000127 Dated: 13/01/2024.

- EPC has applied for Provisional Registration of Renewable Energy Project under Gujarat Renewable Energy Policy- 2023 Reference: PR No.: GEDA/PR/WSH/23-24/02/824/13 Dated 3rd Feb 2024.

- As per the agreement, M/s Opera Energy Private Limited has acquired ~126.45 Acre land at Village: Sardharka Taluka: Wankaner Morbi District, State of Gujrat 363621 for 63.30 MW Hybrid power project. As per the site visit dated, 15th January 2025, we found that the land is an agricultural leasehold land for which Opera needs to obtain CLU certificate from the respective authority.

- Above is the only illustration of the major approvals sought or to be sought by the company. It should not be construed as the exhaustive list and in case any approval is missed to be mentioned then it is the sole responsibility of the company to keep the unit compliant with the necessary statutory approvals/ NOCs.

| PART K | PROJECT’S FINANCIAL FEASIBILITY |
| --- | --- |

- PROJECTIONS OF THE PROJECT:

The financial projections of the proposed Wind-Solar Hybrid power project are prepared from FY 2025 to FY 2052 based on the expected COD and loan tenure as per the best practice in industry to assess the financial feasibility of the project:

- PROJECTED PROFIT & LOSS ACCOUNT:

(INR Crore)

| Year Ending | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Revenue | 120.39 | 121.26 | 121.46 | 122.00 | 122.54 | 123.43 | 123.64 | 124.19 | 124.74 | 125.64 | 125.85 | 126.41 | 126.97 |
| Operating Expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| O & M Expenses | 0.00 | 0.00 | 4.27 | 4.48 | 4.71 | 4.94 | 5.19 | 5.45 | 5.72 | 6.01 | 6.31 | 6.62 | 6.95 |
| Lease Rentals for land | 0.00 | 0.84 | 0.84 | 0.90 | 0.90 | 0.96 | 0.96 | 1.03 | 1.03 | 1.10 | 1.10 | 1.18 | 1.18 |
| Insurance Expenses | 0.45 | 0.43 | 0.41 | 0.40 | 0.38 | 0.36 | 0.34 | 0.33 | 0.31 | 0.29 | 0.27 | 0.26 | 0.24 |
| Total Statutory Fee & Charges | 7.38 | 7.39 | 7.35 | 7.34 | 7.32 | 7.33 | 7.29 | 7.28 | 7.26 | 7.27 | 7.23 | 7.22 | 7.21 |
| Depreciation & Amortization | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 |
| Total Expenses | 25.47 | 26.34 | 30.51 | 30.75 | 30.94 | 31.28 | 31.42 | 31.71 | 31.95 | 32.35 | 32.55 | 32.91 | 33.21 |
| EBIT | 94.92 | 94.91 | 90.95 | 91.25 | 91.60 | 92.15 | 92.22 | 92.47 | 92.78 | 93.28 | 93.30 | 93.50 | 93.76 |
| Interest expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest on term loan | 38.60 | 37.64 | 35.71 | 33.78 | 31.85 | 29.92 | 27.99 | 26.06 | 24.13 | 22.20 | 20.27 | 18.34 | 16.41 |
| Profit before Taxes (PBT) | 56.32 | 57.27 | 55.25 | 57.48 | 59.76 | 62.23 | 64.23 | 66.41 | 68.66 | 71.09 | 73.03 | 75.16 | 77.36 |
| Tax | 9.84 | 10.01 | 9.65 | 10.04 | 10.44 | 10.87 | 11.22 | 11.60 | 12.00 | 12.42 | 15.16 | 23.56 | 24.71 |
| Profit after Taxes (PAT) | 46.48 | 47.27 | 45.59 | 47.43 | 49.32 | 51.36 | 53.01 | 54.81 | 56.66 | 58.67 | 57.87 | 51.60 | 52.65 |

(Continued)

| Year Ending | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Revenue | 127.88 | 128.10 | 128.67 | 129.24 | 130.17 | 130.39 | 130.97 | 131.56 | 132.50 | 132.73 | 133.32 | 133.91 | 134.87 |
| Operating Expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| O & M Expenses | 7.30 | 7.67 | 8.05 | 8.45 | 8.87 | 9.32 | 9.78 | 10.27 | 10.79 | 11.33 | 11.89 | 12.49 | 13.11 |
| Lease Rentals for land | 1.26 | 1.26 | 1.35 | 1.35 | 1.45 | 1.44 | 1.54 | 1.54 | 1.66 | 1.65 | 1.77 | 1.77 | 1.90 |
| Insurance Expenses | 0.22 | 0.20 | 0.19 | 0.17 | 0.15 | 0.13 | 0.12 | 0.10 | 0.08 | 0.06 | 0.04 | 0.03 | 0.01 |
| Total Statutory Fee & Charges | 7.21 | 7.18 | 7.16 | 7.15 | 7.15 | 7.12 | 7.11 | 7.09 | 7.10 | 7.07 | 7.05 | 7.04 | 7.04 |
| Depreciation & Amortization | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 |
| Total Expenses | 33.68 | 33.94 | 34.38 | 34.75 | 35.31 | 35.65 | 36.18 | 36.64 | 37.30 | 37.74 | 38.39 | 38.95 | 39.74 |
| EBIT | 94.21 | 94.16 | 94.29 | 94.49 | 94.87 | 94.75 | 94.79 | 94.92 | 95.20 | 94.99 | 94.93 | 94.96 | 95.13 |
| Interest expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest on term loan | 14.48 | 12.55 | 10.62 | 8.69 | 6.76 | 4.83 | 2.90 | 0.97 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Profit before Taxes (PBT) | 79.73 | 81.62 | 83.68 | 85.81 | 88.11 | 89.92 | 91.90 | 93.95 | 95.20 | 94.99 | 94.93 | 94.96 | 85.94 |
| Tax | 25.84 | 26.75 | 27.67 | 28.56 | 29.47 | 30.18 | 30.92 | 31.66 | 32.16 | 32.19 | 32.26 | 32.34 | 29.79 |
| Profit after Taxes (PAT) | 53.89 | 54.86 | 56.01 | 57.25 | 58.65 | 59.74 | 60.98 | 62.29 | 63.04 | 62.80 | 62.67 | 62.62 | 56.15 |

- PROFORMA BALANCE SHEET:

Below table shows the Projected Balance Sheet of the proposed Captive Wind-Solar Hybrid power project from the period FY 2025 to FY 2052. From 1st March 2025 to 31st March 2026 would be the implementation period of the project:

(INR Crore)

| Year Ending | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 1 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Non-Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity | 23.40 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 |
| Reserve & Surplus | 0.00 | 0.00 | 46.48 | 93.75 | 139.34 | 186.77 | 236.09 | 287.45 | 340.46 | 395.27 | 451.93 | 510.60 | 568.47 | 620.07 |
| Secured Loan | 70.19 | 350.93 | 333.39 | 315.84 | 298.29 | 280.75 | 263.20 | 245.65 | 228.11 | 210.56 | 193.01 | 175.47 | 157.92 | 140.37 |
| Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Term Liabilities Payable Within One Year | 0.00 | 0.00 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 |
| Total | 93.58 | 467.91 | 514.39 | 544.11 | 572.16 | 602.05 | 633.82 | 667.63 | 703.09 | 740.35 | 779.47 | 820.59 | 860.92 | 894.97 |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Gross Block | 93.58 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 |
| Less: Depreciation |  |  | 17.63 | 35.31 | 52.95 | 70.58 | 88.21 | 105.89 | 123.52 | 141.16 | 158.79 | 176.47 | 194.10 | 211.74 |
| Net Block | 93.58 | 467.91 | 450.28 | 432.60 | 414.97 | 397.33 | 379.70 | 362.02 | 344.39 | 326.76 | 309.12 | 291.44 | 273.81 | 256.18 |
| Mat Credit Entitlement | 0.00 | 0.00 | 9.84 | 19.85 | 29.50 | 39.54 | 38.02 | 34.66 | 29.73 | 23.40 | 15.85 | 7.19 | 0.00 | 0.00 |
| Total Non-Current Assets | 93.58 | 467.91 | 460.12 | 452.45 | 444.47 | 436.88 | 417.73 | 396.69 | 374.12 | 350.16 | 324.97 | 298.63 | 273.81 | 256.18 |
| Current Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash & Cash Equivalent | 0.00 | 0.00 | 54.27 | 91.67 | 127.69 | 165.17 | 216.09 | 270.94 | 328.98 | 390.20 | 454.50 | 521.96 | 587.11 | 638.79 |
| Total Current Assets | 0.00 | 0.00 | 54.27 | 91.67 | 127.69 | 165.17 | 216.09 | 270.94 | 328.98 | 390.20 | 454.50 | 521.96 | 587.11 | 638.79 |
| Total | 93.58 | 467.91 | 514.39 | 544.11 | 572.16 | 602.05 | 633.82 | 667.63 | 703.09 | 740.35 | 779.47 | 820.59 | 860.92 | 894.97 |

(Continued)

| Year Ending | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Non-Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 | 116.98 |
| Reserve & Surplus | 672.72 | 726.61 | 781.47 | 837.48 | 894.73 | 953.37 | 1013.12 | 1074.09 | 1136.39 | 1199.43 | 1262.23 | 1324.91 | 1387.52 | 1450.19 |
| Secured Loan | 122.83 | 105.28 | 87.73 | 70.19 | 52.64 | 35.09 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Term Liabilities Payable Within One Year | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 930.07 | 966.41 | 1003.73 | 1042.19 | 1081.89 | 1122.99 | 1165.19 | 1208.62 | 1253.36 | 1316.41 | 1379.21 | 1441.88 | 1504.50 | 1567.17 |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Gross Block | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 | 467.91 |
| Less: Depreciation | 229.37 | 247.05 | 264.68 | 282.31 | 299.95 | 317.63 | 335.26 | 352.89 | 370.52 | 388.21 | 405.84 | 423.47 | 441.10 | 458.78 |
| Net Block | 238.55 | 220.86 | 203.23 | 185.60 | 167.97 | 150.29 | 132.65 | 115.02 | 97.39 | 79.71 | 62.08 | 44.44 | 26.81 | 9.13 |
| Mat Credit Entitlement | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total Non-Current Assets | 238.55 | 220.86 | 203.23 | 185.60 | 167.97 | 150.29 | 132.65 | 115.02 | 97.39 | 79.71 | 62.08 | 44.44 | 26.81 | 9.13 |
| Current Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash & Cash Equivalent | 691.52 | 745.55 | 800.50 | 856.59 | 913.93 | 972.71 | 1032.54 | 1093.60 | 1155.98 | 1236.70 | 1317.14 | 1397.44 | 1477.69 | 1558.04 |
| Total Current Assets | 691.52 | 745.55 | 800.50 | 856.59 | 913.93 | 972.71 | 1032.54 | 1093.60 | 1155.98 | 1236.70 | 1317.14 | 1397.44 | 1477.69 | 1558.04 |
| Total | 930.07 | 966.41 | 1003.73 | 1042.19 | 1081.89 | 1122.99 | 1165.19 | 1208.62 | 1253.36 | 1316.41 | 1379.21 | 1441.88 | 1504.50 | 1567.17 |

- PROJECTED CASH FLOW STATEMENT:

(INR Crore)

| Year Ending (INR Crore) | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 1 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| A. Source Of Fund |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net Profit | 0.00 | 0.00 | 46.48 | 47.27 | 45.59 | 47.43 | 49.32 | 51.36 | 53.01 | 54.81 | 56.66 | 58.67 | 57.87 | 51.60 |
| Increase in Equity / Share Capital/USL | 23.40 | 93.58 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Increase in TL | 70.19 | 280.75 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Depreciation | 0.00 | 0.00 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 |
| Trade payables | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 93.58 | 374.33 | 64.11 | 64.95 | 63.23 | 65.07 | 66.95 | 69.04 | 70.64 | 72.44 | 74.29 | 76.35 | 75.51 | 69.23 |
| B. Application Of Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital Expenses | 93.58 | 374.33 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Change in MAT | 0.00 | 0.00 | 9.84 | 10.01 | 9.65 | 10.04 | -1.52 | -3.36 | -4.94 | -6.33 | -7.55 | -8.66 | -7.19 | 0.00 |
| Decrease in Term Loan | 0.00 | 0.00 | 0.00 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 |
| Total | 93.58 | 374.33 | 9.84 | 27.55 | 27.20 | 27.59 | 16.03 | 14.19 | 12.61 | 11.22 | 9.99 | 8.89 | 10.36 | 17.55 |
| Opening Balance | 0.00 | 0.00 | 0.00 | 54.27 | 91.67 | 127.69 | 165.17 | 216.09 | 270.94 | 328.98 | 390.20 | 454.50 | 521.96 | 587.11 |
| Net Surplus/ Deficit | 0.00 | 0.00 | 54.27 | 37.39 | 36.03 | 37.48 | 50.92 | 54.85 | 58.03 | 61.22 | 64.30 | 67.46 | 65.15 | 51.69 |
| Cumulative Balance | 0.00 | 0.00 | 54.27 | 91.67 | 127.69 | 165.17 | 216.09 | 270.94 | 328.98 | 390.20 | 454.50 | 521.96 | 587.11 | 638.79 |

(Continued)

| Year Ending (INR Crore) | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| A. Source Of Fund |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net Profit | 52.65 | 53.89 | 54.86 | 56.01 | 57.25 | 58.65 | 59.74 | 60.98 | 62.29 | 63.04 | 62.80 | 62.67 | 62.62 | 62.66 |
| Increase in Equity / Share Capital/USL | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Increase in TL | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Depreciation | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 |
| Trade payables | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 70.28 | 71.57 | 72.50 | 73.64 | 74.88 | 76.33 | 77.38 | 78.61 | 79.92 | 80.73 | 80.44 | 80.30 | 80.25 | 80.35 |
| B. Application Of Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital Expenses | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Change in MAT | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Decrease in Term Loan | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Opening Balance | 638.79 | 691.52 | 745.55 | 800.50 | 856.59 | 913.93 | 972.71 | 1032.54 | 1093.60 | 1155.98 | 1236.70 | 1317.14 | 1397.44 | 1477.69 |
| Net Surplus/ Deficit | 52.73 | 54.02 | 54.95 | 56.09 | 57.34 | 58.78 | 59.83 | 61.06 | 62.38 | 80.73 | 80.44 | 80.30 | 80.25 | 80.35 |
| Cumulative Balance | 691.52 | 745.55 | 800.50 | 856.59 | 913.93 | 972.71 | 1032.54 | 1093.60 | 1155.98 | 1236.70 | 1317.14 | 1397.44 | 1477.69 | 1558.04 |

- KEY FINANCIAL RATIO:

| Year Ending (INR Crore) | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBITDA Margin % | 93.49% | 92.86% | 89.40% | 89.25% | 89.14% | 88.99% | 88.85% | 88.66% | 88.52% | 88.32% | 88.15% | 87.92% | 87.73% |
| Average | 87.54% |  |  |  |  |  |  |  |  |  |  |  |  |
| EBIT Margin % | 78.85% | 78.27% | 74.88% | 74.80% | 74.75% | 74.66% | 74.59% | 74.46% | 74.38% | 74.25% | 74.14% | 73.97% | 73.85% |
| Average | 73.67% |  |  |  |  |  |  |  |  |  |  |  |  |
| PAT Margin % | 38.61% | 38.98% | 37.54% | 38.88% | 40.24% | 41.61% | 42.87% | 44.14% | 45.42% | 46.70% | 45.99% | 40.82% | 41.46% |
| Average | 43.69% |  |  |  |  |  |  |  |  |  |  |  |  |
| Revenue Growth Rate |  | 0.72% | 0.17% | 0.44% | 0.44% | 0.72% | 0.17% | 0.44% | 0.44% | 0.72% | 0.17% | 0.44% | 0.44% |
| Average | 0.46% |  |  |  |  |  |  |  |  |  |  |  |  |

| Year Ending (INR Crore) | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBITDA Margin % | 87.49% | 87.27% | 86.99% | 86.76% | 86.46% | 86.18% | 85.84% | 85.55% | 85.19% | 84.85% | 84.43% | 84.08% | 83.64% |
| Average | 87.54% |  |  |  |  |  |  |  |  |  |  |  |  |
| EBIT Margin % | 73.67% | 73.51% | 73.28% | 73.11% | 72.88% | 72.66% | 72.37% | 72.15% | 71.85% | 71.57% | 71.20% | 70.91% | 70.53% |
| Average | 73.67% |  |  |  |  |  |  |  |  |  |  |  |  |
| PAT Margin % | 42.14% | 42.83% | 43.53% | 44.30% | 45.05% | 45.82% | 46.56% | 47.35% | 47.58% | 47.32% | 47.01% | 46.76% | 46.46% |
| Average | 43.69% |  |  |  |  |  |  |  |  |  |  |  |  |
| Revenue Growth Rate | 0.72% | 0.17% | 0.44% | 0.44% | 0.72% | 0.17% | 0.44% | 0.44% | 0.72% | 0.17% | 0.44% | 0.44% | 0.72% |
| Average | 0.46% |  |  |  |  |  |  |  |  |  |  |  |  |

Note: The proposed solar power plant is having an average revenue growth rate of 0.46% during the forecasted period. Revenue growth is in declining trend throughout the projected years due to applicable degradation rate of 0.55% year on year basis. Average EBITDA Margin & EBIT Margin of the project are 87.54% & 73.67% respectively.  The project will be operational from 1st April 2026 and as per the trends analysis above, PAT margin is growing from 38.61% in FY 2027 to 46.46% in FY 2052 due to the lower interest cost on borrowings in the later projected years.

- GRAPHICAL REPRESENTATION OF KEY RATIOS:

- ESTIMATED KEY FINANCIAL METRICS:

DEBT SERVICE COVERAGE RATIO (D.S.C.R)

(INR Crore except D.S.C.R)

| Year Ending (INR Crore) | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Cash accrual | 64.11 | 64.95 | 63.23 | 65.07 | 66.95 | 69.04 | 70.64 | 72.44 | 74.29 | 76.35 | 75.51 | 69.23 | 70.28 |
| Interest on term loan | 38.60 | 37.64 | 35.71 | 33.78 | 31.85 | 29.92 | 27.99 | 26.06 | 24.13 | 22.20 | 20.27 | 18.34 | 16.41 |
| Subtotal | 102.72 | 102.59 | 98.93 | 98.84 | 98.80 | 98.96 | 98.63 | 98.50 | 98.42 | 98.55 | 95.77 | 87.57 | 86.68 |
| Interest on term loan | 38.60 | 37.64 | 35.71 | 33.78 | 31.85 | 29.92 | 27.99 | 26.06 | 24.13 | 22.20 | 20.27 | 18.34 | 16.41 |
| Loan Repayment | 0.00 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 |
| Subtotal | 38.60 | 55.18 | 53.25 | 51.32 | 49.39 | 47.46 | 45.53 | 43.60 | 41.67 | 39.74 | 37.81 | 35.88 | 33.95 |
| DSCR | 2.66 | 1.86 | 1.86 | 1.93 | 2.00 | 2.08 | 2.17 | 2.26 | 2.36 | 2.48 | 2.53 | 2.44 | 2.55 |

(Continue)

| Year Ending (INR Crore) | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Cash accrual | 71.57 | 72.50 | 73.64 | 74.88 | 76.33 | 77.38 | 78.61 | 79.92 | 80.73 | 80.44 | 80.30 | 80.25 | 80.35 |
| Interest on term loan | 14.48 | 12.55 | 10.62 | 8.69 | 6.76 | 4.83 | 2.90 | 0.97 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Subtotal | 86.05 | 85.04 | 84.26 | 83.57 | 83.08 | 82.20 | 81.50 | 80.89 | 80.73 | 80.44 | 80.30 | 80.25 | 80.35 |
| Interest on term loan | 14.48 | 12.55 | 10.62 | 8.69 | 6.76 | 4.83 | 2.90 | 0.97 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Loan Repayment | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Subtotal | 32.02 | 30.09 | 28.16 | 26.23 | 24.30 | 22.37 | 20.44 | 18.51 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| D.S.C.R | 2.69 | 2.83 | 2.99 | 3.19 | 3.42 | 3.67 | 3.99 | 4.37 |  |  |  |  |  |
| Average D.S.C.R | 2.68 |  |  |  |  |  |  |  |  |  |  |  |  |
| Max. D.S.C.R | 4.37 |  |  |  |  |  |  |  |  |  |  |  |  |

Note: D.S.C.R has been calculated for loan repayment period from FY 2027 to FY 2047. The proposed hybrid wind-solar power plant is having a D.S.C.R of more than 1 during the projected loan repayment period.

- NPV,IRR AND PAYBACK PERIOD OF THE PROJECT:

(INR Crore)

| Year Ending | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 1 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBIT | 0.00 | 0.00 | 94.92 | 94.91 | 90.95 | 91.25 | 91.60 | 92.15 | 92.22 | 92.47 | 92.78 | 93.28 | 93.30 | 93.50 |
| Less: Taxes | 0.00 | 0.00 | 27.64 | 27.64 | 26.49 | 26.57 | 26.68 | 26.83 | 26.85 | 26.93 | 27.02 | 27.16 | 27.17 | 27.23 |
| Add: Depreciation & Amortisation | 0.00 | 0.00 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 |
| NOPAT | 0.00 | 0.00 | 84.91 | 84.95 | 82.10 | 82.31 | 82.56 | 83.00 | 83.00 | 83.18 | 83.40 | 83.80 | 83.76 | 83.91 |
| Capex | 93.58 | 374.33 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Free Cash Flow to Firm (FCFF) | -93.58 | -374.33 | 84.91 | 84.95 | 82.10 | 82.31 | 82.56 | 83.00 | 83.00 | 83.18 | 83.40 | 83.80 | 83.76 | 83.91 |

(Continue)

| Year Ending (INR Crore) | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBIT | 93.76 | 94.21 | 94.16 | 94.29 | 94.49 | 94.87 | 94.75 | 94.79 | 94.92 | 95.20 | 94.99 | 94.93 | 94.96 | 95.13 |
| Less: Taxes | 27.30 | 27.43 | 27.42 | 27.46 | 27.52 | 27.63 | 27.59 | 27.60 | 27.64 | 27.72 | 27.66 | 27.64 | 27.65 | 27.70 |
| Add: Depreciation & Amortisation | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 |
| NOPAT | 84.09 | 84.46 | 84.38 | 84.47 | 84.61 | 84.92 | 84.79 | 84.82 | 84.91 | 85.16 | 84.96 | 84.92 | 84.94 | 85.11 |
| Capex | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Free Cash Flow to Firm (FCFF) | 84.09 | 84.46 | 84.38 | 84.47 | 84.61 | 84.92 | 84.79 | 84.82 | 84.91 | 85.16 | 84.96 | 84.92 | 84.94 | 85.11 |
| NPV | INR 244 Crore |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IRR | 16.99% |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Key Input for NPV & IRR |  |
| --- | --- |
| Weight of Debt Wd | 75% |
| Cost of Debt Kd | 11% |
| Tax | 29.12% |
| Post tax Kd | 7.80% |
| Weight of Equity We | 25% |
| Cost of Equity Ke | 18.00% |
| WACC | 10.35% |

| Payback Period of the Project |  |  |
| --- | --- | --- |
| Financial Year | Cash Accrual | Accumulated Cash Accrual |
| 31-Mar-27 | 64.11 | 64.11 |
| 31-Mar-28 | 64.95 | 129.06 |
| 31-Mar-29 | 63.23 | 192.29 |
| 31-Mar-30 | 65.07 | 257.35 |
| 31-Mar-31 | 66.95 | 324.30 |
| 31-Mar-32 | 69.04 | 393.34 |
| 31-Mar-33 | 70.64 | 463.98 |
| 31-Mar-34 | 72.44 | 536.43 |
| 31-Mar-35 | 74.29 | 610.72 |
| 31-Mar-36 | 76.35 | 687.07 |
| 31-Mar-37 | 75.51 | 762.57 |
| 31-Mar-38 | 69.23 | 831.81 |
| 31-Mar-39 | 70.28 | 902.08 |
| 31-Mar-40 | 71.57 | 973.65 |
| 31-Mar-41 | 72.50 | 1046.15 |
| 31-Mar-42 | 73.64 | 1119.79 |
| 31-Mar-43 | 74.88 | 1194.67 |
| 31-Mar-44 | 76.33 | 1271.00 |
| 31-Mar-45 | 77.38 | 1348.38 |
| 31-Mar-46 | 78.61 | 1426.99 |
| 31-Mar-47 | 79.92 | 1506.91 |
| 31-Mar-48 | 80.73 | 1587.64 |
| 31-Mar-49 | 80.44 | 1668.07 |
| 31-Mar-50 | 80.30 | 1748.38 |
| 31-Mar-51 | 80.25 | 1828.63 |
| 31-Mar-52 | 80.35 | 1908.97 |
| Total | 1908.97 |  |
| Total Project Cost | INR 467.91 Crore |  |
| Payback Period | 7.05 Years |  |

Thus, the project will be having a payback period of 7.05 years and NPV & IRR of the project is INR 244 Crore & 16.99% respectively from C.O.D to loan repayment period, which indicates worthiness of the project.

- SENSITIVITY ANALYSIS:

Sensitivity analysis of the project with respect to 5% & 10% decrease in the revenue, 5% & 10% increase in the operating cost and 2% increment in the proposed interest rate has been shown in the below table:

| Sensitivity Analysis of D.S.CR, NPV & IRR |  |  |  |  |
| --- | --- | --- | --- | --- |
| S. No. | Particular | Average D.S.C.R | NPV | IRR |
|  | As a base case | 2.68 | INR 244 Cr. | 16.99% |
|  | If the projected revenue decreased by 5% | 2.54 | INR 208 Cr. | 16.06% |
|  | If the projected revenue decreased by 10% | 2.40 | INR 172 Cr. | 15.13% |
|  | If the projected operating cost increased by 5% | 2.65 | INR 235 Cr. | 16.76% |
|  | If the projected operating cost increased by 10% | 2.61 | INR 226 Cr. | 16.53% |
|  | If interest rate is increased by 2% | 2.48 | INR 185 Cr. | 16.83% |

Observation: The proposed project is found comparatively higher sensitive with respect to the downside variation in the projected revenue, than the upside variation in the projected operational expenses and any surge in the interest rate.

- OTHER FINANCIAL RATIOS:

| Year Ending | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Return on Capital Employed (%) | 19.11% | 18.02% | 16.40% | 15.61% | 14.86% | 14.18% | 13.45% | 12.79% | 12.18% | 11.62% | 11.06% | 10.66% | 10.28% |
| Return on Investment (%) | 39.73% | 40.41% | 38.98% | 40.55% | 42.16% | 43.91% | 45.31% | 46.86% | 48.44% | 50.15% | 49.47% | 44.11% | 45.00% |
| Return on Net Worth | 28.44% | 22.43% | 17.79% | 15.62% | 13.97% | 12.70% | 11.59% | 10.70% | 9.96% | 9.35% | 8.44% | 7.00% | 6.67% |
| DSCR | 2.66 | 1.86 | 1.86 | 1.93 | 2.00 | 2.08 | 2.17 | 2.26 | 2.36 | 2.48 | 2.53 | 2.44 | 2.55 |
| ISCR | 2.92 | 2.99 | 3.04 | 3.22 | 3.43 | 3.67 | 3.92 | 4.23 | 4.58 | 5.00 | 5.47 | 6.06 | 6.79 |
| Fixed Asset Coverage Ratio | 1.35 | 1.37 | 1.39 | 1.42 | 1.44 | 1.47 | 1.51 | 1.55 | 1.60 | 1.66 | 1.73 | 1.82 | 1.94 |
| TOL/TNW | 2.15 | 1.58 | 1.23 | 0.98 | 0.80 | 0.65 | 0.54 | 0.45 | 0.37 | 0.31 | 0.26 | 0.21 | 0.18 |
| Debt to Equity Ratio | 3.00 | 2.85 | 2.70 | 2.55 | 2.40 | 2.25 | 2.10 | 1.95 | 1.80 | 1.65 | 1.50 | 1.35 | 1.20 |

(Continue)

| Year Ending | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Return on Capital Employed (%) | 9.93% | 9.55% | 9.20% | 8.88% | 8.58% | 8.26% | 7.96% | 7.57% | 7.23% | 6.89% | 6.58% | 6.31% | 6.07% |
| Return on Investment (%) | 46.07% | 46.90% | 47.88% | 48.94% | 50.13% | 51.07% | 52.13% | 53.25% | 53.89% | 53.69% | 53.58% | 53.53% | 53.57% |
| Return on Net Worth | 6.39% | 6.11% | 5.87% | 5.66% | 5.48% | 5.29% | 5.12% | 4.97% | 4.79% | 4.55% | 4.35% | 4.16% | 4.00% |
| DSCR | 2.69 | 2.83 | 2.99 | 3.19 | 3.42 | 3.67 | 3.99 | 4.37 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| ISCR | 7.73 | 8.91 | 10.54 | 12.91 | 16.66 | 23.29 | 38.83 |  |  |  |  |  |  |
| Fixed Asset Coverage Ratio | 2.10 | 2.32 | 2.64 | 3.19 | 4.28 | 7.56 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| TOL/TNW | 0.15 | 0.12 | 0.09 | 0.07 | 0.05 | 0.03 | 0.01 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Debt to Equity Ratio | 1.05 | 0.90 | 0.75 | 0.60 | 0.45 | 0.30 | 0.15 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

- BREAK-EVEN ANALYSIS:

| Year Ending (INR Crore) | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Sales | 120.39 | 121.26 | 121.46 | 122.00 | 122.54 | 123.43 | 123.64 | 124.19 | 124.74 | 125.64 | 125.85 | 126.41 | 126.97 |
| Variable Expenses | 2.75 | 2.74 | 6.99 | 7.19 | 7.40 | 7.63 | 7.85 | 8.10 | 8.35 | 8.63 | 8.91 | 9.21 | 9.53 |
| Contribution | 117.64 | 118.51 | 114.47 | 114.81 | 115.15 | 115.80 | 115.79 | 116.09 | 116.38 | 117.00 | 116.94 | 117.20 | 117.44 |
| Fixed Expenses | 22.71 | 23.60 | 23.52 | 23.56 | 23.54 | 23.65 | 23.57 | 23.62 | 23.60 | 23.72 | 23.64 | 23.70 | 23.68 |
| Profit / PBT | 94.92 | 94.91 | 90.95 | 91.25 | 91.60 | 92.15 | 92.22 | 92.47 | 92.78 | 93.28 | 93.30 | 93.50 | 93.76 |
| PV RATIO | 97.71% | 97.74% | 94.25% | 94.11% | 93.96% | 93.82% | 93.65% | 93.48% | 93.30% | 93.13% | 92.92% | 92.71% | 92.50% |
| BEP Sales | 23.25 | 24.15 | 24.95 | 25.03 | 25.05 | 25.21 | 25.17 | 25.27 | 25.30 | 25.47 | 25.44 | 25.56 | 25.60 |
| BEP% (BEP Sales / sales) | 19.31% | 19.91% | 20.55% | 20.52% | 20.45% | 20.42% | 20.36% | 20.35% | 20.28% | 20.27% | 20.21% | 20.22% | 20.16% |

(Continue)

| Year Ending (INR Crore) | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Sales | 127.88 | 128.10 | 128.67 | 129.24 | 130.17 | 130.39 | 130.97 | 131.56 | 132.50 | 132.73 | 133.32 | 133.91 | 134.87 |
| Variable Expenses | 9.87 | 10.21 | 10.58 | 10.97 | 11.39 | 11.81 | 12.26 | 12.74 | 13.24 | 13.76 | 14.32 | 14.90 | 15.51 |
| Contribution | 118.02 | 117.89 | 118.09 | 118.27 | 118.79 | 118.59 | 118.71 | 118.82 | 119.26 | 118.97 | 119.00 | 119.01 | 119.36 |
| Fixed Expenses | 23.81 | 23.73 | 23.80 | 23.78 | 23.92 | 23.84 | 23.92 | 23.90 | 24.06 | 23.98 | 24.07 | 24.06 | 24.23 |
| Profit / PBT | 94.21 | 94.16 | 94.29 | 94.49 | 94.87 | 94.75 | 94.79 | 94.92 | 95.20 | 94.99 | 94.93 | 94.96 | 95.13 |
| PV RATIO | 92.28% | 92.03% | 91.78% | 91.51% | 91.25% | 90.94% | 90.64% | 90.32% | 90.00% | 89.63% | 89.26% | 88.88% | 88.50% |
| BEP Sales | 25.80 | 25.78 | 25.93 | 25.98 | 26.21 | 26.21 | 26.39 | 26.47 | 26.73 | 26.75 | 26.97 | 27.07 | 27.38 |
| BEP% | 20.17% | 20.13% | 20.15% | 20.10% | 20.14% | 20.10% | 20.15% | 20.12% | 20.17% | 20.15% | 20.23% | 20.21% | 20.30% |

- TERM LOAN INPUTS:

| Term Loan Repayment Inputs |  |
| --- | --- |
| Total loan amount | INR 350.93 Crore |
| Rate of Interest | 11% |
| 1st Disbursement | March-25 |
| IDC Start & End Month | March-25 to March-26 |
| IDC Period (construction period) | 12 Month |
| Commencement /Operation Start | 1st April 2026 |
| Moratorium Start & End Month (only interest to pay) | March 2025 to March 2027 |
| Moratorium Period after COD | 12 Month |
| Repayment Start | April-27 |
| Repayment End | March-2047 |
| Repayment Period | 20 Years |

(INR Crore)

| Year Ending | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 1 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Opening Bal | 0.00 | 70.19 | 350.93 | 350.93 | 333.39 | 315.84 | 298.29 | 280.75 | 263.20 | 245.65 | 228.11 | 210.56 | 193.01 | 175.47 |
| Disbursement of loan | 70.19 | 280.75 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Repayment | 0.00 | 0.00 | 0.00 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 |
| Closing Principal o/s | 70.19 | 350.93 | 350.93 | 333.39 | 315.84 | 298.29 | 280.75 | 263.20 | 245.65 | 228.11 | 210.56 | 193.01 | 175.47 | 157.92 |
| Interest | 0.64 | 21.87 | 38.60 | 37.64 | 35.71 | 33.78 | 31.85 | 29.92 | 27.99 | 26.06 | 24.13 | 22.20 | 20.27 | 18.34 |
| IDC | 0.64 | 21.87 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| TL Interest | 0.00 | 0.00 | 38.60 | 37.64 | 35.71 | 33.78 | 31.85 | 29.92 | 27.99 | 26.06 | 24.13 | 22.20 | 20.27 | 18.34 |

(Continue)

| Year Ending | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Opening Bal | 157.92 | 140.37 | 122.83 | 105.28 | 87.73 | 70.19 | 52.64 | 35.09 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Disbursement | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Repayment | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Closing Principal o/s | 140.37 | 122.83 | 105.28 | 87.73 | 70.19 | 52.64 | 35.09 | 17.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Interest | 16.41 | 14.48 | 12.55 | 10.62 | 8.69 | 6.76 | 4.83 | 2.90 | 0.97 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| IDC | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| TL Interest | 16.41 | 14.48 | 12.55 | 10.62 | 8.69 | 6.76 | 4.83 | 2.90 | 0.97 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

- DEPRECIATION SCHEDULE (STRAIGHT  LINE METHOD):

(INR Crore)

| Depreciation Schedule as per Company's Act, 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Particular | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| Building & Civil Works | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 |
| SLM Depreciation | 0.741 | 0.743 | 0.741 | 0.741 | 0.741 | 0.743 | 0.741 | 0.741 | 0.741 | 0.743 | 0.741 | 0.741 | 0.741 |
| Plant & Machinery | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 |
| SLM Depreciation Plant & Machinery | 16.89 | 16.94 | 16.89 | 16.89 | 16.89 | 16.94 | 16.89 | 16.89 | 16.89 | 16.94 | 16.89 | 16.89 | 16.89 |
| Total SLM Depreciation | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 |

(Continue)

| Depreciation Schedule as per Company's Act, 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Particular | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| Building & Civil Works | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 | 23.40 |
| SLM Depreciation | 0.743 | 0.741 | 0.741 | 0.741 | 0.743 | 0.741 | 0.741 | 0.741 | 0.743 | 0.741 | 0.741 | 0.741 | 0.743 |
| Plant & Machinery | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 | 444.52 |
| SLM Depreciation | 16.94 | 16.89 | 16.89 | 16.89 | 16.94 | 16.89 | 16.89 | 16.89 | 16.94 | 16.89 | 16.89 | 16.89 | 16.94 |
| Total SLM Depreciation | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 | 17.63 | 17.63 | 17.63 | 17.68 |

- KEY ASSUMPTIONS & BASIS:

| S. No. | Item | Assumptions and Basis |
| --- | --- | --- |
|  | General | - The projections of the proposed captive hybrid wind-solar power plant are done for the period from FY 2025 to FY 2052, ~25 years, to cover the term loan period as per the industry best practices. It is assumed that the plant will be achieving COD on 1st April 2026. - We have considered both Revenue & cost based model (top to bottom approach) while making the future financial projections. - Revenue modelling has been done based on the net unit generated annually as per defined in the EPC agreement with Opera Energy Private Limited and applicable tariff in the state of Gujrat for Industrial/Commercial Electricity. - Expense modelling has been done based on the terms & conditions mutually agreed by EPC & Company regarding Fixed and variable charges. - The proposed hybrid power plant is assumed to be operational for 360 days for 24 hours annually. |
|  | Revenue Build up | - Company will be generating the revenue in the form of saving from the electricity generation from 36 MW Solar and 27.30 MW Wind Power Plant. - Plant load factor for Solar and Wind are considered as 18.55% and 36.96% respectively as per the EPC agreement. - Degradation factors are considered as 0.55% from 2nd year onwards as per the EPC agreement. Similarly transmission losses are considered as 6.34% including 2.5% of windfarm internal losses. - After multiplying these factors with installed capacity, No. of units Production (Yearly) are determined. After adjusted with transmission losses, Net units Exported annually are determined. - Net units are multiplied by applicable tariff rate of INR 8.75 per unit as per the currently prevailing tariff and Net Revenue is calculated. - Thus the company is expected to generate INR 120.39 Crore annual revenue in FY 2027, which is expected to increase up to INR 134.87 Crore till FY 2052. - Escalation of 1% is considered in applicable tariff rate as informed by client during the projected period. |
|  | Pricing (Average Price Per Unit) | - Applicable tariff rate is considered as INR 8.75 per unit as per the currently prevailing industrial commercial tariff rate per unit in the state of Gujrat. - Escalation of 1% is considered in applicable tariff rate as informed by client during the projected period. |
|  | Capacity Utilization | - The proposed Wind Solar Hybrid power plant will be installed with a combined capacity of 63.30 MW (36 MW DC Solar (~62062 nos. of Solar PV Module) 580Wp of BiN-08-580 type Solar module from Waaree Energies Limited and Suzlon S 120 – (2.1 X 13) 27.30 MW Wind turbine generator (WTG)). - Plant load factor of 18.55% for Solar and 36.96% for wind are considered in the initial operating year and degradation factor of 0.5% y-o-y basis from 2nd year onwards is taken as per the EPC agreement. |
|  | Capital Expenditure | - M/s Sai Infinium Limited has executed an EPC/Techno-Commercial contract with Opera Energy Private Limited for Captive hybrid power plant for 27.30 (13 x 2.1) WTG with 36.96% PLF & 36 MW DC Solar 18.55% PLF. - Opera Energy Limited, is a prominent Gujarat based Specialize turnkey EPC solution provider for Wind-Solar Hybrid projects with battery storage, serving IPP and C&I clients under Capex, Captive, Group Captive, and 3rd Party Sales models. Company has been appointed Opera as an EPC through entering into a legal agreement dated 7th Jan 2025, who will be the solution provider for the proposed 63.30 MW hybrid project to implement on turnkey basis within 13 months of zero and design, develop, transfer and maintain the solar and wind hybrid power plant on behalf of M/s Sai Infinium Limited as an industrial customer. - The proposed wind solar hybrid power plant will not be having major building and civil works. Only land development and foundation work will be there as per the requirement of WTG and PV modules. Out of total EPC cost of INR 438.81 Cr., ~5% i.e. INR 21.94 Cr. will be the cost of Civil work, and rest 95% i.e. INR 416 .87 Cr. will the cost for proposed plant & machinery, which seems to be reasonable after considering the infrastructure of the plant. However we are relied upon the data/information and EPC agreement shared with us by the client in this regard. - As per the data/information provided by the client, applicable Interest during Construction (IDC) is 1%. As per the proposed Loan repayment schedule, company is required to pay INR 25.22 Crore as IDC from March 2025 to 31st March 2026 (12 months). - Preliminary & Pre-Operative Expenses has been considered based on the estimate of company’s resources involvement as INR 4.39 Crore, which is 1% of hard cost of the project. However, Company did not provide us any invoices/bills against these tentative costs considered. We recommend that the bank/financial institutions advice the company to submit actual cost based on the final quotations/invoices/bills. This will help validate the assertion of different costs considered by the client. - Contingency cost of INR 2.19 Crore has been considered based on general assumption and professional experience (~0.5 of Hard Cost of the Project). - As per the EPC agreement, the proposed captive hybrid power plant will be setting up with an initial investment of INR 467.91 Crore including EPC, IDC, and Contingencies & Preliminary & Pre-operative expenses. - Thus, ~INR 7.39 Crore per MW is the expected CAPEX for the proposed 63.30 MW Wind Solar Hybrid power plant, which seems to be reasonable and in the line with industrial benchmark. - Per MW cost of Solar and Wind power plants are in the line with market trends. The cost of a 1 MW solar power plant in India is typically between ₹4 and ₹5 crores. The cost depends on several factors, including: Solar panels, Land, Balance of system (BOS) components, Installation challenges, Batteries. For reference Amplus Solar (https://amplussolar.com/blogs/1mw-solar-power-plant) and Waree (https://waaree.com/blog/5-mw-solar-power-energy-plant-in-india-profit-cost-land-requirement/) are known name in this field. Similarly, According to a report by the Ministry of New and Renewable Energy in India, the capital cost of wind power projects in India ranges from INR 5.5 crore per MW to INR 6.5 crore per MW (approximately USD 750,000 to USD 880,000 per MW) for onshore wind projects, and from INR 8.5 crore per MW to INR 12 crore per MW (approximately USD 1.2 million to USD 1.6 million per MW) for offshore wind project. (https://www.linkedin.com/pulse/india-wind-energy-potential-quesrow#:~:text=According%20to%20a%20report%20by,INR%2012%20crore%20per%20MW%20). |
|  | Expenses | - O&M Expenses are considered as INR 1,26,00,000 and INR 3,00,84,600 yearly for Solar and Wind Plant respectively as per the EPC agreement. As per EPC, 2 years of O&M will be free. An escalation of 5% in O&M are considered for Solar and Wind Plant respectively both as per the terms & conditions defined in EPC agreement. - Banking Charges and Multi-Wheeling Charges are considered as 0.20 per unit as defined in the EPC agreement. - State Load Despatch Centre (SLDC) are considered as INR 614.45 per day as per the government policy and terms & conditions mentioned in EPC agreement. - Transmission charges are considered as INR 4400 per MW Per day as per the government policy and terms & conditions mentioned in EPC agreement. - Forecasting & Scheduling, GEDA Certification Charges and GETCO Feeder Bay Maintenance Charges are considered as INR 1500 per MW per month, INR 12000 per MW per year and INR 60000 per MW per year respectively as per EPC agreement. - Lease rental for land are INR 50 lakhs per acre and INR 3 lakhs per acre for solar and wind respectively as per the EPC agreement. An escalation of 7% every 3 year is considered as per EPC terms & condition. - Insurance expenses are considered as 0.10 of WDV net block y-o-y basis. |
|  | Term Loan | - The project is proposed to be funded through a term loan of INR 350.93 crores and promoter’s margin of INR 116.98 crores. - Interest rate has been considered as 11% on the term loan. - Loan repayment period will be for 20 years as per informed by bank/client/financial Institution. |

Key Findings:

      - Average DSCR, EBIDTA margin, EBIT margin is 2.68, 87.54%, and 73.67% respectively during the estimated period.

      - D.S.C.R of the proposed Wind Solar Hybrid Power plant is found highly sensitive with respect to any downside fluctuation in the projected revenue.

      - The company is having a positive NPV and IRR of INR 244 Crore and 16.99% respectively from C.OD to loan repayment period while it may vary with changes in the assumptions & micro and macro-economic trends considered as on date.

      - The proposed project is having a payback period of 7.05 years.

      - Based on the above key financial ratios of the proposed Project during the forecasted period shows that the project appears financially viable if the promoters of the project are able to maintain assumed capacity utilization, revenue and can contain cost as assumed above in the calculation.

| PART L | CONCLUSION |
| --- | --- |

Based on the technological, economical and market analysis done above, various assumptions of sectoral trends taken, product pricing to be adopted by the company, the Project appears to be Techno-commercially viable subject to the risks, threats, weaknesses, limitations of the product as detailed previously.

As per financial projections for the estimated period, Average DSCR, EBITDA Margin and EBIT Margin of the project are 2.68, 87.54% and 73.67% respectively, where higher DSCR is the indicator of the project capability to pay out its outstanding debt and EBITDA margin shows the capability of the project to generate the operating profits over the forecasted period. Also the project is having the payback period of 7.05 Years in the line with sectoral trends.

The proposed Wind Solar Hybrid project is having a positive NPV and IRR as INR 244 Crore and 16.99% respectively from C.O.D till loan repayment period as the industry is expectedly growing at a CAGR of 8.77% during the forecasted period (2023-32). While it is not avoidable that the future projections may change in the upcoming years due to various factors impacting the operation, managerial, financial efficiency and economies of scale of the project.

While it would be depending on the management’s capability in future that how efficiently company adopts marketing and advertisement strategy, supply chain and carry out inventory & resource management to achieve higher profitability. After considering the foreseen demand of the Power sector domestically and globally, various initiatives taken by the government, financial analysis of the project based on the assumptions taken over the projected period, it appears reasonable to comment that the proposed project is “Technically and Economically” Viable subject to current assumptions considered and occurring the same in the upcoming years same as considered during the forecasted period which is dependent on the sincerity and efforts of the management and various micro and macroeconomic & industry situation.

We have tried our level best to analyse the Project techno-economic feasibility of the Project based on the Industry research, Project information and various futuristic assumption taken within the limitations and challenges came in front of us. However achieving the financial milestones depends on the ability, sincerity and efforts of the company, promoters and its key management to maintain the projected revenue level Y-o-Y basis keeping the fact in mind that the project is found sensitive with respect to the down side fluctuation in the revenue.

| Declaration | - The undersigned does not have any direct/indirect interest in the above property/project/Company. - The information furnished herein is true and correct to the best of our knowledge, logical and scientific assumptions. - This TEV Report is carried out by our Financial Analyst team on the request from M/s Sai Infinium Limited. - Meeting of Financial projections will be subject to the market & economy stability factors, judicious business operations and proper & timely implementation of the project and putting proper plan for achieving high productivity, efficiency and achieving cost saving benefits to increase profitability. - We have submitted TEV report to M/s Sai Infinium Limited. |
| --- | --- |
| Number of Pages in the Report | 107 |
| Enclosed Documents | Disclaimer & Remarks 102-105 |
| Place | Noida |
| Date | 10th January 2025 |

| FOR ON BEHALF OF M/S. R.K. ASSOCIATES VALUER & TECHNO ENGINEERING CONSULTANTS PVT. LTD. |  |  |
| --- | --- | --- |
| SURVEYED BY | PREPARED BY | REVIEWED BY |
| Mr. Shahid Ji | Mr. Gaurav Kumar | Mr. Rachit Gupta |

| PART M | DISCLAIMER ¦ REMARKS |
| --- | --- |

      - No employee or member of R.K Associates has any direct/ indirect interest in the Project.

      - This report is prepared based on the copies of the documents/ information which the Bank/ Company has provided to us out of the standard checklist of documents sought from them and further based on our assumptions and limiting conditions. The client/owner and its management/representatives warranted to us that the information they supplied was complete, accurate and true and correct to the best of their knowledge. All such information provided to us has been relied upon in good faith and we have assumed that it is true and correct in all respect. I/We shall not be liable for any loss, damages, cost or expenses arising from fraudulent acts, misrepresentations, or wilful default on part of the owner, company, its directors, employee, representative or agents. Verification or cross checking of the documents provided to us from the originals or from any Govt. departments/ Record of Registrar has not been done at our end since this is beyond the scope of our work. If at any time in future, it is found or came to our knowledge that misrepresentation of facts or incomplete or distorted information has been provided to us then this report shall automatically become null & void.

      - Legal aspects for e.g. investigation of title, ownership rights, lien, charge, mortgage, lease, sanctioned maps, verification of documents, etc. have not been done at our end and same has to be taken care by legal expert/ Advocate. It is assumed that the concerned Lender/ Financial Institution has satisfied them with the authenticity of the documents, information given to us and for which the legal verification has been already taken and cleared by the competent Advocate before requesting for this report. I/ We assume no responsibility for the legal matters including, but not limited to, legal or title concerns.

      - This report is a general analysis of the project based on the scope mentioned in the report. This is not an Audit report, Design document, DPR or Techno feasibility study. All the information gathered is based on the facts seen on the site during survey, verbal discussion & documentary evidence provided by the client and is believed that information given by the company is true best of their knowledge.

      - This Techno Economic-Viability study is prepared based on certain futuristic assumption which are intra dependent on economic, market and sectorial growth condition in future and socio-economic, socio-political condition at macro and micro level.

      - Meeting of assumption and financial ratio will entirely depend on the sincerity and efforts of the company, promoters and its key managerial performance.

      - All observations mentioned in the report is only based on the visual observation and the documents/ data/ information provided by the client. No mechanical/ technical tests, measurements or any design review have been performed or carried out from our side during Project assessment.

      - This report has been diligently prepared by our techno-financial team to the best of their ability. However, it's important to note that the recommendations provided in this Total Economic Viability (TEV) assessment do not imply an endorsement, validation, or certification of the accuracy or completeness of the disclosed information by the involved stakeholders. Furthermore, we do not claim or endorse that the opinions presented herein are the sole best course of action for decision-makers to follow. There may exist additional approaches and inputs that have not been covered within this report or fall outside the scope of this report.

      - Bank/FII should ONLY take this report as an Advisory document from the Financial/ Chartered Engineering firm and its specifically advised to the creditor to cross verifies the original documents for the facts mentioned in the report which can be availed from the borrowing company directly.

      - In case of any default in loans or the credit facility extended to the borrowing company, R.K Associates shall not be held responsible for whatsoever reason may be and any request for seeking any explanation from the employee/s of R.K Associates will not be entertained at any instance or situation.

      - The documents, information, data provided to us during the course of this assessment by the client are reviewed only up to the extent required in relation to the scope of the work. No document has been reviewed beyond the scope of the work.

      - This report only contains general assessment & opinion as per the scope of work evaluated as per the information given in the copy of documents, information, data provided to us and/ and confirmed by the owner/ owner representative to us at site which has been relied upon in good faith. It doesn’t contain any other recommendations of any sort including but not limited to express of any opinion on the suitability or otherwise of entering into any transaction with the borrower.

      - We have relied on data from third party, external sources & information available on public domain also to conclude this report. These sources are believed to be reliable and therefore, we assume no liability for the truth or accuracy of any data, opinions or estimates furnished by others that have been used in this analysis. Where we have relied on data, opinions or estimates from external sources, reasonable care has been taken to ensure that such data has been correctly extracted from those sources and /or reproduced in its proper form and context, however still we can’t vouch its authenticity, correctness or accuracy.

      - This Report is prepared by our competent technical team which includes Engineers and financial experts & analysts.

      - This is just an opinion report and doesn’t hold any binding on anyone. It is requested from the concerned Financial Institution which is using this report for taking financial decision on the project that they should consider all the different associated relevant & related factors also before taking any business decision based on the content of this report.

      - All Pages of the report including annexure are signed and stamped from our office. In case any paper in the report is without stamp & signature then this should not be considered a valid paper issued from this office.

      - Though adequate care has been taken while preparing this report as per its scope, but still we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it shall be considered that the report is complete in all respect and has been accepted by the client up to their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

      - Defect Liability Period is 15 DAYS. We request the concerned authorized reader of this report to check the contents, data and calculations in the report within this period and intimate us in writing if any corrections are required or in case of any other concern with the contents or opinion mentioned in the report. Corrections only related to typographical, calculation, spelling mistakes, incorrect data/ figures/ statement will be entertained within the defect liability period. Any new changes for any additional information in already approved report will be regarded as additional work for which additional fees may be charged. No request for any illegitimate change in regard to any facts & figures will be entertained.

      - R.K Associates encourages its customers to give feedback or inform concerns over its services through proper channel at valuers@rkassociates.org in writing within 15 days of report delivery. After this period no concern/ complaint/ proceedings in connection with the Techno- Economic Viability Study Services will be entertained due to possible change in situation and condition of the subject Project.

      - Our Data retention policy is of ONE YEAR. After this period, we remove all the concerned records related to the assignment from our repository. No clarification or query can be answered after this period due to unavailability of the data.

      - This Techno Economic Viability Study report is governed by our (1) Internal Policies, Processes & Standard Operating Procedures, (2) Information/ Data/ Inputs given to us by the client and (3) Information/ Data/ Facts given to us by our field/ office technical team. Management of R.K Associates never gives acceptance to any unethical or unprofessional practice which may affect fair, correct & impartial assessment and which is against any prevailing law. In case of any indication of any negligence, default, incorrect, misleading, misrepresentation or distortion of facts in the report then it is the responsibility of the user of this report to immediately or at least within the defect liability period bring all such act into notice of R.K Associates management so that corrective measures can be taken instantly.

      - R.K Associates never releases any report doing alterations or modifications from pen. In case any information/ figure of this report is found altered with pen then this report will automatically become null & void.

      - If this report is prepared for the matter under litigation in any Indian court, no official or employee of R.K Associates will be under any obligation to give in person appearance in the court as a testimony. For any explanation or clarification, only written reply can be submitted on payment of charges by the plaintiff or respondent which will be 10% of the original fees charged where minimum charges will be Rs. 15,000/.

EXTRACTS OF IMPORTANT STATUTORY APPROVALS PROVIDED BY THE CLIENT