File No.: VIS (2024-25)-PL333-292-386		       	                          Dated: 04.09.2024

TECHNO-ECONOMIC VIABILITY

STUDY REPORT

OF

66.20 MW WIND-SOLAR HYBRID POWER PLANT

(41 MW DC Solar + 25.20 MW Wind)

SETUP BY

M/S SAI BANDHAN INFINIUM LIMITED

REPORT PREPARED FOR

M/S IMPETUS FINSOL LLP ADDRESS: OFFICE NO. 903-A, TITENIUM CITY CENTER, NR. SACHIN TOWER 100 FEET RING ROAD, ANAND NAGAR, SATELITE, MANEKBAG AHMEDABAD, GUJARAT, 380015 INDIA

**Important - In case of any query/ issue or escalation you may please contact Incident Manager Valuers@rkassociates.org. We will appreciate your feedback in order to improve our services.

NOTE: As per IBA Guidelines please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct.

IMPORTANT NOTICE

COPYRIGHT FORMAT: This report is prepared on the copyright format of R. K. Associates Valuers & Techno Engineering Consultants (P) Ltd. (R. K. Associates) to serve our clients with the best possible information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R. K. Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format or report or any of its content/ information/ data by any organization or individual other than R.K Associates will be seen as an unlawful act and necessary legal action can be taken against the defaulters.

This report is intended for the sole use of the intended recipient/s and contains material that is STRICTLY CONFIDENTIAL AND PRIVATE.

DEFECT LIABILITY PERIOD: In case of any query/ issue or escalation you may please contact Incident Manager at valuers@rkassociates.org. Though adequate care has been taken while preparing this report as per its scope, but still we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it will be considered that the report is complete in all respect and has been accepted by the client up to their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

Part O: R. K. Associates Important Disclaimer and Remarks are integral part of this report and Feasibility assessment is subject to this section. Reader of the report is advised to read all the points mentioned in these sections carefully.

| TABLE OF CONTENTS |  |  |
| --- | --- | --- |
| SECTIONS | PARTICULARS | PAGE NO. |
| Part A | Report Summary | 4 |
| Part B | INTRODUCTION |  |
|  | - About the Report | 6 |
|  | - Executive summary | 6 |
|  | - Purpose of the Report | 8 |
|  | - Scope of the Report | 8 |
|  | - Methodology/ Model Adopted | 9 |
|  | - Data Information received from | 9 |
|  | - Documents/ Data Referred | 10 |
| Part C | Company Profile |  |
|  | - Company Overview | 11 |
|  | - Proposed Shareholding Pattern | 12 |
|  | - Promoters/Directors Profile | 12 |
| Part D | Proposed Unit’s Infrastructure Details |  |
|  | - Proposed Plant Location | 16 |
|  | - Google Map Location | 17 |
|  | - Layout Plan | 18 |
|  | - Land Details | 19 |
|  | - Site pictures | 19 |
|  | - Building & Civil Works | 22 |
|  | - Plant and Machinery/ Equipment details | 24 |
|  | - Miscellaneous Assets | 27 |
|  | - Utilities | 28 |
| Part E | Project Technical details |  |
|  | - Capacity of Proposed Bio CNG Plant | 32 |
|  | - Process Description | 32 |
|  | - Basic Architecture: Flow Chart Of The Bio CNG Plant | 35 |
|  | - Technical Specification of the Proposed CBG Facility | 35 |
|  | - Technology Used | 37 |
|  | - Technological Assessment | 38 |
|  | - Testing Standards For Production | 39 |
|  | - Manpower | 40 |
| Part F | Product Profile |  |
|  | - Introduction | 42 |
|  | - Product Category | 42 |
|  | - Pricing Strategy | 44 |
|  | - Marketing, Selling & Distribution Plan | 47 |
| Part G | Feedstock Analysis & Supply | 49 |
| Part H | Industry Overview & Analysis | 55 |
| Part I | SWOT Analysis | 59 |
| Part J | Project Cost and Means of Finance | 61 |
| Part K | Project Implementation Schedule | 64 |
| Part L | Statutory Approvals ¦ Licences ¦ NOC | 66 |
| Part M | Company’s Financial Feasibility | 68 |
| Part N | Conclusion | 90 |
| Part O | Disclaimer ¦ Remarks | 92 |

| PART A | REPORT SUMMARY |
| --- | --- |

| S. No. | PARTICULAR | DESCRIPTION |
| --- | --- | --- |
|  | Name of the Company: | M/s Sai Bandhan Infinium Private Limited |
|  | Registered Address: | 3rd Floor, 2137, Bansal House, Nr. Golden Arc, Atabhai Chowk, Bhavnagar, Gujarat, India, 364002 |
|  | Project Name | 91 MW DC [70 MW AC] Ground Mounted Captive Solar Power Plant |
|  | Project Location: | (Mithipaladi, Banaskantha (51 MW)/ Runi, Banaskantha (20 MW) and Dhekwadi, Banaskantha (20 MW), Gujarat |
|  | Project Type: | 91 MW DC Ground Mounted Captive Solar Power Plant (Open Access) |
|  | Project Industry: | Renewable Energy |
|  | Product Type / Deliverables: | Power Generation |
|  | Report Prepared for Organization: | M/s. Impetus Finsol LLP |
|  | TEV Consultant Firm: | M/s. R.K Associates Valuers & Techno Engineering Consultants (P) Ltd. |
|  | Report type: | Techno-Economic Viability Report |
|  | Purpose of the Report: | To assess Technical & Economic Viability for the purpose of seeking external financial assistance to setup captive Solar Power Plant. |
|  | Scope of the Report: | To assess, evaluate & comment on Technical, Economical & Commercial Viability of the Project as per data information provided by the client, independent Industry research and data/ information available on public domain. |
|  | Date of Report: | 4th September, 2024 |
|  | Documents referred for the Project: | - PROJECT INITIATION DOCUMENTS: - Detailed Project Report - Financial Projections of the Project - Project proposed Schedule - Statutory Approval Details - Layout and Master Plan - PROCUREMENT DOCUMENTS: - List of Plant & Machinery along with acquisition costs for the same - List of Expected Raw material Supplier - Process Flow Chart - Sanction/proposed map of the sites - Lease/Sale deeds of the Land - STATUTORY APPROVALS, LICENCES & NOCs - MSME UDYAM Registration Certificate - NOC from Gram Panchayat - NOC/Application for Ground water - Consent to establish approval |
|  | Means of Finance: | Equity & Debt (D/E Ratio 3.00 TPC) |
|  | Key Financial Indicators: | Key Indicators; Value. Average DSCR; 2.80. Average EBITDA Margin; 66.82%. Avg. PAT Margin; 33.76%. NPV & IRR; INR 381.17 Cr. & 17.62%. Payback Period; 6.94 years. |

Note: Above financial indicators are based on the financial projections of the proposed project provided by the firm and assessment and analysis of the same done by us.

| PART B | INTRODUCTION |
| --- | --- |

- ABOUT THE REPORT:

This is a Techno-Economic Viability Study Report of the proposed 91 MW [DC] Ground mounted Captive Solar Power plant at (Mithipaladi, Banaskantha (51 MW)/ Runi, Banaskantha (20 MW) and Dhekwadi, Banaskantha (20 MW), Gujarat.

- EXECUTIVE SUMMARY:

Government of India has pledged for transition to clean energy in power sector through nationwide targets with commitment towards Nationally Determined Contribution of 50% of cumulative electric power installed capacity from non-fossil fuel-based energy resources by the year 2030. Government of Gujarat is playing a pivotal role in this energy transition. State has successfully demonstrated its commitment towards clean energy with installed Renewable Capacity of 21.6 GW at present in which the addition of about 12 GW has taken place during last 5 years.

Taking cognizance of the generational shift occurring in electricity sector, the need for expediting efforts for de-carbonization and in an endeavour to embrace renewable energy more effusively, Government of Gujarat has notified a Renewable Energy Policy-2023 (Reference: GUJARAT RENEWABLE ENERGY POLICY- 2023 G.R. No. REN/e-file/20/2023/0476/B1 Sachivalaya, Gandhinagar, Date: 04/10/2023)  for further encouraging setting up of renewable generation projects based on Wind, Solar and Wind-Solar Hybrid technologies. Ground mount solar under the policy:

- Solar projects can be setup in a solar park, or outside the solar park, on government revenue land, or on private land. Government land or land available with the State Nodal Agency shall be made available to the RE developers as per Clause No. 28 of this Policy.

- The Distribution Licensees may procure from solar power projects in accordance with the Clause No. 16 of this Policy.

- Wheeling of power for captive use or third party sale shall be allowed on payment of charges as per Clause No.15 and energy settlement will be as per Clause No. 14 of this policy.

This executive summary outlines the development of a 91 MW DC [70 MW AC] ground mounted Solar PV power plant for captive purpose located in Gujarat (Mithipaladi, Banaskantha (51 MW)/ Runi, Banaskantha (20 MW) and Dhekwadi, Banaskantha (20 MW), Gujarat). The project, initiated by M/s Sai Bandhan Infinium Private Limited, aims to harness solar energy to meet the organization's growing electricity needs sustainably and to optimize the operation cost while taking the existing Rolling mill to full capacity.

As a parent company M/s Sai Bandhan Infinium Private Limited has been venturing into shipping and ship-breaking industry since last 15 years. The company has forayed into integration with Bandhan TMX with the production capacity of 20,000 MT per month.

IMAGE OF BANDHAN TMX PLANT

The company is having a modern integrated steel manufacturing unit at Bhavnagar – western India, which has the facility of manufacturing of finished steel long product from captive steel semis with adequate refining facility through LRF (Ladle refining furnace) to ensure flawless production of refined steel. This highly sophisticated integrated steel plant facility comprising steel melting shop (SMS) equipped with electric furnace & ladle refining furnace, Continuous Billet Casting unit, Rolling mill with Block mill and German Technology (Thermex). Brief features of integrated plant are as follows:

- 25 Ton X 2 Electric furnace.

- 30 Ton X 1 Ladle refining furnace (for liquid steel refining)

- 3 stand: 6X11 M radius CCM (with copper mould tube)

- Standalone rolling mill equipped with block mill, only it’s kind of mill in western India after TATA.

- Well-equipped in-house laboratory.

As per the data/information provided by the client, Company manufacture TMX bars and structural steel under the brand name “Bandhan TMX” through hot charging rolling mill with latest Tempcore quenching technology under licensing of CRM, Belgium’s Tempcore cooling technology. Company produces their Captive raw material (Billet) from sponge iron by using this technology for manufacturing of TMX bars. Company manufactures as well as deal in the following items on regular basis:

- Thermo Mechanical Treated (TMX) Bars: Fe 500 D, Fe 550, Fe 550 D, Fe 615 – 8mm to 32 mm.

- M.s Billet.

BANDHAN TMX BLOCK MILL

Historical financial position of the company is shown in the below table as on 31st March 2023 & 31st March 2022:

| Particular | As on 31st March 2023 (Lakhs) | As on 31st March 2022 (Lakhs) |
| --- | --- | --- |
| Total Assets | 19,595.46 | 18,746.10 |
| Long term borrowings | 4741.67 | 2257.94 |
| Short term borrowings | 3493.09 | 9061.62 |
| Turnover | 51,010.50 | 14,940.98 |
| PAT | 83.58 | 233.17 |
| Cash flow at the end | 28.34 | 21.52 |

As per the recent electricity bills shared the by client, Company is having a sanction load of 33700 KW at present and this integrated manufacturing plant is running for 8 hours per day where it consumes ~60 lakhs units per month to operate at this scope and scale. Current tariff of electricity is INR 5.96 per unit (subsidized rate as the plant operates only from 10 pm to 6 am)

As per the internal assessment done by the company, if management decide to run the integrated steel manufacturing unit for 24 hours per day, consumption of power is expected to be more than 1.8 Crores units a month and as the company plans to operate the factory for 24 hours the charges will go up to INR 9.15 per unit. And therefore, the promoters of the Company has planned installation of solar project to offset the electricity consumption while the plant operates for 3 shifts.

The plant will feature high-efficiency solar panels with a combined capacity of 91 MW DC. It will utilize advanced photovoltaic (PV) technology and include a state-of-the-art monitoring system to optimize performance and maintenance. With an initial investment of INR 390.53 Crore, the project is expected to achieve a return on investment (ROI) within 6.94 years. Annual savings on energy costs are estimated at ~INR 53.87 Crore, with a payback period of 6.94 years.

| Particular | Hours | Units per month | INR/Unit | Monthly Expense | Yearly Expense |
| --- | --- | --- | --- | --- | --- |
| Current Running Hours | 8 | 60,00,000 | 5.96 | 3,57,60,000 | 42,91,20,000 |
| Proposed Hours | 24 | 1,80,00,000 | 9.15 | 16,47,00,000 | 1,97,64,00,000 |
| Solar Installation | 24 | 1,23,00,000 | 5.50 | 6,76,50,000 | 81,18,00,000 |
| Net-off (Savings) |  |  |  |  | 53,87,40,000 |

As assessed above, Company is expected to save up to INR 53.87 Crore annually by installing the proposed 91 MW DC captive solar power plant. The primary objectives of the solar power plant are to reduce annual electricity costs by 40%, decrease the carbon footprint by 30,000 tons per year, and ensure a reliable and renewable energy source for M/s Sai Bandhan Infinium Private Limited's operations.

This is a 91 MW DC (70 MW AC) ground mounted Captive solar plant with open access, so whatever we will generate here from solar plant, Gujarat Energy Transmission Corporation Limited (GETCO), power transmission company in the state of Gujarat, India will provide same units credit to the company’s electricity bill unit to unit basis.

Further, the proposed solar plant is expected to reduce CO2 emissions by 33,000 tons annually, contributing significantly to M/s Sai Bandhan Infinium Private Limited's sustainability goals. Additionally, the project will create ~150 local jobs during the construction phase and ~25 permanent positions for ongoing operations & maintenance. Plant is expected to be operational from 1st January, 2026 after having a 13 months implementation period from December 2024 to December 2025.

For setting up the Solar power plant, Company has

For the sale of the produced CBG, the company has already secured a LOI from Indian Oil Corporation limited under SATAT initiative to promote Compressed Bio-Gas as an alternative, green transport fuel. (Ref No.: Indian Oil/SATAT/01/3589 Date: 03.11.2023) for which company has paid bank guarantee if INR 5.00 lakhs 19th December 2023. Commercial agreement will be signed before C.O.D between the parties.

As per the revised agreement dated 17th July 2024 provided by the client, Company has appointed an ISO 9001 certified Ghaziabad based solution provider M/s Vimal Organics Ltd as EPC consultant. As per the scope of work mentioned in the agreement, M/s Vimal Organics Ltd will be supplying Equipment, Plant & Machinery, will furnish Building & Civil work and will provide its services for electrical, instrumentation & data collection work.

As per the land deed dated 19th June 2024 shared by the client, Company has procured 5.048 Acre (2.043 Hectare) agricultural land at  Khata No, 208, 42, 226 Khasra No. 161/1, 160, 157 Village- Reda Harsana, Tehsil - Un, District- Shamli 247778. Company is required to apply for Change of land use (CLU) certificate from the respective authority for setting up the proposed Bio-CNG plant at this agricultural land.

Proposed layout plan has been prepared by the appointed technical consultant Mr. Naman (M/s Star Projects Renewable Resources Private Limited) on 9th May 2024. As per the shared data/information by the client, NOC from the Gram Panchayat has already been taken by the company on 25th October 2023 (Ref: Gram Pradhan - Titu Kumar Gram Panchayat - Harsana, Development Block – Un, District Shamli). Company need to obtain approved layout plan.

As per data/information provided to us, the company has obtained some Statutory Approvals/NOC’s such as NOC from village panchayat, Consent to Establish, PESO approval etc. from the respective authorities (Refer the section Statutory Approval in the later part of the report).

During the site visit, we found that the proposed land is a vacant agricultural land which is not demarcated and work on the Project has not been started yet. As per informed by client, land development work will start soon. (Kindly refer the site pictures captured during the survey attached in the later section of the report).

As per the provisional estimation of power shared by the client, ~450 KWA of power load connection will be required to run the proposed CBG plant. Currently, the company is in the process to apply for power load connection. NOC for ground water extraction has been applied by the company on 13th November 2023 (Application Number: SHML1123NIN0034). Company has planned to achieve the C.O.D by 1st October 2025.

Further, the cost of the proposed project from scratch to trial run is being estimated as INR 390.53 Crore, which is proposed to be funded through promoter’s equity of INR 97.63 Crore and bank loan of INR 292.90 Crore.

At present, the company is in discussion with Financial Institutions to fund the project through a term loan of INR 292.90 Crore. In this regard M/s Impetus Finsol LLP has appointed R.K. associates to assess the Techno-Economic Viability of the proposed Bio-CNG production plant. The company plans to achieve the financial closure by December, 2024 (expected).

- PURPOSE OF THE REPORT:

To assess Project’s Technical and Financial Feasibility for Client’s requirement.

- SCOPE OF THE REPORT:

To only assess, evaluate & comment on Technical & Financial Feasibility of the proposed Bio-CNG generating plant being set up by M/s Superior Agro Ventures Private Limited as per the data/information provided by the company.

NOTES:

- Project status is taken as per the Site inspection carried out by our survey team.

- Scrutiny about the company, background check, and credibility, credit worthiness of the company or its promoters is out-of-scope of this report.

- Any verification of the documents/ information from originals/ source is out-of-scope of this report.

- This report is only an opinion in respect to Technical and Financial Feasibility of the project as per the future Projections provided by the firm and independent analysis done by us and doesn’t contains any recommendations including taking decision on the loan or any other financial exposure.

- This is not an audit activity of any kind. We have relied upon the data/ information shared by the company in good faith.

- Any review of the existing business of the promoters is out of scope of this report.

- Detailed cost estimation or detailed cost vetting is out of scope of the project.

- This is not a Detailed Project Report or a detailed design or architecture document. Land and property details mentioned in the report is only for illustration purpose as per the information provided to us by the client. The same doesn’t tantamount for taking any responsibility regarding its legality, ownership and conforming to statutory norms.

- METHODOLOGY/ MODEL ADOPTED:

- Data/ Information collection.

- Review of Data/ Information collected related to TEV study.

- Independent review & assessment of technology used and financial projections provided by the company.

- Projections of Revenue, P&L, Balance Sheet, Working Capital Schedule, Depreciation Schedule, Loan Schedule as per the inputs given by the company and assessed by us

- Calculation of key financial indicators and ratio analysis including DSCR, NPV & IRR and payback period of the project.

- Report compilation and Final conclusion.

- DATA/ INFORMATION RECEIVED FROM:

All the data/Information has been received from Mr. Amit Rana (CEO) and the required details about him shown in the below table:

| Particulars | Details |
| --- | --- |
| Designation | CEO |
| Company | M/s Superior Agro Ventures Private Limited |
| Email Address | amitrana2002@gmail.com |
| Contact No. | +91-9911351936 |

- DOCUMENTS / DATA REFFERED:

- Detailed Project Report and Promoters Profile

- Financial Projections of the proposed Bio CNG generating project.

- Production flow chart,

- Product profile along with Pricing Strategy etc.

- Long term Raw Material Supply agreement with FPO.

- Selling, Marketing & Distribution Plan, LOI with the OMC.

- Site/Layout Plan

- Sale/Lease deed of the land

- Quotation/Contract agreement with EPC consultant along with details of Plant & Machinery.

- Certificates of Statutory approvals/NOC’s.

- Survey Report.

| PART C | COMPANY PROFILE |
| --- | --- |

- COMPANY OVERVIEW:

As per certificate of incorporation shared by the client/company, M/s Superior Agro Ventures Private Limited was incorporated on 4th August, 2022 as per the Companies Act, 2013 as a Non-government company limited by shares. Below table shows the incorporation details of the company:

| Incorporation Details of the Company |  |
| --- | --- |
| Particular | Description |
| Company Name | M/s Superior Agro Ventures Private Limited |
| CIN | U15490PB2022PTC056613 |
| Date of Incorporation | 4th August 2022 |
| Registration Number | 056613 |
| ROC Name | ROC Chandigarh |
| Company Category | Company limited by shares |
| Company Subcategory | Non-government company |
| Class of Company | Private |
| Registered Address | Back Side Old Grain Market, Railway Road, Opposite Water Pump, Kapurthala, Punjab, India, 144601 |
| Authorized Capital | INR 5,00,00,000 |
| Paid up Capital | INR 5,00,00,000 |
| Date of last AGM | 30/09/2023 |
| Date of Balance Sheet | 31/03/2023 |
| Company Status | Active |

Source: Information extracted from MCA website & public domain

As per the amended Memorandum of Association (MoA) on 8th Feb 2024 shared by the client, the company has changed its main objective to carry on the business to produce & sale of Biofuels such as biogas, Bio CNG, Ethanol, Fermented organic manure and Bio Fertilizer for selling to marketing companies or end users and to carry on the business of producers, refiners, processors, Fuel & Gas sales networks, buyers, sellers, distributers, importers, exporters, traders, agents, stockiest, sell & supply of bio energy or any other energy from conventional/non-conventional energy by Biomass, Hydro, thermal, windmill on commercial basis, as civil contractor & engineers, builders etc.

The company is categorised as micro enterprise with Udyam Registration Number UDYAM-MP-21-0006430 dated 30th June 2023. In this company, the promoters have proposed to setup 6,000 Kg/Day of Bio-CNG (compressed biogas) plant along with 24 Ton/day of fermented solid organic fertilizer.

- PROPOSED SHAREHOLDING PATTERN:

Promoters of M/s Superior Agro Ventures Private Limited Mrs. Jaivil Rana and Mrs. Goel are the major shareholders also in the company at present.  As per the data/information provided by the client, shareholding pattern of the company is shown in the table below as on 25th July 2024:

| Proposed Shareholding Pattern as on 25th July 2024 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name Of Shareholders | Father's Name | Address | Type Of Shares | Proposed Shareholding | % Shareholding |

Source: Data/Information provided by the client.

- KEY PROMOTER’S/DIRECTORS PROFILE:

Mrs. Jaivil Rana and Mrs. Mini Panwar are the promoters of M/s Superior Agro Ventures Private Limited as per information available on MCA and both are holding directorship also in the company. As per data/information provided by the client about the promoters & directors, below table illustrate the educational & professional experience of the promoters along with the Address, DIN and contact details:

| Name | Designation/DIN | Address & Contact Details | Appointment Date | Qualifications/Experience |
| --- | --- | --- | --- | --- |
| Mrs. Jaivil Rana (52 Years) | Director DIN: 02013601 | B1/09, Silver City2, Sector Pi2, Greater Noida 201308 G B Nagar, UP +91- 9319061936 (jaivilrana24@gmail.com) | 04/08/2022 |  |
| Mrs. Mini Panwar | Additional Director DIN: 10449033 | Plot No. B-1/16, Upper Ground Floor, Nangal Dewat, Vasant Kunj, Delhi-110070 +91- 8750701282 (panwarmini13@gmail.com) | 28/01/2024 |  |

Source: Data/Information provided by the client

Below tables shows the information of the companies/LLPs with which each Director is associated with to give a basic background detail of the promoters as found on public domain in general/ tertiary category research.

(MRS. JAIVIL RANA DIN: 02013601)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | UP Bio Gas Energy Private Limited (U35201DL2024PTC424857) | Director | 04/01/2024 | 04/01/2024 |
| 2 | Superior Agro Ventures Private Limited (U15490PB2022PTC056613) | Director | 04/08/2022 | 04/08/2022 |

Source: Information extracted from MCA website & public domain

(MRS. MINI PANWAR DIN: 10449033)

| S. No | Company Name (CIN/FCRN) | Designation | Original Date of Appointment | Date Of Appointment at Current Designation |
| --- | --- | --- | --- | --- |
| 1 | Superior Agro Ventures Private Limited (U15490PB2022PTC056613) | Additional Director | 28/01/2024 | 28/01/2024 |
| 2 | Up Bio Gas Energy Private Limited (U35201DL2024PTC424857) | Director | 04/01/2024 | 04/01/2024 |

Source: Information extracted from MCA website & public domain

As per informed by the client and data/information available in the public domain, Mr. Amit Rana is appointed as CEO of the company who belongs to farmer family and working towards the Agriculture Development/Green Energy, Advisor & Execution of Biogas Plants, Transformation with new technologies, interaction with Farmers, Cooperatives, SHG and FPO with an ability for uncovering opportunities in both the market place and within the organization. He has worked with MNRE in past. He also having the experience in the field of Retail, Distribution and manufacturing of Agro Products.

| PART D | PROPOSED INFRASTRUCTURE DETAILS |
| --- | --- |

- PROPOSED PLANT LOCATION:

The proposed Bio-CNG generating plant will be set up by M/s Superior Agro Ventures Private Limited at  Khata No, 208, 42, 226 Khasra No. 161/1, 160, 157 Village- Reda Harsana, Tehsil - Un, District- Shamli 247778, which is spread over an area of 5.048 Acre (2.043 Hectare) as per the sale deed provided to us by the company.

The location of the plant is in the well-known sugarcane belt of the western Uttara Pradesh, where accessibility of agricultural land for cultivating the Sugarcane & Napier grass is sufficient. Availability of the required raw material is the advantage of the proposed location as many Sugar mill are situated near by the location as shown in the below table:

| S. No. | Name of the Sugar Mill | Distance from location |
| --- | --- | --- |
|  | Superior Food Grains (P) Ltd., (Rana Group) Sugar Mill, Village - Gogar, Tehsil – Un, Uttar Pradesh 247778 | ~5 km away |
|  | Bajaj Hindusthan Sugar Ltd., Vill. Thanabhawan, Shamli, UP | ~ 24 km away |
|  | Upper Doab Sugar Mill, Shamli, Uttar Pradesh 247778 | ~25 km away |
|  | The Kisan Sahkari Chini Mills Ltd., Nanauta, Uttar Pradesh | ~27 km away |
|  | Uttam Sugar Mills Ltd. (Unit - 4), Nakur, Saharanpur, Uttar Pradesh | ~35 km away |

Source: Google Map

During the site visit we found that the property is an agricultural land and merged with adjacent plots and not demarcated till the date of survey done by us. The property is having the proximity to the civic amenities such as hospital is situated ~5 km away and market is situated ~4 km away from the proposed plant location. Table: 1 is showing the details of the adjoining properties of the land for proposed CBG plant and Table: 2 is showing the Connectivity Details of the Proposed Location:

| Table: 1 Adjoining Property Details |  |
| --- | --- |
| Location | Details |
| East | Agricultural land |
| West | Agricultural land |
| North | Road |
| South | Agricultural land |

| Table: 2 Connectivity Details of the Proposed Location |  |
| --- | --- |
| Connectivity | Details |
| Road | Meerut - Shamli-Karnal NH 709A - ~7 km away |
| Rail | SHAMLI Railway station - ~25 km away |
| Airport | Indira Gandhi International Airport, Delhi - ~152 km away |

- LOCATION MAP:

- GOOGLE MAP LOCATION:

The Bio-CNG plant is proposed to be commissioned at  Khata No, 208, 42, 226 Khasra No. 161/1, 160, 157 Village- Reda Harsana, Tehsil - Un, District- Shamli 247778 with GPS coordinates 29°36'11.6" North and 77°12'41.3" East as per the Google map attached below:

- GOOGLE MAP LAYOUT:

Demarcation of the land with approximate measurement on the Google map is attached in the below picture:

- LAYOUT PLAN:

As per the data/information provided by the client/Company, Proposed layout plan has been prepared by the appointed technical consultant Mr. Naman (M/s Star Projects Renewable Resources Private Limited) on 9th May 2024. NOC from the Gram Panchayat has already been taken by the company on 25th October 2023 (Ref: Gram Pradhan - Titu Kumar Gram Panchayat - Harsana, Development Block – UN, District Shamli). Proposed layout plan has been attached below for reference:

- LAND DETAILS:

As per the land deed executed on 19th June 2024, promoters of the Company has purchased a 5.048 Acre (2.043 Hectare) land at  Khata No, 208, 42, 226 Khasra No. 161/1, 160, 157 Village- Reda Harsana, Tehsil - Un, District- Shamli U.P 247778 in INR 4.24 Crore. Below table shows the detail of procured land to set up the proposed Bio CBG unit:

| Details of Procured Land for the proposed Unit |  |  |
| --- | --- | --- |
| Particular | Land 1 | Land 2 |
| Location | Village- Reda Harsana, Tehsil - Un, Shamli U.P 247778 | Village- Reda Harsana, Tehsil - Un, Shamli U.P 247778 |
| Area | 4.66 Acre | 0.388 Acre |
| Address | Khata No, 208, 42 Khasra No. 161/1, 160 | Khata No, 226 Khasra No. 157 |
| Type of land | Agricultural | Agricultural |
| Seller Name | Mahipal Singh | Mr. Amit Rana |
| Buyer Name | M/s Superior Agro Ventures Private Limited through its Director Mrs. Jaivil Rana | M/s Superior Agro Ventures Private Limited through its Director Mrs. Jaivil Rana |
| Considered Value of Land | INR 3.92 Crore | INR 32.62 lakhs |

As per informed by client, company needs to obtain Change of land use (CLU) on this agricultural land, to use the land for commercial/industrial purpose by setting up the proposed Bio-CNG plant. The total cost of the land is INR ~4.34 Crore including CLU and other charges of INR 10 lakhs.

During the site visit on 8th May 2024, we found it as a vacant (agricultural) land which was merged with the adjacent agricultural lands and entry of the land is directly connected with 48 ft. UN -Chausana Link Road. As informed by the client, company will start the demarcation and land development work after the sanction of term loan.

- SITE PICTURES:

Site pictures were captured during the site visit on 8th May 2024, for reference few of the pictures are attached below:

- PLANT & MACHINERY/ EQUIPMENTS DETAILS:

Appointed EPC consultant M/s Vimal Organics Ltd is agreed to supply all the Equipment, Plant & Machinery as per scope of work mentioned in the EPC agreement. Detailed bifurcation of the proposed Plant & Machinery has been shown in the below table along with the estimated cost:

| Plant & Machinery and Mechanical Equipment (Lakhs) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars of unit required | Unit | Rate | Amount | GST | Amount Including GST |

Source: Data/information provided by the client.

Thus, as per shared EPC contract provided by the client, the estimated cost for plant & machinery will be ~INR 1713.76 lakhs including applicable GST and 10% EPC fees. ~45% of TPC is the cost Plant & Machinery

The estimated cost of the Plant & Machinery has been provided to us by the client as per EPC agreement. However, as a TEV consultant, the cost of major plant & machinery has been verified by us independently, which we found reasonable & in the permissible range although the cost may change as per specifications & brand.

Note: It is to be noted here that the cost estimation done by us is just a general assessment for TEV purpose. However, detailed cost vetting is out of scope of this TEV report.

- UTILITIES: Details of Water, Electricity and other utilities are describes as below:

- WATER:

As per the data/information provided by the client, ~96 kl water will required on daily basis for proposed plant and water requirement will be fulfilled by setting up the proposed Well (70 Mt. depth). Company has applied for "No Objection Certificate" for groundwater extraction to Ground water department (Namami Gange & Rural Water supply department), Ministry of Jal Shakti, Government of Uttara Pradesh on 13th November 2023 (Application Number: SHML1123NIN0034), after approval the Company can extract 25 m³ water per hour for 2 hours on daily basis. As per the NOC application, maximum allowable annual extraction of ground water is 17,500 Cubic metre i.e. 50 cubic metre per day.

- ELECTRICITY:

As per the data/information provided to us by the client regarding Parasitic Consumption of Power (Tentative), proposed Bio CBG plant will be required a connected load of 500 KVA. Out of which, ~85% of connected load i.e. 426 kva will be the expected running load for the proposed plant. Component wise estimation of the power consumption is shown in the below table:

| Parasitic Consumption of Power (Tentative) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Particulars | Connected Load (Kwh) | Units | operational hours | Power consumption |

Sources: Data/information shared by the client.

Thus, ~INR 6.49 Crore per ton is the expected CAPEX for the proposed 6,000 KGPD Bio-CNG generating plant including GST, land, pre-operative and preliminary expenses, transportation costs, convey vehicle etc. As a TEV consultant we have verified the major costs which we found reasonable & in the permissible range as per the tertiary research done by us, data/information available in the public domain and information provided by the third party consultants/vendors.

For reference, Asia's largest Compressed Bio Gas (CBG) plant inaugurated in Sangrur on 18th Oct 2022 by Ministry of Petroleum & Natural Gas. The Plant was commissioned with an FDI investment of ~INR 220 crores, which is spread over an area of 20 acres. The installed capacity of the plant is 33 TPD. The capital expenditure of the plant is ~INR 6.67 Crore per ton. (Ref: https://pib.gov.in/PressReleasePage.aspx?PRID=1868887). Some of the other references are shown in the below table:

| Reference for Bio Gas Plant |  |  |  |
| --- | --- | --- | --- |
| S. No. | Name of the Party | Contact details | Remarks |
|  | M/s Jog Waste to Energy Pvt Ltd | info@jogwte.com +91 9723269295 www.jogwte.com | - As per JOGWTE, the average installation cost as per EPC basis from scratch to successful trial run would be ranging INR 5.5-6.5 Crore per ton including preliminary and pre-operative expenses and other contingent costs. |
|  | The Global Green Growth Institute, GGGI India | nishant.bhardwaj@gggi.org | - As per information provided by GGGI, The capital expenditure (CAPEX) for a typical 8-10 TPD Bio-CNG plant varies from INR 32-50 Crore which varies based on the type of biomass feedstock and technology deployed. - It has been estimated that the plant and machinery costs contributes ~76% of CAPEX. (Excluding preliminary and pre-operative expenses and excluding all other costs such as engineering, consultancy, installation costs etc. i.e. EPC Costs) |
|  | Ministry of New & Renewable energy | MNRE | - The economics of a CBG plant can vary depending on various factors such as the scale of the plant, technology used, feedstock cost, government incentives and market demand for CBG. - ~INR 20-25 crore is the cost of installing a 5 TPD capacity CBG plant, while ~75-80% of the CAPEX cost is for purchasing plant machinery. |
|  | Others vendors | On the public domain | - CSTR technology which is flexible for all types of organic wastes including mixed wastes. Capital cost for this technology is approximately INR 4-6 Crore per ton including all the costs from scratch to Successful trial run. |

Note: It is to be noted that the detailed cost vetting is out of scope of this TEV and we have done this activity for TEV purpose only.

| PART E | PROJECT TECHNICAL DETAILS |
| --- | --- |

- CAPACITY OF THE PROPOSED SOLAR POWER PLANT:

This Bio-CNG generating plant is proposed to be set up with a designed capacity of 14,500 M3/Day to generate the 6,000 kg/day bio CNG as per LOI with OMC along with 24 Ton/Day of solid organic fertilizer as illustrated in the below table:

| Capacity of the proposed Bio-CNG plant |  |
| --- | --- |
| Particular | Capacity |
| Bio-CNG Plant Design Capacity | 14,500 M3/Day |
| Biogas Plant Generation (Design Capacity x 86%) | 13,416 M3/Day |
| Bio-CNG Plant Capacity | 6,100 kg/Day |
| Leakage factor @1.64% | ~100 kg/day |
| Net Output | 6,000 Kg/day |
| Compost Plant Capacity | 24,000 kg/Day |

Source: Data/information provided by the client.

- PRODUCTION PROCESS OF BIO CNG (CBG):

OVERVIEW:

- PROCESS FLOW CHART OF THE PROPOSED BIO-CNG PLANT:

- TECHNICAL SPECIFICATIONS OF THE PROPOSED BIO-CNG PLANT:

As per the data/information provided by the client, below table shows the technical specification of the proposed Bio CBG generating plant:

- TECHNOLOGY USED:

- TECHNOLOGY SUPPLIER, EPC CONTRACTOR:

As per the data/information provided by the client, Company has appointed an ISO 9001 certified Ghaziabad based solution provider M/s Vimal Organics Ltd. As per the scope of work mentioned in the agreement, EPC Contractor undertakes to supply 14500 CuM Compressed Bio Gas, Bio-Fertilizer. Below table shows the basic details of EPC contractor as per the data/information provided by the client and available in the public domain:

| Particular | Description |
| --- | --- |
| Name | M/s Vimal Organics Limited |
| CIN | U27105DL1984PLC017452 |
| GST No. | 09AAACV7698G1ZP |
| Reg. Address | D-35, B S R Industrial Area, Bulandshahr Road Industrial Area, Ghaziabad- 201009, Uttar Pradesh, India |
| Website | https://www.vimalorganics.com/ |
| About the Company | As per the data/information available in public domain, Vimal Organics Limited was incorporated as a Private Limited Company in the year 1984 and converted into a Public Limited Company in 1994. Company is engaged in manufacturing, supplying and exporting a wide range of equipments which are used in industries. |
| Services | Turnkey Projects for Fertilizer & Micro Nutrients, Turnkey Projects for Chemicals, Turnkey Projects for Food Processing, Activated Bleaching Clay, Individual Equipment and Mechanical Conveying System. |
| Standards & Quality Certifications | SSI Registration No - (C/20/56/01683/PMT/SSI/0) CHEMEXCIL, FIEO, FICCI,CII, SEA, |

- PROPOSED TECHNOLOGY:

Company has proposed to commission this Bio CNG plant with “Sequential Gas Mixing System” which is an Italian based technology supplied by “Mapro International S.p.A.” Sequential Gas Mixing (SGM) ensures anaerobic digesters are mixed continuously to without thermal layering and accumulation of volatile fatty acid (VFA) pockets.

Gas Injection Mixing Systems gives comparatively higher operational efficiency due to no sedimentation because of the mixing by gas bubbling from the bottom in the proposed. Further, production of gas is high due to complete and uniform mixing and to a low temperature gradient in the sludge.

| Proposed Technology (Sequential Gas Mixing System) |  |  |
| --- | --- | --- |
| S. No. | Particular | Description |

Power consumption is low up to 50% energy saving compared to mechanical mixing system due to no friction between sludge and mechanical parts. This technology is more reliability as no corrosion and no struvite. Maintenance cost is low as no parts in movement inside the sludge.

- LATEST TECHNOLOGY/TECHNOLOGICAL ASSESSMENT:

XXX

Thus as per the above technical assessment, M/s Superior Agro Ventures Private Limited has proposed the appropriate Sequential Gas Mixing System with Italian Technology which is a recognized and proven technology. It can be commented positively that the plant will be running smoothly. Technology & specification of the plant are matching with the need to run the plant to achieve the economies of scale.

- TESTING STANDARDS FOR PRODUCTION:

- MANPOWER:

As per information shared by the client/company, a proper ratio between the administrative, managerial, supervisory and shop foor staff has been maintained with a view to affording proper industrial and professional management at various levels in estimating the manpower requirement. The basic structure of the manpower will require the following kind of resources to opearte the plant 24*7 for 350 days a year:

| PART F | PRODUCT PROFILE |
| --- | --- |

- INTRODUCTION:

- PRODUCT CATEGORY:

- PRICING STRATEGY:

- MARKETING, SELLING & DISTRIBUTION PLAN:

| PART G | XXX ANALYSIS |
| --- | --- |

| PART H | INDUSTRY OVERVIEW |
| --- | --- |

- INTRODUCTION:

- POTENTIAL AND EXPANSION:

- CHALLENGES:

- GOVERNMENT INITIATIVES:

- CONCLUSION:

| PART I | SWOT ANALYSIS |
| --- | --- |

| SWOT ANALYSIS |  |
| --- | --- |
| STRENGTHS | - Strategic Location: The project is situated in UN, Shamli. Many sugar mills are situated near by the location of the proposed Bio CNG plant ensures the availability of raw material (press mud). Further availability of agricultural land in western U.P., supply of Napier grass will also be good as farmers are interest towards commercial agriculture & contract farming. - Growing Demand: Due to renewable source of energy, demand for Bio-CNG is expected to grow at a CAGR of ~6 % in the upcoming years. - LOI: The produced 6 TPD Bio CNG will be supplied to IOCL as per the LOI issued by OMC under SATAT scheme, which is an effortless avenue for the project to generate the revenue. (Ref No. - Indian Oil/SATAT/01/3589, Date: 3rd November 2023). - Government Support: The project will be entitled to avail incentives of INR 4.0 Cr per 4800 kg/day for Bio CNG generation from new biogas plant, Under Waste to Energy Programme of Ministry of New and Renewable Energy. Further, Government of Uttar Pradesh is providing the subsidy of INR 75 lac / Ton under the provision of UP Bio Energy Policy 2022 and project is eligible for benefit up to INR 2.0 Cr from Agriculture Infrastructure Fund (AIF) – Circular dated 27th Oct. 2020. Market Development Assistance (MDA) for Promotion of Organic Fertilizers INR 1500 / Ton to CBG Plants - Technology: The proposed plant will be commissioned with Mapro -Sequential Gas Mixing Technology (Italian), which is a proven technology empirically. |
| WEAKNESSES | - CAPEX: The proposed Bio CNG plant would be set up by a high initial investment, in which ~65% capital would be required for land, building and plant & machinery only. - Infrastructure Requirements: The project's power load and water consumption are significant, and ensuring uninterrupted power supply and adequate water resources may pose challenges. - Raw Material Market: There is no any formal market for raw material, leading to establish a feedstock pricing mechanism. |
| OPPORTUNITIES | - Increasing Alternate fuel’s Demand: As the transportation industry is expanding, there will be an organic demand for Bio CNG/CBG as an alternate fuel due to mandatory blending of compressed biogas (CBG) in compressed natural gas (CNG) for transportation. - Expansion Potential: The Company is having the plan to expand its business in future for manufacturing Bio Coal and Bio Pellets. - Government Support: The project can benefit from government initiatives and policies aimed at promoting the Bio CNG production to achieve Net Zero target by 2070. |
| THREATS | - Fluctuating Raw Material Prices: With the increasing demand of sugarcane press mud, the prices are shooting up rapidly. - Economic Factors: Profitability of the project may hamper due to any blockage of feed stock. - Dependency on LOI: Any breach of the LOI agreement with OMC, the company may require to search the new approach to sell its production in the market. - Manufacturing Experience: Promoters are having experience of different industries, however entering into Bio CNG generating business may explore new multidimensional challenges. - Farmers Awareness: Increasing awareness of Bio Fertilizer in Farmers and Marketing of Organic Fertilizer can adversely affect the projected revenue of the company expected to generate from by-products. |

| PART J | PROJECT COST AND MEANS OF FINANCE |
| --- | --- |

As per data/information shared by the client, the proposed Bio CNG generating project is proposed to be commissioned by making an investment of INR 42.65 Crore as shown in the below table along with Means of finance:

| Total Project Cost |  |  |
| --- | --- | --- |
| S. No. | Capital Cost Head | Amount (INR Crore) |
|  | Land Cost | 4.34 |
|  | Building & Civil Works | 8.11 |
|  | Plant & Machinery | 17.52 |
|  | Electricity Infrastructure | 2.79 |
|  | Vehicles | 0.16 |
|  | Office equipment | 0.10 |
|  | Interest During Construction (IDC) | 2.42 |
|  | Sub Total | 35.43 |
|  | Preliminary & Preoperative | 2.40 |
|  | Contingencies at ~4% of Total Project Cost | 0.57 |
|  | Sub Total | 38.40 |
|  | Working Capital Margin @ 25% of WC Gap | 0.54 |
|  | Grand Total (TPC) | 38.93 |

Source: Data/Information provided by the company.

| Means of Finance |  |  |
| --- | --- | --- |
| S. No. | Particular | Amount (INR Crore) |
|  | Equity | 11.68 |
|  | Term Loan from Bank | 27.25 |
|  | Total | 38.93 |
|  | CC Loan | 1.50 |

Source: Data/Information provided by the company.

Notes:

- It is to be noted that the detailed vetting of the project cost is out of scope of this TEV report and we have relied upon the data/information provided by the client regarding Total Project cost in good faith, however as a TEV consultant we have cross verified the cost of the major components of TPC independently wherever required for the purpose of TEV only.

- As per the sale deed executed on 19th June 2024, promoters of the Company has purchased a 5.048 Acre (2.043 Hectare) agricultural land at  Khata No, 208, 42, 226 Khasra No. 161/1, 160, 157 Village- Reda Harsana, Tehsil - Un, District- Shamli U.P 247778. Total cost of the land would be INR ~4.34 Crore including INR 10 lakhs for Change of land use (CLU) and other charges.

- The estimated cost of the Building & Civil works is ~INR 810.69 lakhs including applicable GST and 10% EPC consultant cost as per the signed agreement. Cost of the Building & Civil works has been considered on the basis of shared details/EPC contract provided to us by the client. As a TEV consultant we have checked major unit cost considered in EPC contract which we found in permissible range.

- As per shared EPC contract provided by the client, the estimated cost for plant & machinery will be ~INR 1713.76 lakhs including applicable GST and 10% EPC fees. ~45% of TPC is the cost Plant & Machinery. The estimated cost of the Plant & Machinery has been provided to us by the client as per EPC agreement. However, as a TEV consultant, the cost of major plant & machinery has been verified by us independently, which we found reasonable & in the permissible range although the cost may change as per specifications & brand.

- The cost of Electrical, Instrumentation, PLC, data collection is INR 279.20 lakhs including GST & 10% EPC fess. Tentative cost of Off-site Facilities and office equipment is INR 63.51 lakhs including applicable GST. We found that the costs are in the line with prevailing market standard.

- As per the data/information provided by the client, applicable Interest during Construction (IDC) is 11.50%. Thus the company is required to pay INR 2.66 Crore as IDC from September 2024 to September 2025 (13 months) as per the proposed Loan repayment schedule.

- Preliminary & Pre-Operative Expenses has been considered based on the estimate of company’s resources involvement as INR 2.40 Crore. However, Company did not provide us any invoices/bills against these tentative costs considered. We recommend that the bank/financial institutions advice the company to submit actual cost based on the final quotations/invoices/bills. This will help validate the assertion of different costs considered by the client.

- Contingency cost of INR 0.57 Crore has been considered based on general assumption and professional experience (~2 of Hard Cost of the Project).

- The project is proposed to be funded through a term loan of INR 27.25 crores and promoter’s Equity of INR 11.68 crores. Further, as per the working capital assessment, the working capital will require as INR 2.0.6 Crore, which will be funded through WC loan of INR 1.50 Cr. and promoter’s margin of INR 0.52 (~25% of required WC).

| PART K | PROJECT IMPLEMENTETION SCHEDULE |
| --- | --- |

The proposed Bio CNG generating unit is expected to achieve its C.O.D till 1st October 2025, as per the proposed implementation schedule shown in the table below:

| S. No. | Particulars | Activity | Expected completion date | Status |
| --- | --- | --- | --- | --- |
|  | Land | Land Procurement | 19th June 2024 | CLU is pending |
|  |  | Land Development | 31st October 2024 | Scheduled |
|  | Sanction of Rupee Term Loan | Sanction of Rupee Term Loan | 31st August 2024 | Scheduled |
|  | Building & Civil Works | Appointment of Architect | July 2023 | Completed |
|  |  | Building/Layout Plan Preparation | 9th May 2023 | Completed |
|  |  | Building Plan Sanction | 1st September 2024 | Scheduled |
|  |  | Appointment of Civil contractor/ developer | 31st August 2024 | Scheduled |
|  |  | Building & Civil Works completion | 31st December, 2024 | Scheduled |
|  | Plant & Machinery | Finalization of P&M suppliers | 1st September 2024 | Scheduled |
|  |  | Orders to P&M suppliers | October, 2024 | Scheduled |
|  |  | Arrival of P&M | March, 2025 | Scheduled |
|  |  | Installation of P&M | June, 2025 | Scheduled |
|  |  | Utility Installation | August, 2025 | Scheduled |
|  | Statutory Approvals, registrations & NOCs | From the respective authorities | 1st September, 2025 | Pending except the approval obtained as per “Section L” |
|  | Finishing & Trail Run | Informed by client | 20th September, 2025 | Scheduled |
|  | Commercial Operation Date | Informed by client | 1st October 2025 | Scheduled |

Notes:

- Schedule has been made as per feasibility to achieve different milestones.

- Achievement of Milestone will depend on sanction of term loan as per proposed timeline.

- For current status of statutory approvals, kindly refer the “Section L” of this report.

- As per this timeline, the expected C.O.D will be 1st October 2025.

| PART L | STATUTORY APPROVALS ¦ LICENCES ¦ NOC |
| --- | --- |

As shown in the below table along with current status, following major approvals are required, However the list is not exhaustive and State/District Authorities may be approached for further clearances required (if any):

| S. No. | REQUIRED APPROVALS | DATE REFERENCE NO. | STATUS (Approved/ Applied For/ Pending) |
| --- | --- | --- | --- |
|  | Certificate of Incorporation Ministry of Corporate Affairs, Government of India | 4th August 2022 CIN: U15490PB2022PTC056613 | Approved |
|  | Land conversion to Industrial/Non agriculture Sub Divisional Magistrate, UN, Shamli, U.P. | - | Pending |
|  | NOC from Gram Panchayat Gram Panchayat Harsana, UN, Shamli, Uttar Pradesh | 25th October 2023 | Approved |
|  | Labour Licence Registration & grant of license under The Factories Act, 1948 Labour Department, Government of Uttar Pradesh | - | Pending |
|  | Building and civil works Plan Sanction Approval Concerned local development authority | - | Pending |
|  | Pre-establishment fire NOC Fire and Emergency Services, Government Of Uttar Pradesh | - | Apply in due course |
|  | Fire NOC (on completion) Fire and Emergency Services, Government Of Uttar Pradesh | - | Will be Applied post C.O.D |
|  | New HT line - non domestic /industrial Power Connection Uttar Pradesh Power Corporation Limited | - | Pending |
|  | Consent to Establish under Air (Prevention and Control of Pollution) Act, 1981 & Water (Prevention and Control of Pollution) Act, 1974 Uttar Pradesh Pollution Control Board | 21st October 2023 193603/UPPCB/Circle3(UPPCBHO)/CTE/SHAMLI/2023 | Approved |
|  | No Objection Certificate (NOC) for ground water abstraction Ground water department (Namami Gange & Rural Water supply department), Ministry of Jal Shakti, Government of Uttara Pradesh | 13th November 2023 (Application Number: SHML1123NIN0034) | Applied |
|  | Petroleum & Explosives Safety Organisation (PESO) Ministry of Commerce & Industry, Government of India | 28th November 2023 Prior Approval No : A/G/HO/UP/05/623 &A/G/HO/UP/06/602 (G124605) | Approved |

Observation Note:

- As per the data/information provided by the client, application of No Objection Certificate (NOC) for ground water abstraction was submitted on 13th November 2023 (Application Number: SHML1123NIN0034).

- Consent to establish is valid from 21st Oct, 2023 to 20th Oct 2028 (Ref. No. - 193603/UPPCB/Circle3(UPPCBHO)/CTE/SHAMLI/2023)

- Above is the only illustration of the major approvals sought or to be sought by the company. It should not be construed as the exhaustive list and in case any approval is missed to be mentioned then it is the sole responsibility of the company to keep the unit compliant with the necessary statutory approvals/ NOCs.

| PART M | PROJECT’S FINANCIAL FEASIBILITY |
| --- | --- |

- PROJECTIONS OF THE PROJECT:

The financial projections of the proposed Wind-Solar Hybrid power project are prepared from FY 2027 to FY 2052 based on the expected COD and loan tenure as per the best practice in industry to assess the financial feasibility of the project:

- PROJECTED PROFIT & LOSS ACCOUNT:

(INR Crore)

| Year Ending | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Revenue | 121.41 | 121.97 | 121.21 | 120.80 | 120.38 | 120.30 | 119.56 | 119.16 | 118.76 | 118.70 | 117.98 | 117.60 | 117.22 |
| Operating Expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| O & M Expenses | 0.00 | 0.00 | 4.21 | 4.41 | 4.61 | 4.83 | 5.05 | 5.29 | 5.54 | 5.80 | 6.07 | 6.35 | 6.65 |
| Lease Rentals for land | 0.83 | 0.83 | 0.87 | 0.87 | 0.92 | 0.92 | 0.96 | 0.96 | 1.01 | 1.01 | 1.06 | 1.06 | 1.11 |
| Insurance Expenses | 0.45 | 0.43 | 0.41 | 0.40 | 0.38 | 0.36 | 0.34 | 0.33 | 0.31 | 0.29 | 0.27 | 0.26 | 0.24 |
| Banking charges+ Transmission Charges +Fixed demand Charges | 6.92 | 6.92 | 6.89 | 6.87 | 6.85 | 6.86 | 6.82 | 6.81 | 6.79 | 6.79 | 6.76 | 6.74 | 6.73 |
| Depreciation & Amortization | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 |
| Total Expenses | 25.82 | 25.86 | 30.01 | 30.17 | 30.38 | 30.64 | 30.80 | 31.01 | 31.27 | 31.56 | 31.78 | 32.03 | 32.35 |
| EBIT | 95.58 | 96.11 | 91.21 | 90.63 | 90.00 | 89.66 | 88.76 | 88.16 | 87.50 | 87.13 | 86.20 | 85.57 | 84.87 |
| Interest expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest on term loan | 33.32 | 32.48 | 30.82 | 29.15 | 27.49 | 25.82 | 24.16 | 22.49 | 20.82 | 19.16 | 17.49 | 15.83 | 14.16 |
| Profit before Taxes (PBT) | 62.27 | 63.63 | 60.39 | 61.47 | 62.51 | 63.84 | 64.61 | 65.67 | 66.67 | 67.98 | 68.71 | 69.74 | 70.71 |
| Tax | 10.68 | 10.92 | 10.36 | 10.55 | 10.73 | 10.96 | 11.09 | 11.27 | 11.44 | 13.23 | 21.09 | 21.98 | 22.77 |
| Profit after Taxes (PAT) | 51.58 | 52.71 | 50.03 | 50.92 | 51.78 | 52.89 | 53.52 | 54.40 | 55.23 | 54.75 | 47.62 | 47.76 | 47.93 |

(Continued)

| Year Ending | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Revenue | 117.16 | 116.47 | 116.10 | 115.74 | 115.69 | 115.02 | 114.67 | 114.32 | 114.29 | 113.63 | 113.30 | 112.96 | 112.94 |
| Operating Expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| O & M Expenses | 6.96 | 7.28 | 7.63 | 7.98 | 8.36 | 8.75 | 9.16 | 9.59 | 10.04 | 10.51 | 11.01 | 11.52 | 12.07 |
| Lease Rentals for land | 1.12 | 1.17 | 1.17 | 1.23 | 1.23 | 1.29 | 1.29 | 1.35 | 1.36 | 1.42 | 1.42 | 1.49 | 1.50 |
| Insurance Expenses | 0.22 | 0.20 | 0.19 | 0.17 | 0.15 | 0.13 | 0.11 | 0.10 | 0.08 | 0.06 | 0.04 | 0.03 | 0.01 |
| Banking charges+ Transmission Charges +Fixed demand Charges | 6.73 | 6.70 | 6.68 | 6.67 | 6.67 | 6.64 | 6.63 | 6.61 | 6.61 | 6.58 | 6.57 | 6.55 | 6.56 |
| Depreciation & Amortization | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 |
| Total Expenses | 32.70 | 32.98 | 33.29 | 33.67 | 34.08 | 34.43 | 34.81 | 35.27 | 35.76 | 36.20 | 36.66 | 37.22 | 37.80 |
| EBIT | 84.46 | 83.49 | 82.81 | 82.07 | 81.61 | 80.59 | 79.86 | 79.04 | 78.52 | 77.43 | 76.63 | 75.74 | 75.14 |
| Interest expenses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest on term loan | 12.49 | 10.83 | 9.16 | 7.50 | 5.83 | 4.16 | 2.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Profit before Taxes (PBT) | 71.97 | 72.66 | 73.65 | 74.57 | 75.78 | 76.42 | 77.36 | 79.04 | 78.52 | 77.43 | 76.63 | 75.74 | 75.14 |
| Tax | 23.58 | 24.14 | 24.75 | 25.28 | 25.87 | 26.24 | 26.68 | 27.32 | 27.30 | 27.07 | 26.93 | 26.74 | 26.64 |
| Profit after Taxes (PAT) | 48.39 | 48.52 | 48.90 | 49.29 | 49.91 | 50.18 | 50.67 | 51.73 | 51.23 | 50.36 | 49.71 | 49.00 | 48.50 |

- PROFORMA BALANCE SHEET:

Below table shows the Projected Balance Sheet of the proposed Captive Wind-Solar Hybrid power project from the period FY 2025 to FY 2052. From 1st December 2024 to 31st March 2026 would be the implementation period of the project:

(INR Crore)

| Year Ending | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Non-Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity | 87.68 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 |
| Reserve & Surplus | 0.00 | 0.00 | 51.58 | 104.29 | 154.32 | 205.24 | 257.02 | 309.91 | 363.43 | 417.83 | 473.06 | 527.81 | 575.43 | 623.19 |
| Secured Loan | 140.28 | 350.71 | 333.18 | 315.64 | 298.10 | 280.57 | 263.03 | 245.50 | 227.96 | 210.43 | 192.89 | 175.36 | 157.82 | 140.28 |
| Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Term Liabilities Payable Within One Year | 0.00 | 0.00 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 |
| Total | 227.96 | 467.62 | 519.20 | 554.37 | 586.86 | 620.25 | 654.50 | 689.85 | 725.83 | 762.70 | 800.39 | 837.60 | 867.69 | 897.91 |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Plant & Machinery | 187.05 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 |
| Total Gross Block | 187.05 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 |
| Less: Depreciation |  |  | 17.62 | 35.29 | 52.91 | 70.53 | 88.15 | 105.82 | 123.45 | 141.07 | 158.69 | 176.36 | 193.98 | 211.60 |
| Net Block | 187.05 | 467.62 | 449.99 | 432.32 | 414.70 | 397.08 | 379.46 | 361.79 | 344.17 | 326.55 | 308.93 | 291.26 | 273.64 | 256.01 |
| Total Non-Current Assets | 187.05 | 467.62 | 449.99 | 432.32 | 414.70 | 397.08 | 379.46 | 361.79 | 344.17 | 326.55 | 308.93 | 291.26 | 273.64 | 256.01 |
| Current Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash & Cash Equivalent | 40.92 | 0.00 | 69.20 | 122.05 | 172.16 | 223.17 | 275.04 | 328.06 | 381.66 | 436.15 | 491.47 | 546.35 | 594.05 | 641.89 |
| Total Current Assets | 40.92 | 0.00 | 69.20 | 122.05 | 172.16 | 223.17 | 275.04 | 328.06 | 381.66 | 436.15 | 491.47 | 546.35 | 594.05 | 641.89 |
| Total | 227.96 | 467.62 | 519.20 | 554.37 | 586.86 | 620.25 | 654.50 | 689.85 | 725.83 | 762.70 | 800.39 | 837.60 | 867.69 | 897.91 |

(Continued)

| Year Ending | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Non-Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 | 116.90 |
| Reserve & Surplus | 671.12 | 719.51 | 768.03 | 816.93 | 866.22 | 916.13 | 966.30 | 1016.98 | 1068.70 | 1119.93 | 1170.29 | 1220.00 | 1269.00 | 1317.49 |
| Secured Loan | 122.75 | 105.21 | 87.68 | 70.14 | 52.61 | 35.07 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Current Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Term Liabilities Payable Within One Year | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 928.31 | 959.16 | 990.14 | 1021.51 | 1053.27 | 1085.64 | 1118.28 | 1151.42 | 1185.61 | 1236.83 | 1287.20 | 1336.90 | 1385.90 | 1434.40 |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Plant & Machinery | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 |
| Total Gross Block | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 | 467.62 |
| Less: Depreciation | 229.22 | 246.89 | 264.51 | 282.13 | 299.76 | 317.42 | 335.05 | 352.67 | 370.29 | 387.96 | 405.58 | 423.20 | 440.82 | 458.49 |
| Net Block | 238.39 | 220.72 | 203.10 | 185.48 | 167.86 | 150.19 | 132.57 | 114.95 | 97.33 | 79.66 | 62.04 | 44.41 | 26.79 | 9.12 |
| Total Non-Current Assets | 238.39 | 220.72 | 203.10 | 185.48 | 167.86 | 150.19 | 132.57 | 114.95 | 97.33 | 79.66 | 62.04 | 44.41 | 26.79 | 9.12 |
| Current Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash & Cash Equivalent | 689.92 | 738.44 | 787.04 | 836.03 | 885.41 | 935.45 | 985.71 | 1036.47 | 1088.28 | 1157.18 | 1225.16 | 1292.49 | 1359.11 | 1425.28 |
| Total Current Assets | 689.92 | 738.44 | 787.04 | 836.03 | 885.41 | 935.45 | 985.71 | 1036.47 | 1088.28 | 1157.18 | 1225.16 | 1292.49 | 1359.11 | 1425.28 |
| Total | 928.31 | 959.16 | 990.14 | 1021.51 | 1053.27 | 1085.64 | 1118.28 | 1151.42 | 1185.61 | 1236.83 | 1287.20 | 1336.90 | 1385.90 | 1434.40 |

- PROJECTED CASH FLOW STATEMENT:

(INR Crore)

| Year Ending (INR Crore) | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| A. Source Of Fund |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net Profit | 0.00 | 0.00 | 51.58 | 52.71 | 50.03 | 50.92 | 51.78 | 52.89 | 53.52 | 54.40 | 55.23 | 54.75 | 47.62 | 47.76 |
| Increase in Equity / Share Capital/USL | 87.68 | 29.23 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Increase in TL | 140.28 | 210.43 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Depreciation | 0.00 | 0.00 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 |
| Trade payables | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 227.96 | 239.65 | 69.20 | 70.38 | 67.65 | 68.55 | 69.40 | 70.56 | 71.14 | 72.02 | 72.85 | 72.42 | 65.24 | 65.38 |
| B. Application Of Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital Expenses | 187.05 | 280.57 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Decrease in Term Loan | 0.00 | 0.00 | 0.00 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 |
| Total | 187.05 | 280.57 | 0.00 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 |
| Opening Balance | 0.00 | 40.92 | 0.00 | 69.20 | 122.05 | 172.16 | 223.17 | 275.04 | 328.06 | 381.66 | 436.15 | 491.47 | 546.35 | 594.05 |
| Net Surplus/ Deficit | 40.92 | -40.92 | 69.20 | 52.84 | 50.11 | 51.01 | 51.87 | 53.02 | 53.60 | 54.48 | 55.32 | 54.88 | 47.71 | 47.84 |
| Cumulative Balance | 40.92 | 0.00 | 69.20 | 122.05 | 172.16 | 223.17 | 275.04 | 328.06 | 381.66 | 436.15 | 491.47 | 546.35 | 594.05 | 641.89 |

(Continued)

| Year Ending (INR Crore) | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| A. Source Of Fund |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net Profit | 47.93 | 48.39 | 48.52 | 48.90 | 49.29 | 49.91 | 50.18 | 50.67 | 51.73 | 51.23 | 50.36 | 49.71 | 49.00 | 48.50 |
| Increase in Equity / Share Capital/USL | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Increase in TL | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Depreciation | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 |
| Trade payables | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 65.56 | 66.06 | 66.14 | 66.53 | 66.91 | 67.58 | 67.80 | 68.29 | 69.35 | 68.90 | 67.98 | 67.33 | 66.62 | 66.17 |
| B. Application Of Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital Expenses | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Decrease in Term Loan | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Opening Balance | 641.89 | 689.92 | 738.44 | 787.04 | 836.03 | 885.41 | 935.45 | 985.71 | 1036.47 | 1088.28 | 1157.18 | 1225.16 | 1292.49 | 1359.11 |
| Net Surplus/ Deficit | 48.02 | 48.52 | 48.60 | 48.99 | 49.37 | 50.04 | 50.26 | 50.76 | 51.81 | 68.90 | 67.98 | 67.33 | 66.62 | 66.17 |
| Cumulative Balance | 689.92 | 738.44 | 787.04 | 836.03 | 885.41 | 935.45 | 985.71 | 1036.47 | 1088.28 | 1157.18 | 1225.16 | 1292.49 | 1359.11 | 1425.28 |

- KEY FINANCIAL RATIO:

| Year Ending (INR Crore) | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBITDA Margin % | 93.25% | 93.29% | 89.78% | 89.61% | 89.40% | 89.22% | 88.97% | 88.77% | 88.51% | 88.30% | 88.00% | 87.75% | 87.44% |
| Average | 87.13% |  |  |  |  |  |  |  |  |  |  |  |  |
| EBIT Margin % | 78.73% | 78.80% | 75.24% | 75.02% | 74.76% | 74.53% | 74.24% | 73.98% | 73.67% | 73.41% | 73.06% | 72.76% | 72.40% |
| Average | 72.08% |  |  |  |  |  |  |  |  |  |  |  |  |
| PAT Margin % | 42.49% | 43.22% | 41.27% | 42.16% | 43.02% | 43.96% | 44.76% | 45.65% | 46.51% | 46.12% | 40.36% | 40.61% | 40.89% |
| Average | 43.24% |  |  |  |  |  |  |  |  |  |  |  |  |
| Revenue Growth Rate |  | 0.47% | -0.62% | -0.35% | -0.34% | -0.07% | -0.61% | -0.34% | -0.33% | -0.06% | -0.60% | -0.33% | -0.32% |
| Average | -0.29% |  |  |  |  |  |  |  |  |  |  |  |  |

| Year Ending (INR Crore) | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBITDA Margin % | 87.17% | 86.82% | 86.51% | 86.13% | 85.81% | 85.38% | 85.01% | 84.56% | 84.17% | 83.65% | 83.19% | 82.65% | 82.18% |
| Average | 87.13% |  |  |  |  |  |  |  |  |  |  |  |  |
| EBIT Margin % | 72.09% | 71.69% | 71.33% | 70.91% | 70.54% | 70.06% | 69.64% | 69.14% | 68.71% | 68.14% | 67.64% | 67.05% | 66.53% |
| Average | 72.08% |  |  |  |  |  |  |  |  |  |  |  |  |
| PAT Margin % | 41.30% | 41.66% | 42.12% | 42.59% | 43.14% | 43.62% | 44.19% | 45.25% | 44.82% | 44.32% | 43.87% | 43.38% | 42.94% |
| Average | 43.24% |  |  |  |  |  |  |  |  |  |  |  |  |
| Revenue Growth Rate | -0.05% | -0.59% | -0.32% | -0.31% | -0.04% | -0.58% | -0.31% | -0.30% | -0.03% | -0.57% | -0.30% | -0.29% | -0.02% |
| Average | -0.29% |  |  |  |  |  |  |  |  |  |  |  |  |

Note: The proposed solar power plant is having an average revenue growth rate of 13.61% during the forecasted period. Average EBITDA Margin & EBIT Margin of the project are 66.82% & 60.11% respectively.  The project will be operational only 3 months during FY 2026 and as per the trends analysis above, PAT margin is growing from 30.06% in FY 2026 to 43.58% in FY 2051 due to the lower interest cost on borrowings in the later projected years.

- GRAPHICAL REPRESENTATION OF KEY RATIOS:

- ESTIMATED KEY FINANCIAL METRICS:

DEBT SERVICE COVERAGE RATIO (D.S.C.R)

(INR Crore except DSCR)

| Year Ending (INR Crore) | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Cash accrual | 69.20 | 52.84 | 50.11 | 51.01 | 51.87 | 53.02 | 53.60 | 54.48 | 55.32 | 54.88 | 47.71 | 47.84 | 48.02 |
| Interest on term loan | 33.32 | 32.48 | 30.82 | 29.15 | 27.49 | 25.82 | 24.16 | 22.49 | 20.82 | 19.16 | 17.49 | 15.83 | 14.16 |
| Subtotal | 102.52 | 85.33 | 80.93 | 80.16 | 79.36 | 78.84 | 77.76 | 76.97 | 76.14 | 74.04 | 65.20 | 63.67 | 62.18 |
| Interest on term loan | 33.32 | 32.48 | 30.82 | 29.15 | 27.49 | 25.82 | 24.16 | 22.49 | 20.82 | 19.16 | 17.49 | 15.83 | 14.16 |
| Loan Repayment | 0.00 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 |
| Subtotal | 33.32 | 50.02 | 48.35 | 46.69 | 45.02 | 43.36 | 41.69 | 40.02 | 38.36 | 36.69 | 35.03 | 33.36 | 31.70 |
| DSCR | 3.08 | 1.71 | 1.67 | 1.72 | 1.76 | 1.82 | 1.87 | 1.92 | 1.98 | 2.02 | 1.86 | 1.91 | 1.96 |

(Countinue)

| Year Ending (INR Crore) | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Cash accrual | 48.52 | 48.60 | 48.99 | 49.37 | 50.04 | 50.26 | 50.76 | 51.81 | 68.90 | 67.98 | 67.33 | 66.62 | 66.17 |
| Interest on term loan | 12.49 | 10.83 | 9.16 | 7.50 | 5.83 | 4.16 | 2.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Subtotal | 61.02 | 59.43 | 58.15 | 56.87 | 55.87 | 54.43 | 53.26 | 51.81 | 68.90 | 67.98 | 67.33 | 66.62 | 66.17 |
| Interest on term loan | 12.49 | 10.83 | 9.16 | 7.50 | 5.83 | 4.16 | 2.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Loan Repayment | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Subtotal | 30.03 | 28.36 | 26.70 | 25.03 | 23.37 | 21.70 | 20.03 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| D.S.C.R | 2.03 | 2.10 | 2.18 | 2.27 | 2.39 | 2.51 | 2.66 | 2.95 |  |  |  |  |  |
| Max. D.S.C.R | 3.08 |  |  |  |  |  |  |  |  |  |  |  |  |
| Average D.S.C.R | 2.11 |  |  |  |  |  |  |  |  |  |  |  |  |

Note: D.S.C.R has been calculated for loan repayment period from FY 2027 to FY 2047. The proposed hybrid wind-solar power plant is having a D.S.C.R of more than 1 during the projected loan repayment period.

- NPV,IRR AND PAYBACK PERIOD OF THE PROJECT:

(INR Crore)

| Year Ending | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBIT | 0.00 | 0.00 | 95.58 | 96.11 | 91.21 | 90.63 | 90.00 | 89.66 | 88.76 | 88.16 | 87.50 | 87.13 | 86.20 | 85.57 |
| Less: Taxes | 0.00 | 0.00 | 10.68 | 10.92 | 10.36 | 10.55 | 10.73 | 10.96 | 11.09 | 11.27 | 11.44 | 13.23 | 21.09 | 21.98 |
| Add: Depreciation & Amortisation | 0.00 | 0.00 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 |
| NOPAT | 0.00 | 0.00 | 102.52 | 102.87 | 98.47 | 97.70 | 96.89 | 96.38 | 95.30 | 94.51 | 93.68 | 91.57 | 82.73 | 81.20 |
| Capex | 187.05 | 280.57 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Free Cash Flow to Firm (FCFF) | -187.05 | -280.57 | 102.52 | 102.87 | 98.47 | 97.70 | 96.89 | 96.38 | 95.30 | 94.51 | 93.68 | 91.57 | 82.73 | 81.20 |

(Countinue)

| Year Ending (INR Crore) | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| EBIT | 84.87 | 84.46 | 83.49 | 82.81 | 82.07 | 81.61 | 80.59 | 79.86 | 79.04 | 78.52 | 77.43 | 76.63 | 75.74 | 75.14 |
| Less: Taxes | 22.77 | 23.58 | 24.14 | 24.75 | 25.28 | 25.87 | 26.24 | 26.68 | 27.32 | 27.30 | 27.07 | 26.93 | 26.74 | 26.64 |
| Add: Depreciation & Amortisation | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 |
| NOPAT | 79.72 | 78.55 | 76.97 | 75.69 | 74.41 | 73.41 | 71.96 | 70.79 | 69.35 | 68.90 | 67.98 | 67.33 | 66.62 | 66.17 |
| Capex | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Free Cash Flow to Firm (FCFF) | 79.72 | 78.55 | 76.97 | 75.69 | 74.41 | 73.41 | 71.96 | 70.79 | 69.35 | 68.90 | 67.98 | 67.33 | 66.62 | 66.17 |
| NPV | INR 338 Crore |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IRR | 18.65% |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Key Input for NPV & IRR |  |
| --- | --- |
| Weight of Debt Wd | 75% |
| Cost of Debt Kd | 9.50% |
| Tax | 29.12% |
| Post tax Kd | 6.73% |
| Weight of Equity We | 25% |
| Cost of Equity Ke | 18.00% |
| WACC | 9.55% |

| Payback Period of the Project |  |  |
| --- | --- | --- |
| Financial Year | Cash Accrual | Accumulated Cash Accrual |
| 31-Mar-27 | 69.20 | 69.20 |
| 31-Mar-28 | 52.84 | 122.05 |
| 31-Mar-29 | 50.11 | 172.16 |
| 31-Mar-30 | 51.01 | 223.17 |
| 31-Mar-31 | 51.87 | 275.04 |
| 31-Mar-32 | 53.02 | 328.06 |
| 31-Mar-33 | 53.60 | 381.66 |
| 31-Mar-34 | 54.48 | 436.15 |
| 31-Mar-35 | 55.32 | 491.47 |
| 31-Mar-36 | 54.88 | 546.35 |
| 31-Mar-37 | 47.71 | 594.05 |
| 31-Mar-38 | 47.84 | 641.89 |
| 31-Mar-39 | 48.02 | 689.92 |
| 31-Mar-40 | 48.52 | 738.44 |
| 31-Mar-41 | 48.60 | 787.04 |
| 31-Mar-42 | 48.99 | 836.03 |
| 31-Mar-43 | 49.37 | 885.41 |
| 31-Mar-44 | 50.04 | 935.45 |
| 31-Mar-45 | 50.26 | 985.71 |
| 31-Mar-46 | 50.76 | 1036.47 |
| 31-Mar-47 | 51.81 | 1088.28 |
| 31-Mar-48 | 68.90 | 1157.18 |
| 31-Mar-49 | 67.98 | 1225.16 |
| 31-Mar-50 | 67.33 | 1292.49 |
| 31-Mar-51 | 66.62 | 1359.11 |
| 31-Mar-52 | 66.17 | 1425.28 |
| Total | 1425.28 |  |
| Total Project Cost | INR 467.62 Crore |  |
| Payback Period | 9.86 Years |  |

Thus, the project will be having a payback period of 9.86 years and NPV & IRR of the project is INR 338 Crore & 18.65% respectively from C.O.D to loan repayment period, which indicates worthiness of the project.

- SENSITIVITY ANALYSIS:

Sensitivity analysis of the project with respect to 5% & 10% decrease in the revenue, 5% & 10% increase in the operating cost and 1% increment in the proposed interest rate has been shown in the below table:

| Sensitivity Analysis of D.S.CR, NPV & IRR |  |  |  |  |
| --- | --- | --- | --- | --- |
| S. No. | Particular | Average D.S.C.R | NPV | IRR |
|  | As a base case | 2.11 | INR 338 Cr. | 18.65% |
|  | If the projected revenue decreased by 5% | 1.99 | INR 301 Cr. | 17.71% |
|  | If the projected revenue decreased by 10% | 1.84 | INR 261 Cr. | 16.68% |
|  | If the projected operating cost increased by 5% | 2.09 | INR 331 Cr. | 18.47% |
|  | If the projected operating cost increased by 10% | 2.05 | INR 321 Cr. | 18.22% |
|  | If interest rate is increased by 2% | 1.93 | INR 282 Cr. | 18.67% |

Observation: The proposed project is found comparatively higher sensitive with respect to the downside variation in the projected revenue, than the upside variation in the projected operational and any surge in the interest rate.

- OTHER FINANCIAL RATIOS:

| Year Ending | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Return on Investment (%) | 44.12% | 45.09% | 42.79% | 43.56% | 44.29% | 45.24% | 45.78% | 46.53% | 47.25% | 46.83% | 40.74% | 40.85% | 41.00% |
| Return on Net Worth | 30.61% | 23.83% | 18.44% | 15.81% | 13.85% | 12.39% | 11.14% | 10.17% | 9.36% | 8.49% | 6.88% | 6.45% | 6.08% |
| DSCR | 3.08 | 1.71 | 1.67 | 1.72 | 1.76 | 1.82 | 1.87 | 1.92 | 1.98 | 2.02 | 1.86 | 1.91 | 1.96 |
| ISCR | 3.40 | 3.50 | 3.53 | 3.71 | 3.92 | 4.16 | 4.40 | 4.70 | 5.05 | 5.47 | 5.94 | 6.52 | 7.24 |
| Fixed Asset Coverage Ratio | 1.35 | 1.37 | 1.39 | 1.42 | 1.44 | 1.47 | 1.51 | 1.55 | 1.60 | 1.66 | 1.73 | 1.82 | 1.94 |
| TOL/TNW | 2.08 | 1.51 | 1.16 | 0.93 | 0.75 | 0.62 | 0.51 | 0.43 | 0.36 | 0.30 | 0.25 | 0.21 | 0.18 |
| Debt to Equity Ratio | 3.00 | 2.85 | 2.70 | 2.55 | 2.40 | 2.25 | 2.10 | 1.95 | 1.80 | 1.65 | 1.50 | 1.35 | 1.20 |

(Countinue)

| Year Ending | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Return on Investment (%) | 41.39% | 41.50% | 41.83% | 42.16% | 42.69% | 42.92% | 43.35% | 44.25% | 43.82% | 43.08% | 42.52% | 41.92% | 41.48% |
| Return on Net Worth | 5.79% | 5.48% | 5.24% | 5.01% | 4.83% | 4.63% | 4.47% | 4.36% | 4.14% | 3.91% | 3.72% | 3.54% | 3.38% |
| DSCR | 2.03 | 2.10 | 2.18 | 2.27 | 2.39 | 2.51 | 2.66 | 2.95 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| ISCR | 8.17 | 9.34 | 10.96 | 13.30 | 17.03 | 23.58 | 39.01 |  |  |  |  |  |  |
| Fixed Asset Coverage Ratio | 2.10 | 2.32 | 2.64 | 3.19 | 4.28 | 7.56 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| TOL/TNW | 0.15 | 0.12 | 0.09 | 0.07 | 0.05 | 0.03 | 0.02 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Debt to Equity Ratio | 1.05 | 0.90 | 0.75 | 0.60 | 0.45 | 0.30 | 0.15 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

- BREAK-EVEN ANALYSIS:

| Year Ending (INR Crore) | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Sales | 121.41 | 121.97 | 121.21 | 120.80 | 120.38 | 120.30 | 119.56 | 119.16 | 118.76 | 118.70 | 117.98 | 117.60 | 117.22 |
| Variable Expenses | 0.00 | 1.00 | 2.00 | 3.00 | 4.00 | 5.00 | 6.00 | 7.00 | 8.00 | 9.00 | 10.00 | 11.00 | 12.00 |
| Contribution | 121.41 | 120.97 | 119.21 | 117.80 | 116.38 | 115.30 | 113.56 | 112.16 | 110.76 | 109.70 | 107.98 | 106.60 | 105.22 |
| Fixed Expenses | 25.82 | 25.86 | 30.01 | 30.17 | 30.38 | 30.64 | 30.80 | 31.01 | 31.27 | 31.56 | 31.78 | 32.03 | 32.35 |
| Profit / PBT | 95.58 | 95.11 | 89.21 | 87.63 | 86.00 | 84.66 | 82.76 | 81.16 | 79.50 | 78.13 | 76.20 | 74.57 | 72.87 |
| PV RATIO | 100% | 99.18% | 98.35% | 97.52% | 96.68% | 95.84% | 94.98% | 94.13% | 93.26% | 92.42% | 91.52% | 90.65% | 89.76% |
| BEP Sales | 25.82 | 26.07 | 30.51 | 30.94 | 31.43 | 31.96 | 32.43 | 32.94 | 33.53 | 34.15 | 34.72 | 35.34 | 36.04 |
| BEP% (BEP Sales / sales) | 21.27% | 21.37% | 25.17% | 25.61% | 26.11% | 26.57% | 27.12% | 27.64% | 28.23% | 28.77% | 29.43% | 30.05% | 30.75% |

(Countinue)

| Year Ending (INR Crore) | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Sales | 117.16 | 116.47 | 116.10 | 115.74 | 115.69 | 115.02 | 114.67 | 114.32 | 114.29 | 113.63 | 113.30 | 112.96 | 112.94 |
| Variable Expenses | 13.00 | 14.00 | 15.00 | 16.00 | 17.00 | 18.00 | 19.00 | 20.00 | 21.00 | 22.00 | 23.00 | 24.00 | 25.00 |
| Contribution | 104.16 | 102.47 | 101.10 | 99.74 | 98.69 | 97.02 | 95.67 | 94.32 | 93.29 | 91.63 | 90.30 | 88.96 | 87.94 |
| Fixed Expenses | 32.70 | 32.98 | 33.29 | 33.67 | 34.08 | 34.43 | 34.81 | 35.27 | 35.76 | 36.20 | 36.66 | 37.22 | 37.80 |
| Profit / PBT | 71.46 | 69.49 | 67.81 | 66.07 | 64.61 | 62.59 | 60.86 | 59.04 | 57.52 | 55.43 | 53.63 | 51.74 | 50.14 |
| PV RATIO | 88.90% | 87.98% | 87.08% | 86.18% | 85.31% | 84.35% | 83.43% | 82.50% | 81.62% | 80.64% | 79.70% | 78.75% | 77.86% |
| BEP Sales | 36.78 | 37.48 | 38.22 | 39.07 | 39.95 | 40.82 | 41.72 | 42.75 | 43.81 | 44.89 | 46.00 | 47.26 | 48.55 |
| BEP% | 31.39% | 32.18% | 32.92% | 33.76% | 34.53% | 35.49% | 36.39% | 37.40% | 38.34% | 39.51% | 40.60% | 41.84% | 42.98% |

- TERM LOAN INPUTS:

| Term Loan Repayment Inputs |  |
| --- | --- |
| Total loan amount | INR 350.71 Crore |
| Rate of Interest | 9.50% |
| 1st Disbursement | Dec-24 |
| IDC Start & End Month | Dec-24 to March-26 |
| IDC Period (construction period) | 16 Month |
| Commencement /Operation Start | 1st April 2026 |
| Moratorium Start & End Month (only interest to pay) | Dec 2024 to March 2027 |
| Moratorium Period after COD | 12 Month |
| Repayment Start | April-27 |
| Repayment End | March-2047 |
| Repayment Period | 20 Years |

(INR Crore)

| Year Ending | 31-Mar-25 | 31-Mar-26 | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Months Counter | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Opening Bal | 0.00 | 140.28 | 350.71 | 350.71 | 333.18 | 315.64 | 298.10 | 280.57 | 263.03 | 245.50 | 227.96 | 210.43 | 192.89 | 175.36 |
| Disbursement of loan | 140.28 | 210.43 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Repayment | 0.00 | 0.00 | 0.00 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 |
| Closing Principal o/s | 140.28 | 350.71 | 350.71 | 333.18 | 315.64 | 298.10 | 280.57 | 263.03 | 245.50 | 227.96 | 210.43 | 192.89 | 175.36 | 157.82 |
| Interest | 2.78 | 24.99 | 33.32 | 32.48 | 30.82 | 29.15 | 27.49 | 25.82 | 24.16 | 22.49 | 20.82 | 19.16 | 17.49 | 15.83 |
| IDC | 2.78 | 24.99 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| TL Interest | 0.00 | 0.00 | 33.32 | 32.48 | 30.82 | 29.15 | 27.49 | 25.82 | 24.16 | 22.49 | 20.82 | 19.16 | 17.49 | 15.83 |

(Countinue)

| Year Ending | 31-Mar-39 | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year Counter | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Months Counter | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |
| Opening Bal | 157.82 | 140.28 | 122.75 | 105.21 | 87.68 | 70.14 | 52.61 | 35.07 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Disbursement | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Repayment | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Closing Principal o/s | 140.28 | 122.75 | 105.21 | 87.68 | 70.14 | 52.61 | 35.07 | 17.54 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Interest | 14.16 | 12.49 | 10.83 | 9.16 | 7.50 | 5.83 | 4.16 | 2.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| IDC | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| TL Interest | 14.16 | 12.49 | 10.83 | 9.16 | 7.50 | 5.83 | 4.16 | 2.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

- DEPRECIATION SCHEDULE (STRAIGHT  LINE METHOD):

(INR Crore)

| Depreciation Schedule as per Company's Act, 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Particular | 31-Mar-27 | 31-Mar-28 | 31-Mar-29 | 31-Mar-30 | 31-Mar-31 | 31-Mar-32 | 31-Mar-33 | 31-Mar-34 | 31-Mar-35 | 31-Mar-36 | 31-Mar-37 | 31-Mar-38 | 31-Mar-39 |
| Building & Civil Works | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 |
| SLM Depreciation | 0.740 | 0.742 | 0.740 | 0.740 | 0.740 | 0.742 | 0.740 | 0.740 | 0.740 | 0.742 | 0.740 | 0.740 | 0.740 |
| Plant & Machinery | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 |
| SLM Depreciation Plant & Machinery | 16.88 | 16.93 | 16.88 | 16.88 | 16.88 | 16.93 | 16.88 | 16.88 | 16.88 | 16.93 | 16.88 | 16.88 | 16.88 |
| Total SLM Depreciation | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 |

(Countinue)

| Depreciation Schedule as per Company's Act, 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Particular | 31-Mar-40 | 31-Mar-41 | 31-Mar-42 | 31-Mar-43 | 31-Mar-44 | 31-Mar-45 | 31-Mar-46 | 31-Mar-47 | 31-Mar-48 | 31-Mar-49 | 31-Mar-50 | 31-Mar-51 | 31-Mar-52 |
| Building & Civil Works | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 | 23.38 |
| SLM Depreciation | 0.742 | 0.740 | 0.740 | 0.740 | 0.742 | 0.740 | 0.740 | 0.740 | 0.742 | 0.740 | 0.740 | 0.740 | 0.742 |
| Plant & Machinery | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 | 444.23 |
| SLM Depreciation | 16.93 | 16.88 | 16.88 | 16.88 | 16.93 | 16.88 | 16.88 | 16.88 | 16.93 | 16.88 | 16.88 | 16.88 | 16.93 |
| Total SLM Depreciation | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 | 17.62 | 17.62 | 17.62 | 17.67 |

- KEY ASSUMPTIONS & BASIS:

| S. No. | Item | Assumptions and Basis |
| --- | --- | --- |
|  | General | - The projections of the proposed captive hybrid wind-solar power plant are done for the period from FY 2027 to FY 2052, ~26 years, to cover the term loan period as per the industry best practices. It is assumed that the plant will be achieving COD on 1st April 2026. - We have considered both Revenue & cost based model (top to bottom approach) while making the future financial projections. - Revenue modelling has been done based on the quantity of the proposed production as per the letter of intent (LOI) with the OMC (IOCL) and pricing circular of Compressed Bio Gas under SATAT scheme CO/AE&SD/01 dated 20th May 2022. - Expense modelling has been done based on the required resources and current market inputs such as cost, supply etc. and few expenses projected as % of sales as per the best practice of the industry. - The plant is assumed to be operational for 350 days for 24 hours annually, while operation days are 182 in FY 2026 due to implementation period till September 2025. |
|  | Revenue Build up | - Company will be generating the revenue by selling 6TPD Bio-CNG to IOCL as per LOI with OMC dated 3rd Nov 2023 (Ref: IndianOil/SATAT/01/3589) and 24 TPD fermented organic solid manure/fertilizer as its by-products. Below table shows the Revenue of the company @ 100% capacity: Revenue @100% capacity. Products; Unit Price; Annual Quantity; Amount (INR). Bio-CNG; 62.86 INR/Kg; 21,00,000 kg; 13,20,06,000. Bio Fertilizer; 6.00 INR/Kg; 84,00,000 kg; 5,04,00,000. Total Revenue (INR); 18,24,06,000. - Thus the company is expected to generate INR 18.24 Crore annual revenue. In the initial year there are 182 operating days and projected revenue of the company is 9.49 Cr. which is expected to increase up to INR 28.30 Crore till FY 2035. - Revenue of the Company is expected to grow at the rate of 5% Y-o-Y basis from FY 2028, since selling price are assumed to be inflated @5% during the forecasted period. - Further, Company has paid a GST of INR 3.98 Crore to commission the proposed plant, which has been adjusted as GST input from FY 2026 to FY 2030 and considered as other income for the company. |
|  | Pricing (Average Price Per Unit) | - Proposed selling price per unit of CBG and by-products are shown in the below table: Selling price per unit. Products; Unit prices. Selling price of Bio-CNG; INR 62.86 per kg. Selling price of solid organic fertilizer; INR 7.00 per kg. - Company has already signed a LOI with Indian Oil Corporation Ltd dated 3rd Nov 2023 (Ref: IndianOil/SATAT/01/3589). However signing commercial agreement between IOCL & company is in the process and Retail outlet for procurement will be allocated before C.O.D. - As informed by the client, company has planned to sell its Bio CNG at two Retail Outlets of IOCL at Panipat and Yamuna Nagar in Haryana. The current retail selling price of CNG at OMC outlets in Panipat and Yamuna Nagar is around INR 80.40 per kg on 28th May 2024. (https://www.v3cars.com/haryana/cng-price-in-yamunanagar), however the procurement price of Bio-CNG at Indian Oil as per the SATAT Scheme falls under the slab of INR 62.86 per kg without GST. Kindly refer “Section F” of the report for detailed proposed pricing arrangements. - As per the shared agreement with Chandigarh based facilitator M/s Sevozone Energies & Fertilizers Pvt Ltd (related party) for sale/handling of Bio-fertilizer produced at the proposed unit, ~ 20 TPD Bio fertilizer will be selling out at an agreed price of INR 8-10 per kg. - As per the shared agreement dated 15th July 2024 with M/s Anagram Development and farmers producers Private Ltd (FPO) for sale/handling of Bio-fertilizer produced at the proposed unit, Bio fertilizer will be selling out at an agreed price of INR 6.00 per kg which is reasonable and competitive rate of the market. For reference, IPL Rohana CBG Plant is selling FOM @ INR 10 per kg in 30 kg bags at present. - An escalation factor of 5% has been considered in the prices of the sellable products during the forecasted periods considering the micro and macro-economic factors. |
|  | Capacity Utilization | - The proposed CBG generating plant will be commissioned with a Design capacity of 14,500 M3/Day which can generate ~6 TPD Bio CNG per day, company has proposed to operate the plant at 100% of the designed capacity to generate 6000 Kg Bio-CNG per day as per letter of Intent (LOI) with Indian Oil under SATAT scheme. |
|  | Capital Expenditure | - As per the sale deed executed on 19th June 2024, promoters of the Company has purchased a 5.048 Acre (2.043 Hectare) agricultural land at Khata No, 208, 42, 226 Khasra No. 161/1, 160, 157 Village- Reda Harsana, Tehsil - Un, District- Shamli U.P 247778. Total cost of the land would be INR ~4.34 Crore including INR 10 lakhs for Change of land use (CLU) and other charges. - The estimated cost of the Building & Civil works is ~INR 810.69 lakhs including applicable GST and 10% EPC consultant cost as per the signed agreement. Cost of the Building & Civil works has been considered on the basis of shared details/EPC contract provided to us by the client. As a TEV consultant we have checked major unit cost considered in EPC contract which we found in permissible range. - As per shared EPC contract provided by the client, the estimated cost for plant & machinery will be ~INR 1713.76 lakhs including applicable GST and 10% EPC fees. ~45% of TPC is the cost Plant & Machinery. The estimated cost of the Plant & Machinery has been provided to us by the client as per EPC agreement. However, as a TEV consultant, the cost of major plant & machinery has been verified by us independently, which we found reasonable & in the permissible range although the cost may change as per specifications & brand. - The cost of Electrical, Instrumentation, PLC, data collection is INR 279.20 lakhs including GST & 10% EPC fess. Tentative cost of Off-site Facilities and office equipment is INR 63.51 lakhs including applicable GST. We found that the costs are in the line with prevailing market standard. - As per the data/information provided by the client, applicable Interest during Construction (IDC) is 11.50%. As per the proposed Loan repayment schedule, company is required to pay INR 2.42 Crore as IDC from September 2024 to September 2025 (13 months). - Preliminary & Pre-Operative Expenses has been considered based on the estimate of company’s resources involvement as INR 2.40 Crore. However, we have not recieved any invoices/bills against these tentative costs considered. We recommend that the bank/financial institutions advice the company to submit actual cost based on the final quotations/invoices/bills. This will help validate the assertion of different costs considered by the client. - Contingency cost of INR 0.57 Crore has been considered based on general assumption and professional experience (~2% of hard cost). - Hence, INR 6.49 Crore per ton including land, GST, transportation IDC, pre-operative and preliminary expenses etc. will be the capex for this proposed plant, which we found in the line with industrial and sectoral benchmarks. As per Ministry of New and Renewable energy, the approx. CAPEX of installing a 5 TPD capacity CBG plant is estimated between INR 20-25 crore and ~75 80% of the CAPEX cost is for purchasing plant machinery. (https://cdn.cseindia.org/attachments/0.11235300_1687759489_cse---overview-and-current-status-of--cbg-in-india.pdf) |
|  | Expenses | - As per the agreement with M/s. Anagram Development and Farmer Producer Company Limited (FPO) on 15th July 2024 shared by the client, FPO will supply 100 ton per day Agriculture Residual/Napier grass and 40-50 ton per day Sugarcane press mud. However, Sugarcane press mud supply is depending on the availability and requirement of Company. - As per the agreement, rate of chopped Napier grass has been considered as INR 100 per quintals i.e. INR 1.00 per kg. Escalation of 5% is considered during forecasted period. - As per information provided by the client, estimated annual consumption of the power will be 5,884 Kwh per day. Applicable tariff in Uttara Pradesh is INR 8 per Kwh. An escalation rate of 5% is assumed on it. - As per the data/information provided by the client, ~28 employees will be deployed initially based on the requirement. 10% escalation rate has been considered on the salary & wages of the proposed manpower. - As per informed by the client, Packaging cost of FOM is considered as INR 20 per 50 kg bag i.e. 0.40 per kg for projected period. - Transportation cost has been considered as 3% of the total revenue after assessing the distance of proposed IOCL’s RO from the project location. Marketing & Selling & Distribution expenses has been considered as 1.50% of the revenue. - Maintenance of the plant has been considered as per the industrial trends as shown in the below table: Maintenance on Plant (% of Gross Block). Civil; 0.50%. P&M; 0.50%. Electricity Infrastructure; 0.50%. Vehicles; 0.25%. Office equipment; 0.25%. - Plant and Administrative Overhead Expenses and Insurance Expenses are considered as 1.50% of revenue and 0.25% of net block respectively during the projected period. - Other manufacturing expenses are considered as 1.50% of Revenue. |
|  | Term Loan | - The project is proposed to be funded through a term loan of INR 27.25 crores and promoter’s margin of INR 11.67 crores. - Interest rate has been considered as 11% on the term loan. - Further, as per the working capital assessment, the working capital will require as INR 2.06 Crore, which will be funded through WC loan of INR 1.50 Cr. and promoter’s margin of INR 52 lakhs (~25% of required WC). |

Key Findings:

      - Average DSCR, EBIDTA margin, EBIT margin is 2.60, 56.60%, and 48.53% respectively during the estimated period.

      - D.S.C.R of the proposed Bio CBG plant is found highly sensitive with respect to any downside fluctuation in the projected revenue.

      - The company is having a positive NPV and IRR of INR 16.14 Crore and 26.10% respectively from C.OD to loan repayment period while it may vary with changes in the assumptions & micro and macro-economic trends considered as on date.

      - The proposed project is having a payback period of 4.49 years.

      - Based on the above key financial ratios of the proposed Project during the forecasted period shows that the project appears financially viable if the promoters of the project are able to maintain assumed capacity utilization, revenue and can contain cost as assumed above in the calculation.

| PART N | CONCLUSION |
| --- | --- |

Based on the technological, economical and market analysis done above, various assumptions of sectoral trends taken, product pricing to be adopted by the company, the Project appears to be Techno-commercially viable subject to the risks, threats, weaknesses, limitations of the product as detailed previously.

As per financial projections for the estimated period, Average DSCR, EBITDA Margin and EBIT Margin of the project are 2.60, 56.60% and 48.53% respectively, where higher DSCR is the indicator of the project capability to pay out its outstanding debt and EBITDA margin shows the capability of the project to generate the operating profits over the forecasted period. Also the project is having the payback period of 4.49 Years in the line with sectoral trends.

The proposed Bio-CNG generating facility is having a positive NPV and IRR as INR 16.14 Crore and 26.10% respectively from C.O.D till loan repayment period as the industry is expectedly growing at a CAGR of 6.34% during the forecasted period. While it is not avoidable that the future projections may change in the upcoming years due to various factors impacting the operation, managerial, financial efficiency and economies of scale of the project.

While it would be depending on the management’s capability in future that how efficiently company adopts marketing and advertisement strategy, supply chain and carry out inventory & resource management to achieve higher profitability. After considering the foreseen demand of the Bio CNG and its by-products domestically and globally, various initiatives taken by the government, financial analysis of the project based on the assumptions taken over the projected period, it appears reasonable to comment that the proposed project is “Technically and Economically” Viable subject to current assumptions considered and occurring the same in the upcoming years same as the forecasted period which is dependent on the sincerity and efforts of the management and various micro and macroeconomic & industry situation.

We have tried our level best to analyse the Project techno-economic feasibility of the Project based on the Industry research, Project information and various futuristic assumption taken within the limitations and challenges came in front of us. However achieving the financial milestones depends on the ability, sincerity and efforts of the company, promoters and its key management to maintain the projected revenue level Y-o-Y basis keeping the fact in mind that the project is found sensitive with respect to the down side fluctuation in the revenue.

| Declaration | - The undersigned does not have any direct/indirect interest in the above property/project/Company. - The information furnished herein is true and correct to the best of our knowledge, logical and scientific assumptions. - This TEV Report is carried out by our Financial Analyst team on the request from M/s Superior Agro Ventures Private Limited. - Meeting of Financial projections will be subject to the market & economy stability factors, judicious business operations and proper & timely implementation of the project and putting proper plan for achieving high productivity, efficiency and achieving cost saving benefits to increase profitability. - We have submitted TEV report to M/s Superior Agro Ventures Private Limited. |
| --- | --- |
| Number of Pages in the Report | 97 |
| Enclosed Documents | Disclaimer & Remarks 92-95 |
| Place | Noida |
| Date | 25th July 2024 |

| FOR ON BEHALF OF M/S. R.K. ASSOCIATES VALUER & TECHNO ENGINEERING CONSULTANTS PVT. LTD. |  |  |
| --- | --- | --- |
| SURVEYED BY | PREPARED BY | REVIEWED BY |
| Mr. Sachin Pandey | Mr. Gaurav Kumar | Mr. Rachit Gupta |

| PART O | DISCLAIMER ¦ REMARKS |
| --- | --- |

      - No employee or member of R.K Associates has any direct/ indirect interest in the Project.

      - This report is prepared based on the copies of the documents/ information which the Bank/ Company has provided to us out of the standard checklist of documents sought from them and further based on our assumptions and limiting conditions. The client/owner and its management/representatives warranted to us that the information they supplied was complete, accurate and true and correct to the best of their knowledge. All such information provided to us has been relied upon in good faith and we have assumed that it is true and correct in all respect. I/We shall not be liable for any loss, damages, cost or expenses arising from fraudulent acts, misrepresentations, or wilful default on part of the owner, company, its directors, employee, representative or agents. Verification or cross checking of the documents provided to us from the originals or from any Govt. departments/ Record of Registrar has not been done at our end since this is beyond the scope of our work. If at any time in future, it is found or came to our knowledge that misrepresentation of facts or incomplete or distorted information has been provided to us then this report shall automatically become null & void.

      - Legal aspects for e.g. investigation of title, ownership rights, lien, charge, mortgage, lease, sanctioned maps, verification of documents, etc. have not been done at our end and same has to be taken care by legal expert/ Advocate. It is assumed that the concerned Lender/ Financial Institution has satisfied them with the authenticity of the documents, information given to us and for which the legal verification has been already taken and cleared by the competent Advocate before requesting for this report. I/ We assume no responsibility for the legal matters including, but not limited to, legal or title concerns.

      - This report is a general analysis of the project based on the scope mentioned in the report. This is not an Audit report, Design document, DPR or Techno feasibility study. All the information gathered is based on the facts seen on the site during survey, verbal discussion & documentary evidence provided by the client and is believed that information given by the company is true best of their knowledge.

      - This Techno Economic-Viability study is prepared based on certain futuristic assumption which are intra dependent on economic, market and sectorial growth condition in future and socio-economic, socio-political condition at macro and micro level.

      - Meeting of assumption and financial ratio will entirely depend on the sincerity and efforts of the company, promoters and its key managerial performance.

      - All observations mentioned in the report is only based on the visual observation and the documents/ data/ information provided by the client. No mechanical/ technical tests, measurements or any design review have been performed or carried out from our side during Project assessment.

      - This report has been diligently prepared by our techno-financial team to the best of their ability. However, it's important to note that the recommendations provided in this Total Economic Viability (TEV) assessment do not imply an endorsement, validation, or certification of the accuracy or completeness of the disclosed information by the involved stakeholders. Furthermore, we do not claim or endorse that the opinions presented herein are the sole best course of action for decision-makers to follow. There may exist additional approaches and inputs that have not been covered within this report or fall outside the scope of this report.

      - Bank/FII should ONLY take this report as an Advisory document from the Financial/ Chartered Engineering firm and its specifically advised to the creditor to cross verifies the original documents for the facts mentioned in the report which can be availed from the borrowing company directly.

      - In case of any default in loans or the credit facility extended to the borrowing company, R.K Associates shall not be held responsible for whatsoever reason may be and any request for seeking any explanation from the employee/s of R.K Associates will not be entertained at any instance or situation.

      - The documents, information, data provided to us during the course of this assessment by the client are reviewed only up to the extent required in relation to the scope of the work. No document has been reviewed beyond the scope of the work.

      - This report only contains general assessment & opinion as per the scope of work evaluated as per the information given in the copy of documents, information, data provided to us and/ and confirmed by the owner/ owner representative to us at site which has been relied upon in good faith. It doesn’t contain any other recommendations of any sort including but not limited to express of any opinion on the suitability or otherwise of entering into any transaction with the borrower.

      - We have relied on data from third party, external sources & information available on public domain also to conclude this report. These sources are believed to be reliable and therefore, we assume no liability for the truth or accuracy of any data, opinions or estimates furnished by others that have been used in this analysis. Where we have relied on data, opinions or estimates from external sources, reasonable care has been taken to ensure that such data has been correctly extracted from those sources and /or reproduced in its proper form and context, however still we can’t vouch its authenticity, correctness or accuracy.

      - This Report is prepared by our competent technical team which includes Engineers and financial experts & analysts.

      - This is just an opinion report and doesn’t hold any binding on anyone. It is requested from the concerned Financial Institution which is using this report for taking financial decision on the project that they should consider all the different associated relevant & related factors also before taking any business decision based on the content of this report.

      - All Pages of the report including annexure are signed and stamped from our office. In case any paper in the report is without stamp & signature then this should not be considered a valid paper issued from this office.

      - Though adequate care has been taken while preparing this report as per its scope, but still we can’t rule out typing, human errors, over sightedness of any information or any other mistakes. Therefore, the concerned organization is advised to satisfy themselves that the report is complete & satisfactory in all respect. Intimation regarding any discrepancy shall be brought into our notice immediately. If no intimation is received within 15 (Fifteen) days in writing from the date of issuance of the report, to rectify these timely, then it shall be considered that the report is complete in all respect and has been accepted by the client up to their satisfaction & use and further to which R.K Associates shall not be held responsible in any manner.

      - Defect Liability Period is 15 DAYS. We request the concerned authorized reader of this report to check the contents, data and calculations in the report within this period and intimate us in writing if any corrections are required or in case of any other concern with the contents or opinion mentioned in the report. Corrections only related to typographical, calculation, spelling mistakes, incorrect data/ figures/ statement will be entertained within the defect liability period. Any new changes for any additional information in already approved report will be regarded as additional work for which additional fees may be charged. No request for any illegitimate change in regard to any facts & figures will be entertained.

      - R.K Associates encourages its customers to give feedback or inform concerns over its services through proper channel at valuers@rkassociates.org in writing within 15 days of report delivery. After this period no concern/ complaint/ proceedings in connection with the Techno- Economic Viability Study Services will be entertained due to possible change in situation and condition of the subject Project.

      - Our Data retention policy is of ONE YEAR. After this period, we remove all the concerned records related to the assignment from our repository. No clarification or query can be answered after this period due to unavailability of the data.

      - This Techno Economic Viability Study report is governed by our (1) Internal Policies, Processes & Standard Operating Procedures, (2) Information/ Data/ Inputs given to us by the client and (3) Information/ Data/ Facts given to us by our field/ office technical team. Management of R.K Associates never gives acceptance to any unethical or unprofessional practice which may affect fair, correct & impartial assessment and which is against any prevailing law. In case of any indication of any negligence, default, incorrect, misleading, misrepresentation or distortion of facts in the report then it is the responsibility of the user of this report to immediately or at least within the defect liability period bring all such act into notice of R.K Associates management so that corrective measures can be taken instantly.

      - R.K Associates never releases any report doing alterations or modifications from pen. In case any information/ figure of this report is found altered with pen then this report will automatically become null & void.

      - If this report is prepared for the matter under litigation in any Indian court, no official or employee of R.K Associates will be under any obligation to give in person appearance in the court as a testimony. For any explanation or clarification, only written reply can be submitted on payment of charges by the plaintiff or respondent which will be 10% of the original fees charged where minimum charges will be Rs. 15,000/.

EXTRACTS OF IMPORTANT STATUTORY APPROVALS PROVIDED BY THE CLIENT