## Sheet1
S. No. | Critical Activities | Date
1 | Date of issuance of LOA | 2024-03-01
2 | Commencement of Procurement Activity | 2024-09-01
3 | Completion of preliminary civil work including foundation for Module Mounting Structure | 2024-12-01
4 | Receipt of Inverters at Site | 2024-12-01
5 | Transmission Line & Bay Work completion | 2025-01-01
6 | Receipt of Transformers and other key equipments | 2025-02-01
7 | Receipt of Solar Module & inverters at Site | 2025-03-01
8 | Commissioning | 2025-07-01