**Implementation Schedule**

| **Activity** | **Start Time** | **End Time** | **Remarks** |
| --- | --- | --- | --- |
| Land Acquisition | April 24 | Sep 24  | Acquired in Aug 24 |
| Technical Study and Bidding Procedure | April 24 | Dec 24  | Quotations obtained and shall be finalised on time |
| Building Construction | Nov 24 | Dec 25 | Shall be start upon approval of building plan |
| Equipment Procurement | Nov 24 | Jun 25 | Major long lead items shall be procured |
| Installation and Commissioning | Mar 25 | Jan 26 |  |
| Trial run | Mar 26 | Mar 26 |  |
| Commercial Production Start | April 26 |  |  |