## Sheet1
CONSTRUCTION LINKED PAYMENT PLAN FOR 84 PROJECT
Sr.No. | PARTICULARS | TIME | INSTALMENT TO BE PAID
1 | APPLICATION MONEY |  | 9.90/- LACS
2 | BOOKING AMOUNT AT THE TIME OF SUBMISSION OF APPLICATION FORM |  | 9% (LESS APPLICATION MONEY)(SIMULTANEOUSLY BBA HAS TO BE EXECUTED AND REGISTERED)
3 | WITHIN 90 DAYS OF BOOKING | 90 DAYS | 16%
4 | COMPLETION OF UPPER BASEMENT | 12 MONTHS* | 10%
5 | COMPLETION OF 4TH FLOOR ROOF SLAB |  | 10%
6 | COMPLETION OF 18TH FLOOR ROOF SLAB |  | 10%
7 | COMPLETION OF 30TH FLOOR ROOF SLAB |  | 10%
8 | COMPLETION OF TERRACE FLOOR |  | 10%
9 | ON COMPLETION OF INTERNAL PLASTER |  | 10%
10 | ON COMPLETION OF FLOORING (EXCEL, WOODING FLOORING) |  | 5%
11 | ON APPLICATION OF OCCUPATION CERTIFICATE |  | 5%
12 | ON OFFER OF POSSESSION |  | 5% (Along with charges as applicable at the time of offer of possession.)
1. The taxes as applicable would be payable at each stage. Allottee(s) shall be liable to execute and get registered the Builder Buyer's Agreement/Agreement of Sale. The Payment Plan/Schedule may be preponed if the occupation/Part Occupation Certificate (OC / Part OC) is received before the scheduled possession period.