## Sheet1
| TABLE - 1 : Project cost break-up - 10 TPD CBG Project at Baheri |  |  |  | all numbers are in Rs. Crs.
|  | For 10 TPD Capacity | Phase-I | for Phase-II | Spent till Aug'24 by the Promoter | Balance to spent
| Land | 1.9 | 1.15 | 0.75 | 0.75 | 0
| Building & Other Civil Works | 11 | 8.74 | 2.26 | 0.7 | 1.56
| Plant & Machinery | 63.4 | 26.16 | 37.24 | 16.92 | 20.32 | (proposed break-up of balance P&M expenses is tabulated below in Table-2)
| Pre-operative Expenses | 5.31 | 1.75 | 3.56 | 3.56 | 0
| Interest on Term Loan during Construction | 2.6 | 2.4 | 0.2 | 0.2 | 0
| Margin for Working Capital | 0.56 | 0.21 | 0.35 |  | 0.35
|  | - | - | - | - | -
| TOTAL COST OF THE PROJECT | 84.77 | 40.41 | 44.36 | 22.13 | 22.23
59.339
TABLE-2 : Break-up of remaining P&M expenditure for completing Phase-II Project (5 TPD)
| Anaerobic Digester (AD) Package (Vendor : PlanET Global Biogas GmbH) | 15.5375
| Digester Civil Works | 2.4 |  |  |  | 12600000
| Insulation, cladding and walkway around the Digester | 0.5
| Erection & Commissioning cost related to AD | 0.5
| Cabling - electrical | 0.5
| Engineering & designing | 0.3
| Consultants Fee (Safety, PESO, PCB,etc.) | 0.3
| SCADA (Automation) | 0.3
| Total | 20.3375
Note: cost mentioned above is includive of all duties, taxes, transportation, installation, supervision cost, etc.
| AD offer (in Euro) dated 30.09.2024 | 1401507.85 |  |  |  |  | 1.401.507,85
18.5% | Import Duty | 259278.9523
0.1% | Insurance | 1401.5079
1.6% | Freight Charges | 22424.1256
1.9% | Custom Clearance | 26628.6492
0.4% | Transportation Charges | 5606.0314
| Total (in Euro) | 1716847.1162
90.5 | in Rs. Crs. | 15.5375
| PlanET Offer (Dated 30.09.2024) | amount in Euros
32082
221238
454310
20000
93610
86539.85
141450
| Supply | 1049229.85
| Transportation | 101907
| Service | 250371
| Total | 1401507.85