**File No.:** **VIS (2024-25)-PL689-620859 Dated: 20-01-2025**

**COST VETTING ASSESSMENT**

**OF**

**M/S. JM HOLDINGS PVT LTD**

**SITUATED AT**

**PLOT NO. B1 & PLOT NO. B2, VILLAGE-KINALE, TALUKA-SAWANTWADI, SINDHUDURG MAHARASHTRA-416514**

**REPORT PREPARED FOR**

**STATE BANK OF INDIA, EXIM BRANCH, KOLKATA**

***\*\*Important - In case of any query/ issue or escalation you may please contact Incident Manager***

***at le@rkassociates.org. We will appreciate your feedback in order to improve our services.***

***NOTE: Please provide your feedback on the report within 15 days of its submission after which report will be considered to be correct***

**IMPORTANT NOTICE**

***COPYRIGHT FORMAT:*** *This report is prepared on the copyright format of R.K Associates to serve our clients with the best possible information and analysis to facilitate them to take rational business decisions. Legally no one can copy or distribute this format without prior approval from R.K Associates. It is meant only for the advisory/ reference purpose for the organization/s as mentioned on the cover page of this report. Distribution or use of this format by any organization or individual other than R.K Associates will be seen as an unlawful act and necessary legal action can be taken against the defaulters.*

*This report is intended for the sole use of the intended recipient/s and contains material that is STRICTLY CONFIDENTIAL AND PRIVATE.*

***DEFECT LIABILITY PERIOD:*** *- In case of any query/ issue or escalation you may please contact Incident Manager at le@rkassociates.org. We try to ensure maximum accuracy in the calculations done, rates adopted, assumptions taken and various other data points & information mentioned in the report but even still can’t rule out typing, human errors or any other bonafide mistakes. In case you find any such mistake or inaccuracy in any data point of the report, please help us by bringing all such points into our notice immediately or within 15 days of the r0eport delivery in writing, to rectify these timely failing after which R.K Associates won’t be held responsible for any such inaccuracy in any manner. We would highly appreciate your feedback in order to improve our services.*

|  |  |  |
| --- | --- | --- |
| **TABLE OF CONTENTS** | | |
|  | | |
| **SECTIONS** | **PARTICULARS** | **PAGE NO.** |
| **Part A** | **REPORT SUMMARY** | 04 |
| **Part B** | **COST VETTING ASSESSMENT** | 05 - 06 |
|  | 1. DESCRIPTION | 06 |
| 1. BUILDING & CIVIL WORKS: | 06 – 19 |
| **Part C** | **PHOTOGRAPHS** | 20 – 22 |
| **Part D** | **IMPORTANT DOCUMENTS EXHIBIT** | 23 – 24 |
| **Part E** | **REFERENCE** | 25 |
| **Part F** | **DISCLAIMER** | 25 - 26 |

|  |  |
| --- | --- |
| **PART A** | **REPORT SUMMARY** |

* **DOCUMENT NAME:** Cost Vetting Assessment
* **PREPARED FOR:** State Bank Of India, EXIM Branch, Kolkata
* **BORROWER:** M/s JM Holdings Pvt Ltd.
* **ASSET TYPE**: Building Structure & Civil works
* **ADDRESS OF THE ASSET**: Plot No. B1 & Plot No. B2, Village-Kinale, Taluka-Sawantwadi, Sindhudurg Maharashtra-416514.

|  |  |  |
| --- | --- | --- |
| **S. NO.** | **PARTICULARS** | **DESCRIPTION** |
|  | Date of Work Order | Via Letter dated 13-01-2025 |
|  | Date of site survey | 09-12-2024 |
|  | Documents provided for perusal | Bill of Quantity |
|  | Project Location | Plot No. B1 & Plot No. B2, Village- Kinale, Taluka-Sawantwadi, Sindhudurg Maharashtra-416514 |
|  | Borrowing Company | M/s. JM Holdings Pvt Ltd. |
|  | Type of Assessment | Cost vetting. |
|  | Scope of Assessment | Cost Vetting of the Building Structure & civil work |
|  | Nature of Asset | Building Structure |
|  | Total Project Cost as informed by the borrower | **Rs. 7.08 crores** (Including GST)  (*Including supply and installation as per the List/ quotations / invoices / Cost Estimate provided by the company.)* |
|  | Project Cost as assessed by the consultant | **Approx. Rs. 6.46 crore**(Including GST)  (*Including supply and installation as per the List/ quotations / invoices / Cost Estimate provided by the company.)* |
|  | Total number of pages with Annexure. | 38 |

|  |  |
| --- | --- |
| **PART B** | **COST VETTING ASSESSMENT** |

1. **DESCRIPTION**

This is a cost vetting document of the building structure located aforesaid address. As per the BOQ provided, the client proposed to develop Basement + Ground + 1st Floor, for two Villas i.e Villa 1 and Villa 2. The subject property is situated in hilly terrain with good scenic view of river.

During site visit it has been observed that the building structure is under construction. The detailed progress of the construction is as given below,

**Villa 1:**

|  |  |  |
| --- | --- | --- |
| **S. No.** | **Description** | **Status** |
| **1** | **Basement Floor** | 1. Super structure is completed. 2. Outer wall of the structure is complete. 3. Finishing & MEP work is not done. |
| **2** | **Ground Floor** | 1. Super structure is completed 2. Partition walls are constructed. Finishing & MEP work is not done. |
| **3** | **First Floor** | Columns already casted. Shuttering work for roof slab in progress. |
| **4** | **Boundary Wall** | Three side Boundary wall completed. |
| **5** | **Aesthetic** | RCC work of the swimming pool is completed and finishing work hasn’t been started |

**Villa 2:**

|  |  |  |
| --- | --- | --- |
| **S. No.** | **Description** | **Status** |
| **1** | **Basement Floor** | 1. Super structure is completed for both the Villas. 2. Outer wall of the structure is complete. 3. Finishing & MEP work is not done. |
| **2** | **Ground Floor** | 1. Super structure is completed 2. Partition walls are constructed. Finishing & MEP work is not done. |
| **3** | **First Floor** | Columns already casted. Shuttering work for roof slab in progress. |
| **4** | **Boundary Wall** | Three side Boundary wall completed. |
| **5** | **Aesthetic** | Work hasn’t started as of yet |

1. **BUILDING & CIVIL WORKS:**

The cost involved in the construction of proposed structures and other civil work has been calculated from our analysis and market research. For reference we have considered Rates from Goa Schedule of Rates 2019, CPWD 2023, DSR 2023, MSR 2023, rates from local contractors and online research.

Details estimate cost of the building construction is as shown below:

|  |  |  | **AS PER RKA FINDINGS** | |  |
| --- | --- | --- | --- | --- | --- |
| **S.NO.** | **DESCRIPTION** | **QTY** | **RATE** | **AMOUNT (Inclusive GST-18%)** | **AMOUNT (Exclusive GST)** |
| 1 | **Excavation** in **ordinary (soft) soil** including murrum (clayey sand mixed with kankar), backfilled soil in plinth for foundations of columns, wall foundations, pilecaps, underground tanks, plinth beams, trenches, m/c fnds, manholes,steps etc. including shoring, shuttering, dewatering wherever required (Until foundation work is complete) and removing, spreading and levelling surplus earth on site within an initial lead of 200m radius as directed by Engineer upto 2.0m depth. (Note:All backfilling, spreading, compacting of earth shall be carried out in layers not exceeding 200mm & compacted to a dry density of 90%) |  |  |  |  |
| 2 | **Excavation** in **laterite rock** requiring chiseling or rock breaker/ pneumatic hammer for foundations of columns, wall foundations, pilecaps, underground tanks, plinth beams, trenches, m/c fnds, manholes,steps etc. including shoring, shuttering, dewatering wherever required (Until foundation work is complete) and removing, spreading and levelling surplus earth on site within an initial lead of 100m radius as directed by Engineer upto 2.0m depth. (Note:All backfilling, spreading, compacting of earth shall be carried out in layers not exceeding 200mm & compacted to a dry density of 90%) . | 1500 | 1453.1 | 25,71,987 | 21,79,650 |
| 3 | General **Surface excavation** & excavation for roads, drains in **laterite rock** requiring chiseling upto an average depth of 2.5m including dewatering, surface dressing, shoring, strutting, stacking the excavated material required for backfilling & removing surplus material from the stacks and spreading same on site; lead not exceeding 200m from any outside face of building.. | QOR | 0 | - | - |
| 4 | **Backfilling** **approved excavated materials** under floors, bldg plinth, open trenches, tank foundation etc. in layers not more than 200mm thk including watering, ramming, levelling & through consolidation by power driven 10 MT roller (re-excavation of stacked material for backfill shall not be paid). (Compaction should achieve 95% Procter Density test) | 750 | 254.1 | 2,24,879 | 1,90,575 |
| 5 | **Laying** (consolidated) **rubble packing** with dry laterite boulders or quarried stone available on site under floors, foundations, trenches etc. blinded with approved murrum/rubble chips laid to required levels and slopes including watering, ramming & consolidating with power driven 10 MT roller etc. as directed. | 328 | 1420.1 | 5,49,166 | 4,65,395 |
| 6 | **Providing and Laying** (consolidated) **rubble packing** with dry laterite boulders or quarried stone under floors, foundations, trenches etc. blinded with approved murrum/rubble chips laid to required levels and slopes including watering, ramming & consolidating with power driven 10 MT roller etc. as directed. | 100 | 1768.8 | 2,08,718 | 1,76,880 |
| 7 | Breaking of laterite/brick or rubble masonry including removing of debris from site. | QOR | 0 | - | - |
| 8 | Breaking of RCC work (Reinf. scrap is owner's property) including removing of debris from site.. | QOR | 0 | - | - |
| 9 | Carting away from premises surplus excavated material & Debris | QOR | 0 | - | - |
| 10 | Providing and laying in position Plain cement concrete (PCC) nominal mix 1:3:6 with 20mm downward basalt/granite metal aggregates of approved quality under column footings, walls, plinth beams, trenches, drains, pits, under plinth and for all other PCC work with formwork, if any, including machine mixing, consolidating with heavy wooden rammers or vibrators, curing, levelling and finishing complete. | 180 | 7279.8 | 15,48,291 | 13,12,111 |
| 11 | Providing and laying in position Plain cement concrete (PCC) nominal mix 1:3:6 with 40mm downward basalt/granite metal aggregates of approved quality in Retaining walls with formwork, if any, including machine mixing, consolidating with heavy wooden rammers or vibrators, curing, levelling and finishing complete. | 20 | 7279.8 | 1,72,061 | 1,45,814 |
| 12 | Providing and laying in position controlled Reinforced cement concrete M-25/20 (nominal mix 1:1:2) using 20mm downward graded basalt/Granite metal aggregates of approved quality in RCC work at all levels, leads, heights, shapes including architectural effects like chases, ledges, moulds, arches, pockets for foundation and including all lifts & shuttering/centering, curing for : |  | 0 | - | - |
| 13 | i) foundations, raft, basement/underground water tank raft | 128 | 8719.7 | 13,12,599 | 11,12,372 |
| 14 | ii) RCC columns, pedestals, lift & basement/underground water tank walls | 145 | 9149.8 | 15,61,320 | 13,23,153 |
| 15 | iii) For all flat/sloping RCC slabs, floor beams, tie beams, lintels, chajjas, canopies, ledges, lofts, balconies, cantilever beam slabs, drop pardis, pergola beams, Arc or circular shaped beams & slabs, partly inverted beams, parapets and staircases (waist slab & steps), overhead tank base slab/walls/top slabs etc | 450 | 9912.1 | 52,63,325 | 44,60,445 |
| 16 | Supplying, cutting, bending, and placing in position as per RCC Drawing and instructions ribbed tor steel(IS-1786 & Tor certified) or HYSD (SAIL/Tisco) (with yield stress not less than 415 N/mm2.) at all location and heights including supplying and binding of G.I. binding (18 swg) wire/ ms binding wire(16swg) including placing of approved plastic/concrete cover blocks, chair supports etc complete. | 170 | 92049.1 | 1,84,65,049 | 1,56,48,347 |
| 17 | Supplying, Cutting, Fabricating, Erecting & Fixing in position as per drawing Square Hollow Section (SHS) IS4923 /Rectangular Hollow Section (RHS) IS4923/ Circular Hollow Section (CHS) IS1161 closed Structural Steel of approved make (Min Yeild Stress 310 Mpa) including straightening, bending, welding, full strength Butt welding wherever required, drilling holes, levelling, Surface to be prepared by wire brush cleaning or other mechanical means and there after immediately painting with minimum 1 coat of Red oxide followed by minimum 1 coat of Zinc chromate yellow paint (High build variety) and paint of approved colour(minimum 2 coats). etc. complete, at all heights from ground level for following items of work : (Rate to include the provision of tools, tackles for erection at all levels, temporary bracings, struts, etc. Holding down Botls /Bolts to be paid separately.) (base plate & pocket grouting with non shrink grout only shall be paid separately) |  | 0 | - | - |
| 18 | a) Roof trusses, purlins, bracing members, side cladding & gable members, portals, wind girders, columns, beams, gantry girders, platforms, ladders, staircases, rafters, battens, Gates. | 25 | 130229 | 38,41,756 | 32,55,725 |
| 19 | Supplying, Cutting, Fabricating, Erecting & Fixing in position as per drawing Structural Steel (Channels, Angles, Plates, I sections, Bars, T sections) of approved make including straightening, bending, welding , full strength Butt welding wherever required, drilling holes, levelling, Surface to be prepared by wire brush cleaning or other mechanical means and there after immediately painting with minimum 1 coat of Red oxide followed by minimum 1 coat of Zinc chromate yellow paint (High build variety) and paint of approved colour(minimum 2 coats). etc. complete, at all heights from ground level for following items of work : (Rate to include the provision of tools, tackles for erection at all levels, temporary bracings, struts, etc. Holding down Botls /Bolts to be paid separately.) (base plate & pocket grouting with non shrink grout only shall be paid separately) |  | 0 | - | - |
| 20 | a) Roof trusses, purlins, sag rods with threading , bracing members, side cladding & gable members, portals, wind girders, columns, beams, gantry girders, platforms, ladders, staircases, insert plates, edge angles with all necessary holdfasts, gusset plates, rafters, battens, base plates . | QOR | 0 | - | - |
| 21 | Supplying & fixing black bolts & nuts (supplied by Guest Keen Williams or Other manufacturer approved by the Engineer) upto 20mm dia for connections of structural steel members including washers, etc complete. | QOR | 0 | - | - |
| 22 | Supplying & fixing in position foundation anchor bolts upto 32mm dia and 1000mm long including washers, plates, threading etc. complete in all respect including primer | 992 | 132 | 1,54,545 | 1,30,970 |
| 23 | Providing and grouting column base plates/ cap plates etc 25-30mm thick with non shrink free flow grout (Dr. Fixit 5M Grout) including shuttering etc. complete. | 12 | 10793.8 | 1,57,807 | 1,33,735 |
| 24 | Providing & Fixing in position anchor fasterner using lokset a) 12mm | 61 | 78.925 | 5,634 | 4,775 |
| 25 | Providing & constructing 300mm or above thk laterite stone masonry in neatly dressed stones etc in c.m. 1:5 complete for walls below plinth, in foundation, retaining walls, sumps, drains, septic tanks, etc. including curing complete. | 56 | 8042.38 | 5,29,732 | 4,48,925 |
| 26 | Providing & constructing 230mm thk laterite stone masonry in neatly dressed stones etc in c.m. 1:4 complete above plinth in superstructure at all levels including walls, columns, as shown in drawings etc and including scaffolding, curing etc. complete. | 442 | 8042.38 | 41,94,202 | 35,54,408 |
| 27 | Providing & constructing 150mm thk laterite stone masonry in neatly dressed stones etc in c.m. 1:4 complete above plinth in superstructure at all levels including walls, columns, as shown in drawings etc and including scaffolding, curing etc. complete. | 28 | 710.424 | 23,581 | 19,984 |
| 28 | Providing and applying 12mm thick cement plaster (1:4) for all RCC/brick/block masonry work including bands, grooves, mouldings, if any, internally including scaffolding, curing etc complete as required at all levels. | 3642 | 823.262 | 35,38,115 | 29,98,403 |
| 29 | Providing, applying & Finishing fine with white cement based putty over plastered wall/ceilings with painter putty knife. Minimum 2 coats and average total thickness 1.00mm should be applied to prepare the surface even and smooth with polishing the surface with fine emery (p230 or more) and wiping residual dust complete. | 3642 | 288.959 | 12,41,853 | 10,52,418 |
| 30 | Providing and applying 18mm thick external sand faced cement plaster (1:4) in two coats including bands, grooves, mouldings, etc., if any, using approved waterproofing admixtures as per manufacturer's specifications and including scaffolding and making drip moulds, sponge finish wherever required or as directed at all levels. The second coat to be applied not earlier than 48 hrs of completion of 1st coat.( base coat 12mm to be kept rough & finished with second coat of 6mm thk) | 2792 | 997.821 | 32,87,087 | 27,85,667 |
| 31 | 6mm cement plaster to ceiling 1:4 (1 cement : 4 fine sand) | 1256 | 381.755 | 5,66,003 | 4,79,664 |
| 32 | Providing & applying waterproof neat cement punning to RCC/Masonry surfaces with smooth cement finish/ cement floating, inside drains & gutters, with integral waterproofer as directed. | 106 | 592.02 | 74,385 | 63,038 |
| 33 | Providing & applying two coats of White Wash (SuryaCem prepared from quick lime) to prepared surfaces of plaster/ RCCwork/ brickwork including scraping/scrubbing and cleaning of surfaces of grease/ dirt/ flaky portions/ dust, putty touchup, filling cracks/voids/minor damages, etc. complete including Fevicol DDL, if required, as per manufacturer's Specifications | 1256 | 42.955 | 63,686 | 53,971 |
| 34 | Providing & applying two coats of Acrylic Oil bound Distemper of desired shade (Asian Paints/ Nerolac/ Berger) to prepared surfaces of plaster/ RCCwork/ brickwork including scraping/scrubbing and cleaning of surfaces of grease/ dirt/ flaky portions/ dust, 1 coat of primer followed by putty touchup and applying 2nd coat of primer, filling cracks/voids/minor damages, etc. complete as per manufacturer's Specifications | 4899 | 204.215 | 11,80,477 | 10,00,404 |
| 35 | Providing & Applying two coats of Exterior Acrylic Emulsion of approved desired shade (ICI Weathershield/ Asian Apex/ Killick Snowcryl XT) to prepared surfaces of sand faced plaster/RCC work/brickwork including scraping/scrubbing and washing/ cleaning of surfaces of grease/ dirt/ flaky portions/ dust, Application of 1 coat of primer (Birla white Cement slurry or cemprover as per manufacturer's specifications), filling cracks/voids/minor damages, etc. complete as per manufacturer's Specifications. The contractor to give 5 yrs's guarantee against peeling, fading and fungus. | 2792 | 204.215 | 6,72,721 | 5,70,103 |
| 36 | Providing & Applying two coats of Synthetic Enamel of approved desired shade (Asian Paints/ Nerolac/ Berger)) to prepared surfaces of plaster/ RCC work/ brickwork/ Wood/ Metal including scraping/scrubbing and cleaning of surfaces of grease/ dirt/ flaky portions/ dust, 1 coat of primer (Cement/ Wood/ zinc Chromate yellow metal) followed by putty touchup and applying 2nd coat of primer, filling cracks/voids/minor damages, etc. complete as per manufacturer's Specifications |  | 0 | - | - |
| 37 | Wall painting (two or more coats) with plastic emulsion paint of approved brand and manufacture on new work to give an even shade (including min two priming coats and two layers of putty alternatively) |  | 0 | - | - |
| 38 | Providing and laying 25-32mm thick machine cut and machine polished Kotah flooring (incl Staircase landing) of approved colour and size not less than 55x55 cms on about 20mm thick CM 1:5 bedding, set, jointed and pointed in neat cement slurry including flushing joints with matching colour cement, curing, wax polishing, cleaning etc. complete as directed. | 250 | 2142.8 | 6,32,126 | 5,35,700 |
| 39 | Providing & laying 25mm thick machine polished Black Granite stone platform for Kitchen/wash basin platform of approved quality, colour & shade including cutting the slab to accomodate specified shape of wash basin, chasing the wall & finishing, rounding the edges, bedding, joints, if any, finished with neat coloured cement slurry, curing laying as per design, along with fixing over 25-40 thk Cuddapah stone/ 15/19mm marine ply frame of 120mm deep with fixing to wall along with fascia as instructed complete as directed | 2 | 3301.1 | 7,050 | 5,975 |
| 40 | Providing & laying vaccum dewatered flooring (with tremix machinery) 100mm thk with cement concrete M25 using basaltic/granitic 20mm downgraded aggregates over a base leveling course (paid separately) with necessary steel reinforcement(to be paidseparately) including formwork(MS channels & angles on sides with proper supporting sections), bending, tieing rods etc., concrete to be surface vibrated, levelled, double beam screed vibrated twice, vaccum dewatered by laying suction matts, top spread and dewatering the concrete with the help of vaccum pump, and finished with mechanical power floating, troweling till smooth surface is obtained, curing by ponding, cutting grooves at construction or other joints of size 4mmx25mm by groove cutting m/c, filling grooves with polysulphide or epoxy sealants, topping etc. complete. | 2136 | 1161.6 | 29,27,310 | 24,80,771 |
| 41 | Providing & laying 1st quality **ceramic glazed wall tiles** conforming to IS:15622 (thickness to be specified by the manufacture of approved make in all colours, shades except burgundy, bottle green, black of any size as approved by Engineer-in-charge in **skirting, risers of steps and dados** over 12 mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand ) and jointing with grey cement slurry @3.3kg per sq.m including pointing in white cement mixed with pigment of matching shade complete.a) Wall Ceramic Glazed Tiles : min 300 x 450 (Quality of tile to be conforming to the price range between Rs. 550-600 per sq. mt) | 331 | 1223.97 | 4,77,495 | 4,04,657 |
| 42 | Providing and laying **antiskid floor tiles** 12 x 12 upto 16 x 16 in of Johnson, Somany, Kajaria (thickness to be specified by the manufacturer) of 1st quality conforming to IS:15622 of approved make in shades as specified laid on 20 mm thick cement mortar 1:4 (1 Cement : 4 Coarse sand) including pointing the joints with white cement and matching pigment etc., complete a) Light Shades (Quality of tile to be conforming to the price range between Rs. 312.5-400 per sq. mt) | 38 | 1570.8 | 70,286 | 59,565 |
| 43 | Providing & fixing 125x65mm sal/Matti frames, 30mm solid core marine ply flush door single shutter with S.S. fittings & fixtures finished with 3 coats of synthetic enamel over coat of primer with teak wood beading complete in all respects. | 36 | 1809.5 | 77,786 | 65,920 |
| 44 | Providing, fabricating & fixing in position pull & push type steel rolling shutters, out of 76mm x18 gauge Galv M.S. sheets in one piece without welded jt. interlocked with each other and ends locked with heavy type GMS clips, MS guide channels of size 76x28x10 mm deep, GMS drum top cover, suspension shaft made out of heavy section pipes with sufficient strength to to carry the load of shutters fitted with ball bearings and with tested high tensile steel wire springs, all mounting and fittings, reinforced lock plate with fixtures & locking arrangements, painted with 2 coats of Epoxy paint of approved make and tint over one coat of red oxide and one coat of zinc-rich Epoxy primer. (Measurement for clear unfinished size of door opening. rate to include all civil work, required to provide necessary pockets for fixing lugs & grouting). a) without Hand gear. | 96 | 3510.1 | 3,98,328 | 3,37,566 |
| 45 | Providing & fixing Anodised Aluminium shutters in accordance with the specifications annexed with Goa schedule of rates (2004) Vol I & II including all taxes, transportation, scaffolding and handling etc Complete as per direction of the engineer : Windows with **two sliding shutters using 18mm series** shutters sections with **plain glass** including **powder coating** with pure polyester of required shade and colour. All work between civil work and aluminium frames shall be sealed and made watertight by applying silicone sealant Rectangular Outer Tube @0.637Kg/m 63x37x1.20, 2 Track Top & Side @0.63Kg/m 61.6x31.75x1.20, 2 Track Bottom @0.718Kg/m 61.6x31.75x1.20, Shutter Handle @0.431Kg/m 39.4x17.7x1.20, Shutter Interlock @0.51Kg/m 39.4x17.7x1.20, Shutter Top & Bottom @0.42Kg/m 39.4x17.7x1.20, 4 mm thk clear float glass, EPDM gaskets complete with accessories for locking, handles, stoppers, ball bearing etc. | 450 | 3175.7 | 16,86,297 | 14,29,065 |
| 46 | Providing and fixing colour coated galvalume/zincalume roofing sheets of 0.5mm thickness including all the accessories but excluding the cost of purlins, rafters, trusses,etc. complete as per the directions of the engineer. | 908 | 1196.42 | 12,81,181 | 10,85,747 |
| 47 | Providing & fixing in position Galvalume/Zincalume flashings, cappings, ridges, gutters upto 600mm girth and min 3.00m in length (cold Rolled Steel 500-550 MPa yeild Stress ASTM A 446 Grade E) with hot-dip metallic coating of aluminium-zinc alloy(AZ 150 galvalume) (150 gms/sqm total of both sides with Al-Zn Composition= 50-55% & 40-43.4% resp. & 1-1.6% Si conforming to ASTM 792/ AS 1397) 0.42 mm base metal thickness and 0.50mm total coated thickness, factory cut at all heights for roof, side & gable cladding complete in all respects with AZ 150 GSM SMP color Coated (20mic exterior coat of Silicon Modified Polyester paint system over 5 mic primer and 5 mic polyester back coat over 5 mic primer) incl. fixing to purlins with no 12x14x55mm mechanically galvanised hex head self drilling screws of the best quality as per AS-3566 class 3-4 approved, which should be compatible to be used with sheets. with integral washers and EPDM seals etc. Silicon sealant non-hardening neutral cure type shall be applied at all end laps, complete as directed. | 436 | 441.1 | 2,26,729 | 1,92,143 |
| 48 | Providing and fixing in position 2mm thick one side embossed clear polycarbonate sheet in same profile to match the roofing sheets including self tapping screws. | 227 | 793.307 | 2,12,373 | 1,79,978 |
| 49 | Providing water proofing treatment over the new RCC roofs, terrace, sunken slabs, chajjas by spreading cement slurry over the RCC slab and laying of 100 mm average laterite stone ballast coba with the necessary gradient for easy flow of rain water and the coba should be covered with damp proof, joint less water proofing plaster of mix 1:3 (1 cement : 3 Fine sand), finish smooth with wooden trowel with false marking of 30cm squares. the Vertical surfaces of the adjoining walls are to be treated upto a height of 30cms including rounding of junctions (The rate includes for complete items including labour and materials and including the cost of initial treatment of roof slab as follows. The injection of damp proof or equivalent compound with cement solution will be given as and when found necessary for filling honey comb cracks etc. in the RCC slabs) Note: The cement consumption 25 kg /sq.m. | 548 | 1667.16 | 10,78,052 | 9,13,604 |
| 50 | Providing and applying as per manufacturers specifications a minimum of two coats of proprietary brand waterproofing coating using Two Component flexible acrylic polymers modified cement based Waterproofing Coating free from SBR's including thorough surface preparation, applying (min 1 coat) compatible primer or Key coats (Acrylic Polymer & Cement 1:1) etc for slabs, side walls, retaining wall etc. including providing leakproof treatment by injection grouting (shrinkage Compensating) to concrete members by using waterproof polymer based on acrylates free from SBR's or modified SBR's at 1.0 metre centres in both direction (Using Cement & Expansive plasticising admixture & grouting aid), also at all constuction/ Cold joints and including providing 1:3 waterproof cement mortar 20mm thick plaster at all levels including scaffolding etc.complete all as approved by Engineer. the Vertical surfaces of the adjoining walls are to be treated upto a height of 30cms including rounding of junctions | 548 | 619.41 | 4,00,594 | 3,39,486 |
| 51 | Providing, injecting and spraying chemical emulsions for pre-construction anti termite treatment and creating a chemical barrier as per IS:6313 (part II) 1981, in column foundations, raft foundation, wall foundation, under and around basement, sides of walls, backfill earth in stages as filling proceeds, top surfaces of plinth filling, junction of walls and floors along external perimeter of the building etc. all complete as per specifications and as directed including providing guarantee for a period of 15 years ( Plinth area shall only considered for mode of measurement) (Contractor to specify the agency for this work) | 1056 | 118.404 | 1,47,513 | 1,25,011 |
| 52 | Providing, fabricating & fixing in position hand rails consisting of MS pipes, MS flats, plates, square bars, etc or combination of above including welding, fixing to concrete with wedge bolts wherever required, providing and applying to all MS fixtures 2 coats of epoxy primer paint of approved quality after making surface preparation to suit epoxy enamel paint of approved quality and colour etc complete i) 40mm dia (NB) light MS pipe | 48 | 4736.16 | 2,70,492 | 2,29,230 |
| 53 | Supplying, Fabricating and erecting MS Gates as per design with necessary locking arrangements, Guides, heavy duty hinges for gates etc. and finishing with one coat of anti corrosive primer with two coats of Epoxy paint all as directed approx. 40 kg/m2 using hollow tubes, GI pipes, angles, flats, welded mesh, chainlink mesh, MS plates and other sections etc. complete. | 61 | 4736.16 | 3,38,114 | 2,86,538 |
| 54 | Providing and laying in position box type fan hooks | QOR | 0 | - | - |
| 55 | Making plinth protection 50mm thick of cement concrete 1:3:6 (1cement:3coarse sand:6graded stone aggregate 20mm nominal size) over 75mm bed of dry brick ballast 40mm nominal size well rammed and consolidated and grouted with fine sand including finishing the top smooth. | QOR | 0 | - | - |
| 56 | Providing & fixing Turbo Ventilators as instructed by Engineer in Charge with neccesary fixtures & fastening etc complete. | 24 | 1320 | 37,694 | 31,944 |
| 57 | Proving and fixing **white vitreous china water closet squatting pan** (Indian type w.c. pan) size 580 mm with 100 mm sand cast iron P. or S trap with flush valve nelson/ similar fully chromium plated with stop cock, wall flanges, flush pipe or elbow and vaccum breaker coupling etc. including cutting and making good the walls and floors where required. - orissa pattern wc pan | 1 | 12530 | 14,785 | 12,530 |
| 58 | Proving and fixing white vitreous **china Wall Hung type** (European Type) water closet with seat and lid with C.I. brass hinges and rubber fittings with flush valve nelson/ similar fully chromium plated with stop cock, wall flanges, flush pipe or elbow and vaccum breaker coupling etc. including cutting & making good the walls and floors where required and concealed seat support - W.C. Pan with white plastic seat and lid | 15 | 16499.1 | 2,92,033 | 2,47,486 |
| 59 | Providing and fixing **vitreous china under counter wash basin** with RS or C.I. brackets painted white, NICKEL chrome plated copper alloy Fancy Pillar Cock rocket type Jaquar make or equivalent. Confirming to IS 8931;1993, C.P. brass chain with rubber plug, 32 mm C.P. brass waste of pattern, 32 mm diameter M.I. Or C.P. brass trap and union complete, including cutting and making good the walls where required. - wash basin 550x400/Oval 560x410mm/ round 550x450mm including cutting in base etc complete with sealing | 11 | 5831.1 | 74,931 | 63,501 |
| 60 | Providing & fixing **soap tray**-tile series HS:40054 with Al.rod, in light colour. | 12 | 1963.5 | 28,035 | 23,758 |
| 61 | Providing and fixing white vitreous china flat back Large lipped front **urinal basin** of 590x375x390mm size with PVC automatic flushing cistern with fittings, R.S. or C.I. brackets, standard size C.P. Brassl flush pipe and spreaders with C. P. brass unions & C. P. Brass clamps with waste fitting as per IS 2556, PVC trap with outlet grating and other couplings in CP Brass complete, including painting, fittings, cutting and making good the walls and floors where required. - Range of one urinal basin with pressmatic valve. | 6 | 24264.1 | 1,73,221 | 1,46,798 |
| 62 | Providing and fixing in position beveled edge plate **glass mirror** size 600 x 450 mm mounted on PVC frame with C.P. brass screws, washers, etc complete. | 16 | 1768.75 | 33,394 | 28,300 |
| 63 | Providing & fixing in position C.P. **towel rail** with C.P.brass brackets, 600mm long-20mm dia. | 16 | 779.845 | 14,723 | 12,478 |
| 64 | Supplying, Laying and jointing of **Rigid PVC (SELFIT)** pipes incl cleaning the pipe with solvent cement including the cost of solvent cement and hyrdraulic testing of joints etc. complete as per IS 7634-1975 part 3 for public water supply at store or site of work including railway freight, carting, loading and unloading stacking, transit insurance, Rolling & lowering in trenches, laying to true line and level and perfect linking for joints etc. complete with accessories like elbow, endcap (Plain or threade), Tee, Tail piece, Coupler, Female/Male Threaded Adapter, Service Saddle, Reducer, Long bend 90 degrees etc.. Pipes conforming to IS 4985-2000 and bearing ISI mark, **CLASS 6 KG/ SQ. CM**  with Excise Duty a) Outer dia **63 mm** | 150 | 1841.4 | 3,25,928 | 2,76,210 |
| 65 | Supplying, Laying and jointing of **Rigid PVC (SELFIT)** pipes incl cleaning the pipe with solvent cement including the cost of solvent cement and hyrdraulic testing of joints etc. complete as per IS 7634-1975 part 3 for public water supply at store or site of work including railway freight, carting, loading and unloading stacking, transit insurance, Rolling & lowering in trenches, laying to true line and level and perfect linking for joints etc. complete with accessories like elbow, endcap (Plain or threade), Tee, Tail piece, Coupler, Female/Male Threaded Adapter, Service Saddle, Reducer, Long bend 90 degrees etc.. Pipes conforming to IS 4985-2000 and bearing ISI mark, **CLASS 6 KG/ SQ. CM** with Excise Duty b) Outer dia **75 mm** | 175 | 2382.99 | 4,92,086 | 4,17,022 |
| 66 | Supplying, Laying and jointing of **Rigid PVC (SELFIT)** pipes incl cleaning the pipe with solvent cement including the cost of solvent cement and hyrdraulic testing of joints etc. complete as per IS 7634-1975 part 3 for public water supply at store or site of work including railway freight, carting, loading and unloading stacking, transit insurance, Rolling & lowering in trenches, laying to true line and level and perfect linking for joints etc. complete with accessories like elbow, endcap (Plain or threade), Tee, Tail piece, Coupler, Female/Male Threaded Adapter, Service Saddle, Reducer, Long bend 90 degrees etc.. Pipes conforming to IS 4985-2000 and bearing ISI mark, **CLASS 6 KG/ SQ. CM** with Excise Duty c) Outer dia **110 mm** | 175 | 497.2 | 1,02,672 | 87,010 |
| 67 | Supplying, Laying and jointing of **Rigid PVC (SELFIT)** pipes incl cleaning the pipe with solvent cement including the cost of solvent cement and hyrdraulic testing of joints etc. complete as per IS 7634-1975 part 3 for public water supply at store or site of work including railway freight, carting, loading and unloading stacking, transit insurance, Rolling & lowering in trenches, laying to true line and level and perfect linking for joints etc. complete with accessories like elbow, endcap (Plain or threade), Tee, Tail piece, Coupler, Female/Male Threaded Adapter, Service Saddle, Reducer, Long bend 90 degrees etc.. Pipes conforming to IS 4985-2000 and bearing ISI mark, CLASS **6 KG/ SQ. CM**  with Excise Duty d) Outer dia **140 mm** | 121 | 480.48 | 68,603 | 58,138 |
| 68 | Supplying, Laying and jointing of **Rigid PVC (SELFIT)** pipes incl cleaning the pipe with solvent cement including the cost of solvent cement and hydraulic testing of joints etc, complete as per IS 7634-1975 part 3 for public water supply at store or site of work including railway freight, carting, loading and unloading stacking, transit insurance etc. complete with accessories. Pipes conforming to IS 4985-1968 **CLASS 10 KG/ SQ. CM** - a) Outer dia **63 mm** | 182 | 405.9 | 86,932 | 73,671 |
| 69 | Providing and fixing **chlorinated ployvinyl chloride (CPVC)** pipes confirming to IS:15778, having thermal stability for hot and cold water supply including all CPVC plain and brass threaded fittings including fixing the pipes with clamps at 1 mt. spacing. This includes jointing of pipes and fittings with one step CPVC solvent cement and testing of joints complete as per direction of the Engineer. **Concealed work** (medium duty SDR 13.5 pipe) including cutting chases and making good the walls etc. a) **15 mm** dia nominal outer dia pipes. | 121 | 315.48 | 45,044 | 38,173 |
| 70 | Providing and fixing **chlorinated ployvinyl chloride (CPVC)** pipes confirming to IS:15778, having thermal stability for hot and cold water supply including all CPVC plain and brass threaded fittings including fixing the pipes with clamps at 1 mt. spacing. This includes jointing of pipes and fittings with one step CPVC solvent cement and testing of joints complete as per direction of the Engineer. **Concealed work** (medium duty SDR 13.5 pipe) including cutting chases and making good the walls etc. a) **20 mm** dia nominal outer dia pipes. | 121 | 591.36 | 84,434 | 71,555 |
| 71 | Providing and fixing **chlorinated ployvinyl chloride (CPVC)** pipes confirming to IS:15778, having thermal stability for hot and cold water supply including all CPVC plain and brass threaded fittings including fixing the pipes with clamps at 1 mt. spacing. This includes jointing of pipes and fittings with one step CPVC solvent cement and testing of joints complete as per direction of the Engineer. **Concealed work** (medium duty SDR 13.5 pipe) including cutting chases and making good the walls etc. b) **25 mm** dia nominal outer dia pipes. | 121 | 689.975 | 98,515 | 83,487 |
| 72 | Providing and fixing chlorinated **ployvinyl chloride (CPVC)** pipes confirming to IS:15778, having thermal stability for hot and cold water supply including all CPVC plain and brass threaded fittings, CPVC solvent cement, trenching, refilling and testing of joints complete as per direction of the Engineer. **External work** (heavy duty SDR 11 pipe) a) **20 mm** dia nominal outer dia pipes. | 182 | 301.73 | 64,622 | 54,764 |
| 73 | Providing and fixing **chlorinated ployvinyl chloride (CPVC)** pipes confirming to IS:15778, having thermal stability for hot and cold water supply including all CPVC plain and brass threaded fittings, CPVC solvent cement, trenching, refilling and testing of joints complete as per direction of the Engineer. **External work** (heavy duty SDR 11 pipe) b) **25 mm** dia nominal outer dia pipes. | 182 | 390.94 | 83,728 | 70,956 |
| 74 | Providing and fixing **chlorinated ployvinyl chloride (CPVC)** pipes confirming to IS:15778, having thermal stability for hot and cold water supply including all CPVC plain and brass threaded fittings, CPVC solvent cement, trenching, refilling and testing of joints complete as per direction of the Engineer. **External work** (heavy duty SDR 11 pipe) c) **40 mm** dia nominal outer dia pipes. | 182 | 619.355 | 1,32,647 | 1,12,413 |
| 75 | Providing & fixing in position **100mm dia rigid PVC floor trap** (75mm dia outlet) of self cleansing design with PVC grating on top & bedding concrete 1:2:4 to make the joint around perfectly airtight for the trap etc all complete. | 15 | 891 | 15,981 | 13,543 |
| 76 | Providing & fixing best quality salt **glazed stone ware gully traps** incl. embedding the trap in 1:4:8 cement concrete, 150x150 mm C.I. grating at top with 100mm dia outlet with150x150mm approved CI grating, construction of brick masonry chamber 300 x 300 mm internal size consisting of necessary earthwork excavation, 150mm thick fdn. bed of 1:4:8 cement concrete, 230mm brick masonry in C.M. 1:5, plastering with cement mortar 1:3 both on internal & external surfaces finished smooth with a floating coat of neat cement providing & fixing medium duty C.I. frame and hinged cover of size 300 x 300 mm weighing not less than 7.25 kg, painting the grating, frame & cover with 2 coats of approved bitumastic paint & refilling the sides of excavation & disposing off the surplus material etc. complete. | 15 | 2953.72 | 52,978 | 44,897 |
| 77 | Providing & constructing brick masonry manholes/ inspection chambers upto 0.5m depth (from top to floor haunch) consisting of necessary earthwork excavation, 100mm thick foundation bed of cement concrete 1:3:6, 230mm thk brick masonry in cement mortar 1:5, plastering inside & outside faces with 12mm thk cement plaster 1:3, making haunches and channels on floor with cement concrete 1:2:4, finishing coat of neat cement for inside plastered faces haunches and channels, providing & fixing C.I. steps as specified, providing & fixing medium duty top frame & cover of size 450 x 900mm weighing not less than 50kg fixed with cement concrete 1:2:4, painting frame, cover and steps with 3 coats of approved bitumastic paint, refilling the sides with excavated earth and disposing off the surplus etc. complete. (Excavation will be paid separately) a) 600x600 | 16 | 10598.5 | 1,93,847 | 1,64,277 |
| 78 | Providing & constructing brick masonry manholes/ inspection chambers upto 0.5m depth (from top to floor haunch) consisting of necessary earthwork excavation, 100mm thick foundation bed of cement concrete 1:3:6, 230mm thk brick masonry in cement mortar 1:5, plastering inside & outside faces with 12mm thk cement plaster 1:3, making haunches and channels on floor with cement concrete 1:2:4, finishing coat of neat cement for inside plastered faces haunches and channels, providing & fixing C.I. steps as specified, providing & fixing medium duty top frame & cover of size 450 x 900mm weighing not less than 50kg fixed with cement concrete 1:2:4, painting frame, cover and steps with 3 coats of approved bitumastic paint, refilling the sides with excavated earth and disposing off the surplus etc. complete. (Excavation will be paid separately) b)900x900 | 15 | 12818.3 | 2,29,909 | 1,94,838 |
| 79 | Making soak pit 2.5m dia, 3.0m deep with 45 x 45 cm dry brick honey comb shaft and sw drain pipe 100m dia, 1.8 m long complete. Filled with laterite stone aggregate 125 to 180 mm surrounded by laterite stone aggregate of 200 mm and down guage as per standard design | 2 | 29547.1 | 84,375 | 71,504 |
| 80 | Providing and fixing NICKEL chrome plated copper alloy Fancy BIB Cock Short Body Jaquar make or equivalent. Confirming to IS 8931;1993 a) 15mm nominal bore | 16 | 1746.8 | 32,980 | 27,949 |
| 81 | Providing and fixing NICKEL chrome plated copper alloy Fancy CONCEALED STOP COCK WITH SLINDING FLANCE 15MM Jaquar make or equivalent. Confirming to IS 8931;1993 a) 15mm nominal bore | 16 | 1265 | 23,883 | 20,240 |
| 82 | Providing & fixing **Stainless Sink (IS 13983)**1.0mm thk, Overall size 535mmx460mm(21"x18"), Bowl size 460x380x200mm (18'x15"x8") Glossy manufactured from AISI 304 (18% Chromium / 8% nickel) Stainless steel with coupling & all accessories complete with choke stop strainer, Plain type having flat borders for correct sandwithing between the plaform top and bottom slabs complete | 3 | 7874.9 | 23,231 | 19,687 |
| 83 | Providing & fixing in position **PVC overhead storage tank** with mosquito proof cover for water including polythene ball float valve(upto 50mm), 40mm dia GI 'B' class overflo pipe with mosquito proof coupling approx 500 long, 40mm dia GI 'B' class flushout pipe with puddle flange and medium pattern Gun metal wheel valeve,etc complete Sintex or equivalent approved mark. a) **2000 ltrs** | 2 | 14300 | 40,498 | 34,320 |
| 84 | Providing & fixing in position **100mm** dia nominal size CP brass **shower rose** with 12/15mm inlet testing complete etc. | 10 | 1309 | 15,446 | 13,090 |
| **TOTAL (RS)** | | | | **6,46,07,860** | **5,47,52,424** |

**REMARKS:**

1. Estimated cost by the company as per their BOQ is ~7.08 crore and estimated construction cost as per RKA findings for civil and structure including GST is 6.46 crore
2. Above Rates are for residential building construction and accordingly the rates have been taken.
3. As per our assessment cost may vary from Rs.6.4 crores to Rs.6.8 crores including GST for the above work, excluding electrical and Bringing of cost.
4. Cost difference may be there when labour is deployed through local contractor on daily basis Vs engaging EPC contractor and also difference in using concrete mixer at site Vs using of RMC.
5. Also 10% increased rates are taken for works in tribal area/hilly and inaccessible areas, as our focused property lies in hilly terrain. For same we have attached screenshot in PART E.

|  |  |
| --- | --- |
| **PART C** | **PHOTOGRAPHS** |


|  |
| --- |
| X:\In Progress Files\Anuj Sharma\VIS(2024-25)-PL576-514-730-JM Holdings\SiteImage\c_TimePhoto_20241209_095855.jpg |
| X:\In Progress Files\Anuj Sharma\VIS(2024-25)-PL576-514-730-JM Holdings\SiteImage\c_TimePhoto_20241209_095628.jpg |

|  |
| --- |
| X:\In Progress Files\Anuj Sharma\VIS(2024-25)-PL576-514-730-JM Holdings\SiteImage\c_TimePhoto_20241209_102100.jpg |
| X:\In Progress Files\Anuj Sharma\VIS(2024-25)-PL576-514-730-JM Holdings\SiteImage\c_TimePhoto_20241209_102212.jpg |




|  |  |
| --- | --- |
| **PART D** | **IMPORTANT DOCUMENT EXHIBIT** |

|  |  |
| --- | --- |
|  |  |



|  |  |
| --- | --- |
| **PART E** | **REFERENCE** |



|  |  |
| --- | --- |
| **PART F** | **DISCLAIMER** |

1. *We have received sample BOQ for building construction and civil work.*
2. *The client/ owner and its management/ representatives warranted to us that the information they have supplied was complete, accurate and true and correct to the best of their knowledge. All such information provided to us either verbally, in writing or through documents has been relied upon in good faith and we have assumed that it is true & correct without any fabrication or misrepresentation. I/We shall not be held liable for any loss, damages, cost or expenses arising from fraudulent acts, misrepresentations, or willful default on part of the owner, company, its directors, employee, representative or agents.*
3. *Legal aspects for eg. Investigation of title, ownership rights, lien, charge, mortgage, lease, sanctioned maps, and verification of documents provided to us such as title documents, Map, etc. from any concerned Govt. office etc. have to be taken care by legal expert/ Advocate and same is not done at our end. I/ We assume no responsibility for the legal matters including, but not limited to, legal or title concerns.*
4. *Wherever any details are mentioned in the report in relation to any legal aspect of the property such as name of the owner, leases, etc. is only for illustration purpose and should not be construed as a professional opinion. Legal aspects are out of scope of this report. Details mentioned related to legal aspect are only based on the copy of the documents provided to us and whatever we can interpret as a non-legally trained person. This should be cross validated with a legal expert. We do not vouch any responsibility regarding the same.*
5. *We have relied on the data from third party, external sources & information available on public domain to conclude the valuation. These sources are believed to be reliable and therefore, we assume no liability for the truth or accuracy of any data, opinions or estimates furnished by others that have been used in this analysis. Where we have relied on the data, opinions or estimates from external sources, reasonable care has been taken to ensure that such data is extracted from authentic sources, however we still can’t vouch its authenticity, correctness, or accuracy.*
6. *Documents, information, data including provided to us during the course of this assessment by the client is reviewed only upto the extent required in relation to the scope of the work. No document has been reviewed beyond the scope of the work. These are not reviewed in terms of legal rights for which we do not have expertise. Wherever any information mentioned in this report is mentioned from the documents like owner’s name, etc., it is only for illustration purpose and may not necessarily represent accuracy.*
7. *This cost vetting is done only on the basis of market research and BOQ provided to us by the company and we don’t recommend any sort of recommendation in our Document.*
8. *The estimated cost verification of item to item can’t exactly match as per our vetting due to several market consideration. In some of the items it is lower while in some of the item’s price comes to be higher but on an average the price as per list provided to us falls in the range as confirmed by us.*
9. *There can be variation in the estimated price if the specification & make of any items procured is different from the list provided to us during assessment.*
10. *The estimated cost verification is made based on the third-party information which has been replied upon in good faith.*
11. *Ownership and other legal point of view in respect of the asset is not considered in this report as same is out of scope of this document.*
12. *This document is made at the request of the Bank.*

**For R.K Associates Valuers** **& Techno** **FOR INTERNAL USE Engineering Consultants (P) Ltd. *PREPARED BY: Anuj Sharma***  ***REVIEWED BY: Anil Kumar***